## CPES Report 24th Release
NAME OF CONSTRUCTOR | LICENSE NO. | L/F | CATEGORY |  |  | PROJECT | PROJECT LOCATION | DATE OF EVALUATION | NO. of VISIT | *IMPL. AGENCY | FUNDING SOURCE | CONTRACT |  | DATE |  | SLIPPAGE (%) | STATUS | WMS | MTL | TIME | FAC | ESH | RDR | CPES VISIT RATING | FINAL RATING/ QUALITATIVE DESCRIPTION
|  |  | PCAB | ARC | TYPE | [6 empty] | AMOUNT (Php, M) | DUR (C.D.) | STARTED | COMP
"R.R. Seismundo Construction & Supply" | 10961 | L | A | MA | GE1 | Const./Widening/Upgrading/Rehab. of Del Pilar (San Juan)-New Cortez-San Jose Carcor Panas Rd. | Davao Del Norte | 2013-08-12 | 2nd | XI | LF | 45.784 | 205 | 2013-01-23 | 2013-08-15 | 6.35 | O | 0.245 | 0.3 | 0.15 | 0.03 | 0.05 | 0.033 | 80.8 | -
"R.R. Seismundo Construction & Supply" | 10961 | L | A | MA | GE1 | Const./Widening/Upgrading/Rehab. of Del Pilar (San Juan)-New Cortez-San Jose Carcor Panas Rd. | New Corella, Davao del Norte | 2013-03-18 | 1st | XI | LF | 45.784 | 179 | 2013-01-23 | 2013-07-20 | 0 | O | 0.338 | 0.231 | 0.15 | 0.03 | 0.045 | 0.05 | 84.4 | -
"R.R. Seismundo Construction & Supply" | 10961 | L | A | MA | GE1 | Widening of Surigao-Davao Coastal Rd., Km.1822+(-423)-Km.1822+821, Apokon Sect. | Tagum City, Davao del Norte | 2013-03-18 | 1st | XI | LF | 17.793 | 125 | 2013-01-25 | 2013-05-29 | 0 | O | 0.355 | 0.24 | 0.15 | 0.03 | 0.045 | 0.05 | 87 | -
"R.R. Seismundo Construction & Supply" / Davao Concrete Products Joint Venture | JV-12-116 | L | A | MA | GE2 | Const. of Flood Control Structure (Sheet Piles & Grouted Riprap) Agusan River, Brgy. Inambatan | Monkayo, COMVAL Province | 2012-11-27 | 1st | XI | LF | 27.838 | 240 | 2012-08-28 | 2013-04-24 | 0.86 | O | 0.333 | 0.24 | 0.15 | 0.03 | 0.04 | 0.05 | 84.3 | -
121 Construction Corporation (Formerly: 121 Construction) | 21686 | L | D | SB | GE | Improvement/Concreting with Drainage System along Ballesteros Street | Brgy. Zaniga, Mandaluyong City | 2014-11-29 | 1st | NCR | LF | 6.6843 | 120 | 2014-08-14 | 2014-12-11 | 1% | O | 0.355 | 0.24 | 0.15 | 0.03 | 0.035 | 0.033 | 84.3% | 84.30% Satisfactory
12-30 CONSTRUCTION & SUPPLY | 37025 | L | A | SB | GB | Construction of 1-CL Trinidad Cario PS | Roxas, Palawan | 2015-11-13 | Final | Palawan 1st DEO | LF | 1.0696 | 90 | 2015-01-04 | 2015-04-03 | 0 | C | 0.444 | 0.133 | 0.3 | - | - | - | 87.7% | 87.7% Satisfactory
2M Construction & Enterprises | 33331 | L | C | SB | GE2 | Slope Protection (Grouted Riprap) along Isabela-Maluso Rd., Matarling Sect. at K15+190-K15+249 | Basilan Province | 2013-03-13 | 1st | IX | LF | 4.842 | 75 | 2013-02-15 | 2013-04-30 | 3.25 | O | 0.328 | 0.24 | 0.15 | 0.03 | 0.04 | 0.05 | 83.8 | -
2-R CONSTRUCTION & SUPPLY | 15304 | L | C | SB | GE | Off Carriage Improvement at Lingayen, Captiol Loop | KO 364+(-229) - KO 364+836, Ligayen, Pangasinan | 2015-06-11 | 1st | Pangasinan 2nd DEO | LF | 9.34 | 105 | 2015-03-06 | 2015-06-18 | 0.26% | C | 0.28 | 0.3 | 0.15 | 0.03 | 0.06 | 0.03 | 85.2% | -
2-R CONSTRUCTION & SUPPLY | 15304 | L | C | SB | GE | Raising of Grade of Dike Agno River Basin Flood Control Project (Phase III), Brgy. Cabalitian, Asingan, Pangasinan | Asingan, Pangasinan | 2015-11-16 | 1st | PANGASINAN 3RD DEO | LF | 9.1675 | 120 | 2015-08-26 | 2015-12-23 | 0.05 | OG | 0.391 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 91.1% | 91.1% Very Satisfactory
2-RCONSTRUCTION & SUPPLY | 15304 | L | C | SB | GE | Off Carriageway Improvement at Lingayen Capitol Loop, K0364+(-219) to K0364+836, Lingayen, Pangasinan | K0364+(-219) to K0364+836, Lingayen, Pangasinan | 2016-09-02 | Final | Pangasinan 2nd DEO | LF | 9.34 | 105 | 2015-03-06 | 2015-06-19 | - | C | 0.473 | 0.133 | 0.3 | - | - | - | 90.6% | *87.36% Satisfactory
3A'S BUILDERS | 33251 | L | D | SB | GE | Rehabilitation/Major Repair of Permanent Bridges Tagbinunga Bridge (B00549LT) along Daang Maharlika (LT), Mahaplag, Leyte | Mahaplag, Leyte | 2015-11-15 | Final | Leyte Fifth DEO | LF | 5.4028 | 150 | 2015-03-02 | 2015-07-29 | - | C | 0.484 | 0.133 | 0.3 | - | - | - | 91.7% | 91.7% Very Satisfactory
3C'SL CONSTRUCTION AND SUPPLY | 36393 | L | D | SB | GE | Construction/ Upgrading of Local Road | Barangay Comagascas, Cabadbaran City, Agusan del Norte | 2015-06-02 | Final | AGUSAN DEL NORTE DEO | LF | 3.763 | 48 | 2015-03-27 | 2015-05-13 | 0% | C | 0.461 | 0.133 | 0.3 | - | - | - | 89.4% | *89.4% Very Satisfactory
3K ROCK ENGINEERING | 27908 | L | B | MA | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Road including Drainage based on Pavement Management System/Highway Development & Management-4 (HDM-4) (Intermittent Section), Asin Road, K0305+(-291) - K0305+958 | Baguio City | 2015-06-12 | Final | Baguio City DEO | LF | 22.149 | 170 | 2015-02-06 | 2015-07-25 | (+) 23.20% | C | 0.414 | 0.196 | 0.3 | - | - | - | 90.97% | *90.97% Very Satisfactory
3K ROCK ENGINEERING | 27908 | L | A | MB | GE | Road Upgrading (Unpaved to Paved) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standards (HDM-4 Project Analysis) (Intermittent Sections) of Kabugao - Pudtol - Luna - Cagayan Bdry. Road, K0611+917 to K0612+961, K0612+973 to K0613+699, K0613+723 to K0614+500, Apayao | Apayao | 2015-08-27 | 1st | CAR | LF | 75.709 | 221 | 2015-05-26 | 2016-01-01 | -16.41% | O | 0.363 | 0.241 | 0 | 0.03 | 0.061 | 0.033 | 72.8% | -
3K Rock Engineering/RVC Construction (J.V.) | 27908 | L | B | MA | GE | Road Upgrading (Gravel to Concrete) of Asin -Nanganban - San Pascual Road K0270+594 - K0272+220 ; K0275+5311 - K0275+7178 |  | 2014-08-16 | 1st | CAR | LF | 91.3578 | 237 | 2014-03-28 | 2014-11-19 | 7.2 | O | 0.379 | 0.24 | 0.15 | 0.024 | 0.06 | 0.05 | 90.3 | -
3RB Construction & Supply | 19541 | L | B | MA | GE-5 | Prieto Diaz Port Development Project | Prieto Diaz, Sorsogon | 2015-08-19 | 1st | DOTC | LF | 8.512 | 124 | 2015-05-01 | 2015-09-01 | 1.12 | O | 0.367 | 0.3 | 0.15 | 0.03 | 0.054 | 0.05 | 95.1 | -
4B Construction Corporation |  | L |  |  |  | 2014 heavy maintenance works along SCTEX lot 2 - Bridge revetment, slope and drainage repair works | Bataan and Pampanga/Region 3 | 2014-10-31 | 1st | BCDA | L | 12.43 | 90 | 2014-08-03 | 2014-11-01 | 0 | O | 0.2978 | 0.2875 | 0.135 | 0 | 0.035 | 0.05 | 80.53 | -
4B Construction Corporation | [5 empty] | Gumain Bridges Pier 5 & 6 Protection Works | Floridablanca, Pampanga | 2015-02-05 | 2nd | BCDA | L | 18.951 | 120 | 2014-09-03 | 2014-12-31 | 21.45 | O | 0.377 | 0.2934 | 0 | 0.03 | 0.041 | 0.033 | 77.44 | -
4B Construction Corporation | [5 empty] | Gumain Bridges Pier 5 & 6 Protection Works | Floridablanca, Pampanga | 2014-11-20 | 1st | BCDA | L | 18.951 | 120 | 2014-09-03 | 2014-12-31 | 0 | O | 0.4 | 0.271 | 0.105 | 0 | 0.032 | 0.033 | 84.1 | -
4B CONSTRUCTION CORPORATION | 23445 | L | AAA | LA | GE | Widening along Roman Expressway, K153+263 to K153+938, K153+938 to K154+780, Mariveles, Bataan | Mariveles, Bataan | 2015-06-04 | Final | Bataan 2nd DEO | LF | 22.523 | 99 | 2014-10-10 | 2015-01-16 | 0% | C | 0.4 | 0.2 | 0.3 | - | - | - | 90% | *90% Very Satisfactory
5'S CONSTRUCTION & SUPPLY | 32404 | L | D | SB | GB | Construction of One (1) Storey, Two (2) Classroom School Building at Dumangas National High School | Poblacion, Dumangas, Iloilo | 2015-06-10 | Final | Iloilo Second DEO | LF | 1.479 | 60 | 2015-03-05 | 2015-05-03 | 3.5% | C | 0.478 | 0.172 | 0.3 | - | - | - | 95% | *95% Very Satisfactory
626 Construction and Trading | 34990 | L | D | SB | GE | Improvement of Balungao Hot and Cold Spring Resort | Balungao, Pangasinan | 2015-05-27 | 1st | TIEZA | LF | 11.8 | 180 | 2015-01-21 | 2015-07-19 | -17.71 | O | 0.397 | 0.299 | 0 | 0.03 | 0.045 | 0.0167 | 78.74
626 CONSTRUCTION AND TRADING | 34990 | L | D | SB | GE | Improvement of Hot and Cold Spring Resort | Balungao, Pangasinan | 2015-10-09 | 2nd | TIEZA | LF | 12 | 240 | 2015-01-21 | 2015-09-19 | -4.71 | O | 0.3952 | 0.3 | 0.103 | 0.03 | 0.0467 | 0.05 | 92.49 | -
626 CONSTRUCTION AND TRADING | 34990 | L | D | SB | GE | Improvement of Hot and Cold Spring Resort | Balungao, Pangasinan | 2015-11-25 | Final | TIEZA | LF | 12 | 240 | 2015-01-21 | 2015-09-19 | -3.21 | C | 0.473 | 0.2 | 0.3 |  |  |  | 97.3 | 89.1% Very Satisfactory
722 CONSTRUCTION INC (Formerly 722 Construction) | 21923 | L | A | MA | GE | Repair/Rehabilitation/Improvement along Baliuag-Candaba Road, K0054+000 to K0057+000, Baliuag-Candaba Road, Baliuag, Bulacan | K0054+000 to K0057+000, Baliuag-Candaba Road, Baliuag, Bulacan | 2015-08-26 | 1st & Final | Bulacan First DEO | LF | 12.104 | 72 | 2014-09-27 | 2014-12-07 | - | C | 0.394 | 0.2 | 0.3 | - | - | - | 89.4% | *82.86% Satisfactory
722 CONSTRUCTION, INC. (Formerly: 722 Construction) | 21923 | L | A | MA | GE | Construction/Rehabilitation of Road with Drainage, Barangay Poblacion II, Phase III Constantino, Municipality of Marilao, Bulacan 4th LD | Barangay Poblacion II, Phase III Constantino, Municipality of Marilao, Bulacan 4th LD | 2015-11-19 | Final | Bulacan Second DEO | LF | 6.509 | 90 | 2015-02-16 | 2015-05-16 | - | C | 0.493 | 0.133 | 0.3 | - | - | - | 92.6% | 92.6% Very Satisfactory
722 Construction, Inc.(Formerly: 722 Construction) | 21923 | L | A | MA | GE | Repair/Rehabilitation/Improvement along Baliuag-Candaba Road K0054+000 to K0057+000 | Baliuag, Bulacan | 2014-11-24 | 1st | III | LF | 12.1042 | 72 | 2014-09-27 | 2014-12-07 | 0.69% | O | 0.295 | 0.24 | 0.15 | 0.03 | 0.037 | 0.033 | 78.5% | 78.50% Unsatisfactory
739 BUILDERS | 31174 | L | B | MA | GE | Widening of Vigan - Sta. Catalina Road | KO 408+910 - KO409+630, Sta. Catalina, Ilocos Sur | 2015-06-05 | Final | Ilocos Sur 1st DEO | LF | 15.404 | 96 | 2015-02-02 | 2015-05-08 | 11.46% | C | 0.22 | 0.2 | 0.3 | - | - | - | 72% | *72% Poor
808 CONSTRUCTION AND SUPPLY | 18711 | L | D | SB | GE | Construction of Local Roads, Ortiz-Baraoas-Roas | Naguilian, La Union | 2015-06-07 | Final | La Union 2nd DEO | LF | 1.887 | 37 | 2015-02-10 | 2015-03-18 | 24.32% | C | 0.396 | 0.133 | 0.3 | - | - | - | 82.9% | *82.9% Satisfactory
888 ACY ENTERPRISES | 32898 | L | A | MA | GE | Rehab/Major Repair of Permanent Bridges, Pandan Bridge, Along Brdy, S. leyte-Maasin-Macrohon-Sogod-Daang Maharlika | Along Brdy, S. leyte-Maasin-Macrohon-Sogod-Daang Maharlika | 2015-06-03 | 1st | Southern Leyte DEO | LF | 8.812 | 150 | 2015-03-04 | 2015-07-31 | - | O | 0.4 | 0.24 | 0.15 | 0.03 | 0.052 | 0.033 | 90.5% | -
888 ACY ENTERPRISES | 32898 | L | A | MA | GE | Rehabilitation/Major Repair of Permanent Bridge, Pandan Bridge along Bdry. Southern Leyte-Macrohon-Sogod-Daang Maharlika (BOO344LT), Sogod, Southern Leyte | Sogod, Southern Leyte | 2015-08-30 | Final | Southern Leyte DEO | LF | 8.812 | 150 | 2015-03-04 | 2015-07-31 | - | C | 0.411 | 0.2 | 0.3 | - | - | - | 91.1% | *90.74% Very Satisfactory
888 ACY ENTERPRISES | 32898 | L | B | MA | GE | Rehabilitation/Major Repair of Permanent Bridges, Pangi Bridge Along Daang Maharlika (B00597LT), Libagon, Southern Leyte | Libagon, Southern Leyte | 2015-11-16 | Final | Southern Leyte DEO | LF | 14.826 | 180 | 2015-03-04 | 2015-08-30 | - | C | 0.442 | 0.2 | 0.18 | - | - | - | 82.2% | 82.2% Satisfactory
8R'S CONSTRUCTION | 22997 | L | B | MA | GE | Concreting of Daig - Tumapon - Maybo Farm to Market Road, Boac, Marinduque | Boac, Marinduque | 2015-09-01 | 1st & Final | Marinduque DEO | LF | 23.211 | 195 |  | 2016-06-08 | - | C | 0.442 | 0.137 | 0.3 | - | - | - | 87.9% | *87.9% Satisfactory
8R'S CONSTRUCTION | 22997 | L | B | MA | GE | Concreting of Farm to Market Road, Brgy. Maligaya and Brgy. Buliasnin (Brgy. Buliasnin-Maligaya) | Boac, Marinduque | 2015-11-16 | Final | Marinduque DEO | LF | 1.9472 | 41 | 2015-06-29 | 2015-08-08 | 0 | C | 0.405 | 0.147 | 0.3 | - | - | - | 85.2% | 85.2% Satisfactory
A B Aponesto Construction, Parts & Supply | 22998 | L | A | MA | GE | Repair/Rehab of Agusan River Flood Control, Osmena Section, Compostela along Montevista – Compostela – New Bataan – Maragusan – Mati Bdry. Road. | Compostela Valley | 2014-08-09 | 1st | XI | LF | 30.5331 | 183 | 2013-12-27 | 2014-07-27 | -2.74 | O | 0.384 | 0.219 | 0.123 | 0.03 | 0.042 | 0.033 | 83.1 | -
A DE GUIA CONSTRUCTION | 18228 | L | AA | MA | GE | Construction of River Bank Protection, Siffu Flood Control Project, Sittio Gabit Section, Roxas, Isabela | Roxas, Isabela | 2015-08-28 | 1st | Isabela 2nd DEO | LF | 18.346 | 215 | 2015-02-24 | 2015-09-26 | 0.32% | O | 0.354 | 0.3 | 0.15 | 0.03 | 0.04 | 0.05 | 92.4% | -
A DE GUIA CONSTRUCTION | 18228 | L | AA | MA | GE | Construction of River Bank Protection, Stiffu River Flood Control Project, Sitio Gabit Section, Roxas, Isabela | Roxas, Isabela | 2015-11-14 | Final | ISABELA 2ND DEO | LF | 18.3468 | 219 | 2015-02-24 | 2015-09-30 | (+) 0.02 | C | 0.3 | 0.133 | 0.3 | - | - | - | 73.3% | 73.3% Poor
A J TAYLAN CONSTRUCTION & DEVELOPMENT/JLP CONSTRUCTION & SUPPLY JOINT VENTURE | JV-14-518 | L | A | MB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads including Drainage Based on Pavement Management System/Highway Development and Management- 4(HDM-4), Pinili-Nueva Era Road, K0453+(-224)-K0454+1013, K0455+884-K0456+433, Pinili Road, Ilocos Norte | Pinili-Nueva Era Road, K0453+(-224)-K0454+1013, K0455+884-K0456+433, Pinili Road, Ilocos Norte | 2015-08-26 | 1st | Ilocos Sur 2nd DEO | LF | 37.519 | 219 | 2015-04-29 | 2015-12-04 | (+)2.27 | O | 0.355 | 0.209 | 0.15 | 0.03 | 0.051 | 0.05 | 84.5% | -
A. C. RIVERO DEVELOPMENT CORPORATION (Formerly: A.C. Rivero Construction) | 5122 | L | A | MB | GE | Construction of Bridge at Dodiongan Box Culvert along Sta. Felomina-Bonbonon-Digkilaan-Rogongon Road, Barangay Bonbonon, Iligan City, K01526+078.00 to K01526+108.00, K0 0+000.00 to K0 0+000.00 | Barangay Bonbonon, Iligan City, K01526+078.00 to K01526+108.00, K0 0+000.00 to K0 0+000.00 | 2015-06-08 | Final | Lanao del Norte Second DEO | LF | 24.567 | 295 | 2014-01-30 | 2014-11-20 | - | C | 0.433 | 0.2 | 0.3 | - | - | - | 93.3% | *90% Very Satisfactory
A. De Guia Construction | 18228 | L | AA | MA | GE | Construction of Drainage System / Protection Works along Daang Maharlika, Isabela 4th LD K0311+590 - K0314+350, San Luis - Caquilingan | Cordon, Isabela | 2014-10-27 | 1st | II | LF | 19.4025 | 231 | 2014-03-26 | 2014-11-11 | 0.96% | O | 0.347 | 0.3 | 0.15 | 0.03 | 0.029 | 0.033 | 88.9% | 88.90% Satisfactory
A. De Guia Construction | 18228 | L | AA | MA | GE | Construction/ Rehabilitation of Flood Control Projects, Nagassican Flood Control Projects, Sta. 0+000 to Sta. 0+224 | Nagassican, Santiago City | 2014-08-12 | 1st | II | LF | 19.5 | 184 | 2014-04-03 | 2014-10-03 | 13.19 | O | 0.288 | 0.248 | 0.15 | 0.03 | 0.055 | 0.05 | 82.1 | -
A. DE GUIA CONSTRUCTION | 18228 | L | AA | MA | GE | Construction of Drainage System/Protection Works along Daang Maharlika | Isabela 4th LD, K0390+200 to K0311+590 San Luis-Caquilingan, Cordon Isabela | 2015-06-07 | Final | Isabela 4th DEO | LF | 19.403 | 261 | 2014-03-26 | 2014-12-11 | 0% | C | 0.422 | 0.133 | 0.3 | - | - | - | 85.5% | *87.54% Satisfactory
A. DE GUIA CONSTRUCTION | 18228 | L | AA | MA | GE | Construction/Rehabilitation of Flood Control Projects in Isabela 4th DEO/4th LD-Nagassican Flood Control Project, Sta. 0+000 - Sta. 0+224 | Nagassican, Santiago City, Isabela | 2015-06-07 | Final | Isabela 4th DEO | LF | 19.5 | 214 | 2014-04-03 | 2014-11-02 | 0% | C | 0.365 | 0.2 | 0.3 | - | - | - | 86.5% | *83.86% Satisfactory
A. I. P. CONSTRUCTION | 32458 | L | A | MA | GE | Rehabilitation/ Reconstruction/ Upgrading of Damaged Paved National Roads Including Drainage Based on Pavement Management System/ Highway Development and Management-4 (HDM-4) (Intermittent Sections), Lt. Tacay Road, K0308+(-599)-K0308+000 & K0308+616-K0308+754, | Brgy. Caupasan and Brgy. Danglas, Danglas, Abra | 2015-11-09 | Final | Baguio City | LF | 13.4424 | 104 | 2015-06-15 | 2015-09-26 | - | C | 0.415 | 0.195 | 0.3 | - | - | - | 91% | 87.82% Satisfactory
A. J. LAVA BUILDERS CORP. (Formerly: A. J. Lava Builders) | 22265 | L | B | MA | GE | Flood Management Services Construction/Maintenance of Flood Mitigation Structures and Drainage System Improvement/Riprapping of Sitio Kapatagan River (Downstream), Brgy. San Jose, Antipolo City, 2nd LD | Brgy. San Jose, Antipolo City | 2015-11-11 | 1st | RIZAL 1ST DEO | LF | 27.6119 | 180 | 2015-06-10 | 2015-12-06 | 0.0018 | OG | 0.39 | 0.24 | 0.15 | 0.03 | 0.06 | 0.05 | 92% | 92% Very Satisfactory
A. M. Oreta and Co., Incorporated | 108 | L | AAA | LB |  | Region 2-PIDP-CBIMO | Sta. Ana, Cagayan | 2015-09-19 | 1st | NIA | LF | 80.788 | 690 | 2014-04-01 | 2015-10-09 | -1.58 | O | 0.37 | 0.3 | 0.13 | 0.03 | 0.06 | 0.05 | 94 | -
A. P. B. CONSTRUCTION | 17055 | L | B | MA | GE | Network Development/ Widening of National Roads-Secondary Road-Abra-Ilocos Norte Road K0409+000-K0409+100, K0409+115-K409+178, K0409+307-K0409+404, K0409+531-K0409+648, K0409+748-K0410+139, K0410+159-K0410+360, K0410+369-K0410+777, K0411+050-K0411+220, K0412+122-K0412+499, K0413+000-K0414+354, K0414+764-K0415+747, K0416+175-K0416+445, K041 | Abra | 2015-11-20 | 1st | Regional Office | LF | 81.9712 | 286 | 2015-06-25 | 2016-04-05 | 2.15% | OG | 0.318 | 0.29 | 0.15 | 0.022 | 0.045 | 0.033 | 85.8% | 85.8% Satisfactory
A. SANDOVAL CONSTRUCTION & SUPPLY | 35991 | L | C | SB | GE | Construction and Maintenance of Bridges along National Roads - Retrofitting/Strengthening of Permanent Bridges Leviste Bridge 1 (B03170LZ) along Talisay - Laurel - Agoncillo Road, Laurel, Batangas | Talisay - Laurel - Agoncillo, Laurel, Batangas | 2015-11-13 | Final | BATANGAS 3RD DEO | LF | 4.5569 | 150 | 2015-02-03 | 2015-07-02 | - | C | 0.372 | 0.2 | 0.3 | - | - | - | 87.2% | 87.2% Satisfactory
A.A. DE VERA CONSTRUCTION | 6191 | L | B | MA | GE | Concreting /Road Upgrading (Unpaved to Paved) Jct. (TNR) Cortes-Balilihan-Catigbian-Macaas Road, K0046+592.75 - K0046+858.9, Tubigon, Bohol | Tubigon, Bohol | 2015-11-16 | Final | Bohol 1st | LF | 8.485 | 155 | 2015-02-18 | 2015-07-22 | 0 | C | 0.344 | 0.2 | 0.3 | - | - | - | 84.4% | 84.4% Satisfactory
A.B. OPEÑA BUILDERS | 33996 | L | D | SB | GE | Concreting of Barangay Roads, Brgy. Sooc-Haluban, Lupi, Camarines Sur | Brgy. Sooc-Haluban, Lupi, Camarines Sur | 2015-11-12 | Final | Camarines Sur Fifth DEO | LF | 1.881 | 60 | 2015-03-12 | 2015-05-10 | 1.67% | C | 0.359 | 0.172 | 0.3 | - | - | - | 83.1% | 83.1% Satisfactory
A.C. MOJARES CONSTRUCTION, INC. | 1771 | L | AAA | MA | GE | Concreting and Sidewalk Improvement of Phase 2, Scout Tobias St., Brgy. Laging Handa, Quezon City | Quezon City | 2014-06-03 | 1st | Quezon City 2nd DEO | LF | 10.018 | 207 | 2015-02-20 | 2015-09-14 | (+) 41.00 | O | 0.394 | 0.24 | 0.15 | 0.015 | 0.028 | 0.05 | 87.7% | -
A.C. MOJARES CONSTRUCTION, INC. (DOING BUSINESS UNDER THE NAME AND STYLE OF A.C. MOJARES CONSTRUCTION) | 1771 | L | AAA | MA | GE | Construction/Improvement of Road and Bridge, Brgy. Obrero and Kristong Hari, Quezon City | Brgy. Obrero and Kristong Hari, Quezon City | 2015-12-04 | Final | QC 2nd DEO | LF | 9.1054 | 102 | 2015-05-04 | 2015-08-13 | 0.00% | C | 0.481 | 0.133 | 0.3 | - | - | - | 91.4% | 91.4% Very Satisfactory
A.C. Rivero Development Corporation (Formerly: A.C. Rivero Construction) | 5122 | L | A | MA | GE1 | Const./Completion of Subang Daku Bridge, Subang Daku River, San Miguel | Sogod, Southern Leyte | 2012-08-17 | 1st | VIII | LF | 42.82 | 220 | 2012-02-20 | 2012-09-26 | 0.24 | O | 0.383 | 0.3 | 0.15 | 0.03 | 0.04 | 0.033 | 93.6 | -
A.C. Rivero Development Corporation (Formerly: A.C. Rivero Construction) | 5122 | L | A | MA | GE1 | Const./Impv't. of San Miguel-Jct. Buac Rd., Daang Maharlika Rd (Km1207+000 - Km1209+454.40) | Sogod, Southern Leyte | 2012-08-19 | 1st | VIII | LF | 35.731 | 220 | 2012-02-20 | 2012-09-26 | 0.24 | O | 0.349 | 0.289 | 0.15 | 0.03 | 0.045 | 0.033 | 89.6 | -
A.C. Rivero Development Corporation (Formerly: A.C. Rivero Construction) | 5122 | L | A | MA | GE1 | Upgrading/Conc. of San Juanico-Basey-Sohoton Rd., K0913+721.75-K0917+915.72, w/ exceptions | Basey, Samar | 2012-08-07 | 1st | VIII | LF | 47.065 | 200 | 2012-04-27 | 2012-11-12 | 23.72 | O | 0.357 | 0.24 | 0.15 | 0.03 | 0.04 | 0.033 | 85 | -
A.C. RIVERO DEVELOPMENT CORPORATION (Formerly: A.C. Rivero Construction) | 5122 | L | A | MB | GE | Rehab/Major Repair of Permanent Bridges, Amparo Bridge, Along Bdry, S. Leyte- Maasin-Macrohon-Sogod-Daang Maharlika | Along Bdry, S. Leyte- Maasin-Macrohon-Sogod-Daang Maharlika | 2015-06-03 | Final | Southern Leyte DEO | LF | 8.928 | 150 | 2015-02-02 | 2015-07-01 | 1.81% | C | 0.426 | 0.133 | 0.3 | - | - | - | 85.9% | *85.9% Satisfactory
A.C. RIVERO DEVELOPMENT CORPORATION (Formerly: A.C. Rivero Construction) | 5122 | L | A | MB | GE | Off-Carriageway Improvement along Jct. Taft - Oras - San Policarpio-Arteche Road, K0950+000 - K0955+000 | K0950+000 - K0955+000 | 2015-06-29 | 1st | Eastern Samar DEO | LF | 33.355 | 150 | 2015-03-17 | 2015-08-13 | - | O | 0.297 | 0.3 | 0.15 | 0.03 | 0.04 | 0.033 | 85% | -
A.C. RIVERO DEVELOPMENT CORPORATION (Formerly: A.C. Rivero Construction) | 5122 | L | A | MB | GE | Completion of Dodiongan Bridge along Sta. Felomina-Bonbonon-Digkilaan-Rogongon Road, Brgy. Bonbonon, Iligan City K01526+058-K01526+118, K01526+910-K01526+297 | Brgy. Bonbonon, Iligan City K01526+058-K01526+118, K01526+910-K01526+297y | 2015-09-03 | 1st | Lanao del Norte 2nd DEO | LF | 37.105 | 236 | 2015-02-18 | 2015-10-11 | 1.32% | O | 0.384 | 0.285 | 0.15 | 0.02 | 0.045 | 0.05 | 93.4% | -
A.C. RIVERO DEVELOPMENT CORPORATION (Formerly: A.C. Rivero Construction) | 5122 | L | A | MB | GE | Replacement of Permanent Weak Bridge, Ramon Magsaysay Bridge (B0469MN) along Jct. Switch-Jct.Monte Alegre Road | Ramon Magsaysay, Zamboanga del Sur | 2015-08-29 | 1st | Zamboanga del Sur 1st | LF | 29.101 | 230 | 2015-05-11 | 2015-12-26 | (+)19.46 | O | 0.288 | 0.2989 | 0.15 | 0.03 | 0.051 | 0.05 | 86.79% | -
A.C. RIVERO DEVELOPMENT CORPORATION (Formerly: A.C. Rivero Construction) | 5122 | L | A | MB | GE | Construction and Maintenance of Bridges along National Rd. (Replacement of Permanent Weak Bridge) at Olingan Bridge along Dipolog-Oroquieta National Road, Olingan, Dipolog City, Zamboanga del Norte | Olingan, Dipolog City, Zamboanga del Norte | 2015-11-16 | 1st | Zamboanga Del Norte 1st DEO | LF | 21.2177 | 220 | 2015-05-29 | 2016-01-03 | 0.16% | OG | 0.371 | 0.22 | 0.15 | 0.022 | 0.042 | 0.05 | 85.5% | 85.5% Satisfactory
A.C. RIVERO DEVELOPMENT CORPORATION/JQD CONSTRUCTION AND GENERAL SERVICES JOINT VENTURE | JV-14-1038 | L | A | MB | GE | Rehabilitation/Major Repair of Permanent Weak Bridges, Otikon Bridge Along Daang Maharlika (B00598LT), Libagon, Southern Leyte | Libagon, Southern Leyte | 2015-11-16 | 1st | Southern Leyte DEO | LF | 31.056 | 195 | 2015-06-24 | 2016-01-04 | (+)22.63% | OG | 0.249 | 0.3 | 0.15 | 0.03 | 0.06 | 0.05 | 83.9% | 83.9% Satisfactory
A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 19278 | L | B | MA | GE | Construction of River Bank Protection along Marusay River, San Vicente Section | Calasiao, Pangasinan | 2015-06-10 | Final | Pangasinan 4th DEO | LF | 18.228 | 116 | 2015-02-03 | 2015-05-29 | 0% | C | 0.35 | 0.2 | 0.3 | - | - | - | 85% | *85% Satisfactory
A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 19278 | L | B | MA | GE | Construction of Bank Protection Works, Agnooo River Basin Flood Control Project (Phase III) Brgy. Bantog, Asingan, Pangasinan | Asingan, Pangasinan | 2015-11-16 | 1st | PANGASINAN 3RD DEO | LF | 18.3356 | 180 | 2015-08-26 | 2016-02-23 | 0.025 | OG | 0.389 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 91.4% | 91.4% Very Satisfactory
A.D.P CONST. & SUPPLY | 3466 | L | A | MB | GE | Network Development, Widening of National Road, Secondary Road along Roxas City-Cagay-Sibaguan Balijuagan-Cudian-Ivisan Road Chainage 0-200, Chainage 942-1182 (0-200(0+304.50) (K0104+122.50) 942-1182 (K0104+760-K0105+000) | Sibaguan, Roxas City, Capiz | 2015-09-02 | 1st & Final | Capiz 1st | LF | 10.341 | 121 | 2015-03-12 | 2015-07-10 | 0% | C | 0.418 | 0.133 | 0.3 | - | - | - | 85.1% | *85.1% Satisfactory
A.D.P Construction & Supply | 3466 |  |  |  |  | Impvt./Conc. of Access Road, Tubalan Port, Tubalan |  | 2010-06-14 |  | XI |  | 58.261 | 320 |  |  |  | O | 0.338 | 0.3 | 0 | 0.03 | 0.04 | 0.033 | 74.1 | -
A.D.P Construction & Supply | 3466 |  |  |  |  | Rehab./Reconst./Upgrading of Damaged Paved National Road, Roxas City Boundary-Panitan Road-Jct. Bailan Road, Capiz (KM.112+750-Km.122+705) with exception |  | 2010-08-31 |  | VI |  | 53.673 | 225 |  |  |  | O | 0.364 | 0.24 | 0.15 | 0.03 | 0.051 | 0.05 | 88.5 | -
A.D.P Construction & Supply | 3466 | L | A | MB | GE | Malag-it Box Culvert along Iloilo East Coast-Capiz Road (Construction of Malag-it Bridge along Iloilo East Coast-Capiz Road) | Pontevedra, Capiz | 2014-10-29 | 1st | VI | LF | 35.132 | 240 | 2014-05-23 | 2015-01-17 | -37.28% | O | 0.388 | 0.249 | 0 | 0.03 | 0.054 | 0.033 | 75.4% | 75.40% Unsatisfactory
A.D.P Construction & Supply | 3466 | L | A | MB | GE | Widening of Caradio-an Bridge alog Bacolod South Road, Barangay Caradio-an | Himamaylan City, Negros Occidental | 2014-10-23 | 1st | VI | LF | 24.8045 | 273 | 2014-02-16 | 2014-11-15 | -11.6% | O | 0.378 | 0.221 | 0.034 | 0.03 | 0.045 | 0.033 | 74.1% | 74.10% Poor
A.D.P Construction & Supply | 3466 | L | A | MB | GE | Construction/Rehab. Of Drainage System along Balasan-Carles Road, Brgy. Barosbos | Carles, Iloilo | 2014-10-29 | 1st | VI | LF | 43.9538 | 274 | 2014-04-24 | 2015-01-22 | 6.46% | O | 0.373 | 0.218 | 0.15 | 0.03 | 0.054 | 0.05 | 87.5% | 87.50% Satisfactory
A.D.P Construction & Supply | 3466 | L | A | MA | GB | Construction of Multi-Purpose Building | Poblacion, Pavia, Iloilo | 2014-10-28 | 1st | VI | LF | 4.2269 | 120 | 2014-06-17 | 2014-10-14 | -2.91% | O | 0.362 | 0.214 | 0.121 | 0.03 | 0.049 | 0.05 | 82.6% | 82.60% Satisfactory
A.D.P Construction & Supply | 3466 | L | A | MB | GE | Road Upgrading (Gravel to Paved) along Davao-Sarangani Coastal Road km. 1671+600 to km. 1673+060, Biton-Lanao Section | Davao del Sur | 2014-08-07 | 2nd | XI | LF | 40.0822 | 208 | 2013-03-07 | 2013-09-30 | 0 | O | 0.014 | 0.3 | 0 | 0.03 | 0.014 | 0 | 35.8 | -
A.D.P Construction & Supply | 3466 | L | A | MB | GE1 | Rd. Upgrading (Gravel to Paved) along Davao-Sarangani Coastal Rd., Km.1671+600-Km.1673+060, Biton-Lanao Sect. | Davao del Sur | 2013-08-06 | 1st | XI | LF | 40.082 | 179 | 2013-03-07 | 2013-09-01 | -19.55 | O | 0.322 | 0.248 | 0 | 0.03 | 0.033 | 0.033 | 66.6 | -
A.D.P Construction & Supply | 3466 | L | A | MA | GE2 | Const. of Slope Protection along Jct. Bancal-Leon-Antique Boundary Rd., K0031+722-K0031+891 | Leon, Iloilo | 2013-03-22 | 1st | VI | LF | 13.802 | 188 | 2012-11-05 | 2013-05-11 | 0.59 | O | 0.388 | 0.241 | 0.15 | 0.03 | 0.055 | 0.05 | 91.4 | -
A.D.P. CONST. & SUPPLY | 3466 | L | A | MB | GE | Network Development, Widening of National Road, Secondary Road along Roxas City, Cagay-Sibaguan Balijuangan-Cudian-Ijisan Road | Chainage 0-200, Chainage 942-1182 10-200 (0+304.80) (K0104+760- K0105+000), Pontevedra, Capiz | 2015-06-06 | 1st | Capiz First DEO | LF | 10.341 | 121 | 2015-03-12 | 2015-07-10 | -4.53% | O | 0.368 | 0.251 | 0.105 | 0.03 | 0.035 | 0.033 | 82.2% | -
A.D.P. CONST. & SUPPLY | 3466 | L | A | MB | GE | Widening of Sara-San Dionisio Road | K0203+(-882) to K0203+243, Sara, Iloilo | 2015-06-09 | 1st | Iloilo Third DEO | LF | 26.054 | 175 | 2015-02-16 | 2015-08-09 | 29% | O | 0.344 | 0.252 | 0.15 | 0.022 | 0.035 | 0.05 | 85.3% | -
A.D.P. CONST. & SUPPLY | 3466 | L | A | MA | GE | Construction of Drainage System along Iloilo East Coast Capiz Road | K0204+106, Sara, Iloilo | 2015-06-09 | 1st | Iloilo Third DEO | LF | 44.467 | 252 | 2015-02-18 | 2015-10-27 | 2.63% | O | 0.37 | 0.247 | 0.15 | 0.022 | 0.035 | 0.05 | 87.4% | -
A.D.P. CONST. & SUPPLY | 3466 | L | A | SB | GE | Retrofitting/Strengthening of Cabiri-an Bridge (B00165PN) along Guimbal-Tubungan Road | (K0033+163), Guimbal, Iloilo | 2015-06-03 | Final | Iloilo First DEO | LF | 9.3 | 90 | 2015-02-16 | 2015-05-16 | 0% | C | 0.5 | 0.133 | 0.3 | - | - | - | 93.3% | *93.3% Very Satisfactory
A.D.P. CONST. & SUPPLY | 3466 | L | A | MB | GE | Widening of Sara - San Dionisio Road, K0203+ (-882) - K0203+243 | Sara, Iloilo | 2015-08-29 | Final | Iloilo 3rd | LF | 26.054 | 175 | 2015-02-16 | 2015-08-09 | 2.86% | C | 0.449 | 0.133 | 0.3 | - | - | - | 88.2% | *87.3% Satisfactory
A.D.P. CONST. & SUPPLY | 3466 | L | A | MB | GE | Construction/Improvement of Access Road Leading to Declared Tourism Destination, Hanay-Hanay Road leading to Twin Lake, San Jose, 2nd District, Negros Oriental | San Jose, 2nd District, Negros Oriental | 2015-11-11 | Final | Negros Oriental 2nd DEO | LF | 9.3097 | 131 | 2015-03-25 | 2015-08-02 | - | C | 0.457 | 0.133 | 0.3 | - | - | - | 89% | 89% Satisfactory
A.F.G. CONSTRUCTION AND CONSTRUCTION SUPPLY | 17161 | L | A | MB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Road including Drainage Based on Pavement Management System / Highway Development and Management - 4 (HDM-4) (Intermittent Section) along Hinigaran - Isabela Road, K0058+263 - K0059+000 | Barangay Paticui, Hinigaran, Negros Occidental | 2015-08-27 | 1st | Negros Occidental 2nd | LF | 12.674 | 127 | 2015-05-06 | 2015-09-09 | 0.25% | O | 0.358 | 0.239 | 0.15 | 0.03 | 0.05 | 0.033 | 86% | -
A.F.G. Construction and Construction Supply | 17161 | L | A | MA | GE1 | Odiong-Sibalom-San Remegio-Leon Rd. Upgrading (Gravel to Paved), Km. 129+328-Km. 131+275 | San Remigio, Antique | 2013-08-15 | 1st | VI | LF | 40.453 | 179 | 2013-02-22 | 2013-08-19 | 15.36 | O | 0.336 | 0.24 | 0.15 | 0.03 | 0.037 | 0.033 | 82.6 | -
A.F.G. Construction and Construction Supply | 17161 | L | A | MA | GB1 | Const. of Two (2) Storey, Eight (8) Cl Sch. Bldg., Leonora Salapantan NHS | San Miguel, Iloilo | 2013-08-22 | 1st | VI | LF | 8.949 | 150 | 2013-04-03 | 2013-08-30 | -4.25 | O | 0.347 | 0.2 | 0.108 | 0.03 | 0.032 | 0.033 | 75 | -
A.F.G. Construction and Construction Supply | 17161 | L | A | MA | GE1 | Const. of Tangalan-Ibajay Rd. | Aklan | 2013-03-19 | 1st | VI | LF | 45.834 | 179 | 2013-01-15 | 2013-07-12 | 7.79 | O | 0.387 | 0.259 | 0.15 | 0.024 | 0.03 | 0.033 | 88.3 | -
A.F.G. Construction and Construction Supply | 17161 | L | A | MA | GE1 | Replacement/Const. of Tubog Bridge, Brgy. Tubog | Hamtic, Antique | 2012-08-15 | 1st | VI | LF | 7.587 | 180 | 2012-02-29 | 2012-08-26 | 5.13 | O | 0.372 | 0.23 | 0.15 | 0.01 | 0.035 | 0.033 | 83 | -
A.F.G. CONSTRUCTION AND CONSTRUCTION SUPPLY | 17161 | L | A | MA | GB | Construction of 2-CL Alimanguan National High School Brgy. Alimanguan | San Vicente, Palawan | 2015-06-05 | 1st | Palawan 1st DEO | LF | 1.721 | 120 | 2015-02-17 | 2015-06-16 | 0% | O | 0.36 | 0.24 | 0.15 | 0.03 | 0.047 | 0.033 | 86% | -
A.F.G. CONSTRUCTION AND CONSTRUCTION SUPPLY | 17161 | L | A | MA | GE | Construction/Improvement of J.M. Basa-Gen. Hughes-Fort San Pedro Road | K0001+530 to K0001+852 and K0001+852 to K0002+308, Iloilo City | 2015-06-02 | Final | Iloilo City DEO | LF | 23.375 | 155 | 2015-05-12 | 2015-10-13 | 4.42% | C | 0.386 | 0.2 | 0.3 | - | - | - | 88.6% | *88.6% Satisfactory
A.F.G. CONSTRUCTION AND CONSTRUCTION SUPPLY | 17161 | L | A | MB | GE | Widening of Jct. New Sagay - Old Sagay Rd with drainage, K0084 + (-828) - K0085+337, Sagay City, Negros Occidental | Sagay City, Negros Occidental | 2015-11-19 | Final | Regional Office, NIR | LF | 49.2118 | 245 | 2015-03-02 | 2015-11-01 | - | C | 0.44 | 0.135 | 0.3 | - | - | - | 87.5% | 87.5% Satisfactory
A.F.G. CONSTRUCTION AND CONSTRUCTION SUPPLY | 17161 | L | A | MB | GE | Construction/Upgrading/Rehabilitation of Drainage along Bacolod North Road, K0005+(-135) - K0006+622, Talisay City, Negros Occidental | Talisay City, Negros Occidental | 2015-11-18 | Final | Negros Occidental 1st DEO | LF | 9.2968 | 252 | 2015-02-13 | 2015-10-22 | - | C | 0.454 | 0.133 | 0.3 | - | - | - | 88.7% | 88.7% Satisfactory
A.F.G. CONSTRUCTION AND CONSTRUCTION SUPPLY | 17161 | L | A | MB | GE | Rehabilitation /Reconstruction/ Upgrading of Damaged Paved National Road including Drainage Based on Pavement Management System / Highway Development and Management - 4 (HDM-4) (Intermittent Section), along Hinigaran-Isabela Road, K0058+263 - K0059+000, Barangay Paticui, Hinigaran, Negros Occidental | Barangay Paticui, Hinigaran, Negros Occidental | 2015-11-16 | Final | Negros Occidental 2nd DEO | LF | 12.6742 | 157 | 2015-05-06 | 2015-10-09 | (+)0.36% | C | 0.427 | 0.134 | 0.3 | - | - | - | 86.1% | 86.04% Satisfactory
A.F.G. CONSTRUCTION AND CONSTRUCTION SUPPLY/REDSON CONSTRUCTION AND SUPPLIES (JOINT VENTURE) | JV-13-257 | L | A | MA | GE | Rehab./Reconstruction/Upgrading/Concreting of Access Road Leading to Gawahon Resort, with exceptions | Sta. 0+000-Sta. 20+000, Victorias City, Negros Occidental | 2015-06-12 | Final | Negros First DEO | LF | 36.23 | 280 | 2014-05-05 | 2015-02-08 | 0% | C | 0.356 | 0.2 | 0.3 | - | - | - | 85.6% | *85.6% Satisfactory
A.F.G. CONSTRUCTION AND SUPPLY | 27999 | L | B | SB | GE | Construction of Farm to Market Road, Barangay Laguinbanwa West, Numancia, Aklan | Barangay Laguinbanwa West, Numancia, Aklan | 2015-11-16 | Final | Aklan | LF | 4.6517 | 80 | 2015-08-05 | 2015-10-24 | 0.00% | C | 0.421 | 0.2 | 0.3 | - | - | - | 92.1% | 92.1% Very Satisfactory
A.I.P. CONSTRUCTION | 32458 | L | A | MA | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads including Drainage Based on Pavement Management System/Highway Development and Management-4 (HDM-4) (Intermittent Section), Lt. Takay Road, K0308+(-599) to K0308+000 & K0308+616 to K0308+754, Baguio City | Baguio City | 2015-09-04 | 1st | Baguio City DEO | LF | 13.442 | 104 | 2015-06-15 | 2015-09-26 | 2.59% | O | 0.36 | 0.228 | 0.15 | 0.03 | 0.056 | 0.05 | 87.4% | -
A.J Taylan Construction Corporation | 2336 | L | A | MB | GE1 | Road Opening/Const. of Missing Links of National Road, Solsona-Kabugao Road, Ilocos Norte Side |  | 2009-09-09 | 1st | I |  | 48.199 | 300 |  |  |  | O | 0.379 | 0.25 | 0.15 | 0.03 | 0.05 | 0.033 | 89.2 | -
A.J. Lava Builders | 22265 | L | C | SB | GE2 | Repair & Maint. of Flood Control & Drainage Structures along Rofriguez-San Jose-Quezon City Rd. | Rodriguez, Rizal | 2012-11-19 | 1st | IVA | LF | 2.449 | 90 | 2012-09-11 | 2012-12-09 | 29.23 | O | 0.337 | 0.3 | 0.15 | 0.03 | 0.025 | 0.033 | 87.5 | -
A.J. LAVA BUILDERS CORP. (Formerly: A.J. Lava Builders) | 22265 | L | B | MA | GE | National Road Services - Network Development - Widening of National Road - Arterial Roads, Marikina-Infanta Roads, K0 035+540 - K0 036+440, K0 037+290 - K0 037+484 | Antipolo City, 2nd LD | 2015-08-26 | 1st & Final | Rizal 1st | LF | 19.6 | 180 | 2015-03-06 | 2015-09-01 | 1.33% | C | 0.454 | 0.133 | 0.3 | - | - | - | 88.7% | *88.7% Satisfactory
A.J. Taylan Construction Corp/FR Espiritu Jr. Builders (JV) | JV-14-074 | L | B | MA | GE | Additional Priority Flood Control Project | San Isidro, Dumalneg, Ilocos Norte | 2014-10-21 | 1st | I | LF | 41.1788 | 163 | 2014-09-11 | 2015-02-20 | 0.36% | O | 0.299 | 0.276 | 0.15 | 0.03 | 0.056 | 0.05 | 86.1% | 86.10% Satisfactory
A.J. TAYLAN CONSTRUCTION CORPORATION | 2336 | L | B | MA | GE | Laoag River Basin Flood and Sabo Project, Concrete Revetment along Bongo River Brgy. Sta. Monica, Sitio 2, San Nicolas, Ilocos Norte | San Nicolas, Ilocos Norte | 2015-11-13 | 1st | ILOCOS NORTE 2ND DEO | LF | 9.65 | 194 | 2015-08-12 | 2016-02-21 | 0.016 | OG | 0.38 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 90.5% | 90.5% Very Satisfactory
A.J. Taylan Construction Corporation/Zedik Builders (JV) | JV-13-345 | L | B | MA | GE | Road Upgrading (Gravel to Paved) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Standard (HDM-4 Project Analysis) of Piniti-Banna (Espiritu) Road | Ilocos Norte | 2014-08-08 | 1st | I | LF | 28.9422 | 236 | 2014-02-14 | 2014-10-07 | 27.99 | O | 0.38 | 0.24 | 0.15 | 0.03 | 0.055 | 0.033 | 88.8 | -
A.L Gantuangco Construction | 30872 |  |  |  |  | Construction of the Diversion Works and Canal System of Libertad CIP - Phase 2 |  | 11/15-20/2010 |  | NIA |  | 16.06 | 202 |  |  |  | O | 0.3729 | 0.2638 | 0.15 | 0.0225 | 0.0377 | 0.05 | 89.69 | -
A.L Gantuangco Construction | 30872 | L | C | SB | GE2 | Benolho CIS |  | 10/6-10/08 | 1st | NIA |  | 3.72 | 90 |  |  |  | O | 0.277 | 0.18 | 0.05 | 0.02 | 0.038 | 0.1 | 66.5 | -
A.L. Dare Construction | 11932 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rd. (Int. Sect.) at Candaba-San Miguel Rd., K0070+290-K0071+184 | Candaba, Pampanga | 2013-07-29 | 1st | III | LF | 11.909 | 139 | 2013-03-25 | 2013-08-10 | -1.4 | O | 0.319 | 0.24 | 0.136 | 0.03 | 0.055 | 0.033 | 81.3
A.L. DARE CONSTRUCTION | - | L | - | - | GE | Rehabilitation/Construction of Slope Protection along Cabetican, Bacolor, Pampanga | Bacolor, Pampanga | 2015-06-01 | Final | Pampanga 1st DEO | LF | 6.32 | 118 | 2014-08-04 | 2014-11-29 | 0% | C | 0.333 | 0.2 | 0.3 | - | - | - | 83.3% | *83.3% Satisfactory
A.L. SALAZAR CONSTRUCTION INC. | 3899 | L | AAA | LA | GE | Drainage Improvement of Commonwealth Avenue Drive to Zuzuaregui, Brgy. Batasan Hills, Quezon City | Brgy. Batasan Hills, Quezon City | 2015-08-25 | 1st | QC 1st DEO | LF | 17.562 | 270 | 2015-04-07 | 2016-01-01 | 22.77% | O | 0.38 | 0.24 | 0.15 | 0.023 | 0.045 | 0.05 | 88.8% | -
A.L. Salazar Construction, Inc. | 3899 | L | AAA | LA | GE | Rehabiliation/Improvement of drainage System along C-3 Road | Caloocan City | 2014-11-22 | 1st | NCR | LF | 17.4251 | 209 | 2014-05-02 | 2014-11-26 | 0.36% | O | 0.38 | 0.24 | 0.15 | 0.03 | 0.045 | 0.033 | 87.8% | 87.80% Satisfactory
A.L. Salazar Construction, Inc. | 3899 | L | AAA | LA | GE1 | Const./Widening/Upgrading/Rehab. of Access Rd. to Taytay-Bantulan Port (Km.210+000-Km.214+211) | Taytay, Palawan | 2013-03-12 | 2nd | IVB | LF | 89.312 | 450 | 2012-03-28 | 2013-06-20 | -11.99 | O | 0.364 | 0.3 | 0.03 | 0.03 | 0.055 | 0.033 | 81.2 | -
A.L. Salazar Construction, Inc. | 3899 | L | AAA | LA | GE1 | Const./Widening/Upgrading/Rehab. of Access Road (Km.210+000-Km.214+211) | Taytay, Palawan | 2012-08-03 | 1st | IVB | LF | 81.362 | 349 | 2012-03-28 | 2013-02-19 | 2.82 | O | 0.332 | 0.24 | 0.15 | 0.03 | 0.045 | 0.05 | 84.7 | -
A.L.R. Construction Corporation | 24110 |  |  |  |  | Completion of 2-Storey 4-CL @ Landayan E/S |  | 2010-02-24 |  | IVA |  | 5.03 | 225 |  |  |  | O | 0.354 | 0.3 | 0.15 | 0.015 | 0.018 | 0.033 | 87 | -
A.M. AYUNAN CONSTRUCTION | 13983 | L | AAA | SB | GB | Construction/Rehabilitation of Brgy Hall | Brgy. Langkong, M'lang, Cotabato | 2015-11-11 | 1st | Cotabato First DEO | LF | 0.924 | 75 | 2015-08-12 | 2015-11-24 | (-) 9.80% | OG | 0.363 | 0.16 | 0.052 | 0.03 | 0 | 0.016 | 62.1% | 62.1% Poor
A.M. Oreta & Co., Inc./IBC Int'l Builders Corp. (JV) | JV-07096 | L | AAA | LB |  | Kalibo Airport Development Project | Pook, Kalibo, Aklan | 2015-06-17 | 1st | DOTC | LF | 287.056 | 360 | 2010-04-04 | 2015-09-24 | 4.92 | O | 0.381 | 0.3 | 0.15 | 0.02 | 0.044 | 0.033 | 92.8 | -
A.M. Oreta / IBC (Joint Venture) | JV-11-210 | L | AAA | LB | GE2 | Const. of Drainage System along Iloilo-Capiz Rd. (Old Route) Nat'l Rd. CPU Sect., Iloilo City | Jaro, Iloilo City | 2012-08-06 | 1st | VI | LF | 42.875 | 240 | 2012-01-04 | 2012-08-30 | 6.12 | O | 0.321 | 0.239 | 0.15 | 0.03 | 0.055 | 0.05 | 84.5 | -
A.M. TABAYAG BUILDERS | 15008 | L | D | SB | GE | Construction/Concreting of Local Road, Lower Bayao, Tukuran, Zamboanga del Sur | Tukuran, Zamboanga del Sur | 2015-11-13 | Final | Zamboanga Del Sur 1st DEO | LF | 2.938 | 45 | 2015-03-05 | 2015-04-18 | - | C | 0.422 | 0.133 | 0.3 | - | - | - | 85.5% | 85.5% Satisfactory
A.P Palacios Construction | 29021 | L | C | SB | GE1 | Rehab./Impvt. of Dikidit-Suguit FTMR |  | 2009-09-08 | 1st | III |  | 4.723 | 150 |  |  |  | O | 0.3 | 0.3 | 0.15 | 0.03 | 0.05 | 0.033 | 86.3 | -
A.P. CONSEBIDO CONSTRUCTION AND TRADING | 33616 | L | D | SB | GE | Cnstruction of Barangay Road (New Road with PCCP Surfacing), Brgy. Tagumpay Sta. 000+008.10- Sta. 000+225 | Roxas, Palawan | 2015-06-04 | Final | Palawan 1st DEO | LF | 1.866 | 40 | 2015-02-16 | 2015-03-27 | 0% | C | 0.456 | 0.133 | 0.3 | - | - | - | 88.9% | *88.9% Satisfactory
A.P. CONSEBIDO CONSTRUCTION AND TRADING | 33616 | L | D | SB | GE | Construction of Barangay Road (New Road with PCCP Surfacing) Brgy, Tagumpay Sta. 000+0008.10-Sta. 000+225.00, Roxas, Palawan | Roxas, Palawan | 2015-08-26 | 1st & Final | Palawan I DEO | LF | 1.866 | 40 | 2015-02-16 | 2015-03-27 | - | C | 0.425 | 0.136 | 0.3 | - | - | - | 86.1% | *86.1% Satisfactory
A.P. CONSEBIDO CONSTRUCTION AND TRADING | 33616 | L | D | SB | GE | Repair/Maintenance of Tagbulan River Revetment, K0143+955, Roxas-Taytay Road, Brgy. Minara | Roxas, Palawan | 2015-11-13 | Final | Palawan 1st DEO | LF | 2.4146 | 45 | 2014-12-07 | 2015-01-20 | 0 | C | 0.428 | 0.133 | 0.3 | - | - | - | 86.1% | 86.1% Satisfactory
A.P.B. Construction | 17055 | L | C | SB | GE1 | Rehab./Reconst./Upgrading of Damaged Paved National Road, PMA cut-off Road 2 K0+000-K0+360 | Baguio City | 2011-08-18 | 1st | CAR | LF | 5.61 | 102 | 2011-05-06 | 2011-08-15 | - | O | 0.37 | 0.24 | 0 | 0.03 | 0.042 | 0.033 | 71.5 | -
A.P.B. CONSTRUCTION | 17055 | L | B | MA | GE | Off-Carriageway Improvement along Baguio-Bontoc Road, K0253+(-586) to K0253+000, K0259+450 to K0259+600, K0260+500 to K0262+000 | La Tridad, Benguet | 2015-06-02 | 1st | Benguet 1st DEO | LF | 18.999 | 150 | 2015-02-20 | 2015-07-19 | (-) 0.02% | O | 0.333 | 0.274 | 0.149 | 0.03 | 0.05 | 0.035 | 87.1% | -
A.P.B. CONSTRUCTION | 17055 | L | B | MB | GE | Improvement/Upgrading of Naguilian-Bagulin Road Leading to Tudingan Falls and Kedlap Burial Cave Sta. 266+980 to Sta. 271+279, Naguilian, La Union | Naguilian, La Union | 2015-08-30 | 1st | La Union 2nd DEO | LF | 41.295 | 179 | 2015-05-22 | 2015-11-17 | (+)0.69 | O | 0.335 | 0.287 | 0.15 | 0.023 | 0.037 | 0.05 | 88.2% | -
A.P.O. General Construction | 7010 | L | B | MA | GE | Road Upgrading (Gravel to Paved) along Acop-Kapangan-Kibungan-Bakun Road, K0283+636 - K0283+796, K0287+621 - K0287+685, K0289+214 - K0289+473, K0289+549 - K0289+709, K0290+901 - K0291+000, K0292+016 - K0292+114, K0298+781 - K0299+514, K0299+531 - K0299+816 | Kapangan, Benguet | 2014-11-20 | 1st | CAR | LF | 72.0261 | 267 | 2014-06-09 | 2015-03-02 | 10.93% | O | 0.362 | 0.24 | 0.15 | 0.03 | 0.061 | 0.05 | 89.3% | 89.30% Very Satisfactory
A.P.O. General Construction | 7010 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Paved) Int. Sect., Acop-Kapangan-Kibungan-Bakun Rd., K0348+000-K0349+000 | Benguet | 2013-08-01 | 1st | CAR | LF | 23.654 | 207 | 2013-02-05 | 2013-08-30 | 0.91 | O | 0.356 | 0.239 | 0.15 | 0.023 | 0.048 | 0.05 | 86.6 | -
A.P.O. General Construction | 7010 | L | B | MA | GE1 | Rd. Upgrading (gravel to concrete) along Acop-Kapangan-Kibungan-Bakun Rd., K0285+444-K0286+840 V.S. (K0285+423-K0286+836 as per RBIA) & K0345+470-K0348+000 V.S. (K0345+500-K0348+000 as per RBIA) | Benguet | 2012-11-21 | 1st | CAR | LF | 59.896 | 237 | 2012-04-26 | 2012-12-18 | 0.78 | O | 0.333 | 0.24 | 0.15 | 0.015 | 0.047 | 0.05 | 83.5 | -
A.P.O. GENERAL CONSTRUCTION | 7010 | L | B | MA | GE | Road Upgrading (Gravel to Paved) along Acop-Kapangan-Kibungan-Bakun Road, K0283+636 - K0283+796, K0287+621 - K0287+685, K0289+214 - K0289+473, K0289+549 - K0289+709, K0290+901 - K0291+000, K0292+016 - K0929+114, K0296+781 - K0299+514, K0299+531 - k0299+816 | Kapangan, Benguet | 2015-06-03 | Final | CAR | LF | 72.026 | 267 | 2015-06-09 | 2015-03-02 | 0% | C | 0.398 | 0.175 | 0.3 | - | - | - | 87.3% | *88.5% Satisfactory
A.P.O. GENERAL CONSTRUCTION | 7010 | L | B | MA | GE | Road Upgrading (Unpaved to Paved) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standards (HDM-4 Project Analysis) (Intermittent Sections) along Mt. Province - Ifugao Road (Kiling - Paracelis Section), K0460+508 to K0460+868, K0467+904 to K0469+000, K0471+451 to K0472+061, K0473+155 to K0473+582, K0474+350 to K0474+368, K0477+312 to K0477+341, Paracelis, Mt. Province | Paracelis, Mt. Province | 2015-08-29 | 1st | CAR | LF | 54.883 | 237 | 2015-04-07 | 2015-11-29 | 1.01% | O | 0.367 | 0.246 | 0.15 | 0.03 | 0.051 | 0.05 | 89.4% | -
A.R. & Mark Builders | 31673 | L | C | SB | GB | Const. of Multi-Purpose Building, BUSECO Compound | Manolo Fortich, Bukidnon | 2014-10-21 | 1st | X | LF | 7.92 | 124 | 2014-07-28 | 2014-11-28 | -13.35% | O | 0.304 | 0.24 | 0.017 | 0.01 | 0.022 | 0.033 | 62.6% | 62.60% Poor
A.R. & Mark Builders | 31673 | L | D | SB | GB1 | Const. of 1-Storey, 1-CL & 1-Storey, 1-CL Kinder at Maramag South PS, Pob. | Maramag, Bukidnon | 2013-08-08 | 1st | X | LF | 1.448 | 187 | 2013-03-25 | 2013-09-27 | -2.86 | O | 0.393 | 0.235 | 0.12 | 0.03 | 0.023 | 0.033 | 83.4 | -
A.R. & MARK BUILDERS | 31673 | L | C | SB | GE | Cluster 2014-28, Construction of Roads; Municipalities of El Salvador (Brgy. Sinaloc, Bolisong, Himaya, Sambulawan); Jasaan (Brgy. Kimaya, Luz Banson), Misamis Oriental | Misamis Oriental | 2015-11-16 | Final | Misamis Oriental 2nd | LF | 8.348 | 105 | 2015-02-02 | 2015-05-18 | 0.00% | C | 0.207 | 0.2 | 0.3 | - | - | - | 70.7% | 70.7% Poor
A.R. Lustre Jr. Construction | 7680 | L | AAA | MB | GE1 | Conc. of Puerto Princesa South Rd. (Aborlan Sect. Km.60+024.80-Km.64+000 w/ exceptions) | Aborlan, Palawan | 2013-03-15 | 1st | IVB | LF | 62.614 | 240 | 2012-12-14 | 2013-08-10 | -10.01 | O | 0.362 | 0.24 | 0.15 | 0.03 | 0.055 | 0.033 | 87 | -
A.R. Lustre, Jr. Construction | 7680 | L | AAA | MB | GE1 | Const. of Taguliat Bridge along PPSR-JCT-Napsan-Apurawan Rd., K0037+675 | Puerto Princesa City | 2013-08-15 | 1st | IVB | LF | 18.839 | 515 | 2012-05-17 | 2013-10-14 | -10.34 | O | 0.373 | 0.3 | 0.047 | 0.03 | 0.042 | 0.033 | 82.5 | -
A.R.T. DWELL LIFESTYLE STORE and ECO BUILDERS | 38284 | L | B | SB | GE | Rehab./Reconst./Upgrading of Damaged Paved National Road Including Drainage Based on Pavement Management System Highway Development & Management-4 (Intermittent Section), Angeles-Porac-Floridablanca-Dinalupihan Road at K0084+(-305) - K0084+122 | Angeles-Porac-Floridablanca-Dinalupihan Road at K0084+(-305) - K0084+122 | 2015-11-13 | Final | Pampanga Third DEO | LF | 5.855 | 75 | 2015-02-19 | 2015-05-05 | - | C | 0.458 | 0.133 | 0.3 | - | - | - | 89.1% | 89.1% Very Satisfactory
A.S.S. Construction | 31509 | L | D | MA | GB1 | Completion of ACA Building II |  | 05/14-15/09 | 1st | DOST |  | 9.631 | 210 |  |  |  | O | 0.38 | 0.296 | 0.15 | 0.03 | 0.062 | 0.05 | 96.8 | -
A.S.T. BUILDERS | 34104 | L | B | MA | GE | Widening of National Roads, Secondary Roads, R. Palma Street, Chainage 0 - Chainage 38, Chainage 0 - Chainage 379 | Cebu City | 2015-09-03 | 1st & Final | Cebu City | LF | 7.71 | 150 | 2015-02-20 | 2015-07-19 | 0% | C | 0.432 | 0.178 | 0.3 | - | - | - | 91% | *91% Very Satisfactory
A.T. DUMLAO CONSTRUCTION INC. | 34028 | L | B | MA | GE | Rehabilitation/Reconstruction of National Roads with Slips, Slope Collapse and Landslide along NRJ Cuevas-Bislig Road, K1378+327 - K1378+443 (RBIA Chainage), K1378+320 - K1378+450 (Survey), (S00464MN), Trento, Agusan del Sur) | Trento, Agusan del Sur | 2015-11-11 | 1st | Agusan del Sur 2nd DEO | LF | 25.2155 | 208 | 2015-06-24 | 2016-01-17 | (+) 11.11 | OG | 0.383 | 0.252 | 0.15 | 0.03 | 0.045 | 0.05 | 91% | 91% Very Satisfactory
A.T. DUMLAO CONSTRUCTION, INC. | 34028 | L | B | MA | GE | Construction/Widening of Adlayan Bridge Along Daang Maharlika (Agusan-Davao Section) (B00914MN) K1307+585-K1307+614.80 | San Francisco, Agusan Del Sur | 2015-08-25 | Final | Agusan del Sur 2nd | LF | 36.641 | 377 | 2015-02-20 | 2016-03-02 | 0% | C | 0.463 | 0.133 | 0.3 | - | - | - | 89.6% | *85.52% Satisfactory
A.T. Dumlao Construction, Inc. (Formerly: Andoni T. Dumalao Civil Engineer - Contractor) | 34028 | L | B | MA | GE | Construction/Widening of Adlayan Bridge along Daang Maharlika (Agusan - Davao Section) K1307+585 - K1307+614.8 | San Francisco, Agusan del Sur | 2014-08-08 | 1st | XIII | LF | 36.6501 | 196 | 2014-02-20 | 2014-09-03 | -9.08 | O | 0.4 | 0.24 | 0.06 | 0.03 | 0.065 | 0.033 | 82.8 | -
A.T. Dumlao Construction, Inc. (Formerly: Andoni T. Dumlao Civil Engineer-Contractor) | 34028 | L | B | MA | GE1 | Replacement of San Pedro Bridge along Daang Maharlika (Surigao-Agusan Rd.) Brgy. San Pedro | Alegria, Surigao del Norte | 2012-11-21 | 2nd | XIII | LF | 14.945 | 390 | 2012-01-13 | 2013-02-06 | -2.26 | O | 0.36 | 0.231 | 0.127 | 0.03 | 0.055 | 0.033 | 83.6 | -
A.T. Dumlao Construction, Inc. (Formerly: Andoni T. Dumlao Civil Engineer-Contractor) | 34028 | L | B | MA | GE | Replacement of Lengigon Bridge (Temporary to Permanent) along Argao - Moalboal Road, Municipality of Argao | Argao, Cebu | 2014-10-24 | 1st | VII | LF | 12.2302 | 270 | 2014-02-26 | 2014-11-22 | -44.15% | O | 0.4 | 0.3 | 0 | 0.03 | 0.055 | 0 | 78.5% | 78.50% Unsatisfactory
A.T. Dumlao Construction, Inc. (Formerly: Andoni T. Dumlao, Civil Engineer - Contractor) | 34028 | L | B | MA | GE1 | Reconst. of Timamana Bridge along Daang Maharlika Highway (Surigao-Agusan Rd.), Brgy. Timamana | Tubod, Surigao del Norte | 2013-03-14 | 1st | XIII | LF | 24.213 | 496 | 2011-12-16 | 2013-04-24 | 0.29 | O | 0.305 | 0.252 | 0.15 | 0.03 | 0.056 | 0.05 | 84.3 | -
A.T. DUMLAO CONSTRUCTION, INC. (Formerly: Andoni T. Dumlao, Civil Engineer - Contractor) | 34028 | L | B | MA | GE | Widening of Permanent Bridge (from 1 lane to 2 lane) at Sumaguan Bridge along Argao - Moalboal Road | Argao, Cebu | 2015-08-29 | 1st & Final | Cebu 4th | LF | 24.872 | 191 | 2015-02-27 | 2015-09-05 | 7% | C | 0.355 | 0.2 | 0.3 | - | - | - | 85.5% | *85.5% Satisfactory
A.T. Dumlao Construction, Inc. (Formerly: Andoni T. Dumlao, Civil Engineer-Contractor) | 34028 | L | B | MA | GE1 | Replacement of San Pedro Bridge along Daang Maharlika (Surigao-Agusan Rd.), Brgy. San Pedro | Alegria, Surigao del Norte | 2013-03-14 | 3rd | XIII | LF | 15.781 | 435 | 2012-01-13 | 2013-03-23 | 0.42 | O | 0.355 | 0.223 | 0.15 | 0.03 | 0.035 | 0.033 | 82.6 | -
A.T. Dumlao Construction, Inc. (Formerly: Andoni T. Dumlao, Civil Engineer-Contractor) | 34028 | L | B | MA | GE1 | Rehab./Reconst. of Hubang Bridge along Daang Maharlika (Agusan-Davao Rd.) Km.1307+369-Km.1307+536 | San Francisco, Agusan del Sur | 2013-03-09 | 1st | XIII | LF | 19.141 | 380 | 2012-01-27 | 2013-02-10 | - | O | 0.338 | 0.3 | 0 | 0.03 | 0.058 | 0.033 | 75.9 | -
A.T. DUMLAO CONSTRUCTION, INC. (Formerly: Andoni T. Dumlao, Civil Engineer-Contractor) | 34028 | L | B | LB | GE | Replacement of Lengigon Bridge( Temporary to Permanent) along Argao-Boalboal Road | Municipality of Argao, Cebu City | 2015-06-11 | Final | Cebu Fourth DEO | LF | 13.23 | 300 | 2014-02-26 | 2014-12-22 | 2% | C | 0.477 | 0.16 | 0.3 | - | - | - | 93.7% | *84.58% Satisfactory
A.V. CONSTRUCTION & SUPPLY (Formerly: A.V. Construction) | 13202 | L | B | MA | GB | Construction of Two (2) Storey, Two (2) Classroom School Building at Marcos E/S | San Marcos, San Pablo City | 2015-06-12 | Final | Laguna 3rd DEO | LF | 4.196 | 90 | 2015-01-14 | 2015-04-13 | 0% | C | 0.365 | 0.161 | 0.3 | - | - | - | 82.6% | *82.6% Satisfactory
A.V. CONSTRUCTION AND SUPPLY (Formerly: A.V. Construction) | 13202 | L | B | SB | GE | Concreting of Tiguion-Canaon-Talao Farm to Market Road | Gasan, Marinduque | 2015-11-16 | Final | Marinduque DEO | LF | 5.6981 | 85 | 2015-07-13 | 2015-10-05 | 0 | C | 0.449 | 0.133 | 0.3 | - | - | - | 88.2% | 88.2% Satisfactory
A.V.M. Construction and Supplies | 114114 |  |  |  |  | NHA Bayside Subdivision Housing Project | Brgy. Poblacion, Bislig City, Surigao del Sur | 2014-10-24 | 1st | NHA | L | 19.225 | 330 | 2013-10-04 | 2015-03-06 | 5.49 | O | 0.376 | 0.3 | 0.0951 | 0.03 | 0.0233 | 0.033 | 85.74 | -
A.Y.U. ENGINEERING AND CONSTRUCTION | 25632 | L | B | SB | GE | Improvement/Rehabilitation @ Quimpo Boulevard Ecowest Drive, Ecoland, Barangay Bucana, Brgy. 76-A, Davao City | Davao City | 2015-11-19 | Final | Davao City 1st DEO | LF | 9.66e-06 | 149 | 2015-05-16 | 2015-10-11 | 0 | C | 0.479 | 0.133 | 0.3 | - | - | - | 91.2% | 91.2% Very Satisfactory
AB Aponesto Construction, Parts & Supply | 22998 |  |  |  |  | Conc. of Lublub-Bolilac-Salad Road, Km.277+707.50-Km.278+711 |  | 2010-09-05 |  | VI |  | 14.425 | 192 |  |  |  | O | 0.356 | 0.24 | 0.15 | 0.03 | 0.042 | 0.033 | 85.1 | -
ABJ CONTRACTOR SERVICES | 35865 | L | D | SB | GE | Construction of Farm-to-Market Road, Guiwan, Zamboanga City | Zamboanga City | 2015-11-18 | Final | Zamboanga City DEO | LF | 2.8192 | 68 | 2015-04-06 | 2015-06-12 | - | C | 0.402 | 0.133 | 0.3 | - | - | - | 83.5% | 83.5% Satisfactory
Abulug Construction Company, Inc. | 5593 | L | B | MA | GE1 | Const. of Colony Road |  | 2008-11-13 | 1st | II |  | 2.894 | 120 |  |  |  | O | 0.329 | 0.24 | 0.1 | 0.03 | 0.033 | 0.1 | 83.2 | -
Abulug Developers & Builders Co., Inc. | 2366 | L | AAA | LB | GE1 | Reblocking along Manila North Road (Fugu Bdry.-Bangag Section) |  | 2009-05-21 | 1st | II |  | 19.299 | 210 |  |  |  | O | 0.368 | 0.24 | 0.15 | 0.03 | 0.051 | 0.033 | 87.2 | -
AC RIVERO DEVELOPMENT CORPORATION | 5122 | L | A | MB | GE | Const./Imprv't of Access Road to Sabsaban Falls & Eco Park | Aribungos, Brooke's Point, Palawan | 2015-11-10 | 1st | Palawan 2nd Deo | LF | 31.3446 | 172 | 2015-06-01 | 2015-11-19 | 0 | OG | 0.308 | 0.3 | 0.15 | 0.006 | 0.035 | 0.033 | 83.2% | 83.2% Satisfactory
AC Rivero Development Corporation (Formerly: AC Rivero Construction) | 5122 | L | A | MB | GE | Const. of Bridge at Dodiongan Box Culvert along Sta. Felomina-Bonbon-Digkilaan-Rogongon Road | Iligan City | 2014-10-29 | 1st | X | LF | 24.5674 | 295 | 2014-01-30 | 2014-11-20 | 7.27% | O | 0.339 | 0.278 | 0.15 | 0.01 | 0.051 | 0.05 | 87.8% | 87.80% Satisfactory
ACCELERATED METAL TECHNOLOGY & CONSTRUCTION, INC. (Formerly: A.M. Tumolva Construction and Development Corp.) | 32073 | L | AAA | SB | GB | Construction of Multi-Purpose Building at Delnacia Subd., Brgy. Talipapa, Quezon City | Brgy. Talipapa, Quezon City | 2015-08-25 | 1st & Final | QC 1st DEO | LF | 4.749 | 120 | 2015-02-24 | 2015-06-23 | 4.17% | C | 0.487 | 0.2 | 0.3 | - | - | - | 98.7% | *98.7% Outstanding
Accuracy Builders Enterprise | 27507 | L | B | MA | GE | Rehabilitation of Banaue Hotel Roofing | Banaue, Ifugao | 2014-01-13 | 1st | TIEZA | LF | 19.88 | 180 | 2013-06-19 | 2013-12-18 | -9.81 | S | 0.304 | 0.3 | 0.052 | 0.15 | 0.008 | 0.033 | 71.14 | -
ACJ Construction Resources | 10635 | L | B | MA | GE1 | Road Upgrading of Nat'l Rd. (Gravel to Concrete) Nat'l Secondary Rd., Km.1628+584-Km.1630+803 along Kidapawan-Magpet-Pangao-an Rd. | Magpet, Cotabato | 2011-08-17 | 1st | XII | LF | 24.178 | 180 | 2011-04-06 | 2011-10-03 | -34.26 | O | 0.342 | 0.3 | 0 | 0.03 | 0.045 | 0.033 | 75 | -
ACJ Construction Resources | 10635 | L | B | MB | GE1 | Conc. of Paco-Roxas-Arakan Road Kiyaab-Antipas Section (Km. 1648+300-Km.1649+385.63) |  | 2009-09-05 | 1st | XII |  | 16.826 | 150 |  |  |  | O | 0.324 | 0.3 | 0.15 | 0.015 | 0.042 | 0.05 | 88.1 | -
ACJ Construction Resources | 10635 | L | B | MA | GE1 | Concreting of Poblacion Magpet-Nowa Road (Nowa Basak Sect.) |  | 2009-03-10 | 1st | XII |  | 18.798 | 180 |  |  |  | O | 0.356 | 0.284 | 0.15 | 0.03 | 0.035 | 0.05 | #VALUE! | -
ACJ Construction Resources | 10635 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Conc.) Nat'l Secondary Rd., K1657+(-247)-K1659+824 along Paco-Roxas-Arakan Valley Rd. | Arakan, Cotabato | 2012-08-10 | 1st | XII | LF | 46.844 | 384 | 2011-08-11 | 2012-08-29 | 0.9 | O | 0.354 | 0.244 | 0.15 | 0.03 | 0.051 | 0.05 | 87.9 | -
Acme Builders Corporation | 6442 | L | A | MA | GE1 | Rd. Upgrading of Tigbao-Sta. Fe-San Miguel Rd., K0910+000-K0911+500 & K0913+000-K0913+900 | Tacloban City | 2013-08-22 | 1st | VIII | LF | 55.416 | 270 | 2013-02-27 | 2013-11-23 | 2.49 | O | 0.383 | 0.24 | 0.15 | 0.012 | 0.042 | 0.05 | 87.7 | -
Acme Builders Corporation | 6442 | L | A | MA | GE1 | Rehab./Strengthening of Rosales Bridge along Daang Maharlika (SM) (San Isidro-San Juanico Bridge) | Calbayog City, Samar | 2013-08-14 | 1st | VIII | LF | 25.251 | 165 | 2013-02-06 | 2013-08-16 | 3 | O | 0.393 | 0.242 | 0.15 | 0.03 | 0.06 | 0.033 | 90.8 | -
Acme Builders Corporation | 6442 |  |  |  |  | Rehab./Reconst./Impvt./Upgrading of Damaged Pavement, Tacloban Baybay South Rd. |  | 2010-06-17 |  | VIII |  | 34.6 | 150 |  |  |  | O | 0.366 | 0.3 | 0.15 | 0.03 | 0.032 | 0.033 | 91.1 | -
Acme Builders Corporation | 6442 | L | B | MA | GE1 | Construction of Bagacay Bridge |  | 2009-03-02 | 1st | VIII |  | 39.1221 | 332 |  |  |  | O | 0.319 | 0.288 | 0 | 0.03 | 0.023 | 0.05 | #VALUE! | -
Acme Builders Corporation / B. Vicencio Construction | JV-07-066 | L | A | MB | GE1 | Const. of Palo East By Pass Road (Const. of Bernard Reed II Bridge) |  | 2009-08-31 | 3rd | VIII |  | 57.823 | 616 |  |  |  | O | 0.384 | 0.24 | 0.15 | 0.03 | 0.047 | 0.033 | 88.4 | -
Acme Builders Corporation / MWJ Construction (JV) | JV-08-243 | L | A | MB | GE1 | Const. of Albuera-Burauen Road including Bridges, Burauen Sect. |  | 2009-09-02 | 1st | VIII |  | 47.235 | 240 |  |  |  | O | 0.352 | 0.245 | 0.15 | 0.03 | 0.045 | 0.05 | 87.2 | -
Adfil Corporation | 14437 | L | AA | LA | GE1 | Rehab./Reconst. of Damaged Paved National Roads Gingoog-Calveria-Villanueva Road |  | 2009-09-10 | 1st | X |  | 96.4 | 405 |  |  |  | O | 0.259 | 0.3 | 0.15 | 0.03 | 0.061 | 0.05 | 85 | -
Adfil Corporation | 14437 | L | AAA | MB | GE | Const./Improvement of Road to Support River Rhine Cruise leading to Banza Ruins, Barangay Banza | Brangay Banza, Butuan City | 2014-08-14 | 1st | XIII | LF | 26.7059 | 148 | 2014-04-25 | 2014-09-19 | 0.58 | O | 0.332 | 0.254 | 0.15 | 0.03 | 0.07 | 0.05 | 88.6 | -
Adfil Corporation | 14437 | L | AAA | MB | GE | Rehab./Reconstruction/Replacement/Retrofitting of Magsaysay Bridge along Butuan - Cagayan de Oro - Iligan (Agusan - Misamis Oriental) | Butuan City | 2014-08-15 | 1st | XIII | LF | 36.8434 | 234 | 2014-02-14 | 2014-10-05 | 12.89 | O | 0.384 | 0.234 | 0.15 | 0.03 | 0.047 | 0.05 | 89.5 | -
Adfil Corporation | 14437 | L | AAA | MB | GE | Construction of Agusan - Bukidnon Road, Sta. 1262+260 - Sta. 1265+120 | Buenavista, Agusan del Norte | 2014-08-05 | 1st | XIII | LF | 40.1405 | 209 | 2014-02-04 | 2014-09-01 | 0.51 | O | 0.36 | 0.264 | 0.15 | 0.03 | 0.037 | 0.05 | 89.1 | -
Adfil Corporation | 14437 |  |  |  |  | Repair/Maintenance with Asphalt Overlay of Tabon-Tabon Slip along Agusan- Davao Road |  | 2010-06-17 |  | XIII |  | 32.364 | 225 |  |  |  | O | 0.371 | 0.24 | 0.15 | 0.03 | 0.055 | 0.033 | 87.9 | -
Adfil Corporation | 14437 |  |  |  |  | Rehab. of Magsaysay Bridge along Iligan City |  | 2010-09-09 |  | XIII |  | 48.161 | 300 |  |  |  | O | 0.352 | 0.3 | 0.15 | 0.03 | 0.055 | 0.05 | 93.7 | -
Adfil Corporation | 14437 | L | AA | LA | GE1 | Rehab./Reconst. of Damaged Paved National Rd. along Butuan City-CDO-Iligan Rd.,(Agusan-Misamis Oriental Sect.)Libertad-Bancasi Sect. |  | 2009-09-16 | 1st | XIII |  | 54.954 | 285 |  |  |  | O | 0.371 | 0.3 | 0.15 | 0.03 | 0.055 | 0.05 | 95.6 | -
Adfil Corporation | 14437 | L | AA | LA | GB1 | Const./Completion/Continuation of Unfinished Bridge and Approaches, Brgy. Libertad |  | 2009-09-16 | 1st | XIII |  | 23.83 | 195 |  |  |  | O | 0.364 | 0.3 | 0.15 | 0.03 | 0.055 | 0.05 | 94.9 | -
Adfil Corporation | 14437 | L | AA | LA | GE1 | Concreting of NRJ-Bahbah-Talacogon Rd. |  | 2009-09-13 | 1st | XIII |  | 15.872 | 225 |  |  |  | O | 0.371 | 0.244 | 0.15 | 0.03 | 0.065 | 0.05 | 91 | -
Adfil Corporation (Formerly: Adfil Construction) | 14437 | L | AAA | MB | GE | Construction of Agusan-Bukidnon Road, Sta. 1262+260 - Sta. 1265+120 | Buenavista, Agusan del Norte | 2014-10-21 | 1st | XIII | LF | 40.1397 | 271 | 2014-02-04 | 2014-11-01 | 0.46% | O | 0.387 | 0.182 | 0.15 | 0.024 | 0.065 | 0.05 | 85.8% | 85.80% Satisfactory
Adfil Corporation (Formerly: Adfil Construction) | 14437 | L | AAA | MB | GE1 | Rehab./Reconst. of Ampayon Bridge along Daang Maharlika | Butuan City | 2013-08-23 | 2nd | XIII | LF | 19.207 | 219 | 2013-01-30 | 2013-09-05 | 1.87 | O | 0.397 | 0.24 | 0.15 | 0.018 | 0.04 | 0.05 | 89.5 | -
Adfil Corporation (Formerly: Adfil Construction) | 14437 | L | AAA | MB | GE1 | Widening/Conc. of Add'l. Lane Both Directions along Butuan City-Cagayan de Oro-Iligan Rd., K1249+461-K1253+310.50 | Buenavista, Agusan del Norte | 2013-08-06 | 1st | XIII | LF | 86.661 | 240 | 2013-03-25 | 2013-11-19 | 14.58 | O | 0.39 | 0.238 | 0.15 | 0.03 | 0.035 | 0.05 | 89.3 | -
Adfil Corporation (Formerly: Adfil Construction) | 14437 | L | AAA | MB | GE | Road Upgrading (Gravel to Paved) of Butuan City-Pianing-Tandag Road, K1237+055 - K1240+040, with exceptions | Butuan City | 2014-10-30 | 1st | XIII | LF | 127.2866 | 270 | 2014-05-15 | 2015-02-08 | 0.02% | O | 0.346 | 0.24 | 0.15 | 0.024 | 0.056 | 0.05 | 86.6% | 86.60% Satisfactory
Adfil Corporation (Formerly: Adfil Construction) | 14437 | L | AAA | MB | GE | Reconstruction/Replacement/Completion of Minusong Bridge along Butuan-Cagayan de Oro-Iligan Road (Agusan--Misamis Oriental), Km1269+217 | Agusan del Norte | 2014-10-21 | 1st | XIII | LF | 34.6274 | 270 | 2014-02-04 | 2014-10-30 | 0.05% | O | 0.343 | 0.286 | 0.15 | 0.03 | 0.065 | 0.05 | 92.4% | 92.40% Very Satisfactory
Adfil Corporation (Formerly: Adfil Construction) | 14437 | L | AAA | MB | GE | Rehab./Reconst./Replacement/Retrofitting of Salvacion Bridge along NRJ Cuevas - Bislig Road, K1374+670 - K1374+731 | Trento, Agusan del Sur | 2014-08-08 | 1st | XIII | LF | 36.6555 | 196 | 2014-02-18 | 2014-09-02 | 10.85 | O | 0.4 | 0.2 | 0.15 | 0.03 | 0.042 | 0.05 | 87.2 | -
Adfil Corporation (Formerly: Adfil Construction) | 14437 | L | AA | MB | GE1 | Rehab./Reconst./Upgrading of Butuan City-Cagayan de Oro-Iligan City Rd. a)K1494+049-K1495+240; b)K1499+692-K1499+712; c)K1500+678-K1500+902; d)K1501+905-K1507+000; e)K1508+000-K1508+919 | Misamis Oriental | 2013-03-12 | 2nd | X | LF | 48.167 | 285 | 2012-06-13 | 2013-03-24 | 3.06 | O | 0.293 | 0.271 | 0.15 | 0.01 | 0.05 | 0.05 | 82.4 | -
Adfil Corporation (Formerly: Adfil Construction) | 14437 | L | AA | MB | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rds., Butuan City-Cagayan de Oro City-Iligan City Rd.: a.)K1494+049-K1495+240; b.)K1499+692-K1499+712; c.)k1500+678-K1500+902; d.)K1501+905-K1507+000; e.)K1508+000-K1508+919 | Misamis Oriental | 2012-11-23 | 1st | X | LF | 44.537 | 255 | 2012-06-13 | 2013-02-23 | 7.85 | O | 0.332 | 0.3 | 0.15 | 0.03 | 0.04 | 0.05 | 90.2 | -
Adfil Corporation (Formerly: Adfil Construction) | 14437 | L | AAA | MB | GE1 | Rehab./Reconst. of Ampayon Bridge along Daang Maharlika | Butuan City | 2013-03-21 | 1st | XIII | LF | 18.426 | 171 | 2013-01-30 | 2013-07-19 | 11.89 | O | 0.39 | 0.3 | 0.15 | 0.03 | 0.054 | 0.033 | 95.7 | -
Adfil Corporation (Formerly: Adfil Construction) | 14437 | L | AAA | MB | GE1 | Widening/Conc. of Add'l Lane along Daang Maharlika (Agusan-Surigao Rd.) Cabadbaran City Sect., Sta.1213+540-Sta.1215+520 | Cabadbaran, Agusan del Norte | 2013-03-11 | 1st | XIII | LF | 29.059 | 142 | 2013-02-08 | 2013-06-29 | 24.99 | O | 0.365 | 0.3 | 0.15 | 0.03 | 0.05 | 0.033 | 92.8 | -
Adfil Corporation (Formerly: Adfil Construction) | 14437 | L | AAA | MB | GE1 | Completion of Maraput Bridge along Daang Maharlika (Surigao-Agusan Rd.), Sta.1207+192 | Tubay, Agusan del Norte | 2013-03-11 | 1st | XIII | LF | 9.115 | 120 | 2012-12-26 | 2013-04-24 | 21.54 | O | 0.348 | 0.3 | 0.15 | 0.03 | 0.037 | 0.033 | 89.8 | -
Adfil Corporation (Formerly: Adfil Construction) | 14437 | L | AAA | MB | GE1 | Const./Impv't of Rd. to Support River Rhine Cruise, Banza Ruins | Butuan City | 2013-03-21 | 1st | XIII | LF | 29.509 | 155 | 2013-01-30 | 2013-07-03 | 2.48 | O | 0.313 | 0.3 | 0.15 | 0.024 | 0.06 | 0.033 | 88 | -
Adfil Corporation (Formerly: Adfil Construction) | 14437 | L | AAA | MB | GE1 | Completion of La Union Bridge along Pandanon-Magallanes Rd. | Cabadbaran, Agusan del Norte | 2013-03-11 | 1st | XIII | LF | 15.889 | 150 | 2013-01-23 | 2013-06-21 | 37.3 | O | 0.312 | 0.3 | 0.15 | 0.02 | 0.047 | 0.033 | 86.2 | -
Adfil Corporation (Formerly: Adfil Construction) | 14437 | L | AA | MB | GE1 | Conc. of Agusan-Malaybalay Road, Km. 1283+183.50-Km.1284+780 | Esperanza, Agusan del Sur | 2012-03-31 | 1st | XIII | LF | 39.495 | 300 | 2011-08-26 | 2012-06-20 | 0.49 | O | 0.351 | 0.3 | 0.15 | 0.03 | 0.04 | 0.05 | 92.1 | -
Adfil Corporation (Formerly: Adfil Construction) | 14437 | L | AAA | MB | GE1 | Widening of Butuan-Cagayan de Oro-Iligan Rd. (Agusan-Misamis Oriental Sect.) Pob., Buenavista Sect. | Agusan del Norte | 2012-08-06 | 1st | XIII | LF | 24.129 | 255 | 2012-01-12 | 2012-09-22 | 0.77 | O | 0.336 | 0.296 | 0.15 | 0.03 | 0.055 | 0.033 | 90 | -
Adfil Corporation (Formerly: Adfil Construction) | 14437 | L | AAA | LA | GE2 | Rehab. of Salvacion (Crossing Luna Flood Control) | Esperanza, Agusan del Sur | 2012-08-20 | 1st | XIII | LF | 16.733 | 285 | 2012-03-07 | 2012-12-17 | 47.69 | O | 0.375 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 89.5 | -
Adfil Corporation (Formerly: Adfil Construction) | 14437 | L | AAA | MB | GE1 | Widening of Daang Maharlika (Agusan-Usrigao Rd.) Pob., Cabadbaran Sect. | Agusan del Norte | 2012-08-06 | 2nd | XIII | LF | 27.39 | 255 | 2012-01-12 | 2012-09-22 | 1.1 | O | 0.37 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 89 | -
Adfil Corporation (Formerly: Adfil Construction) | 14437 | L | AAA | MB | GE1 | Rehab./Reconst./Strengthening of Minusong Bridge along Butuan-Cagayan de Oro-Iligan (Agusan Misamis Oriental) Km.1269+217, Aclan, Nasipit | Agusan del Norte | 2012-08-06 | 2nd | XIII | LF | 28.848 | 270 | 2012-01-12 | 2012-10-22 | 3.53 | O | 0.383 | 0.246 | 0.15 | 0.03 | 0.045 | 0.033 | 88.7 | -
Adfil Corporation (Formerly: Adfil Construction) | 14437 | L | AAA | MB | GE1 | Rehab./Reconst./Strengthening of Minusuang Bridge along Daang Maharlika (Surigao-Agusan Rd.) Km.1206+561 | Tubay, Agusan del Norte | 2012-08-07 | 2nd | XIII | LF | 23.512 | 270 | 2012-01-11 | 2012-10-22 | 0.8 | O | 0.326 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 85.1 | -
Adfil Corporation (Formerly: Adfil Construction) | 14437 | L | AAA | MB | GE1 | Rehab./Reconst./Strengthening of Maraput Bridge along Daang Maharlika (Surigao-Agusan Rd.) Km.1207+192, Brgy. Victory | Tubay, Agusan del Norte | 2012-08-07 | 2nd | XIII | LF | 23.512 | 285 | 2012-01-12 | 2012-10-22 | 1.45 | O | 0.325 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 85 | -
ADFIL CORPORATION (Formerly: Adfil Construction) | 14437 | L | AAA | LA | GE | Construction/Upgrading of Banza to Magallanes Road leading to Centennial Tree and Beaches, Magallanes, Agusan del Norte | Magallanes, Agusan del Norte | 2015-11-19 | Final | Agusan del Norte DEO | LF | 37.2186 | 185 | 2015-03-10 | 2015-09-10 | (+) 0.54 | C | 0.403 | 0.2 | 0.3 | - | - | - | 90.3% | 90.3% Very Satisfactory
ADFIL CORPORATION (Formerly: Adfil Construction) | 14437 | L | AAA | LA | GE | Widening of Daang Maharlika (Agusan-Davao Section), K1304+(-404) - K1307-471, K1309+138.1 - K1312+810, San Francisco, Agusan del Sur | San Francisco, Agusan del Sur | 2015-11-11 | 1st | Regional Office | LF | 169.7987 | 300 | 2015-05-20 | 2016-03-14 | (+) 29.68 | OG | 0.257 | 0.3 | 0.15 | 0.03 | 0.065 | 0.033 | 83.5% | 83.5% Satisfactory
ADFIL CORPORATION (Formerly: Adfil Construction) | 14437 | L | AAA | LA | GE | Widening of Permanent Bridges to more than 2 lanes, Wawa Bridge (B00896MN) along Daang Maharlika (Agusan-Davao Road Section), Brgy. Wawa, Sibagat, Agusan del Sur | Brgy. Wawa, Sibagat, Agusan del Sur | 2015-11-09 | 1st | Regional Office | LF | 207.6948 | 340 | 2015-08-26 | 2016-07-30 | (+) 19.17 | OG | 0.317 | 0.24 | 0.15 | 0.03 | 0.055 | 0.033 | 82.5% | 82.5% Satisfactory
Adige Sta. Clara (JV) | JV-06-032 | L | AAA | LB | GE1 | DPWH Component Project under the Help for Catubig Agricultural Advancement Proj. |  | 2009-05-30 | 5th | VIII |  | 519.663 | 1073 |  |  |  | O | 0.378 | 0.3 | 0.15 | 0.03 | 0.05 | 0.05 | 95.8 | -
Adige Sta. Clara (JV) | JV-06-032 | FA/LF | AAA | LB | GE1 | DPWH Component Project under the HELP for Catubig Agricultural Project (HCAAP) |  | 2008-08-25 | 3rd | VIII |  | 448.581 | 734 |  |  |  | O | 0.377 | 0.3 | 0.07 | 0.03 | 0.05 | 0.067 | 89.4 | -
Adimre Construction | 25534 | L | B | MA |  | Taytay Airport Development Project | Taytay, Palawan | 07/22/15 | 1st | DOTC | LF | 10.794 | 154 | 02/27/15 | 2015-09-01 | -11.75 | O | 0.39 | 0.3 | 0.033 | 0.03 | 0.044 | 0.05 | 84.7 | -
Adimre Construction | 25534 | L | B | MA | GB-1 | Marinduque Airport Development Project | Gasan, Marinduque | 2015-08-07 | 1st | DOTC | LF | 6.293 | 120 | 2015-07-05 | 2015-11-01 | 27.87 | O | 0.384 | 0.3 | 0.15 | 0.015 | 0.035 | 0.05 | 93.4 | -
Adimre Construction | 25534 | L | B | SB | GE-5 | Balagtas Port Development Project | Balagtas, Bulacan | 2014-07-10 | 1st | DOTC | LF | 7.802 | 180 | 2014-03-13 | 2014-09-09 | 0.61 | O | 0.385 | 0.3 | 0.15 | 0.02 | 0.04 | 0.033 | 92.8 | -
Adimre Construction | 25534 | L | B | SB | GE-5 | Obando Port Development Project | Brgy. Paliwas & Bargy. Binuangan, Obando, Bulacan | 2014-08-18 | 1st | DOTC | LF | 8.109 | 194 | 2014-03-13 | 2014-10-22 | 7.73 | O | 0.3777 | 0.3 | 0.15 | 0.01 | 0.0155 | 0.0333 | 88.65 | -
Adimre Construction | 25534 | L | B | SB | GE-5 | Malolos Port Development Project | Brgy. Panasahan & Brgy. Namayan, Malolos, Bulacan | 2014-08-19 | 1st | DOTC | LF | 9.625 | 254 | 2014-03-12 | 2014-11-20 | 29.72 | O | 0.3969 | 0.3 | 0.15 | 0.01 | 0.0087 | 0.05 | 91.56 | -
Adimre Construction | 25534 | L | B | MA | GB1 | Const. of Three Storey Six CL Sch. Bldg. Tibagan NHS | Bustos, Bulacan | 2013-08-14 | 1st | III | LF | 7.027 | 180 | 2013-04-02 | 2013-09-28 | 3.82 | O | 0.326 | 0.24 | 0.15 | 0.03 | 0.047 | 0.033 | 82.6 | -
Adimre Construction | 25534 | L | B | SB | GE2 | Const. of Drainage Canal along Pulilan-Calumpit Rd., Pulilan Section Km. 46+000-Km. 47+200 | Pulilan, Bulacan | 2012-08-02 | 1st | III | LF | 11.886 | 170 | 2012-05-08 | 2012-10-24 | 1.71 | O | 0.376 | 0.283 | 0.15 | 0.022 | 0.06 | 0.05 | 94.1 | -
Adimre Construction | 25534 | L | B | SB | GE-5 | Meycauayan Port Development Project | Meycauayan, Bulacan | 2014-07-09 | 1st | DOTC | LF | 8.3 | 150 | 2014-03-12 | 2014-08-09 | 0.68 | O | 0.385 | 0.3 | 0.15 | 0.02 | 0.035 | 0.033 | 92.3 | -
ADIMRE CONSTRUCTION | 25534 |  | B | MA |  | Marinduque Airport Development Project | Gasan, Marinduque/ Region IV-B | 2015-11-12 | 2nd & Final | DOTC | LF | 6.293 | 120 | 2015-07-05 | 2015-11-01 | 0 | C | 0.4975 | 0.2 | 0.3 | - | - | - | 99.75 | 95.31% V. Satisfactory
ADIMRE CONSTRUCTION | 25534 |  | B | MA |  | Taytay Airport Development Project | Taytay, Palawan/ Region 4B | 2015-12-17 | 2nd & Final | DOTC | LF | 10.794 | 105 | 2015-04-01 | 2015-10-29 | 0 | C | 0.4404 | 0.2 | 0.3 | - | - | - | 94.04 | 88.43% Satisfactory
ADIMRE CONSTRUCTION | 25534 |  | B | MA |  | Puerto Princesa Airport Development Project | Puerto Princesa, Palawan/ Region 4B | 2016-03-29 | 1st | DOTC | LF | 64.553 | 420 | 2015-10-07 | 2016-11-29 | 4.24 | O | 0.3534 | 0.3 | 0.15 | 0.02 | 0.0389 | 0.05 | 91.23 | -
Adimre Construction | 25534 | L | B | MA |  | Puerto Princesa Airport Development Project | Puerto Princesa, Palawan/ Region 4B | 2016-09-20 | 2nd | DOTC | LF | 64.553 | 420 | 2015-10-07 | 2016-11-30 | -8.79 | O | 0.3962 | 0.3 | 0.0621 | 0.02 | 0.0389 | 0.0333 | 85.05 | -
ADP Construction & Supply | 3466 | L | A |  |  | Const. of Sta. Barbara Catching DAM and Canal Struc. | Legares, Iloilo | 2014-04-05 | 1st | NIA | LF | 16.962 | 150 | 2013-04-17 | 2014-04-30 | 0 | O | 0.327 | 0.245 | 0.15 | 0.018 | 0.032 | 0.05 | 82.2 | -
ADP Construction & Supply | 3466 | L |  |  | GE2 | Const. of Various CIP's Package 1 - Badbaran CIP | Badbaran CIP, Dumarao, Capiz | 2013-04-13 | 1st | NIA | LF | 24.77 | 210 | 2013-02-13 | 2013-09-22 | 26.15 | O | 0.348 | 0.249 | 0.15 | 0 | 0.027 | 0.05 | 82.4 | -
ADP CONSTRUCTION AND SUPPLY | 3466 | L | A | MB | GE | Construction of Juaneza-Aguirre-Malapaya Farm-to-Market Road (Sta. 0+000-Sta.4+000 with exceptions), Sara, Iloilo | Sara, Iloilo | 2015-11-14 | Final | Iloilo 3rd | LF | 47.7674 | 190 | 2015-05-11 | 2015-11-17 | 0.00% | C | 0.365 | 0.2 | 0.3 | - | - | - | 86.5% | 86.5% Satisfactory
ADP CONSTRUCTION AND SUPPLY | 3466 | L | A | MB | GE | Reconstruction/Improvement of Dumalag Municipal Road, Brgy. Poblacion, Dumalag, Capiz (Section I) | Brgy. Poblacion, Dumalag, Capiz (Section I) | 2015-11-13 | 1st | Capiz 2nd | LF | 35.9599 | 224 | 2015-07-02 | 2016-02-11 | 14.45% | OG | 0.366 | 0.232 | 0.15 | 0.03 | 0.07 | 0.05 | 89.8% | 89.8% Very Satisfactory
Advance Foundation Const. System Corp. / Abulug Developer Builders Const. Inc. (JV) | JV-09-289 | L | AAA | LB | GE1 | Const. of Gov. Edgar R. Lara Bridge along Cagayan-Apayao Road | Rizal, Cagayan | 2011-03-30 | 1st | II | LF | 112.029 | 240 | 2010-09-13 | 2011-05-10 | -63.6 | O | 0.36 | 0.3 | 0 | 0.023 | 0.051 | 0.017 | 75.1 | -
Advance Tech Construction & Trading Corp. | 35288 | L | B | SB | GE-5 | Cabucgayan Seaport Construction | Sitio Lakay, Brgy. Bunga, Cabuacgayan, Biliran | 2015-08-11 | 1st | DOTC | LF | 8.606 | 240 | 2015-04-29 | 2015-12-24 | 20.87 | O | 0.4 | 0.3 | 0.15 | 0.015 | 0.0292 | 0.05 | 94.42 | -
Advance Tech Construction & Trading Corp/ | 35288 | L | B | SB |  | Miag-ao Feeder Port Development | Miag-ao, Iloilo/ Region 6 | 2016-11-16 | 1st | DOTC | LF | 7.1615 | 120 | 2016-09-21 | 2017-01-18 | 1.09 | O | 0.4 | 0.3 | 0.15 | 0.02 | 0.0408 | 0.05 | 96.08 | -
Advance Tech Construction & Trading Corporation | 35288 |  | B | SB |  | Construction of Brgy. Iquiran Wharf | Brgy. Iquiran, Daram, Western Samar/ Region VIII | 2015-10-14 | 1st | DOTC | LF | 9.438 | 180 | 2015-06-03 | 2015-11-29 | 18.64 | O | 0.4 | 0.3 | 0.15 | 0.02 | 0.0175 | 0.05 | 93.75 | -
Advance Tech Construction & Trading Corporation | 35288 |  |  | SB |  | Construction of Iquiran Wharf | Brgy. Iquiran, Daram, Western Samar/ Region VIII | 2016-01-21 | 2nd & Final | DOTC | LF | 9.438 | 180 | 2015-06-03 | 2015-11-25 | 0 | C | 0.4915 | 0.2 | 0.3 | - | - | - | 99.15 | 95.91% V. Satisfactory
Advance Tech Construction & Trading Corporation | 35288 |  | B | SB |  | Cabucgayan Port Development Project | Brgy. Bunga, Canucgayan, Biliran | 2016-02-16 | 2nd & Final | DOTC | LF | 8.602 | 240 | 2015-04-29 | 2016-07-25 | 57.13 | C | 0.467 | 0.2 | 0.3 | - | - | - | 96.7 | 95.30% V. Satisfactory
ADVANCED FOUNDATION CONSTRUCTION SYSTEM CORP./PULSAR CONSTRUCTION (JV) | JV-13-601 | L | AAA | LB | GE | Construction and Maintenance of Bridges along National Roads-Construction of Bridges-On-going, Lucban Bridge along Manila North Road | Abulug, Cagayan Province | 2015-06-01 | 2nd | Regional Office No. I | LF | 278.183 | 674 | 2014-03-18 | 2016-01-20 | 16.94% | O | 0.398 | 0.3 | 0.15 | 0.024 | 0.05 | 0.033 | 95.5% | -
Advanced Foundation Construction System, Corp. | 15449 | L | AAA | LB | GE1 | Lucban Bridge & Approaches Phase I along Manila North Rd. | Abulug, Cagayan | 2013-08-01 | 1st | II | LF | 153.067 | 450 | 2013-03-26 | 2014-06-18 | 23.14 | O | 0.328 | 0.3 | 0.15 | 0.03 | 0.056 | 0.033 | 89.7 | -
Advanced Foundtaion Construction System Corp./Pulsar Construction(JV) | JV-13-601 | F | AAA | LB | GE | Construction and Maintenance of Bridges along National Roads - Construction of Bridges - On going; Lucban Bridge along Manila North Road | Abulug, Cagayan | 2014-10-22 | 1st | II | LF | 253.2675 | 650 | 2014-03-18 | 2015-12-27 | 23.35% | O | 0.456 | 0.225 | 0.15 | 0.03 | 0.033 | 0.033 | 92.7% | 92.70% Very Satisfactory
Advanced Matrix Construction Inc. | 32873 | L |  | MA |  | Structural Retrofitting of Buildings at PICC Phase 1 | PICC Complex, Pasay City | 2016-01-27 | Final | BSP | LF | 36.535 | 240 | 2013-12-18 | 2016-07-31 | 0 | C | 0.481 | 0.2 | 0.3 | - | - | - | 98.1 | 92.50% Very Satisfactory
Advanced Matrix Construction Inc. | 32873 | L |  | MA |  | Rehabilitation of Common Maintenance Shop (CMS) at BSP, SPC | Building A, SPC | 2016-01-27 | Final | BSP | LF | 19.053 | 188 | 2013-10-29 | 2014-10-01 | 6.02 | C | 0.466 | 0.2 | 0.119 | - | - | - | 78.5 | 86.90% Satisfactory
Advanced Matrix Construction Inc. | 32873 | L |  | MA |  | Full Upgrading of Toilets at PICC | PICC Complex, Pasay City | 2016-01-26 | Final | BSP | LF | 29.298 | 210 | 2014-02-20 | 2015-07-18 | 0 | C | 0.481 | 0.2 | 0.3 | - | - | - | 98.1 | 93.50% Very Satisfactory
Advanced Matrix Construction Inc. | 32873 | L |  | MA |  | New Roofing System for Building E Roofdeck | Security Plant Complex | 2016-03-02 | Final | BSP | LF | 23.296 | 321 | 2014-02-06 | 2014-12-23 | 3.54 | C | 0.469 | 0.2 | 0.194 | - | - | - | 86.3 | 84.30% Satisfactory
Advanced Matrix Construction Incorporated | 32873 | L | A |  |  | Rehabilitation of Building B Lighting System | BSP, Security Plant Complex, East Ave., Quezon City | 2013-10-08 | 1st | BPS | LF | 2 | 60 | 2013-03-26 | 2013-11-20 | 4.5 | O | 0.346 | 0.279 | 0.15 | 0.03 | 0.035 | 0.05 | 89 | -
Advanced Matrix Construction Incorporated | 32873 | L | A |  |  | Proposed Renovation of Executive Offices Located at 5th Floor, 5-Storey Building-Phase IV | 5th Flr. Five-Storey Bldg., BSP Head Office, Malate Manila | 2014-03-06 | 1st & Final | BSP | LF | 14.5 | 146 | 2013-11-07 | 2014-03-31 | 0 | C | 0.431 | 0.2 | 0.3 | - | - | - | 93.1 | *93.10% V. Satisfactory
Advanced Matrix Construction, Inc. | 32873 | L |  | MA |  | New Roofing System for Building E Roofdeck | Security Plant Complex | 2014-11-19 | 1st | BSP | L | 22.3 | 120 | 2014-02-06 | 2014-06-05 | 7.87 | O | 0.389 | 0.3 | 0.071 | 0.02 | 0.03 | 0.025 | 83.5 | -
Advanced Matrix Construction, Incorporated |  | L |  | MA |  | Improvement of BSP-SPC Parking Lot at BSP Security Plant Complex | BSP, Security Plant Complex, Cor BIR Road, East Ave., Quezon City | 2013-03-31 | 1st | BSP | LF | 13.8 | 180 | 2013-03-22 | 2013-09-07 | 0 | O | 0.399 | 0.19 | 0.15 | 0.03 | 0.051 | 0.05 | 87 | -
AEJ Hardware Construction & Enterprises | 34740 | L | D | SB | GE1 | Repair/Rehab. of Licomo Failed Rd. Shoulder along Maria Clara Lobregat Highway (Pagadian-ZC Rd.), K1851+500-K1851+600 | Zamboanga City | 2013-03-11 | 1st | IX | LF | 1.88 | 64 | 2013-02-26 | 2013-05-01 | -2.6 | O | 0.363 | 0.24 | 0.124 | 0.03 | 0.035 | 0.033 | 82.5 | -
AFG CONSTRUCTION AND SUPPLY | 17161 | L | A | SB | GB | Construction of Academic Building at: 6. Construction of 2-CL Alimanguan National High School, Brgy. Alimanguan, San Vicente, Palawan | Brgy. Alimanguan, San Vicente, Palawan | 2015-08-26 | 1st & Final | Palawan I DEO | LF | 1.712 | 120 | 2015-02-17 | 2015-06-16 | - | C | 0.485 | 0.167 | 0.3 | - | - | - | 95.2% | *95.2% Very Satisfactory
Agafer Construction | 7912 | L | B | SB | GE2 | Const. of Cagayan River Control |  | 2008-11-11 | 2nd | II |  | 14.241 | 240 |  |  |  | O | 0.318 | 0.16 | 0.03 | 0.03 | 0.033 | 0.133 | 70.4 | -
AGUERO CONSTRUCTION | 23338 | L | D | SB | GB | Cluster XII- Construction of Classrooms in Areas Experiencing Acute classroom Shortage in Lake Sebu, South Cotabato (1 Unit-2CL/1 Unit-3CL & 1 Unit-1CL) | 1. Upper Maculan NHS-Lake Sebu, NHS Annex, Lake Sebu (1-2CL/1-3CL) 2. Haliland ES, Lake SEBU (1CL) | 2015-06-02 | Final | South Cotabato DEO | LF | 4.808 | 210 | 2015-09-22 | 2016-04-19 | 7.53% | C | 0.45 | 0.133 | 0.3 | - | - | - | 88.3% | *88.3% Satisfactory
AGUINSOD GENERAL CONSTRUCTION | 34741 | L | B | SB | GE | Construction of Slope Protection/Retaining Wall along Pico-Lamtang Road, K0256+300 - K0256+420, K0258+163 - K0258+235, K0259+670 - K0259+700, K0260+665 - K0260+725, K0262+500 - K0262+585 | La Tridad, Benguet | 2015-06-02 | 1st | Benguet 1st DEO | LF | 8.292 | 120 | 2015-02-20 | 2015-06-19 | (+) 1.00% | O | 0.237 | 0.3 | 0.15 | 0.02 | 0.045 | 0.05 | 80.2% | -
AHMADI BUILDERS | 31752 | L | D | SB | GE | Construction of roads at Iligan City a) Purok 8, Upper Tominobo, Iligan City, b) Purok Mauswagon to Purok Pag-asa, Barangay Ditucalan, Iligan City, c) Purok 5, Barangay Sta. Elena, Iligan City | Iligan City | 2015-06-08 | Final | Lanao del Norte Second DEO | LF | 1.927 | 45 | 2015-02-20 | 2015-04-05 | - | C | 0.424 | 0.2 | 0.3 | - | - | - | 92.4% | *92.4% Very Satisfactory
Ahnex Builders & Ready Mix Corporation | 32296 | L | AAA | MA | GE1 | Widening of Cavite-Batangas Rd., Km.22+000-Km.23+653 | Imus, Cavite | 2012-11-23 | 1st | IVA | LF | 30.797 | 369 | 2012-02-07 | 2013-02-08 | -4.41 | O | 0.352 | 0.3 | 0.106 | 0.022 | 0.05 | 0.033 | 86.3 | -
Ahnex Builders & Ready Mix Corporation | 32296 | L | AAA | MA | GE1 | Widening of Governors Drive (Carmona-Dasmariñas-Trece Martires City Rd.) inc. Drainage System | G.M.A. and Carmona, Cavite | 2012-08-15 | 1st | IVA | LF | 38.813 | 190 | 2012-02-07 | 2012-08-14 | -6.91 | O | 0.366 | 0.3 | 0.081 | 0.03 | 0.055 | 0.033 | 86.5 | -
AJ TAYLAN CONSTRUCTION CORPORATION/DJCM CNSTRUCTION/ALTHEA CONSTRUCTION (JV) | JV-14-867 | L | B | MA | GE | Rehabilitation/Reconstruction of National Roads with Slips, Slope Collapse and Landslide, Batac-Pinili via Maipag Road, K0472+520, K0479+192, K0479+735, Batac, Ilocos Norte | Batac, Ilocos Norte | 2015-11-12 | Final | REGIONAL OFFICE | LF | 56.5365 | 242 | 2015-04-22 | 2015-12-19 | 0.2025 | C | 0.478 | 0.147 | 0.3 | - | - | - | 92.5% | 92.5% Very Satisfactory
AJ Tylan Const., Corp./DJCM Const/VVH Const., Corp./ZEDIK Builders (DAVZ JV) | JV-13-702 | L | A | MA | GE | Construction and Maintenance of Bridges along National Roads-Widening of Permanent Bridges, Subec Bridge along MNR | Pagudpud, Ilocos Norte | 2014-10-21 | 1st | I | LF | 36.7064 | 304 | 2014-05-09 | 2015-03-08 | 0.01% | O | 0.33 | 0.249 | 0.15 | 0.03 | 0.056 | 0.05 | 86.5% | 86.50% Satisfactory
Ajan Jaeda, inc. | 17869 | L | A | MB | GB1 | Corollary Works for Banquerohan Resettlement Project, Ph. 2 |  | 9/14-18/09 | 1st | NHA |  | 30.991 | 150 |  |  |  | O | 0.3975 | 0.245 | 0.015 | 0.024 | 0.07 | 0.05 | 80.15 | -
Ajan Jeada, Inc. | 17869 | L | A | MB | GE1 | Impv't. of Bahi-Cagubulacao Rd. (Cagraray Eco Park) | Bacacay, Albay | 2011-08-03 | 1st | V | LF | 18.989 | 221 | 2011-01-03 | 2011-08-11 | 0.63 | O | 0.317 | 0.3 | 0.15 | 0.03 | 0.045 | 0.033 | 87.5 | -
AJYSC Marketing | 26924 | L | A | MA | GE2 | Completion of Drainage Canal along Dulawan-Marbel Rd. (New Carment Sect.) | Tacurong City | 2013-03-11 | 3rd | XII | LF | 17.419 | 214 | 2012-05-19 | 2012-12-28 | - | O | 0.364 | 0.3 | 0 | 0.03 | 0.05 | 0.033 | 77.7 | -
AJYSC Marketing | 26924 |  |  |  |  | Const./Replacement of Banga Bridge and Approaches Phase II |  | 2010-03-08 |  | XII |  | 24.657 | 240 |  |  |  | O | 0.35 | 0.24 | 0.15 | 0.03 | 0.04 | 0.033 | 84.3 | -
AJYSC Marketing | 26924 | L | A | MA | GE2 | Rehab./Improvement of Bulok Bridge along Marbel-Makar Road |  | 2009-06-05 | 1st | R-XII |  | 4.764 | 90 |  |  |  | O | 0.271 | 0.3 | 0.15 | 0.03 | 0.059 | 0.05 | 86 | -
AJYSC Marketing | 26924 | L | A | MA | GE2 | Completion of Drainage Canal along Dulawan-Marbel Rd., New Carmen Sect. | Tacurong City | 2012-11-24 | 2nd | XII | LF | 17.419 | 214 | 2012-05-19 | 2012-12-28 | -4.81 | O | 0.359 | 0.3 | 0.102 | 0.03 | 0.055 | 0 | 84.6 | -
AJYSC Marketing | 26924 | L | A | MA | GE2 | Completion of Drainage Canal along Dulawqan-Marbel Rd. (New Carment Sect.) | Tacurong City, Sultan Kudarat | 2012-08-08 | 1st | XII | LF | 17.419 | 196 | 2012-05-29 | 2012-12-10 | -6.47 | O | 0.386 | 0.3 | 0.085 | 0.03 | 0.045 | 0.033 | 87.9 | -
AJYSC MARKETING | 26924 | L | A | MA | GE | Repair/Rehab./Improvement along Dulawan-Marbel Road (Griño- Tacurong Section) | Tacurong City | 2015-06-03 | Final | Sultan Kudarat 1st DEO | LF | 10.349 | 143 | 2014-10-14 | 2015-03-05 | 0.5% | C | 0.441 | 0.133 | 0.3 | - | - | - | 87.4% | *87.4% Satisfactory
AJYSC MARKETING | 26924 | L | A | MA | GE | Construction of Revetment at the Side of Damaged River Bank of Banga Bridge along Cotabato-Marbel Road | Banga, South Cotabato 2nd LD | 2015-06-02 | Final | South Cotabato DEO | LF | 5.798 | 150 | 2015-02-18 | 2015-07-18 | 32.59% | C | 0.398 | 0.133 | 0.3 | - | - | - | 83.1% | *83.1% Satisfactory
AJYSC MARKETING | 26924 | L | A | MA | GE | Midsayap-Marbel Road, K1777+409-K1780+1020 ( with exceptions), Luayan-Dumadalig Section, Tantangan, South Cotabato Modified to: MF01- Widening of Secondary Road-Midsayap-Marbel Road, K1777+353-K1779+553.16 ( with exceptions), Luayan-Dumadalig Section | Tantangan, South Cotabato | 2015-06-02 | 1st | South Cotabato DEO | LF | 43.944 | 174 | 2015-03-31 | 2015-09-20 | 15.05% | O | 0.358 | 0.24 | 0.15 | 0.03 | 0.02 | 0.033 | 83.1% | -
AJYSC MARKETING | 26924 | L | A | MA | GE | Midsayap-Marbel Road K1777+353 to K1779+553.16 with exception Luayan-Dumadalig Section, Tantangan South Cotabato, 2nd LD | Tantangan, South Cotabato | 2015-11-09 | 1st | South Cotabato First DEO | LF | 47.9577 | 234 | 2015-03-31 | 2015-11-19 | (+) 0.09% | OG | 0.36 | 0.248 | 0.15 | 0.03 | 0.042 | 0.05 | 88% | 88% Satisfactory
AJYSC MARKETING | 26924 | L | A | MA | GE | Construction and Namleaning of Bridges along National Roads- Widening of Permanent Bridges to more than 2 lanes, Bawing Bridge along Makar-Kiamba Road | General Santos City | 2015-11-18 | 1st | South Cotabato Second DEO | LF | 25.4812 | 176 | 2015-04-01 | 2015-10-12 | (-) 24.00% | OG | 0.346 | 0.3 | 0 | 0 | 0.023 | 0 | 66.9% | 66.9% Poor
AJYSC MARKETING | 26924 | L | A | MA | GE | Construction/Rehabilitation of Drainage Protection Works along National Roads - Nationwide: Construction of the Revetment along the Damaged Riverbank of Banga Bridge along Cotabato-Marbel Road | Banga, South Cotabato | 2015-09-02 | 1st & Final | South Cotabato | LF | 5.24 | 98 | 2015-01-22 | 2015-04-29 | (+)0.08% | C | 0.411 | 0.147 | 0.3 | - | - | - | 85.8% | *85.8% Satisfactory
AKH Construction and Trading Corporation | 20759 | L | A | MA | GE | Preventive Maintenance Based on Pavement Management System/Highway Development and Management-4 (HDM-4) along V. Mapa Street | Sta. Mesa, Manila | 2014-11-24 | 1st | NCR | LF | 22.598 | 206 | 2014-05-28 | 2014-12-19 | 0.17% | O | 0.381 | 0.24 | 0.15 | 0.03 | 0.045 | 0.033 | 87.9% | 87.90% Satisfactory
AKH Construction and Trading Corporation | 20759 | L | A | MA | GE | Proposed Repair/Rehab. Of Road along Jalandoni St., CCP Complex | Pasay City | 2014-08-17 | 1st | NCR | LF | 8.0997 | 90 | 2014-05-21 | 2014-08-18 | 14.3 | O | 0.446 | 0.215 | 0.15 | 0.03 | 0.04 | 0.03 | 91.1 | -
AKH Construction and Trading Corporation | 20759 | L | AAA | MB | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rd. (Int. Sect.) of Mendiola Extension (Chainage 0000-Chainage 0119, A) Prev. Maint. (Int. Sect.) of Mendiola (Chainage 0119-085) | Manila | 2013-03-13 | 1st | NCR | LF | 2.678 | 69 | 2013-02-20 | 2013-04-29 | 10.22 | O | 0.366 | 0.2 | 0.15 | 0.03 | 0.048 | 0.033 | 82.7 | -
AKH CONSTRUCTION AND TRADING CORPORATION | 20759 | L | A | MA | GE | Concrete Reblocking along commonwealth Ave., Quezon City, K0017+061 - K0020+(-262), K0016+938 - K0019+731, Quezon City | Quezon City | 2015-06-06 | 1st | NCR | LF | 17.988 | 273 | 2014-10-29 | 2015-07-28 | (+) 21.83 | O | 0.387 | 0.24 | 0.15 | 0.024 | 0.056 | 0.05 | 90.7% | -
AKH CONSTRUCTION AND TRADING CORPORATION | 20759 | L | A | MA | GE | Rehabilitation/Reconstruction/Upgrading of Damaged South Super Highway East Service Road, K13+890 to K16+793, Parañaque City | Parañaque City | 2015-09-03 | 1st | NCR | LF | 27.364 | 165 | 2015-05-15 | 2015-10-26 | 8.29% | O | 0.376 | 0.24 | 0.15 | 0.03 | 0.053 | 0.05 | 89.9% | -
AKN Construction Corporation (Formerly: AKN Construction) | 11845 | L | AAA | LB | GE | Slope Protection of Estero Tripa De Gallina, Barangay Bangkal | District I, Makati City, M.M. | 2014-11-19 | 1st | NCR | LF | 17.3213 | 150 | 2014-06-18 | 2014-11-14 | -9.07% | O | 0.357 | 0.3 | 0.059 | 0.03 | 0.049 | 0.05 | 84.5% | 84.50% Satisfactory
AKN Construction Corporation (Formerly: AKN Construction) | 11845 | L | AAA | MA | GE1 | Widening/Conc. of R-10 inc. ROW, (Const. of Footbridge at corner Pacheco) | Tondo, Manila | 2011-04-15 | 1st | NCR | LF | 17.977 | 248 | 2010-06-25 | 2011-02-27 | 1.67 | O | 0.371 | 0.296 | 0.15 | 0.03 | 0.035 | 0.05 | 93.2 | -
AKN Construction Corporation (Formerly: AKN Construction) | 11845 | L | AAA | MB | GE1 | Rehab./Reconstruction of Muntinlupa Insular Prison Road and its Vicinity, Brgy. Poblacion |  | 2009-09-09 | 1st | NCR |  | 19.113 | 100 |  |  |  | O | 0.297 | 0.219 | 0.15 | 0.023 | 0.035 | 0.05 | 77.4 | -
AKN CONSTRUCTION CORPORATION (Formerly: AKN Construction) | 11845 | L | AAA | LB | GE | Dredging of Marala River, (from C-3 to C-4), Sta. 1+400 to Sta. 2+750, Navotas City | Navotas City | 2015-06-06 | Final | NCR | LF | 50.541 | 120 | 2014-11-24 | 2015-03-24 | - | C | 0.48 | 0.2 | 0.3 | - | - | - | 98% | *98% Outstanding
AKN CONTRUCTION CORP. | 11845 | L | AAA | MA | GE | Dredging of Paranaque River Mouth (Phase I), Paranaque City, Metro Manila | Metro Manila | 2015-12-03 | 1st | Metro Manila 2nd DEO | LF | 86.1326 | 240 | 2015-05-12 | 2016-01-01 | (+)6.05% | OG | 0.4 | 0.2 | 0.05 | 0.036 | 0.25 | - | 93.6% | 93.6% Very Satisfactory
AL CHRIS CONSTRUCTION | 12406 | L | B | MA | GB | Health Facilities and Multi-Purpose Buildings (Cluster II) a) Construction of Public Market | Camayaan, Loboc, Bohol | 2015-08-27 | 1st & Final | Bohol | LF | 2.877 | 140 | 2015-04-14 | 2015-08-31 | 2.86% | C | 0.473 | 0.078 | 0.3 | - | - | - | 85.1% | *85.1% Satisfactory
AL Chris Construction | 12406 |  |  |  |  | BERRRP-Candumayao (Catigbian) - Cabanugan (San Isidro) rd. | Catigbian-San Isidro, Bohol | 2015-01-19 | 1st | Bohol | L | 8.874 | 209 | 2014-06-05 | 2015-01-14 | -0.59 | O | 0.338 | 0.3 | 0.066 | 0.03 | 0.051 | 0.05 | 83.5 | -
AL HUSSEIN CONSTRUCTION | 18438 | L | A | MA | GE | Rehabilitation/Reconstruction of National Road with Slips, Collapse and Landslides, Lanao del Norte Interior Circumferential Road (LDN1CR), K1536+610-K1536+750; K1544+120-K1544+725, Tagoloan, Lanao del Norte | K1536+610-K1536+750; K1544+120-K1544+725, Tagoloan, Lanao del Norte | 2015-09-03 | 1st | Lanao del Norte 1st DEO | LF | 44.744 | 205 | 2015-02-25 | 2015-09-17 | 0.34% | O | 0.384 | 0.24 | 0.15 | 0.03 | 0.06 | 0.05 | 91.4% | -
Al-B Construction | 11740 |  |  |  |  | Rehab./Reconst./Upgrading along Angeles-Porac-Floridablanca-Dinalupihan Rd. |  | 2010-06-01 |  | III |  | 18.839 | 90 |  |  |  | O | 0.389 | 0.24 | 0.15 | 0.03 | 0.047 | 0.033 | 88.9 | -
AL-B DEVELOPMENT CORP./PING-ANN'S CONSTRUCTION AND TRADING (JV) | JV-14-075 | L | A | MA | GE | Reconstruction of Loboc River Terminal | Loboc, Bohol | 2015-08-27 | Final | TIEZA | LF | 19.5 | 240 | 2014-11-04 | 2015-07-01 | 0 | C | 0.481 | 0.2 | 0.3 |  |  |  | 98.1 | 93.9% Very Satisfactory
AL-B DEVELOPMENT CORPORATION (Formerly ALB Construction) | 11740 | L | A | MA | GE | Network Development, Widening of National Roads, (Arterial Roads-Outside N1), Angeles-Porac-Floridablanca-Dinalupihan Road at KO084+(-615) to KO085+(-024), Angeles City, Pamapanga 1st LD | Angeles City, Pamapanga 1st LD | 2015-08-29 | 1st | Pampanga Third DEO | LF | 34.069 | 210 | 2015-04-29 | 2015-11-24 | 1.9% | O | 0.379 | 0.24 | 0.15 | 0.03 | 0.07 | 0.05 | 91.9% | -
AL-B Dev't Corp./ Ping-Ann's Construction and Trading (JV) | JV-14-075 | L | A | MA | GE | Reconstruction of Loboc River Terminal | Loboc, Bohol | 2015-06-24 | 1st | TIEZA | LF | 19.55 | 240 | 2014-11-04 | 2015-07-01 | -5.35 | O | 0.3745 | 0.3 | 0.0965 | 0.03 | 0.07 | 0.05 | 92.1 | -
ALBERTO UY CONSTRUCTION & DEVELOPMENT | 20924 | L | B | MA | GE | Rehabilitation/Upgrading of Mapang (Taas) Formon Road, Bongabong, Oriental Mindoro | Bongabong, Oriental Mindoro | 2015-08-28 | 1st | Southern Mindoro DEO | LF | 14.477 | 149 | 2015-04-07 | 2015-09-02 | 1.64% | O | 0.368 | 0.24 | 0.15 | 0.03 | 0.057 | 0.05 | 89.5% | -
ALBERTO UY CONSTRUCTION & DEVELOPMENT | 20924 | L | B | MA | GE | Rehab./Upgrading of Mapang Road (Taas) Formon Road | Bongabong, Oriental Mindoro | 2015-11-19 | Final | Southern Mindoro DEO | LF | 14.4768 | 149 | 2015-04-07 | 2015-09-02 | 0.1147 | C | 0.471 | 0.133 | 0.3 | - | - | - | 90.4% | 90.4% Very Satisfactory
Alcel Construction | 15129 | L | A | MA | GE | Road Upgrading (Gravel-Paved) Along Gurel-Bokod-Kabayan-Buguias-Abatan Road, K0338+481-K0339+838, Kabayan, Benguet | Kabayan, Benguet | 2014-08-14 | 1st | CAR | LF | 46.4607 | 240 | 2014-01-31 | 2014-09-27 | 0.13 | O | 0.361 | 0.24 | 0.15 | 0.023 | 0.05 | 0.05 | 87.4 | -
Alcel Construction | 15129 | L | A | MA | GE1 | Const. of Access Rd. to Airport, Alaminos City Airport | Alaminos, Pangasinan | 2013-03-15 | 1st | I | LF | 1.821 | 45 | 2013-02-22 | 2013-04-07 | 18.23 | O | 0.39 | 0.3 | 0.15 | 0.01 | 0.023 | 0.033 | 90.6 | -
Alcel Construction | 15129 | L | A | MA | GE1 | Const. of Access Rd. for Alaminos Airport (Phase I) | Alaminos City, Pangasinan | 2012-08-16 | 1st | I | LF | 17.991 | 253 | 2011-12-13 | 2012-08-21 | 6.64 | O | 0.384 | 0.24 | 0.15 | 0.03 | 0.045 | 0.033 | 88.2 | -
ALCEL CONSTRUCTION | 15129 | L | A | MB | GE | Rehabilitation/Improvement of Gurel - Bokod - Kabayan - Buguias - Abatan Road Including ROW, Bokod and Kabayan Section, K0301+(-797) - K0326+004 (I.S.) | Bokod and Kabayan, Benguet | 2015-02-26 | Final | CAR | LF | 97 | 403 | 2013-01-15 | 2014-02-21 | 0% | C | 0.392 | 0.2 | 0.3 | - | - | - | 89.2% | *89.2% Very Satisfactory
ALCEL CONSTRUCTION | 15129 | L | A | MB | GE | Rehabilitation/Reconstruction/Upgrading of Alaminos-Bolinao Road, K0325+000 to K0326+000, K0321+(-204) to K0323+133, Alaminos City, Pangasinan | K0325+000 to K0326+000, K0321+(-204) to K0323+133, Alaminos City, Pangasinan | 2015-09-01 | 1st | Pangasinan 1st DEO | LF | 43.823 | 240 | 2015-05-22 | 2016-01-17 | (+)29.75 | O | 0.331 | 0.3 | 0.15 | 0.023 | 0.042 | 0.05 | 89.6% | -
ALCEL CONSTRUCTION | 15129 | L | A | MB | GE | Construction of Road (Baywalk) Brgy. Libsong East, Lingayen to Baybay Lopez, Binmaley, Pangasinan | Binmaley, Pangasinan | 2015-11-19 | Final | PANGASINAN 2ND DEO | LF | 28.8118 | 180 | 2015-08-28 | 2016-02-23 | - | C | 0.376 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 89.6% | 89.6% Very Satisfactory
Alcel Construction/Oriental Sales Center and Contractor (J.V.) | JV-12-432 | L | A | MA | GE1 | Prev. Maint. of Manila North Rd. K0169+700-K0172+105 w/ exception w/n the District | Carmen, Rosales, Pangasinan | 2013-08-09 | 1st | I | LF | 34.285 | 150 | 2013-03-27 | 2013-08-23 | 0.44 | O | 0.345 | 0.3 | 0.15 | 0.03 | 0.047 | 0.033 | 90.5 | -
Alebon Genuine Merchandising | 26300 | L | B | MA | GE | Widening of Butuan City - Cagayan de Oro City - Ilagan City Road Km1425+500 - Km.1426+500 | Cagayan de Oro City | 2014-08-04 | 1st | X | LF | 18.5783 | 191 | 2014-01-31 | 2014-08-10 | 0 | O | 0.383 | 0.3 | 0.15 | 0.03 | 0.04 | 0.05 | 95.3 | -
Alebon Genuine Merchandising | 26300 | L | B | SB | GE | Construction of Concrete Revetment along Kinoguitan By-Pass Road | Brgy. Poblacion, Kinoguitan, Misamis Oriental | 2014-08-11 | 1st | X | LF | 13.4816 | 210 | 2014-01-20 | 2014-08-17 | 0.18 | O | 0.383 | 0.3 | 0.15 | 0.03 | 0.047 | 0.033 | 94.3 | -
Alebon Genuine Merchandising | 26300 | L | B | MA | GE1 | Widening of Carmen-Patag-Bulua Rd., Bulua-Patag Sect. | Cagayan de Oro City | 2013-03-11 | 1st | X | LF | 4.198 | 37 | 2013-01-15 | 2013-02-20 | 6.52 | O | 0.371 | 0.244 | 0.15 | 0.01 | 0.037 | 0.05 | 86.2 | -
ALEBON GENUINE MERCHANDISING | 26300 | L | B | MA | GE | Rehab/Reconst/Upgrading of Damaged Paved National Roads Including Drainage Based on Pavement Management System/Highway Development and Management-4 (HDM-4) (Intermittent Section) CDO-Cadre Circumferential Ext., Rd., Chainage 0-556.00, Cagayan de Oro City | CDO-Cadre Circumferential Ext., Rd., Chainage 0-556.00, Cagayan de Oro City | 2015-06-11 | 1st | Cagayan de Oro City First DEO | LF | 8.865 | 170 | 2015-02-09 | 2015-07-28 | - | O | 0.353 | 0.3 | 0.15 | 0.02 | 0.025 | 0.05 | 89.8% | -
Al-Fahdel Const. and Eng'g | 17953 | L | B | MA | GE1 | Conc./Impvt. of Tubod-Ganassi Road (Caniogan Sect.) Sta. 1602+000-Sta. 1603+000 with exception |  | 2009-06-05 | 1st | X |  | 18.126 | 150 |  |  |  | O | 0.344 | 0.265 | 0.15 | 0.015 | 0.043 | 0.05 | 86.7 | -
Al-Fahdel Const. and Eng'g. | 17953 | L | B | MA | GE1 | Repair/Rehab. of Rd. Slip (down) along Dobleston-Butadon Nat'l Rd. (Secondary Rd.), K2007+860-K2007+900 | Butadon, Kapatagan, Lanao del Norte | 2012-11-28 | 1st | X | LF | 3.79 | 59 | 2012-10-04 | 2012-12-01 | 0.23 | O | 0.363 | 0.226 | 0.15 | 0.03 | 0.023 | 0.033 | 82.5 | -
Alfalfa Construction | 29712 | L | B | MA | GE1 | Road Upgrading of Banaue-Hungduan Benguet Bdry. Road Hapao-Abatan Section | Hungduan, Ifugao | 2011-04-08 | 1st | CAR | LF | 16.56 | 177 | 2011-01-20 | 2011-07-02 | -6 | O | 0.385 | 0.3 | 0.09 | 0.01 | 0.054 | 0.017 | 85.6 | -
Alfie's Const. & Const. Supply, Inc. (Formerly: Alfie's Construction & Const. Supply) | 17162 | L | A | MB | GE1 | Completion of Binalbagan Bridge 2 - Km. 66+910 along Hinigaran-Isabela Road |  | 2009-03-05 | 4th | VI |  | 45.049 | 809 |  |  |  | O | 0.316 | 0.3 | 0.15 | 0.03 | 0.04 | 0.033 | #VALUE! | -
Alfie's Const. & Const. Supply, Inc. (Formerly: Alfie's Construction & Const. Supply) | 17162 | L | A | MB | GE1 | Road Upgrading, Jct. Palencia-Boy Scout, Campsite Road |  | 2009-03-05 | 2nd | VI |  | 66.624 | 553 |  |  |  | O | 0.263 | 0.296 | 0.15 | 0.03 | 0.05 | 0.033 | #VALUE! | -
Alfie's Construction & Const. Supply, Inc. (Formerly: Alfie's Construction & Construction Supply) | 17162 | L | A | MB | GE1 | Const. of Access Rd. for Himoga-an Bridge, Bacolod North Rd., Sta. 71+035.20-Sta. 74+557.20 | Sagay City, Negros Occidental | 2013-08-12 | 1st | VI | LF | 109.29 | 310 | 2013-01-15 | 2013-11-20 | 10.51 | O | 0.342 | 0.24 | 0.15 | 0.03 | 0.042 | 0.05 | 85.4 | -
Alfie's Construction & Const. Supply, Inc. (Formerly: Alfie's Construction & Construction Supply) | 17162 | L | A | MB | GE1 | Road Upgrading of Villahermoso-Canla-on City-La Castellana Road, K0074+205-K0074+995 | La Castellana, Negros Occidental | 2013-08-10 | 1st | VI | LF | 23.131 | 182 | 2013-01-28 | 2013-07-28 | -3.18 | O | 0.356 | 0.206 | 0.047 | 0.03 | 0.035 | 0.033 | 70.7 | -
Alfie's Construction & Construction Supply Inc. (Formerly: Alfie's Construction and Construction Supply) | 17162 | L | A | MB | GE1 | Conc. of Nat'l Rd. along Bacolod South Rd., K0086+061-K0088+003 | Kabankalan City, Negros Occidental | 2012-08-11 | 1st | VI | LF | 32.631 | 222 | 2012-01-27 | 2012-09-04 | 0.31 | O | 0.242 | 0.3 | 0.15 | 0.03 | 0.05 | 0.05 | 82.2 | -
Alfie's Construction & Construction Supply Inc. (Formerly: Alfie's Construction and Construction Supply) | 17162 | L | A | MB | GE | Road Upgrading (Gravel to Paved) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standard (HDM-4 Project Analysis - Intermittent Sections) National Secondary Road, Kabankalan Jct. Salong Tapi Dacongcogon Bantayan Road - Package B | Kabankalan City, Negros Occidental | 2014-10-24 | 1st | VI | LF | 48.4607 | 209 | 2014-05-29 | 2014-12-23 |  | O | 0.361 | 0.232 | 0.15 | 0.03 | 0.048 | 0.033 | 85.4% | 0% Poor
Alfies Construction & Construction Supply, Inc. | 17162 | L | A | MB | GE1 | Conc. of Junction Bearin-Salong-Tapi-Dacongcogon-Bantayan Raod (Km. 99+675.50-Km.131+142.75 w/ exception, Brgy. Salong & Batayan |  | 2009-09-17 | 2nd | VI |  | 79.4 | 400 |  |  |  | O | 0.304 | 0.3 | 0.15 | 0.03 | 0.035 | 0.033 | 85.2 | -
ALFIE'S CONSTRUCTION & CONSTRUCTION SUPPLY, INC. (Formerly: Alfie's Construction & Construction Supply) | 17162 | L | A | MB | GE | Rehabilitation/Reconstruction/Upgrading of Bacolod North Road, | K0086+000 - K0087+000, K0087+540 - K0088+327, K0088+362 - K0090+933 | 2015-08-25 | 1st | Regional Office No.VI | LF | 65.069 | 250 | 2015-03-11 | 2015-11-15 | 17.6% | O | 0.357 | 0.24 | 0.15 | 0.03 | 0.06 | 0.05 | 88.7% | -
ALFIE'S CONSTRUCTION & CONSTRUCTION SUPPLY, INC. (Formerly: Alfie's Construction & Construction Supply) | 17162 | L | A | MB | GE | Construction/Replacement of Permanent Weak Bridges along National Road, Tapi Bridge (B00211NR), along Kabankalan Jct. Salong Tapi Dacongcogon Bantayan Road, Brgy. Tapi, Kabankalan City, Negros Occidental | Brgy. Tapi, Kabankalan City, Negros Occidental | 2015-11-14 | 1st | Negros Occidental 3rd DEO | LF | 10.094 | 286 | 2015-02-26 | 2015-12-08 | (+)11.0% | OG | 0.363 | 0.241 | 0.15 | 0.03 | 0.045 | 0.05 | 87.9% | 87.9% Satisfactory
ALFIE'S CONSTRUCTION & CONSTRUCTION SUPPLY, INC. (Formerly: Alfie's Construction & Construction Supply) | 17162 | L | A | MB | GE | Widening of National Roads along Bacolod South Road, K0048+542-K0051+468; K0052+444-K0053+600; K0064+250-K0065+360, Hinigaran, Negros Occidental | Hinigaran, Negros Occidental | 2015-11-16 | 1st | Regional Office, NIR | LF | 119.1023 | 310 | 2015-05-20 | 2016-03-24 | (+)7.18% | OG | 0.373 | 0.238 | 0.15 | 0.03 | 0.055 | 0.05 | 89.6% | 89.6% Very Satisfactory
ALFIE'S CONSTRUCTION & CONSTRUCTION SUPPLY, INC. (Formerly: Alfie's Construction & Construction Supply) | 17162 | L | A | MB | GE | Widening of Bacolod Circumferential Road (South) with Drainage (including RROW), K0006+451 - K0011+476, Bacolod City, Negros Occidental | Bacolod City, Negros Occidental | 2015-11-09 | 1st | Regional Office, NIR | LF | 81.4428 | 255 | 2015-03-16 | 2015-11-25 | (-)7.23% | OG | 0.337 | 0.3 | 0.078 | 0.03 | 0.06 | 0.033 | 83.8% | 83.8% Satisfactory
ALFIE'S CONSTRUCTION & CONSTRUCTION SUPPLY, INC. (Formerly: Alfie's Construction & Construction Supply) | 17162 | L | A | MB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Road along Bacolod North Road, K0039+771-K0040+288; K0061+420-K0062+000; K0075+903-K0075+953; K0076+620-K0077+000; K0080+060-K0081+000; K0081+558-K0082+000; K0082+000-K0083+000; K0036+902-K0036+952; K0038+200-K0038+406; K0041+843-K0042+300; K0042+500-K0043+000, Manapla, Negros Occidental | Manapla, Negros Occidental | 2015-11-19 | 1st | Regional Office, NIR | LF | 75.6255 | 265 | 2015-04-08 | 2015-12-28 | (+)0.75% | OG | 0.34 | 0.214 | 0.15 | 0.03 | 0.055 | 0.05 | 83.9% | 83.9% Satisfactory
ALFIE'S CONSTRUCTION & CONSTRUCTION SUPPLY, INC. (Formerly: Alfie's Construction & Construction Supply) | 17162 | L | A | MB | GE | Rehabilitation/Reconstruction/Upgrading of Bacolod North Road, K0086+000 - K0087+000, K0087+540 - K0088+327, K0088+362 - K0090+933, Sagay City, Negros Occidental | Sagay City, Negros Occidental | 2015-11-19 | 1st | Regional Office, NIR | LF | 68.4997 | 280 | 2015-03-11 | 2015-12-15 | (+)0.04% | OG | 0.371 | 0.237 | 0.15 | 0.03 | 0.055 | 0.05 | 89.3% | 89.3% Very Satisfactory
Alfie's Construction & Construction Supply, Inc. (Formerly: Alfie's Construction & Construction Supply) | 17162 | L | A | MB | GE1 | Const. of the Remaining Structures: Himogaan Bridge, Sta. 71+035.20-Sta. 74+557.20 | Sagay City, Negros Occidental | 2013-08-12 | 1st | VI | LF | 116.246 | 505 | 2012-05-14 | 2013-09-30 | 0.66 | O | 0.376 | 0.24 | 0.15 | 0.03 | 0.042 | 0.05 | 88.8 | -
ALFREDO D. SANTOS CONSTRUCTION | 36902 | L | D | SB | GB | Construction of Academic Building Mabuanbuan Elementary School, Mabuanbuan, Sasmuan, Pampanga | Sasmuan, Pampanga | 2015-06-03 | Final | Pampanga 2nd DEO | LF | 1.898 | 90 | 2014-10-10 | 2015-01-07 | 0% | C | 0.445 | 0.198 | 0.3 | - | - | - | 94.3% | *94.3% Very Satisfactory
Alfrego Builders & Supply | 19284 | L | D | SB | GE2 | Improvement/Riprapping of Sasa Creek Second Congressional District |  | 2009-06-11 | 1st | XI |  | 4.72 | 150 |  |  |  | O | 0.343 | 0.3 | 0.15 | 0.03 | 0.047 | 0.05 | 92 | -
ALFREGO BUILDERS & SUPPLY | 19284 | L | D | SB | GE | Concreting of Roads, Davao City 2nd LD Package 19, a. Concreting of Road, Brgy. San Isidro, b. Concreting of Orad, Brgy. Acacia, c. Concreting of Road, Brgy. Tigatto, 2nd LD, Davao City | Davao City | 2015-11-18 | Final | Davao City 1st DEO | LF | 8.731e-06 | 88 | 2015-05-25 | 2015-08-20 | 0 | C | 0.411 | 0.133 | 0.3 | - | - | - | 84.4% | 84.4% Satisfactory
Algamon Construction | 30704 | L | C | SB | GE2 | Protection Works along Daang Maharlika, (Surigao-Ipil-Lipata Rd.) Kinabutan Bridge II, Brgy. Rizal | Surigao City | 2012-11-21 | 1st | XIII | LF | 4.735 | 120 | 2012-08-16 | 2012-12-13 | -7.9 | O | 0.395 | 0.268 | 0.071 | 0.02 | 0.045 | 0.017 | 81.6 | -
ALGAMON CONSTRUCTION | 30704 | L | B | MA | GE | Rehabilitation/Reconstruction of National Roads with Slip, Slope Collapse and Land Slide Along Dinagat-Loreto Road | Dinagat-Loreto Road, San Jose, Province of Dinagat Islands | 2015-08-31 | 2nd | Dinagat Island | LF | 6.385 | 180 | 2015-03-20 | 2015-09-15 | (+) 0.17% | O | 0.366 | 0.234 | 0.15 | 0.03 | 0.046 | 0.05 | 87.6% | -
ALGAMON CONSTRUCTION | 30704 | L | B | SB | GE | Rehabilitation/Reconstruction of National Roads with Slip, Slope Collapse and Land Slide along Dinagat-Loreto Road, San Jose, Province of Dinagat Islands | San Jose, Province of Dinagat Islands | 2015-11-16 | Final | Dinagat Island DEO | LF | 6.3851 | 180 | 2015-03-20 | 2015-09-15 | - | C | 0.452 | 0.19 | 0.3 | - | - | - | 94.2% | 90.24% Very Satisfactory
ALGAMON CONSTRUCTION | 30704 | L | B | MA | GE | Rehabilitation/ Reconstruction of National Roads with Slip, Slope Collapse and Land Slide along Dinagat - Loreto Road | San Jose, Province of Dinagat Islands | 2015-06-11 | 1st | DINAGAT ISLANDS DEO | LF | 6.385 | 180 | 2015-03-20 | 2015-09-15 | (+) 0.92% | O | 0.366 | 0.234 | 0.15 | 0.03 | 0.045 | 0.033 | 85.8% | -
Algimar Construction | 15232 | L | AA | MB | GE | Road Upgrading ( Gravel to Paved) Quezon-Aramaywan Road, K0154+950-K0156+851.20 with Exception | Quezon, Palawan | 2014-11-22 | 1st | IV | LF | 34.9578 | 209 | 2014-05-28 | 2014-12-22 | -2% | O | 0.36 | 0.24 | 0.13 | 0.03 | 0.054 | 0.05 | 86.4% | 86.40% Satisfactory
Algimar Construction | 15232 | L | A | MA | GE1 | Conc. of Tablas Circumferential Road (Doña Juana-Binunga-an Section) |  | 2009-08-27 | 1st | IVB |  | 19.652 | 180 |  |  |  | O | 0.319 | 0.291 | 0.15 | 0.03 | 0.047 | 0.033 | 87 | -
Algimar Construction | 15232 | L | A | MA | GE1 | Concreting of Tablas Circumferential Road (Hinugasan-Camantaya Section) |  | 2009-05-21 | 1st | IV-B |  | 19.298 | 180 |  |  |  | O | 0.312 | 0.236 | 0.15 | 0.03 | 0.04 | 0.033 | 80.1 | -
Algimar Construction | 15232 | L | A | MA | GE1 | Repair of Damaged Rd. Sect. along Looc-Odiongan-San Andres Rd., Km.104+400-Km.122+400 (IS) | Tablas Island, Romblon | 2012-11-29 | 1st | IVB | LF | 15.86 | 210 | 2012-09-20 | 2013-04-17 | 26.67 | O | 0.306 | 0.291 | 0.15 | 0.03 | 0.04 | 0.033 | 85 | -
Algimar Construction | 15232 | L | A | SB | GB1 | Const. of 1 Unit 7x7 S/B at Teofilo Tamabago E/S, Palanas South realigned to Dimasalang C/S |  | 2009-05-26 | 1st | V |  | 0.843 | 90 |  |  |  | O | 0.292 | 0.3 | 0.15 | 0.03 | 0.032 | 0.033 | 83.7 | -
Algimar Construction | 15232 | L | A | MA | GE1 | Const. of Bridge Approaches @ Maingaran Bridge |  | 2009-02-27 | 1st | V |  | 9.495 | 87 |  |  |  | O | 0.337 | 0.235 | 0 | 0.03 | 0.056 | 0.033 | #VALUE! | -
ALGIMAR CONSTRUCTION | 15232 | L | AA | MB | GE | Road Upgrading (Unpaved to Paved) of Tablas Circumferential Road, K0029+765-K0029+990, K0112+196.60-K00112+281, K0115+190-K0115+219, K0115+392-K0115+838, K0116+300-K0116+674, Re-aligned to Road Upgrading (Unpaved to Paved) of Tablas Circumferential Road, K0029+765-K0029+990, K0115+090-K0115+219, K0115+392-K0115+838, K0116+300-K0116+674. | Tablas Island, Romblon | 2015-06-12 | 1st | Romblon DEO | LF | 29.682 | 145 | 2015-04-15 | 2015-09-06 | 0% | O | 0.381 | 0.24 | 0.15 | 0.03 | 0.051 | 0.05 | 90.2% | -
ALGIMAR CONSTRUCTION | 15232 | L | AA | MB | GE | Road Upgrading Based on Gravel Road Strategies Traffic Benchmark for Upgrading to Paved Road Standard | San Fernando, Masbate | 2015-06-11 | 1st | Masbate 3rd | LF | 37.877 | 178 | 2015-03-09 | 2015-09-06 | 3.5% | O | 0.352 | 0.253 | 0.15 | 0.018 | 0.051 | 0.05 | 87.4% | -
ALGIMAR CONSTRUCTION | 15232 | L | AA | MB | GE | Road Upgrading(Gravel to Paved) Based on Gravel Road Strategies Traffic Benchmark for Upgrading to Paved Road Standard (HDM-4 Project Analysis) San Fernando-Talisay Road, San Fernando, Masbate | San Fernando, Masbate | 2015-09-03 | 2nd | Masbate Third DEO | LF | 37.877 | 200 | 2015-03-11 | 2015-09-26 | 0.21% | O | 0.321 | 0.281 | 0.15 | 0.03 | 0.06 | 0.05 | 89.2% | -
Algimar Construction | 15232 | L | A | MA | GE1 | Upgrading of Balud-Tawad-Milagros-Aroroy Road (Bangad Sect.) | Masbate | 2011-08-09 | 1st | V | LF | 96.1 | 360 | 2010-11-23 | 2011-11-17 | 17.47 | O | 0.382 | 0.237 | 0.15 | 0.03 | 0.061 | 0.033 | 89.3 | -
Algon Engineering Construction Corp. | 270 | L | AAA | LB | GB1 | Construction of Overhead Water Tank with Cistern |  | 2009-04-29 | Final | DOST |  | 3.153 | 124 |  |  |  | O | 0.373 | 0.291 | 0.12 | 0.03 | 0.07 | 0.05 | 93.4 | -
Algon Engineering Construction Corporation | 270 | L | AAA | LB | GE1 | Widening of Davao-Bukidnon Rd., Davao City, Tugbok-Mintal Sect., Km.1693+400-Km.1697+335.40 | Davao City | 2013-08-07 | 1st | XI | LF | 46.965 | 209 | 2013-02-26 | 2013-09-22 | -0.69 | O | 0.352 | 0.298 | 0.143 | 0.03 | 0.025 | 0.033 | 88.1 | -
Algon Engineering Construction Corporation | 270 | L | AAA | LB | GE1 | Prev. Maint. (Int. Sects.) along Pres. Diosdado Macapagal Highway, a)Km.1712+000-Km.1712+802.90; b)Km.1713+303-Km.1713+815.64 | Davao Oriental | 2013-03-20 | 1st | XI | LF | 24.973 | 52 | 2013-01-25 | 2013-03-17 | 7.83 | O | 0.319 | 0.299 | 0.15 | 0.03 | 0.04 | 0.05 | 88.8 | -
Algon Engineering Construction Corporation | 270 | L | AAA | LB | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rd. along Davao-Cotabato Rd. (Davao City-Jct. Digos) Sta.1556+000-Sta.1561+249 | Davao del Sur | 2012-03-24 | 1st | XI | LF | 46.285 | 249 | 2011-07-21 | 2012-03-25 | -4.97 | O | 0.36 | 0.3 | 0.1 | 0.03 | 0.041 | 0.033 | 86.4 | -
Algon Engineering Construction Corporation | 270 | L | AAA | LB | GE1 | Widening of Davao-Bukidnon Rd. | Davao City | 2012-08-17 | 1st | XI | LF | 36.342 | 210 | 2012-01-31 | 2012-08-27 | -0.29 | O | 0.379 | 0.213 | 0.147 | 0.03 | 0.055 | 0.033 | 85.7 | -
Algon Engineering Construction Corporation | 270 | L | AAA | LB | GE1 | Conc. of NRJ Bayugan-Calaitan-Tandag Rd. (Km.1273+491.80-Km.1281+040 w/ exception) | Bayugan, Agusan del Sur | 2013-03-20 | 2nd | XIII | LF | 159.496 | 495 | 2011-12-26 | 2013-05-03 | 4.25 | O | 0.312 | 0.3 | 0.15 | 0.03 | 0.051 | 0.05 | 89.3 | -
Algon Engineering Construction Corporation | 270 | L | AAA | LB | GE1 | Conc. of NRJ Bayugan-Lalaitan-Tandag Rd. Km. 1273+491.80-Km. 1281+040 (w/ exceptions) | Bayugan, Agusan del Sur | 2012-11-29 | 1st | XIII | LF | 159.496 | 435 | 2011-12-26 | 2013-03-04 | 12.5 | O | 0.332 | 0.289 | 0.15 | 0.03 | 0.06 | 0.05 | 91.1 | -
Allado Construction Company, Inc. | 073-667 | L | AAA |  | GE1 | Rehabilitation of Jct Sayre Highway (Kibawe) - Natulongan - Bukangliwayway Footbridge P1C | Kibawe Bukidnon/X | 2011-11-23 | 1st | Bukidnon | LF | 19.145 | 226 | 2011-04-05 | 2012-01-16 | -5.65 | O | 0.31 | 0.29 | 0.09 | 0.03 | 0.06 | 0.05 | 83 | -
ALLEN CONSTRUCTION | 12584 | L | B | SB | GE | Peñaranda River Control, Burgos Section, San Leonardo, Nueva Ecija 4th LD | San Leonardo, Nueva Ecija 4th LD | 2015-09-01 | 1st & Final | Nueva Ecija Second DEO | LF | 4.719 | 90 | 2015-03-02 | 2015-05-30 | - | C | 0.407 | 0.133 | 0.3 | - | - | - | 84% | *84% Satisfactory
Allen Construction | 12584 | L |  | SB | GE2 | Restoration of Embankment @ D-Main & Const. of Thresher Crossing with Turn-out @ Div II Service Area | Talavera, Nueva Ecija | 2012-07-21 | 1st | NIA | LF | 8.653 | 90 |  | 2012-07-11 | 8.8 | O | 0.3575 | 0.2929 | 0.15 | 0.03 | 0.0573 | 0.05 | 93.77 | -
Allencon Development Corporation | 12302 | L | D | SB | GE2 | Const. of Coastal Protection Works along Iloilo-Antique Rd. K0026+700-K0027+151 | Guimbal, Iloilo | 2013-08-14 | 1st | VI | LF | 7.301 | 244 | 2012-12-28 | 2013-08-28 | 0.48 | O | 0.269 | 0.3 | 0.15 | 0.03 | 0.037 | 0.05 | 83.6 | -
Allencon Development Corporation | 12302 | L | D | SB | GE1 | Reconst. of Cabasi Bridge along Iloilo-Antique Rd., Km.30+534 | Guimbal, Iloilo | 2012-08-14 | 1st | VI | LF | 4.978 | 240 | 2012-01-20 | 2012-09-15 | 1.68 | O | 0.279 | 0.3 | 0.15 | 0.03 | 0.04 | 0.05 | 84.9 | -
Alleyway Construction | 15310 | L | A | MA | GE | Construction/Repair/Rehabilitation/Improvement of Various Infrastructure including Local Projects-Construction/Rehabilitation of various Projects in Manila City 2nd LD - Rehabilitation with Drainage Improvement of Torres Bugallon St. And Vicinity | Manila City 2nd Legislative District | 2014-11-24 | 1st | NCR | LF | 9.0986 | 120 | 2014-09-09 | 2015-01-06 | 13.4% | O | 0.365 | 0.229 | 0.15 | 0.03 | 0.045 | 0.033 | 85.2% | 85.20% Satisfactory
ALLEYWAY CONSTRUCTION | 15310 | L | A | MA | GE | Construction/Maintenance of Flood Mitigation Structures and Drainage System (RCBC) along Raxabago Chainage 285.00 to Chainage 504.00, Tondo, Manila City 2nd LD | Tondo, Manila | 2015-06-11 | 1st | North Manila DEO | LF | 33.638 | 200 | 2015-03-20 | 2015-10-05 | (-) 4.40 | O | 0.37 | 0.24 | 0.106 | 0.012 | 0.06 | 0.033 | 82.1% | -
ALLEYWAY CONSTRUCTION | 15310 | L | A | MA | GE | Const/Repair/Rehab/Improvement of Various Infrastructure Including Local Projects - Const/Rehab of Various Projects in Manila City 2nd LD - Rehab with Drainage Improvement of Raxabago St., District II, Manila | District II, Manila | 2015-09-01 | 1st & Final | NM DEO | LF | 19.6 | 223 | 2014-10-06 | 2015-05-16 | 0% | C | 0.477 | 0.133 | 0.3 | - | - | - | 91% | *91% Very Satisfactory
Allied Trade Resources Multi-Purpose Cooperative | 31667 | L | B | MA | GB1 | DOTC CARAGA Regional Office Development Project | Capitol Drive, Butuan City | 2013-08-27 | 1st | DOTC | L | 10.258 | 180 | 2013-04-22 | 2013-10-18 | 38.26 | O | 0.3886 | 0.3 | 0.15 | 0.015 | 0.0035 | 0.05 | 90.71 | -
Allied Trade Resources Multi-Purpose Cooperative | 31667 | L | B | MA | GB1 | PATIN-AY LTO District Office Development Project | Patin-ay, Prosperidad, Agusan del Sur | 2013-08-28 | 1st | DOTC | L | 5.147 | 180 | 2013-04-08 | 2013-10-04 | 2.99 | O | 0.3914 | 0.24 | 0.15 | 0.015 | 0.03 | 0.05 | 87.64 | -
Almakar Builders and Metal Works | 21929 | L | C | SB | GB1 | Const. of MPB in Poblacion I-A | Imus, Cavite | 2012-11-23 | 1st | IVA | LF | 0.681 | 135 | 2012-07-18 | 2012-11-29 | 1.2 | O | 0.342 | 0.3 | 0.15 | 0.02 | 0.041 | 0.033 | 88.6 | -
ALMAKAR BUILDERS AND METAL WORKS | 21929 | L | B | SB | GB | Construction of Health Center, Molino III | Bacoor City, Cavite | 2015-06-13 | Final | Cavite 1st DEO | LF | 1.424 | 60 | 2014-10-17 | 2014-12-15 | 0% | C | 0.462 | 0.133 | 0.3 | - | - | - | 89.5% | *89.5% Very Satisfactory
ALPHA RYDER CONSTRUCTION AND SUPPLIES | 12197 | L | A | MA | GE | Rehab./Reconst./Upgrading of Jct. Donsol-Banuang Gurang Road, Donsol, Sorsogon | Donsol, Sorsogon | 2015-11-19 | Final | Sorsogon First DEO | LF | 46.648 | 270 | 2015-02-03 | 2015-11-01 | 1.970% | C | 0.396 | 0.136 | 0.3 | - | - | - | 83.2% | 83.2% Satisfactory
Alraf Construction & Enterprises | 17297 | L | AAA | MB | GE1 | Settled/Collapsed PCCP along Maria Clara L. Lobregat H-way (Pagadian ZC Road) w/n Km.1867+000 to K1868+000, Mangusu Sect. | Zamboanga City | 2013-03-12 | 1st | IX | LF | 2.514 | 78 | 2013-02-22 | 2013-05-11 | -0.6 | O | 0.4 | 0.24 | 0.144 | 0.03 | 0.038 | 0.033 | 88.5 | -
Alraf Construction & Enterprises | 17297 | L | AAA | LA | GE1 | Rehab./Const./Impvt. of Zamboanga City-Pagadian Road |  | 2009-05-26 | 2nd | IX |  | 44.695 | 253 |  |  |  | O | 0.396 | 0.3 | 0.15 | 0.03 | 0.042 | 0.05 | 96.8 | -
Alraf Construction & Enterprises | 17297 | L | AAA | LA | GE1 | Rehab./Const./Impvt. of Zambaonga City-Pagadian Road (with Intermittent Section) |  | 2009-09-02 | 3rd | IX |  | 46.408 | 295 |  |  |  | O | 0.338 | 0.3 | 0.15 | 0.03 | 0.055 | 0.05 | 92.3 | -
Alraf Construction & Enterprises | 17297 | L | AAA | MB | GE1 | Upgrading/Concrete Paving of Nat'l Rd. along Liloy-Siocon Rd., Kipit-La Libertad-Loay-Imelda San Roque Sect. | Zamboanga del Norte | 2012-11-27 | 1st | IX | LF | 64.478 | 244 | 2012-04-10 | 2012-12-09 | -0.5 | O | 0.264 | 0.3 | 0.145 | 0.03 | 0.059 | 0.033 | 83.1 | -
ALRAF CONSTRUCTION & ENTERPRISES | 17297 | L | AAA | MA | GE | Construction/Upgrading/Rehabilitation of Drainage along National Roads pagadian-Zamboanga City Road, K1929+700-K1932+540 (Boalan-Dvisoria-Putik Section), Zamboanga City | Zamboanga City | 2015-09-03 | 1st | Zamboanga City | LF | 16.984 | 218 | 2015-06-22 | 2016-01-25 | (+)0.31% | O | 0.351 | 0.24 | 0.15 | 0.03 | 0.054 | 0.05 | 87.5% | -
ALRAF CONSTRUCTION & ENTERPRISES | 17297 | L | AAA | MB | GE | Widening of National Roads along Pagadian-City-Zamboanga City Road, Manicahan-Cabaluay-Culianan Section, K1916+560-K1923+396.70, Zamboanga City | K1916+560-K1923+396.70, Zamboanga City | 2015-08-24 | 1st | Regional Office No. IX | LF | 148.858 | 280 | 2015-04-20 | 2016-01-25 | (+)7.42 | O | 0.354 | 0.24 | 0.15 | 0.022 | 0.056 | 0.05 | 87.2% | -
Alro Construction & Development Corporation | 18361 | L | A | MA | GE1 | Guicadale Rd. Network to Int'l Airport, Albay (Comun-Cotmon-Del Rosario Rd. Sect.) | Camalig, Albay | 2013-08-11 | 1st | V | LF | 46.044 | 215 | 2013-02-06 | 2013-09-08 | 4.9 | O | 0.362 | 0.245 | 0.15 | 0.03 | 0.052 | 0.033 | 87.2 | -
ALRO CONSTRUCTION & DEVELOPMENT CORPORATION | 18361 | L | A | MB | GE | Camarines Sur-Albay Diversion Road, San Fernando-Oas-Daraga Section of the PAN Philippine Highway Including Bridges-Camarines Sur Section, Upgrading of Bula-Nabua (ACC-PCCP) Including Slope Protection, Bula, Camarines Sur | Bula, Camarines Sur | 2015-09-05 | 1st | Regional Office No. V | LF | 92.618 | 196 | 2015-06-24 | 2016-01-05 | 1.06% | O | 0.391 | 0.24 | 0.15 | 0.03 | 0.06 | 0.05 | 92.1% | -
Al's Enterprise and Construction | 9721 | L | A | MA | GB1 | Const./Rehab. of Hospital (Felipe Abrigo Memorial Hospital) |  | 2009-03-17 | 2nd | VIII |  | 4.775 | 151 |  |  |  | O | 0.349 | 0.24 | 0 | 0.01 | 0 | 0 | #VALUE! | -
Alta Negros Industrial Supply Corporation | 33806 | L | C | SB | GE1 | Repair/Rehab. of Lacson Street | Bacolod City | 2012-08-13 | 1st | VI | LF | 6.465 | 145 | 2012-04-10 | 2012-09-01 | 3.89 | O | 0.332 | 0.297 | 0.15 | 0.015 | 0.029 | 0.033 | 85.6 | -
ALXM CONSTRUCTION | 33436 | L | B | MA | GE | Construction of Flood Control Structure along Danlog River | Brgy. San Isidro, Barcelona, Sorsogon | 2015-06-10 | 1st | Sorsogon 2nd | LF | 21.347 | 171 | 2015-02-16 | 2015-08-05 | -3.84% | O | 0.379 | 0.3 | 0.112 | 0.03 | 0.06 | 0.05 | 93.1% | -
ALXM CONSTRUCTION | 33436 | L | A | MA | GE | Construction of Flood Control Structure along Danlog River, Brgy. San Isidro, Barcelona, Sorsogon | Brgy. San Isidro, Barcelona, Sorsogon | 2015-09-02 | 1st & Final | Sorsogon Second | LF | 21.347 | 171 | 2015-02-16 | 2015-08-05 | - | C | 0.385 | 0.18 | 0.3 | - | - | - | 86.5% | *86.5% Satisfactory
Alzam Enterprises | 19113 | L | A | MA | GE1 | Rd. Upgrading (Gravel/Asphalt to Concrete) of Mintal (Davao-Bukidnon Rd.) Bago Oshiro-Bago Gallera (Old Davao-Cotabato Rd.) | Davao City | 2013-08-21 | 1st | XI | LF | 72.933 | 269 | 2013-03-06 | 2013-11-29 | -2.68 | O | 0.374 | 0.3 | 0.123 | 0.03 | 0.025 | 0.03 | 88.2 | -
Alzam Enterprises | 19113 | L | A | MA | GE1 | Widening of Davao-Cotabato Rd., Davao City, Lizada Sect., Km.1525+920-Km.1527+800 | Toril District, Davao City | 2013-08-05 | 1st | XI | LF | 37.443 | 179 | 2013-02-26 | 2013-08-23 | -0.29 | O | 0.343 | 0.292 | 0.147 | 0.03 | 0.025 | 0.033 | 87 | -
Alzam Enterprises | 19113 | L | A | MA | GE2 | Const. of Davao River Control Proj. | Davao City | 2013-03-21 | 1st | XI | LF | 22.942 | 221 | 2012-12-02 | 2013-07-10 | 39.3 | O | 0.377 | 0.24 | 0.15 | 0.02 | 0.045 | 0.05 | 88.2 | -
Alzam Enterprises | 19113 | L | A | MA | GE1 | Rd. Upgrading (Gravel to Paved) of Inawayan-Baracatan Rd., Km.1538+770-Km.1539+110 | Toril, Davao City | 2013-03-12 | 1st | XI | LF | 6.854 | 55 | 2013-01-22 | 2013-03-17 | 0 | O | 0.269 | 0.235 | 0.15 | 0.03 | 0.045 | 0.05 | 77.9 | -
Alzam Enterprises | 19113 | L | A | MA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rds. (IS)/ Imprv't./Widening of Davao-Bukidnon Rd. leading to Phil. Eagle Foundation, Km.1698+780-Km.1701+828 | Davao City | 2012-08-21 | 1st | XI | LF | 45.68 | 250 | 2012-01-25 | 2012-09-30 | 1.46 | O | 0.387 | 0.221 | 0.15 | 0.03 | 0.055 | 0.033 | 87.6 | -
Alzam Enterprises | 19113 | L | A | MA | GE1 | Widening of Davao-Cotabato Rd. | Davao City | 2012-08-21 | 1st | XI | LF | 43.791 | 250 | 2012-01-24 | 2012-09-29 | 6.06 | O | 0.292 | 0.287 | 0.15 | 0.03 | 0.045 | 0.05 | 85.4 | -
ALZEN ENGINEERING AND CONSTRUCTION SUPPLY | 13911 | L | A | MB | GB | Construction of Multi-Purpose Bldg. at Brgy. Birada | Birada, Kidapawan City | 2015-11-11 | Final | Cotabato First DEO | LF | 1.9581 | 85 | 2015-03-06 | 2015-05-29 | 0.00% | C | 0.399 | 0.16 | 0.3 | - | - | - | 85.9% | 85.9% Satisfactory
AMMAR CONSTRUCTION AND ENTERPRISES | 35325 | L | B | SB | GB | Construction of 2-Storey 6-Classroom School Building at Binuni-Demologan NHS, Bacolod, Lanao del Norte | Bacolod, Lanao del Norte | 2015-11-17 | 1st | Lanao del Norte 2nd | LF | 8.1859 | 150 | 2015-08-25 | 2016-01-22 | (+) 8.00% | OG | 0.386 | 0.24 | 0.15 | 0.03 | 0.047 | 0.05 | 90.3% | 90.3% Very Satisfactory
Andoni T. Dumlao Civil Engineer - Contractor | 34028 | L | B | MA | GE1 | Replacement of San Pedro Bridge along Daang Maharlika (Surigao-Agusan Rd.), Brgy. San Pedro | Alegria, Surigao del Norte | 2012-08-08 | 1st | XIII | LF | 14.945 | 375 | 2012-01-13 | 2013-01-22 | 1.71 | O | 0.328 | 0.29 | 0.15 | 0.03 | 0.06 | 0.05 | 90.8 | -
Andoni T. Dumlao Civil Engineer - Contractor | 34028 | L | B | MA | GE1 | Repair/Reconst. Of Boan Bridge along Daang Maharlika (Agusan-Davao Rd.) Km.1331+632-Km.1380+775 w/ exceptions | Rosario, Agusan del Sur | 2012-08-18 | 1st | XIII | LF | 12.163 | 240 | 2012-01-27 | 2012-09-24 | 1.25 | O | 0.312 | 0.262 | 0.15 | 0.03 | 0.05 | 0.033 | 83.7 | -
ANGEL & SAM CONST. & GENERAL MERCHANDISE | 19968 | L | B | MA | GB | Construction of 1 Storey, 3 Classroom & 1 Storey 2 Classroom School Building, Impasug-ong CES, Impasug-ong, Bukidnon | Impasug-ong, Bukidnon | 2015-08-28 | 2nd | Bukidnon 1st DEO | LF | 4.056 | 90 | 2015-01-12 | 2015-04-11 | -5% | C | 0.476 | 0.2 | 0.15 | - | - | - | 82.6% | -
Angel & Sam Construction & General Merchandise | 19968 | L | B | MA | GB | Const. of 2 units, 1 Storey, 1 Classroom School Building, Aglayan ES | Aglayan, Malaybalay City | 2014-10-24 | 1st | X | LF | 2.0215 | 105 | 2014-07-28 | 2014-11-09 | 0.35% | O | 0.25 | 0.278 | 0.15 | 0.01 | 0.016 | 0.033 | 73.7% | 73.70% Poor
Angel & Sam Construction & General Merchandise | 19968 | L | B | MA | GE1 | Rehab. of ICBR Puerto-Cugman Section |  | 2009-03-02 | 1st | X |  | 13.912 | 198 |  |  |  | O | 0.298 | 0.24 | 0.144 | 0.03 | 0.04 | 0.05 | #VALUE! | -
ANIMAS BROS CONSTRUCTION | 35002 | L | B | SB | GE | Asset Preservation of National Roads, Rehab./Reconst./Upgrading of Damaged Paved National Roads including Drainage Based on Pavement Management System/Highway Dev't and Management-4 (HDM-4)(Intermittent Sections) Rizal - Dakak - Dapitan Coastal Loop Road, Rehab./Reconst. K1800+347 to K1800+461, Zamboanga del Norte | Zamboanga del Norte | 2015-06-05 | Final | Zamboanga del Norte 3rd DEO | LF | 2.161 | 76 | 2015-02-24 | 2015-05-09 | 0% | C | 0.458 | 0.131 | 0.3 | - | - | - | 88.9% | *88.9% Satisfactory
ANIMAS BROS CONSTRUCTION | 35002 | L | B | SB | GE | Repair/Rehabilitation and Construction/Concreting of Farm-to-Market Road, Calilic-Marapong, Sibutad, Zamboanga del Norte | Sibutad, Zamboanga del Norte | 2015-11-14 | Final | Zamboanga Del Norte 3rd DEO | LF | 7.0281 | 70 | 2015-06-22 | 2015-08-30 | 1.85% | C | 0.414 | 0.2 | 0.3 | - | - | - | 91.4% | 91.4% Very Satisfactory
Antonio V. Nidea Construction | 6382 |  |  |  |  | Const. of Iriga Flood Control Project (Consolidation Dam, Ground Sill, Slope Protection & Damage Canal) |  | 2010-02-28 |  | V |  | 28.505 | 240 |  |  |  | O | 0.352 | 0.24 | 0.15 | 0.03 | 0.035 | 0.033 | 84 | -
Antonio V. Nidea Construction, Inc. (Formerly: Antonio V. Nidea Construction) | 6382 | L | A | MA | GB1 | Const./Repair/Rehab. of MPB, Albay III DEO | Paulog, Ligao City | 2013-08-09 | 1st | V | LF | 3.679 | 90 | 2013-06-25 | 2013-09-22 | 6.65 | O | 0.334 | 0.286 | 0.15 | 0.03 | 0.04 | 0.033 | 87.3 | -
Antonio V. Nidea Construction, Inc. (Formerly: Antonio V. Nidea Construction) | 6382 | L | A | MB | GE1 | Guicadale Platform Rd., Cotmon-Maninila-Taplacon-Taloto Rd., (Cotmon-Maninila Sect.) | Camalig, Albay | 2013-08-10 | 1st | V | LF | 22.843 | 206 | 2013-02-01 | 2013-08-25 | -3.26 | O | 0.366 | 0.241 | 0.117 | 0.03 | 0.041 | 0.033 | 82.8 | -
ANTONIO V. NIDEA CONSTRUCTION, INC. (Formerly: Antonio V. Nidea Construction) | 6382 | L | A | MB | GE | Off-Carriageway Improvement along Daang Maharlika, KO535+330 - KO537+840 (RS), K0535+432-KO537+840 (LS), Daraga, Albay | Daraga, Albay | 2015-11-10 | Final | Albay Second DEO | LF | 18.5126 | 120 | 2015-02-09 | 2015-06-08 | - | C | 0.35 | 0.2 | 0.3 | - | - | - | 85% | 85% Satisfactory
APD CONSTRUCTION | 17467 | L | A | MB | GE | Preventive Maintenance Based on Pavement Management System/Highway Development and Management-4 (HDM-4) (Intermittent Section) - Reblocking of Shattered Blocks along Jct. Mangandingay - Saguday - Isabela Bdry. Road, K0336+(-872) to K0336+259, K0340+027 to K0340+463, K0342+410 to K0342+881, K0343+054 to K0343+400, Diffun, Saguday & Cabarroguis, Quirino | Diffun, Saguday & Cabarroguis, Quirino | 2015-08-30 | 1st & Final | Quirino DEO | LF | 5.934 | 121 | 2015-03-06 | 2015-07-04 | 5.96% | C | 0.439 | 0.133 | 0.3 | - | - | - | 87.2% | *87.2% Satisfactory
Aqualine Construction | 11555 | L | AA |  |  | National Irrigation System Rehabilitation & Improvement Project | Narra, Palawan/Region IV-B | 2016-08-06 | 1st | NIA | LF | 189.364 | 730 | 2015-08-26 | 2017-08-24 | -12.77 | O | 0.3158 | 0.3 | 0.0223 | 0.03 | 0.0513 | 0.0333 | 75.27 | -
Aqualine Construction/C.R. Domingo Construction, Inc. (JV) | 2992 | L | A |  |  | Nueva Viscaya Bagabag Irrigation System | San Geronimo, Bagabag, Nueva Viscaya | 2015-09-29 | 1st | NIA | LF | 74.478 | 866 | 2013-05-17 | 2015-09-30 | -10.3 | O | 0.3726 | 0.2959 | 0.047 | 0.03 | 0.045 | 0.05 | 84.05 | -
AQUATERRA KONSTRUKT, INC. | 15929 | L | A | MB | GE | Construction/Repair/Improvement of Flood Control at Tumaga River, Pasonanca Section, Zamboanga City | Zamboanga City | 2015-09-03 | 1st | Zamboanga City | LF | 9.766 | 191 | 2015-03-30 | 2015-10-07 | (+)0.18% | O | 0.34 | 0.24 | 0.15 | 0.03 | 0.051 | 0.05 | 86.1% | -
AQUATERRA KONSTRUKT, INC. | 15929 | L | A | MB | GE | Construction/Repair/Improvement of Flood Control at Tumaga River, Pasonanca Section, Zamboanga City | Zamboanga City | 2015-11-09 | 2nd | Zamboanga City DEO | LF | 9.7655 | 161 | 2015-03-30 | 2015-09-06 | 5.43% | OG | 0.268 | 0.3 | 0.15 | 0.02 | 0.047 | 0.05 | 83.5% | 83.5% Satisfactory
AQUINO DELA CRUZ ENG'G. & CONSTRUCTION | 16751 | L | B | MA | GE | Widening of Carmen Jct.-Bayambang-Manat Road, K0.190+169 - K0.193+864.60 (Bayambang Section), Bayambang, Pangasinan | Bayambang, Pangasinan | 2015-11-26 | 1st | PANGASINAN 4TH DEO | LF | 48.9997 | 264 | 2015-03-11 | 2015-11-29 | 0.0114 | OG | 0.372 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 89.7% | 89.7% Very Satisfactory
AQUINO-DE LA CRUZ ENG'G. & CONSTRUCTION | 16751 | L | B | MA | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Road including Drainage along Manila North Road | KO202+695 - KO203+060 (Bobonan Section) | 2015-06-08 | 1st | Pangasinan 3rd DEO | LF | 12.518 | 131 | 2015-02-20 | 2015-06-30 | -7.6% | O | 0.351 | 0.3 | 0.074 | 0.03 | 0.045 | 0.033 | 83.3% | -
Aquino-Dela Cruz Eng'g & Construction | 16751 | L | D | MA | GE1 | Replacement/Rehab./Strengthening of Quintans Bridge along Camiling-Wawa-Bayambang-Malasiqui-Sta. Barbara Rd. | Malasiqui, Pangasinan | 2013-08-03 | 1st | I | LF | 11.081 | 225 | 2013-01-16 | 2013-08-28 | 13.67 | O | 0.4 | 0.2 | 0.15 | 0.03 | 0.047 | 0.033 | 86 | -
Aquino-Dela Cruz Eng'g & Construction | 16751 | L | B | MA | GE1 | Widening/Rehab./Reconst./Upgrading of MNR | Urdaneta, Pangasinan | 2013-08-09 | 1st | I | LF | 36.32 | 242 | 2013-03-27 | 2013-11-23 | -10.42 | O | 0.39 | 0.3 | 0.046 | 0.03 | 0.042 | 0.033 | 84.1 | -
Aquino-Dela Cruz Eng'g. & Construction | 16751 | L | B | MA | GE1 | Prev. Maint. along Calasiao Old Rd., K0204+(-030)-K0206+305 w/ exception | Calasiao, Pangasinan | 2013-03-14 | 1st | I | LF | 38.759 | 75 | 2013-01-16 | 2013-03-31 | -5.24 | O | 0.375 | 0.3 | 0.098 | 0.02 | 0.03 | 0.017 | 84 | -
Aquino-Dela Cruz Eng'g. & Construction | 16751 | L | B | MA | GE1 | Widening of Pangasinan-Nueva Vizcaya Rd. (PNVR), Km.171+138-Km.204+550 w/ exception | Pangasinan | 2013-03-13 | 1st | I | LF | 19.351 | 104 | 2013-01-11 | 2013-04-24 | 1.51 | O | 0.317 | 0.3 | 0.15 | 0.015 | 0.02 | 0.033 | 83.5 | -
Aquino-dela Cruz Eng'g. & Construction | 16751 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of Pangasinan-Nueva Ecija Road, IS K0184+000-K0185+667 w/ exceptions | Rosales, Pangasinan | 2012-08-10 | 1st | I | LF | 20.375 | 133 | 2012-04-16 | 2012-08-26 | 2.55 | O | 0.29 | 0.3 | 0.125 | 0.03 | 0.055 | 0.033 | 83.3 | -
Aquino-Dela Cruz Engineering & Construction | 16751 | L | B | MA | GB1 | Construction of San Carlos City District Office | San Carlos City, Pangasinan | 2013-07-19 | 1st | DOTC | L | 8.671 | 180 | 2013-03-13 | 2013-09-08 | 14.26 | O | 0.3907 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 91.07 | -
Aquino-Dela Cruz Engineering & Construction | 16751 | L | B | MA | GB1 | San Fernando, La Union LTFRB Regional Office Project | San Fernando, La Union | 2013-07-30 | 1st | DOTC | L | 7.949 | 180 | 2013-03-13 | 2013-09-08 | 6.07 | O | 0.39 | 0.24 | 0.15 | 0.03 | 0.035 | 0.05 | 89.5 | -
AR Adlawan Construction | 13108 | L | A | MA | GE1 | Widening of Natalio Bacalso Avenue | Naga, Cebu | 2012-11-20 | 1st | VII | LF | 71.121 | 265 | 2012-04-11 | 2012-12-31 | -10.37 | O | 0.35 | 0.239 | 0.15 | 0.03 | 0.035 | 0.05 | 85.4 | -
AR Adlawan Construction | 13108 | L | A | MA | GE1 | Widening of Natalio Bacalso Ave., Naga to Carcar Sect. | Cebu | 2012-08-20 | 1st | VII | LF | 71.121 | 265 | 2012-04-11 | 2012-12-31 | 0.14 | O | 0.368 | 0.256 | 0.15 | 0.024 | 0.045 | 0.033 | 87.6 | -
Arca Builders | 34537 | L | D | SB | GE2 | Const./Impvt. of Drainage System along Palompon-Isabel-Merida-Ormoc Rd., Km.1132+700-Km.1133+763 w/ exceptions | Leyte | 2012-11-22 | 1st | VIII | LF | 1.512 | 105 | 2012-08-22 | 2012-12-04 | -0.21 | O | 0.334 | 0.3 | 0.15 | 0.03 | 0.02 | 0.033 | 86.7 | -
Arcinue Commercial |  | L |  |  |  | NHA-Tambo Resettlement Project | Brgy. Tambo, Babak District, IGACOS, Davao del Norte | 2014-05-30 | 2nd | NHA | LF | 19.6 | 268 | 2013-04-23 | 2014-06-13 | -11.84 | O | 0.3984 | 0.3 | 0.0316 | 0.03 | 0.056 | 0.0333 | 84.93 | -
Arcinue Commercial |  | L |  |  |  | NHA-Tambo Resettlement Project | Brgy.Tambo, Babak District, IGACOS, Davao del Norte | 2013-11-29 | 1st | NHA | LF | 19.6 | 313 | 2013-04-23 | 2014-03-01 | -6.76 | O | 0.3897 | 0.3 | 0.0824 | 0.03 | 0.0653 | 0.05 | 91.74 | -
Arcinue Commercial | 6746 | L | A | MA | GE1 | Widening of San Fernando By Pass Rd. inc. Rd. Right-of-Way | San Fernando City, La Union | 2013-03-11 | 1st | I | LF | 19.364 | 120 | 2013-01-10 | 2013-05-09 | 26.02 | O | 0.356 | 0.3 | 0.15 | 0.015 | 0.03 | 0.033 | 88.4 | -
Arcinue Commercial | 6746 | L | A | MA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rd.. along Camiling-Wawa-Bayambang-Sta. Barbara Rd., K0172+(-006)-K0172+594 | Bayambang, Pangasinan | 2013-03-14 | 1st | I | LF | 10.031 | 105 | 2013-01-16 | 2013-04-30 | 6.05 | O | 0.372 | 0.289 | 0.15 | 0.015 | 0.03 | 0.017 | 87.3 | -
Arcinue Commercial | 6746 | L | A | MA | GE1 | Prev. Maint. along Bacnotan-Luna Balaoan Rd. (Clustered) K0286+000-K0287+498 w/ exception | La Union | 2013-03-11 | 1st | I | LF | 6.729 | 113 | 2013-01-10 | 2013-05-02 | 2.41 | O | 0.37 | 0.2 | 0.15 | 0.015 | 0.04 | 0.033 | 80.8 | -
Arcinue Commercial | 6746 | L | A | MA | GE1 | Rehab./Reconts./Upgrading along Bacnoton-Luna-Balaoan Road, Km. 283+221-Km. 307+896 w/exception |  | 2009-05-27 | 1st | I |  | 16.169 | 90 |  |  |  | O | 0.358 | 0.207 | 0.15 | 0.03 | 0.04 | 0.033 | 81.8 | -
Arcinue Commercial | 6746 | L | A | MA | GE1 | Widening/Reconst. of San Fernando By-Pass Road (Sta. 0+000-Sta. 3+840) w/ exceptions | San Fernando City, La Union | 2012-03-12 | 1st | I | LF | 44.687 | 270 | 2012-01-19 | 2012-10-14 | -3.91 | O | 0.374 | 0.24 | 0.111 | 0.03 | 0.042 | 0.033 | 83 | -
Arcinue Commercial | 6746 | L | A | MA | GE2 | Repair/Rehab. Of MNR, Patac, Sto. Tomas and Urayong Sections | Bauang, La Union | 2012-11-24 | 1st | I | LF | 8.834 | 280 | 2012-06-19 | 2013-03-25 | 34.67 | O | 0.3 | 0.3 | 0.15 | 0.02 | 0.03 | 0.033 | 83.3 | -
Arcinue Commercial | 6746 | L | A | MA | GE1 | Widening/Reconst. of San Fernando By-Pass Rd., Sta.0+000-Sta.3+840 w/ exception | San Fernando, La Union | 2012-08-07 | 2nd | I | LF | 46.334 | 224 | 2012-01-19 | 2012-08-29 | 16.84 | O | 0.362 | 0.272 | 0.15 | 0.03 | 0.055 | 0.033 | 90.2 | -
Arcinue Commercial | 6746 | L | A | MA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rd. along MNR, K0370+000-K0371+249 | Sta. Maria, Ilocos Sur | 2012-07-31 | 1st | I | LF | 22.295 | 251 | 2012-01-26 | 2012-10-02 | -4.33 | O | 0.253 | 0.3 | 0.107 | 0.02 | 0.04 | 0.033 | 75.3 | -
Arcinue Commercial | 6746 | L | A | MA | GE2 | Const. of Malita Seawall at SPAMAST-SAMTALIKA Sect., Pob. | Malita, Davao del Sur | 2012-08-09 | 1st | XI | LF | 33.521 | 285 | 2012-01-09 | 2012-10-20 | 3.57 | O | 0.334 | 0.22 | 0.15 | 0.03 | 0.057 | 0.033 | 82.4 | -
ARKY CONSTRUCTION AND SUPPLY | 32692 | L | AA | LA | GE | Concreting of Road at Barangay Magdalena, Baleno, Masbate 2nd LD, Sta 0+000 - Sta 0+239 | Baleno, Masbate | 2015-06-11 | Final | Masbate 1st | LF | 2.812 | 43 | 2015-04-13 | 2015-04-29 | 0% | C | 0.378 | 0.193 | 0.3 | - | - | - | 87.1% | *87.1% Satisfactory
ARKY CONSTRUCTION AND SUPPLY | 32692 | L | AA | LA | GE | Off-Carriageway Improvement (Paving of Shoulder) San Fernando North Road, San Fernando, Masbate | San Fernando, Masbate | 2015-09-03 | 1st | Masbate Third DEO | LF | 21.345 | 210 | 2015-03-11 | 2015-10-06 | 0.02% | O | 0.373 | 0.252 | 0.15 | 0.03 | 0.06 | 0.05 | 91.5% | -
ARMANDO U. KHONG HUN GENERAL CONTRACTOR, INC (Formerly: Armando U. Khong Hun General Contractor) | 16163 | L | AAA | MB | GE | Reblocking with Laneline Marking along C-5 Road at Intermittent Sections, Sta. 0+000 to Sta. 3+845.50 & Sta. 0+000 to Sta. 1+720, Pasig City and Taguig City | Pasig City and Taguig City | 2015-08-27 | 1st | NCR | LF | 31.018 | 624 | 2014-04-10 | 2015-12-24 | 40.31% | O | 0.331 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 85.1% | -
Armando U. Khong Hun General Contractor, Inc. | 16163 | L | AAA | MB | GE1 | Prev. Maint. (Int. Sect.) San Marcelino St., 5th District, Manila A) K0003+783 B) K0003+78 -K0003+836 | City of Manila | 2013-03-13 | 1st | NCR | LF | 14.517 | 104 | 2013-02-19 | 2013-06-02 | 2.08 | O | 0.344 | 0.24 | 0.15 | 0.03 | 0.048 | 0.033 | 84.5 | -
Armando U. Khong Hun General Contractor, Inc. (Formerly: Armando U Khong Hun General Contractor) | 16163 | L | AAA | MB | GE1 | Const./Widening of Pres. Garcia Ave. (C-5), Sta. 0+000-Sta. 2+897.20 | Taguig City | 2013-07-27 | 1st | NCR | LF | 33.084 | 120 | 2013-05-22 | 2013-09-18 | 0.1 | O | 0.329 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 84.9 | -
Armando U. Khong Hun General Contractor, Inc. (Formerly: Armando U Khong Hun General Contractor) | 16163 | L | AAA | LB | GB1 | Const. of Four (4) Storey, Twelve (12) Cl. at R.P. Cruz Elem. Sch. | Taguig City | 2013-08-07 | 1st | NCR | LF | 21.781 | 178 | 2013-03-26 | 2013-09-19 | 9.31 | O | 0.326 | 0.24 | 0.15 | 0.03 | 0.047 | 0.05 | 84.3 | -
Armando U. Khong Hun General Contractor, Inc. (Formerly: Armando U Khong Hun General Contractor) | 16163 | L | AAA | LB | GB1 | Const. of Four (4) storey, Twenty (20) Cl. Bldg. at San Antonio Elem. Sch. | Parañaque City, Metro Manila | 2013-08-08 | 1st | NCR | LF | 36.242 | 233 | 2013-03-27 | 2013-11-14 | 10.5 | O | 0.332 | 0.24 | 0.15 | 0.03 | 0.058 | 0.033 | 84.3 | -
Armando U. Khong Hun General Contractor, Inc. (Formerly: Armando U Khong Hun General Contractor) | 16163 | L | AAA | MA | GE | Improvement/Clearing & Desilting including Right of Way (ROW) of Zapote River, Manila Bay towards Alido Bridge (Vice Versa), Sta. 0+000 to Sta. 1+540 | Las Pinas, Metro Manila | 2014-11-17 | 1st | NCR | LF | 43.6751 | 195 | 2014-06-09 | 2014-12-20 | 1.25% | O | 0.263 | 0.25 | 0.15 | 0.03 | 0.054 | 0.05 | 79.7% | 79.70% Unsatisfactory
Armando U. Khong Hun General Contractor, Inc. (Formerly: Armando U. Khong Hun General Contractor) | 16163 | L | AAA | MB | GE1 | Proposed Const. of Diokno Blvd. incl. Bridge Approaches | Pasay City | 2012-07-30 | 1st | NCR | LF | 43.663 | 120 | 2012-03-28 | 2012-07-25 | 2.3 | O | 0.38 | 0.24 | 0.15 | 0.023 | 0.035 | 0.033 | 86.1 | -
ARMANDO U. KHONG HUN GENERAL CONTRACTOR, INC. (Formerly: Armando U. Khong Hun General Contractor) | 16163 | L | AAA | MB | GE | Concreting of Brgy. Serverino De Las Alas to F. De Castro FMR | G.M.A., Cavite | 2015-06-13 | Final | Cavite 1st DEO | LF | 14.161 | 110 | 2014-10-17 | 2015-02-03 | 50% | C | 0.335 | 0.2 | 0.3 | - | - | - | 83.5% | *83.5% Satisfactory
Arn Builders | 18930 |  |  |  |  | Rehab./Reconstruction of Aklan East Road |  | 2008-11-30 |  | VI |  | 19.283 | 180 |  |  |  | O | 0.218 | 0.24 | 0.1 | 0.015 | 0.032 | 0.1 | 70.5 | -
Arn Builders | 18930 | L | AAA | LB | GE1 | Rehab./Reconst./Upgrading of Aklan East Road |  | 2009-09-05 | 2nd | VI |  | 31.795 | 240 |  |  |  | O | 0.335 | 0.24 | 0.15 | 0 | 0.032 | 0.1 | 72.5 | -
Arn Builders | 18930 | L | AAA | LB | GE2 | Const. of Flood Control along Left Bank of Dipolog River Looc | Estaka, Dipolog City | 2013-08-22 | 3rd | IX | LF | 62.3 | 437 | 2012-07-31 | 2013-10-10 | 0 | O | 0.191 | 0.3 | 0.15 | 0.02 | 0.042 | 0.05 | 75.3 | -
Arn Builders | 18930 | L | AAA | LB | GE2 | Const. of Flood Control along Left Bank of Dipolog River | Looc, Estaka, Dipolog City | 2012-11-28 | 1st | IX | LF | 62.3 | 408 | 2012-07-31 | 2013-09-12 | 2.9 | O | 0.388 | 0.239 | 0.15 | 0.03 | 0.054 | 0.05 | 91.1 | -
Arn Builders | 18930 | L | AAA | LB | GE1 | Const. of Lugusan Bridge & Approaches along Surigao del Sur Bdry., Davao Oriental Coastal Rd. | Davao Oriental | 2013-08-16 | 2nd | XI | LF | 27.687 | 351 | 2012-05-11 | 2013-04-26 | -8.47 | O | 0.376 | 0.259 | 0 | 0.03 | 0.025 | 0.033 | 72.3 | -
Arn Builders | 18930 | L | AAA | LB | GE1 | Const. of Lugusan Bridge & Approaches along Surigao del Sur Bdry., Davao Oriental Coastal Rd. | Davao Oriental | 2012-08-17 | 1st | XI | LF | 27.687 | 244 | 2012-05-11 | 2013-01-09 | -7.3 | O | 0.4 | 0.2 | 0.077 | 0.022 | 0.051 | 0.017 | 76.7 | -
Arn Builders | 18930 | L | AAA |  | GE2 | Mabini Cayacay SRIP | Mabini, Bohol Region VII | 2013-07-13 | 1st | NIA | L | 4.922 | 150 | 2012-08-07 | 2013-03-06 | -34.72 | O | 0.365 | 0.3 | 0 | 0.02 | 0.045 | 0.05 | 78 | -
Arn Builders | 18930 | L | AAA | LB | GE1 | Repair of Langkilaan Rd. along Daang Maharlika Rd. (Agusan-Davao Sect.) Km. 1375+302.90-Km. 1375+460 | Agusan del Sur | 2012-11-26 | 1st | XIII | LF | 9.356 | 235 | 2012-05-30 | 2013-01-19 | -1.47 | O | 0.39 | 0.22 | 0.135 | 0.03 | 0.035 | 0.033 | 84.3 | -
ARN Builders, Inc. | 18930 | L |  | LB | GE2 | Const. of Flood Control along Left Bank of Dipolog River Looc | Bataka, Dipolog City | 2013-03-23 | 2nd | IX | LF | 62.3 | 408 | 2012-07-31 | 2013-09-12 | 0.2 | O | 0.365 | 0.24 | 0.15 | 0.03 | 0.042 | 0.05 | 87.7 | -
ARN Builders, Inc. | 18930 | L |  | LB | GE2 | Const. of Flood Control Disakan Bridge, Jose Dalman | Zamboanga del Norte | 2013-03-23 | 1st | IX | LF | 6.549 | 146 | 2013-01-08 | 2013-06-02 | 0.5 | O | 0.383 | 0.24 | 0.15 | 0.03 | 0.033 | 0.033 | 86.9 | -
ARR Construction | 17300 |  | AAA |  |  | New Washington Homes Site 1 | Brgy. Fatima/ Dumanguit, New Washington, Aklan | 2016-04-09 | 1st | NHA | LF | 98.279 | 322 | 2015-06-12 | 2016-04-28 | -38.33 | O | 0.3591 | 0.2903 | 0 | 0.03 | 0.0653 | 0.033 | 77.77 | -
ARR Construction | 17300 |  | AAA |  |  | New Washington Homes Site 2 | Brgy. Fatima/ Dumanguit, New Washington, Aklan | 2016-04-09 | 1st | NHA | LF | 46.193 | 272 | 2015-06-13 | 2016-03-10 | -46.25 | O | 0.3836 | 0.3 | 0 | 0.03 | 0.0653 | 0.033 | 81.19 | -
Arthur Blanco Construction and Development Corp. | 33999 | L | C | SB | GB1 | Const. of MPB, Brgy. Kumintang Ilaya, Capitol Site | Batangas City, Batangas | 2012-11-23 | 1st | IVA | LF | 3.997 | 167 | 2012-06-28 | 2012-12-11 | 0.56 | O | 0.364 | 0.3 | 0.15 | 0.03 | 0.023 | 0.033 | 90 | -
AS MACHA CONSTRUCTION AND TRADING | 36878 | L | C | SB | GB | Construction of Multi-Purpose Building, Barangay Hall, Pentor, Dinalupihan, Bataan | Pentor, Dinalupihan, Bataan | 2015-06-06 | Final | Bataan 1st DEO | LF | 1.248 | 60 | 2014-12-15 | 2015-02-12 | 3.33% | C | 0.49 | 0.149 | 0.3 | - | - | - | 93.9% | *93.9% Very Satisfactory
Asand Construction & Devt. | 21691 | L |  | MA | GB1 | Completion of Academic Bldg. II | Langka Balol, Lanao del Norte | 2011-08-25 | 1st | DOST | LF | 9.082 |  | 2010-03-01 | 2010-08-30 | -6 | O | 0.3758 | 0.3 | 0.09 | 0.03 | 0.0175 | 0.033 | 84.63 | -
ASC Construction and Concrete Product | 26788 | L |  | MA | GE2 | Banurbur Creek Irrigation System | Cagayan, Region 2 | 2014-04-26 | 1st | NIA | LF | 65.41 | 730 | 2013-05-24 | 2015-03-15 | 0.06 | O | 0.3833 | 0.3 | 0.15 | 0.018 | 0.042 | 0.05 | 94.33 | -
ASC Construction and Concrete Product | 26788 | L | A |  |  | Rehab./Restoration and extension of Pinacanauan RIS Including Suppy, Delivery Installation of Steel Gates | Penablaca, Cagayan/ Region 2 | 2014-04-26 | 1st | NIA | LF | 77.856 | 640 | 2014-05-16 | 2015-02-15 | 22.84 | O | 0.36 | 0.27 | 0.15 | 0.02 | 0.05 | 0.05 | 90 | -
ASC Construction and Concrete Products | 26788 | L | A | MA | GE2 | Const. of Cataggaman River Control System | Cataggaman, Tuguegarao City | 2013-07-29 | 1st | II | LF | 47.042 | 245 | 2013-03-27 | 2013-11-26 | -7.29 | O | 0.383 | 0.3 | 0.077 | 0.03 | 0.055 | 0.05 | 89.5 | -
ASC Construction and Concrete Products / D.J.D. Construction (JV) | JV-12-522 | L | A | MA | GE1 | Rd. Upgrading (Gravel to Paved) K0548+500-K0551+271, Baybayog-San Jose-Dalin-Abusag-Sta. Margarita-Bolos Point Rd. | Baggao, Cagayan | 2013-07-30 | 1st | II | LF | 46.277 | 179 | 2013-02-22 | 2013-08-19 | -11.88 | O | 0.372 | 0.3 | 0.031 | 0.03 | 0.055 | 0.05 | 83.8 | -
Ashlee Construction & Allied Engineering Services | 36738 | L | B | SB | GB | Construction of Multi-Purpose Building, Puntian | Puntian, Sumilao, Bukidnon | 2014-08-09 | 1st | X | LF | 1.98 | 91 | 2014-05-30 | 2014-08-28 | 7.43 | O | 0.319 | 0.241 | 0.076 | 0.02 | 0.035 | 0.033 | 72.4 | -
Ashlee Construction & Allied Engineering Services | 36738 | L | B | SB | GB | Const. of Multi-Purpose Bldg. (Fibelo Compound) Brgy. Anahawon | Maramag, Bukidnon | 2014-10-22 | 1st | X | LF | 4.9366 | 120 | 2014-08-04 | 2014-12-01 | -6.75% | O | 0.322 | 0.24 | 0.083 | 0.01 | 0.032 | 0.033 | 72% | 72.00% Poor
Ashlee Construction & Allied Engineering Services | 36738 | L | B | SB | GB | Const. of Classroom - Northern Bukidnon Community College | Tankulan, Manolo Fortich, Bukidnon | 2014-10-21 | 1st | X | LF | 1.98 | 104 | 2014-05-30 | 2014-09-10 | -9.48% | O | 0.342 | 0.269 | 0.055 | 0.01 | 0.022 | 0.033 | 73.1% | 73.10% Poor
Asia Konstrakt Philippines, Inc. | 32706 | L | A | SB | GE2 | Const. of Talomo Flood Control Proj. | Talomo District, Davao City | 2013-03-22 | 2nd | XI | LF | 6.353 | 111 | 2012-10-26 | 2013-02-13 | 0.08 | O | 0.263 | 0.3 | 0.15 | 0.03 | 0.028 | 0.05 | 82.1 | -
Asia Konstrakt Philippines, Inc. | 32706 | L | A | SB | GE2 | Const. of Talomo Flood Control Proj. | Davao City | 2012-11-29 | 1st | XI | LF | 6.353 | 96 | 2012-10-26 | 2013-01-29 | 1.92 | O | 0.36 | 0.24 | 0.15 | 0.03 | 0.035 | 0.05 | 86.5 | -
ASIAN PEARL CONSTRUCTION & DEVELOPMENT CORP. | 9059 | L | B | MA | GE | Widening of National Road along Laoag-Airport Road | KO486+(-622) - KO491+268, Brgy. Nangalisan A-Cabungaan A Section, Laoag City | 2015-06-03 | 1st | Ilocos Norte 1st DEO | LF | 37.892 | 209 | 2015-03-12 | 2015-10-06 | 13.31% | O | 0.272 | 0.299 | 0.15 | 0.03 | 0.055 | 0.033 | 83.9% | -
ASIAN PEARL CONSTRUCTION & DEVELOPMENT CORP. | 9059 | L | B | MA | GE | Widening of National Road along (S04143LZ) Laoag-Airport Road, K0486+(-622) to K0491+268, Brgy. Nangalisan A-Cabungaan A Section, Laoag City | K0486+(-622) to K0491+268, Brgy. Nangalisan A-Cabungaan A Section, Laoag City | 2015-08-25 | 1st | Ilocos Norte 1st DEO | LF | 37.892 | 209 | 2015-03-12 | 2015-10-07 | (-)0.05 | O | 0.327 | 0.24 | 0.149 | 0.03 | 0.042 | 0.033 | 82.1% | -
ASJ Builders | 35988 | L | D | SB | GB | Construction of Multi-Purpose Building, Brgy. Banban, Tagana-an, Surigao del Norte | Tagana-an, Surigao del Norte | 2014-10-28 | 1st | XIII | LF | 2.4127 | 90 | 2014-08-15 | 2014-11-12 | 2.94% | O | 0.327 | 0.24 | 0.15 | 0.02 | 0.048 | 0.05 | 83.5% | 83.50% Satisfactory
ASM Francisco Const. & Devt. Corporation |  | L |  |  | GB1 | Manila Museum and Archives Project Phase 1 | UPM | 2011-02-17 | 1st | UP | LF | 15.698 | 150 | 2009-06-08 | 2011-05-03 | - | O | 0.384 | 0.299 | 0.15 | 0.03 | 0.056 | 0.05 | 96.9 | -
ASS Construction |  |  | B | MA |  | Construction of PSHS-CLC Dormitory Bldg. I, Phase 3 | Lily Hill Street, Clark Freeport Zone, Pampanga | 2016-10-19 | 1st & Final | DOST | LF | 34.475 | 290 | 2016-09-04 | 2016-07-13 | 0 | C | 0.456 | 0.2 | 0.3 | - | - | - | 95.6 | *95.60% Very Satisfactory
Atlantic Construction | 24232 | L | D | SB | GB | Const. of Multi-Purpose Building at San Andres E/S | San Andres, Delfin Albano, Isabela | 2014-08-08 | 1st | II | LF | 2.886 | 97 | 2014-05-29 | 2014-09-02 | 0.1 | O | 0.282 | 0.3 | 0.15 | 0.03 | 0.035 | 0.033 | 83 | -
ATLANTIC CONSTRUCTION | 24232 | L | D | SB | GB | Construction of Multi-Purpose Building, San Andres, E/S, San Andres | Delfin Albano, Isabela | 2015-06-04 | Final | Isabela 1st DEO | LF | 2.969 | 133 | 2014-05-29 | 2014-10-08 | 0% | C | 0.396 | 0.2 | 0.3 | - | - | - | 89.6% | *84.98% Satisfactory
Atlas General Contractors and Enterprises Corporation | [5 empty] | Package X-D: Construction of lateral "N" (Sta. 10+000) Sub-lat. R "N-6" (Sta. 0+000-1+200). "N-6a" (Sta. 0+000-1+480) and "N-6b" (Sta. 0+000-1+940) including related structures and supply, delivery and installation of steel gates | Guimba, Nueva Ecija | 2015-02-07 | 1st | NIA | L | 38.176 | 246 | 2014-07-29 | 2015-03-31 | 13.11 | O | 0.3275 | 0.2748 | 0.15 | 0.03 | 0.0233 | 0.05 | 85.56 | -
Atolba Construction | 33768 | L | C | SC | GE | Const of Various Drainage & Box Culvert J. Banaue-Hungduan-Benguet Bdry Rd, K0360+060, Hungduan, 2. Banaue-Hungduan-Benguet Bdry Rd, K0398+497 3. Nueva Vizcaya-Ifugao-Mt. Province Bdry Rd, K0311+976, Kiangan` | Kiangan, Ifugao | 2014-08-05 | 1st | CAR | LF | 1.1609 | 109 | 2014-04-21 | 2014-08-07 | 0.3 | O | 0.391 | 0.24 | 0.15 | 0.022 | 0.035 | 0.05 | 88.8 | -
ATOLBA CONSTRUCTION | 33768 | L | C | SB | GE | Construction of Various Drainage and Box Culvert along 1. Banaue-Hungduan-Benguet Boundary Road, K0398+497 2. Banaue-Hungduan-Benguet Boundary Road, K0360+060 3. Nueva Vizcaya-Ifugao-Mt. Province Boundary Road, K0311+079 | Hungduan, Tinoc & Kaingan, Ifugao | 2015-06-06 | Final | Ifugao 1st DEO | LF | 1.604 | 109 | 2014-04-21 | 2014-08-07 | (-) 14.00% | C | 0.297 | 0.2 | 0 | - | - | - | 49.7% | *73.16% Poor
Avatar Construction Company | 31455 | L | B | SB | GE | Protection Works along Dinagat - Loreto Road (San Jose Section), Brgy. Don Ruben, San Jose, Dinagat Islands | San Jose, Dinagat Islands | 2014-10-27 | 1st | XIII | LF | 9.4359 | 70 | 2014-04-22 | 2014-06-30 | -14.9% | O | 0.355 | 0.3 | 0 | 0.02 | 0.042 | 0.033 | 75% | 75.00% Poor
Avatar Construction Company | 31455 | L | B | MA | GE1 | Replacement of Pangi Bridge 2 along Dinagat-Loreto Rd. | Dinagat Islands | 2012-08-10 | 1st | XIII | LF | 6.447 | 165 | 2012-03-05 | 2012-09-25 | -11.68 | O | 0.363 | 0.3 | 0.033 | 0.03 | 0.06 | 0.05 | 83.6 | -
Aylan Construction and Trading | 11884 | L | A | MA | GB | Construction of 4 Storey Twenty (20) Classroom Building at Novaliches H/S | Quezon City | 2014-08-14 | 1st | NCR | LF | 36.2049 | 395 | 2013-09-02 | 2014-10-01 | 1.15 | O | 0.371 | 0.24 | 0.15 | 0.018 | 0.051 | 0.02 | 85 | -
Aylan Construction and Trading | 11884 | L | A | SB | GB1 | Const. of Two (2) Sch. Bldg. Four (4) Storey Sixteen (16) Cl. at Amparao H/S | Caloocan City | 2013-08-13 | 1st | NCR | LF | 46.3 | 330 | 2013-03-27 | 2014-02-19 | 1.2 | O | 0.298 | 0.221 | 0.15 | 0.03 | 0.046 | 0.05 | 79.5 | -
AZTEK CONSTRUCTION | 32911 | L | D | SB | GB | Development of Puting Buhangin Spelunkers'Hub | Prosperidad, Agusan del Sur | 2015-11-12 | Final | TIEZA | LF | 2 | 90 | 2015-04-30 | 2015-09-27 | 0 | C | 0.494 | 0.191 | 0.3 |  |  |  | 98.6 | 98.6% Outstanding
AZUL BUILDERS | 21870 | L | B | MA | GE | Construction/Rehabilitation of Road with Drainage, Brgy. Abangan Sur, Municipality of Marilao, Bulacan 4th LD | Brgy. Abangan Sur, Municipality of Marilao, Bulacan 4th LD | 2015-11-19 | Final | Bulacan Second DEO | LF | 9.293 | 100 | 2015-02-16 | 2015-05-26 | - | C | 0.481 | 0.133 | 0.3 | - | - | - | 91.4% | 91.4% Very Satisfactory
B. M. Marketing | 9852 | L | AAA | MB |  | Tacloban Airport Development Project | Brgy. San Jose, Tacloban City | 2014-12-11 | 1st | DOTC | LF | 123.417 | 240 | 2014-06-20 | 2014-03-05 | 21.95 | O | 0.3845 | 0.3 | 0.15 | 0.02 | 0.0311 | 0.05 | 93.56 | -
B. M. Marketing | 9852 |  | AAA | LA |  | Balangkayan Port Development Project | Balangkayan, Eastern Samar/ Region VIII | 2016-03-29 | 1st | DOTC | LF | 31.481 | 180 | 2016-03-23 | 2016-09-18 | 46.72 | O | 0.376 | 0.3 | 0.15 | 0.03 | 0.053 | 0.05 | 95.9 | -
B. M. Marketing | 9852 |  | AAA | LA |  | Yolanda Rehabilitation Project | Hermani & Llorente, Eastern Samar/ Region VIII | 2016-08-17 | 1st & Final | DOTC | LF | 15.73 | 210 | 2016-03-21 | 2016-10-18 | 21.76 | C | 0.4529 | 0.2 | 0.3 | - | - | - | 95.29 | *95.29% Very Satisfactory
B. M. Marketing | 9852 |  | AAA | LA |  | Yolanda Rehabilitation Project | Giporlos, Eastern Samar/ Region VIII | 2016-08-17 | 1st & Final | DOTC | LF | 11.416 | 120 | 2016-01-18 | 2016-09-08 | 19.96 | C | 0.49801 | 0.2 | 0.3 | - | - | - | 99.801 | *99.80% Outstanding
B. M. Marketing | 9852 |  | AAA | LA |  | Yolanda Rehabilitation Project | Brgy. 03, Balangkayan, Eastern Samar/ Region VIII | 2016-08-17 | 2nd & Final | DOTC | LF | 31.481 | 180 | 2016-01-18 | 2016-09-18 | 9.95 | C | 0.4972 | 0.2 | 0.3 | - | - | - | 99.72 | 97.43% Outstanding
B. M. Marketing | 9852 | L | AAA | LA |  | Typhoon Yolanda Rehabilitation | Brgy. Sto. Nino, Quinapondan, Eastern Samar | 2016-09-29 | 1st | DOTC | LF | 47.3605 | 270 | 2016-05-11 | 2016-02-06 | 0.69 | O | 0.3551 | 0.3 | 0.15 | 0.03 | 0.049 | 0.05 | 93.41 | -
B. M. MARKETING | 9852 | L | AAA | MB | GE | Road Opening/Road Upgrading Along Bagahupi-Babatngon-Sta. Cruz-Caray-caray Section, 1st District, Babatngon, Leyte | 1st District, Babatngon, Leyte | 2015-11-10 | Final | Leyte First DEO | LF | 38.884 | 231 | 2015-01-30 | 2015-09-17 | - | C | 0.426 | 0.133 | 0.3 | - | - | - | 85.9% | 85.9% Satisfactory
B. M. Marketing | 9852 | L | AAA | MB | GE1 | Borongan Airport Development Project | Borongan City, Eastern Samar | 2012-11-27 | 1st | DOTC | LF | 14.283 | 120 | 2012-09-12 | 2013-01-09 | 44.76 | O | 0.38 | 0.3 | 0.15 | 0.03 | 0.07 | 0.05 | 98 | -
B. P. Cruz Builders & Trading | 33272 | L | A | SB | GE | Rehabilitation of Songkoy-Honrado-Sering Road | Socorro, Surigao del Norte | 2015-04-21 | 1st | TIEZA | LF | 15.9 | 225 | 2014-08-29 | 2015-04-10 | -49.95 | O | 0.4 | 0.3 | 0 | 0.015 | 0.058 | 0.05 | 82.33 | -
B. P. CRUZ BUILDERS & TRADING | 33272 | L | A | MA | GE | Rehabilitation of Songkoy-Honrado-Sering Road | Socorro, Surigao del Norte | 2015-07-30 | Final | TIEZA | LF | 16 | 285 | 2014-08-29 | 2015-06-09 | 0 | C | 0.443 | 0.2 | 0.3 |  |  |  | 94.3 | 87.10% Satisfactory
B. P. CRUZ BUILDERS & TRADING | 33272 | L | A | MA | GE | Construction of Tourism Center and Souvenir Shop | San Julian Sur,Vigan City, Ilocos Sur | 2015-12-10 | 1st | TIEZA | LF | 9.9 | 201 | 2015-04-01 | 2015-10-19 |  | O | 0.395 | 0.3 | 0 | 0.03 | 0.047 | 0.05 | 82.22 | -
B. P. Cruz Builders and Trading | 33272 | L | A | SB | GE | Tourism Center and Souvenir Shop | San Julian, Vigan City, Ilocos Sur | 2016-03-09 | 2nd | TIEZA | LF | 10 | 201 | 2016-04-01 | 2016-01-21 | -1.26 | O | 0.36 | 0.287 | 0.137 | 0.03 | 0.047 | 0.025 | 88.6
B. P. Cruz Builders and Trading | 33272 | L | A | SB | GE | Concreting of Access Road Leading to Mt. Pinatubo | Brgy. Sapang Uwak, Porac, Pampanga | 2016-05-19 | 1st | TIEZA | LF | 30 | 210 | 2016-01-31 | 2016-08-30 | -9.09 | O | 0.381 | 0.3 | 0.06 | 0.03 | 0.07 | 0.05 | 89.12
B. Vicencio Construction | 9687 | L | A | MB | GE | Completion of Padog Bridge along Dinagat - Loreto Road, Tubajon, Dinagat Islands | Tubajon, Dinagat Islands | 2014-10-27 | 1st | XIII | LF | 7.469 | 219 | 2014-03-10 | 2014-10-14 | -10.58% | O | 0.326 | 0.3 | 0.044 | 0.02 | 0.042 | 0.033 | 76.5% | 76.50% Unsatisfactory
B. Vicencio Construction |  | L |  |  |  | Help for Catubig Agricultural Advancement Project HCAAP-LCB-C2-2012 | Catubig, Northern Samar/Region 8 | 2014-03-15 | 1st | NIA | LF | 15.995 | 597 | 2012-07-27 | 2012-11-24 | 1.95 | SUSPENDED | 0.3657 | 0.1766 | 0.15 | 0.03 | 0.07 | 0.05 | 84.23 | -
B. Vicencio Construction | 9687 | L | A | MB | GE1 | Const. of Altavas-Jamindan Rd., K0324+085-K0324+844 | Altavas, Aklan | 2013-03-19 | 1st | VI | LF | 20.307 | 142 | 2013-01-15 | 2013-06-05 | 26.67 | O | 0.333 | 0.3 | 0.15 | 0.018 | 0.04 | 0.033 | 87.4 | -
B. Vicencio Construction | 9687 | L | A | MB | GE1 | Concreting of Antequera-Catagbacan (Loon) Rd. |  | 2009-09-01 | 1st | VII |  | 18.313 | 172 |  |  |  | O | 0.375 | 0.246 | 0.15 | 0.03 | 0.042 | 0.05 | 89.3 | -
B. Vicencio Construction | 9687 | L | A | MB | GE | Rehab./Reconst. Along Tacloban Baybay South Road KO915+(-267) - KO915+(-118.20) and KO915+(-118.20) - KO915+607.80 | Tacloban City | 2014-08-15 | 1st | VIII | LF | 13.054 | 153 | 2014-02-21 | 2014-07-23 | -3 | O | 0.334 | 0.3 | 0.12 | 0.022 | 0.04 | 0.017 | 83.3 | -
B. Vicencio Construction | 9687 | L | A | MB | GE1 | Replacement of Bugtong Bridge along Daang Maharlika (SM) (San Isidro-San Juanico Bridge) | Calbayog City, Samar | 2013-08-13 | 2nd | VIII | LF | 32.855 | 205 | 2013-02-06 | 2013-09-28 | 2.44 | O | 0.345 | 0.258 | 0.15 | 0.03 | 0.06 | 0.033 | 87.6 | -
B. Vicencio Construction | 9687 | L | A | MB | GE1 | Replacement of Bugtong Bridge along Daang Maharlika (SM) (San Isidro-San Juanico Bridge) | Calbayog City, Samar | 2013-03-19 | 1st | VIII | LF | 31.952 | 160 | 2013-02-06 | 2013-07-15 | 15.37 | O | 0.37 | 0.225 | 0.15 | 0.03 | 0.05 | 0.05 | 87.5 | -
B. Vicencio Construction | 9687 | L | A | MB | GE1 | Rehab./Reconst./Upgrading of Damaged Paved National Roads Calbayog-Catarman Road |  | 2009-06-02 | 1st | VIII |  | 94.55 | 300 |  |  |  | O | 0.303 | 0.238 | 0.089 | 0.03 | 0.045 | 0.033 | 73.8 | -
B. Vicencio Construction | 9687 | L | A | MB | GE1 | Const. (Road Opening) of Missing Link of Calbayog Diversion Road, Cagsalaosao-Gadgaran Road Section |  | 2009-06-02 | 1st | VIII |  | 18.794 | 150 |  |  |  | O | 0.223 | 0.24 | 0.15 | 0.03 | 0.05 | 0.033 | 72.6 | -
B. Vicencio Construction | 9687 | L | A | MA | GE2 | Const. of Maasin Shore Protection/Seawall |  | 2008-08-29 | 1st | VIII |  | 3.809 | 240 |  |  |  | O | 0.3 | 0.1 | 0.1 | 0 | 0.022 | 0.2 | 72.2 | -
B. Vicencio Construction | 9687 | L | A | MA | GE1 | Rehab./Impvt. of Brdy. Mahaplag-Sogod Road (Dampoy) |  | 2009-05-27 | 2nd | VIII |  | 9.446 | 310 |  |  |  | O | 0.345 | 0.258 | 0.15 | 0.03 | 0.047 | 0.033 | 86.3 | -
B. Vicencio Construction | 9687 | L | A | MB | GE1 | Concreting of Villaba-Leyte Road Km. 1015+820-Km. 1017+420 |  | 2009-06-02 | 1st | VIII |  | 31.694 | 330 |  |  |  | O | 0.339 | 0.24 | 0.15 | 0.022 | 0.037 | 0.033 | 82.1 | -
B. Vicencio Construction | 9687 | L | A | MB | GE1 | Concreting of Tawid-Guadalupe Circumferential Road |  | 2009-03-06 | 1st | VIII |  | 7.517 | 180 |  |  |  | O | 0.338 | 0.238 | 0.15 | 0.015 | 0.03 | 0.05 | #VALUE! | -
B. Vicencio Construction | 9687 | L | A | MB | GE1 | Rehab./Impv't of Brgy. Mahaplag-Sogod Road (Dampoy) |  | 2009-03-06 | 1st | VIII |  | 9.4456 | 310 |  |  |  | O | 0.3 | 0.18 | 0.15 | 0.015 | 0.033 | 0.05 | #VALUE! | -
B. Vicencio Construction | 9867 | L | A | MA | GE1 | Road Upgrading of Junction Himay-Angan-Silago-Abuyog Road |  | 2009-09-08 | 1st | VIII |  | 53.21 | 365 |  |  |  | O | 0.35 | 0.3 | 0.15 | 0.008 | 0.035 | 0.05 | 89.3 | -
B. Vicencio Construction | 9867 | L | A | MA | GE1 | Rehab./Reconst./Upgrading of Calbayog-Catarman Road |  | 2009-09-10 | 2nd | VIII |  | 94.551 | 300 |  |  |  | O | 0.32 | 0.3 | 0.15 | 0.023 | 0.05 | 0.05 | 89.3 | -
B. Vicencio Construction | 9687 | L | A | MB | GE1 | Conc. of Villaba-Leyte Road, Km. 1015+820-Km. 1017+420 |  | 2009-09-05 | 2nd | VIII |  | 31.695 | 330 |  |  |  | O | 0.354 | 0.248 | 0.15 | 0.018 | 0.045 | 0.05 | 86.5 | -
B. Vicencio Construction | 9687 | L | A | MB | GE1 | Road Opening/Impvt. (Conc.) of Calbayog Diversion Road (IS) Sta.1+247.50-Sta.15+530 w/ exceptions | Calbayog City, Samar | 2012-03-26 | 1st | VIII | LF | 88.3579 | 270 | 2011-08-22 | 2012-05-18 | 31.39 | O | 0.303 | 0.3 | 0.15 | 0.03 | 0.045 | 0.05 | 87.8 | -
B. Vicencio Construction | 9687 | L | A | MB | GE1 | Rehab./Reconst. of Catbalogan Diversion Rd. (Sta.0+468.25-Sta.5+530.59) w/ exception | Catbalogan, Samar | 2013-03-18 | 2nd | VIII | LF | 95.459 | 390 | 2012-03-05 | 2013-03-29 | 1.32 | O | 0.296 | 0.253 | 0.15 | 0.03 | 0.06 | 0.05 | 83.9 | -
B. Vicencio Construction | 9687 | L | A | MB | GE1 | Rehab./Reconst. of Catbalogan Diversion Rd., (Sta.0+468.25-Sta.5+530.59 w exceptions) | Catbalogan, Samar | 2012-08-09 | 1st | VIII | LF | 95.459 | 270 | 2012-03-05 | 2012-11-29 | -2.87 | O | 0.336 | 0.3 | 0.121 | 0.03 | 0.037 | 0.033 | 85.7 | -
B. VICENCIO CONSTRUCTION | 9687 | L | A | MB | GE | Construction of New Permanent Bridges, Balutakay Bridge 2 (Digos) along Davao-Cotabato Road (Jct. Digos-Cotabato Section) | Davao del Sur | 2015-06-04 | 1st | Davao del Sur 1st | LF | 33.666 | 210 | 2015-03-03 | 2015-09-28 | (+)0.04% | O | 0.371 | 0.225 | 0.15 | 0.03 | 0.051 | 0.033 | 86% | -
B. VICENCIO CONSTRUCTION | 9687 | L | A | MB | GE | Cluster I - Const. & Maint. Of Bridge along Nat'l. Roads Widening of Permanent Bridges to more than two lanes Boton Bridge (B00345LZ) Himaoyon Bridge (B00348LZ) and Suji Bridge along Daang Maharlika Road | Casiguran, Sorsogon | 2015-06-09 | 1st | Sorsogon 1st | LF | 47.231 | 270 | 2015-01-29 | 2015-10-27 | 0.53% | O | 0.391 | 0.297 | 0.15 | 0.03 | 0.05 | 0.033 | 95.1% | -
B. VICENCIO CONSTRUCTION | 9687 | L | A | MB | GE | Widening along National Road (N1) Daang Maharlika (IZ) Asian Highway - 26 K0590+243 - K0592+000 w/ exceptions | Casiguran, Sorsogon | 2015-06-09 | 1st | Sorsogon 1st | LF | 45.715 | 150 | 2015-02-27 | 2015-07-26 | 0.53% | O | 0.387 | 0.262 | 0.15 | 0.024 | 0.051 | 0.05 | 92.4% | -
B. VICENCIO CONSTRUCTION | 9687 | L | A | MB | GE | Road Upgrading (Unpaved to Paved) based on Gravel to Road Strategies, Traffic Benchmark for Upgrading to Paved Standard (HDM-4 Project Analysis Intermittent Sections), Jct.Taft-Oras-San Policarpio-Arteche Road, K0963+906-K0964+347, K0969-K0969+970 | Jct.Taft-Oras-San Policarpio-Arteche Road, K0963+906-K0964+347, K0969-K0969+970 | 2015-06-29 | 1st | Eastern Samar DEO | LF | 38.15 | 120 | 2015-03-16 | 2015-07-13 | - | O | 0.363 | 0.238 | 0.15 | 0.03 | 0.035 | 0.033 | 84.9% | -
B. VICENCIO CONSTRUCTION | 9687 | L | A | MA | GE | Rehabilitation/Improvement of Catumsan Flood Control, Arteche, Eastern Samar | Arteche, Eastern Samar | 2015-06-29 | Final | Eastern Samar DEO | LF | 18.556 | 121 | 2015-03-03 | 2015-07-01 | - | C | 0.415 | 0.133 | 0.3 | - | - | - | 84.8% | *84.8% Satisfactory
B. VICENCIO CONSTRUCTION | 9687 | L | A | MA | GE | Local Infrastucture Program - Drainage and Protection Works in Payahan, Calbayog City, Samar 1st LD | Calbayog City, Samar 1st LD | 2015-06-28 | Final | Samar First DEO | LF | 8.919 | 120 | 2015-03-13 | 2015-07-10 | - | C | 0.41 | 0.2 | 0.3 | - | - | - | 91% | *91% Very Satisfactory
B. VICENCIO CONSTRUCTION | 9687 | L | A | MA | GE | Construction/Extension of Calambis Flood Control along Biliran Circumferential Road, Naval, Biliran Lone District | Naval, Biliran Lone District | 2015-06-03 | Final | Biliran DEO | LF | 15.807 | 106 | 2015-02-06 | 2015-05-22 | - | C | 0.387 | 0.2 | 0.3 | - | - | - | 88.7% | *88.7% Satisfactory
B. VICENCIO CONSTRUCTION | 9687 | L | A | MB | GE | Construction of New Permanent Bridges, Napuro RCBC along Daang Maharlika, (SM) (Sn. Isidro-Sn. Juanico Bridge), Sta. Margarita, Samar | Sta. Margarita, Samar | 2015-09-02 | 1st | Samar 1st DEO | LF | 9.004 | 221 | 2015-01-30 | 2015-09-07 | (-)46.67 | O | 0.34 | 0.3 | 0 | 0.01 | 0.045 | 0.017 | 71.2% | -
B. VICENCIO CONSTRUCTION | 9687 | L | A | MA | GE | Replacement of Paragua Bridge II Along Dinagat-Loreto Road | Tubajon, Dinagat Islands | 2005-08-31 | 1st | Dinagat Island | LF | 23.129 | 252 | 2015-03-20 | 2015-11-26 | (-) 2.83% | O | 0.383 | 0.24 | 0.122 | 0.03 | 0.05 | 0.033 | 85.8% | -
B. VICENCIO CONSTRUCTION | 9687 | L | A | MB | GE | Road Improvement of Matnog- Sta. Magdalena - Bulusan Road leading to Bulusan National Park, Sorsogon, Brgys. Tinampo, Cogon and Lalud, Bulusan, Sorsogon | Brgys. Tinampo, Cogon and Lalud, Bulusan, Sorsogon | 2015-11-18 | 1st | Sorsogon 2nd | LF | 37.1516 | 135 | 2015-08-06 | 2015-12-18 | -4.79% | OG | 0.383 | 0.287 | 0.102 | 0.008 | 0.035 | 0.017 | 83.2% | 83.2% Satisfactory
B. VICENCIO CONSTRUCTION | 9687 | L | A | MA | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads including Drainage (Intermittent Sections), Concreting of Iloilo - Capiz Road (New Route). Brgy. Malusgod, Pototan, Iloilo, KO032+291-KO032+803. | Brgy. Malusgod, Pototan, Iloilo | 2015-11-17 | Final | Iloilo 2nd | LF | 9.4707 | 54 | 2015-10-14 | 2015-12-07 | 0.00% | C | 0.333 | 0.2 | 0.3 | - | - | - | 83.3% | 83.3% Satisfactory
B. Vicencio Construction / EZJones Construction, Inc. (JV) | JV-11-120 | L | A | MA | GE2 | Const./Extension of Catarman River Flood Control | Catarman, Northern Samar | 2013-03-21 | 1st | VIII | LF | 85.828 | 290 | 2012-07-17 | 2013-05-02 | -2.88 | O | 0.37 | 0.3 | 0.12 | 0.03 | 0.045 | 0.033 | 89.8 | -
B. Vicencio Construction / Jet Construction Supply (JV) | JV-11-186 | L | A | MB | GE1 | Conc. of Guimaras Circ. Rd., K067+380-K073+100 w/ exceptions | Nueva Valencia, Guimaras | 2012-11-19 | 1st | VI | LF | 102.3 | 450 | 2012-03-05 | 2013-05-28 | 6.38 | O | 0.366 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 89.1 | -
B. VICENCIO CONSTRUCTION / MWJ CONSTRUCTION JOINT VENTURE | JV-14-268 | L | A | MB | GE | Widening of Daang Maharlika, K0948+000 - K0949+000, K0950+00 - K0953+620 (Section ID: S00083LT), Mayorga, Leyte | Mayorga, Leyte | 2015-06-30 | 1st | Regional Office No. VIII | LF | 118.929 | 260 | 2015-02-13 | 2015-10-30 | - | O | 0.398 | 0.238 | 0.15 | 0.03 | 0.045 | 0.033 | 89.4% | -
B. Vicencio Construction / Victoria Development and Construction Supply (JV) |  | L |  |  | GB1 | Const. of 2-Storey, 2-CL Catbalogan NCHS | Catbalogan City | 2013-08-15 | 1st | VIII | LF | 2.104 | 168 | 2013-03-21 | 2013-09-04 | 3.96 | O | 0.324 | 0.226 | 0.15 | 0.03 | 0.058 | 0.033 | 82.1 | -
B. Vicencio Construction/JQD Construction and General Services Joint Venture | JV-13-371 | L | A | MB | GE | Road Upgrading (gravel to Paved) along San Ricardo - Bil-atan Km. 1101+000 - Km. 1102+000 | San Ricardo, Southern Leyte | 2014-08-05 | 1st | VIII | LF | 35.2119 | 179 | 2014-02-14 | 2014-08-11 | 7.735 | O | 0.382 | 0.222 | 0.15 | 0.022 | 0.045 | 0.017 | 83.8 | -
B. VICENCIO CONSTRUCTION/MWJ CONSTRUCTION JOINT VENTURE | JV-14-268 | L | A | MB | GE | Widening of Daang Maharlika, K0948+000-K0949+000, K0950+00-K0953+620 (Section ID:S00083LT), Mayorga, Leyte | Mayorga, Leyte | 2015-11-12 | 1st | Regional Office No. VIII | LF | 118.9291 | 380 | 2015-02-13 | 2016-02-27 | (+)2.25% | OG | 0.348 | 0.241 | 0.15 | 0.022 | 0.065 | 0.05 | 87.6% | 87.6% Satisfactory
B.C. Cuerpo Construction Corporation | 11898 | L | A | MB | GB | Local Infrastructure Program: Construction of Multi-Purpose Building | Poblacion, Banga, South Cotabato | 2014-10-21 | 1st | XII | LF | 4.7024 | 150 | 2014-08-06 | 2015-01-02 | 0.12% | O | 0.391 | 0.23 | 0.15 | 0.02 | 0.048 | 0.033 | 87.2% | 87.20% Satisfactory
B.C. CUERPO CONSTRUCTION CORPORATION | 11898 | L | A | MB | GE | Widening-Daang Maharlika K0908+000-KO909+111, Tacloban City | Tacloban City | 2015-09-01 | 1st | Tacloban City | LF | 43.855 | 179 | 2015-06-24 | 2015-12-19 | (+)30.00 | O | 0.317 | 0.294 | 0.15 | 0.02 | 0.035 | 0.05 | 86.6% | -
B.K. SY TU CONSTRUCTION | 12655 | L | B | MA | GB | Construction of Senior High School Classroom in Areas Experiencing Acute Classroom Shortage: Three (3) Storey, Nine Classroom School Building, Capas High School, Conception, Tarlac | Conception, Tarlac | 2015-11-18 | 1st | Tarlac Second DEO | LF | 14.579 | 210 | 2015-08-19 | 2016-03-15 | 7.34% | OG | 0.382 | 0.24 | 0.15 | 0.015 | 0.051 | 0.05 | 88.8% | 88.8% Satisfactory
B.M. Marketing | 9852 | L | AAA | LA |  | Tacloban Airport Development Project (Immediate Rehabilitation of Tacloban Airport) | Tacloban City, Leyte/Region VIII | 2015-03-18 | 2nd | DOTC | L | 46.606 | 270 | 2014-03-07 | 2015-04-18 | -5.15 | O | 0.3953 | 0.3 | 0.0985 | 0.03 | 0.042 | 0.05 | 91.58 | -
B.M. Marketing | 9852 | L | AAA | MB |  | Tacloban Airport Development Project (Asphalt Overlay of Runway and Construction of Turn-Around Pad | Tacloban City, Leyte/Region VIII | 2015-03-19 | 2nd | DOTC | L | 123.417 | 240 | 2014-06-20 | 2015-05-15 | 5.37 | O | 0.3885 | 0.3 | 0.15 | 0.02 | 0.035 | 0.05 | 94.35 | -
B.M. Marketing | 9852 | L |  | MB |  | Tacloban Airport Development Project | Brgy.San Jose, Tacloban City/ Region VIII | 2014-06-24 | 1st | DOTC | LF | 42.467 | 180 | 2014-03-07 | 2014-09-02 | 4.05 | O | 0.3786 | 0.3 | 0.15 | 0.03 | 0.035 | 0.05 | 94.36 | -
B.M. Marketing | 9852 | L | AAA | MB | GE1 | Rehab./Repair/Improvement of Baras-Candahug-Manlurip-DZR Airport Rd. | Palo, Leyte | 2013-08-20 | 1st | VIII | LF | 19.009 | 130 | 2013-05-20 | 2013-09-26 | 36.17 | O | 0.377 | 0.209 | 0.15 | 0.03 | 0.047 | 0.033 | 84.6 | -
B.M. Marketing | 9852 | L | AAA | MB | GE1 | Concrete Paving of Biliran Circ. Rd., Km.1073+760-Km.1074+640 (Pinamihagan-Tanghas Rd. Sect.) | Biliran Province | 2013-03-12 | 1st | VIII | LF | 20.089 | 150 | 2013-02-07 | 2013-07-07 | -1.99 | O | 0.312 | 0.141 | 0.13 | 0.03 | 0.045 | 0.033 | 69.1 | -
B.M. Marketing | 9852 | L | AAA | MB | GE1 | Concrete Paving of Biliran Circ. Road, Tanghas-Kaulangohan Rd. Sect., Km.1074+580-Km.1077+761 w/ exceptions | Caibiran, Biliran Province | 2012-08-07 | 1st | VIII | LF | 47.981 | 280 | 2012-02-01 | 2012-11-07 | 31.88 | O | 0.334 | 0.3 | 0.15 | 0.03 | 0.04 | 0.05 | 90.4 | -
B.M. Marketing & Fiat Construction Services (JV) | 9852 | L |  | MB | GE1 | Tacloban Airport Development Project | Brgy. San Jose, Tacloban City | 2013-08-15 | 1st | DOTC | L | 176.112 | 300 | 2013-04-25 | 2013-04-25 | 20.44 | O | 0.329 | 0.277 | 0.15 | 0.03 | 0.056 | 0.05 | 89.2 | -
B.M.K. Construction | 8292 | L | AAA | LB | GE1 | Impvt. of Lingayen-Binmaley (via Matalava), Lingayen-Binmaley |  | 2009-08-28 | 1st | I |  | 23.809 | 359 |  |  |  | O | 0.349 | 0.3 | 0.077 | 0.03 | 0.055 | 0.033 | 84.4 | -
B.M.K. Construction | 8292 | L | AAA | LA | GE | Construction/Improvement of Sabangan-Sagada Road Leading to Poblacion Sagada, Sumaguing Cave, Hanging Coffins, Bomod-ok Falls, Bokong Falls, "MARCOS" Cave (Declared Tourist Destination) | Sagada, Mt. Province | 2014-11-22 | 1st | CAR | LF | 135.0998 | 421 | 2014-04-28 | 2015-06-22 | 19.59% | O | 0.346 | 0.238 | 0.15 | 0.03 | 0.056 | 0.05 | 87% | 87.00% Satisfactory
B.M.K. Construction | 8292 | L | AAA | LA | GE1 | Const./Continuation/Completion of Bagulin Bridge (Phase III) | Bagulin, La Union | 2013-03-18 | 1st | I | LF | 109.073 | 645 | 2011-08-23 | 2013-05-28 | 0.82 | O | 0.328 | 0.3 | 0.15 | 0.03 | 0.055 | 0.05 | 91.3 | -
B.M.K. Construction | 8292 | L | AAA | MB | GE2 | Const. of Slope Protection/Flood Control in La Union 2nd Dist.-Groins & Extension of Groins, Brgy. San Carlos | Caba, La Union | 2013-03-12 | 1st | I | LF | 27.359 | 240 | 2013-01-16 | 2013-09-12 | 61.68 | O | 0.379 | 0.3 | 0.15 | 0.015 | 0.015 | 0.017 | 87.6 | -
B.M.K. Construction | 8292 | L | AAA | MB | GE2 | CP 45, Restoration/Rehab. of Flood Control Facilities along Banila River in Umingan, under POPSTIRP, Flood Control Component | Pangasinan | 2011-08-14 | 1st | I / MFCP II-PMO | LF | 29.035 | 90 | 2011-05-26 | 2011-08-23 | 9.82 | O | 0.32 | 0.24 | 0.15 | 0.03 | 0.06 | 0.05 | 85 | -
B.M.K. Construction | 8292 | L | AAA | LA | GE1 | Restoration of Collapsed Retaining Wall & Damaged PCCP along Baguio-Bontoc Rd., Km.267+700-Km.279+830 (POPSTIRP) | Tublay, Benguet | 2012-11-21 | 1st | CAR | LF | 87.101 | 345 | 2011-11-15 | 2012-10-25 | -2.79 | O | 0.37 | 0.3 | 0.044 | 0.03 | 0.055 | 0.033 | 83.2 | -
B.M.K. Construction | 8292 | L | AAA | LA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rd., K0251+000-K0253+600 Manila North Road | Bauang, La Union | 2012-08-08 | 1st | I | LF | 44.805 | 240 | 2012-01-11 | 2012-09-07 | 6.48 | O | 0.304 | 0.3 | 0.15 | 0.03 | 0.05 | 0.033 | 86.7 | -
B.M.K. Construction | 8292 | L | AAA | LA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rds., K0214+243-K0216+613, Manila North Rd. | Rosario, La Union | 2012-08-08 | 1st | I | LF | 36.908 | 195 | 2012-02-16 | 2012-08-29 | 1.34 | O | 0.231 | 0.3 | 0.15 | 0.03 | 0.06 | 0.05 | 82.1 | -
B.M.K. CONSTRUCTION | 8292 | L | AAA | LA | GE | Construction/Improvement of Sabangan-Sagada Road Leading to Poblacion Sagada, Sumaguing Cave, Hanging Coffins, Bomod-ok Falls, Bokong Falls, "Marcos" Cave, (Declared Tourist Destinations) | Sagada, Mt. Province | 2015-06-04 | 1st | CAR | LF | 135.1 | 421 | 2014-04-28 | 2015-06-22 | (-) 12.34% | O | 0.343 | 0.3 | 0.027 | 0.024 | 0.037 | 0.033 | 76.4% | -
B.M.K. Construction / Jann-Norris Construction & Supplies (JV) | JV-12-367 | L | AAA | MB | GE2 | Repair/Maint. of Flood Control Structure along Magat River, Batu Sect. | Bambang, Nueva Vizcaya | 2013-03-20 | 1st | II | LF | 18.585 | 120 | 2012-12-18 | 2013-04-16 | 18.47 | O | 0.324 | 0.3 | 0.15 | 0.03 | 0.047 | 0.033 | 88.4 | -
B.M.K. Construction / Jasa Builders (JV) | JV-11-394 | L | AAA | LA | GE1 | Rehab./Reconst./Upgrading of Pangasinan-Zambales Rd. a)Km.324+035-Km.324+895; b)Km.325+108-Km.326+552; c)Km.327+033-Km.327+293; d)Km.332+084-Km.332+560; e)Km.335+000-Km.337+500; f)Km.339+700-Km.339+780 | Alaminos City & Sual, Pangasinan | 2013-03-15 | 1st | I | LF | 98.561 | 360 | 2012-05-25 | 2013-05-19 | 13.88 | O | 0.375 | 0.223 | 0.15 | 0.03 | 0.055 | 0.05 | 88.3 | -
B.M.K. Construction / R.N.G.M. Construction Joint Venture | JV-12-655 | L | AAA | LA | GE1 | Const./Widening/Upgrading of Access Rd. Leading to Tourist Destination, Sabang | Baler, Aurora | 2013-08-10 | 1st | III | LF | 43.292 | 214 | 2013-03-27 | 2013-10-26 | 0.31 | O | 0.309 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 82.9 | -
B.M.K. Construction / Viking Construction and Builders (JV) | JV-12-296 | L | AAA | LA | GE1 | Replacement of Bimmeclat Bridge K0436-386 | Cabugao, Ilocos Sur | 2013-03-20 | 1st | I | LF | 27.325 | 180 | 2013-02-11 | 2013-08-09 | -5.4 | O | 0.382 | 0.262 | 0.096 | 0.03 | 0.043 | 0.033 | 84.6 | -
B.M.K. Construction / Viking Construction and Supplies (JV) | JV-12-296 | L | AAA | LA | GE1 | Replacement of Bimmeclat, KO436-386 | Cabugao, Ilocos Sur | 2013-08-13 | 2nd | I | LF | 27.325 | 202 | 2013-02-11 | 2013-08-31 | -8.55 | O | 0.394 | 0.3 | 0.065 | 0.03 | 0.047 | 0.033 | 86.9 | -
B.M.K. Construction / Viking Construction and Supplies (JV) | JV-12-294 | L | AAA | MB | GE2 | Repair/Rehab./Const. of Flood Control Structure, Banbangar | Bangued, Abra | 2013-08-14 | 1st | CAR | LF | 37.853 | 260 | 2012-12-11 | 2013-08-28 | 0.21 | O | 0.333 | 0.3 | 0.15 | 0.03 | 0.053 | 0.033 | 89.9 | -
B.P. Cruz Builders and Trading | 33272 | L | A | MA | GE2 | Flood Control & Drainage Project along Manila North Road (MNR) @ K082+(-750)-K094+000 (w/ exception) Angeles City to Mabalacat | Pampanga | 2013-08-06 | 1st | III | LF | 22.797 | 180 | 2013-03-05 | 2013-08-31 | 0.96 | O | 0.343 | 0.24 | 0.15 | 0.03 | 0.051 | 0.033 | 84.7 | -
B.P. Cruz Builders and Trading | 33272 | L | A | MA | GB1 | Repair/Rehab. of Jose S. Lapid District Hospital, Phase II (Formerly Porac District Hospital), Babo Sacan | Porac, Pampanga | 2013-03-11 | 1st | III | LF | 18.594 | 75 | 2013-01-07 | 2013-03-23 | 0.67 | O | 0.391 | 0.2 | 0.15 | 0.015 | 0.041 | 0.033 | 83 | -
B.P. CRUZ BUILDERS AND TRADING | 33272 | L | A | MA | GB | Construction/Rehabilitation of Porac Public Market, Cangatba, Porac, Pampanga | Porac, Pampanga | 2015-06-03 | 1st | Pampanga 2nd DEO | LF | 28.174 | 180 | 2015-01-22 | 2015-07-20 | 1.65% | O | 0.395 | 0.3 | 0.15 | 0.023 | 0.048 | 0.05 | 96.6% | -
B.R.G. Construction | 21931 | L | C | SB | GE | Construction of Bridges, New (along Arterial Road) Pacquet Bridge along Aritao-Quirino Road | Kasibu, Nueva Vizcaya | 2014-08-15 | 1st | II | LF | 9.1291 | 150 | 2014-04-21 | 2014-09-17 | -6.48 | O | 0.311 | 0.24 | 0.085 | 0.024 | 0.025 | 0.017 | 70.2 | -
B.R.G. Construction | 21931 | L | C | SB | GE1 | Concreting of Aritao-Quirino Road, Bua Section |  | 2009-06-04 | 1st | II |  | 9.65 | 104 |  |  |  | O | 0.375 | 0.24 | 0.15 | 0.03 | 0.047 | 0.05 | 89.2 | -
B.R.G. CONSTRUCTION | 21931 | L | B | MA | GE | Construction of Bridges New (along Arterial Rd), Pacquet Bridge along Aritao-Quirino Road | Kasibu, Nueva Vizcaya | 2015-06-09 | Final | Nueva Vizcaya 2nd DEO | LF | 9.421 | 180 | 2014-04-21 | 2014-10-17 | 0% | C | 0.365 | 0.2 | 0.3 | - | - | - | 86.5% | *76.72% Unsatisfactory
B.Vicencio Construction | 9687 | L | A | MA | GE | Construction of Flood Control Structure along Burayan River | Tacloban City | 2014-10-30 | 1st | VIII | LF | 9.8735 | 110 | 2014-08-07 | 2014-11-24 | -5% | O | 0.36 | 0.3 | 0.1 | 0.03 | 0.055 | 0.033 | 87.8% | 87.80% Satisfactory
B.Vicencio Construction | 9687 | L | A | MA | GE | Rehabilitation of Flood Control Structure, 1st LD Brgy. San Policarpio Calbayog City, Samar | Calbayog City, Samar | 2014-08-11 | 1st | VIII | LF | 13.9541 | 172 | 2014-02-24 | 2014-08-14 | 0.44 | O | 0.356 | 0.24 | 0.15 | 0.03 | 0.052 | 0.033 | 86.1 | -
B-12 CONST & TRADING CORP. | 31997 | L | A | MB | GE | Concreting of Road Barangay Manibaug, Porac, Pampanga | Porac, Pampanga | 2015-09-05 | Final | Pampanga Second DEO | LF | 13.822 | 150 | 2014-07-31 | 2014-12-27 | - | C | 0.312 | 0.2 | 0.3 | - | - | - | 81.2% | *83.72% Satisfactory
B-12 CONST & TRADING CORP. | 31997 | L | A | MB | GE | Road Opening Capas-Botolan Road, Tarlac Section 2nd LD Realigned to Paving of Shoulder along Tarlac - Sta. Rosa Road, Tarlac City KO 144+066.80 - KO 147+778.00 w/ exception, Tarlac City | Tarlac City | 2015-09-03 | Final | Tarlac First DEO | LF | 27.923 | 160 | 2014-07-23 | 2014-12-29 | 1.25% | C | 0.324 | 0.13 | 0.3 | - | - | - | 75.4% | *83.32% Satisfactory
B-12 Construction and Trading Corporation | 31997 | L | A | MB | GE | Road Opening Capas-Botolan Road, Tarlac Section 2nd LD Realigned to Paving of Shoulder along Tarlac-Sta. Rosa Road, Tarlac City, KO144+066.80 - KO147+778.00 w/ exception | Tarlac City | 2014-11-20 | 1st | III | LF | 27.9226 | 160 | 2014-07-23 | 2014-12-29 | 3% | O | 0.396 | 0.24 | 0.15 | 0.03 | 0.037 | 0.033 | 88.6% | 88.60% Satisfactory
B-12 Construction and Trading Corporation | 31997 | L | A | MB | GE | Concreting of Road | Barangay Manibaug, Porac, Pampanga | 2014-11-20 | 1st | III | LF | 14.5778 | 150 | 2014-07-31 | 2014-12-27 | 7.86% | O | 0.372 | 0.24 | 0.15 | 0.024 | 0.035 | 0.033 | 85.4% | 85.40% Satisfactory
B-12 Construction and Trading Corporation | 31997 | L | A | MA | GE1 | Prev. Maint. of Angeles-Porac-Floridablanca-Dinalupihan Rd. | Porac, Pampanga | 2013-03-11 | 1st | III | LF | 12.371 | 58 | 2013-02-06 | 2013-04-04 | 9.59 | O | 0.348 | 0.202 | 0.15 | 0.02 | 0.04 | 0.033 | 79.3 | -
B2K Lumber Construction Supplies and Services | 33069 | L | B | MA | GE1 | a. Prev. Maint. (Int. Sect.) Secondary Daet-Mercedes Rd. K0343+(-531)-K0343+469, K0343+469, K0344+369, K0369+165-K0345+165 & K0346+000-K0348+661 ERRATA to: Rd. Widening Daang Maharlika (w/ exceptions) K0340+174-K0343+679 | Daet, Camarines Norte | 2013-03-23 | 1st | V | LF | 40.491 | 150 | 2013-01-10 | 2013-06-01 | 14.64 | O | 0.286 | 0.29 | 0.15 | 0.024 | 0.04 | 0.033 | 82.3 | -
B2K Lumber, Construction Supplies and Services | 33069 | L | B | MA | GE | Construction/Improvement of Access Roads leading to Airports, Seaports & Tourism Destinations, Pres. Cory Aquino Blvd. to Bagasbas Beach | Talisay, Camarines Norte | 2014-08-05 | 1st | V | LF | 14.3514 | 105 | 2014-05-16 | 2014-08-28 | 0 | O | 0.322 | 0.3 | 0.15 | 0.02 | 0.025 | 0.05 | 86.7 | -
B5 BUILDERS & SUPPLIES | 0 | L | C | SB | GB | Const. of 2-Storey / 6-Classroom of Senior High School at Malatoc | Victoria, Oriental Mindoro | 2015-11-20 | 1st | Mindoro Oriental DEO | LF | 8.3274 | 150 | 2015-09-09 | 2016-02-05 | 0 | OG | 0.327 | 0.3 | 0.15 | 0.01 | 0.023 | 0.05 | 86% | 86% Satisfactory
Badoc Builders & Supply (Formerly: Badoc Builders) | 31564 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Paved), Batac-Pinili via Maipalig Rd., K0480+112-K0481+104 | Ilocos Norte | 2013-03-21 | 1st | I | LF | 9.309 | 80 | 2013-01-30 | 2013-03-31 | 3.58 | O | 0.35 | 0.227 | 0.15 | 0.024 | 0.035 | 0.033 | 81.9 | -
BADOC BUILDERS & SUPPLY (Formerly: Badoc Builders) | 31564 | L | B | MA | GE | Concreting of Farm to Market Road Brgy. Saud, Pagsanahan Norte, La Virgen Milagroso | Ilocos Norte | 2015-06-04 | 1st | Ilocos Norte 1st DEO | LF | 14.256 | 126 | 2015-04-01 | 2015-08-04 | 76.17% | O | 0.329 | 0.241 | 0.15 | 0.03 | 0.045 | 0.033 | 82.8% | -
BADOC BUILDERS & SUPPLY (Formerly: Badoc Builders) | 31564 | L | B | MA | GE | Widening of National Road, MNR, K0450+873-K0452+409, Badoc, Ilocos Norte | K0450+873-K0452+409, Badoc, Ilocos Norte | 2015-08-26 | 1st | Ilocos Norte 2nd DEO | LF | 18.62 | 149 | 2015-04-30 | 2015-09-26 | (+)28.37 | O | 0.341 | 0.219 | 0.15 | 0.03 | 0.065 | 0.05 | 85.5% | -
BADOC BUILDERS & SUPPLY (Formerly: Badoc Builders) | 31564 | L | B | MA | GE | Widening of National Roads, Manila North Road K0458+138 - K0458+820, Currimao, Ilocos Norte | Currimao, Ilocos Norte | 2015-11-13 | Final | ILOCOS NORTE 2ND DEO | LF | 13.9082 | 204 | 2015-04-30 | 2015-11-19 | - | C | 0.452 | 0.133 | 0.3 | - | - | - | 88.5% | 86.34% Satisfactory
Badsbro Construction and General Merchandise | 32876 | L | B | MA | GE | Const. of Flood Control Structure (Revetment) along Imelda-Bayog-Kumalarang-Lapuyan-Margasatubig Rd, Brgy. Pilar, Diplahan, (K1763+793.95 - K1763+833.50), Zamboanga Sibugay | Diplahan, Zamboanga Sibugay | 2014-10-25 | 1st | IX | LF | 3.8928 | 80 | 2014-09-05 | 2014-11-23 | 1.06% | O | 0 | 0.15 | 0.15 | 0.03 | 0.04 | 0.033 | 40.3% | 40.30% Poor
BADSBRO CONSTRUCTION AND GENERAL MERCHANDISE | 32876 | L | B | MA | GE | Construction of Flood Control Structure Along Lanao-Pagadian-Zamboanga City Road, Part of Sibuguey River, Sta. 00+000 - Sta. 00+856, Poblacion, Imelda, Zamboanga Sibugay | Sta. 00+000 - Sta. 00+856, Poblacion, Imelda, Zamboanga Sibugay | 2015-11-11 | Final | Zamboanga Sibugay 1st DEO | LF | 37.235 | 300 | 2015-03-05 | 2015-12-29 | 17.50% | C | 0.457 | 0.133 | 0.3 | - | - | - | 89% | 89.648% Very Satisfactory
BADSBRO CONSTRUCTION AND GENERAL MERCHANDISE | 32876 | L | B | MA | GE | Construction of Flood Control Structures along Lanao-Pagadian-Zamboanga City Road, Part of Sibuguey River, Poblacion, Imelda, Zamboanga Sibugay, Sta. 00+000-Sta.00+856 | Poblacion, Imelda, Zamboanga Sibugay | 2015-09-01 | 1st | Zamboanga Sibugay 1st | LF | 37.235 | 300 | 2015-03-05 | 2015-12-29 | (+)21.583 | O | 0.3138 | 0.3 | 0.15 | 0.03 | 0.057 | 0.05 | 90.08% | -
Bantay Construction | 35290 | L | D | SB | GB1 | Repair/Rehab. of DPWH Cebu 6th District Eng'g Office (Phase II) Bldg. A.C. Cortes Ave. | Mandaue City, Cebu | 2013-03-20 | 1st | VII | LF | 1.162 | 73 | 2013-01-08 | 2013-03-21 | 1.93 | O | 0.369 | 0.3 | 0.15 | 0.03 | 0.028 | 0.05 | 92.7 | -
BCT Trading & Construction | 15199 | L | AAA |  | GE5 | Proposed Coron Port Expansion Project | Port of Coron, Palawan | 2012-09-28 | 2nd | PPA | LF | 95.289 | 360 | 2011-11-21 | 2012-11-14 | -14.92 | O | 0.394 | 0.294 | 0.076 | 0.024 | 0.061 | 0.05 | 89.9 | -
BCT Trading & Construction | 15199 | L | AAA |  | GE5 | Proposed Coron port Expansion Project | Port of Coron, Palawan | 2012-05-23 | 1st | PPA | LF | 95.289 | 360 | 2011-11-21 | 2012-11-14 | -12.57 | O | 0.4 | 0.3 | 0.024 | 0.024 | 0.061 | 0.05 | 85.9 | -
BCT Trading & Construction | 15199 | L | AAA | MA | GB1 | San Vicente Airport Development Project | San Vicente, Palawan | 2014-01-29 | 1st | DOTC | LF | 50.161 | 360 | 2013-03-25 | 2014-03-19 | 2.44 | O | 0.378 | 0.3 | 0.15 | 0.01 | 0.045 | 0.05 | 82.8 | -
BCT Trading & Construction | 15199 | L | AAA | MB | GE1 | San Vicente Airport Development Project | San Vicente, Palawan / Region 4B | 2013-10-16 | 1st | DOTC | L | 56.132 | 360 | 2013-03-25 | 2014-03-19 | 16.04 | O | 0.4 | 0.3 | 0.15 | 0.01 | 0.0445 | 0.05 | 95.45 | -
BCT Trading & Construction | 15199 | L | AAA | MB | GE | Replacement of Camuran Bridge along Puerto Princesa Road | Puerto Princesa City | 2014-11-24 | 1st | IV | LF | 15.383 | 304 | 2014-02-17 | 2014-12-17 | 9.85% | O | 0.383 | 0.24 | 0.15 | 0.03 | 0.047 | 0.05 | 90% | 90.00% Very Satisfactory
BCT Trading & Construction | 15199 | L | AAA | MB | GE1 | Conc. of Puerto Princesa North Rd. (PPNR) Taytay (Pancol)-El Nido Rd. (Km.222+700-Km.225+000 w/ E) | Taytay, Palawan | 2012-11-22 | 1st | IVB | LF | 49.791 | 270 | 2012-03-28 | 2012-12-22 | 0.97 | O | 0.319 | 0.284 | 0.15 | 0.03 | 0.05 | 0.033 | 86.6 | -
BCT Trading & Construction | 15199 | L | AAA | MB | GE1 | Rehab./Reconst./Strengthening of Cabongan Bridge I along PPSR, K0010+058 | Puerto Princesa, Palawan | 2012-07-31 | 1st | IVB | LF | 10.803 | 228 | 2012-01-26 | 2012-09-10 | 1.8 | O | 0.372 | 0.272 | 0.15 | 0.03 | 0.045 | 0.033 | 90.2 | -
BCT Trading & Construction | 15199 | L | AAA | MB | GE1 | Rehab./Reconst./Upgrading Paved Nat'l Rd. (Mambalot-Ipilan Sect.) Km.176+000-Km.179+700) w/ exception | Brooke's Point, Palawan | 2012-08-01 | 1st | IVB | LF | 76.502 | 240 | 2012-03-15 | 2012-11-09 | 38.7 | O | 0.322 | 0.3 | 0.15 | 0.03 | 0.045 | 0.05 | 89.7 | -
BCT Trading & Construction | 15199 | L | AAA | MB | GE1 | Roa Upgrading of (Gravel to Paved) of Puerto Princesa South Road (PPSR), (IS) b)K0113+736-K0114+000 | Puerto Princesa, Palawan | 2012-08-04 | 1st | IVB | LF | 5.399 | 180 | 2012-02-13 | 2012-08-10 | 16.73 | O | 0.331 | 0.29 | 0.15 | 0.03 | 0.045 | 0.05 | 89.6 | -
BCT Trading and Construction | 15199 | L | AAA | MB | GE | Replacement of Caramuran Bridge along Puerto Princesa South Road | Puerto Princesa City | 2014-08-08 | 1st | IV-B | LF | 14.5109 | 275 | 2014-02-17 | 2014-11-18 | 3.97 | O | 0.368 | 0.267 | 0.15 | 0.03 | 0.04 | 0.033 | 88.8 | -
BCT TRADING AND CONSTRUCTION | 15199 | L | AAA | MB | GE | Construction/Widening of Plaridel Bridge I along PPSR | Aborlan, Palawan | 2015-06-02 | 1st | Palawan 3rd DEO | LF | 5.735 | 162 | 2015-02-11 | 2015-08-05 | 0% | O | 0.35 | 0.282 | 0.15 | 0.023 | 0.055 | 0.05 | 91% | -
BCT TRADING AND CONSTRUCTION | 15199 | L | AAA | MB | GE | Replacement of Caramuran Bridge along Puerto Princesa South Road | Puerto Princesa, Palawan | 2015-06-02 | Final | Palawan 3rd DEO | LF | 15.406 | 305 | 2014-02-17 | 2014-12-18 | 0% | C | 0.495 | 0.139 | 0.3 | - | - | - | 93.4% | *91.36% Very Satisfactory
BCT Trading and Construction | 15199 |  | AAA | MA |  | San Vicente Airport Development Project | San Vicente, Palawan/ Region 4B | 2015-12-16 | 3rd & Final | DOTC | LF | 50.161 | 434 | 2013-03-25 | 2014-06-01 | -128.34 | C | 0.4755 | 0.2 | 0 | - | - | - | 67.55 | 85.57% Satisfactory
BCT Trading and Construction | 15199 |  | AAA | MB |  | San Vicente Airport Development Project | San Vicente, Palawan/ Region 4B | 2015-12-16 | 3rd & Final | DOTC | LF | 56.132 | 434 | 2013-03-25 | 2014-03-19 | -128.34 | C | 0.422 | 0.2 | 0 | - | - | - | 62.2 | 82.18% Satisfactory
Bendimil Construction & Development Corporation | 6135 | L | AA | MB |  | Upgrading of Zamboanga City-Labuan-Limpapa Rd (Gravel to Concrete) K1975+000-K1977+100 w/ RCDG Bridge Const. (Latap Bridge) | Zamboanga City | 2013-08-05 | 4th | IX | LF | 43.655 | 435 | 2012-05-17 | 2013-07-25 | - | O | 0.13 | 0.24 | 0 | 0.02 | 0.047 | 0.033 | 47 | -
Bendimil Construction & Development Corporation | 6135 | L | AA | MB | GE1 | Upgrading of Zamboanga City-Labuan-Limpapa Rd. (Gravel to Concrete) K1975+000-K1977+100 w/ RCDG Bridge Const. (Latap Bridge) | Zamboanga City | 2013-03-12 | 3rd | IX | LF | 43.655 | 360 | 2012-05-17 | 2013-05-11 | -4.18 | O | 0.364 | 0.24 | 0.108 | 0.03 | 0.051 | 0.033 | 82.6 | -
Bendimil Construction & Development Corporation | 6135 | L | AA | MB | GE1 | Upgrading Zamboanga City-Labuan-Limpapa Rd. (Gravel to Concrete) K1975+000-K1977+100 w/ RCDG Bridge Const. (Latap Bridge) | Zamboanga City | 2012-11-19 | 2nd | IX | LF | 43.655 | 330 | 2012-05-17 | 2013-04-11 | 4.65 | O | 0.192 | 0.253 | 0.15 | 0.03 | 0.06 | 0.05 | 73.5 | -
Bendimil Construction & Development Corporation | 6135 | L | AA | MB | GE1 | Upgrading of Zamboanga City-Labuan-Limpapa Rd. (Gravel to Concrete) K1975+000-K1977+100 w/ RCDG Bridge Const. (Latap Bridge) | Zamboanga City | 2012-08-13 | 1st | IX | LF | 43.655 | 330 | 2012-05-17 | 2013-04-11 | 14 | O | 0.4 | 0.237 | 0.15 | 0.023 | 0.032 | 0.033 | 87.5 | -
BENDIMIL CONSTRUCTION & DEVELOPMENT CORPORATION | 6135 | L | AA | MB | GE | Construction of Bridge and Approaches at Labuan Spillway along Zamboanga City - Labuan - Limpapa Road, K1971+130 to K1971+443, Zamboanga City | Zamboanga City | 2015-06-11 | 1st | Zamboanga City DEO | LF | 36.192 | 482 | 2014-04-07 | 2015-08-01 | -0.29% | O | 0.368 | 0.219 | 0.147 | 0.03 | 0.043 | 0.033 | 84% | -
BENDIMIL CONSTRUCTION & DEVELOPMENT CORPORATION | 6135 | L | AA | MB | GE | Construction of Bridge at Labuan Spillway along Zamboanga City-Labuan-Limpapa Road, Zamboanga City | Zamboanga City | 2015-09-03 | Final | Zamboanga City | LF | 36.192 | 482 | 2015-04-07 | 2016-08-01 | - | C | 0.385 | 0.2 | 0.3 | - | - | - | 88.5% | *85.8% Satisfactory
Bendimil Construction and Development Corp. | 6135 | L | AA | MB | GE1 | Impvt./Gravelling of Siocon-Sirawai Road (Sirawai Side) |  | 2008-08-26 | 1st | IX |  | 47.894 | 300 |  |  |  | O | 0.158 | 0.225 | 0 | 0.03 | 0.033 | 0.067 | 51.3 | -
BENTRIX BUILDERS | 35226 | L | D | SB | GE | Rehabilitation/Reconstruction/Upgrading of Dantay-Sagada Rd K0390+941 - K0391+000, K0391+740 - K0391+788, K0392+175 - K0392+604, | Sagada, Mt. Province | 2015-06-05 | Final | Benguet 2nd DEO | LF | 7.164 | 186 | 2014-05-26 | 2014-11-27 | (-) 9.11% | C | 0.43 | 0.2 | 0 | - | - | - | 63% | *63% Poor
Berson's Construction & Trading | 31181 | L | B | MA | GE1 | Widening of Urdaneta Jct.-Dagupan Rd., K0190+734-K0192+096 w/ exception | Sta. Barbara, Pangasinan | 2013-08-02 | 2nd | I | LF | 16.512 | 210 | 2013-01-16 | 2013-08-13 | 3.34 | S | 0.331 | 0.233 | 0.15 | 0.03 | 0.042 | 0.05 | 83.6 | -
Berson's Construction & Trading | 31181 | L | B | MA | GE1 | Widening of San Carlos-Calasiao Rd. (San Carlos Sect.) Km.203+960-Km.204+330 | San Carlos City, Pangasinan | 2013-08-03 | 1st | I | LF | 8.539 | 183 | 2013-01-16 | 2013-07-17 | - | O | 0.35 | 0.3 | 0.018 | 0.03 | 0.051 | 0.033 | 78.2 | -
Berson's Construction & Trading | 31181 | L | B | MA | GE1 | Prev. Maint. along Alaminos-Lucap Rd., K0321+(-107)-K0321+000 w/ exception; K0321+000-K0322+446 w/ exception | Alaminos, Pangasinan | 2013-03-15 | 1st | I | LF | 14.318 | 71 | 2013-01-28 | 2013-04-08 | 13.15 | O | 0.385 | 0.3 | 0.15 | 0.015 | 0.03 | 0.033 | 91.3 | -
Berson's Construction & Trading | 31181 | L | B | MA | GE1 | Widening of Urdaneta Jct.-Dagupan Rd., K0190+734-K0192+096 w/ exception | Sta. Barbara, Pangasinan | 2013-03-14 | 1st | I | LF | 16.512 | 180 | 2013-01-16 | 2013-07-14 | 5.88 | O | 0.345 | 0.291 | 0.15 | 0.018 | 0.03 | 0.033 | 86.7 | -
Berson's Construction & Trading | 31181 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rds. K0258+000-K0259+730, Manila North Rd. | Bauang, La Union | 2012-08-08 | 1st | I | LF | 30.881 | 195 | 2012-02-16 | 2012-08-28 | 11.44 | O | 0.269 | 0.3 | 0.15 | 0.03 | 0.065 | 0.033 | 84.7 | -
BERSON'S CONSTRUCTION & TRADING | 31181 | L | B | MA | GE | Rehabilitation/Reconstruction/Upgrading of Alaminos-Bolinao Road | KO335+226.49 - KO336+080, Bani, Pangasinan | 2015-06-12 | 1st | Pangasinan 1st DEO | LF | 18.616 | 150 | 2015-01-23 | 2015-06-21 | -14.01% | O | 0.339 | 0.3 | 0.01 | 0.03 | 0.055 | 0.017 | 75.1% | -
BERSON'S CONSTRUCTION & TRADING | 31181 | L | B | MA | GE | Construction of Boulder Bank Protection at Brgy. Pangapisan, Agno River Basin Flood Control Phase I, Lingayen, Pangasinan | Lingayen, Pangasinan | 2015-11-19 | Final | PANGASINAN 2ND DEO | LF | 13.9003 | 125 | 2015-08-28 | 2015-12-30 | 0.086 | C | 0.39 | 0.225 | 0.15 | 0.03 | 0.055 | 0.05 | 90% | 90% Very Satisfactory
BERSON's CONSTRUCTION AND TRADING | 31181 | L | B | MA | GE | Widening of Calasiao Old Road, K0204+(-030) to K0207+267 With Exception, Calasiao, Pangasinan | K0204+(-030) to K0207+267 With Exception, Calasiao, Pangasinan | 2015-09-03 | 1st | Pangasinan 4th DEO | LF | 37.552 | 178 | 2015-04-24 | 2015-10-19 | (+)1.78 | O | 0.345 | 0.261 | 0.15 | 0.023 | 0.042 | 0.05 | 87.1% | -
Bet Construction & Supply | 31764 | L | A | MA | GE | Widening of Urdaneta Jctn.-Lingayen Road via Zambales, K0373+507-K0374+900 | Dagupan City | 2014-10-28 | 1st | I | LF | 25.775 | 180 | 2014-06-03 | 2014-11-29 | 23.58% | O | 0.312 | 0.3 | 0.15 | 0.03 | 0.047 | 0.05 | 88.9% | 88.90% Satisfactory
Bet Construction & Supply | 71764 | L | B | MA | GE1 | Prev. Maint. of Pangasinan-La Union Inter-Prov. Rd., K0399+495-K0403+025 w/ exception | San Fabian, Pangasinan | 2013-08-06 | 1st | I | LF | 44.119 | 180 | 2013-03-27 | 2013-09-22 | 9.21 | O | 0.382 | 0.217 | 0.15 | 0.03 | 0.042 | 0.033 | 85.4 | -
Bet Construction & Supply | 31764 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat' Rd. (Pangasinan-Zambales Rd.) Jct. Lingayen Rd. (K0377+612-K0378+700 A.B. Fernandez Ave.) | Dagupan City, Pangasinan | 2013-08-05 | 1st | I | LF | 45.764 | 180 | 2013-03-27 | 2013-09-23 | 15.16 | O | 0.355 | 0.24 | 0.15 | 0.03 | 0.042 | 0.033 | 85 | -
Bet Construction & Supply | 31764 | L | B | MA | GE1 | River Bank Protection along Mangueragtay River (Phase II), Bonoan | Binloc, Dagupan City | 2013-08-06 | 1st | I | LF | 28.04 | 180 | 2013-03-26 | 2013-09-21 | 13.72 | O | 0.35 | 0.24 | 0.15 | 0.03 | 0.042 | 0.033 | 84.5 | -
BET CONSTRUCTION & SUPPLY | 31764 | L | A | MA | GE | Widening of National Road (Secondary Roads) Judge Jose De Venecia Sr. Avenue | KO207+882 - KO228+051, KO207+992 - KO208+455, Dagupan City | 2015-06-11 | 1st | Pangasinan 2nd DEO | LF | 9.73 | 156 | 2015-03-09 | 2015-08-11 | 2.38% | O | 0.316 | 0.24 | 0.15 | 0.03 | 0.055 | 0.033 | 82.4% | -
Bicol Goldrock Construction Corporation | 32376 | L | B | MA | GE | Construction/Rehabilitation/Improvement of Magarao River Control | Magarao, Camarines Sur | 2014-08-08 | 1st | V | LF | 17.6811 | 168 | 2014-02-25 | 2014-08-11 | -0.91 | O | 0.304 | 0.3 | 0.141 | 0.02 | 0.051 | 0.033 | 84.9 | -
BICOL GOLDROCK CONSTRUCTION CORPORATION | 32376 | L | B | MA | GE | Off-Carriageway Improvement of National Road (Conc. Of Road Shoulder w/ Drainage), Tigaon-Goa-San Jose-Lagonoy via San Vicente Road (Mabca-San Antonio-San Rafael Road Section), KO481+(-745)-KO483+858 Tigaon, Camarines Sur | Tigaon, Camarines Sur | 2015-11-15 | Final | Camarines Sur Third DEO | LF | 42.515 | 204 | 2015-02-13 | 2015-09-05 | - | C | 0.458 | 0.095 | 0.3 | - | - | - | 85.3% | 85.3% Satisfactory
Bicol Goldrock Construction Corporation / EGB Construction Joint Venture | JV-11-574 | L | B | MA | GE1 | Rehab. of Cagayan-Apayao Rd. (CAR), Fugu Sect. | Tuao, Cagayan | 2012-11-19 | 1st | II | LF | 45.231 | 300 | 2012-06-04 | 2013-03-31 | 3.7 | O | 0.398 | 0.24 | 0.15 | 0.03 | 0.059 | 0.05 | 92.7 | -
Bicol Goldrock Construction Corporation/GCI. Construction and Development Corp. (JV) | JV-12-286 | L | B | MA | GE1 | Road Upgrading (Gravel to Paved), CCR Cabungahan Sect, (K0156+850 - K0159+000) | San Andres, Catanduanes | 2013-07-30 | 1st | V | LF | 48.247 | 184 | 2013-02-15 | 2013-08-17 | -6.49 | O | 0.361 | 0.283 | 0.085 | 0.03 | 0.058 | 0.033 | 85 | -
BIG BERTHA CONSTRUCTION AND DEVELOPMENT | 3191 | L | A | MB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads Including Drainage Based on Pavement Management System/Highway Development (HDM-4)(Intermittent Section) Carmen Jct. Manat Road, Bautista Section | Bautista, Pangasinan | 2015-06-08 | 1st | Pangasinan 3rd DEO | LF | 44.14 | 165 | 2015-02-05 | 2015-07-19 | -12% | O | 0.317 | 0.292 | 0.028 | 0.03 | 0.045 | 0.017 | 72.9% | -
BIG BERTHA CONSTRUCTION AND DEVELOPMENT | 3191 | L | A | MB | GE | Widening of Permanent Bridge to more than two lanes at Bacag Bridge (B00724LZ) along Manila North Road, Villasis, Pangasinan | Villasis, Pangasinan | 2015-11-16 | Final | PANGASINAN 3RD DEO | LF | 27.44 | 259 | 2015-04-17 | 2015-12-31 | 0.0984 | C | 0.382 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 90.2% | 90.2% Very Satisfactory
Big Joe's Enterprises | 33601 | L | B | MA | GE1 | Reconst. of Nat'l Sec. Rd. along Binalbagan-Isabela Rd., a)K0065+004-K0065+146, b)K0067+200-K0067+866 | Binalbagan, Negros Occidental | 2013-08-10 | 2nd | VI | LF | 11.438 | 179 | 2013-01-28 | 2013-07-26 | -4.99 | O | 0.35 | 0.3 | 0.017 | 0.03 | 0.042 | 0.05 | 78.9 | -
Big Joe's Enterprises | 33601 | L | B | MA | GE1 | Reconst. of Nat'l Secondary Rd. along Binalbagan-Isabela Rd., a) K0065+004-K0065+146, b) K0067+200-K0067+866 | Binalbagan, Negros Occidental | 2013-03-12 | 1st | VI | LF | 11.438 | 119 | 2013-01-28 | 2013-05-26 | 2.22 | O | 0.345 | 0.295 | 0.15 | 0.015 | 0.04 | 0.033 | 87.8 | -
Billena Construction | 7431 | L | C | SB | GE1 | Rehab. of Morocco-Particion-Anono-o-Cabubugan Rd. | Guimbal, Iloilo | 2013-03-17 | 1st & Final | VI | LF | 4.726 | 60 | 2013-01-17 | 2013-03-17 | 0 | O | 0.367 | 0.2 | 0.3 | - | - | - | 86.7 | 86.70% Satisfactory
Billena Construction/D.M. House Construction, Inc. (JV) | JV-08-145 | L | A | MB | GE1 | Conc. of Bantayan-San Pedro-Cubay Road, San Jose and Sibalom |  | 2009-09-02 | 2nd | VI |  | 27.016 | 360 |  |  |  | O | 0.356 | 0.239 | 0.15 | 0.015 | 0.025 | 0.033 | 81.8 | -
Bilrey Const./Eddmari Const./CS Garcia Const.-JV |  | L |  |  |  | Procurement of Fully Developed Lots & Completed Housing Units Under the NHA's Yolanda Permanent Housing Program at Ridge View Park Phase 1 | Brgy. Cabalawan, Tacloban City, Leyte/Region 8 | 03/13/15 | 1st | NHA | LF | 289.938 | 405 | 12/18/14 | 01/26/16 | 41.69 | O | 0.363 | 0 | 0.15 | 0.03 | 0.023 | 0.05 | 61.6 | -
Bilrey Construction |  | L |  |  |  | Z3R Tulungatung Housing Project | Brgy. Tulungatung, Zamboanga City | 03/27/15 | 1st | NHA | LF | 78.62 | 210 | 2014-07-12 | 06/28/15 | -11.3 | O | 0.3604 | 0.3 | 0.0349 | 0.03 | 0.0572 | 0.0333 | 81.58 | -
Bilrey Construction | 32877 | L | A |  | GB1 | Construction of Livelihood, Production & Training Center (Building) | Kasiglahan Vill. I-K Site 3 Brgy. San Jose, Rodriguez, Rizal | 2010-09-29 | 1st | NHA |  | 4.99 | 90 | 2010-07-27 | 2010-10-24 | 15.88 | O | 0.3914 | 0.3 | 0.15 | 0.03 | 0.0653 | 0.05 | 98.67 | -
Bilrey Construction | [5 empty] | Z3R Tulungatung Housing Project | Brgy. Tulungatung, Zamboanga City | 2016-03-04 | 2nd | NHA | LF | 78.62 | 642 | 2014-07-12 | 2016-03-04 | -7.46 | O | 0.3644 | 0.3 | 0.0754 | 0.03 | 0.0574 | 0.05 | 87.72 | -
Bilrey Construction/ Eddmari Construction and Trading/ C.S. Garcia - JV | [5 empty] | Procurement of House and Lot Packages at Ridgeview Park Ph. 1 | Brgy. Cabalawan, Tacloban City, Leyte | 2016-04-08 | 2nd | NHA | LF | 289.938 | 487 | 2014-12-18 | 2016-04-17 | 12.64 | O | 0.3769 | 0.0972 | 0.15 | 0.03 | 0.061 | 0.05 | 76.51 | -
Bilrey Construction/Eddmari Construction & Trading JV |  | L |  |  |  | Antonino Heights | Brgy. Luna, Cadiz City, Negros Occidental | 2015-09-11 | 1st | NHA | LF | 289.932 | 365 | 03/20/15 | 03/19/16 | 2.17 | O | 0.2936 | 0.2561 | 0.15 | 0.03 | 0.0592 | 0.05 | 83.89 | -
Bislig Venture Construction & Dev't., Inc. | 36370 | L | B | SB | GE | Local Infrastructure Program-Construction of Three (3) Barrel Box Culvert, Brgy. Mangagoy | Bislig City, Surigao del Sur | 2014-10-24 | 1st | XIII | LF | 2.6799 | 90 | 2014-07-30 | 2014-10-27 | 1.39% | O | 0.297 | 0.265 | 0.15 | 0.02 | 0.051 | 0.05 | 83.3% | 83.30% Satisfactory
Bislig Venture Construction & Dev't., Inc. | 36370 | L | B | SB | GB | Local Infrastructure Program-Construction of Multi-Purpose Building, DepEd, Bislig City Division Office | Bislig City, Surigao del Sur | 2014-10-24 | 1st | XIII | LF | 4.7011 | 175 | 2014-07-11 | 2015-01-01 | 1.17% | O | 0.338 | 0.25 | 0.15 | 0.02 | 0.059 | 0.05 | 86.7% | 86.70% Satisfactory
BL Jadulco Construction & Supply | 33684 |  |  |  |  | Const. of Dainage in the Municipality of Naval |  | 2010-08-26 |  | VIII |  | 1.926 | 100 |  |  |  | O | 0.397 | 0.24 | 0.15 | 0.03 | 0.042 | 0.033 | 89.2 | -
BL PANGAN CONSTRUCTION | 25158 | L | B | SB | GE | Concreting of Farm-to-Market Road, Buhingtubig - Binabag | Pinamungajan, Cebu Sta. 000 + 000 - Sta. 000 + 274 | 2015-08-29 | 1st & Final | Cebu 3rd | LF | 1.897 | 70 | 2015-05-29 | 2015-08-06 | 2.5% | C | 0.339 | 0.185 | 0.3 | - | - | - | 82.4% | *82.4% Satisfactory
BLACKRAM BUILDERS INC. | 33899 | L | D | SB | GB | Local Infrastructure Program - Construction of Multi Purpose Buildings (Covered Court), Barangay 137, Zone 12, Buendia St., Balut, Tondo, Manila City 1st LD | Buendia St., Balut, Tondo, Manila City 1st LD | 2015-09-01 | 1st & Final | NM DEO | LF | 0.989 | 90 | 2015-03-10 | 2015-06-07 | 0% | C | 0.48 | 0.133 | 0.3 | - | - | - | 91.3% | *91.3% Very Satisfactory
BLC Construction & Aggregates | 16424 | L | B | MA | GE1 | Upgrading of Dantay-Sagada Rd. (K0391+000-K0391+677 & K0392+603-K0393+048.2) | Bontoc, Mt. Province | 2013-08-03 | 1st | CAR | LF | 30.6 | 159 | 2013-04-02 | 2013-09-07 | 0.2 | O | 0.365 | 0.24 | 0.15 | 0.023 | 0.04 | 0.033 | 85.1 | -
BLESSING BUILDERS AND CONSTRUCTION SUPPLY | 36064 | L | C | SB | GE | Construction/Maintenance of Flood Control Mitigation Structures and Drainage Systems, Construction of Tammang Flood Control, Luttucan, Kabugao, Apayap | Luttucan, Kabugao, Apayap | 2015-08-27 | 1st | Apayao 1st DEO | LF | 4.712 | 246 | 2015-02-16 | 2015-10-19 | 1.17% | O | 0.371 | 0.225 | 0.15 | 0.03 | 0.04 | 0.05 | 86.6% | -
Blimex Construction and Supply | 27259 | L | B | SB | GE2 | Repair/Restoration of Damaged Slope Protection & Slope Line Canal along Santander-Barili-Toledo Rd., K0170+250-K0221+869 (Int. Sect.) | Alegria to Dumanjug, Cebu | 2013-08-09 | 1st | VII | LF | 9.733 | 140 | 2013-05-13 | 2013-09-29 | 22.86 | O | 0.31 | 0.248 | 0.15 | 0.03 | 0.055 | 0.05 | 84.3 | -
Blimex Construction and Supply | 27259 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Concrete) along Awang-Upi-Lebak-Kalamansig-Palimbang-Sarangani Rd. (Km.2036+896-Km.2038+728 w/ exception) | Palimbang, Sultan Kudarat | 2013-08-18 | 1st | XII | LF | 39.234 | 172 | 2013-04-02 | 2013-09-20 | 0.63 | O | 0.339 | 0.236 | 0.15 | 0.023 | 0.051 | 0.05 | 84.9 | -
BLIMEX CONSTRUCTION AND SUPPLY | 27259 | L | B | MA | GE | Road Upgrading (Gravel to Concrete) Based on Gravel Strategies, Traffic Benchmark for Upgrading to Paved Road Standard (HDM-4 Project Analysis) along Awang-Upi-Lebak-Kalamansig-Palimbang-Sarangani Road | Palimbang, Sultan Kudarat (K2027+135-K2029+680 with exception)( original contract)( K2025+593-K2027+978 with exception) (RBIA) | 2015-06-09 | Final | Sultan Kudarat 2nd DEO | LF | 22.849 | 167 | 2014-09-18 | 2015-03-03 | 0.22% | C | 0.41 | 0.133 | 0.3 | - | - | - | 84.3% | *84.3% Satisfactory
BLIMEX CONSTRUCTION AND SUPPLY | 27259 | L | B | MA | GE | Rehabilitation/Reconstruction of A. Soriano Street | Cebu City | 2015-09-03 | 1st | Cebu City | LF | 45.08 | 260 | 2015-03-03 | 2015-11-17 | 0.5% | O | 0.259 | 0.3 | 0.15 | 0.03 | 0.05 | 0.05 | 83.9% | -
Blue Eagle Construction Company | 10915 | L | A | MA |  | Marinduque Airport Development Project | Gasan, Marinduque | 2015-08-06 | 2nd | DOTC | LF | 6.061 | 150 | 2014-12-02 | 04/30/15 | -9.54 | O | 0.382 | 0.3 | 0.055 | 0 | 0.012 | 0 | 74.9 | -
Blue Eagle Construction Company | 10915 | L | A | LA | GE-1 | Marinduque Airport Development Project | Brgy. Masiga, Gasan, Marinduque/ Region 4-B | 2015-04-08 | 1st | DOTC | LF | 4.028 | 150 | 2014-03-26 | 2014-08-22 | -48.87 | O | 0.341 | 0.3 | 0 | 0.01 | 0.0087 | 0.0333 | 69.3 | -
Blue Eagle Construction Company | 10915 | L | A | MA |  | Marinduque Airport Development Project | Gasan, Marinduque | 2016-04-14 | 3rd & Final | DOTC | LF | 6.061 | 150 | 2014-12-02 | 2015-04-30 | -23.02 | C | 0.5 | 0.2 | 0 | - | - | - | 70 | 71.30% Poor
BLUE MOUNTAIN BUILDERS & GENERAL MERCHANDISE (Formerly: Blue Mountain Builders) | 34745 | L | D | SB | GE | Construction Maintenance of Flood Mitigation Structures & Grainage System, Laoag River Basin Flood and SABO Projects, Construction/Extension of Revetment (Dupitac Flood Control) Piddig, Ilocos Norte | Piddig, Ilocos Norte | 2015-11-15 | Final | ILOCOS NORTE 1ST DEO | LF | 9.157 | 140 | 2015-07-31 | 2015-12-17 | 0.1082 | C | 0.377 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 89.7% | 89.7% Very Satisfactory
BM MARKETING | 9852 | L | AAA | MB | GE | Road Widening of Naval-Caibiran Cross Country Road, km. 1030+860-Km 1033+180, Naval, Biliran | km. 1030+860-Km 1033+180, Naval, Biliran | 2015-08-27 | 1st | Regional Office No. VIII | LF | 75.478 | 280 | 2015-02-16 | 2015-11-22 | (+)32.19 | O | 0.373 | 0.24 | 0.15 | 0.01 | 0.055 | 0.05 | 87.8% | -
BMJ CONSTRUCTION | 14571 | L | B | SB | GE | Construction/Upgrading/Rehabilitation of Drainage along National Roads, Construction of Drainage System Cabagan - Sta. Maria Rd., K0448+912.6 to K0449+409 - Stretch 1, K0405+451 - Stretch 2, Cabagan, Isabela | Cabagan, Isabela | 2015-08-27 | 1st | Isabela 1st DEO | LF | 13.969 | 161 | 2015-04-01 | 2015-09-08 | 0.14% | O | 0.353 | 0.3 | 0.15 | 0.03 | 0.035 | 0.033 | 90.1% | -
BMJ CONSTRUCTION | 14571 | L | B | MA | GE | Construction/Upgrading/Rehabilitation of Drainage along National Roads, Construction of Drainage System Cabagan-Sta. Maria Road, K0448+912.60 - K0449+405.60 - Stretch 1 K0450+405.60 - Stretch 2 | Cabagan Sta. Maria | 2015-11-13 | Final | ISABELA 1ST DEO | LF | 13.9696 | 161 | 2015-04-01 | 2015-09-08 | (+) 0.61 | C | 0.485 | 0.133 | 0.3 | - | - | - | 91.8% | 90.78% Very Satisfactory
BMJ Construction | 14571 | L |  |  | GE2 | MARIIS Sivision 3 - Improvement Projects | San Manuel, Isabela, Region 2 | 2012-07-27 | 1st | NIA | LF | 9.441 | 120 | 2012-04-18 | 2012-08-15 | -6.86 | O | 0.36 | 0.3 | 0.081 | 0.03 | 0.032 | 0.05 | 85.3 | -
BMK Construction | 8292 | L |  | MB | GE-2 | Const. San Angel Small Reservoir Irrigation Project (Canal Structures) | San Angel, Rosales, Pangasinan | 05/12-14/11 | 1st | NIA | LF | 12.808 | 180 | 2010-12-20 | 2011-06-17 | 15.11 | O | 0.351 | 0.2762 | 0.15 | 0.024 | 0.0373 | 0.05 | 88.85 | -
BMK Construction/R.N.G.M. Construction (J.V.) | 30458 | L | D | SB | GE | Construction/Improvement of Access Roads Leading to Declared Tourism Destination, Sabang-Baler Road Leading to Sabang Garden Malls and Garden Plaza | Aurora | 2014-08-08 | 1st | III | LF | 45.8898 | 240 | 2014-03-25 | 2014-11-19 | 2.67 | O | 0.342 | 0.24 | 0.15 | 0.012 | 0.056 | 0.033 | 83.3 | -
BN BUILDERS & CONSTRUCTION SUPPLIES/ REY ROSE CONSTRUCTION & SUPPLY JOINT VENTURE | JV-14-410 | L | D | SB | GB | Completion of Multi-Purpose Building (Covered Court Bleacher) | Brgy. Taguibo, Butuan City (72) 10 | 2015-09-01 | 1st & Final | Butuan City | LF | 1.018 | 90 | 2015-03-05 | 2015-06-02 | (+) 0.38% | C | 0.466 | 0.16 | 0.3 | - | - | - | 92.6% | *92.6% Very Satisfactory
BNG Construction and General Services | 18503 | L | C | SB | GE1 | Rd. Upgrading (Gravel to Concrete), Quezon-Capalayan-Espina-Navarro Rd., Arellano Dist. |  | 2009-09-07 | 1st | XIII |  | 9.231 | 253 |  |  |  | O | 0.378 | 0.225 | 0.15 | 0.03 | 0.054 | 0.033 | 87 | -
BNR Construction & Development Corporation | 12903 | L | AAA | MB | GE1 | Widening of Nat'l Rd. at Cebu North Hagnaya Wharf Rd., K0013+560-K0014+505 (Proposed for Realignment/Modification to Impv't. of Nat'l Rd. at Cebu North Hagnaya Wharf Road, K0013+560-K0014+505 | Consolacion, Cebu | 2013-08-12 | 1st | VII | LF | 25.8 | 300 | 2013-03-27 | 2014-01-20 | 1.93 | O | 0.356 | 0.232 | 0.15 | 0.03 | 0.055 | 0.05 | 87.3 | -
BNR CONSTRUCTION & DEVELOPMENT CORPORATION / ZION CONSTRUCTION (JV) | JV-13-452 | L | AAA | MB | GE | Upgrading of the Access Road Leading to White beach, Sec. 1: Sta. 0+000 - Sta. 1+947.344; Sec.2: Sta. 0+000 - Sta. 5+867.673, Moalboal, Cebu Province | Moalboal, Cebu Province | 2015-11-20 | Final | Regional Office | LF | 115.2951 | 405 | 2014-06-10 | 2015-07-19 | 0.0015 | C | 0.446 | 0.133 | 0.3 | - | - | - | 87.9% | 87.9% Satisfactory
BNR Construction & Development Corporation/ZION Construction -JV | JV-13-452 | L | AAA | MB | GE | Upgrading of Access Road Leading to White Beach, Section 1) Sta. 0+000 to Sta. 1+947.344; Section 2) Sta. 0+000 to Sta. 5+867.673 | Moalboal, Cebu Province | 2014-10-25 | 1st | VII | LF | 115.2951 | 270 | 2014-06-10 | 2015-03-06 | -6.54% | O | 0.324 | 0.3 | 0.085 | 0.03 | 0.05 | 0.05 | 83.9% | 83.90% Satisfactory
BNYU Enterprises & Construction | 27725 | L | B | SB | GE2 | Talibon Area | Biis, Talibon Area, Bohol, Region 7 | 2013-07-13 | 1st | NIA | L | 3.867 | 120 | 2013-01-24 | 2013-09-20 | 22.92 | O | 0.37 | 0.3 | 0.15 | 0.02 | 0.06 | 0.05 | 95 | -
BNYU Enterprises and Construction | 27725 |  |  | MA |  | PW-BHL-13-12 Emergency Repair & Rehabilitation of calape-Pangangan Road | Calape, Bohol | 2015-01-19 | 1st | Bohol | L | 10.242 | 165 | 2014-06-05 | 2014-11-16 | 16.05 | O | 0.38 | 0.299 | 0.15 | 0.03 | 0.06 | 0.033 | 95.2 | -
BNYU Enterprises and Construction | 27725 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Paved) Jct. (TNR) Cortes-Balilihan-Catigbian-Macaas Rd., Km.46+045-Km.46+575 | Tubigon, Bohol | 2013-08-17 | 1st | VII | LF | 18.966 | 245 | 2013-01-31 | 2013-10-02 | 4.8 | O | 0.38 | 0.26 | 0.15 | 0.03 | 0.065 | 0.05 | 93.5 | -
BNYU Enterprises and Construction | 27725 | L | B | MA | GE2 | Talibon Small Reservoir Irrigation Project |  | 9/29/08 10/3/08 | 1st | NIA |  | 4.99 | 210 |  |  |  | O | 0.328 | 0.173 | 0.1 | 0.03 | 0.047 | 0.2 | 87.8 | -
BOMEL CONSTRUCTION | 32878 | L | C | SB | GE | Repair/Rehabilitation and Construction of Farm to Market Road, Brgy. Manggas to Sitio Patik, Brgy. Pansol | Padre Garcia, Batangas | 2015-06-05 | 1st | Batangas 4th DEO | LF | 9.247 | 90 | 2015-04-06 | 2015-07-04 | 2.45% | O | 0.288 | 0.3 | 0.15 | 0.03 | 0.05 | 0.033 | 85.1% | -
BOMEL CONSTRUCTION | 32878 | L | C | SB | GE | Construction/Upgrading/Rehabilitation of Drainage along National Road, Lucena - Tayabas - Lucban - Sampaloc - Mauban Port Road, K0129+800 to K0130+040, K0132+500 to K0133+720, Lucban, Quezon | Lucban, Quezon | 2015-06-09 | 1st | Quezon 1st DEO | LF | 4.675 | 150 | 2015-02-23 | 2015-07-22 | 14.89% | O | 0.304 | 0.281 | 0.15 | 0.03 | 0.029 | 0.033 | 82.7% | -
BOMEL CONSTRUCTION | 32878 | L | C | SB | GE | Construction/Upgrading/Rehabilitation of Drainage along National Road along Lucena-Tayabas-Lucban-Sampaloc-Mauban Port Road, K0129+800 - K0130+040, K0132+500 - K0133+720 | Quezon | 2015-09-04 | 1st & Final | Quezon 1st | LF | 4.675 | 150 | 2015-02-23 | 2015-07-22 | 0% | C | 0.408 | 0.133 | 0.3 | - | - | - | 84.1% | *84.1% Satisfactory
Bonifacio M. Carlos Construction Corp. (Formerly: Bonifacio M. Carlos Construction) | 3303 | L | A | MA | GE | Road Upgrading (Gravel to Paved) of PPSR Jct. - Napsan - Apurawan Road - K0027+967 to K0028+731 and K0028+731 to K0029+237 | Puerto Princesa City | 2014-08-08 | 1st | IV-B | LF | 20.4308 | 113 | 2014-04-04 | 2014-07-25 | -10.45 | O | 0.387 | 0.21 | 0 | 0.03 | 0.05 | 0.033 | 71 | -
BONIFACIO M. CARLOS CONSTRUCTION CORP. (Formerly: Bonifacio M. Carlos Construction) | 3303 | L | A | MA | GE | Construction of Tacduan Diversion Road, K0033+540 - K0035+540 & K0034+520 - K0035+000, PPSR | Puerto Princesa City | 2015-06-01 | 1st | Palawan 3rd DEO | LF | 39.241 | 173 | 2015-02-11 | 2015-08-03 | 0% | O | 0.379 | 0.26 | 0.15 | 0.03 | 0.06 | 0.05 | 92.9% | -
BONIFACIO M. CARLOS CONSTRUCTION CORPORATION | 3303 | L | A | MA | GE | Construction of Tacduan Diversion Road, K0033+540-K0035+540 & K0034+520-K0035+000, PPSR, Puerto Princesa City | PPSR, Puerto Princesa City | 2015-09-25 | 1st & Final | Palawan III DEO | LF | 39.196 | 201 | 2015-02-11 | 2015-08-31 | 4.92% | C | 0.454 | 0.133 | 0.3 | - | - | - | 88.7% | *88.7% Satisfactory
Bonifacio M. Carlos Trading Corp. (Formerly: Bonifacio M. Carlos Construction) | 3303 | L | A | MA | GE1 | Rd. Upgrading (Gravel to Paved) of PPSR Jct.-Napsan-Apurawan Rd., K0041+100-K0042+138 & K0042+138-K0042+588 | Puerto Princesa City | 2013-08-15 | 1st | IVB | LF | 33.94 | 201 | 2013-04-02 | 2013-10-22 | 0.01 | O | 0.355 | 0.091 | 0.15 | 0.03 | 0.042 | 0.05 | 71.8 | -
Bonimar Construction Enterprises | 23760 | L | B | MA | GE1 | Reconst./Widening of Manila North Rd., K0262+497-K0264+236 | Bauang, La Union | 2012-08-08 | 1st | I | LF | 30.098 | 240 | 2012-02-21 | 2012-10-17 | 15.59 | O | 0.249 | 0.3 | 0.15 | 0.03 | 0.05 | 0.033 | 81.2 | -
Borongan MBC Merchandising & Construction | [5 empty] | WSIIMO Contract No. 12-2014 | Gandara, Western Samar | 2015-11-21 | 1st & Final | NIA | LF | 4.534 | 150 | 2014-08-29 | 2015-01-25 | 0 | C | 0.482 | 0.115 | 0.3 | - | - | - | 89.7 | *89.70% V. Satisfactory
Bre Construction | 32605 | L | B | SB | GE1 | Const. of Slope Protection Works along Awang-Upi-Lebak-Kalamansig Rd. (Awang Jct.-DOS-Nuro) Km.1844+970-Km.1875+148.20 w/ exception | North Upi, Maguindanao | 2013-08-13 | 1st | XII | LF | 9.397 | 220 | 2013-07-01 | 2014-02-05 | 0.11 | O | 0.335 | 0.24 | 0.15 | 0.02 | 0.043 | 0.033 | 82.1 | -
Brima Construction and Enterprises | 8746 |  |  |  |  | Rehab./Reconst./Upgrading along Linamon-Zamboanga Road, Larapan Section, Sta.1535+817 - Sta.1540+771 |  | 2010-06-07 |  | X |  | 10.248 | 105 |  |  |  | O | 0.225 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 75 | -
Brostan Construction & Development | 12360 | L | AA | MB | GB1 | Const. of MPB (Phase I), Cagayan State University |  | 2008-11-14 | 2nd | II |  | 9.64 | 300 |  |  |  | O | 0.316 | 0.24 | 0.1 | 0.03 | 0.037 | 0.1 | 82.3 | -
Brostan Construction & Development | 12360 | L | AAA | LB | GE2 | Addalam River Irrigation Project |  | 04/27/09 05/01/09 | 1st | NIA |  | 9.225 | 235 |  |  |  | O | 0.3514 | 0.3 | 0.0773 | 0.0225 | 0.0382 | 0.0333 | 82.27 | -
Brostan Construction & Development | 12360 | L | AAA | MB | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rds. along Sta.Maria-Norzagaray Rd., a)K0035+259-K0035+965.50 (w/ exception), b)K0037+611-K0037+775 (w/ exception), c)K0037+775-K0037+895 (w/ exception), d)K0035+1449-K0037+611 (w/ exception), e)K0040+398-K0040+790 w/ exception), f)K0040+790-K0041+150 (w/ exception) | Sta. Maria, Bulacan | 2012-08-06 | 2nd | III | LF | 42.817 | 220 | 2012-01-27 | 2012-09-02 | 5.85 | O | 0.319 | 0.3 | 0.15 | 0.03 | 0.045 | 0.05 | 89.4 | -
Brostan Construction and Development | 12360 | L | AAA | LB | GE2 | Help for Catubig Agricultural Advancement Project HCAAPD-C-2 | Catubig Service Area/Northern Samar, Region 8 | 2014-03-15 | 1st | NIA | LF | 172.723 | 874 | 2011-09-22 | 2014-01-31 | -53.54 | O | 0.3685 | 0.2713 | 0 | 0.03 | 0.07 | 0.05 | 78.98 | -
Brostan Construction and Development | 12360 | L | AAA | MB | GE1 | Road Opening/Const. of Aguinaldo-Magallanes-Nasugbu Rd. (East-West), Bendita Sect. | Magallanes, Cavite | 2011-08-17 | 1st | IVA | LF | 24.1 | 90 | 2011-02-14 | 2011-05-14 | 2.77 | O | 0.333 | 0.3 | 0.15 | 0.03 | 0.05 | 0.033 | 89.6 | -
Brostan Construction and Development | 12360 |  |  |  |  | Rehab./Reconst./Upgrading of Santiago-Tuguegarao Road (Roxas Section) |  | 2010-02-23 |  | II |  | 19.29 | 228 |  |  |  | O | 0.339 | 0.3 | 0.15 | 0.03 | 0.05 | 0.05 | 91.9 | -
BUGANI CONSTRUCTION AND ENTERPRISES INC. | 36435 | L | C | SB | GE | Construction of Multi-Purpose Building (Phase II) | Amduntog, Asipulo, Ifugao | 2015-06-06 | Final | Ifugao 1st DEO | LF | 1.978 | 98 | 2014-10-06 | 2015-01-11 | 0% | C | 0.332 | 0.2 | 0.3 | - | - | - | 83.2% | *86.92% Satisfactory
Bugani Construction and Enterprises, Inc. | 36435 | L | C | SB | GB | Construction of Multi-Purpose Building (Phase II) | Amduntog, Asipulo, Ifugao | 2014-11-24 | 1st | CAR | LF | 1.8493 | 88 | 2014-10-06 | 2015-01-01 | 5.17% | O | 0.377 | 0.24 | 0.15 | 0.03 | 0.047 | 0.05 | 89.4% | 89.40% Very Satisfactory
Builders Multi-Purpose Cooperative (BMPC) | 31386 | L | B | SB | GB1 | Const. of Macangao Agri. Vocational HS | Lupon, Davao Oriental | 2011-08-19 | 1st | XI | LF | 1.779 | 90 | 2011-06-01 | 2011-08-29 | 1.11 | O | 0.373 | 0.24 | 0.15 | 0.03 | 0.045 | 0.033 | 87.1 | -
Busilac Builders, Incorporated | 7701 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of Damaged National Road, Ilocos Norte-Apayao Road |  | 2009-09-09 | 1st | I |  | 24.758 | 206 |  |  |  | O | 0.295 | 0.3 | 0.15 | 0.03 | 0.05 | 0.033 | 85.8 | -
BVG Construtcion and Development Corp. | [5 empty] | Bamban Communal Irrigation System | Bamban, Tarlac | 2016-05-12 | Final | NIA | LF | 33.927 | 210 | 2014-03-19 | 2016-12-23 | 0 | C | 0.4079 | 0.2 | 0.3 | - | - | - | 90.79 | 82.51% Satisfactory
BVG Contruction and Development Corp. |  | L |  |  |  | Bamban Communal Irrigation System | Bamban, Tarlac | 2015-08-15 | 1st | NIA | LF | 33.927 | 210 | 2014-03-19 | 2014-10-15 | -5.74 | O/E | 0.2549 | 0 | 0.0926 | 0.0075 | 0.0047 | 0.05 | 40.97 | -
C & F Construction & Development Corporation | 3509 | L | A | MA | GE | Asphalt Overlay of N. Domingo St., K007+542 (Banahaw St.) - K007+792 (near Aurora Blvd.), K0006+372 - K0007+217) | Quezon City | 2014-11-28 | 1st | NCR | LF | 23.2091 | 241 | 2014-01-30 | 2014-09-27 | 0% | O | 0.43 | 0.133 | 0.3 |  |  |  | 86.3% | 86.30% Satisfactory
C & F Construction & Development Corporation | 3509 | L | A | MA | GE1 | Impv't./Asphalt Overlay of Ermin Garcia St., K0011+(-240)-K0011+000-K0012+677 | Quezon City | 2013-08-05 | 1st | NCR | LF | 19.831 | 150 | 2013-03-25 | 2013-08-21 | 0.95 | O | 0.347 | 0.206 | 0.15 | 0.03 | 0.05 | 0.05 | 83.3 | -
C & F Construction & Development Corporation | 3509 | L | A | MA | GE1 | Reblocking with Asphalt Overlay of Aurora Blvd. (East Bound), EDSA-Marikina Bdry. Sta. 10+(-347)-Sta.13+105 | Quezon City | 2012-08-10 | 1st | NCR | LF | 30.827 | 180 | 2012-02-24 | 2012-08-21 | -1.46 | O | 0.38 | 0.3 | 0.135 | 0.023 | 0.035 | 0.033 | 90.6 | -
C & F CONSTRUCTION & DEVELOPMENT CORPORATION | 3509 | L | A | MB | GE | Paving of Shoulder along Eastern Bulacan Road, K0066+(-68)-K0069+000, D.R.T., Bulacan | D.R.T., Bulacan | 2015-08-30 | 1st & Final | Bulacan Second DEO | LF | 18.597 | 151 | 2015-02-18 | 2015-07-18 | - | C | 0.387 | 0.2 | 0.3 | - | - | - | 88.7% | *88.7% Satisfactory
C D U Construction | 13915 | L | B | SB | GE2 | Const. of Flood Control (Drainage Canal) along Palapag-Mapanas-Gamay-Lapinig Rd., Mapno-Cabatuan Sect., K0805+300-K0817+800 | Palapag, Northern Samar | 2013-08-06 | 1st | VIII | LF | 9.141 | 180 | 2013-03-27 | 2013-09-23 | -5.44 | O | 0.332 | 0.3 | 0.096 | 0.03 | 0.06 | 0.05 | 86.8 | -
C D U Construction | 13915 | L | B | MA | GB1 | Const. of Sch. Bldg., Calbayog City Night High Sch. | Calbayog City, Samar | 2013-08-14 | 1st | VIII | LF | 4.994 | 150 | 2013-04-03 | 2013-08-30 | 2.33 | O | 0.343 | 0.24 | 0.15 | 0.03 | 0.047 | 0.025 | 83.5 | -
C D U Construction | 13915 | L | B | MA | GB1 | Const. of Sch. Bldg. (Two Storey) College of Law, University of Eastern Phil. (Main Campus) | Catarman, Northern Samar | 2013-08-09 | 1st | VIII | LF | 5.675 | 180 | 2013-03-27 | 2013-09-22 | 6.38 | O | 0.392 | 0.24 | 0.15 | 0.03 | 0.052 | 0.05 | 91.4 | -
C D U Construction | 13915 |  |  |  |  | Road Opening/Const. of Nijaga Sect. along Calbayog Diversion Rd. |  | 2010-06-12 |  | VIII |  | 19.295 | 150 |  |  |  | O | 0.353 | 0.238 | 0.15 | 0.03 | 0.037 | 0.033 | 84.1 | -
C D U Construction | 13915 |  |  |  |  | Rehab./Reconst./Upgrading of Catarman-Calbayog Rd., |  | 2010-06-14 |  | VIII |  | 19.275 | 130 |  |  |  | O | 0.325 | 0.24 | 0.15 | 0.03 | 0.042 | 0.05 | 83.7 | -
C D U Construction | 13915 |  |  |  |  | Conc. of Laoang-Lapinig-Arteche-San Policarpio Road Mapanas-Manaybanay Section, with exception |  | 2010-08-25 |  | VIII |  | 18.82 | 200 |  |  |  | O | 0.321 | 0.3 | 0.15 | 0.03 | 0.025 | 0.05 | 87.6 | -
C D U Construction | 13915 | L | B | MA | GE1 | Conc. of Laoang-Calomotan Road |  | 2008-11-29 | 1st | VIII |  | 19.065 | 180 |  |  |  | O | 0.358 | 0.24 | 0.1 | 0.015 | 0.025 | 0.1 | 83.8 | -
C D U Construction | 13915 | L | B | MA | GE1 | Upgrading of Allen-Frederick National Road |  | 2009-09-14 | 1st | VIII |  | 8.652 | 120 |  |  |  | O | 0.337 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 85.7 | -
C D U Construction | 13915 | L | B | MA | GE1 | Conc. of Laoang-Lapinig-Arteche (SONA), Laoang-Binaticlan Sect. |  | 2009-09-12 | 1st | VIII |  | 18.756 | 200 |  |  |  | O | 0.331 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 85.1 | -
C D U Construction | 13915 | L | B | MA | GE1 | Upgrading of Allen-Cabacungan National Road |  | 2009-09-14 | 1st | VIII |  | 19.231 | 150 |  |  |  | O | 0.334 | 0.24 | 0.15 | 0.015 | 0.05 | 0.05 | 83.9 | -
C L Carandang Enterprises | 29494 | L | A | MA | GE1 | Rehab./Reconst. of Damaged Masbate Port National Road |  | 2009-05-25 | 1st | V |  | 7.715 | 150 |  |  |  | O | 0.317 | 0.3 | 0.15 | 0.023 | 0.04 | 0.033 | 86.3 | -
C L Carandang Enterprises | 29494 | L | A | SB | GB1 | Rehab./Impvt. of DPWH Bldg., Masbate 1st DEO |  | 2009-05-25 | 1st | V |  | 1.926 | 80 |  |  |  | O | 0.331 | 0.24 | 0.15 | 0.03 | 0.04 | 0.033 | 82.4 | -
C L Carandang Enterprises | 29494 | L | A | MA | GE2 | Const. of Drainage and Slope Protection, Masbate-Cataingan Rd. (K0001+700-K0015+554) w/ exception | Masbate City | 2013-03-12 | 1st | V | LF | 9.332 | 132 | 2012-12-07 | 2013-04-17 | 8.28 | O | 0.304 | 0.3 | 0.15 | 0.03 | 0.025 | 0.033 | 84.2 | -
C L Carandang Enterprises | 29494 |  |  |  |  | Road Upgrading of San Fernando-Talisay Rd. |  | 2010-08-24 |  | V |  | 11.001 | 190 |  |  |  | O | 0.313 | 0.3 | 0.15 | 0.02 | 0.025 | 0.033 | 84.1 | -
C L Carandang Enterprises / Lim General Contractor Corporation (JV) | JV-09-089 |  |  |  |  | Conc. Of Jct. Paguiran-Brgy. Paguiran rd. |  | 2010-08-21 |  | V |  | 72.357 | 378 |  |  |  | O | 0.33 | 0.241 | 0.15 | 0.022 | 0.033 | 0.033 | 80.9 | -
C L V Enterprises | 18512 | L | D | SB | GB1 | Const. of Multi-Purpose Building, Cawayan |  | 2009-05-27 | 1st | X |  | 0.939 | 119 |  |  |  | O | 0.3 | 0.3 | 0.15 | 0.02 | 0.025 | 0.033 | 82.8 | -
C L V Enterprises | 18512 | L | D | SB | GB1 | Const. of Multi-Purpose Building, Bukidnon State University |  | 2009-09-02 | 1st | X |  | 3.372 | 150 |  |  |  | O | 0.388 | 0.24 | 0.15 | 0.03 | 0.047 | 0.033 | 88.8 | -
C N E Construction | 22148 | L | B | MA | GB1 | Const. of 1 unit 2 storey 8-CL & 1 unit - 2 storey 6 CL Sch. Bldg., Tanauan Sch. of Craftsman & Home Industries (LIT Tanauan Campus) | Tanauan, Leyte | 2013-08-19 | 1st | VIII | LF | 16.594 | 240 | 2013-03-19 | 2013-11-13 | 16 | O | 0.4 | 0.237 | 0.15 | 0.02 | 0.019 | 0.05 | 87.6 | -
C N E Construction | 22148 | L | B | SB | GE1 | Rehab. of Rd. Slip along Tacloban-Ormoc-Baybay-Maasin Rd. along Baybay-Matalom Rd. | Baybay City, Leyte | 2013-03-15 | 1st | VIII | LF | 6.495 | 100 | 2013-01-25 | 2013-05-04 | 0.33 | O | 0.4 | 0.24 | 0.15 | 0.03 | 0.047 | 0.033 | 90 | -
C. DY BUILDERS & GENERAL MERCHANDISE (Formerly CD Construction) | 17003 | L | B | MA | GB | Completion of Hospital Facilities (Tagoloan Mini Hospital), Tagoloan, Misamis Oriental | Tagoloan, Misamis Oriental | 2015-06-08 | Final | Misamis Oriental Second DEO | LF | 4.648 | 60 | 2014-09-09 | 2014-11-07 | - | C | 0.492 | 0.133 | 0.3 | - | - | - | 92.5% | *92.5% Very Satisfactory
C. DY BUILDERS & GENERAL MERCHANDISE (Formerly: CD Construction) | 17003 | L | B | MA | GB | Construction of Multi-Purpose Building (TESDA), Ozamiz City, Misamis Occidental | Ozamiz City, Misamis Occidental | 2015-11-19 | Final | Misamis Occidental 2nd | LF | 1.9404 | 60 | 2015-09-14 | 2015-11-13 | (+) 24.5% | C | 0.357 | 0.2 | 0.3 | - | - | - | 85.7% | 85.7% Satisfactory
C. G. CABANA CONSTRUCTION AND SUPPLIES | 10728 | L | B | MA | GE | Tourist Visitors Center and Three (3) Green Restrooms to ward Underground River | Puerto Princesa City, Palawan | 2015-07-15 | 1st | TIEZA | LF | 6 | 180 | 2015-01-05 | 2015-07-10 | -24.55 | O | 0.383 | 0.2541 | 0 | 0.03 | 0.0233 | 0.0333 | 72.39 | -
C. M. Tan Construction | 28087 | L | B | MA | GE | Construction/Improvement of Road along NRJ - Bayugan - Calaitan - Tandag Road, K1295+260 - K1296+615 | Bayugan, Agusan del Sur | 2014-08-06 | 1st | XIII | LF | 42.1191 | 276 | 2014-02-11 | 2014-11-13 | 2.66 | O | 0.4 | 0.254 | 0.15 | 0.007 | 0.023 | 0.05 | 88.4 | -
C. T. Leoncio Construction & Trading | 17371 | L | A | MA |  | Gasan Port Development Project | Gasan, Marinduque | 2016-04-14 | 3rd & Final | DOTC | LF | 16.602 | 347 | 2015-03-04 | 2016-02-13 | 0 | C | 0.448 | 0.2 | 0.3 | - | - | - | 94.8 | 91.40% V. Satisfactory
C. T. Leoncio Construction & Trading | 17371 | L | A | MB |  | Romblon Airport Development Project | Alcantara, Romblon | 2016-09-28 | 1st | DOTC | LF | 9.9901 | 165 | 2015-06-01 | 2015-10-28 | 39.22 | O-S | 0.4 | 0.3 | 0.15 | 0.03 | 0.028 | 0.05 | 95.8 | -
C. T. LEONCIO CONSTRUCTION & TRADING / MAR-VEL CONSTRUCTION & SUPPLY (JOINT VENTURE) | JV-14-805 | L | A | MB | GE | Construction/Rehabilitation/Improvement of Revetment/River Control along Sinalhan Waterways | Brgy. Sinalhan, Sta. Rosa City, Laguna 1st LD | 2015-08-28 | 1st & Final | Laguna 2nd | LF | 37.251 | 180 | 2015-03-25 | 2015-09-20 | 20% | C | 0.444 | 0.133 | 0.3 | - | - | - | 87.7% | *87.7% Satisfactory
C. T. Leoncio Construction and Trading | 17371 |  |  | MA |  | Sta. Fe Port Development Project | Sta. Fe, Romblon | 2015-10-14 | 1st | DOTC | LF | 12.967 | 180 | 2015-06-01 | 2015-11-27 | -7.39 | O | 0.3769 | 0.3 | 0.0761 | 0.03 | 0.0408 | 0.0333 | 85.71 | -
C. T. Leoncio Construction and Trading | 17371 |  | A | MA |  | Gasan Port Development Project | Gasan, Marinduque | 2015-11-11 | 2nd | DOTC | LF | 17.614 | 180 | 2015-03-04 | 2016-01-04 | -5.39 | O | 0.3714 | 0.3 | 0.0961 | 0.015 | 0.0583 | 0.05 | 89.08 | -
C. T. Leoncio Construction and Trading | 17371 |  | A | MA |  | Sta. Fe Port Development Project | Sta. Fe, Tablas Island, Romblon/ Region IV-B | 2016-02-25 | 2nd & Final | DOTC | LF | 12.948 | 251 | 2015-06-01 | 2016-04-07 | 13.09 | C | 0.4768 | 0.2 | 0.3 | - | - | - | 97.68 | 90.50% V. Satisfactory
C.A. BETALAC CONSTRUCTION & GEN. MDSE. | 28222 | L | A | MA | GE | Widening of Roads along Isulan Jct.-Ninoy Aquino Road, K1776+(-749)-K1776+451 | Isulan, Sultan Kudarat | 2015-06-03 | 1st | Sultan Kudarat 1st DEO | LF | 22.685 | 146 | 2015-03-04 | 2015-07-27 | 8.49% | O | 0.327 | 0.24 | 0.15 | 0.03 | 0.048 | 0.033 | 82.8% | -
C.A. BETALAC CONSTRUCTION AND GEN. MDSE. | 28222 | L | A | MA | GE | Widening of Roads along Isulan Jct.-Ninoy Aquino Road, K1776+(-749) - K1776+451 | Isulan, Sultan Kudarat | 2015-11-11 | Final | Sultan Kudarat First DEO | LF | 22.5195 | 161 | 2015-03-04 | 2015-08-11 | 0.00% | C | 0.447 | 0.136 | 0.3 | - | - | - | 88.3% | 88.3% Satisfactory
C.B Garay Philwide Builders | 6004 |  |  |  |  | Construction of 1 Unit 3-Storey, 15-Classroom School Building |  | 2010-01-18 |  | NHA |  | 18.115 | 150 |  |  |  | O | 0.3596 | 0.2756 | 0 | 0.015 | 0.0255 | 0.0167 | 69.24 | -
C.B Tampengco Construction & Supply | 18505 | L | B | MA | GB1 | Completion of School Bldg., Tampo E/S Main, Brgy. Tampo |  | 2009-09-03 | 1st | NCR |  | 1.904 | 60 |  |  |  | O | 0.328 | 0.225 | 0.15 | 0.03 | 0.041 | 0.033 | 80.7 | -
C.B. Tampengco Construction & Supply | 18505 | L | B | MA | GB1 | Const. of Three (3) Storey, Nine (9) Cl Sch. Bldg. Tinajeros NHS(Phase II)-Acacia Annex | Tinajeros, Malabon City | 2013-08-12 | 1st | NCR | LF | 5.784 | 150 | 2013-03-27 | 2013-08-23 | 2.44 | O | 0.303 | 0.24 | 0.15 | 0.03 | 0.035 | 0.033 | 79.1 | -
C.B. Tampengco Construction & Supply | 18505 | L | B | MA | GB1 | Const. of Three (3), Nine (9) Classroom Tinajeros NHS-Acacia Annex | Malabon City | 2013-03-15 | 1st | NCR | LF | 5.563 | 135 | 2012-11-19 | 2013-04-02 | 0.83 | O | 0.39 | 0.24 | 0.15 | 0.023 | 0.029 | 0.033 | 86.5 | -
C.B. Tampengco Construction & Supply | 18505 | L | B | MA | GE1 | Imprv't. of Marikina-Infante Rd., Sta. Cruz, Dela-Paz Sect. 1st Leg. District | Antipolo City | 2012-07-31 | 1st | IVA | LF | 17.46 | 180 | 2012-03-29 | 2012-09-24 | 0.01 | O | 0.359 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 88.4 | -
C.B. TAMPENGCO CONSTRUCTION & SUPPLY | 18505 | L | B | MA | GE | Rehabilitation of Local Roads (Matahong St. and Luna II St.) Brgy. San Agustin, Malabon City | Brgy. San Agustin, Malabon City | 2015-06-05 | Final | Malabon-Navotas DEO | LF | 5.381 | 90 | 2015-03-10 | 2015-06-07 | (+) 4.44 | C | 0.482 | 0.133 | 0.3 | - | - | - | 91.5% | *91.5% Very Satisfactory
C.C.M. Construction | 11043 | L | B | MA | GE | Rehabilitation/Reconstruction of Loay Interior Road, Section 1) K0134+000 to K0136+000; Section 2) K0145+000 to K0145+157; Section 3) K0145+181 to K0145+301 | Bohol Province | 2014-10-26 | 1st | VII | LF | 48.4952 | 241 | 2014-03-31 | 2014-11-26 | -6.54% | O | 0.344 | 0.3 | 0.085 | 0.03 | 0.047 | 0.033 | 83.9% | 83.90% Satisfactory
C.C.M. Construction | 11043 | L | B | MA | GE1 | Conc./Widening of Dauis-Panglao Island Center Rd., Sta.3+800-Sta.6+635, Dauis-Panglao | Bohol | 2013-03-12 | 2nd | VII | LF | 48.619 | 300 | 2012-01-24 | 2012-11-18 | - | O | 0.332 | 0.2 | 0 | 0.03 | 0.038 | 0.017 | 61.7 | -
C.C.M. Construction | 11043 | L | B | MA | GE1 | Conc./Widening of Dauis-Panglao Island Center Rd., Sta.3+800-Sta.6+635, Dauis-Pangalo | Bohol | 2012-08-07 | 1st | VII | LF | 48.619 | 270 | 2012-01-24 | 2012-10-19 | 0.12 | O | 0.365 | 0.239 | 0.15 | 0.03 | 0.05 | 0.033 | 86.7 | -
C.C.M. CONSTRUCTION | 11043 | L | B | MA | GE | Rehabilitation/Reconstruction of Loay Interior Road, Section 1: K0134+000-K0136+000; Section 2: K0145+000-K0145+157; Section 3: K0145+181-K0145+301, Bohol Province | Loay Interior Road, Bohol Province | 2015-06-09 | Final | Regional Office No. VII | LF | 48.495 | 341 | 2015-03-31 | 2016-03-06 | 0% | C | 0.46 | 0.137 | 0.3 | - | - | - | 89.7% | *86.22% Satisfactory
C.C.M. CONSTRUCTION | 11043 | L | B | MA | GE | Network Development-Construction of By-Passess/ Diversion Roads, including ROW, Construction of Tagbilaran City By-Pass; Section 1: Sta. 0+000.000 - Sta. 0+244.440; Section 2: Sta. 0+000.000 - Sta. 0+228.610; Section 3: Sta. 6+917.780 - Sta. 7+286.240; Section 4: Sta. 0+000.000 - Sta. 0+500.000; Section 5: Sta. 1+143.300 - Sta. 1+485.350; Section 6: Sta. 5+178.900 - Sta. 5+668.650; Section 7: Sta. 1+143.300 - Sta. 1+571.150; Section 8: Sta. 1+918.500 - Sta. 2+940.500; Section 9: Sta. 0+000.000 - Sta. 0+979.000, Bohol 1st DEO/ LD, Bohol Province | Bohol 1st DEO/ LD, Bohol Province | 2015-11-19 | 1st | Regional Office | LF | 89.2959 | 300 | 2015-04-03 | 2016-01-27 | 0.079 | OG | 0.382 | 0.24 | 0.15 | 0.03 | 0.032 | 0.05 | 88.4% | 88.4% Satisfactory
C.D.J. Builders & Construction Supplies | 30347 | L | B | MA | GE | Construction/Rehab. of Gucab Flood Control Project, Sta. 0+000 - Sta. 0+302 | Gucab, Echague, Isabela | 2014-08-12 | 1st | II | LF | 19.2999 | 201 | 2014-03-07 | 2014-09-23 | 15.08 | O | 0.279 | 0.3 | 0.15 | 0.03 | 0.04 | 0.033 | 83.2 | -
C.D.J. BUILDERS & CONSTRUCTION SUPPLIES | 30347 | L | B | MA | GE | Construction/Rehabilitation of Flood Control Projects in Isabela 4th DEO/4th LD-Gucab Flood Control | Sta. 0+000 - Sta. 0+302, Echague, Isabela | 2015-06-09 | Final | Isabela 4th DEO | LF | 19.3 | 201 | 2014-03-07 | 2014-09-23 | 0% | C | 0.333 | 0.2 | 0.3 | - | - | - | 83.3% | *83.12% Satisfactory
C.Dy Builders and General Merchandise (Formerly: CD Construction) | 17003 | L | B | MA | GB | Completion of Hospital Facilities (Tagoloan Mini Hospital) | Tagoloan, Misamis Oriental | 2014-10-28 | 1st | X | LF | 4.4675 | 60 | 2014-09-09 | 2014-11-07 | 0% | O | 0.358 | 0.24 | 0.15 | 0.01 | 0.022 | 0.033 | 81.3% | 81.30% Unsatisfactory
C.F. Trinidad Construction and Supplies Corp. (Formerly: C.F. Trinidad Construction) | 9199 | L | B | MA | GE1 | Prev. Maint. (Asphalt Overlay) of Imelda Ave., 1. K0018+(-232)-K0018+808; 2. K0018+(-010)-K0020+732 (Int. Sect.) | Cainta, Rizal | 2013-03-22 | 1st | IVA | LF | 41.107 | 179 | 2013-01-29 | 2013-07-26 | 6.78 | O | 0.385 | 0.3 | 0.15 | 0.03 | 0.048 | 0.033 | 94.6 | -
C.F. Trinidad Construction and Supplies Corp. (Formerly: C.F. Trinidad Construction) | 9199 | L | B | MA | GE1 | Widening of Taytay Diversion Road (6-Lanes) | Taytay, Rizal | 2012-07-30 | 2nd | IVA | LF | 41.454 | 240 | 2012-01-16 | 2012-09-12 | 0.02 | O | 0.381 | 0.178 | 0.15 | 0.03 | 0.045 | 0.05 | 83.4 | -
C.G. CABANA CONSTRUCTION AND SUPPLIES | 10728 | L | B | MA | GE | Typhoon Damages at Tapyas Hill | Coron, Palawan | 2015-08-19 | 1st | TIEZA | LF | 7.5 | 105 | 2015-05-20 | 2015-09-01 | -17.33 | O | 0.3625 | 0.2986 | 0 | 0.03 | 0.053 | 0.1 | 84.44 | -
C.G. CABANA CONSTRUCTION AND SUPPLIES | 10728 | L | B | MA | GE | Tourist Information Center and Tourist Rest Area (Green Restroom) | Buenavista, Honda Bay and Baywalk, Puerto Princesa City,Palawan | 2015-10-28 | Final | TIEZA | LF | 6 | 180 | 2015-03-02 | 2015-09-11 | 0 | C | 0.479 | 0.2 | 0.3 |  |  |  | 97.9 | 80.10% Unsatisfactory
C.J.T. PASCUAL CONSTRUCTION | 34285 | L | C | SB | GE | Construction/Concreting of Nagattatan Road @ Nagattatan | Pamplona, Cagayan | 2014-10-23 | 1st | II | LF | 3.96 | 47 | 2014-03-25 | 2014-05-10 | 2.27% | O | 0.414 | 0.133 | 0.3 |  |  |  | 84.7% | 84.70% Satisfactory
C.L Carandang Enterprises | 29494 | L | A | MA | GE1 | Rehab./Reconst. of Masbate Circumferential Road |  | 2009-08-26 | 1st | V |  | 32.805 | 210 |  |  |  | O | 0.371 | 0.279 | 0.15 | 0.03 | 0.037 | 0.033 | 90 | -
C.L Carandang Enterprises | 29494 | L | A | MA | GE1 | Rehab./Reconst. of Damaged Masbate Port National Road |  | 2009-08-26 | 2nd | V |  | 7.715 | 180 |  |  |  | O | 0.32 | 0.3 | 0.15 | 0.03 | 0.047 | 0.033 | 88 | -
C.L Carandang Enterprises | 29494 | L | A | MA | GE1 | Impvt. of Canvanez-Nasandig Brgy. Road |  | 2009-09-26 | 1st | V |  | 4.725 | 120 |  |  |  | O | 0.293 | 0.3 | 0.15 | 0.03 | 0.033 | 0.033 | 83.9 | -
C.L CARANDANG ENTERPRISES | 29494 | L | A | MA | GB | Cluster E - Local Infrastructure Program (LIP) Construction of Multi-Purpose Covered Court (Multi-Purpose Covered Court per Barangay: Brgy. Candelaria, Brgy. Dapdap, Brgy. Marcella, Brgy. Simawa, Brgy. San Jose, Uson, Masbate | Barangay Marcella, Uson, Masbate | 2015-09-04 | 1st & Final | Masbate Second DEO | LF | 1.91 | 120 | 2015-04-13 | 2015-08-10 | 20% | C | 0.497 | 0.133 | 0.3 | - | - | - | 93% | *93% Very Satisfactory
C.L. Carandang Enterprises | 29494 | L | A | MA | GE2 | Const./Repair of Slope Protection/Embankment and Draiange System Masbate-Cataingan-Placer Rd. (Km.27+600-Km.29+404.25) | Masbate | 2013-03-12 | 1st | V | LF | 8.96 | 119 | 2012-12-20 | 2013-04-17 | -38.33 | O | 0.322 | 0.294 | 0 | 0.02 | 0.01 | 0.017 | 66.3 | -
C.M Dancel Construction & Supply | 12640 |  |  |  |  | Asphalt Overlay along Laoag-Sarrat-Piddig-Solsona Road |  | 2010-02-24 |  | I |  | 13.678 | 90 |  |  |  | O | 0.3 | 0.3 | 0.15 | 0.03 | 0.055 | 0.033 | 86.8 | -
C.M Dancel Construction & Supply | 12640 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved National Road, Bonifacio Road |  | 2009-06-05 | 1st | I |  | 10.26 | 130 |  |  |  | O | 0.358 | 0.225 | 0.15 | 0.03 | 0.045 | 0.033 | 35.8 | -
C.M. Pancho Construction Incorporated | 183 | L | AAA | LB | GE1 | Rehab. of Surigao-Davao Coastal Road, Jct. Bacuag-Claver Section |  | 2008-11-23 | 2nd | XIII |  | 661.069 | 540 |  |  |  | O | 0.338 | 0.3 | 0.07 | 0.03 | 0.07 | 0.1 | 90.8 | -
C.M. Pancho Construction, Incorporated | 183 | L | AAA | LB | GE1 | Const. of Dalton Pass Nueva Vizcaya (New Alignment) San Jose-Aritao Rd., Segment 5, Dalton Pass Sect. Eastern Alternate Route | Nueva Vizcaya | 2013-08-15 | 1st | II | LF | 351.745 | 720 | 2012-11-13 | 2014-11-02 | 44.76 | O | 0.334 | 0.3 | 0.15 | 0.03 | 0.061 | 0.05 | 92.5 | -
C.M. Tan Construction (Formerly: C.M. Tan Construction Supplies) | 28087 | L | B | SB | GE2 | Const. of Protection Works along NRJ- Bayugan-Esperanza Rd. crossing Luna (Sect. 2) 1276+566.2-1276+648.4 | Esperanza, Agusan del Sur | 2012-11-28 | 1st | XIII | LF | 18.188 | 165 | 2012-09-20 | 2013-03-03 | 1.15 | O | 0.331 | 0.3 | 0.15 | 0.02 | 0.055 | 0.05 | 90.6 | -
C.R. DOMINGO CONSTRUCTION, INC. (Formerly C.R. Domingo Construction) | 2992 | L | A | MA | GE | Construction of Stiffu River Flood Control Project, (Baramban Creek Section) Phase II, left and right Banks Sta. 0+000 - Sta. 0+725, Brgy. Sotero Nuesa, Roxas, Isabela | Roxas, Isabela | 2015-11-14 | 1st | ISABELA 2ND DEO | LF | 33.8327 | 347 | 2015-06-01 | 2016-05-12 | (+) 1.71 | OG | 0.373 | 0.24 | 0.15 | 0.024 | 0.035 | 0.033 | 85.5% | 85.5% Satisfactory
C.R. DOMINGO CONSTRUCTION, INC. (Formerly: C.R. Domingo Construction) | 2992 | L | A | MA | GE | Road Upgrading (Gravel to Paved) along Alfonso Lista-Aurora Boundary Road, K0445+540 - K0447+130 | Alfonso Lista, Ifugao | 2015-06-08 | Final | Ifugao 2nd DEO | LF | 46.653 | 296 | 2014-02-17 | 2014-12-09 | 0% | C | 0.384 | 0.2 | 0.3 | - | - | - | 88.4% | *87.14% Satisfactory
C.R. DOMINGO CONSTRUCTION, INC. (Formerly: C.R. Domingo Construction) | 2992 | L | A | MA | GE | Road Upgrading (Gravel to Paved) along Banaue-Mayoyao-Alfonso Lista-Isabel Bdry. Road, K0422+243 - K0422+558 and K0425+483 - K0426+092 | Aguinaldo, Ifugao | 2015-06-08 | Final | CAR | LF | 30.117 | 297 | 2014-06-11 | 2015-04-03 | 0% | C | 0.402 | 0.2 | 0.3 | - | - | - | 90.2% | *89.3% Very Satisfactory
C.R. DOMINGO CONSTRUCTION, INC. (Formerly: C.R. Domingo Construction) | 2992 | L | A | MA | GE | Road Upgrading (Gravel to Paved) along Ubao-Taang Road, K0399+540 - K0400+837 | Aguinaldo, Ifugao | 2015-06-08 | Final | CAR | LF | 43.806 | 299 | 2014-06-11 | 2015-04-05 | 0% | C | 0.389 | 0.2 | 0.3 | - | - | - | 88.9% | *90.1% Very Satisfactory
C.R. DOMINGO CONSTRUCTION, INC. (Formerly: C.R. Domingo Construction) | 2992 | L | A | MA | GE | Road Upgrading (Unpaved to Paved) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Strandards (HDM-4 Project Analysis) (Intermittent Section), A. Lista, Aurora Bdry. Road, K0447+640 to K0449+640, Alfonso Lista, Ifugao | Alfonso Lista, Ifugao | 2015-08-30 | 1st | Ifugao 2nd DEO | LF | 45.966 | 239 | 2015-02-10 | 2015-10-06 | 5.21% | O | 0.38 | 0.238 | 0.15 | 0.03 | 0.061 | 0.05 | 90.9% | -
C.R. DOMINGO CONSTRUCTION, INC. (Formerly: C.R. Domingo Construction) | 2992 | L | A | MA | GE | Repair/Rejabilitation and Construction of San Pedro to Bagnos Farm to Market Road, San Pedro, Alicia, Isabela | San Pedro, Alicia, Isabela | 2015-08-29 | 1st & Final | Isabela 3rd DEO | LF | 19.899 | 178 | 2014-11-28 | 2015-05-24 | 32.22% | C | 0.424 | 0.193 | 0.3 | - | - | - | 91.7% | *91.7% Very Satisfactory
C.R. Domingo Construction, Inc. (Formerly: CR Domingo Const.) | 2992 | L | A | MA | GE | Road Upgrading (Gravel to Paved) along Ubao - Taang Road, K0399+540 - K0400+837 | Aguinaldo, Ifugao | 2014-11-26 | 1st | CAR | LF | 43.8059 | 257 | 2014-06-11 | 2015-02-22 | 22% | O | 0.358 | 0.265 | 0.15 | 0.03 | 0.056 | 0.05 | 90.9% | 90.90% Very Satisfactory
C.R. Domingo Construction, Inc. (Formerly: CR Domingo Const.) | 2992 | L | A | MA | GE | Road Upgrading (Gravel to Paved) along Banaue-Mayoyao-Alfonso Lista-Isabela Boundary Road, KO 422+243 - KO 422+558 and KO 425+558 and KO 425+483 - KO 426+092 | Aguinaldo, Ifugao | 2014-11-26 | 1st | CAR | LF | 30.1174 | 255 | 2014-06-11 | 2015-02-20 | 1.46% | O | 0.358 | 0.243 | 0.15 | 0.03 | 0.056 | 0.05 | 88.7% | 88.70% Satisfactory
C.R. Domingo Construction, Inc. (Formerly: CR Domingo Const.) | 2992 | L | A | MA | GE | Road Upgrading (Gravel to Paved) along Alfonso Lista - Aurora Boundary Road, KO445+540 - KO447+130 | Alfonso Lista, Ifugao | 2014-11-26 | 1st | CAR | LF | 46.6529 | 296 | 2014-02-17 | 2014-12-09 | -3.76% | O | 0.352 | 0.281 | 0.112 | 0.03 | 0.055 | 0.033 | 86.3% | 86.30% Satisfactory
C.R. Domingo Construction, Inc. (Formerly: CR Domingo Const.) | 2992 | L | A | MA | GE1 | Rd. Upgrading (Gravel to Paved) along Ubao-Taang Rd., K0422+300-K0425+765 (w/ exceptions) | Aguinaldo, Ifugao | 2013-08-07 | 1st | CAR | LF | 44.268 | 215 | 2013-02-21 | 2013-09-23 | -4.67 | O | 0.341 | 0.3 | 0.103 | 0.03 | 0.05 | 0.017 | 84.1 | -
C.R. Domingo Construction, Inc. (Formerly: CR Domingo Const.) | 2992 | L | A | MA | GE1 | Rd. Upgrading (Gravel to Paved) along Alfonso Lista-Aurora Bdry. Rd. K0442+124.5-K0445+540 | Alfonso Lista, Ifugao | 2013-08-07 | 1st | CAR | LF | 38.538 | 230 | 2013-02-21 | 2013-10-08 | -4.67 | O | 0.317 | 0.3 | 0.103 | 0.03 | 0.05 | 0.033 | 83.3 | -
C.T LEONCIO CONSTRUCTION AND TRADING | 17371 | L | A | M | GB | Construction of Multi-Purpose Building at Esteban Abada E/S, Quezon City | Quezon City | 2015-12-08 | Final | QC 1st DEO | LF | 10.5426 | 120 | 2015-03-04 | 2015-07-31 | 0.00% | C | 0.388 | 0.133 | 0.3 | - | - | - | 82.1% | 82.1% Satisfactory
C.T. LEOCIO CONSTRUCTION AND TRADING | 17371 | L | A | M | GE | Construction/Maintenance of Flood Control Mitigation Structures and Drainage System, Deeping/Widening/Construction of Retaining Wall, Estero de Sto. Nino, Pasay City Lone District | Pasay City Lone District | 2015-12-08 | 1st | South Manila DEO | LF | 31.8201 | 236 | 2015-05-15 | 2016-01-04 | (-)6.55% | OG | 0.333 | 0.3 | 0.085 | 0.03 | 0.03 | 0.033 | 81.1% | 81.1% Unsatisfactory
C.T. LEOCIO CONSTRUCTION AND TRADING | 17371 | L | A | M | GE | Construction/Maintenance of Flood Control Mitigation Structures and Drainage System, Deeping/Widening/Construction of Retaining Wall, Estero de Sto. Nino, Pasay City Lone District | Pasay City Lone District | 2015-12-08 | 1st | South Manila DEO | LF | 31.8201 | 236 | 2015-05-15 | 2016-01-04 | (-)6.55% | OG | 0.333 | 0.3 | 0.085 | 0.03 | 0.03 | 0.033 | 81.1% | 81.1% Unsatisfactory
C.T. Leoncio Construction & Trading | 17371 | L | A | MA | GE-5 | Gasan Port Development Project | Gasan, Marinduque | 2015-08-05 | 1st | DOTC | LF | 17.614 | 180 | 12/15/14 | 08/30/15 | -8.23 | O | 0.4 | 0.3 | 0.068 | 0.015 | 0.061 | 0.05 | 89.4 | -
C.T. Leoncio Construction & Trading | 17371 | L | A | MB | GE | Construction/Rehabilitation/Improvement of Clupa-Calauag-Canaman Flood Control | Naga City & Canaman, Camarines Sur | 2014-08-08 | 1st | V | LF | 44.0705 | 234 | 2014-03-16 | 2014-11-04 | 2.41 | O | 0.327 | 0.3 | 0.126 | 0.02 | 0.047 | 0.033 | 85.3 | -
C.T. Leoncio Construction & Trading | 17371 | L | A | MB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads along Rolando Andaya Highway, KO287+000 to KO288+996 | Camarines Sur | 2014-08-06 | 1st | V | LF | 38.8 | 174 | 2014-03-18 | 2014-09-07 | -4.51 | O | 0.347 | 0.3 | 0.105 | 0.022 | 0.045 | 0.033 | 85.2 | -
C.T. Leoncio Construction & Trading | 17371 | L | A | MB | GE1 | Widening of Old Cagayan Valley Rd., Km.45+388-Km.52+985 (Baliuag Sect.) | Baliuag, Bulacan | 2013-08-13 | 1st | III | LF | 33.978 | 165 | 2013-06-04 | 2013-11-15 | 0.59 | O | 0.335 | 0.24 | 0.15 | 0.023 | 0.045 | 0.033 | 82.6 | -
C.T. Leoncio Construction & Trading | 17371 | L | A | MB | GE1 | Rd. Upgrading (Gravel to Paved), Conc, of Cabatuan-New Lucena-Banga Bante Rd., K0028+677-K0030+208.80 | Cabatuan, Iloilo City | 2013-08-20 | 1st | VI | LF | 26.461 | 135 | 2013-06-03 | 2013-10-15 | -3.03 | O | 0.377 | 0.24 | 0.12 | 0.023 | 0.04 | 0.033 | 83.3 | -
C.T. Leoncio Construction & Trading | 17371 | L | A | MB | GE1 | Reconst. Of Siniloan Bridge II along Paete-Pakil Pob. Rd. | Siniloan, Laguna | 2013-03-20 | 2nd | IVA | LF | 28.543 | 201 | 2012-07-02 | 2013-01-19 | -14.64 | O | 0.395 | 0.3 | 0 | 0.03 | 0.055 | 0.033 | 81.3 | -
C.T. Leoncio Construction & Trading | 17371 | L | A | MB | GE1 | Reconst. of Siniloan Bridge II along Paete-Pakil Pob. Rd. | Siniloan, Laguna | 2012-11-27 | 1st | IVA | LF | 28.543 | 170 | 2012-07-02 | 2012-12-19 | -7.72 | O | 0.369 | 0.294 | 0.073 | 0.018 | 0.04 | 0.033 | 82.7 | -
C.T. Leoncio Construction & Trading / Eric Van P. Sesbreno Construction (JV) | JV-12-323 | L | A | MA | GE1 | Rd. Upgrading (Gravel to Paved) Intermittent Sects., Bambang-Kasibu-Quezon-Solano Rd., K0262+000-K0264+050, Antutot Sect. | Kasibu, Nueva Vizcaya | 2013-03-22 | 1st | II | LF | 42.486 | 179 | 2013-01-21 | 2013-07-18 | 24.75 | O | 0.377 | 0.24 | 0.15 | 0.03 | 0.051 | 0.033 | 88.1 | -
C.T. Leoncio Construction & Trading/VCH Construction and Trading - Joint Venture | JV-13-226 | L | A | MB | GE | Reconstruction of Igang Bridge I (Existing Permanent Bridge) along PPN Road, K0219+718, Taytay, Palawan | Taytay, Palawan | 2014-08-06 | 1st | IV-B | LF | 18.071 | 220 | 2014-02-17 | 2014-09-24 | -4.73 | O | 0.373 | 0.227 | 0.103 | 0.03 | 0.045 | 0.033 | 81.1 | -
C.T. Leoncio Construction & Trading/VCH Construction and Trading - Joint Venture | JV-13-226 | L | A | MB | GE | Construction/Improvement of Access Road from Sandoval Airport to Poblacion, K0212+300-K0214+855 | Taytay, Palawan | 2014-11-21 | 1st | IV | LF | 45.9659 | 239 | 2014-04-13 | 2014-12-07 | 1% | O | 0.339 | 0.24 | 0.15 | 0.03 | 0.048 | 0.05 | 85.7% | 85.70% Satisfactory
CAGER CONSTRUCTION AND SUPPLY | 21743 | L | B | SB | GE | MFO 1 - National Road Network Services - Asset Preservation of National Roads, Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads including Drainage based on Pavement Management System/Highway Development and Management-4 (HDM-4) (Intermittent Sections), Secondary Roads, San Mateo - Rodriguez Road, (K0 027+560 - K0 028+750 | - | 2015-08-25 | 1st & Final | Rizal 2nd | LF | 2.248 | 37 | 2015-02-05 | 2015-03-13 | 0% | C | 0.438 | 0.133 | 0.3 | - | - | - | 87.1% | *87.1% Satisfactory
CAMCU Construction and Supply | 18507 | L |  |  | GE2 | Bayag Sur CIP | Leon, Iloilo/Region 6 | 2013-11-13 | 1st | NIA | L | 1.83 | 148 | 2013-05-21 | 2013-10-23 | -12.35 | O | 0.395 | 0.3 | 0.027 | 0.02 | 0.058 | 0.05 | 85 | -
CAMIA CONST. DEVELOPMENT CORPORATION (Formerly: Camia Construction) | 20506 | L | AAA | MB | GE | Construction and Maintenance of Bridges along National Roads, Rehabilitation/Major Repair of Permanent Bridges, Calafug Bridge along Abbut - Conner Rd., Apayao | Apayao | 2015-08-27 | 1st | Apayao 1st DEO | LF | 35.308 | 230 | 2015-03-04 | 2015-10-19 | 10.22% | O | 0.399 | 0.226 | 0.15 | 0.03 | 0.042 | 0.05 | 89.7% | -
CAMIA CONST. DEVELOPMENT CORPORATION (Formerly: Camia Construction) | 20506 | L | AAA | MB | GE | Road Upgrading (Unpaved to Paved) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standards (HDM-4 Project Analysis) (Intermittent Sections) along Conner - Kabugao Road, K0570+000 to K0570+048, K0570+222 to K0570+364, K0585+177 to K0585+834, K0594+774 to K0589+347, K0601+016 to K0602+766, K0603+119 to K0603+187, Apayao | Apayao | 2015-08-27 | 1st | CAR | LF | 173.766 | 360 | 2015-06-30 | 2016-06-23 | 7.87% | O | 0.373 | 0.294 | 0.15 | 0.03 | 0.047 | 0.05 | 94.4% | -
CAMIA CONST. DEVELOPMENT CORPORATION (Formerly: Camia Construction) | 20506 | L | AAA | MB | GE | Construction and Maintenance of Bridges along National Roads, Rehabilitation/Major Repair of Permanent Bridges, Calafug Bridge (B02240LZ) | Abbut-Conner Road | 2015-11-14 | 2nd | Apayao 1st | LF | 35.3083 | 271 | 2015-03-04 | 2015-11-29 | 1.20% | OG | 0.398 | 0.208 | 0.15 | 0.022 | 0.045 | 0.033 | 85.6% | 85.6% Satisfactory
Camia Construction | 20506 | L | AA | MB | GE1 | Concreting along Kabugao-Pudtol-Luna Road, Nagsungbatan Section |  | 2009-06-01 | 1st | CAR |  | 14.117 | 277 |  |  |  | O | 0.4 | 0.3 | 0.15 | 0.03 | 0.045 | 0.033 | 95.8 | -
Camia Construction | 20506 | L | AA | MB | GE1 | Conc. along Kabugao-Pudtol-Luna Road, Swan Section |  | 2009-06-01 | 1st | CAR |  | 18.862 | 277 |  |  |  | O | 0.357 | 0.24 | 0.15 | 0.03 | 0.056 | 0.033 | 86.6 | -
Camia Construction | 20506 | L | AA | MB | GE1 | Upgrading of Kabugao-Pudtol-Luna Road (Lenneng Sect.) |  | 2009-09-04 | 3rd | CAR |  | 13.87 | 402 |  |  |  | O | 0.331 | 0.24 | 0.15 | 0.024 | 0.056 | 0.033 | 83.4 | -
Camia Construction | 20506 | L | AA | MB | GE1 | Rehab. of Kabugao-Pudtol-Luna Road, Lenning Section |  | 2009-05-30 | 2nd | CAR |  | 13.87 | 366 |  |  |  | O | 0.294 | 0.3 | 0.15 | 0.03 | 0.035 | 0.033 | 84.2 | -
Camia Construction | 20506 | L | AA | MB | GE1 | Rehab. of Kabugao-Pudtol-Luna Road, Capitol Poblacion Section |  | 2009-05-30 | 2nd | CAR |  | 18.562 | 391 |  |  |  | O | 0.288 | 0.3 | 0.15 | 0.03 | 0.04 | 0.033 | 84.1 | -
Camia Construction | 20506 | L | AA | MA | GE1 | Rehab. of Kabugao-Pudtol-Luna Road, Capitol-Poblacion Section |  | 2009-02-28 | 1st | CAR |  | 18.563 | 390 |  |  |  | O | 0.351 | 0.3 | 0.15 | 0.03 | 0.035 | 0.033 | #VALUE! | -
Camia Construction | 20506 |  |  |  |  | Road Upgrading of Abbut-Conner- Kabugao Road (Gravel to Concrete), Manag-Guina-ang Section |  | 2010-02-20 |  | CAR |  | 9.358 | 360 |  |  |  | O | 0.381 | 0.234 | 0.15 | 0.03 | 0.04 | 0.033 | 86.8 | -
Camia Construction | 20506 | L | AAA | MB | GE1 | Rehab. of Nat'l Rd. along Conner-Kabugao Road, Cut Section K0570+000-K0571+000 w/ exception, Matalag Sect. | Conner, Apayao | 2012-11-28 | 2nd | CAR | LF | 24.11 | 255 | 2011-11-23 | 2012-08-04 | - | O | 0.372 | 0.3 | 0 | 0.03 | 0.051 | 0.033 | 78.6 | -
Camia Construction | 20506 | L | AAA | MB | GE1 | Rehab. of Nat'l Rd. along Conner-Kabugao Rd., Cut Sect. K0570+000-K0571+000 w/ exception, Matalag Sect. | Conner, Apayao | 2012-08-10 | 1st | CAR | LF | 24.11 | 255 | 2011-11-23 | 2012-08-04 | -33.83 | O | 0.31 | 0.3 | 0 | 0 | 0.037 | 0.033 | 68 | -
CAMIA CONSTRUCTION DEVELOPMENT CORP. | 20506 | L | AAA | LA | GE | Rehabilitaion/Improvement (Concreting) of Dana Ili-Curva Farm to Market Road, Abulug, Cagayan | Abulug, Cagayan | 2015-11-11 | Final | CAGAYAN 2ND DEO | LF | 9.6691 | 120 | 2015-02-13 | 2015-06-12 | (+) 0.28 | C | 0.448 | 0.131 | 0.3 | - | - | - | 87.9% | 87.9% Satisfactory
Camia Construction Development Corporation | 20506 | L | AAA | MB | GE | Widening/Road Upgrading (Gravel to Concrete) along Kabugao, Apayao-Solsona-Ilocos Norte Road, Apayao Side, K0607+378 to K0608+879, Apayao | Ilocos Norte, Road | 2014-08-08 | 1st | CAR | LF | 46.2128 | 239 | 2013-12-04 | 2014-07-30 | 0.08 | O | 0.368 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 88.8 | -
CARLYZ Construction | 19776 | L | D | SB | GB | Construction of Multi-Purpose Building (Public Market) | Poblacion, Kiangan, Ifugao | 2014-11-24 | 1st | CAR | LF | 2.3215 | 120 | 2014-09-05 | 2015-01-02 | 0.78% | O | 0.353 | 0.24 | 0.15 | 0.03 | 0.058 | 0.05 | 88.1% | 88.10% Satisfactory
CARLYZ CONSTRUCTION | 19776 | L | D | SB | GE | Road Construction-Barangay Antipolo Road | Asipulo, Ifugao | 2015-06-06 | Final | Ifugao 1st DEO | LF | 1.863 | 66 | 2015-02-20 | 2015-04-26 | 0% | C | 0.438 | 0.2 | 0.3 | - | - | - | 93.8% | *93.8% Very Satisfactory
CARLYZ CONSTRUCTION | 19776 | L | D | SB | GE | Construction of Multi-Purpose Building (Public Market) | Poblacion, Kiangan | 2015-06-07 | Final | Ifugao 1st DEO | LF | 2.321 | 120 | 2014-09-05 | 2015-01-02 | (+) 0.07% | C | 0.454 | 0.2 | 0.3 | - | - | - | 95.4% | *91.02% Very Satisfactory
CARME ROSE ENTERPRISE | 35007 | L | D | SB | GE | Concreting of Mabini Street Leading to Aklan Freedom Shrine D. Maagma Street | Kalibo, Aklan | 2015-09-01 | 1st | Aklan | LF | 4.018 | 120 | 2015-05-14 | 2015-09-10 | 2.5% | O | 0.371 | 0.239 | 0.15 | 0.03 | 0.055 | 0.05 | 89.5% | -
CARME ROSE ENTERPRISE | 35007 | L | D | SB | GE | Concreting of Mabini Street Leading to Aklan Freedom Shrine, Maagma Street, Kalibo, Aklan | Kalibo, Aklan | 2015-11-11 | Final | Aklan | LF | 4.0178 | 120 | 2015-05-14 | 2015-09-11 | 0.00% | C | 0.375 | 0.2 | 0.3 | - | - | - | 87.5% | 88.7% Satisfactory
Carrascal Integrated Enterprises | 4764 | L | A | MA | GE1 | Rehab./Reconst./Replacement/Retrofitting of Existing Permanent Bridges, Macapagal Bridge along SDCR | Lanuza, Surigao del Sur | 2013-03-16 | 1st | XIII | LF | 5.991 | 88 | 2013-02-04 | 2013-05-02 | 9.87 | O | 0.329 | 0.225 | 0.15 | 0.03 | 0.05 | 0.033 | 81.7 | -
Carrascal Integrated Enterprises | 4764 | L | A | MB | GE1 | Replacement of Bridge along Nat'l Rds. Catupgas Bridge II along Surigao-Davao Coastal Rd. | Surigao del Sur | 2012-03-14 | 1st | XIII | LF | 9.952 | 150 | 2012-01-24 | 2012-06-21 | 0.23 | O | 0.375 | 0.24 | 0.15 | 0.03 | 0.051 | 0.05 | 89.6 | -
Carrascal Integrated Enterprises | 4764 | L | A | MB | GE1 | Replacement of Bridge along Nat'l Rds. Catugpas Bridge 1 along Surigao-Davao Coastal Rd. | Lanuza, Surigao del Sur | 2012-08-14 | 2nd | XIII | LF | 17.416 | 330 | 2012-01-24 | 2012-12-18 | 3.54 | O | 0.355 | 0.3 | 0.15 | 0.03 | 0.05 | 0.05 | 93.5 | -
CARTESIAN BUILDERS | 35386 | L | B | MA | GB | Construction of Multi-Purpose Building | Barangay Don Ruben and Sta.Cruz, San Jose, Dinagat Islands | 2015-06-11 | 1st | DINAGAT ISLANDS DEO | LF | 9.3 | 150 | 2015-03-05 | 2015-08-01 | (+) 2.43% | O | 0.382 | 0.227 | 0.15 | 0.03 | 0.045 | 0.05 | 88.4% | -
CAUAYAN UNITED ENTERPRISES AND CONSTRUCTION BUILDERS | 8816 | L | B | MA | GE | Widening of Daang Maharlika (LZ) K0368+000 - K0373+000 (with exception) | Cabaruan, Cauayan City, Isabela | 2015-06-05 | Final | Isabela 3rd DEO | LF | 26.14 | 272 | 2014-02-05 | 2014-11-03 | -2.26% | C | 0.402 | 0.2 | 0.232 | - | - | - | 83.4% | *82.98% Satisfactory
CAUAYAN UNITED ENTERPRISES AND CONSTRUCTION BUILDERS | 8816 | L | B | MA | GE | Network Development - Off-carriageway Improvement - Improvement of Flaring of Critical Intersections and Junctions, Daang Maharlika, K0366+000 to K0366+613, Brgy. Fermin, District I, Cauayan City, Isabela | Cauayan City, Isabela | 2015-08-29 | 1st | Isabela 3rd DEO | LF | 27.414 | 192 | 2015-05-15 | 2015-11-22 | 4.71% | O | 0.346 | 0.247 | 0.15 | 0.03 | 0.06 | 0.05 | 88.3% | -
Cauayan United Entterprises and Construction Builders | 8816 | L | B | MA | GE | Widening of Daang Maharlika (LZ) K0368+000 - K0373_000 (with excpetion), Cabaruan, Cauayan City, Isabela | Cabaruan, Cauayan City, Isabela | 2014-10-25 | 1st | II | LF | 26.1716 | 267 | 2014-02-05 | 2014-10-29 | -2.27% | O | 0.368 | 0.24 | 0.128 | 0.03 | 0.028 | 0.033 | 82.7% | 82.70% Satisfactory
Cauayan United Entterprises and Construction Builders | 8816 | L | B | MA | GE1 | Prev. Maint. along Daang Maharlika (LZ) K0361+820-K0363+899 (GAA), K0361+793-K0363+667.12 (POW), Nungnungan II | Cauayan City, Isabela | 2013-03-19 | 1st | II | LF | 22.574 | 131 | 2013-01-25 | 2013-06-04 | 1.33 | O | 0.3 | 0.3 | 0.15 | 0.03 | 0.05 | 0.033 | 86.3 | -
Cauayan United Entterprises and Construction Builders | 8816 | L | B | MA | GE1 | Prev. Maint. along Daang Maharlika (LZ) K0370+840-K0373+178 (GAA), K0370+840-K0372+933.77 (POW), Tagaran | Cauayan City, Isabela | 2013-03-19 | 1st | II | LF | 25.373 | 139 | 2013-01-25 | 2013-06-12 | 2.94 | O | 0.3 | 0.3 | 0.15 | 0.023 | 0.05 | 0.033 | 85.6 | -
Cauayan United Entterprises and Construction Builders | 8816 | L | B | MA | GE1 | Asphalt Overlay along Daang Maharlika w/ Corrections (Reblocking), K0395+659-K0396+1050.70, Baligatan | Ilagan, Isabela | 2013-03-14 | 1st | II | LF | 22.18 | 65 | 2013-01-28 | 2013-04-02 | 3.31 | O | 0.371 | 0.2 | 0.15 | 0.03 | 0.05 | 0.033 | 83.4 | -
Cavacon Corporation (Formerly: Cagayan Valley Const. Corp.) | 2622 | L | AAA | LB | GE1 | Road Upgrading (Gravel to Paved), Baler-Casiguran Road (Dinadiawan-Casiguran Sect.) K0295+438-K0296+244 & K0296+244-K0296+603 | Aurora | 2012-11-28 | 1st | III | LF | 33.767 | 210 | 2012-03-23 | 2012-10-18 | -0.12 | O | 0.334 | 0.3 | 0.149 | 0.03 | 0.056 | 0.05 | 91.9 | -
Cavacon Corporation (Formerly: Cagayan Valley Construction Corporation) | 2622 | L | AAA | MB | GE | Construction of Flood Control Projects, Cavite 5th LD, Brgy. Mabuhay; Cabilang Baybay; Brgy. Milagrosa; Brgy. 8 Carmona; Maderan; and Brgy. Poblacion, G.M.A. with drainage outfall connecting to national road | Carmona & G.M.A., Cavite | 2014-11-05 | 1st | IV | LF | 9.0157 | 175 | 2014-02-08 | 2014-08-01 | -3% | O | 0.35 | 0.3 | 0.12 | 0.03 | 0.054 | 0.05 | 90.4% | 90.40% Very Satisfactory
Cavacon Corporation (Formerly: Cagayan Valley Construction Corporation) | 2622 | L | AAA | LB | GE | Network Development Off-Carriagewat Improvement (Paving of Shoulders) National Arterial Naguillian-San Mariano Road K0386+546 to K0391+000 (with exception), K0396+000 to K0397+460 (with exception) | Naguilian & Benito Doliven, Isabela | 2014-08-09 | 1st | II | LF | 31.6764 | 179 | 2014-05-20 | 2014-11-14 | 32.63 | O | 0.364 | 0.234 | 0.15 | 0.03 | 0.05 | 0.05 | 87.8 | -
CAVACON CORPORATION (Formerly: Cagayan Valley Construction Corporation) | 2622 | L | AAA | LB | GE | National Road Network Service: Network Development - Widening of National Roads - Arterial Roads along National Road 1 (N1)/Daang Maharlika/Asian Highway-26, K0398+691 to K0400+012, K0401+853 to K0405+881.43 (w/ Exception), K0407+000 to K0408+797 (w/ Exception), Ilagan, Isabela | Ilagan, Isabela | 2015-08-27 | 1st | Regional Office No. II | LF | 141.915 | 300 | 2015-03-30 | 2016-01-24 | 1.11% | O | 0.379 | 0.239 | 0.15 | 0.03 | 0.055 | 0.05 | 90.3% | -
CAVACON CORPORATION (Formerly: Cagayan Valley Construction Corporation) | 2622 | L | AAA | LB | GE | MFO-1 National Road Network Services: Network Development-Widening of National Roads-Arterial Roads along National Road 1 (N1)/Daang Maharlika/Asian Highway-26 Daang Maharlika (LZ), K0398+691 - K0400+012, K0400+012, K0401+853 - K0405+881.43 (with exceptio | Iligan, Isabela | 2015-11-13 | 1st | REGIONAL | LF | 156.1069 | 345 | 2015-03-30 | 2016-03-08 | (+) 3.66 | OG | 0.384 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 90.4% | 90.4% Very Satisfactory
CAVACON CORPORATION (Formerly: Valley Construction Corporation) | 2622 | L | AAA | LB | GE | Network Development-Off Carriageway Improvement (Paving of Shoulders) National Arterial Naguillian-San Mariano Rd | K0386+546 - K0391+000 (w/ exception) K0396+000 - K0397+460 (w/ exception) Naguillian and Benito Soliven, Isabela | 2015-06-05 | Final | Regional Office No. I | LF | 32.613 | 179 | 2014-05-20 | 2014-11-14 | 2.23% | C | 0.37 | 0.2 | 0.3 | - | - | - | 87% | *87.48% Satisfactory
Cavacon Corporation (Formerly:Cagayan Valley Construction Corporation) | 2622 | L | AAA | LA | GE1 | Road Upgrading (Gravel to Paved) San Luis-Ma. Aurora-Castañeda Rd. Km.252+000 to Km.251+784 to Km.252+008 | Ma. Aurora, Aurora | 2011-08-16 | 1st | III | LF | 13.468 | 120 | 2011-05-03 | 2011-08-30 | -4.15 | O | 0.299 | 0.3 | 0.108 | 0.03 | 0.055 | 0.033 | 82.5 | -
Cavdeal-Cavite Ideal International Construction and Development Corporation | 5599 | L | AAA | LB | GE1 | MMURTRIP Phase II, Const. of Metro Manila Urban Transport Integrated CP4, SLEX East & West Service Roads and Pasong Tamo Ext. |  | 2008-11-15 | 3rd | URPO |  | 629.011 | 752 |  |  |  | O | 0.36 | 0.3 | 0.1 | 0.03 | 0.042 | 0.1 | 93.2 | -
Cavdeal-Cavite Ideal International Construction and Development Corporation | 5599 |  |  |  |  | Const. of El Nido-Bataraza Rd. Contract Package 3B-3, Segment 1-8 Abo-abo - Brooke's Point - Rio Tuba Rd. Sect. |  | 2010-06-01 |  | PJHL |  | 1988.008 | 730 |  |  |  | O | 0.334 | 0.3 | 0.15 | 0.03 | 0.065 | 0.05 | 92.9 | -
Cavdeal-Cavite Ideal International Construction and Development Corporation | 5599 | L | AAA | LB | GE1 | Const. of El Nido-Bataraza Road, CP 3B-1, Segments 1-8, Abo-abo-Brooke's Point-Rio Tuba Section, (Sta. 128+026.93 to Sta. 247+923 w/ exception) |  | 2009-06-01 | 1st | PJHL |  | 1988.008 | 730 |  |  |  | O | 0.325 | 0.3 | 0.15 | 0.03 | 0.042 | 0.05 | 89.7 | -
CAVDEAL-Cavite Ideal International Construction and Development Corporation (Formerly: Cavite Ideal Int'l. & Dev. Corp.) | 5599 | L | AAA | LB | GE1 | Const./Impv't. of Ternate-Nasugbu Rd. Proj. (Km.94+112-Km.99+991) | Ternate, Cavite | 2013-03-26 | 1st | BOC | LF | 808.952 | 1609 | 2009-01-12 | 2013-07-08 | 0.004 | O | 0.384 | 0.258 | 0.15 | 0.03 | 0.07 | 0.05 | 94.2 | -
Cavite Ideal International Construction and Development Corp. (CAVDEAL) | 5599 |  | AAA |  |  | Basey Pointe | Brgy. Tingib, Basey, Samar | 2016-04-22 | 1st | NHA | LF | 290 | 495 | 2015-07-03 | 2016-11-08 | -7.83 | O | 0.3636 | 0.2812 | 0.0717 | 0.03 | 0.0607 | 0.0333 | 84.05 | -
CCM Construction | 11043 | L |  |  |  | BERRRP-Sikatuna-Sevilla via Cambuac Road | Sikatuna, and Sevilla, Bohol | 2015-01-19 | 1st | Bohol | L | 23.327 | 465 | 2014-07-01 | 2015-09-02 | 2.2 | O | 0.358 | 0.261 | 0.15 | 0.024 | 0.061 | 0.05 | 90.4 | -
CDC Construction and Supplies | 28275 | L | B | MA | GE1 | Repair/Rehab./Impv't. of Alaminos-Bolinao Rd., K0355+500-K0356+470 | Alaminos, Pangasinan | 2013-03-15 | 1st | I | LF | 9.85 | 60 | 2013-02-07 | 2013-04-07 | 23.33 | O | 0.361 | 0.291 | 0.15 | 0.015 | 0.03 | 0.05 | 89.7 | -
CDC CONSTRUCTION AND SUPPLIES | 282275 | L | B | MA | GE | Rehabilitation/Upgrading of (Cluster) a) Sagun Road | Pangapisan, Alaminos, Pangasinan | 2015-06-12 | Final | Pangasinan 1st DEO | LF | 4.574 | 75 | 2015-03-30 | 2015-06-12 | 0% | C | 0.439 | 0.133 | 0.3 | - | - | - | 87.2% | *87.2% Satisfactory
CDC CONSTRUCTION AND SUPPLIES/ALCEL CONSTRUCTION (JV) | - | - | - | - | - | Rehab./Reconst./Upgrading of Pangasinan-Zambales Road, Pangasinan-Zambales Road (Widening), K0320+765 to K0321+000, K0322+810 to K0323+770, K0329+535 to K0330+000,K0330+258 to K0332+085, Alaminos City and Sual, Province of Pangasinan | K0320+765 to K0321+000, K0322+810 to K0323+770, K0329+535 to K0330+000,K0330+258 to K0332+085, Alaminos City and Sual, Province of Pangasinan | 2015-09-01 | 1st | Pangasinan 1st DEO | LF | 46.467 | 240 | 2015-05-12 | 2016-01-07 | (+)20.58 | O | 0.3 | 0.3 | 0.15 | 0.023 | 0.047 | 0.05 | 87% | -
CDH BUILDERS INC (Formerly CDH Builders and Fabrication, Services) | 37082 | L | C | SB | GE | Concreting of Roads, Barangay Macasandig, Cagayan de Oro City | Barangay Macasandig, Cagayan de Oro City | 2015-08-26 | 2nd | Cagayan de Oro City 2nd DEO | LF | 5.922 | 120 | 2015-03-30 | 2015-07-28 | 0.83% | C | 0.452 | 0.136 | 0.3 | - | - | - | 88.8% | -
CDH BUILDERS, INC. (Formerly: CDH Builders and Fabrication Services) | 37082 | L | C | SB | GE | Concreting of Road, Barangay Macasandig, Cagayan de Oro City | Barangay Macasandig, Cagayan de Oro City | 2015-06-12 | 1st | Cagayan de Oro City Second DEO | LF | 5.922 | 90 | 2015-03-30 | 2015-06-27 | - | C | 0.368 | 0.3 | 0.15 | 0.03 | 0.047 | 0.05 | 94.5% | -
CDU Construction | 13915 | L | B | MA | GE1 | Replacement of Lipata Bridge I along Pob.-Brgy. Cabacungan Road | Allen, Northern Samar | 2012-03-20 | 1st | VIII | LF | 8.809 | 120 | 2012-02-06 | 2012-06-04 | 2.48 | O | 0.4 | 0.24 | 0.15 | 0.015 | 0.035 | 0.033 | 87.3 | -
CDU Construction | 13915 | L | B | MA | GE1 | Upgrading of Pob.-Brgy. Cabacungan Road, Km. 699+630-Km.699+1103 | Allen, Northern Samar | 2012-03-20 | 1st | VIII | LF | 9.137 | 90 | 2012-02-06 | 2012-05-05 | 2.85 | O | 0.353 | 0.246 | 0.15 | 0.03 | 0.03 | 0.05 | 85.9 | -
CDU Construction | 13915 | L | B | MA | GE1 | Repair/Restoration of Damaged Dale Rive Control, Catarman (Bdry.)-Rawis Road, San Roque-Pambujan Sect., Km.773+856-Km.773+930, Brgy. Dale | San Roque, Northern Samar | 2012-03-23 | 1st | VIII | LF | 14.219 | 90 | 2012-02-01 | 2012-04-30 | 8.83 | O | 0.333 | 0.225 | 0.15 | 0.03 | 0.055 | 0.033 | 82.6 | -
CDU Construction | 13915 | L | B | MA | GE | Repair and Maintenance of Iba Bridge along Basey-Marabut-Pinamitinan Road Section | Basey, Samar | 2014-10-25 | 1st | VIII | LF | 4.5057 | 150 | 2014-04-21 | 2014-09-17 | -12.41% | O | 0.399 | 0.24 | 0.026 | 0.03 | 0.041 | 0.033 | 76.9% | 76.90% Unsatisfactory
CE Padilla | 11278 | L | AAA |  |  | Design and Renovation of Existing Cancer Center Facility | BGHMC, Baguio City | 2015-09-16 | 1st | DOH | LF | 64.586 | 180 | 2014-02-10 | 2015-12-12 | 0.76 | O | 0.29 | 0.3 | 0.15 | 0.02 | 0.04 | 0.03 | 83 | -
CE Padilla | 11278 |  |  |  |  | Design and Renovation of Existing Cancer Center | BGHMC, Baguio City | 2016-06-16 | Final | DOH | LF | 64.586 | 180 | 2014-02-10 | 2014-08-09 | 0 | C | 0.497 | 0.2 | 0.3 | - | - | - | 99.7 | 88.01% Satisfactory
CE Padilla Construction Incorporated |  |  | AAA |  |  | Design & Construction of College of UP Prof. Schools Library Building | SRP, Cebu City | 2016-08-06 | 1st | UP | LF | 72.699 | 350 | 2014-11-06 | 2015-07-06 | 0 | O | 0.393 | 0.26 | 0 | 0.03 | 0.057 | 0.05 | 79 | -
CE Padilla Construction Incorporated |  |  | AAA |  |  | Design & Construction of College of UP Prof. Schools Library Building | SRP, Cebu City | 2016-07-29 | 1st | UP | LF | 72.699 | 350 | 2014-11-06 | 2015-07-06 | 0 | C | 0.495 | 0.2 | 0.3 | - | - | - | 99.5 | 84.30% Satisfactory
Cebu 7H Technochem Industries, Inc. | 31578 | L | B | MA | GE1 | Impv't./Conc. of Jct. Osmeña-Pilar Rd. (Mabini-Datu Sect.) | Pilar, Surigao del Norte | 2012-08-13 | 1st | XIII | LF | 36.91 | 285 | 2012-02-28 | 2012-12-08 | -11.08 | O | 0.366 | 0.3 | 0.039 | 0.03 | 0.05 | 0.033 | 81.8 | -
Cebu 7H Technochem Industries, Inc. | 31578 | L | B | MA | GE1 | Impv't./Conc. Of Jct. Cancohoy-Pilar Rd., Jamoyaon-Sto. Niño-Macapagal Rd. Sect. | Surigao del Norte | 2012-08-13 | 1st | XIII | LF | 43.203 | 285 | 2012-02-28 | 2012-11-23 | -27.5 | O | 0.359 | 0.3 | 0 | 0.03 | 0.055 | 0.017 | 76.1 | -
Cebu 7H Technochem Industries Inc. / Uy Construction and Development (JV) | JV-12-136 | L | A | MB | GE1 | Impv't. of Tagbilaran North Rd. (Tagbilaran-Cortes-Tubigon, w/ Int. Sect.) Sec. 1:K0008+904-K0009+795; Sec. 2:K0038+818-K0041+012; Sec. 3:K0047+108-K0047+551; Sec. 4:K0051+470-K0052+942 | Bohol Province | 2013-08-15 | 1st | VII | LF | 70.221 | 270 | 2013-02-07 | 2013-11-03 | 0.72 | O | 0.364 | 0.292 | 0.15 | 0.03 | 0.04 | 0.033 | 90.9 | -
Cebu 7H Technochem Industries, Inc. | 31578 | L | A | MA | GE | Asphalt Overlay of Tabilaran East Road(TER) | Ubay, Bohol | 2014-08-11 | 1st | VII | LF | 19.7677 | 101 | 2014-05-14 | 2014-08-22 | -4.72 | O | 0.34 | 0.24 | 0.15 | 0.022 | 0.051 | 0.05 | 85.3 | -
Cebu 7H Technochem Industries, Inc. | 31578 | L | B | MA | GE1 | Asphalt Overlay of Tagbilaran East Rd., K0149+000-K0149+990, San Pascual | Ubay, Bohol | 2013-03-13 | 1st | VII | LF | 11.528 | 46 | 2013-01-30 | 2013-03-16 | 4.98 | O | 0.374 | 0.3 | 0.15 | 0.03 | 0.014 | 0.017 | 88.5 | -
CEBU 7TH TECHNOCHEM INDUSTRIES INC. | 31578 | L | A | MB | GE | Asphalting/Widening of Shoulders, Tagbiliran City-Corella-Sikatuna-Loboc Road, Tagbiliran City, Bohol | Tagbiliran City, Bohol | 2015-06-09 | Final | Bohol First DEO | LF | 3.539 | 60 | 2015-02-18 | 2015-04-18 | 0% | C | 0.475 | 0.133 | 0.3 | - | - | - | 90.8% | *90.8% Very Satisfactory
CEBU 7TH TECHNOCHEM INDUSTRIES, INC. | 31578 | L | A | MB | GE | Road Upgrading (Gravel to Concrete) of Jct. Del Carmen - Sta. Monica - San Isidro Road (Burgos-San Isidro Section), K60+680 - K065+560 | Siargao Island, Surogap Del Norte | 2015-06-09 | 1st | Regional Office No. XIII | LF | 108.273 | 420 | 2014-05-15 | 2015-07-08 | (+) 3.09% | O | 0.395 | 0.24 | 0.15 | 0.03 | 0.045 | 0.05 | 91% | -
Cedan Construction | 10172 | L | B | MA | GB1 | Const. of MPB, Bangcol | Sta. Cruz, Zambales | 2012-08-16 | 1st | III | LF | 1.42 | 83 | 2012-05-27 | 2012-08-17 | 0.67 | O | 0.374 | 0.284 | 0.15 | 0.03 | 0.023 | 0.033 | 89.4 | -
CEDAR CONSTRUCTION | 24865 | L | C | SB | GE | Construction/Rehabilitation of Drainage along GSO Road, Km. 79+144 to Km. 79+340, Sta. Ana, Pampanga | Sta. Ana, Pampanga | 2015-06-01 | Final | Pampanga 1st DEO | LF | 2.183 | 60 | 2014-12-23 | 2015-02-20 | 0% | C | 0.362 | 0.16 | 0.3 | - | - | - | 82.2% | *82.2% Satisfactory
Celedio Construction Builders & Supply | 33923 | L | D | SB | GE2 | Cayacay Small River Impounding Project | Mabini, Bohol Region VII | 2013-07-13 | 1st | NIA | L | 3.389 | 120 | 2012-09-27 | 2013-05-09 | -10.02 | O | 0.33 | 0.3 | 0 | 0.02 | 0.06 | 0.03 | 74 | -
Celso C. Ferrer Contractor | 10643 | L | A | MB | GE1 | Conc. of Bambang-Kasibu-Quezon-Solano Road (San Fernando Sect.) |  | 2008-11-27 | 1st | II |  | 47.758 | 120 |  |  |  | O | 0.366 | 0.24 | 0.1 | 0.03 | 0.033 | 0.067 | 83.6 | -
Celso C. Ferrer-Contractor/ MIVICO Builders and Developers-JV | SL2-SN-001648 |  |  |  |  | Package X-J: Construction of lateral "N" (Sta. 11+880-Sta. 13+440), sub-lat. "N-9" (Sta. 0+000-Sta. 1+020) and "N-9a" (Sta. 0+000-Sta. 0+920) including related structures and supply, delivery and installation of steel gates | Guimba, Nueva Ecija | 2015-02-07 | 1st | NIA | L | 23.569 | 180 | 2014-07-29 | 2015-03-31 | 23.73 | O | 0.3856 | 0.2332 | 0.15 | 0.015 | 0.0047 | 0.05 | 83.85 | -
CENTIARE CONSTRUCTION AND TRADING CORP. | 33309 | L | D | MA | GE | Rehanilitaion/Improvement of Dario Creek, Brgy. Sauyo, Quezon City | Brgy. Sauyo, Quezon City | 2015-12-08 | 1st | QC 1st DEO | LF | 8.9853 | 270 | 2015-06-29 | 2016-03-24 | (+)18.7% | OG | 0.28 | 0.3 | 0.15 | 0.03 | 0.03 | 0.05 | 84% | 84% Satisfactory
Central Mindanao Const. Multi-Purpose Cooperative | 23697 | L | D | SB | GB1 | Const. of MPB @ Pilot Provincial Science and Technology H/S |  | 2008-11-07 | 1st | XII |  | 1.907 | 65 |  |  |  | O | 0.211 | 0.3 | 0.1 | 0.03 | 0.016 | 0.067 | 72.4 | -
Central Mindanao Construction Multi-Purpose Cooperative | 23697 | L | B | SB | GB1 | Const. of Two (2) Storey, Four (4) Cl Sch. Bldg., at Antipas NHS | Antipas, Cotabato | 2013-08-09 | 1st | XII | LF | 4.958 | 120 | 2013-06-07 | 2013-10-05 | 0.25 | O | 0.351 | 0.24 | 0.15 | 0.01 | 0.052 | 0.05 | 85.3 | -
Central Mindanao Construction Multi-Purpose Cooperative | 23697 | L | B | SB | GE1 | Road Upgrading (Gravel to Concrete) Nat'l Secondary Rd. Km.1642+765-Km.1642+792, Km.1643+586-Km.1643+793 and Km.1644+772.50-Km.1645+131 (clustered) along Matalam-Lampayan-Antipas Rd. | Matalam, Cotabato | 2011-08-17 | 1st | XII | LF | 11.578 | 100 | 2011-04-25 | 2011-08-02 | -46.77 | O | 0.359 | 0.239 | 0 | 0.03 | 0.045 | 0.017 | 69 | -
Central Mindanao Construction Multi-Purpose Cooperative | 23697 | L | D | SB | GE1 | Conc. of Paco-Roxas-Arakan Road, Pontevedra Section Km. 1656+100-Km. 1656+750 |  | 2009-09-05 | 1st | XII |  | 9.337 | 150 |  |  |  | O | 0.376 | 0.3 | 0.15 | 0.015 | 0.047 | 0.05 | 93.8 | -
Central Mindanao Construction Multi-Purpose Cooperative | 23697 | L | D | SB | GE1 | Conc. of Paco-Roxas-Arakan Road, CFCST Section (KM. 1667+200-Km. 1667+963.65 |  | 2009-09-05 | 1st | XII |  | 9.251 | 120 |  |  |  | O | 0.362 | 0.3 | 0.15 | 0.015 | 0.047 | 0.05 | 92.4 | -
Cesar T. Carpio Construction | 20833 | L | B | SB | GE1 | Const./Rehab./Impvt. of Pambujan Circ. Road , Cababtoan-Cabarian-Canjumadal Road |  | 2008-08-31 | 2nd | VIII |  | 9.295 | 180 |  |  |  | O | 0.288 | 0.225 | 0.1 | 0.03 | 0.04 | 0.1 | 78.3 | -
Cesar T. Carpio Construction | 20833 | L | B | SB | GE1 | Repair/Rehab. of Catarman-Calbayog Road |  | 2008-08-26 | 1st | VIII |  | 9.594 | 150 |  |  |  | O | 0.364 | 0.24 | 0.1 | 0.03 | 0.032 | 0.1 | 86.6 | -
CGGA Builders & Enterprises | 23762 |  |  |  |  | Const. of FMR |  | 2010-09-02 |  | VIII |  | 0.908 | 40 |  |  |  | O | 0.46 | 0.133 | 0.3 | - | - | - | 89.3 | 89.30% Very Satisfactory
CGGFR CONSTRUCTION & CONSTRUCTION SUPPLY | 37075 | L | D | SB | GE | Construction of Brgy. Road at Brgy. Calumangan, Sta. 0+000 - Sta. 0+130 | Bago City, Negros Occidental | 2015-08-26 | 1st & Final | Negros Occidental 4th | LF | 1.96 | 37 | 2015-05-18 | 2015-06-23 | 0% | C | 0.437 | 0.133 | 0.3 | - | - | - | 87% | *87% Satisfactory
CGGFR CONSTRUCTION & CONSTRUCTION SUPPLY | 37075 | L | D | SB | GB | Construction/Completion of Mutli-Purpose Building | Brgy. Pahanocoy, Bacolod City | 2015-08-28 | 1st & Final | Bacolod City | LF | 2.425 | 120 | 2015-03-09 | 2015-07-06 | 0% | C | 0.47 | 0.133 | 0.3 | - | - | - | 90.3% | *90.3% Very Satisfactory
CGGFR CONSTRUCTION & CONSTRUCTION SUPPLY | 37075 | L | D | SB | GB | Construction of One (1) Storey Two (2) Classroom with Attached Toilet at Don I. Nessia Sr. Elementary School, Bacolod City | Bacolod City | 2015-11-17 | 1st | Bacolod City DEO | LF | 1.8946 | 60 | 2015-10-15 | 2015-12-13 | (+)13.2% | OG | 0.369 | 0.2 | 0.15 | 0.03 | 0.052 | 0.05 | 85.1% | 85.1% Satisfactory
CGR Camille Builder, Inc. (Formerly: CGR Camille Builder) | 32259 | L | D | SB | GE | Construction of Local Road at Pasonanca-Layuhan Road | Zamboanga City | 2014-10-21 | 1st | IX | LF | 4.668 | 90 | 2014-05-15 | 2014-08-12 | -6.69% | O | 0.379 | 0.239 | 0.083 | 0.03 | 0.025 | 0.017 | 77.3% | 77.30% Unsatisfactory
CHA Construction and Supply | 28420 | L | A | MA | GE | Tourist Information Center and Tourist Rest Area (Green Restroom) | Miagao, Iloilo | 2016-04-07 | 1st | TIEZA | LF | 4 | 120 | 2015-11-22 | 2016-06-14 |  | O | 0.302 | 0.225 | 0.15 | 0.03 | 0.053 | 0.025 | 78.5
CHA Construction and Supply | 28420 | L | A | MA | GE | Tourist Information Center and Tourist Rest Area (Green Restroom) | Moalboal, Cebu | 2016-04-14 | 1st | TIEZA | LF | 4 | 120 | 2016-01-11 | 2016-05-09 | -25.58 | O | 0.39 | 0.3 | 0 | 0.03 | 0.053 | 0.025 | 79.7
CHA Construction and Supply | 28420 | L | A | MA | GE | Tourist Information Center and Tourist Rest Area (Green Restroom) | Argao, Cebu | 2016-04-14 | 1st | TIEZA | LF | 4 | 120 | 2016-01-11 | 2016-07-05 | -26.23 | O | 0.394 | 0.3 | 0 | 0.03 | 0.07 | 0.025 | 81.9
Chariot's Construction & Trading | 27627 | L | D | SB | GE1 | Repair/Rehab./Impvt. of Northwest Diversion Rd., Km. 63+537.50-Km. 69+807.50 w/ exceptions | San Fernando City, Pampanga | 2012-11-19 | 1st | III | LF | 5 | 118 | 2012-08-03 | 2012-11-28 | 2.52 | O | 0.268 | 0.3 | 0.15 | 0.03 | 0.047 | 0.05 | 84.5 | -
Charlz Construction | 8709 | L | AA | MB | GE | Widening of National Roads,Improvement/Widening of Daang Maharlika (Surigao - Agusan Section), Brgy. Luna, Surigao City | Surigao City | 2014-10-26 | 1st | XIII | LF | 41.6842 | 179 | 2014-05-29 | 2014-11-23 | 4.12% | O | 0.335 | 0.24 | 0.15 | 0.02 | 0.051 | 0.05 | 84.6% | 84.60% Satisfactory
Charlz Construction | 8709 | L | AA | MB | GE1 | Rd. Upgrading (Gravel to Paved) of Jct. S.H.-Manolo Fortich-Libona-Indahag Rd. (Gango Sect.) (K1492+845-K1494+000) Pob. Libona | Bukidnon | 2013-03-21 | 1st | X | LF | 25.514 | 106 | 2013-01-23 | 2013-05-08 | -11.46 | O | 0.31 | 0.251 | 0.035 | 0.03 | 0.04 | 0.05 | 71.6 | -
Charlz Construction | 8709 | L | AA | MB | GE1 | Rehab./Impvt. of Butuan City-Misamis Oriental Road (Selective Conc. Paving along Balingasag-Binuangan Sect.) |  | 2008-08-24 | 3rd | X |  | 38.527 | 379 |  |  |  | O | 0.316 | 0.3 | 0.1 | 0.015 | 0.041 | 0.1 | 87.2 | -
Charlz Construction | 8709 | L | AA | MB | GB1 | Const. of DPWH Bukidnon 3rd DEO Building (Phase III), Diklum |  | 2009-05-29 | 1st | X |  | 4.795 | 90 |  |  |  | O | 0.35 | 0.263 | 0.15 | 0.03 | 0.011 | 0.033 | 83.7 | -
Charlz Construction | 8709 | L | AA | MB | GE1 | Rehab./Reconst. (Asphalt to Concrete) of Jct. S.H. Manolo Fortich Libona-Indahag Rd., (Kiliog Section) |  | 2009-09-04 | 2nd | X |  | 19.21 | 150 |  |  |  | O | 0.394 | 0.236 | 0.15 | 0.03 | 0.047 | 0.033 | 89 | -
Charlz Construction | 8709 | L | AA | MB | GE1 | Cala-anan Resettlement Site Dev't., Const. of Rds. (Conc.) & Drainages, Phase III, Brgy. Canitoan | Cagayan de Oro City | 2012-08-23 | 1st | X | LF | 55.782 | 150 | 2012-05-30 | 2012-10-26 | 30.62 | O | 0.309 | 0.3 | 0.15 | 0.03 | 0.035 | 0.05 | 87.4 | -
CHARLZ CONSTRUCTION | 8709 | L | AA | MA | GE | Construction/ Upgrading/ Rehabilitation of Drainage along Daang Maharlika (Surigao-Agusan Section); Km.1126+555 to Km.1128+000, Rehab./Construction of RCBC 1 | Surigao City | 2015-06-10 | 1st | SURIGAO DEL NORTE FIRST DEO | LF | 9.095 | 211 | 2015-04-17 | 2015-11-13 | (+) 5.44% | O | 0.392 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 91.2% | -
Chedmaryl Construction & Supplies | 27073 | L | B | SB | GB1 | Const. of Lambunao NHS, Two (2) Storey 6 Classrooms Bldg. | Lambunao, Iloilo | 2013-08-20 | 1st | VI | LF | 6.432 | 90 | 2013-06-24 | 2013-09-21 | 6.11 | O | 0.37 | 0.226 | 0.15 | 0.03 | 0.048 | 0.033 | 85.7 | -
Chiara Construction | 8736 | L | AA | LA | GE1 | Const. of Two (2) Storey Building / Library at Tarlac State University, Lucinda Campus |  | 2008-11-13 | 1st | III |  | 14.416 | 270 |  |  |  | O | 0.388 | 0.18 | 0.1 | 0.03 | 0.022 | 0.1 | 82 | -
CHIARA CONSTRUCTION | 8736 | L | AA | LA | GE | Construction/Maintenance of Flood Control Mitigation Structures & Drainage Systems Flood Control along Angat River Parulan, Plaridel, Bulacan | Plaridel, Bulacan | 2015-11-20 | Final | Bulacan First DEO | LF | 11.025 | 230 | 2015-03-14 | 2015-10-29 | - | C | 0.5 | 0.133 | 0.3 | - | - | - | 93.3% | 93.3% Very Satisfactory
China CAMC Engineeing Co., LTD. |  | F | AAA |  | GE2 | Const. of Agno River Integrated Irrigation Project (ARIIP) | San Manuel, Pangasinan | 08/15-20/11 | 1st | NIA | FA | 93.846 | 900 | 2010-03-01 | 2012-07-19 | 2.13 | O | 0.3702 | 0.2895 | 0.15 | 0.03 | 0.07 | 0.05 | 95.97 | -
China Harbour Engineering Company | SL1-SN-005059/FC-07-005 | F | AAA | LB | GE1 | CP5, Cervantes-Mankayan-Abatan, Phase V |  | 2009-03-11 | 2nd | PJHL |  | 682.076 | 812 |  |  |  | O | 0.365 | 0.3 | 0.15 | 0.03 | 0.07 | 0.05 | #VALUE! | -
China Harbour Engineering Company | FC-98-264 | F | AAA | LB | GE1 | CP5, Cervantes-Mankayan-Abatan, Phase V |  | 2008-11-14 | 1st | PJHL |  | 682 | 812 |  |  |  | O | 0.369 | 0.3 | 0.1 | 0.03 | 0.051 | 0.1 | 95 | -
China Harbour Engineering Company | FC-07-005 | F | AAA | LB | GE1 | Contract Package 5, Cervantes-Mankayan-Abatan under Arterial Road Links Development Project, Phase V, Sta.383+135 to Sta. 414+679.38 |  | 2009-08-27 | 1st | PJHL |  | 682.076 | 812 |  |  |  | O | 0.373 | 0.24 | 0.15 | 0.03 | 0.056 | 0.033 | 88.2 | -
China Henan Shuili Yiju | FC-10-003 | F | AAA | LB | GE1 | Landslide Risk Mitigation: Digos-Gen. Santos City Rd. & Davao-Calinan-Buda Rd., Mindanao Nat'l Rds. Impv't & Mgt. Program Phase II (NRIMP) | Region XI and XII | 2013-08-10 | 2nd | NRIM-PMO | FA | 535.161 | 731 | 2011-08-16 | 2013-08-15 | -7.3 | O | 0.39 | 0.3 | 0.077 | 0.03 | 0.047 | 0.05 | 89.4 | -
China Henan Shuili Yiju | FC-10-003 | F | AAA | LB | GE1 | Landslide Risk Mitigation, Digos-Gen. Santos City Rd. & Davao-Calinan-Buda Rd. Sarangani and Davao City | Davao del Sur | 2013-03-16 | 1st | NRIM-PMO | FA | 535.16 | 730 | 2011-08-16 | 2013-08-15 | -5.63 | O | 0.389 | 0.3 | 0.094 | 0.03 | 0.05 | 0.017 | 88 | -
China International Water & Electric Corporation | FC-10-001 | F | AAA | LB | GE1 | Impv't. of Digos-Cotabato Rd., Contract Package (CP)-RI 2.7 C: Pagalungan-Jct. Cotabato Sect., Mindanao Region, under the Nat'l Rds. Impv't. & Mgt. Program, Phase II (NRIMP-II) | Mindanao | 2013-03-17 | 2nd | NRIM II - PMO | FA | 977.493 | 823 | 2011-08-17 | 2013-11-16 | 10.14 | O | 0.318 | 0.3 | 0.15 | 0.03 | 0.06 | 0.05 | 90.8 | -
China International Water & Electric Corporation | FC-10-001 | F | AAA | LB | GE1 | Impvt. of Digos-Cotabato Rd., Contract Package (CP)-RI 2.7 C: Pagalungan-Jct. Cotabato Sect., Mindanao Region, under NRIMP II | Mindanao | 2012-08-14 | 1st | NRIM-PMO | FA | 977.493 | 823 | 2011-08-17 | 2013-11-16 | 21.709 | O | 0.386 | 0.3 | 0.15 | 0.03 | 0.051 | 0.05 | 96.7 | -
China Road & Bridge Corporation | SL-2-SN-000631 | F | AAA | LB | GE1 | Contract Package III, Calbayog-Gatanguit Road Sect., Arterial road links Dev't. Project, Phase VI |  | 2008-12-02 | 4th | PJHL |  | 1397.424 | 1020 |  |  |  | O | 0.36 | 0.3 | 0.1 | 0.03 | 0.07 | 0.1 | 96 | -
China State (Phils.) Construction Eng'g. Corp. | SL1-SN-004865 | F | AAA | LB | GE1 | CP No. C-5, Metro Manila Urban Transport Integration Project (MMURTRIP), NLEX Junction to North Fairview |  | 2008-11-24 | 3rd | URPO |  | 606.345 | 720 |  |  |  | O | 0.34 | 0.3 | 0.05 | 0.03 | 0.056 | 0.067 | 84.3 | -
CHL CONSTRUCTION AND DEVELOPMENT ENTERPRISES INC. | 13001 | L | A | MA | GE | Const./Upgrading/Rehabilitation of Drainage along, National Roads, Makar-Marbel Road, K1668+732 to K1669+732 with Exception | Polomolok, South Cotabato | 2015-11-18 | 1st | South Cotabato Second DEO | LF | 28.7561 | 235 | 2015-04-30 | 2015-10-21 | (+) 12.37% | OG | 0.383 | 0.225 | 0.15 | 0 | 0.023 | 0.05 | 83.1% | 83.1% Satisfactory
CHL CONSTRUCTION AND DEVELOPMENT ENTERPRISES, INC. | 15001 | L | A | MA | GE | Widening of National Roads Outside N1-Jct. Digos- Buayan Airport Road K1649+1650 with exceptions (.21650 km) | Brgy. Baluan, General Santos City | 2015-06-12 | 1st | South Cotabato 2nd DEO | LF | 22.943 | 120 | 2015-04-20 | 2015-08-17 | 44.32% | O | 0.373 | 0.24 | 0.15 | 0.03 | 0.032 | 0.05 | 87.5% | -
CHL CONSTRUCTION AND DEVELOPMENT ENTERPRISES., INC | 15001 | L | A | MA | GE | Construction/Upgrading/Rehabilitation of Drainage along National Roads | Marbel-Makar Road, K1668+732-K1669+732 with Exception (0.109 Km) Polomolok, South Cotabato | 2015-09-04 | 1st | South Cotabato II | LF | 26.93 | 175 | 2015-04-30 | 2015-10-21 | (+)0.29% | O | 0.371 | 0.231 | 0.15 | 0.03 | 0.047 | 0.05 | 87.9% | -
Cholo Construction and Trading | 32138 | L | B | SB | GE2 | Drainage/Slope Protection along San Miguel-Concepcion Rd. | San Simon, Pampanga | 2012-11-19 | 1st | III | LF | 4.725 | 90 | 2012-10-23 | 2013-01-20 | -9.16 | O | 0.32 | 0.24 | 0.058 | 0.03 | 0.029 | 0.033 | 71 | -
CHRISHELLE CONSTRUCTION | 17108 | L | B | MA | GE | Widening of Puerto Princesa South Road K0000+000 - K0001+410 | Puerto Princesa City | 2015-11-12 | 1st | Palawan 3rd DEO | LF | 33.5487 | 184 | 2015-06-12 | 2015-12-12 | - | OG | 0.347 | 0.24 | 0.15 | 0 | 0.04 | 0.05 | 82.7% | 82.7% Satisfactory
Chris-James Construction | 11202 | L | B | MA | GE1 | Upgrading (Gravel to Paved) of Pangpang-Palapag-Mapanas-Gamay-Lapinig Rd., K0813+464-K0815+194 | Northern Samar | 2013-08-08 | 1st | VIII | LF | 41.807 | 180 | 2013-03-27 | 2013-09-22 | -4.22 | O | 0.344 | 0.3 | 0.108 | 0.03 | 0.065 | 0.017 | 86.4 | -
Chris-James Construction | 11202 | L | B | MA | GE1 | Road Upgrading (Gravel to Paved) Conc. of Pangpang-Palapag-Mapanas-Gamay-Lapinig Rd., Km.824+000-Km.825+494.00 | Mapanas, Northern Samar | 2012-08-17 | 1st | VIII | LF | 31.28 | 237 | 2012-02-01 | 2012-09-24 | 0.1 | O | 0.277 | 0.3 | 0.15 | 0.03 | 0.033 | 0.033 | 82.3 | -
Christian Ian Construction Corporation | 8191 | L | AAA | MB | GE1 | Improvement/Rehab.of Daang Maharlika Road |  | 2009-09-05 | 1st | III |  | 41.225 | 180 |  |  |  | O | 0.342 | 0.3 | 0.15 | 0.03 | 0.05 | 0.033 | 90.5 | -
Chu Construction | 33747 | L | B | MA | GE | Replacement of Mabini Bridge 2 along Jct. Mabini - Tubajon Road (Const. of Two Barrel RCBC), Tubajon, Dinagat Islands | Tubajon, Dinagat Islands | 2014-10-27 | 1st | XIII | LF | 5.2872 | 190 | 2014-04-22 | 2014-10-28 | -18.26% | O | 0.344 | 0.3 | 0.001 | 0.02 | 0.042 | 0.033 | 74% | 74.00% Poor
Chu Construction | 33747 | L | B | MA | GE | Protection Works along Dinagat - Loreto Road, Wilson, San Jose, Dinagat Islands | San Jose, Dinagat Islands | 2014-10-27 | 1st | XIII | LF | 9.142 | 130 | 2014-04-22 | 2014-08-29 | -15.05% | O | 0.366 | 0.3 | 0 | 0.02 | 0.042 | 0.033 | 76.1% | 76.10% Unsatisfactory
Chu Construction | 33747 | L | B | MA | GE1 | Road Upgrading for Kiling-Tanauan-Tabontabon-Julita Road, K0934+128-K0935+(-)429; K0935+(094)-K0935+388; K0936+(-)071-K0937+000 | Tabontabon, Leyte | 2013-03-11 | 1st | VIII | LF | 8.566 | 126 | 2013-01-15 | 2013-05-20 | 11.88 | O | 0.392 | 0.18 | 0.15 | 0.023 | 0.05 | 0.05 | 84.5 | -
Chu Construction | 33747 | L | B | MA | GE1 | Rehab./Reconst. Along Jct.-Taft-Oras-San-San Policarpio-Arteche Rd., K0908+385-K0908+211 | Eastern Samar | 2013-08-19 | 1st | VIII | LF | 11.69 | 114 | 2013-01-30 | 2013-05-23 | -5.32 | O | 0.33 | 0.3 | 0 | 0.03 | 0.06 | 0.033 | 75.3 | -
Chu Construction / Jelm Construction (JV) | JV-12-301 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rd. along Naga-Naga Anibong Rd., Km.0906+(-858)-K0906+(-405); K0906+103-K0906+1950 & K0906+039-K0906+439 | Tacloban City | 2013-08-22 | 1st | VIII | LF | 30.164 | 258 | 2013-01-29 | 2013-10-13 | 4.9 | O | 0.356 | 0.24 | 0.15 | 0.03 | 0.06 | 0.05 | 88.6 | -
Cielito A. Bay-ag Construction | 19032 | L | B | SB | GE1 | Concreting of Aritao-Quirino Road, Lupa Section |  | 2009-06-04 | 1st | II |  | 9.606 | 120 |  |  |  | O | 0.338 | 0.24 | 0.15 | 0.03 | 0.051 | 0.033 | 84.2 | -
Ciriaco Corporation | 6932 | L | AAA | LB | GE1 | Contract Package II-A Lullutan Bridge | Ilagan, Isabela | 2013-03-14 | 2nd | FABP-PMO | FA | 712.913 | 840 | 2011-06-16 | 2013-10-02 | 5.98 | O | 0.385 | 0.24 | 0.15 | 0.03 | 0.056 | 0.05 | 91.1 | -
Ciriaco Corporation | 6932 | L | AAA | LB | GE1 | Contract Package II-A, Lullutan Bridge | Ilagan, Isabela | 2012-08-07 | 1st | PMO-PBPO | LF | 712.913 | 840 | 2011-06-16 | 2013-10-02 | 23.8 | O | 0.384 | 0.3 | 0.15 | 0.03 | 0.061 | 0.033 | 95.8 | -
Ciriaco Corporation | 6932 | L | AAA | LB | GE1 | Const. of Delfin Albano Bridge along Tumauini-Delfin Albano Road (SA #2) |  | 2009-03-05 | 3rd | II |  | 234.155 | 360 |  |  |  | O | 0.388 | 0.3 | 0.15 | 0.03 | 0.05 | 0.05 | #VALUE! | -
Ciriaco Corporation | 6932 | L | AAA | LB | GE1 | Const. of Delfin Albano Bridge along Tumauini-Delfin Albano Road (SA #1) |  | 2008-08-13 | 1st | II |  | 234.155 | 360 |  |  |  | O | 0.4 | 0.296 | 0.1 | 0.03 | 0.06 | 0.1 | 98.6 | -
Citystar Construction | 32774 | L | D | SB | GE2 | Const. of Pasugui Flood Control (Pasugui Sect. Phase 2) | Sablayan, Occidental Mindoro | 2013-07-30 | 1st | IVB | LF | 8.38 | 204 | 2013-03-21 | 2013-10-10 | -2.61 | O | 0.31 | 0.3 | 0.124 | 0.03 | 0.03 | 0.033 | 82.7 | -
Clifford Construction Corporation | 3724 | L | B | MA | GE-5 | Hamtic Port Development Project | Hamtic, Antique/Region VI | 2014-07-10 | 1st | DOTC | LF | 11.634 | 210 | 2014-04-17 | 2014-11-08 | 3.41 | O | 0.3744 | 0.3 | 0.15 | 0.03 | 0.0408 | 0.05 | 94.52 | -
Clifford Construction Corporation | 3724 | L | B | MA | GE1 | Rehab./Reconst./Replacement/Retrofitting of Existing Bridge along Nat'l Rds., Catipayan Bridge along Iloilo East Coast Capiz Bridge | Pontevedra, Capiz | 2013-08-18 | 1st | VI | LF | 5.98 | 170 | 2013-02-06 | 2013-07-26 | - | O | 0.366 | 0.24 | 0 | 0.03 | 0.042 | 0.033 | 71.1 | -
Clifford Construction Corporation | 3724 | L | A | MB | GE1 | Road Upgrading (Gravel to Concrete) Altavas-Jamindan Road |  | 2009-06-06 | 1st | VI |  | 3.849 | 150 |  |  |  | O | 0.362 | 0.246 | 0.15 | 0.023 | 0.045 | 0.033 | 85.9 | -
Clifford Construction Corporation | 3724 | L | A | MB | GE1 | Road Upgrading / Concreting along Altavas-Jamindan Road |  | 2009-03-14 | 1st | VI |  | 21.841 | 210 |  |  |  | O | 0.33 | 0.294 | 0.15 | 0.03 | 0.055 | 0.033 | #VALUE! | -
Clifford Construction Corporation | 3724 | L | A | MB | GE1 | Road Upgrading/Conc. along Altavas-Jamindan Road |  | 2009-09-05 | 3rd | VI |  | 22.278 | 349 |  |  |  | O | 0.336 | 0.287 | 0.11 | 0.023 | 0.04 | 0.017 | 81.3 | -
Clifford Construction Corporation | 3724 | L | B | MA | GE2 | Rehab. of Tambak Seawall along Jaime Cardinal Sin Ave. (Phase II) Brgy. Tambak | New Washington, Aklan | 2012-03-25 | 1st | VI | LF | 26.668 | 210 | 2011-11-24 | 2012-06-20 | 0.36 | O | 0.331 | 0.3 | 0.15 | 0.03 | 0.043 | 0.033 | 88.7 | -
Clifford Construction Corporation | 3724 | L | B | MA | GE2 | Rehab. of Tambak Seawall along Jaime Cardinal Sin Ave. (Phase 2), Brgy. Tambak | New Washington, Aklan | 2012-08-17 | 2nd | VI | LF | 26.662 | 300 | 2011-11-24 | 2012-09-18 | 0.4 | O | 0.334 | 0.254 | 0.15 | 0.03 | 0.043 | 0.033 | 84.4 | -
Clifford Construction Corporation | 3724 | L | B | MA | GE2 | Rehab. of Tambak Seawall along Jaime Cardinal Sin Ave. (Phase I), Brgy. Tambak | New Washington, Aklan | 2012-08-17 | 2nd | VI | LF | 25.631 | 270 | 2011-11-29 | 2012-08-24 | 1.8 | O | 0.358 | 0.251 | 0.15 | 0.03 | 0.043 | 0.05 | 88.2 | -
CLIFFORD CONSTRUCTION CORPORATION | 3724 | L | B | MA | GE | Rehabilitation/Major Repair of Permanent Bridges, Sibaguan Bridge (B00489PN) along Roxas City-Cagay-Sibaguan-Balijuagan-Cudian-Ivisan Road | Brgy. Sibaguan, Roxas City | 2015-09-02 | 1st & Final | Capiz 1st | LF | 9.839 | 180 | 2015-01-25 | 2015-07-23 | 1.67% | C | 0.432 | 0.133 | 0.3 | - | - | - | 86.5% | *86.5% Satisfactory
CLIFFORD CONSTRUCTION CORPORATION | 3724 | L | B | MA | GE | Rehabilitation/Major Repair of Permanent Bridges, Dinginan Bridge along Roxas City-Cagay-Sibaguan-Balijuagan-Cudian-Ivisan Rd., Brgy. Dinginan, Roxas City, Capiz | Brgy. Dinginan, Roxas City, Capiz | 2015-11-12 | Final | Capiz 1st | LF | 12.2476 | 180 | 2015-01-25 | 2015-07-24 | 0.00% | C | 0.387 | 0.2 | 0.3 | - | - | - | 88.7% | 88.7% Satisfactory
Clifford Construction Corporation | 3724 | L | B | MA | GB1 | Roxas PCG Station Building Development Project | Roxas City | 2013-08-13 | 1st | DOTC | L | 10.762 | 240 | 2013-04-02 | 2013-11-28 | 0.5 | O | 0.3242 | 0.3 | 0.15 | 0.03 | 0.0233 | 0.05 | 87.75 | -
CLTG Builders | 16852 | L | B | MA | GE1 | Const. of Calinan-Toril Rd., incl. ROW, Tagakpan Sect., Km.1695+247.93-Km.1698+750 | Davao City | 2013-08-06 | 1st | XI | LF | 46.053 | 209 | 2013-03-27 | 2013-10-21 | -4.8 | O | 0.316 | 0.3 | 0.102 | 0.03 | 0.036 | 0.033 | 81.7 | -
CLTG Builders | 16852 | L | B | MA | GE1 | Rd. to Address Critical Bottlenecks Widening of Daang Maharlika (Agusan-Davao Rd.) Davao City Sect. | Davao City | 2012-08-20 | 1st | XI | LF | 19.429 | 165 | 2012-01-24 | 2012-07-06 | -1.01 | O | 0.335 | 0.231 | 0.14 | 0.03 | 0.055 | 0.033 | 82.4 | -
CLTG BUILDERS | 16852 | L | B | MA | GE | Construction of Concrete Revetment on Steel Sheet Piles along Talomo River, Riverside Section, Calinan District, Davao City | Calinan District, Davao City | 2015-11-18 | Final | Davao City 2nd DEO | LF | 1.8716e-05 | 160 | 2015-02-10 | 2015-07-19 | 0.0247 | C | 0.472 | 0.155 | 0.3 | - | - | - | 92.7% | 92.7% Very Satisfactory
CLTG Builders / Square Cube Construction (JV) | JV-11-293 | L | B | MA | GE1 | Widening of Tagum-Panabo Circ. Rd., Pob. Kapalong Sect. | Davao del Norte | 2012-08-12 | 1st | XI | LF | 38.317 | 263 | 2012-01-31 | 2012-10-20 | 0.68 | O | 0.361 | 0.225 | 0.15 | 0.03 | 0.055 | 0.033 | 85.4 | -
CM Tan Construction (Formerly: CM Tan Construction Supplies) | 28087 | L | B | MA | GE | Construction/Improvement of Road along NRJ-Bayugan-Calaitan-Tandag Road, K1295+260 - K1296+615 | Bayugan, Agusan del Sur | 2014-10-22 | 1st | XIII | LF | 42.1191 | 276 | 2014-02-11 | 2014-11-13 | 3.92% | O | 0.355 | 0.22 | 0.15 | 0.023 | 0.037 | 0.05 | 83.5% | 83.50% Satisfactory
CM Tan Construction (Formerly: CM Tan Construction Supplies) | 28087 | L | B | SB | GE2 | Const. of Protection Works along NRJ-Bayugan-Esperanza Rd. crossing Luna, (Sect. 2) 1276+566.20-1276+648.40 | Esperanza, Agusan del Sur | 2013-03-20 | 2nd | XIII | LF | 18.188 | 225 | 2012-09-20 | 2013-05-02 | 1.06 | O | 0.339 | 0.3 | 0.15 | 0.03 | 0.03 | 0.03 | 87.9 | -
CM Tan Construction (Formerly: CM Tan Construction Supplies) | 28087 | L | B | SB | GE2 | Rehab. of Crossing Luna Flood Control, NRJ-Bayugan-Esperanza Nat'l Rd. (Sect. 3) K1276+648-K1276+662.8 (Piling); K1276+400-K1276+720 (Deepening) Crossing Luna | Esperanza, Agusan del Sur | 2013-03-20 | 1st | XIII | LF | 16.726 | 225 | 2012-09-25 | 2013-05-07 | -0.29 | O | 0.4 | 0.225 | 0.147 | 0.022 | 0.032 | 0.033 | 85.9 | -
CM TAN CONTRUCTION (FORMERLY CM TAN CONSTRUCTION SUPPLIES) | 28087 | L | B | MA | GE | Road Upgrading (Unpaved to Paved) along Agusan-Malaybalay Road | K1288+531 to K1290+631, Esperanza, Agusan Del Sur | 2015-06-04 | 1st | AGUSAN DEL SUR FIRST DEO | LF | 45.704 | 179 | 2015-03-28 | 2015-09-22 | (+) 8.83% | O | 0.397 | 0.235 | 0.15 | 0.03 | 0.05 | 0.05 | 91.2% | -
CNE CONSTRUCTION | 22148 | L | B | SB | GE | Construction of Drainage along Biliran Circumferential Road to include Payment of RROW Damages, K1083+330 to K1084+005, Caibiran, Biliran Province | K1083+330 to K1084+005, Caibiran, Biliran Province | 2015-06-03 | 1st | Biliran DEO | LF | 8.834 | 169 | 2015-03-18 | 2015-09-02 | - | O | 0.377 | 0.12 | 0.15 | 0.03 | 0.005 | 0.05 | 73.2% | -
Coastland Construction and Development Corp. | 11487 | L | A | MA | GE1 | Widening of Pres. Diosdado P. Macapagal Highway (Caganganan Sect.) Km.1757+440-Km.1759+000 | Banaybanay, Davao Oriental | 2013-03-19 | 1st | XI | LF | 23.855 | 130 | 2013-01-25 | 2013-06-03 | 8.84 | O | 0.33 | 0.219 | 0.15 | 0.03 | 0.045 | 0.05 | 82.4 | -
Coastland Construction and Development Corp. | 11487 | L | A | MA | GE1 | Widening of Pres. Diosdado P. Macapagal Highway (Manikling Sect.) Km.1742+889-Km.1743+586 | San Isidro, Davao Oriental | 2013-03-19 | 1st | XI | LF | 15.461 | 99 | 2013-01-25 | 2013-05-03 | 16.36 | O | 0.334 | 0.216 | 0.15 | 0.03 | 0.055 | 0.033 | 81.8 | -
Coastland Construction and Development Corporation | 11487 | L | A | MA | GE1 | Widening of Pres. Diosdado P. Macapagal Highway (Pob.-Lupon Sect.) a)Km.1751+046.67-Km.1752+797.67; b)Km.1753+673.86-Km.1754+880 | Lupon, Davao Oriental | 2013-03-19 | 1st | XI | LF | 46.479 | 176 | 2013-01-25 | 2013-07-19 | 10.02 | O | 0.339 | 0.218 | 0.15 | 0.03 | 0.045 | 0.05 | 83.2 | -
COFEJOK Construction and Supply Corp. | 27493 | L | B | MA | GE | Tourism Information Center | Brgy. Poblacion, Tiboli, South Cotabato | 2016-04-20 | 1st | TIEZA | LF | 2 | 90 | 2016-03-09 | 2016-06-06 |  | O | 0.396 | 0.3 | 0.15 | 0.03 | 0.07 | 0.05 | 99.6
COFEJOK Construction and Supply Corp. | 27493 | L | B | MA | GE | New Israel Eco-Tourism Park | Brgy. New Israel, Makilala, North Cotabato | 2016-05-26 | 1st | TIEZA | LF | 10.5 | 150 | 2016-01-22 | 2016-06-19 | -8.70 | O | 0.35 | 0.3 | 0.063 | 0.03 | 0.07 | 0.05 | 86.3
COFEJOK CONSTRUCTION AND SUPPLY CORPORATION | 27493 | L | B | MA | GB | Local Infrastructure Program: Construction of Multi-Purpose Building, Poblacion | Norala, South Cotabato | 2015-06-02 | Final | South Cotabato DEO | LF | 4.787 | 150 | 2014-08-20 | 2015-01-16 | 0% | C | 0.46 | 0.133 | 0.3 | - | - | - | 89.3% | *89.3% Very Satisfactory
COFEJOK CONSTRUCTION AND SUPPLY CORPORATION | 27493 | L | B | MB | GE | Const. of Drainage Canal along Marbel- Ala Valley Cotabato Road | Isulan, Sultan Kudarat XII | 2015-11-10 | 1st | Sultan Kudarat First DEO | LF | 7.989 | 152 | 2015-08-26 | 2016-01-24 | (+) 2.86% | OG | 0.347 | 0.265 | 0.15 | 0.03 | 0.035 | 0.05 | 87.7% | 87.7% Satisfactory
COFEJOK Construction and Supply Corporation (Formerly: COFEJOK Construction and Supply) | 27493 | L | B | MA | GB | Local Infrastructure Program: Construction of Multi-Purpose Building | Norala, South Cotabato | 2014-10-21 | 1st | XII | LF | 4.7871 | 150 | 2014-08-20 | 2015-01-16 | 1.55% | O | 0.396 | 0.24 | 0.15 | 0.02 | 0.043 | 0.033 | 88.2% | 88.20% Satisfactory
COFEJOK Construction and Supply Corporation (Formerly: COFEJOK Construction and Supply) | 27493 | L | B |  | GE | Road Upgrading (Gravel to Concrete) along Isulan Hwy. Jct. Dukay-Bagumbayan-Sen. Aquino-Kalamansig Road (Km. 1859+000 - Km. 1859+900) | Tinalon, Sen. Ninoy Aquino, Sultan Kudarat | 2014-10-27 | 1st | XII | LF | 19.5214 | 83 | 2014-02-19 | 2014-05-12 | -1.2% | O | 0.384 | 0.237 | 0 | 0.03 | 0.045 | 0.033 | 72.9% | 72.90% Poor
COFEJOK Construction and Supply Corporation (Formerly: COFEJOK Construction and Supply) |  | L |  |  | GE | Rehabilitation/Reconstruction of Critical Sections along National Roads, Road Slip along Isulan Hwy. Jct. - Sen. Ninoy Aquino Road (K1808+523 - K1817+000 w/ exceptions) | Bagumbayan, Sultan Kudarat | 2014-10-27 | 1st | XII | LF | 34.7548 | 336 | 2014-08-08 | 2015-07-09 | 21.42% | O | 0.37 | 0.24 | 0.15 | 0.03 | 0.05 | 0.033 | 87.3% | 87.30% Satisfactory
COLBY CONSTRUCTION | 33969 | L | B | SB | GB | Local Infrastructure Program - Construction of Multi-Purpose Building, Barangay Bunhian, Municipality of Aguinaldo, Ifugao Lone District | Aguinaldo, Ifugao | 2015-11-12 | Final | Ifugao 2nd | LF | 1.8568 | 115 | 2015-02-10 | 2015-06-04 | - | C | 0.388 | 0.133 | 0.3 | - | - | - | 82.1% | 82.1% Satisfactory
Collera's Construction | 13246 | L |  | MA | GE | Widening of Daang Maharlika (SO0024LT), KO915+411 - KO916+911, KO919+754 - KO920+300.15 Salvacion - Cogon Section, Palo, Leyte & Calogcog - Solano Section | Tanauan, Leyte | 2014-08-10 | 1st | VIII | LF | 34.1199 | 210 | 2014-01-17 | 2014-08-14 | 0.16 | O | 0.362 | 0.207 | 0.15 | 0.03 | 0.045 | 0.033 | 82.7 | -
Collera's Construction | 11246 | L | B | MA | GE1 | Rehab. of Rd. Slip along Daang Maharlika, Abuyog | Mahaplag, Leyte | 2013-03-15 | 1st | VIII | LF | 7.223 | 100 | 2013-01-25 | 2013-05-04 | 0.85 | O | 0.334 | 0.24 | 0.15 | 0.03 | 0.035 | 0.033 | 82.2 | -
COLLERA'S CONSTRUCTION | 13246 | L | B | MA | GE | Road Upgrading (Unpaved to Paved) along Mainit-San Miguel-Santol Road | K0945+741-K0945+865; KO945+933-KO947+097; 50950+399-K0951+199, San Miguel, Leyte | 2015-08-24 | 1st & Final | Leyte 1st DEO | LF | 46.25 | 209 | 2015-01-30 | 2015-08-26 | - | C | 0.427 | 0.143 | 0.3 | - | - | - | 87% | *87% Satisfactory
Comfac Corporation | 26293 | L |  |  |  | Procurement of Materials and Labor for the Rehabilitation of Electrical System & Improvement of NEDA-10 | Capistrano-Echem Streets, Cagayan de Oro City | 2016-09-09 | Final | PICE-CDO | LF | 4.447 | 88 | 4/29/16 | 7/25/16 | 0 | C | 0.5 | 0.2 | 0.3 | - | - | - | 100 | 97.32% Outstanding
Comfac Corporation | 26293 | L |  |  |  | Procurement of Materials and Labor for the Rehabilitation of Electrical System & Improvement of NEDA-10 | Capistrano-Echem Streets, Cagayan de Oro City | 4/18/16 | 2nd | PICE-CDO | LF | 4.447 | 88 | 4/29/16 | 7/25/16 | 3.72 | O | 0.4 | 0.3 | 0.15 | 0.03 | 0.065 | 0.05 | 99.5 | -
Comfac Corporation | 26293 | L |  |  |  | Rehabilitation of Electrical System & Improvement of NEDA-10 | Capistrano-Echem Streets, Cagayan de Oro City | 2016-06-08 | 1st | PICE-CDO | LF | 4.447 | 88 | 4/29/16 | 7/25/16 | -5.66 | O | 0.327 | 0.291 | 0.093 | 0.02 | 0.053 | 0.033 | 81.7 | -
Compact Builders, Inc | 14492 |  |  |  |  | Const. of 1 unit 3-Storey, 15-Classroom School Building |  | 2009-12-10 |  | NHA |  | 21.491 | 210 |  |  |  | O | 0.291 | 0.3 | 0.121 | 0.03 | 0.038 | 0.05 | 83 | -
Compact Builders, Inc | 14492 |  |  |  |  | Construction of Livehood, Productivity & Training Center |  | 2010-02-09 |  | NHA |  | 4.992 | 120 |  |  |  | O | 0.334 | 0.3 | 0.15 | 0.03 | 0.059 | 0.923 | 92.3 | -
Concepcion Basic Builders, Incorporated | 5255 | L | AAA | LB | GE | Completion/Retrofitting of Tago-San Miguel Bridge along Jct. Gamut - San Miguel Road | San Miguel, Surigao del Sur | 2014-10-30 | 1st | XIII | LF | 19.4154 | 270 | 2014-03-17 | 2014-12-11 | 10.12% | O | 0.334 | 0.224 | 0.15 | 0.023 | 0.051 | 0.05 | 83.2% | 83.20% Satisfactory
Concepcion Basic Builders, Incorporated | 5255 |  |  |  |  | Const. of Bislig Bridge (Completion) along Surigao-Davao Coastal Rd. |  | 2010-03-03 |  | XIII |  | 92.432 | 340 |  |  |  | O | 0.373 | 0.235 | 0.15 | 0.03 | 0.05 | 0.033 | 87.1 | -
Concepcion Basic Builders, Incorporated | 5255 | L | AA | LA | GE1 | Const. of Bislig Bridge along Surigao-Davao Coastal Road |  | 2009-06-06 | 2nd | XIII |  | 81.615 | 365 |  |  |  | O | 0.4 | 0.3 | 0.097 | 0.03 | 0.056 | 0.05 | 93.3 | -
Concepcion Basic Builders, Incorporated | 5255 | L | AA | LA | GE1 | Const. of Bislig Bridge along Surigao-Davao Coastal Road |  | 2008-11-27 | 1st | XIII |  | 81.615 | 365 |  |  |  | O | 0.286 | 0.3 | 0.1 | 0.03 | 0.059 | 0.1 | 87.5 | -
Concepcion Basic Builders, Incorporated | 5255 | L | AAA | LB | GE1 | Reconst./Completion of Tago La-Paz Bridge & Approaches | Tago, Surigao del Sur | 2012-08-14 | 2nd | XIII | LF | 143.105 | 465 | 2011-09-19 | 2012-11-26 | -9.12 | O | 0.358 | 0.3 | 0.059 | 0.03 | 0.05 | 0.033 | 83 | -
Concepcion Basic Builders, Incorporated | 5255 | L | AAA | LB | GE1 | Reconst./Completion of Tago-La Paz Bridge & Approaches | Tago, Surigao del Sur | 2012-03-25 | 1st | XIII | LF | 143.104 | 405 | 2011-09-19 | 2012-10-27 | 14.38 | O | 0.343 | 0.3 | 0.15 | 0.03 | 0.035 | 0.05 | 90.8 | -
Concepcion Basic Builders, Incorporated | 5255 | L | AAA | LB | GE1 | Rehab. of Tago-San Miguel Bridge along Jct. Gamut-San Miguel Rd. | San Miguel, Surigao del Sur | 2012-08-17 | 2nd | XIII | LF | 42.877 | 330 | 2011-10-28 | 2012-10-21 | -14.77 | O | 0.4 | 0.3 | 0.002 | 0.03 | 0.06 | 0.017 | 80.9 | -
Concepcion Basic Builders, Incorporated | 5255 | L | AAA | LB | GE1 | Rehab. of Tago-San Miguel Bridge along NRJ-Bahbah-Talacogon Rd. at Mapaga-Mabagoy Sect. | Prosperidad, Agusan del Sur | 2012-03-25 | 1st | XIII | LF | 42.8765 | 300 | 2011-10-28 | 2012-08-22 | 4.54 | O | 0.36 | 0.24 | 0.15 | 0.03 | 0.04 | 0.05 | 87 | -
CONCEPTION BASIC BUILDERS, INCORPORATED | 5255 | L | AAA | LB | GE | Concreting of NRJ-Cumawas-Tinuy-an Falls Road Section with Bagnan Bridge, Borboanan, Bislig, Surigao del Sur | Bislig City, Surigao del Sur | 2015-11-13 | 1st | Regional Office | LF | 91.8433 | 296 | 2015-04-02 | 2016-02-09 | (+) 3.66 | OG | 0.39 | 0.3 | 0.15 | 0.03 | 0.03 | 0.045 | 94.5% | 94.5% Very Satisfactory
CPR CONSTRUCTION AND SUPPLY "JV" GRANDBY TRADING AND CONSTRUCTION | 32698 | L | B | SB | GE | Rehabilitation / Reconstruction of Don Leon Kilat Street | Cebu City | 2015-09-03 | 1st | Cebu City | LF | 22.775 | 210 | 2015-03-03 | 2015-09-28 | -4.67% | O | 0.202 | 0.3 | 0.103 | 0.03 | 0.03 | 0 | 66.5% | -
CR Domingo Construction, Inc. (Formerly: CR Domingo Const.) | 2992 | L | A | SB | GE2 | Const. of San Juan-San Jose Flood Control | Alfonso Lista, Ifugao | 2012-11-25 | 1st | CAR | LF | 13.475 | 148 | 2012-09-27 | 2013-02-21 | 0.27 | O | 0.388 | 0.238 | 0.15 | 0.022 | 0.033 | 0.033 | 86.4 | -
Crest Construction | 15240 | L | A | MB | GE1 | Rehab. of Itawes Bridge Approach, K0519+725 (CAR) | Piat, Cagayan | 2012-11-19 | 1st | II | LF | 7.726 | 166 | 2012-07-17 | 2012-12-29 | 4.33 | O | 0.38 | 0.24 | 0.15 | 0.03 | 0.059 | 0.05 | 90.9 | -
CREST CONSTRUCTION | 15240 | L | A | MB | GE | Road Upgrading (Unpaved to Paved) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standards (HDM-4 Project Analysis) (Intermittent Sections) CVR Regional Government Center Road Network (Dalan na Pappabalo Extension Section), Chainage 0+000 to Chainage 0+344, Tuguegarao City, Cagayan | Tuguegarao City, Cagayan | 2015-08-24 | 1st & Final | Cagayan 3rd DEO | LF | 6.841 | 105 | 2015-04-22 | 2015-08-04 | 17.67% | C | 0.459 | 0.133 | 0.3 | - | - | - | 89.2% | *89.2% Very Satisfactory
CREST CONSTRUCTION | 15240 | L | A | MB | GE | Road Upgrading (Unpaved to Paved) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standards (HDM-4 Project Analysis) (Intermittent Sections) CVR Regional Government Center Road Network (Dalan na Pappabalo Extension Section), Chainage 0+000 to Chainage 0+166, Tuguegarao City, Cagayan | Tuguegarao City, Cagayan | 2015-08-24 | 1st & Final | Cagayan 3rd DEO | LF | 3.613 | 90 | 2015-02-16 | 2015-05-16 | 0% | C | 0.468 | 0.133 | 0.3 | - | - | - | 90.1% | *90.1% Very Satisfactory
Crizel Construction & Concrete Products | 20835 | L | C | SB | GE1 | Rd. Upgrading (Gravel to Conc.) Int. Sect., Dipolog-Punta-Dansullan-Sergio Osmeña, Zamboanga Norte/Sur Bdry., K1866+000-K1866+635 | Zamboang del Norte | 2013-03-22 | 1st | IX | LF | 4.399 | 45 | 2013-02-01 | 2013-03-17 | - | O | 0.323 | 0.24 | 0 | 0.03 | 0.047 | 0.033 | 67.3 | -
CSE Builders/ Eddmari Construction & trading - JV |  | L |  |  |  | Land Development and Construction of 1000 Housing Units (Channel Ridgeview 1) | Brgy. Poblacion, Babatngon, Leyte | 2015-09-05 | 1st | NHA | LF | 289.7 | 405 | 11/18/14 | 01/21/16 | -25.13 | O | 0.3191 | 0.247 | 0 | 0.03 | 0.042 | 0.0333 | 67.14 | -
CSE Builders/ Eddmari Construction & Trading - JV | [5 empty] | Land Development and Construction of 1000 Housing Units (Channel Ridgeview 1) | Brgy. Poblacion, Babatngon, Leyte | 2016-03-19 | 2nd | NHA | LF | 289.7 | 405 | 2014-11-18 | 2016-06-02 | -15.13 | O | 0.366 | 0.2993 | 0 | 0.03 | 0.0607 | 0.0333 | 78.93 | -
CSR CONSTRUCTION & SUPPLY (Formerly: CSR CONSTRUCTION) | 14427 | L | D | SB | GB | Const. of Multi-Purpose Building, Tabing Dagat | Odiongan, Romblon | 2015-11-21 | 1st | Romblon DEO | LF | 1.9196 | 120 | 2015-09-01 | 2015-12-29 | 0.3002 | OG | 0.384 | 0.24 | 0.15 | 0.015 | 0.017 | 0.033 | 83.9% | 83.9% Satisfactory
CTC Builder and Supplies Inc./Sunwest Const. & Dev. Corp. (JV) | JV-06-070 | L | AAA | LB | GE1 | Const. of Dancalan Bridge |  | 2009-02-25 | 3rd | V |  | 57.031 | 720 |  |  |  | O | 0.352 | 0.24 | 0.15 | 0.03 | 0.061 | 0.033 | #VALUE! | -
CTC BUILDER AND SUPPLIES INCORPORATED (Formerly: CTC Builder) | 12088 | L | A | MA | GE | Off-Carriageway Improvement along Jct. Gubat-Pto. Diaz Road, K0599+(-500)-K0604+000 (with Exception), K0608+022-K0615+175 (with Exception), Gubat and Pto, Diaz, Sorsogon | Gubat and Pto, Diaz, Sorsogon | 2015-09-02 | 1st & Final | Sorsogon Second DEO | LF | 46.55 | 176 | 2015-03-09 | 2015-08-31 | - | C | 0.473 | 0.132 | 0.3 | - | - | - | 90.5% | *90.5% Very Satisfactory
CTC BUILDER AND SUPPLIES INCORPORATED (Formerly: CTC Builders) | 12088 | L | A | MA | GE | Widening of National Roads DM Jct. - Legazpi - Sto. Domingo - Tabaco - Cam. Sur. Bdry., K0567+400 - K0568+216 w/ Exception, Brgy. Coro-Coro to Gajo, Tiwi, Albay | Tiwi, Albay | 2015-11-17 | Final | Albay First DEO | LF | 17.9687 | 162 | 2015-03-23 | 2015-08-31 | - | C | 0.393 | 0.152 | 0.3 | - | - | - | 84.5% | 84.5% Satisfactory
CTC Builders & Supplies Incorporated (Formerly: CTC Builder) | 12088 | L | A | MA | GE2 | Const. of Macawayan River Flood Control Structures | Macawayan, Irosin, Sorsogon | 2013-03-15 | 1st | V | LF | 13.958 | 131 | 2013-01-22 | 2013-06-01 | 8.71 | O | 0.294 | 0.3 | 0.15 | 0.015 | 0.055 | 0.033 | 84.7 | -
CTC Builders & Supplies Incorporated (Formerly: CTC Builder) | 12088 | L | A | MA | GE2 | Const. of Bacolod River Flood Control Structures, Brgy. Bacolod | Irosin, Sorsogon | 2013-03-15 | 1st | V | LF | 13.96 | 123 | 2013-02-04 | 2013-06-06 | 18.09 | O | 0.344 | 0.222 | 0.15 | 0.03 | 0.045 | 0.05 | 84.1 | -
CTC CONSTRUCTION & SUPPLIES | 33039 | L | C | SB | GE | Local Infrastructure Program-Riprapping Projects, So. Anas, Naval, Biliran Lone District | Naval, Biliran Lone District | 2015-06-03 | Final | Biliran DEO | LF | 3.71 | 60 | 2015-02-06 | 2015-04-06 | - | C | 0.348 | 0.2 | 0.3 | - | - | - | 84.8% | *84.8% Satisfactory
Culasi General Merchandising & Construction Services | 22157 | L |  | SB | GE2 | Construction of Canal Bench Flume | Jelicuon, New Lucena, Iloilo | 2013-10-19 | 1st | NIA | L | 2.029 | 120 | 2012-12-11 | 2013-09-11 | 0 | O | 0.2603 | 0.12 | 0 | 0.02 | 0.03 | 0.05 | 48.03 | -
Culasi General Merchandising and Construction Services | 22157 | L | B | SB | GB1 | Const. of Two (2) CL Sch. Bldg, Buenavista Elem. Sch. | Belison, Antique | 2013-08-15 | 1st | VI | LF | 1.486 | 60 | 2013-03-13 | 2013-05-11 | - | O | 0.36 | 0.24 | 0 | 0.03 | 0.027 | 0.033 | 69 | -
C'ZARLES CONSTRUCTION & SUPPLY | 23426 | L | B | MA | GE | Rehabilitation/Reconstruction Along Butuan City-Malaybalay Road (S00431MN), Chainage 0 - Chainage 500, Chainage 1100 - Chainage 1200 & Chainage 1500 - Chainage 1889 | Butuan City | 2015-09-01 | 1st & Final | Butuan City | LF | 5.498 | 100 | 2015-02-28 | 2015-06-07 | (+) 6% | C | 0.426 | 0.137 | 0.3 | - | - | - | 86.3% | *86.3% Satisfactory
D & D Construction | 33327 | L | B | SB | GB1 | Const. of MPB Poblacion, La Paz | Abra | 2011-08-02 | 1st | CAR | LF | 1.403 | 120 | 2011-03-25 | 2011-07-22 | - | O | 0.386 | 0.3 | 0 | 0.03 | 0.041 | 0.025 | 78.2 | -
D AND A CONSTRUCTION | 37246 | L | D | SB | GE | Construction of Multi Purpose Building | Poblacion West, Lamut, Ifugao | 2015-06-07 | 1st | Ifugao 1st DEO | LF | 1.863 | 120 | 2015-04-07 | 2015-08-04 | (+) 1.37% | O | 0.306 | 0.269 | 0.15 | 0.015 | 0.021 | 0.05 | 81.1% | -
D. C. E. Construction | 29347 | L | B | MA | GE2 | Const. of Ili Flood Control | Conner, Apayao | 2013-03-21 | 2nd | CAR | LF | 12.905 | 225 | 2012-09-24 | 2013-04-21 | -14.44 | O | 0.328 | 0.288 | 0.006 | 0.018 | 0.023 | 0 | 66.3 | -
D. C. E. Construction | 29347 | L | B | MA | GE2 | Const. of Ili Flood Control | Conner, Apayao | 2012-11-28 | 1st | CAR | LF | 12.859 | 210 | 2012-09-24 | 2013-04-21 | -3.86 | O | 0.355 | 0.273 | 0.111 | 0.02 | 0.033 | 0.033 | 82.5 | -
D. G. Sarmenta Construction | 13024 | L | B | MA |  | Puerto Princesa Airport Development Project | Puerto Princesa, Palawan | 2014-04-28 | 1st | DOTC | LF | 21.496 | 150 | 2013-12-20 | 2014-07-02 | -1.45 | O | 0.3679 | 0.3 | 0.1355 | 0.03 | 0.0269 | 0.05 | 91.03 | -
D. K. Jocson Construction | 6896 |  | A | MA |  | Dipolog Feeder Port Development Project | Brgy. Galas, Dipolog City, Zamboanga del Norte/ Region IX | 2016-01-28 | 2nd | DOTC | LF | 49.38 | 762 | 2014-07-14 | 2016-07-16 | -40.81 | O | 0.3788 | 0.3 | 0 | 0.03 | 0.0445 | 0.05 | 80.33 | -
D. K. Jocson Construction | 6896 | L | A | MA |  | Dipolog Feeder Port Development Project | Brgy. Galas, Dipolog City, Zamboanga del Norte | 2016-04-07 | 3rd | DOTC | LF | 49.38 | 761 | 2014-07-14 | 2016-07-15 | 4.1 | O | 0.329 | 0.3 | 0.15 | 0.03 | 0.044 | 0.05 | 90.3 | -
D. L. CERVANTES | JV-14-617 | L | AAA | LB | GE | Road Upgrading (Unpaved to Paved) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standards (HDM-4 Project Analysis) Intermittent Sectionsalong Banaue-Hungduan-Benguet Boundary Road, K0398+537 to K0405+000, Chainage 838 - Chainage 1075 | Tinoc, Ifugao | 2015-11-14 | 1st | Regional Office | LF | 184.6036 | 360 | 2015-04-15 | 2016-04-08 | 3.87% | OG | 0.344 | 0.245 | 0.15 | 0.03 | 0.06 | 0.05 | 87.9% | 87.9% Satisfactory
D. M. CATIGNAS ENTERPRISES | 20149 | L | B | SB | GB | Construction of Two (2) Strorey (4) CL School Building Pagsanjan, Pagsanjan, Laguna | Pagsanjan, Laguna | 2015-11-18 | 1st | LAGUNA 1ST DEO | LF | 6.0371 | 120 | 2015-08-06 | 2015-12-03 | 0.0035 | OG | 0.39 | 0.255 | 0.15 | 0.03 | 0.035 | 0.05 | 91% | 91% Very Satisfactory
D. S. Pamintuan Construction | 4326 | L |  | MA |  | Canalization Works | San Isidro, Lupao, Nueva Ecija | 2015-05-23 | 1st | NIA | L | 8.098 | 180 | 2014-12-30 | 2015-06-27 | -48.49 | O | 0.3651 | 0.2 | 0 | 0.03 | 0.07 | 0.05 | 71.51 | -
D. S. T. METALCRAFT AND ENGINEERING WORKS | 34382 | L | D | SB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Road, Based on Pavement Management System/Highway Development and Management-4 (HDM-4) along Daang Maharlika, K0391+-149 to K0391+050 | Gamu, Isabela | 2015-06-05 | 1st | Isabela 2nd DEO | LF | 2.975 | 97 | 2015-03-26 | 2015-06-30 | 5.53% | O | 0.374 | 0.3 | 0.15 | 0.03 | 0.05 | 0.033 | 93.7% | -
D.C.E. CONSTRUCTION | 29347 | L | B | MA | GE | Network Development (Widening) Kalinga - Cagayan Road, K0497+501 to K0498+344, K0499+915 to K0502+000, Tabuk City, Kalinga | Tabuk City, Kalinga | 2015-08-29 | 1st | CAR | LF | 64.239 | 237 | 2015-04-03 | 2015-11-25 | -7.95% | O | 0.319 | 0.3 | 0.071 | 0.03 | 0.041 | 0.033 | 79.4% | -
D.C.M Construction | 5641 | L | A | MA | GE1 | Completion of the Const. of Agus II Bridge (Pumping Bridge) & Approaches, Phase II Raya Madaya-Pumping Road |  | 2009-09-13 | 1st | X |  | 22.952 | 2868 |  |  |  | O | 0.383 | 0.185 | 0.15 | 0.03 | 0.051 | 0.033 | 83.2 | -
D.C.M. Construction | 5641 | L | A | MA | GE1 | Const. of Agus III (Pumping) Bridge & Approaches along Raya-Madaya Pumping Road | Marawi City | 2011-04-11 | 1st | X | LF | 32.933 | 180 | 2010-11-22 | 2011-05-20 | 0.67 | O | 0.401 | 0.24 | 0.15 | 0.03 | 0.042 | 0.033 | 89.6 | -
D.C.M. CONSTRUCTION | 5641 | L | A | MA | GE | Construction/Concreting of Local Roads, Junction Kapatagan-Lanao del Norte Interior Circumferential Road (LDNICR) Junction Sapad (Kapatagan-Sapad Road Section), Kapatagan, Lanao del Norte | Kapatagan, Lanao del Norte | 2015-11-18 | 1st | Lanao del Norte 1st | LF | 18.5652 | 121 | 2015-08-10 | 2015-12-09 | (+) 0.27% | OG | 0.37 | 0.237 | 0.15 | 0.03 | 0.045 | 0.033 | 86.5% | 86.5% Satisfactory
D.C.R. Construction | 5040 | L | A | MA | GE1 | Widening of Cavite-Batangas Rd., Km.23+653 - Km.25+306 | Imus, Cavite | 2012-11-23 | 2nd | IVA | LF | 31.628 | 271 | 2012-02-07 | 2012-02-03 | 0.32 | O | 0.338 | 0.3 | 0.15 | 0.03 | 0.056 | 0.033 | 90.7 | -
D.C.R. Construction | 5040 | L | A | MA | GE1 | Widening of Cavite-Batangas Road, Km.23+653-Km.25+306 | Imus, Cavite | 2012-08-15 | 1st | IVA | LF | 31.628 | 271 | 2012-02-07 | 2012-11-03 | 2.59 | O | 0.341 | 0.3 | 0.15 | 0.03 | 0.05 | 0.05 | 92.1 | -
D.G. Chico Trading & Construction Corporation | 8748 | L | A | MB | GE | Proposed Rehabilitation of Road and Drainage System along Galvez St. And Villanueva St. | Pasay City | 2014-11-20 | 1st | NCR | LF | 17.4214 | 179 | 2014-07-04 | 2014-12-29 | 0% | O | 0.364 | 0.233 | 0.15 | 0.022 | 0.055 | 0.033 | 85.7% | 85.70% Satisfactory
D.G. SARMENTA CONSTRUCTION | 13024 | L | B | MA | GE | Concreting of Sitio Culiat Farm to Market Road Phase II, Laur, Nueva Ecija | Laur, Nueva Ecija | 2015-11-16 | Final | Nueva Ecija Second DEO | LF | 5.14 | 75 | 2015-04-06 | 2015-06-19 | - | C | 0.492 | 0.133 | 0.3 | - | - | - | 92.5% | 92.5% Very Satisfactory
D.G.O. Construction | 6788 | L | D | SB | GE1 | Repair/Rehab. along Baguio-Bauang Rd., K0281+800-K0285+400 (w/ exception) | Sablan, Benguet | 2013-03-12 | 1st | CAR | LF | 9.167 | 170 | 2012-11-17 | 2013-05-04 | 6.76 | O | 0.381 | 0.24 | 0.15 | 0.03 | 0.03 | 0.05 | 88.1 | -
D.J. Valera Construction & Supply | ARC-C 34003 | L |  | SB |  | IMPROVEMENT OF BITUKANG MANOK DAM #7 | SAN LUIS & CANDABA. PAMPANGA | 2015-08-15 | 1st | NIA | LF | 13.569 | 120 | 2015-07-09 | 2015-11-09 | 5.98 | O | 0.3097 | 0.3 | 0.15 | 0 | 0.0233 | 0.05 | 83.3 | -
D.J.D. CONSTRUCTION | 32217 | L | B | MA | GE | Concreting of Dungeg - Patunungan Farm to Market Road (Phase I), Sta. Ana, Cagayan | Sta. Ana, Cagayan | 2015-08-25 | 1st | Cagayan 1st DEO | LF | 23.733 | 248 | 2015-03-17 | 2015-11-19 | -5.26% | O | 0.366 | 0.3 | 0.097 | 0.03 | 0.054 | 0.025 | 87.2% | -
D.K Jocson Construction / TSD Builders Const. and Supply JV | JV-08-024 | L | A | MA | GE1 | Conc. of Road along Bacolod North Road (Toboso Section) |  | 2009-03-09 | 1st | VIII |  | 18.174 | 281 |  |  |  | O | 0.333 | 0.297 | 0.15 | 0.03 | 0.05 | 0.033 | #VALUE! | -
D.K. Jocson Construction | 6896 | L | A | MB | GE-5 | San Vicente Port Development Project | Brgy. San Vicente, Caramoan, Camarines Sur/Region V | 2015-05-27 | 1st | DOTC | LF | 17.559 | 180 | 2014-03-06 | 2015-05-12 | -14.8 | O | 0.3596 | 0.3 | 0.002 | 0.015 | 0.035 | 0.05 | 76.16 | -
D.K. Jocson Construction | 6896 | L | A | MA | GE_5 | Dipolog Feeder Port Development Project | Brgy. Galas, Dipolog City, Zamboanga del Norte/Region IX | 2015-06-10 | 1st | DOTC | LF | 49.38 | 475 | 2014-06-14 | 2016-01-30 | 14.98 | O | 0.3767 | 0.3 | 0.15 | 0.015 | 0.0292 | 0.0333 | 90.42 | -
D.K. Jocson Construction | 6896 | L | A | MA | GE | Rehabilitation/Reconstruction/Replacement/Retrofitting of Permanent Bridge, Oas Diversion Bridge along Daang Maharlika Road | Oas, Albay | 2014-08-11 | 1st | V | LF | 8.964 | 210 | 2014-02-20 | 2014-09-17 | 0 | O | 0.338 | 0.24 | 0.15 | 0.02 | 0.037 | 0.05 | 83.5 | -
D.K. Jocson Construction | 6896 | L | A | MA | GE1 | Conc. of Nat'l. Rd. along Bacolod South Rd., (K0207+900-K0208+356) | Hinoba-an, Negros Occidental | 2013-03-13 | 1st | VI | LF | 34.447 | 190 | 2012-06-11 | 2013-04-01 | -5.79 | O | 0.384 | 0.3 | 0.092 | 0.018 | 0.04 | 0.033 | 86.7 | -
D.K. Jocson Construction / TSD Builders Construction and Supply (JV) | JV-12-178 | L | A | MA | GE1 | Rehab./Reconst. of Malogo Bridge along Bacolod North Rd. | Victorias City, Negros Occidental | 2013-03-15 | 1st | VI | LF | 13.625 | 121 | 2013-02-04 | 2013-06-04 | 19.44 | O | 0.341 | 0.212 | 0.15 | 0.018 | 0.06 | 0.05 | 83.1 | -
D.L. AUREO CONSTRUCTION | 24894 | L | D | SB | GB | Construction/Rehabilitation/Repair of Multi-Purpose Building Covered Court-Leyte National High School, Tacloban City | Tacloban City | 2015-11-11 | Final | Tacloban City DEO | LF | 4.9626 | 90 | 2015-06-08 | 2015-09-05 | (+)36.67% | C | 0.481 | 0.133 | 0.3 | - | - | - | 91.4% | 91.4% Very Satisfactory
D.L. CERVANTES CONSTRUCTION CORPORATION/BUGANI CONSTRUCTION AND ENTERPRISES, INC. -Joint Venture | JV-14-617 | L | AAA | LB | GE | Road Upgrading (Unpaved to Paved) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standards (HDM-4 Project Analysis) (Intermittent Sctions) along Banaue - Hungduan - Benguet Bdry. Road, K0398+537 to K0405+000, Chainage 838 to Chainage 1075, Tinoc, Ifugao | Tinoc, Ifugao | 2015-08-31 | 1st | CAR | LF | 184.603 | 360 | 2015-04-15 | 2016-04-08 | 6.74% | O | 0.362 | 0.225 | 0.15 | 0.03 | 0.056 | 0.05 | 87.3% | -
D.M House Const. Inc. | 25810 |  |  |  |  | Impvt./Rehab. of Roman Expressway, Bataan 1st Congressional District |  | 2010-05-28 |  | III |  | 53.666 | 90 |  |  |  | O | 0.386 | 0.24 | 0.15 | 0.03 | 0.043 | 0.033 | 88.2 | -
D.M House Const. Inc. | 25810 | L | AAA | MB | GE1 | Improvement/Rehabilitation of Roman Expressway |  | 2009-05-21 | 1st | III |  | 71.9549 | 150 |  |  |  | O | 0.378 | 0.3 | 0.15 | 0.03 | 0.037 | 0.05 | 94.5 | -
D.M. House Construction, Inc. | 25810 | L | A | MB | GE | Rehab./Reconst./Upgrading of Damaged Paved National Road HDM-4 (Intermittent Section) G.S.U. Road | Dinalupihan, Bataan | 2014-11-26 | 1st | III | LF | 23.0791 | 120 | 2014-09-15 | 2015-01-12 | 0% | O | 0.228 | 0.3 | 0.15 | 0.023 | 0.032 | 0.033 | 76.6% | 76.60% Unsatisfactory
D.M. House Construction, Inc. | 25810 | L | A | MB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Road HDM-4 (Intermittent Sections) G.S.U. Road | Dinalupihan, Bataan | 2014-11-26 | 1st | III | LF | 7.0791 | 135 | 2014-09-15 | 2015-01-27 | -4.67% | O | 0.306 | 0.3 | 0.103 | 0.023 | 0.032 | 0.033 | 79.7% | 79.70% Unsatisfactory
D.M. MALIWANAG BUILDERS AND ENTERPRISES/KING'S BUILDERS & DEVELOPMENT CORP.-JOINT VENTURE | 0 | L | B | MA | GE | Const. of Gabions Revetment, Wasig River Control | Mansalay, Oriental Mindoro | 2015-11-18 | Final | Southern Mindoro DEO | LF | 9.6505 | 89 | 2015-08-25 | 2015-11-21 | 0.02 | C | 0.482 | 0.133 | 0.3 | - | - | - | 91.5% | 91.5% Very Satisfactory
D.R. Robles Construction | 28559 | L |  | MA |  | IMPROVEMENT OF LATERAL G-2 (AMRIS) | PULILAN, BULACAN | 2015-08-15 | 1st | NIA | LF | 9.211 | 120 | 2015-07-10 | 2015-11-06 | 24.18 | O | 0.309 | 0.3 | 0.15 | 0.015 | 0.0311 | 0.0333 | 83.84 | -
D.R. Robles Construction | 28559 | L | B | MA | GE1 | Widening of Angono Diversion Rd. Angono & Binangonan | Rizal | 2012-07-31 | 2nd | IVA | LF | 28.896 | 210 | 2012-01-16 | 2012-08-12 | 2.89 | O | 0.39 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 91.5 | -
D.T. Estaron Engineering and Construction | 5082 | L | C | SB | GB1 | Const. of 1-Unit, 2-Storey, 6-Cl Sch. Bldg. at Maypangadan NHS | Borongan City, Eastern Samar | 2013-08-20 | 1st | VIII | LF | 6.301 | 250 | 2013-03-27 | 2013-12-01 | 14.7 | O | 0.391 | 0.258 | 0.15 | 0.03 | 0.053 | 0.033 | 91.5 | -
D.V. Salud Construction | 6564 | L | AA | MB | GE1 | Repair/Rehab./Impvt. of Pedestrian Overpass along Old Manila South Rd., Sta. Rosa-Dila Sect., K0039+900 | Sta. Rosa City, Laguna | 2013-08-10 | 1st | IVA | LF | 9.752 | 120 | 2013-04-05 | 2013-08-02 | -24.5 | O | 0.339 | 0.071 | 0 | 0.022 | 0.023 | 0.017 | 47.2 | -
Da Cadeliña Construction | 29004 | L | D |  | GE2 | Dabubu River Irrigation Project | San Agustin, Isabela / Region 2 | 2013-04-27 | 1st | NIA | LF | 7.597 | 180 | 2013-02-11 | 2013-08-18 | 5.49 | O | 0.3598 | 0.2584 | 0.15 | 0.012 | 0.0233 | 0.05 | 85.35 | -
Dahl Construction | 8931 | L | A | MA | GE1 | Rehab./Reconst./Upgrading of Marikina-Infanta Rd., Brgy. San Jose | Antipolo City | 2012-07-30 | 1st | IVA | LF | 17.46 | 210 | 2012-02-29 | 2012-09-26 | 3.24 | O | 0.347 | 0.24 | 0.15 | 0.03 | 0.045 | 0.05 | 86.2 | -
DAHL CONSTRUCTION | 8931 | L | A | MB | GE | Construction of Slope Protection and Desilting of Creek along C-6, Brgy. Palingon-Tipas, Taguig City | Taguig City | 2015-06-04 | Final | Metro Manila 1st DEO | LF | 17.369 | 180 | 2015-03-02 | 2015-08-28 | (+) 47.22 | C | 0.45 | 0.133 | 0.3 | - | - | - | 88.3% | *88.3% Satisfactory
Dakay Construction & Develoopment Corp. | 8838 | L | AAA | LB |  | San Jose Port Expansion Project | Port of San Jose, Caminawit, Occidental Mindoro | 2015-03-06 | 1st | PPA | L | 117.812 | 480 | 2014-01-10 | 2015-05-04 | -19.937 | O | 0.399 | 0.3 | 0 | 0.024 | 0.07 | 0.05 | 84.3 | -
Dakay Construction & Development Corp. | 8838 |  | AAA | LB |  | San Jose Port Expansion Project | Port of San Jose, Caminawit, Occidental Mindoro | 03-18, 2016 | 2nd & Final | PPA | LF | 117.812 | 692 | 2014-01-10 | 2016-01-06 | -5.058 | C | 0.473 | 0.2 | 0.249 | - | - | - | 92.2 | 87.47% Satisfactory
DALANON CONSTRUCTION REF. SUPPLY AND SERVICES | 11205 | L | B | 0 | GE | Road Upgrading (gravel to paved) Isulan Jct. Dukay-Bag. SNA Rd. K1781+594 to K1782+064, K1782+668 K1780+878 | Isulan, Sultan Kudarat | 2015-11-10 | Final | Sultan Kudarat First DEO | LF | 11.7662 | 139 | 2015-03-04 | 2015-07-20 | 0.00% | C | 0.46 | 0.157 | 0.3 | - | - | - | 91.7% | 91.7% Very Satisfactory
Dalanon Construction Refregiration Supply & Service | 11205 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Paved) along Awang-Upi-Lebak-Kalamansig-Palimbang-Sarangani Rd. (Km.1963+471-Km.1977+121) realigned to Rd. Upgrading (Gravel to Paved) along Awang-Upi-Lebak-Kalamansig-Palimbang-Sarangani Rd. (Km.2034+798-Km.2036+898) | Palimbang, Sultan Kudarat | 2013-03-13 | 1st | XII | LF | 47.765 | 327 | 2012-07-06 | 2013-05-28 | 12.16 | O | 0.365 | 0.232 | 0.15 | 0.03 | 0.045 | 0.05 | 87.2 | -
DALANON CONSTRUCTION REFREGIRATION SUPPLY & SERVICE | 11205 | L | B | MA | GE | Road Upgrading (Unpaved to Paved) based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standard (HDM-4 Project Analysis) (Intermittent Section) K1781+594-K1782+064, K1782+668-K1782+878 | Isulan, Sultan Kudarat | 2015-06-03 | 1st | Sultan Kudarat 1st DEO | LF | 12.084 | 119 | 2015-03-04 | 2015-07-01 | -4.81% | O | 0.354 | 0.24 | 0.102 | 0.03 | 0.051 | 0.05 | 82.7% | -
Dalanon Construction Refregiration Suppply & Service | 11205 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Paved) along Awang-Upi-Lebak-Kalamansig-Palimbang-Sarangani Rd. (Km.2010+661-Km.2012+961 w/ exception) | Palimbang, Sultan Kudarat | 2013-08-18 | 1st | XII | LF | 45.366 | 196 | 2013-04-02 | 2013-10-14 | -1.17 | O | 0.34 | 0.3 | 0.138 | 0.024 | 0.051 | 0.033 | 88.6 | -
Dalanon Construction Refrigeration Supply & Service | 11205 |  |  |  |  | Rehab./Reconst. of Dulawan-Marbel (Tacurong-New Carmen Section) |  | 2010-06-08 |  | XII |  | 12.222 | 254 |  |  |  | O | 0.291 | 0.203 | 0.15 | 0.03 | 0.051 | 0.05 | 77.5 | -
Damico Builders & Supplies | 30355 | L | B | MA | GE1 | Repair/Rehab./Impv't. of Damaged Paved Nat'l Rd. along Tibag-Burgos Rd., K0137+600-K0147+570, w/ exception | Tarlac City | 2013-08-08 | 1st | III | LF | 9.601 | 120 | 2013-06-02 | 2013-09-29 | 1.01 | O | 0.343 | 0.238 | 0.15 | 0.03 | 0.043 | 0.033 | 83.7 | -
Damico Builders & Supplies | 30355 | L | B | MA | GE1 | Concreting of Brgy. Road from Brgy. San Agustin to Brgy. Bantog |  | 2009-09-02 | 1st | III |  | 1.687 | 87 |  |  |  | O | 0.365 | 0.24 | 0.15 | 0.03 | 0.047 | 0.033 | 86.5 | -
Damico Builders & Supplies | 30355 | L | B | MA | GE1 | Conc. of Brgy. Road @ Nagmisaan | Paniqui, Tarlac | 2012-11-24 | 1st | III | LF | 5.894 | 75 | 2012-09-17 | 2012-11-30 | 0.56 | O | 0.323 | 0.274 | 0.15 | 0.03 | 0.025 | 0.05 | 85.2 | -
Danvic Construction | 24439 | L | B | MA | GE1 | Rds. to Address Critical Bottlenecks, Nat'l Rd. Traffic Decongestion-Widening of ABS-CBN Quimpo Blvd. Diversion Rd. | Davao City | 2013-03-22 | 1st | XI | LF | 18.618 | 102 | 2013-01-23 | 2013-05-04 | 1.57 | O | 0.347 | 0.245 | 0.15 | 0.03 | 0.045 | 0.033 | 85 | -
DANVIC CONSTRUCTION | 24439 | L | B | MA | GE | Construction of Barangay Road, Brgy. San Roque to Katualan, Malativas and Mabunao | Panabo City, Davao del Norte | 2015-06-10 | 1st | Davao del Norte | LF | 13.355 | 110 | 2015-03-04 | 2015-06-21 | (+)0.90% | O | 0.359 | 0.236 | 0.15 | 0.03 | 0.047 | 0.033 | 85.5% | -
DANVIC CONSTRUCTION | 24439 | L | B | MA | GE | Construction of Barangay Road, Brgy. San Roque to Katualan, Malativas and Mabunao | Brgy. San Roque to Katualan, Malativas and Mabunao | 2015-08-30 | Final | Davao del Norte DEO | LF | 13.355 | 110 | 2015-03-04 | 2015-06-21 | - | C | 0.457 | 0.103 | 0.3 | - | - | - | 86% | *85.7% Satisfactory
Danysons Construction | 25452 | L |  |  |  | Irrigation | Barculan, Gamu, Isabela, Region 2 | 2015-04-27 | 1st | NIA | L | 19.816 | 162 | 2014-11-17 | 2015-04-28 | -3.54 | O | 0.3534 | 0.3 | 0.1146 | 0.03 | 0.07 | 0.0167 | 88.47 | -
Danysons Construction | 25452 | L | A | MA | GE1 | Conc. of Dummon-Turod FMR | Quezon, Isabela | 2013-03-18 | 1st | II | LF | 4.6 | 60 | 2013-01-29 | 2013-03-29 | 3.3 | O | 0.39 | 0.24 | 0.15 | 0.03 | 0.039 | 0.05 | 89.9 | -
DANYSONS CONSTRUCTION | 25452 | L | A | MA | GE | Construction of Siffu Flood Control Project Cullalabo Section | Burgos, Isabela | 2015-06-05 | 1st | Isabela 2nd DEO | LF | 18.296 | 217 | 2015-02-24 | 2015-09-28 | 2.82% | O | 0.272 | 0.3 | 0.15 | 0.03 | 0.04 | 0.033 | 82.5% | -
DANYSONS CONSTRUCTION | 25452 | L | A | MA | GE | Construction of Siffu River Flood Control Project Cullalabo Section, Burgos, Isabela | Burgos, Isabela | 2015-08-28 | 1st | Isabela 2nd DEO | LF | 18.296 | 209 | 2015-02-24 | 2015-09-20 | -0.12% | O | 0.354 | 0.3 | 0.149 | 0.03 | 0.045 | 0.033 | 91.1% | -
DANYSONS CONSTRUCTION | 25452 | L | A | MA | GE | Construction of Stiffu River Flood Control Project, Cullalabo Section, Burgos, Isabela | Burgos, Isabela | 2015-11-14 | Final | ISABELA 2ND DEO | LF | 18.2964 | 219 | 2015-02-24 | 2015-09-30 | (+) 0.01 | C | 0.4 | 0.1 | 0.3 | - | - | - | 80% | 84.08% Satisfactory
DATREBIL CONSTRUCTION & SUPPLY | 36908 | L | B | SB | GE | Repair/Rehabilitation/Improvement Of Daang Maharlika (Agusan - Davao Road), Osmeña Section, K1274+780.00 - K1274+840; K1279+400.00 - K1279+437.00; K1279+690.00 - K1279+746 | Bayugan, Agusan Del Sur | 2015-08-24 | 1st & Final | Agusan del Sur 1st | LF | 11.709 | 162 | ###### | 2015-05-27 | 0% | C | 0.475 | 0.146 | 0.3 | - | - | - | 92.1% | *92.1% Very Satisfactory
DATREBIL CONSTRUCTION & SUPPLY | 36908 | L | B | SB | GE | Concreting of Access Road to Provincial Correctional Services, Prosperidad, Agusan del Sur | Prosperidad, Agusan del Sur | 2015-11-09 | Final | Agusan del Sur 1st DEO | LF | 4.7483 | 67 | 2015-03-03 | 2015-05-08 | (+) 3.75 | C | 0.423 | 0.2 | 0.3 | - | - | - | 92.3% | 92.3% Very Satisfactory
DATRIBEL CONSTRUCTION & SUPPLY | 36908 | L | B | SB | GE | Construction/ Upgrading of Local Road | Barangay Calamba, Cabadbaran City, Agusan Del Norte | 2015-06-02 | Final | AGUSAN DEL NORTE DEO | LF | 3.743 | 48 | 2015-03-27 | 2015-05-13 | (+)2.08 | C | 0.462 | 0.133 | 0.3 | - | - | - | 89.5% | *89.5% Very Satisfactory
DATRIBEL CONSTRUCTION & SUPPLY | 36908 | L | B | SB | GE | Rehabilitation of Sta.Irene Bridge along NRJ - Bayugan - Calaitan - Tandag Road | Bayugan, Agusan Del Sur | 2015-06-04 | 1st | AGUSAN DEL SUR FIRST DEO | LF | 10.076 | 179 | 2015-03-03 | 2015-08-28 | (+) 4.35% | O | 0.36 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 88% | -
Davao Concrete Products | 12090 | L | A | MA | GE1 | Embankment of Maniki Jumbo Bridge Approach "B" (Upstream R/S) Tagum Panabo Circ. Rd. | Davao del Norte | 2013-03-18 | 1st | XI | LF | 1.985 | 135 | 2012-11-06 | 2013-03-20 | 0.52 | O | 0.299 | 0.24 | 0.15 | 0.03 | 0.04 | 0.033 | 79.2 | -
Davao Concrete Products | 12090 | L | A | MA | GE1 | Impvt./Conc. of Babak-Samal-Kaputian, Island Garden |  | 2009-06-02 | 1st | XI |  | 33.719 | 90 |  |  |  | O | 0.366 | 0.3 | 0.15 | 0.03 | 0.037 | 0.05 | 93.3 | -
Davao Concrete Products | 12090 | L | A | MA | GE1 | Impvt./Conc. of Babak-Samal-Katipunan Road, Katipunan Section |  | 2009-03-13 | 2nd | XI |  | 34.712 | 286 |  |  |  | O | 0.327 | 0.274 | 0.15 | 0.022 | 0.06 | 0.05 | #VALUE! | -
Davao Concrete Products | 12090 | L | A | MA | GE2 | Const. of Revetment, Saug River Flood Control, Cambanogoy, (Tagum Panabo Circ. Rd.) | Asuncion, Davao del Norte | 2012-11-24 | 1st | XI | LF | 18.589 | 161 | 2012-08-07 | 2013-01-14 | 0.4 | O | 0.386 | 0.24 | 0.15 | 0.03 | 0.03 | 0.05 | 88.6 | -
Davao Concrete Products | 12090 | L | A | MA | GE2 | Const. of Revetment Kapalong Flood Control (Left Side of Old Maniki Bridge), Maniki | Kapalong, Davao del Norte | 2012-08-12 | 1st | XI | LF | 33.27 | 266 | 2011-12-28 | 2012-09-18 | -0.4 | O | 0.399 | 0.059 | 0.146 | 0.03 | 0.06 | 0.033 | 72.7 | -
Davao Concrete Products | 12090 |  | A | MA |  | Rehabilitation and Minor Improvement of Km. 9, Sagayen-Sawata Provincial Road | Municipalitites of Asuncion and San Isidro/ Region 11 | 2015-10-27 | Final | Provincial Government of Davao del Norte | LF | 14.389 | 260 | 2014-09-08 | 2015-05-25 | 0 | C | 0.5 | 0.2 | 0.3 | - | - | - | 100 | 87.33% Satisfactory
Davao Concrete Products | 12090 |  | A | MA |  | Rehabilitation and Minor Improvement of Km. 9, Sagayen-Sawata Provincial Road | Municipalitites of Asuncion and San Isidro/ Region 11 | 2015-03-31 | 1st | Provincial Government of Davao del Norte | LF | 17.644 | 220 | 2014-09-08 | 2015-04-15 | 2.26 | O | 0.3244 | 0.2097 | 0.15 | 0.03 | 0.04 | 0.05 | 80.41 | -
Davao Concrete Products | 12090 |  | A | MA |  | Rehabilitation and Minor Improvement of Km. 9, Sagayen-Sawata Provincial Road | Municipalitites of Asuncion and San Isidro/ Region 11 | 2015-04-08 | 2nd | Provincial Government of Davao del Norte | LF | 17.644 | 220 | 2014-09-08 | 2015-04-15 | 1.67 | O | 0.3474 | 0.1495 | 0.15 | 0.03 | 0.0467 | 0.05 | 77.36 | -
Davao Concrete Products/MN Bayalas Const. (JV) |  | L | A | MA | GE | Construction of Flood Control Structure/Drainage along SDCR, Surigao del Sur 2nd LD, K1464+491 - K1465+960 | Bislig City, Surigao del Sur | 2014-08-09 | 1st | XIII | LF | 11.1288 | 251 | 2014-04-01 | 2014-12-07 | 3.82 | O | 0.321 | 0.237 | 0.15 | 0.03 | 0.056 | 0.05 | 84.4 | -
Davao Rock Mixer Ent./Wee Eng. Construction Inc. (JV) | JV-13-476 | L | A | MA | GE | Replacement of Camanlangan Bridge, New Bataan Nabunturan – Maragusan Road | Comval Province | 2014-08-09 | 1st | XI | LF | 27.6459 | 195 | 2014-01-20 | 2014-07-04 | -4.5 | O | 0.377 | 0.24 | 0.105 | 0.03 | 0.023 | 0.033 | 80.8 | -
Davao Rock Mixer Enterprises | 19250 | L | A |  |  | Bislig City IDP-IC LCB-SDS-BCIDP-IC(LP-1)-14-2013 | Bislig City, Surigao del Sur | 2014-06-07 | 1st | NIA | LF | 16.194 | 250 | 2013-04-22 | 2014-08-30 | 0 | O | 0.347 | 0.233 | 0.15 | 0.024 | 0.043 | 0.05 | 84.7 | -
DAVAO ROCK MIXER ENTERPRISES | 19250 | L | A | MA | GE | Improvement/Rehabilitation of Anda Bonifacio, Legaspi and Ponciano Main Drainage, Davao City | Davao City | 2015-11-19 | 1st | Davao City 1st DEO | LF | 4.7409e-05 | 203 | 2015-07-04 | 2016-01-22 | 0.0001 | OG | 0.369 | 0.226 | 0.15 | 0.03 | 0.07 | 0.05 | 89.5% | 89.5% Very Satisfactory
Davao United Builders Cooperative | 3310 | L | B |  |  | Bislig City IDP-IC LCB-SDS-BCIDP-IC(LP-3)-16-2013 | Bislig City, Surigao del Sur | 2014-06-07 | 1st | NIA | LF | 24.271 | 300 | 2013-06-01 | 2014-03-27 | 0 | O | 0.347 | 0.24 | 0.15 | 0.024 | 0.043 | 0.05 | 85.4 | -
Davhez Trading and Construction | 9833 | L | A | MA | GB1 | Const. of Three (3) Storey, Nine (9) CL Sch. Bldg., Las Piñas Science High School |  | 2009-09-04 | 1st | NCR |  | 10.049 | 140 |  |  |  | O | 0.331 | 0.225 | 0.15 | 0.02 | 0.058 | 0.033 | 81.7 | -
DAVHEZ TRADING AND CONSTRUCTION | 9833 | L | A | MA | GB | Construction of School Building including Facilities Pathwalk (Connecting Bridge), Talon 2, Las Pinas City, Metro Manila | Las Piñas | 2015-06-10 | 1st | Las Pinas-Muntinlupa | LF | 9.196 | 150 | 2015-04-01 | 2015-08-28 | (+) 4.86 | O | 0.363 | 0.24 | 0.15 | 0.015 | 0.048 | 0.05 | 86.6% | -
DBMR BUILDERS AND SUPPLY/DAN-BEL CONSTRUCTION & SUPPLY JOINT VENTURE | JV-14-434 | L | B | MA | GE | Road Upgrading (Unpaved to Paved) along Asuncion - San Isidro - Laak - Veruela Road, K1552+140 - K1553+760 | Veruela, Agusan Del Sur | 2014-08-25 | 1st | Agusan del Sur 2nd | LF | 45.761 | 179 | 2013-03-25 | 2013-09-19 | (+) 0.32% | O | 0.37 | 0.242 | 0.15 | 0.015 | 0.025 | 0.05 | 85.2% | -
DBMR BUILDERS AND SUPPLY/DAN-BEL CONSTRUCTION & SUPPLY JOINT VENTURE | 0 | L | B | MA | GE | Road Upgrading (Unpaved to Paved) along Asuncion-San Isidro-Laak-Veruela Road, K1552+140 - K1553+760 S00480MN, Veruela, Agusan del Sur | Veruela, Agusan del Sur | 2015-11-11 | Final | Agusan del Sur 2nd DEO | LF | 48.251 | 241 | 2015-03-25 | 2015-11-20 | (+) 5.01 | C | 0.372 | 0.2 | 0.3 | - | - | - | 87.2% | 87.2% Satisfactory
DCD BUILDERS AND ENTERPRISES | 38029 | L | C | SB | GB | Cluster 10: Construction of Multi-Purpose Building at Iligan City a) Purok 10-B, Tomas Cabili, Iligan City | Tomas Cabili, Iligan City | 2015-11-17 | Final | Lanao del Norte 2nd | LF | 2.8179 | 150 | 2015-02-20 | 2015-07-20 | 0.00% | C | 0.497 | 0.133 | 0.3 | - | - | - | 93% | 93% Very Satisfactory
DCE Construction | 29347 |  |  |  |  | Conc. along Calanasan-Claveria Road, Poblacion Section |  | 2010-02-19 |  | CAR |  | 14.875 | 538 |  |  |  | O | 0.353 | 0.24 | 0.15 | 0.03 | 0.035 | 0.033 | 84.1 | -
DCE Construction | 29347 | L | B | MA |  | Cauayan Airport Development Project | Cauayan City, Isabela | 2016-10-27 | 1st | DOTC | LF | 30.1214 | 270 | 2016-01-11 | 2017-01-05 | 9.95 | O | 0.353 | 0.3 | 0.15 | 0.03 | 0.07 | 0.05 | 95.3 | -
DDS BUILDERS | 37010 | L | B | SB | GB | Construction/Repair/Rehabilitation/Improvement of Various Infrastructure Including Local Projects Construction of Office of the Vice President (OVP) Office Senior Citizen's Affair (OSCA), (Multi-Purpose Building), Center, Lopez Jaena, Misamis Occidental | Lopez Jaena, Misamis Occidental | 2015-11-20 | Final | Misamis Occidental 1st | LF | 1.8881 | 90 | 2015-07-03 | 2015-10-01 | 0.00% | C | 0.477 | 0.133 | 0.3 | - | - | - | 91% | 91% Very Satisfactory
DEKM CONSTRUCTION | 32409 | L | D | SB | GE | Construction/Maintenance of Flood Control Mitigation Structures and Drainage Systems, Construction of Buluan Flood Control, Buluan, Conner, Apayao | Buluan, Conner, Apayao | 2015-08-27 | 1st | Apayao 1st DEO | LF | 4.899 | 220 | 2015-02-16 | 2015-09-23 | 8.68% | O | 0.356 | 0.236 | 0.15 | 0.03 | 0.04 | 0.05 | 86.2% | -
DEKM CONSTRUCTION | 32409 | L | D | SB | GE | Construction/ Maintenance of Flood Control Mitigation Structures and Drainage System, Construction of Buluan Flood Control | Buluan, Conner, Apayao | 2015-11-14 | Final | Apayao 1st | LF | 4.8995 | 250 | 2015-02-16 | 2015-10-23 | 9.51% | C | 0 | 0.2 | 0.3 | - | - | - | 50% | 71.72% Poor
DELA ROSA CONSTRUCTION & DEV'T. CORP. (Formerly: Zact Builders) | 33702 | L | D | SB | GB | Construction of Multi-Purpose Building, Milagrosa, Quezon City | Quezon City | 2015-06-03 | Final | Quezon City 2nd DEO | LF | 3.182 | 75 | 2015-02-18 | 2015-05-03 | - | C | 0.44 | 0.133 | 0.3 | - | - | - | 87.3% | *87.3% Satisfactory
DELLOSA DESIGN - BUILD SERVICES | 11533 | L | A | MB | GE | Rehabilitation/Upgrading of Digos-Makar Road (Asphalt to Concrete) | General Santos City | 2015-11-17 | Final | Regional Office No. XII | LF | 101.4923 | 310 | 2015-04-15 | 2016-02-19 | (+) 48.23% | C | 0.442 | 0.136 | 0.3 | - | - | - | 87.8% | 87.8% Satisfactory
Dellosa Design-Build Services | 11533 | L | A | MA | GE | Widening of Jct. Digos-Buayan Airport Road, K1652+500 - K1653+375, Buayan Sect. K0+000 - K0+481, Buayan-Glan Sect. | General Santos City | 2014-10-29 | 1st | XII | LF | 46.0617 | 300 | 2014-01-26 | 2014-11-22 | 0.53% | O | 0.367 | 0.236 | 0.15 | 0.03 | 0.045 | 0.033 | 86.1% | 86.10% Satisfactory
Dellosa Design-Build Services | 11533 | L | A | MA | GE1 | Impv't. of Jct. GSC Circ. Rd., Makar-Tupi-Marbel Rd. (Geometric Control) | General Santos City | 2013-03-23 | 1st | XII | LF | 13.75 | 95 | 2013-01-14 | 2013-04-18 | -12.97 | O | 0.357 | 0.3 | 0.02 | 0.03 | 0.055 | 0.033 | 79.5 | -
DENISSE-JOHN CONSTRUCTION AND SUPPLIES | 37550 | L | B | SB | GB | Construction of Classroom in Areas Experiencing Acute Classroom Shortage, One (1) Storey, Two (2) Classroom School Building at Capisaan ES, Kasibu, Nueva Vizcaya | Kasibu, Nueva Vizcaya | 2015-09-04 | 1st & Final | NV 2nd DEO | LF | 2.015 | 120 | 2014-07-15 | 2014-11-11 | 0% | C | 0.473 | 0.133 | 0.3 | - | - | - | 90.6% | *90.6% Very Satisfactory
DENISSE-JOHN CONSTRUCTION AND SUPPLIES | 37550 | L | B | SB | GB | Construction/Rehabilitation of Aritao Rural Health Unit, Aritao, Nueva Vizcaya | Aritao, Nueva Vizcaya | 2015-09-04 | 1st & Final | NV 2nd DEO | LF | 1.492 | 180 | 2014-08-29 | 2015-02-24 | 37.06% | C | 0.469 | 0.133 | 0.3 | - | - | - | 90.2% | *90.2% Very Satisfactory
DENISSE-JOHN CONSTRUCTION AND SUPPLIES | 37550 | L | B | SB | GB | Construction of Barangay Multi-Purpose Building Dupax del Norte, Dupax Del Norte, Nueva Vizcaya | Dupax Del Norte, Nueva Vizcaya | 2015-09-03 | 1st & Final | NV 2nd DEO | LF | 1.875 | 90 | 2015-03-04 | 2015-06-01 | 0% | C | 0.47 | 0.133 | 0.3 | - | - | - | 90.3% | *90.3% Very Satisfactory
DENISSE-JOHN CONSTRUCTION AND SUPPLIES | 37550 | L | B | SB | GE | Construction of Baliling - Bacneg Farm to Market Road, Sta. Fe. Nueva Vizcaya | Sta. Fe. Nueva Vizcaya | 2015-09-04 | 1st & Final | NV 2nd DEO | LF | 1.955 | 60 | 2014-12-18 | 2015-02-15 | 0% | C | 0.405 | 0.2 | 0.3 | - | - | - | 90.5% | *90.5% Very Satisfactory
DENISSE-JOHN CONSTRUCTION AND SUPPLIES | 37750 | L | B | SB | GB | Construction of Kasibu Multi-Purpose Building, Kasibu, Nueva Vizcaya | Kasibu, Nueva Vizcaya | 2015-11-19 | Final | NUEVA VIZCAYA 2ND DEO | LF | 7.1213 | 90 | 2015-04-01 | 2015-06-30 | (+) 16.67 | C | 0.493 | 0.133 | 0.3 | - | - | - | 92.6% | 92.6% Very Satisfactory
DIADEMA ENTERPRISES | 16759 | L | B | SB | GB | Completion of 4 Storey, 12 Classroom School Building, Carlos Albert High School, Caloocan City | Caloocan City | 2015-06-03 | Final | Quezon City 2nd | LF | 5.397 | 84 | 2015-02-24 | 2015-05-18 | - | C | 0.472 | 0.133 | 0.3 | - | - | - | 90.5% | *90.5% Very Satisfactory
DICON BUILDERS CORP. | 33181 | L | A | SB | GE | Rehabilitation/Major Repair of Permanent Bridges at Manticao Bridge (BO1336MN) along Butuan City-Cagayan de Oro City-Iligan City Road, Manticao, Misamis Oriental | Manticao, Misamis Oriental | 2015-11-16 | Final | Misamis Oriental 2nd | LF | 4.6313 | 90 | 2015-02-02 | 2015-05-03 | 0.00% | C | 0.494 | 0.133 | 0.3 | - | - | - | 92.7% | 92.7% Very Satisfactory
DICON BUILDERS CORP. | 33181 | L | A | SB | GE | Rehabilitation/Major Repair of Permanent Bridge at Initao Bridge (BO1331MN) along Butuan City-Cagayan de Oro City-Iligan City Road, Initao, Misamis Oriental | Initao, Misamis Oriental | 2015-11-16 | Final | Misamis Oriental 2nd | LF | 7.3569 | 60 | 2015-02-02 | 2015-04-03 | 0.00% | C | 0.491 | 0.133 | 0.3 | - | - | - | 92.4% | 92.4% Very Satisfactory
DICON BUILDERS CORPORATION | 33181 | L | A | SB | GE | Construction/Rehabilitation of Flood Mitigation Facilities along Major River Basins, Construction of Slope Protection along Manticao Bridge Approaches "A" and "B" (Downstream and Upstream) (Phase I), Manticao, Misamis Oriental | Manticao, Misamis Oriental | 2015-06-08 | Final | Misamis Oriental Second DEO | LF | 9.087 | 130 | 2014-08-18 | 2014-12-25 | - | C | 0.482 | 0.133 | 0.3 | - | - | - | 91.5% | *86.7% Satisfactory
Dicon Builders, Corp. | 33181 | L | A | SB | GE | Const./Rehab. Of Flood Control Mitigation Facilities along Major River Basin Const. of Slope Protection along Manticao Approaches A & B (Downstream) (Phase I) | Manticao, Misamis Oriental | 2014-10-27 | 1st | X | LF | 8.2605 | 105 | 2014-08-18 | 2014-11-30 | 5.64% | O | 0.275 | 0.289 | 0.15 | 0.015 | 0.056 | 0.05 | 83.5% | 83.50% Satisfactory
DIGOS CONSTRAK CORPORATION | 36332 | L | D | SB | GE | Rehabilitation/ Reconstruction/ Upgrading of Damaged Paved National Roads including Drainage of Davao-Cotabato Road (Davao City-Jct. Digos Section) K1542+000 - k1542+049 | Davao del Sur | 2015-06-05 | Final | Davao del Sur 1st | LF | 0.869 | 45 | 2015-02-24 | 2015-04-09 | 0% | C | 0.41 | 0.133 | 0.3 | - | - | - | 84.3% | *84.3% Satisfactory
Digos Tesston Construction & Supplies | 8921 |  |  |  |  | Rehab./Reconst. of Damaged Paved National at Lipata, Surigao Del Norte-Davao City Highway through Marlika, Daang Maharlika Rd. (Agusan to Davao Rd.) Ilang-Tibungco Sect. |  | 2010-06-17 |  | XI |  | 19.29 | 113 |  |  |  | O | 0.361 | 0.24 | 0.15 | 0.03 | 0.047 | 0.05 | 87.8 | -
Digos Tesston Construction & Supplies (Formerly: ACT Construction) | 8921 | L | A | MA | GE | Construction/ Repair/ Rehabilitation/ Improvement of Various Infrastructure including Local Projects Road and Related Infrastructure Facilities for 2015 APEC Summit, Region XI-Local Roads, L. Ma. Guerrero Street, Junction Fatima to Gaisano/ San Pedro Hospital | Davao City | 2014-10-30 | 1st | XI | LF | 35.8634 | 190 | 2014-04-26 | 2014-11-01 | -9.92% | O | 0.349 | 0.297 | 0.051 | 0.03 | 0.055 | 0 | 78.2% | 78.20% Unsatisfactory
Digos Tesston Construction & Supplies (Formerly: ACT Construction) | 8921 | L | A | MA | GE | Rehab./Reconst./Replacement/Retrofitting of Waloe Bridge along Butuan City - Talacogon - Loreto - Veruela - Sta. Josefa Road, K1377+(-527) - K1377+(-402) | Loreto, Agusan del Sur | 2014-08-08 | 1st | XIII | LF | 24.4352 | 185 | 2014-02-06 | 2014-08-09 | -2.85 | O | 0.365 | 0.201 | 0.121 | 0.023 | 0.025 | 0.033 | 76.8 | -
Digos Tesston Construction & Supplies (Formerly: ACT Construction) | 8021 | L | A | MA | GE1 | Completion of Coronon Bridge I along Davao-Cotabato Rd., (Davao City Jct Digos Sect.) K1542+612.696-K1543+291.112 | Sta. Cruz, Davao del Sur | 2013-03-16 | 1st | XI | LF | 14.229 | 74 | 2013-01-28 | 2013-04-11 | 0.11 | O | 0.342 | 0.235 | 0.15 | 0.03 | 0.035 | 0.033 | 82.5 | -
Digos Tesston Construction & Supplies (Formerly: ACT Construction) | 8921 |  |  |  |  | Conc. Of Bansalan-Mt.Apo National Park Road, Managa-Buenavista Section |  | 2010-08-27 |  | XI |  | 9.907 | 210 |  |  |  | O | 0.333 | 0.29 | 0.15 | 0.03 | 0.043 | 0.033 | 87.9 | -
Digos Tesston Construction & Supplies (Formerly: Act Construction) | 8921 | L | A | MA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rd. (IS)/ Impv't. of Don Julian Rodriguez Ave. Leading to Davao Crocodile Park, Km.1509+(-328)-Km.1511+796, IS | Davao City | 2012-08-20 | 1st | XI | LF | 45.598 | 220 | 2012-01-29 | 2012-09-04 | 2.33 | O | 0.354 | 0.237 | 0.15 | 0.03 | 0.055 | 0.05 | 87.6 | -
Digos Tesston Construction & Supplies / TSK Builders & Supplies (JV) | JV-12-365 | L | A | MA | GE1 | Rd. Upgrading (Gravel to Paved) along Bansalan-Mt. Apo Nat'l Park Rd., K1584+(-234)-K1585+008 | Bansalan, Davao del Sur | 2013-03-16 | 1st | XI | LF | 28.001 | 93 | 2013-01-28 | 2013-04-30 | 1.02 | O | 0.368 | 0.212 | 0.15 | 0.03 | 0.04 | 0.033 | 83.3 | -
DIGOS TESTTON CONSTRUCTION & SUPPLY (Formerly: ACT Construction) | 8921 | L | A | MA | GE | Concreting of Roads, Colorado Pier Uno, Barangay Colorado, Digos City, Davao del Sur | Digos City, Davao del Sur | 2015-11-17 | Final | Davao del Sur 1st DEO | LF | 9.601e-06 | 120 | 2015-04-17 | 2015-08-14 | 0 | C | 0.421 | 0.198 | 0.3 | - | - | - | 91.9% | 91.9% Very Satisfactory
Dimaguila Construction and Supply Incorporated | 14904 | L | B | SB | GE | Asphalt Overlay of Santol Street, Chainage 0+000-Chainage 0+776; Chainage 0+776-Chainage 0+848 | Quezon City | 2014-11-28 | 1st | NCR | LF | 8.4683 | 90 | 2014-04-04 | 2014-07-02 | -35% | O | 0.387 | 0.2 | 0 | 0.03 | 0.052 | 0.033 | 70.2% | 70.20% Poor
Dimaguila Construction and Supply Incorporated | 14904 | L | B | SB | GE1 | Impv't./Conc. of Maginhawa St. (Sta.14+(-555)-Sta.14+(-338) | Quezon City | 2012-08-19 | 1st | NCR | LF | 8.868 | 163 | 2012-03-06 | 2012-08-15 | -9.44 | O | 0.35 | 0.3 | 0.056 | 0.03 | 0.035 | 0.033 | 80.4 | -
DINGO BUILDERS AND SUPPLY | 37794 | L | D | SB | GB | Construction of One Storey Two Classroom School Building Sta. Maria Integrated Secondary School, Tagbina, Surigao del Sur | Tagbina, Surigao del Sur | 2015-11-12 | 1st | Surigao del Sur 2nd DEO | LF | 1.7931 | 120 | 2015-08-03 | 2015-11-30 | (+) 6.26 | OG | 0.391 | 0.3 | 0.15 | 0.03 | 0.052 | 0.05 | 97.3% | 97.3% Outstanding
Dipolog Top Construction and Development Corporation | 6678 | L | A | MA | GE | Rehab./Reconst./Replacement/Retrofitting of Existing Permanent Bridge, Timan Bridge along Sindangan-Liloy Road | Liloy, Zamboanga del Norte | 2014-10-24 | 1st | IX | LF | 15.084 | 155 | 2014-05-15 | 2014-10-16 | -5% | O | 0.27 | 0.212 | 0.1 | 0.03 | 0.025 | 0.033 | 67% | 67.00% Poor
Dipolog Top Construction and Development Corporation | 6678 | L | A | MA | GE2 | Const. of Flood Control, Bolicon | Turno, Dipolog City | 2013-08-22 | 2nd | IX | LF | 29.844 | 255 | 2012-07-31 | 2013-04-10 | -9.04 | O | 0.329 | 0.3 | 0 | 0.02 | 0.042 | 0.033 | 72.4 | -
Dipolog Top Construction and Development Corporation | 6678 | L | A | MA | GE2 | Const. of Flood Control, Bolicon | Turno, Dipolog City | 2013-03-23 | 1st | IX | LF | 29.844 | 255 | 2012-07-31 | 2013-04-10 | -2.47 | O | 0.366 | 0.24 | 0.125 | 0.03 | 0.033 | 0.033 | 82.7 | -
Dipolog Top Construction and Development Corporation | 6678 | L | A | MA | GE1 | Const./Concrete Paving of Dipolog By Pass Road (Phase II) Turno-Galas-Sinaman Rd. | Dipolog City | 2013-03-23 | 1st | IX | LF | 34.592 | 255 | 2012-05-30 | 2013-02-08 | -0.95 | O | 0.364 | 0.238 | 0.141 | 0.03 | 0.042 | 0.033 | 84.8 | -
Dipolog Top Construction and Development Corporation | 6678 | L | A | MA | GE1 | Road Upgrading of Dipolog-Punta Dansullan-Sergio Osmeña Road |  | 2009-03-18 | 2nd | IX |  | 18.879 | 400 |  |  |  | O | 0.38 | 0.263 | 0.15 | 0.03 | 0.048 | 0.05 | #VALUE! | -
Dipolog Top Construction and Development Corporation | 6678 | L | A | MA | GE2 | Const. of River Bank Protection Work/River Control | Estaka Side, Dipolog City | 2012-08-24 | 1st | IX | LF | 8.568 | 253 | 2011-12-16 | 2012-08-24 | -1.5 | O | 0.384 | 0.24 | 0.135 | 0.03 | 0.044 | 0.033 | 86.6 | -
DJCM Construction | 27678 | L | C | SB | GB1 | Const. of Hall of Justice | Luna, Apayao | 2013-08-12 | 1st | CAR | LF | 4.606 | 170 | 2013-03-27 | 2013-09-12 | 0.2 | O | 0.38 | 0.24 | 0.15 | 0.015 | 0.047 | 0.05 | 88.2 | -
DJCM CONSTRUCTION | 27678 | L | B | MA | GE | Road Leading to Laoag-La Paz Sand Dunes | Laoag City, Ilocos Norte | 2015-06-03 | 1st | Ilocos Norte 1st DEO | LF | 12.556 | 121 | 2015-03-13 | 2015-07-11 | 1.48% | O | 0.243 | 0.293 | 0.15 | 0.03 | 0.055 | 0.033 | 80.4% | -
DJCM CONSTRUCTION | 27678 | L | B | MA | GE | Road Leading to Laoag-La Paz San Dunes, Laoa City, Ilocos Norte | Laoa City, Ilocos Norte | 2015-08-25 | Final | Ilocos Norte 1st DEO | LF | 12.556 | 121 | 2015-03-13 | 2015-07-12 | (+)4.25 | C | 0.408 | 0.2 | 0.3 | - | - | - | 90.8% | *84.56% Satisfactory
DJCM Construction | 27678 | L | B | SB |  | Resto/ Rehab of Zanjera Pideng-Tartarabang CIS (Phase-1) | Pinili, Ilocos Norte | 2016-04-16 | 1st | NIA | LF | 12.042 | 180 | 2015-11-12 | 2016-04-14 | -5.44 | O | 0.3618 | 0.2438 | 0.0956 | 0.012 | 0.0318 | 0.05 | 79.5 | -
DJY Construction / E.K.C. Construction and Aggregates (JV) | JV-12-089 | L | B | MA | GE1 | Impv't. of Bengaw-ngaw Caves Rd., Sta. 0+000-Sta. 2+500 (v.s.), Ambongdolan | Tublay, Benguet | 2013-03-14 | 1st | CAR | LF | 18.984 | 180 | 2012-11-10 | 2013-05-08 | -0.12 | O | 0.366 | 0.24 | 0.149 | 0.03 | 0.055 | 0.05 | 89 | -
DL Enterprises | 18155 | L | A | MA | GE | Const. of Pedestrian Overpass (Bridge) | Brgy. Carmen, Cagayan de Oro City | 2014-10-20 | 1st | X | LF | 3.9925 | 150 | 2014-06-30 | 2014-11-26 | 1.12% | O | 0.322 | 0.3 | 0.15 | 0.01 | 0.042 | 0.05 | 87.4% | 87.40% Satisfactory
DL Enterprises | 18155 | L | B | MA | GE1 | Const. of Tangub City-Don Victoriano Road, Tangub City Section |  | 2009-03-17 | 2nd | X |  | 22.914 | 723 |  |  |  | O | 0.331 | 0.3 | 0.15 | 0.03 | 0.045 | 0.05 | #VALUE! | -
DL ENTERPRISES | 18155 | L | A | MA | GE | Construction of Pedestrian Overpass (Bridge), Barangay Carmen, Cagayan de Oro City | Barangay Carmen, Cagayan de Oro City | 2015-06-11 | Final | Cagayan de Oro City First DEO | LF | 3.993 | 240 | 2014-06-30 | 2015-02-24 | - | C | 0.475 | 0.2 | 0.3 | - | - | - | 97.5% | *97.5% Outstanding
Domarax Construction and Development | 5502 |  |  |  |  | Conc. of Roads, Brgy. Del Rosario |  | 2010-06-07 |  | XIII |  | 1.398 | 117 |  |  |  | O | 0.395 | 0.24 | 0.15 | 0.03 | 0.035 | 0.033 | 88.3 | -
Domarax Construction and Development | 5502 |  |  |  |  | Conc. of Road Protection Tubod, Brgy. Poblacion |  | 2010-06-07 |  | XIII |  | 0.978 | 115 |  |  |  | O | 0.367 | 0.245 | 0.15 | 0.03 | 0.035 | 0.033 | 86 | -
Domarax Construction and Development | 5502 |  |  |  |  | Road Upgrading (Gavel to Concrete) Surigao City-San Juan Coastal Road |  | 2010-06-07 |  | XIII |  | 5.199 | 150 |  |  |  | O | 0.347 | 0.24 | 0.15 | 0.03 | 0.035 | 0.033 | 83.5 | -
Double L Construction and Development Enterprises | 9834 | L | A | MB | GE1 | Rehab./ Reconst./ Upgrading Dumaguete North, Mainit-Ajong Road Section |  | 2009-09-12 | 1st | VII |  | 38.32 | 280 |  |  |  | O | 0.387 | 0.3 | 0.15 | 0.03 | 0.042 | 0.05 | 95.9 | -
Double L Construction and Development Enterprises | 9834 |  |  |  |  | Const./Impvt. of Dumaguete North Road (Intemittent Sections) a) Himampangon Section, Manjuyod: Km. 62.720-Km.63.233; b) Manjuyod Section: Km.52+971-Km. 54.000; c) Tayasan Section: Km. 92.761 |  | 2010-09-09 |  | VII |  | 63.69 | 330 |  |  |  | O | 0.323 | 0.3 | 0 | 0.03 | 0.061 | 0.05 | 76.4 | -
Double MM Builders | 33758 | L | D | SB | GB1 | Const. of DepEd Standard Type Sch. Bldg. @ Cauayan NHS | Cauayan, Negros Occidental | 2013-08-09 | 1st | VI | LF | 2.283 | 95 | 2013-05-24 | 2013-08-26 | -1.78 | O | 0.357 | 0.212 | 0.132 | 0.03 | 0.043 | 0.05 | 82.4 | -
DQT Builders Corporation | 7950 | L | A | MA | GE-5 | Development of Quezon Port | Quezon, Quezon/ Region IV-A | 2015-09-03 | 1st | DOTC | LF | 18.48 | 270 | 2015-07-16 | 2016-04-10 | 23.46 | O | 0.3236 | 0.3 | 0.15 | 0.03 | 0.0466 | 0.05 | 90.02 | -
DQT Builders Corporation | 7950 | L | A | MA | GE | Widening of Daang Maharlika with exception, K0117+566 to K0121+896, Siriaya Section, Quezon 2nd LD | Siriaya, Quezon | 2014-08-13 | 1st | IV-A | LF | 35.828 | 180 | 2014-03-28 | 2014-09-23 | 0.27 | O | 0.384 | 0.3 | 0.15 | 0.03 | 0.032 | 0.033 | 92.9 | -
DQT Builders Corporation | 7950 |  | A | MA |  | Development of Quezon Port | Quezon, Quezon/ Region IV-A | 2016-02-11 | 2nd | DOTC | LF | 18.48 | 270 | 2015-07-16 | 2016-04-10 | 8.11 | O | 0.3673 | 0.3 | 0.15 | 0.03 | 0.0466 | 0.05 | 94.39 | -
DQT Builders Corporation | 7950 | L | A | MA |  | Development of Quezon Port | Quezon, Quezon/ Region IV-A | 2016-06-22 | 3rd & Final | DOTC | LF | 18.48 | 270 | 2015-07-16 | 2016-04-10 | 0 | C | 0.3619 | 0.2 | 0.3 | - | - | - | 86.19 | 89.80% V. Satisfactory
DQT BUILDERS CORPORATION (Formerly: DQT Buidlers) | 7950 | L | A | MB | GE | Rehabilitation/Reconst./Upgrading of Marinduque Circumferential Road K0017+000-K0018+000 w/e, K0022+000-K0022+883 w/e, K0041+000-K0044+000 w/e, K0059+000-K0061+000 w/e, K0062+162-K0062+700 w/e, K0067+063-K0068+000 w/e, K0086+000-K0087+505, Marinduque | Marinduque | 2015-09-01 | 1st & Final | Marinduque DEO | LF | 17.856 | 109 | 2015-02-19 | 2015-06-07 | - | C | 0.454 | 0.133 | 0.3 | - | - | - | 88.7% | *88.7% Satisfactory
DQT Builders Corporation (Formerly: DQT Builders) | 7950 | L | A | MA | GE1 | Rd. Upgrading (Concrete Paving) of Mulanay-San Francisco Rd., K0287+115-K0288+000 | Quezon | 2013-08-07 | 1st | IVA | LF | 20 | 180 | 2013-03-11 | 2013-09-06 | 0.07 | O | 0.303 | 0.284 | 0.15 | 0.03 | 0.03 | 0.033 | 83 | -
DQT Builders Corporation (Formerly: DQT Builders) | 7950 | L | A | MA | GE1 | Rd. Upgrading (Concrete Paving) Mulanay-San Francisco Rd., K0288+000-K0289+102 | Quezon | 2013-08-07 | 1st | IVA | LF | 24.847 | 180 | 2013-03-11 | 2013-09-06 | 0.08 | O | 0.283 | 0.3 | 0.15 | 0.03 | 0.03 | 0.033 | 82.6 | -
DQT Builders Corporation (Formerly: DQT Builders) | 7950 | L | A | MA | GE1 | 1. Assets Preservation of Nat'l Rds., Intermittent Sect,; A. Prev. Maint.; 1. Nat'l. Arterial (Prev. Maint.); 1. Daang Maharlika; D. K0182+500-K0185+481 | Quezon | 2013-03-19 | 1st | IVA | LF | 36.599 | 120 | 2013-02-12 | 2013-06-11 | 20.05 | O | 0.386 | 0.198 | 0.15 | 0.03 | 0.047 | 0.033 | 84.4 | -
DQT Builders Corporation (Formerly: DQT Builders) | 7950 | L | A | MA | GE1 | Repair/Rehab. of Service Road, Sta. Cruz RIS | Pila, Laguna | 2011-08-10 | 1st | IVA | LF | 9.36 | 120 | 2011-06-09 | 2011-10-07 | 20.15 | O | 0.011 | 0.107 | 0.15 | 0.02 | 0.025 | 0.033 | 34.6 | -
DQT Builders Corporation (Formerly: DQT Builders) | 7950 | L | A | MA | GE1 | Rehab./Reconst./Upgrading of MCR (Km.101+000-Km.103+814 & Km.99+741-Km.100+072) (Gasan Sect.) | Gasan, Marinduque | 2013-08-08 | 2nd | IVB | LF | 46.713 | 213 | 2013-01-25 | 2013-08-25 | -0.97 | O | 0.339 | 0.291 | 0.14 | 0.015 | 0.03 | 0.033 | 84.8 | -
DQT Builders Corporation (Formerly: DQT Builders) | 7950 | L | A | MA | GE1 | Rehab./Reconst./Upgrading of MCR (Km.101+000-Km.103+814 & Km.99+741-Km.100+072) (Gasan Sect.) | Gasan, Marinduque | 2013-03-23 | 1st | IVB | LF | 46.713 | 160 | 2013-01-25 | 2013-07-03 | 25.45 | O | 0.384 | 0.24 | 0.15 | 0.03 | 0.055 | 0.033 | 89.2 | -
DQT BUILDERS CORPORATION (Formerly: DQT Builders) | 7950 | L | A | MA | GE | Network Development - Off Carriageway Improvement Paving of Shoulder along Tayabas - Mainit - Mauban Road, K0141+580- K0143+528, K0143+606- K0144+648, K0144+656-K0145+166 | Quezon | 2015-06-09 | 1st | Quezon 1st DEO | LF | 34.971 | 180 | 2015-04-10 | 2015-10-06 | 0.85% | O | 0.381 | 0.237 | 0.15 | 0.024 | 0.03 | 0.033 | 85.5% | -
DQT Builders Corpration (Formerly: DQT Builders) | 7950 | L | A | MA | GE1 | Const. of Lucban Overpass SLSU along Lucena-Tayabas-Lucban-Sampaloc-Mauban Port Rd. | Lucban, Quezon | 2013-08-08 | 1st | IVA | LF | 8.932 | 150 | 2013-02-26 | 2013-07-25 | 20.37 | O | 0.357 | 0.212 | 0.15 | 0.03 | 0.023 | 0.05 | 82.2 | -
DREAMWORX BUILDERS & TRADING INC. | 34004 | L | C | SB | GB | Improvement of Ibajay Public Market | Ibajay, Aklan | 2015-06-05 | 1st | Aklan DEO | LF | 1.945 | 72 | 2015-04-16 | 2015-06-26 | 3.64% | O | 0.395 | 0.199 | 0.15 | 0.02 | 0.029 | 0.033 | 82.6% | -
DS Pamintuan Construction | 31868 | L |  |  | GE2 | Rehab. Of Murcon Dam D/S Apron @ Division II Service Area | Minabuyoc, Talavera, Nueva Ecija / Region III | 2013-07-27 | 1st | NIA | L | 35.824 | 120 | 2013-01-11 | 2013-07-31 | 2 | O | 0.364 | 0.2844 | 0.15 | 0.02 | 0.056 | 0.05 | 92.44 | -
DSB Construction & Supply, Inc. | 16126 | L | AA | MB | GE1 | Road Upgrading of San Fernando North Road (San Fernando Sect.) Km. 2+070-Km. 3+070 | San Fernando, Masbate | 2011-08-11 | 1st | V | LF | 20.888 | 150 | 2011-06-22 | 2011-11-20 | 2.28 | O | 0.357 | 0.237 | 0.15 | 0.03 | 0.025 | 0.033 | 83.2 | -
DSB Construction & Supply, Inc. | 16126 | L | B | MA | GB1 | Construction of Multi-Purpose Building |  | 2009-09-08 | 1st | V |  | 9.553 | 189 |  |  |  | O | 0.289 | 0.3 | 0.15 | 0.03 | 0.043 | 0.033 | 84.5 | -
DSB Construction & Supply, Inc. | 16126 | L | B | MA | GE1 | San Vicente-San Carlos Road Linking Tabaco-Ligao to Legazpi-Tabaco-Tiwi Road |  | 2009-09-01 | 2nd | V |  | 38.4 | 390 |  |  |  | O | 0.314 | 0.256 | 0.15 | 0.03 | 0.037 | 0.05 | 83.7 | -
DSB Construction & Supply, Inc. | 16126 |  |  |  |  | Repair of Bridge Approach/Abutment Protection and Rechannelization of River Course, Taboc Bridge & along Juban Magallanes Road |  | 2010-02-16 |  | V |  | 4.77 | 83 |  |  |  | O | 0.321 | 0.24 | 0.15 | 0.015 | 0.035 | 0.033 | 79.4 | -
DSB Construction & Supply, Inc. (Formerly: DSB Construction & Supply) | 16126 | L | AA | MB | GE1 | Package I, Repair/Rehab./Impvt. of Daan Maharlika Nat'l Rd., San Rafael, Castilla & Repair/Rehab./Impvt. of Daang Maharlika Nati'l Rd., San Vicente | Castilla, Sorsogon | 2013-08-14 | 1st | V | LF | 23.554 | 180 | 2013-03-25 | 2013-09-20 | 3.05 | O | 0.353 | 0.276 | 0.15 | 0.03 | 0.035 | 0.033 | 87.7 | -
DSB Construction & Supply, Inc. (Formerly: DSB Construction & Supply) | 16126 | L | AA | MA | GE2 | Const./Rehab./Impv't. of Basud River Control, Brgy, Basud | Bacacay, Albay | 2013-08-12 | 1st | V | LF | 18.139 | 200 | 2013-02-12 | 2013-08-30 | -9.89 | O | 0.368 | 0.3 | 0.051 | 0.03 | 0.055 | 0.033 | 83.7 | -
DSB Construction & Supply, Inc. (Formerly: DSB Construction & Supply) | 16126 | L | AA | MB | GE1 | Const. of Sta. Misericordia Bridge No. 1 | Sto. Domingo, Albay | 2013-03-18 | 2nd | V | LF | 5.106 | 344 | 2012-05-14 | 2013-04-20 | -1.55 | O | 0.37 | 0.24 | 0.134 | 0.024 | 0.06 | 0.05 | 87.8 | -
DSB Construction & Supply, Inc. (Formerly: DSB Construction & Supply) | 16126 | L | AA | MB | GE1 | Const. of Sta. Misericordia Bridge No. 1 | Sto. Domingo, Albay | 2012-11-22 | 1st | V | LF | 5.106 | 209 | 2012-05-14 | 2012-12-09 | -3.95 | O | 0.374 | 0.271 | 0.111 | 0.03 | 0.052 | 0.05 | 88.8 | -
DSB Construction & Supply, Inc. (Formerly: DSB Construction & Supply) | 16126 |  |  |  |  | Const. of Double Barrel Box Culvert Tramo Road |  | 2010-05-28 |  | V |  | 4.794 | 180 |  |  |  | O | 0.373 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 89.3 | -
DSB Construction & Supply, Inc. (Formerly: DSB Construction & Supply) | 16126 |  |  |  |  | Rehab./Reconst. of Gahonon Road Brgy. Gahonon, (KO 342+442 - KO 342+618) |  | 2010-06-10 |  | V |  | 12.984 | 145 |  |  |  | O | 0.35 | 0.24 | 0.15 | 0.03 | 0.04 | 0.033 | 84.3 | -
DSB Construction & Supply, Inc. (Formerly: DSB Construction & Supply) | 16126 | L | AA | MB | GE | Repair/Rehab./Improvement (Additional Pavement Width) Along Daang Maharlika K0555+903 with exceptions and K0557+000-K0557+800 with exceptions | San Rafael-San Isidro, Castilla | 2014-11-16 | 1st | V | LF | 10.8625 | 135 | 2014-08-12 | 2014-12-24 | 4% | O | 0.354 | 0.237 | 0.15 | 0.03 | 0.035 | 0.033 | 83.9% | 83.90% Satisfactory
DSB CONSTRUCTION & SUPPLY, INC. (Formerly: DSB Construction & Supply) | 16126 | L | AA | MA | GE | Drainage Protection along Mt. Mayon Park Road, Buang Section, K0521+500 to K0525+500 w/ Exceptions | Brgy. Buang, Tabaco City | 2015-06-01 | 1st | Albay 1st | LF | 17.237 | 162 | 2015-04-10 | 2015-09-18 | 1.96% | O | 0.37 | 0.291 | 0.15 | 0.018 | 0.051 | 0.05 | 93% | -
DSB CONSTRUCTION & SUPPLY, INC. (Formerly: DSB Construction & Supply) | 16126 | L | AA | MB | GE | Concreting of Road, Shoulder, P-3 San Jose St., Malinao, Albay | Malinao, Albay | 2015-11-17 | Final | Albay First DEO | LF | 1.8427 | 156 | 2015-03-11 | 2015-08-13 | 19.05% | C | 0.376 | 0.147 | 0.3 | - | - | - | 82.3% | 82.3% Satisfactory
DSB Construction and Supply | 16126 | L | B | MA | GE1 | Conc. of Bical Road |  | 2008-08-12 | 2nd | V |  | 14.163 | 120 |  |  |  | O | 0.318 | 0.24 | 0.07 | 0.03 | 0.028 | 0.067 | 75.3 | -
DSB Construction and Supply, Inc. | 16126 | L | A | MB | GE1 | Conc. of San Fernardo North Road |  | 2009-03-01 | 1st | V |  | 18.898 | 270 |  |  |  | O | 0.356 | 0.236 | 0.15 | 0.03 | 0.056 | 0.05 | #VALUE! | -
DSB Construction and Supply, Inc. | 16126 | L | D | MB | GB1 | Completion of Multi-Purpose Building Phase VII |  | 2009-02-24 | 1st | V |  | 7.188 | 160 |  |  |  | O | 0.391 | 0.24 | 0.15 | 0.03 | 0.056 | 0.05 | #VALUE! | -
DSJP Construction | 30643 | L |  |  |  | Improving the Existing Facilities of PSHS-CV | Talaytay, Argao Cebu | 2016-06-30 | FInal | DOST | LF | 10.587 | 180 | 2015-06-04 | 2015-11-30 | 0 | C | 0.484 | 0.2 | 0.3 | - | - | - | 98.4 | 92.00% Very Satisfactory
DSJP Construction | 30643 | L |  |  |  | Rehabilitation of Dormitory Building for Boys | Talaytay, Argao Cebu | 2016-06-30 | Final | DOST | LF | 6.121 | 120 | 2015-04-24 | 2015-09-05 | 0 | C | 0.4876 | 0.2 | 0.3 | - | - | - | 98.76 | 94.00% Very Satisfactory
DSO ENTERPRISES | 10733 | L | B | MA | GB | Construction of Multi-Purpose Building | Brgy. Asufre, Pangil, Laguna | 2015-08-27 | 1st & Final | Laguna 1st | LF | 3.982 | 90 | 2015-02-12 | 2015-05-12 | 0% | C | 0.478 | 0.133 | 0.3 | - | - | - | 91.1% | *91.1% Very Satisfactory
Dungan Constructors and Trading Corp. | 19301 | L | D | MA | GE1 | Const./Rehab. of Drainage System & other Facilities & Structures, Brgy. Tunasan | Muntinlupa City, Metro Manila | 2012-11-28 | 1st | NCR | LF | 7.038 | 90 | 2012-05-18 | 2012-08-15 | 0.64 | O | 0.263 | 0.3 | 0.15 | 0.02 | 0.043 | 0.05 | 82.6 | -
Duros Development Corp. | 7494 | L | AAA | LA | GE | Rehabilitation of Road from Brgy. Curva, Medellin to Brgy. Poblacion, Daan - Bantayan Leading to Maya Roro Port to Malapascua Island, Sta. 111+952.67 to Sta. 117+500 | Cebu Province | 2014-10-22 | 1st | VII | LF | 127.4012 | 240 | 2014-05-15 | 2015-01-09 | -11.11% | O | 0.339 | 0.3 | 0.039 | 0.03 | 0.05 | 0 | 75.8% | 75.80% Unsatisfactory
DUROS DEVELOPMENT CORP. | 22729 | L | AAA | LA | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Road including Drainage along Cebu North Hagnaya Wharf Road: K0092+195 - K0093+000; K0094+113 - K0094+257; K0094+257 - K0094+457, Cebu North Hagnaya Wharf Road | Cebu North Hagnaya Wharf Road | 2015-11-13 | Final | Cebu 1st | LF | 19.8264 | 209 | 2015-03-03 | 2015-09-27 | 0 | C | 0.404 | 0.133 | 0.3 | - | - | - | 83.7% | 83.7% Satisfactory
Duros Development Corporation | 22729 | L | AAA | SB | GE2 | Guiwanon Revetment along Toledo-Tabuelan Rd., K0106+179 | Tabuelan, Cebu | 2012-11-27 | 1st | VII | LF | 1.476 | 63 | 2012-10-25 | 2012-12-26 | 0.03 | O | 0.24 | 0.3 | 0.15 | 0.03 | 0.05 | 0.05 | 82 | -
Duros Development Corporation | 22729 | L | AA | LA | GE1 | Concreting of Baloc-Isabela Rd. |  | 2009-09-14 | 2nd | VII |  | 14.22 | 260 |  |  |  | O | 0.396 | 0.24 | 0.15 | 0.022 | 0.037 | 0.033 | 87.8 | -
Duros Development Corporation | 22729 | L | AA | LB | GE1 | Impvt./Conc. of Access Road to RORO Port at Maya-Daan Bantayan Road |  | 2009-09-01 | 2nd | VII |  | 19.005 | 162 |  |  |  | O | 0.247 | 0.3 | 0.106 | 0.03 | 0.045 | 0.033 | 76.1 | -
DUROS DEVELOPMENT CORPORATION | 22729 | L | AAA | LA | GE | Rehabilitation of Road from Brgy. Curva, Medelin to Brgy. Poblacion, Daan-Bantayan Leading to Maya Roro Port to Malapascua Island, Sta. 111+952.67- Sta. 117+500, Cebu Province | Maya Roro Port to Malapascua | 2015-06-06 | Final | Regional Office No. VII | LF | 127.401 | 290 | 2015-05-15 | 2016-02-28 | 0% | C | 0.479 | 0.197 | 0.3 | - | - | - | 97.6% | *84.52% Satisfactory
DUROS DEVELOPMENT CORPORATION | 22729 | L | AAA | LA | GE | Rehab/Reconst/Upgrading of Damaged Paved National Road Including Drainage along North Hagnaya Wharf Road: K0082+116 to K0084+000; K0086+000 to K0086+870 Intermittent Sections, Tabogon, Cebu | Cebu North Hagnaya Wharf Road, Tabogon, Cebu | 2015-06-06 | 1st | Cebu First DEO | LF | 44.782 | 179 | 2015-03-03 | 2015-08-28 | 0% | O | 0.363 | 0.247 | 0.15 | 0.03 | 0.047 | 0.033 | 87% | -
DUROS DEVELOPMENT CORPORATION | 22729 | L | AAA | LA | GE | Rehab./Reconst./Upgrading of Damaged Paved National Road Including Drainage along Cebu, North Hagnaya Wharf Road: K0092+195 to K0093+000; K0094+113 to K0094+257; K0094+257 to K0094+457 | Cebu North Hagnaya Wharf Road, Tabogon, Cebu | 2015-06-06 | 1st | Cebu First | LF | 19.826 | 179 | 2015-03-03 | 2015-08-28 | 0.2% | O | 0.345 | 0.25 | 0.15 | 0.03 | 0.047 | 0.033 | 85.5% | -
DYNAMIC BUILDERS | 34227 | L | D | SB | GE | Construction of River Dike for Flood Control | Barangay Kauswagan, Cabadbaran City, Agusan Del Norte | 2015-06-02 | 1st | AGUSAN DEL NORTE DEO | LF | 4.681 | 122 | 2014-02-12 | 2014-06-13 | (+) 0.99% | O | 0.395 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 91.5% | -
Dynamic Builders & Construction Co. (Phil) Inc. | 24712 |  |  |  |  | Rehab./Reconst./Upgrading along Bacolod City Bdry. Rd. Km.2+555 - Km.5+092 w/ exceptions |  | 2010-06-07 |  | VI |  | 37.772 | 270 |  |  |  | O | 0.315 | 0.238 | 0.15 | 0.03 | 0.056 | 0.05 | 83.9 | -
Dynamic Builders & Construction Co. (Phil) Inc. | 24712 | L | AAA | LA | GE1 | Rehab. of Bacolod South Road (Caradio-An Section) |  | 2009-05-28 | 1st | VI |  | 42.774 | 392 |  |  |  | O | 0.396 | 0.24 | 0.15 | 0.03 | 0.06 | 0.05 | 92.6 | -
Dynamic Builders & Construction Co. (Phil) Inc. | 24712 | L | AAA | LA | GE1 | Rehab./Recons/Upgrading of Concreting of Bacolod North road, Caduha-an Section |  | 2009-05-26 | 1st | VI |  | 18.331 | 140 |  |  |  | O | 0.355 | 0.3 | 0.13 | 0.03 | 0.045 | 0.05 | 91 | -
Dynamic Builders & Construction Co. (Phil) Inc. | 24712 | L | AAA | LA | GE1 | Rehab./Reconst./Upgrading along Bacolod-San Carlos Road, Km. 3+990-Km. 13+610 with exception |  | 2009-09-12 | 2nd | VI |  | 20.8 | 235 |  |  |  | O | 0.32 | 0.3 | 0.15 | 0.03 | 0.055 | 0.05 | 90.5 | -
Dynamic Builders & Construction Co. (Phil.), Inc. | 24712 | L | AAA | LA | GE1 | Impv't./Widening of Bacolod-Murcia-D.S. Benedicto-San Carlos City Rd., (Murcia Sect.), Km.17+260-Km.029+860 (w/ exceptions) | Murcia, Negros Occidental | 2013-08-13 | 3rd | VI | LF | 189.98 | 525 | 2012-07-09 | 2013-12-15 | 1.7 | O | 0.335 | 0.237 | 0.15 | 0.03 | 0.047 | 0.05 | 84.9 | -
Dynamic Builders & Construction Co. (Phil.), Inc. | 24712 | L | AAA | LA | GE1 | Impv't./Widening of Bacolod-Murcia-D.S. Benedicto-San Carlos City Rd. (Murcia Sect.), Km.17+260-Km.29+860 (w exceptions) | Murcia, Negros Occidental | 2013-03-15 | 2nd | VI | LF | 180.602 | 480 | 2012-07-09 | 2013-10-31 | 7.24 | O | 0.351 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 87.6 | -
Dynamic Builders & Construction Co. (Phil.), Inc. | 24712 | L | AAA | LA | GE1 | Impv't./Widening of Bacolod-Murcia-D.S. Benedicto-San Carlos City Rd. (Murcia Sect.), Km.17+260-Km.0029+860 w/ exceptions | Murcia, Negros Occidental | 2012-11-27 | 1st | VI | LF | 180.602 | 480 | 2012-07-09 | 2013-10-30 | 4.56 | O | 0.38 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 90 | -
Dynamic Builders & Construction Co. (Phil.), Inc. | 24712 | L | AAA | LA | GE1 | Impv't. of Bacolod-Mucia-D.S. Benedicto-San Carlos City Rd. & Slope Protection, Km.42+400-Km.52+760 (Road), Km.71+933-Km.75+855 (Coconet) | Negros Occidental | 2013-03-15 | 2nd | VI | LF | 94.398 | 360 | 2012-04-23 | 2013-04-16 | -3.51 | O | 0.366 | 0.24 | 0.115 | 0.03 | 0.06 | 0.033 | 84.4 | -
Dynamic Builders & Construction Co. (Phil.), Inc. | 24712 | L | AAA | LA | GE1 | Impv't. of Bacolod-Murcia-D.S. Benedicto-San Carlos City Rd. & Slope Protection Km.42+400-Km. 52+760 (Rd.), Km.71+933-Km.75+855 (Coconet), D.S. Benedicto-San Carlos City Rd. | Negros Occidental | 2012-11-27 | 1st | VI | LF | 94.398 | 360 | 2012-04-23 | 2013-04-16 | 1.31 | O | 0.325 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 85 | -
E E I Corporation | 333 | L | AAA | LB | GE1 | NAIA Expressway and its Related Roads Project, Phase I, Package IV-A, Sales St. Viaduct and Ramp Structure (MSE Retaining Wall) |  | 2009-03-12 | 2nd | URPO |  | 368.005 | 270 |  |  |  | O | 0.364 | 0.3 | 0 | 0.03 | 0.065 | 0.05 | #VALUE! | -
E F C Enterprises | 11795 | L | AA | MA | GB1 | Const. of Four (4) Storey, Sixteen (16) CL Sch. Bldg. at Muntinlupa NHS, Brgy. Pob. | Muntinlupa City | 2013-08-14 | 1st | NCR | LF | 28.943 | 240 | 2013-05-31 | 2014-01-25 | 14.22 | O | 0.305 | 0.24 | 0.15 | 0.03 | 0.041 | 0.033 | 79.9 | -
E F C Enterprises | 11795 | L | AA | MB | GE2 | Const. of Slope Protection, Zapote River Impvt. Proj., Phase III | Las Piñas City, Metro Manila | 2012-11-28 | 1st | NCR | LF | 12.295 | 331 | 2012-01-24 | 2012-12-19 | 1.3 | O | 0.287 | 0.298 | 0.15 | 0.03 | 0.045 | 0.05 | 86 | -
E F C Enterprises | 11795 | L | AA | MB | GE2 | Riprapping of Creek Near (Phase II), Brgy. B.F. Homes | Parañaque City, Metro Manila | 2012-08-02 | 1st | NCR | LF | 2.421 | 74 | 2012-05-25 | 2012-08-06 | 3.03 | O | 0.297 | 0.24 | 0.15 | 0.03 | 0.04 | 0.033 | 79 | -
E F C Enterprises/B.M.K. Construction (JV) | JV-08-321 | L | AA | MB | GE1 | Const./Widening of Katihan/NBP Bridge, SLEX, Brgy. Pob. | Muntinlupa City, Metro Manila | 2012-11-26 | 1st | NCR | LF | 55.86 | 356 | 2011-12-28 | 2012-12-17 | 0.28 | O | 0.38 | 0.292 | 0.15 | 0.03 | 0.042 | 0.033 | 92.7 | -
E G & I CONSTRUCTION CORPORATION | 16225 | L | A | MA | GE | Installation of Center Island Median at A.C. Cortes Avenue Including Landscaping at A.C. cortes Avenue, Mandaue City | Mandaue City, Cebu | 2015-06-01 | Final | Cebu Sixth DEO | LF | 26.749 | 176 | 2015-05-09 | 2015-10-31 | 0% | C | 0.457 | 0.169 | 0.3 | - | - | - | 92.6% | *92.6% Very Satisfactory
E M L Construction & Trading | 10151 | L | A | MA | GE1 | Widening/Conc. of McArthur Highway MNR inc. Drainage and Traffic Mgt. @ K083+580-K0094+000 (w/ exceptions) | Angeles City | 2013-08-06 | 1st | III | LF | 44.024 | 214 | 2013-03-05 | 2013-10-04 | 43.99 | O | 0.358 | 0.24 | 0.15 | 0.03 | 0.051 | 0.033 | 86.2 | -
E M L Construction & Trading | 10151 | L | A | MA | GE1 | Const. and Repair of Drainage System along Old Manila North Rd. (OMNR) | Balanga City, Bataan | 2013-08-07 | 1st | III | LF | 22.501 | 180 | 2013-02-26 | 2013-08-24 | 0.73 | O | 0.354 | 0.24 | 0.15 | 0.03 | 0.051 | 0.033 | 85.8 | -
E M L Construction & Trading | 10151 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rds. along Gapan-San Fernando-Olongapo Rd., Km. 0069+000-Km. 0070+000, Km. 0071+(-445-Km. 071+0000125+080-K0125+962 | San Fernando City, Pampanga | 2012-11-19 | 1st | III | LF | 39.453 | 300 | 2012-03-17 | 2013-01-11 | 0.15 | O | 0.325 | 0.293 | 0.15 | 0.03 | 0.05 | 0.05 | 89.8 | -
E S De Guzman Construction | 17494 | L | B | MA | GE | Construction of Classroom in Areas Experiencing Acute Classroom Shortage, Cordon E/S, One (1) Storey, One (1) Classroom, SB, Cordon | Cordon, Kasibu, Isabela | 2014-10-30 | 1st | II | LF | 1.1423 | 90 | 2014-07-15 | 2014-10-12 |  | O | 0.398 | 0.224 | 0.15 | 0.03 | 0.011 | 0.033 | 84.6% | 84.60% Satisfactory
E S De Guzman Construction | 17494 | L | B | SB | GB1 | Const. of Classroom, Bambang NHS | Bambang, Nueva Vizcaya | 2013-08-13 | 1st | II | LF | 4.59 | 150 | 2013-04-10 | 2013-09-16 | 0.55 | O | 0.367 | 0.24 | 0.15 | 0.03 | 0.052 | 0.033 | 87.2 | -
E S De Guzman Construction | 17494 | L | B | MA | GB1 | Construction of Multipurpose Bldg. |  | 2009-04-16 | 1st | DOST |  | 30.986 | 120 |  |  |  | O | 0.361 | 0.264 | 0.15 | 0.03 | 0.052 | 0.05 | 90.7 | -
E S DE GUZMAN CONSTRUCTION | 17494 | L | B | SB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Pved National Roads including Drainage Based on Pavement Management System/Highway Development and Management-4 (HDM-4) (Inter,ittent Sections), Bam-Kas-Que-Sol Road, K0281+000 to K0281+208, Poblacion, Ka | Poblacion, Kasibu, Nueva Vizcaya | 2015-11-19 | Final | NUEVA VIZCAYA 2ND DEO | LF | 2.4831 | 70 | 2015-02-06 | 2015-04-16 | - | C | 0.484 | 0.135 | 0.3 | - | - | - | 91.9% | 91.9% Very Satisfactory
E U S Construction | 21878 | L | B | MA | GE1 | Nat'l. Rds. to other Strategic Tourist Destinations President Cory Aquino Blvd. (Bagasbas-Talisay Sect.), Brgy. Bagasbas | Daet, Camarines Norte | 2013-03-27 | 1st | V | LF | 47.775 | 210 | 2012-12-07 | 2013-07-04 | 19.52 | O | 0.319 | 0.236 | 0.15 | 0.024 | 0.045 | 0.05 | 82.4 | -
E U S CONSTRUCTION | 21878 | L | A | MA | GE | Construction/Improvement of Access Roads Leading to Airports, Seaports and Declared Tourism Destinations c. To Declared Tourism Destinations 4.Mercedes-Bagasbas Road Leading to Bagasbas Beach, Brgy. San Roque, Mercedes, Camarines Norte | Brgy. San Roque, Mercedes, Camarines Norte | 2015-08-31 | 1st | Camarines Norte DEO | LF | 45.815 | 180 | 2015-03-30 | 2015-09-25 | 1.06% | O | 0.362 | 0.27 | 0.15 | 0.03 | 0.05 | 0.05 | 91.2% | -
E U S CONSTRUCTION / 128 DRAGON CONSTRUCTION AND SUPPLIES (JV) | JV-13-535 | L | B | MA | GE | Widening of Nat'l Roads 1 - Widening of Daang Maharlika (w/ exceptions) Camarines Norte, a. K0032+(907) to K0335+657, Vinzon - Talisay Section ERRATA to K0332+(907) to K0346+361 | Vinzon - Talisay - Daet - Basud Section, Camarines Norte | 2015-06-08 | Final | Camarines Norte | LF | 46.549 | 180 | 2014-02-06 | 2014-08-04 | 0% | C | 0.43 | 0.151 | 0.3 | - | - | - | 88.1% | *88.1% Satisfactory
E. C. T. CONSTRUCTION | 10060 | L | B | SB | GE | Concreting of Libertad Farm to Market Road | Abulug, Cagayan | 2015-06-02 | 1st | Cagayan 2nd DEO | LF | 6.697 | 136 | 2015-03-09 | 2015-07-22 | 4.16% | O | 0.344 | 0.24 | 0.15 | 0.03 | 0.028 | 0.033 | 82.5% | -
E. Garcia Construction & E. Garcia Gravel & Sand | 7243 | L | AA | MB | GE1 | Preventive Maint. (IS Arterial) along Rolando R. Andaya Highways A)Km.282+000-Km.282+900 B)Km.285+000-Km.285+838 | Camarines Sur | 2012-03-23 | 1st | V | LF | 20.101 | 120 | 2012-01-05 | 2012-05-03 | 38.83 | O | 0.343 | 0.3 | 0.15 | 0.023 | 0.04 | 0.033 | 88.9 | -
E. Garcia Construction and E. Garcia Gravel | 7243 | L | A | MB | GE5 | Naga Airport Development Project |  | 2009-03-07 | 1st | PMS |  | 43.333 | 150 |  |  |  | O | 0.373 | 0.3 | 0.15 | 0.02 | 0.063 | 0.05 | 95.6 | -
E. Garcia Construction Corp. (Formerly E. Garcia Construction & E. Garcia Gravel and Sand) | 7243 | L | AA | MA | GE | Construction of Flood Control, Camarines Sur 1st DEO, Labmanan Flood Control | Libmanan, Camarines Sur | 2014-08-07 | 1st | V | LF | 22.7849 | 165 | 2014-03-03 | 2014-08-14 | 0.75 | O | 0.336 | 0.3 | 0.15 | 0.022 | 0.05 | 0.05 | 90.8 | -
E. Garcia Construction Corp. (Formerly E. Garcia Construction & E. Garcia Gravel and Sand) | 7243 | L | AA | MA | GE | Channel Improvement/Revetment of Waras River, Iriga Section | Iriga City, Camarines Sur | 2014-08-10 | 1st | V | LF | 18.1871 | 200 | 2014-02-17 | 2014-09-04 | 2.86 | O | 0.332 | 0.3 | 0.15 | 0.02 | 0.039 | 0.05 | 89.1 | -
E. GARCIA CONSTRUCTION CORP. (Formerly: E. Garcia Construction & E. Garcia Gravel & Sand) | 7243 | L | AA | MB | GE | Widening of Daang Maharlika, Camarines Sur 2nd L.D. | Milaor, Camarines Sur | 2015-06-04 | Final | Camarines Sur 1st | LF | 31.838 | 225 | 2014-06-23 | 2015-02-06 | 0% | C | 0.498 | 0.133 | 0.3 | - | - | - | 93.1% | *93.1% Very Satisfactory
E. GARCIA CONSTRUCTION CORP. (Formerly: E. Garcia Construction & E. Garcia Gravel & Sand) | 7243 | L | AA | MA | GE | Camaligan Flood Control, Riprapping/ Revetment along Bicol River, Brgy. Tarusanan and San Francisco | Camaligan, Camarines Sur | 2015-06-06 | 1st | Camarines Sur 2nd | LF | 40.748 | 267 | 2015-03-10 | 2015-12-01 | 57.53% | O | 0.391 | 0.271 | 0.15 | 0.03 | 0.042 | 0.033 | 91.7% | -
E. GARCIA CONSTRUCTION CORP. (Formerly: E. Garcia Construction & E. Garcia Gravel & Sand) | 7243 | L | AA | MA | GE | Construction/Rehabilitation of Gainza Flood Control, Gainza, Camarines Sur | Gainza, Camarines Sur | 2015-08-29 | 1st & Final | Camarines Sur First DEO | LF | 4.459 | 90 | 2015-02-20 | 2015-05-20 | 37.97% | C | 0.49 | 0.133 | 0.3 | - | - | - | 92.3% | *92.3% Very Satisfactory
E. GARCIA CONSTRUCTION CORP. (Formerly: E. Garcia Construction & E. Garcia Gravel & Sand) | 7243 | L | AA | MA | GE | Camaligan Flood Control, Riprapping/Revetment along Bicol River, Brgy. Tarusanan and San Francisco, Camaligan, Camarines Sur | Brgy. Tarusanan and San Francisco, Camaligan, Camarines Sur | 2015-08-30 | Final | Camarines Sur Second DEO | LF | 40.748 | 267 | 2015-03-11 | 2015-12-02 | 39.7% | C | 0.494 | 0.133 | 0.3 | - | - | - | 92.7% | *92.1% Very Satisfactory
E. GARCIA CONSTRUCTION CORP. (Formerly: E. Garcia Construction & E. Garcia Gravel & Sand) | 7243 | L | AA | MB | GE | Construction/Rehabilitation of Milaor Flood Control, Milaor, Camarines Sur | Milaor, Camarines Sur | 2015-11-12 | Final | Camarines Sur First DEO | LF | 4.459 | 90 | 2015-02-20 | 2015-05-20 | 37.97% | C | 0.444 | 0.133 | 0.3 | - | - | - | 87.7% | 87.7% Satisfactory
E. Garcia Construction Corporation | 7243 | L | AA | SB | GE5 | Sabang Port Development Project | Sabang, San Jose, Camarines Sur | 2014-03-06 | 1st | DOTC | LF | 11.896 | 180 | 2013-10-30 | 2014-04-27 | 5.18 | O | 0.344 | 0.3 | 0.15 | 0.02 | 0.07 | 0.05 | 93.4 | -
E. Garcia Construction Corporation | 7243 | L | AA | MB | GB1 | Camarines Sur LTFRB Building Construction Project | Naga City, Camarines Sur | 2013-09-05 | 1st | DOTC | L | 16.796 | 240 | 2013-04-19 | 2013-12-14 | 13.31 | O | 0.381 | 0.3 | 0.15 | 0.03 | 0.062 | 0.033 | 95.6 | -
E. Guadiz Construction | 27172 | L | B | SB | GE1 | Prev. Maint. along Manila North Rd., K0676+200-K0676+900 | Abulug, Cagayan | 2013-03-12 | 1st | II | LF | 6.245 | 45 | 2013-02-27 | 2013-04-12 | 65.78 | O | 0.35 | 0.2 | 0.15 | 0.03 | 0.059 | 0.033 | 82.2 | -
E. K. C. CONSTRUCTION AND AGGREGATES | 14833 | L | B | MA | GE | Road Upgrading (Unpaved to Paved) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standards (HDM-4 Project Analysis) Intermittent Sections, Itogon-Dalupirip Road (Oncalew Section), K0269+257-K0269+552 (w/ Slope Protection) | Itogon, Benguet | 2015-11-09 | 1st | Benguet 1st | LF | 16.3883 | 155 | 2015-06-22 | 2015-11-23 | -9.00% | OG | 0.386 | 0.3 | 0.06 | 0.03 | 0.035 | 0.017 | 82.8% | 82.8% Satisfactory
E. M. Abin Trading & Construction | 34513 | L | D | SB | GE | Tourism Information Center | Dumaran, Palawan | 2016-05-05 | 1st | TIEZA | LF | 2 | 90 | 2016-02-28 | 2016-05-27 | -22.53 | O | 0.4 | 0.3 | 0 | 0.03 | 0.053 | 0.05 | 83.3
E. M. Cuerpo Inc. | 30963 | L | AAA |  | GB1 | Construction of Eight (8) Five Storey Low Rise Buildings w/ Land Development and Survey Works | Tala Phase II, Tala, Caloocan City | 2013-07-12 | 1st | NHA | L | 242.299 | 360 | 2012-12-12 | 2013-12-16 | -1.41 | O | 0.387 | 0.2046 | 0.1359 | 0.03 | 0.065 | 0.05 | 87.25 | -
E. M. Cuerpo Inc. | 30963 | L | AAA | LB | GE1 | Cagayan de Oro Airport Development Project | Cagayan de Oro City | 2012-10-24 | 1st | DOTC | LF | 21.315 | 120 | 2012-07-24 | 2012-11-20 | 9.21 | O | 0.368 | 0.3 | 0.15 | 0.03 | 0.035 | 0.05 | 93.3 | -
E. M. Cuerpo, Inc. | 30963 | L |  |  |  | Construction of (8) Five storey Low Rise Buildings with Land Development and Survey Works, Tala Phase II | Tala, Caloocan City | 2014-05-09 | 3rd | NHA | LF | 266.494 | 514 | 2012-12-22 | 2014-05-19 | -4.89 | O | 0.3893 | 0.3 | 0.101 | 0.03 | 0.06 | 0.033 | 91.33 | -
E. M. Cuerpo, Inc. | 30963 | L |  |  |  | Construction of (8) Five storey Low Rise Buildings with Land Development and Survey Works, Tala Phase II | Tala, Caloocan City | 2013-10-31 | 2nd | NHA | LF | 266.494 | 514 | 2012-12-22 | 2014-05-19 | -4 | O | 0.3792 | 0.2828 | 0.11 | 0.03 | 0.065 | 0.05 | 91.7 | -
E. M. CUERPO, INC. | 30963 |  | AAA | LB |  | Dapa Port Development Project | Diargao Island, Surigao del Norte | 2016-03-09 | 1st & Final | DOTC | LF | 9.467 | 150 | 2015-09-29 | 2016-02-25 | 0 | C | 0.458 | 0.2 | 0.3 | - | - | - | 95.8 | *95.80% V. Satisfactory
E. M. DANAN TRADING & CONSTRUCTION | 22171 | L | B | SB | GB | Construction of Multi-Purpose Building, Sebitanan, Sasmuan, Pampanga | Sasmuan, Pampanga | 2015-06-03 | Final | Pampanga 2nd DEO | LF | 1.899 | 90 | 2014-10-10 | 2015-01-07 | 0% | C | 0.496 | 0.2 | 0.3 | - | - | - | 99.6% | *99.6% Outstanding
E. P. Manantan Construction and Development Corporation | 6457 | L | A | MA | GB | Reconstruction of First District Engineering Office Building | First District, Davao Oriental | 2014-10-27 | 1st | XI | LF | 10.8888 | 300 | 2014-05-05 | 2015-02-28 | 9.86% | O | 0.322 | 0.235 | 0.15 | 0.03 | 0.029 | 0.033 | 79.9% | 79.90% Unsatisfactory
E. U. Jingco Construction | 31486 |  | A |  |  | Emergency Repair of Damaged Rock Bulkhead Along Old R. C. Wharf & RoRo Ramp-1 Caused by 7.2 Magnitute Earthquake | Port of Tagbilaran, Tagbilaran, Bohol/ Region 7 | 2014-08-15 | 1st | PPA | LF | 23.629 | 180 | 2014-05-02 | 2014-10-25 | 28.71 | O | 0.396 | 0.3 | 0.15 | 0.03 | 0.056 | 0.05 | 98.2 | -
E. U. Jingco Construction | 31486 | L | A | SB | GE | Construction of Eco-Tourism Pavillon | Lulugayan Falls, Brgy. Literon, Calbiga, Western Samar | 2014-12-02 | 1st | TIEZA | LF | 7.395 | 300 | 2013-12-24 | 2014-12-14 | 0 | O | 0.386 | 0.3 | 0.15 | 0.015 | 0.018 | 0.05 | 91.9 | -
E. U. Jingco Construction | 31486 | L |  |  | GE5 | Repair of Damaged Retaining Wall & Concrete Pavement Bet. Pier I & II | Port of Catbalogan, Catbalogan City | 2011-03-25 | 1st | PPA | LF | 6.928 | 90 | 2010-12-26 | 2011-03-25 | -13.97 | O | 0.364 | 0.225 | 0.15 | 0.03 | 0.035 | 0.033 | 83.7 | -
E.A Ramirez Construction, Inc. | 11631 | L | B | MA | GB1 | Construction of 3-Storey School Building |  | 2009-09-08 | 1st | NHA |  | 19.08 | 204 |  |  |  | O | 0.364 | 0.271 | 0.053 | 0.03 | 0.056 | 0.05 | 82.4 | -
E.A Ramirez Construction, Inc. | 11631 |  |  |  |  | Construction of one (1) Unit Public Market |  | 2010-09-16 |  | NHA |  | 3.972 | 90 |  |  |  | O | 0.3906 | 0.2904 | 0.0092 | 0.015 | 0.025 | 0.0333 | 76.35 | -
E.A Sancho Construction | 5648 |  |  |  |  | Impvt./Conc. Of Tabgon-Maysalay Road KO 502+400 - KO 504+476 |  | 2010-06-04 |  | V |  | 14.142 | 150 |  |  |  | O | 0.301 | 0.293 | 0.15 | 0.03 | 0.035 | 0.033 | 84.2 | -
E.A Sancho Construction | 5648 |  |  |  |  | Impv't./Conc. of Maysalay-Lamon Rd. |  | 2010-08-25 |  | V |  | 14.147 | 168 |  |  |  | O | 0.345 | 0.3 | 0.15 | 0.03 | 0.055 | 0.033 | 91.3 | -
E.A. Sancho Construction Inc. (Formerly: E.A. Sancho Construction) | 5648 | L | AA | LA | GE1 | CP-II(1-2) Rd. Upgrading (Gravel to Paved) along Iriga City-San Isidro-Hanawan Rd. | Iriga City | 2013-08-01 | 1st | V | LF | 11.654 | 178 | 2013-02-22 | 2013-08-18 | 2 | O | 0.345 | 0.243 | 0.15 | 0.03 | 0.055 | 0.033 | 85.6 | -
E.A. SANCHO CONSTRUCTION INC. (Formerly: E.A. Sancho Construction) | 5648 | L | AA | LA | GE | Indv. Proj. Retrofitting/Strengthening of Waras Bridge, Iriga City | Iriga City | 2015-11-16 | Final | Camarines Sur Fourth DEO | LF | 18.4212 | 120 | 2015-02-09 | 2015-06-08 | - | C | 0.491 | 0.059 | 0.3 | - | - | - | 85% | 85% Satisfactory
E.A. Unabia Construction | 29305 | L | B | MA | GE1 | Conc. of Sta. Filomena FMR | Calanasan, Apayao | 2013-03-22 | 1st | CAR | LF | 9.319 | 180 | 2012-12-20 | 2013-01-18 | 2.64 | O | 0.357 | 0.238 | 0.15 | 0.023 | 0.045 | 0.033 | 84.6 | -
E.A. Unabia Construction / KDCM Construction / BHM Construction, Joint Venture |  | L |  |  | GE1 | Replacement of Saleng Bridge along Kalinga-Abra Rd. | Balbalan, Kalinga | 2012-11-26 | 1st | CAR | LF | 7.809 | 270 | 2012-02-01 | 2012-10-27 | -3.51 | O | 0.341 | 0.3 | 0.05 | 0.022 | 0.028 | 0.033 | 77.4 | -
E.B.A Construction | 6210 | L | B |  | GB1 | UP OU Centennial Center for Digital Learning |  | 2009-07-20 | 1st | U.P. |  | 12.948 | 60 |  |  |  | O | 0.361 | 0.261 | 0.15 | 0.02 | 0.02 | 0.05 | 86.2 | -
E.B.J.R. Construction | 19780 | L | C | SB | GE1 | Maint. of Nat'l Rd. (Item 200-Aggregate Base Course a)Abbut-Conner Rd., K0542+370-K0562+000 (w/ exceptions); b)Conner-Kabugao Rd., K0577+369- K0602+792; c) Kabugao-Pudtol-Luna Rd., K0591+413-K0603+000 (w/ exceptions); d)Abbut-Conner Rd., K0548+500-K0550+500 w/ exception | Apayao | 2013-08-10 | 1st | CAR | LF | 2.998 | 90 | 2013-06-28 | 2013-09-25 | -3.87 | O | 0.333 | 0.3 | 0.111 | 0.03 | 0.05 | 0.017 | 84.1 | -
E.C De Luna Const. Corp. (Formerly E.C. De Luna Const.) | 11906 | L | AAA | LB | GE1 | CP IV, Gatanguit-Calbiga Road Sect. Phase VI |  | 2008-12-03 | 3rd | PJHL |  | 1466.751 | 1080 |  |  |  | O | 0.35 | 0.3 | 0.1 | 0.03 | 0.065 | 0.1 | 94.5 | -
E.C De Luna Construction Corporation | 11906 |  |  |  |  | Marikina-Infanta Road Project, Km. 91+910-Km. 120+925 under SONA Projects in Luzon Beltway |  | 2010-03-05 |  | PJHL |  | 1915.106 | 720 |  |  |  | O | 0.368 | 0.3 | 0.15 | 0.03 | 0.056 | 0.05 | 95.4 | -
E.C De Luna Construction Corporation (Formerly: E.C De Luna Const.) | 11906 |  |  |  |  | Const. of El Nido-Bataraza Rd. CP-3B-1 Puerto Prinsesa-Aborlan Abo-abo Sect. Segments 1-7 Km.02+376 - Km.128+026.93 w/ exception |  | 2010-06-01 |  | IVB |  | 1792.809 | 730 |  |  |  | O | 0.38 | 0.3 | 0.15 | 0.03 | 0.06 | 0.05 | 97 | -
E.C. TIMBANCAYA ENTERPRISES | 15244 | L | B | MA | GE | Road Widening of Puerto Princesa South Road, K0002+941 to K0003+610 | Puerto Princesa City, Palawan | 2015-06-01 | 1st | Palawan 3rd DEO | LF | 12.327 | 110 | 2015-04-17 | 2015-08-05 | 0% | O | 0.358 | 0.238 | 0.15 | 0.023 | 0.06 | 0.05 | 87.9% | -
E.C. TIMBANCAYA ENTERPRISES | 15244 | L | B | MA | GE | Road Widening of Puerto Princesa South Road, K0002+941 to K0003+610, Puerto Princesa City | Puerto Princesa City | 2015-08-24 | 1st | Palawan III DEO | LF | 12.326 | 140 | 2015-04-17 | 2015-09-04 | 0.18% | O | 0.378 | 0.239 | 0.15 | 0.015 | 0.037 | 0.05 | 86.9% | -
E.C.T CONSTRUCTION | 10060 | L | B | MA | GE | Construction/Upgrading/Rehabilitation of Drainage along Cagayan-Apayao Road, K0490+510 - K0491+127, Abulug, Cagayan | Cagayan, Apayao | 2015-11-12 | Final | CAGAYAN 3RD DEO | LF | 5.0022 | 192 | 2015-04-28 | 2015-11-05 | - | C | 0.466 | 0.133 | 0.3 | - | - | - | 89.9% | 89.9% Very Satisfactory
E.C.T. CONSTRUCTION | 10060 | L | B | SB | GE | Concreting of Libertad Farm to Market Road, Abulug, Cagayan | Abulug, Cagayan | 2015-08-26 | Final | Cagayan 2nd DEO | LF | 6.696 | 121 | 2015-03-09 | 2015-07-07 | 0.27% | C | 0.414 | 0.134 | 0.3 | - | - | - | 84.8% | *83.42% Satisfactory
E.G Guillen Builders | 14174 | L | B | MA | GE1 | Conc. along Kabugao-Pudtol-Luna Road, Kapanikian Section |  | 2009-06-01 | 1st | CAR |  | 9.338 | 277 |  |  |  | O | 0.293 | 0.3 | 0.15 | 0.023 | 0.045 | 0.05 | 86.1 | -
E.G. & I Construction Corporation | 16225 | L | A | MA | GE | Installation of Center Island/Median at A.C. Cortes Ave., Including Landscaping | Mandaue City, Cebu | 2014-10-21 | 1st | VII | LF | 28.4459 | 186 | 2014-05-09 | 2014-11-10 | 0.5% | O | 0.382 | 0.265 | 0.15 | 0.015 | 0.033 | 0.033 | 87.8% | 87.80% Satisfactory
E.I. Templonuevo and Associates, Incorporated | 1090 | L | A | MA | GE1 | Road Upgrading (Gravel to Concrete) Caticlan-Malay-Libertad Road | Malay, Aklan | 2011-04-08 | 1st | VI | LF | 9.64 | 120 | 2010-12-21 | 2011-04-19 | 0.56 | O | 0.36 | 0.237 | 0.15 | 0.03 | 0.037 | 0.033 | 84.7 | -
E.K.C Construction and Aggregates | 14833 | L | B | MA | GE1 | Impvt. of Baguio-Bontoc-Banaue Road, Conc. of Mt. Data-Bontoc Road, Km. 367+228 - Km. 368+444 (one section), |  | 2009-03-08 | 2nd | CAR |  | 13.75 | 657 |  |  |  | O | 0.3 | 0.3 | 0 | 0.03 | 0.045 | 0.033 | #VALUE! | -
E.K.C Construction and Aggregates | 14833 | L | B | MA | GE | Road Upgrading (Gravel to Concrete) based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standard (HDM-4 Project Analysis) (Intermittent Sections) along Acop-Kapangan-Kibungan-Bakun Road, K0311+254 - K0312+000 & K0312+000 - K0312+670 | Kibungan, Benguet | 2014-11-21 | 1st | CAR | LF | 47.7353 | 231 | 2014-06-25 | 2015-02-10 | 11.33% | O | 0.362 | 0.239 | 0.15 | 0.03 | 0.05 | 0.033 | 86.4% | 86.40% Satisfactory
E.K.C CONSTRUCTION AND AGREGGATES | 14833 | L | B | MB | GE | Road Upgrading (Gravel to Concrete) based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standard (HDM-4 Project Analysis)(Intermittent Sections) along Acop-Kapangan-Kibungan-Bakun Rd., K0311+254 - K0312+000 & K0312+000 - K0312+670 | Kibungan, Benguet | 2015-06-03 | Final | CAR | LF | 47.735 | 231 | 2014-06-25 | 2015-02-10 | (+) 3.90% | C | 0.4 | 0.2 | 0.3 | - | - | - | 90% | *87.84% Satisfactory
E.K.C. Construction and Aggregates / Lab General Engineering (JV) | JV-10-136 | L | B | MA | GE1 | Rehab./Reconst. Of Mt. Province-Ilocos Sur via Tue Rd,. K0403+500-K0403+926.50; K0413+437-K0414+052 | Tadian, Mt. Province | 2012-08-04 | 2nd | CAR | LF | 14.526 | 395 | 2011-08-24 | 2012-07-23 | -15.55 | O | 0.317 | 0.3 | 0 | 0 | 0.023 | 0.033 | 67.3 | -
E.K.C. Construction and Aggregates / Lab General Engineering (JV) | JV-10-136 | L | B | MA | GE1 | Rehab. of Mt. Province-Ilocos Sur via Tue Road, K0413+347-K0414+052; K0403+500-K0404+044 | Tadian, Mountain Province | 2012-03-16 | 1st | CAR | LF | 14.526 | 290 | 2011-08-24 | 2012-06-08 | -18.62 | O | 0.299 | 0.3 | 0 | 0.03 | 0.04 | 0.033 | 70.2 | -
E.L. Anolin Construction | 35406 | L | B | SB | GE | Rehabilitation/Upgrading (Preventive Maintenance) of Congressional Avenue, Q.C. (K011+(-205) to K013+(-065)) with exception | Quezon City | 2014-11-27 | 1st | NCR | LF | 7.5689 | 150 | 2014-05-13 | 2015-04-26 | 10% | O | 0.351 | 0.24 | 0.15 | 0.03 | 0.04 | 0.033 | 84.4% | 84.40% Satisfactory
E.L. TORRES CONSTRUCTION AND TRADING | 31406 | L | B | MA | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads Including Drainage (Intermittent Section) along Mac Arthur Highway, Valenzuela City | Valenzuela City | 2015-08-28 | 1st | MM 3rd DEO | LF | 15.321 | 180 | 2015-03-17 | 2015-09-12 | 12.02% | O | 0.354 | 0.2 | 0.15 | 0.03 | 0.04 | 0.05 | 82.4% | -
E.M. ARAGON ENTERPRISES | 3314 | L | A | MA | GE | Construction of Flood Control and Road Dike along Kawit-Cavite Export Processing Zone (CPEZ) Road, Brgy. Gahak, Kawit, Cavite (Construction of Flood Control Projects, Cavite 1st LD, Construction of Road Dike in Brgy. Gahak, Kawit within Kawit-Noveleta Diversion Road) | Kawit, Cavite | 2015-09-05 | 1st & Final | Cavite 1st | LF | 18.032 | 140 | 2014-09-25 | 2015-02-11 | 0% | C | 0.425 | 0.133 | 0.3 | - | - | - | 85.8% | *85.8% Satisfactory
E.M. Bayatan Construction | 21332 | L | D | SB | GE | Const. of Bridge, New 9 (along Arterial Rd.) Dumog Box Culvert along Aritao-Quirino Road | Kasibu, Nueva Vizcaya | 2014-08-15 | 1st | II | LF | 9.767 | 150 | 2014-04-21 | 2014-09-17 | 1.13 | O | 0.349 | 0.239 | 0.15 | 0.024 | 0.045 | 0.033 | 84 | -
E.M. Bayatan Construction | 21332 | L | D | SB | GE2 | Cupas River Control, Sto. Domingo Sect. | Bambang, Nueva Vizcaya | 2013-03-20 | 1st | II | LF | 14.7 | 90 | 2013-02-23 | 2013-05-23 | 46.69 | O | 0.4 | 0.225 | 0.15 | 0.03 | 0.045 | 0.033 | 88.3 | -
E.M. BAYATAN CONSTRUCTION | 21332 | L | B | SB | GE | Construction of Bridges New (along Arterial Rd), Dumog Box Culvert along Aritao-Quirino Road | Kasibu, Nueva Vizcaya | 2015-06-08 | Final | Nueva Vizcaya 2nd DEO | LF | 9.767 | 150 | 2014-04-21 | 2014-09-17 | 0% | C | 0.354 | 0.2 | 0.3 | - | - | - | 85.4% | *84.56% Satisfactory
E.M. BAYATAN CONSTRUCTION | 21332 | L | D | SB | GE | Construction of New Permanent Bridges, Binogawan Bridge at Papaya - Malabing - Wangal - Binogawan - Tadji - Runruno, Kasibu, Nueva Vizcaya | Kasibu, Nueva Vizcaya | 2015-09-03 | 1st & Final | NV 2nd DEO | LF | 10.878 | 210 | 2015-02-06 | 2015-09-03 | 0% | C | 0.448 | 0.13 | 0.3 | - | - | - | 87.8% | *87.8% Satisfactory
E.M. Cuerpo Inc |  |  | AAA |  |  | Cosntruction of Six (6) Five-Storey LRB and Land Development, Manggahan Residences | Manggahan Floodway (East Embankment) Brgy. Sta. Lucia Pasig City | 2016-05-11 | 1st | NHA | LF | 206.3 | 360 | 2015-07-19 | 2016-07-12 | -25.15 | O | 0.3828 | 0.0328 | 0 | 0.0225 | 0.0467 | 0.0167 | 50.15 | -
E.M. Cuerpo Inc | 30963 |  |  |  |  | Design & Build of MSU-IIT CSM Research Building | A. Bonifacio Ave., Tibanga, Iligan City, Region X | 2015-11-06 | 2nd | PICE-CDO | LF | 147.889 |  | 2014-02-10 | 2015-12-20 | 1.51 | O | 0.388 | 0.3 | 0.135 | 0.03 | 0.07 | 0.05 | 97.3 | -
E.M. Cuerpo, Inc. | 30963 |  | AAA |  |  | College of Engineering Building Expansion | A. Bonifacio Ave., Tibanga, Illigan City, Region X | 2014-07-31 | 2nd | PICE-Misamis Oriental-CDO | L | 108.334 | 360 | 2013-02-25 | 2014-08-30 | 9.94 | O | 0.382 | 0.3 | 0.051 | 0.03 | 0.06 | 0 | 82.3 | -
E.M. Cuerpo, Inc. | 30963 |  | AAA |  |  | College of Engineering Building Expansion | A. Bonifacio Ave., Tibanga, Illigan City, Region X | 2014-04-29 | 1st | PICE-Misamis Oriental-CDO | L | 108.334 |  | 2013-02-25 | 2014-06-27 | 8.94 | O | 0.4 | 0.3 | 0.061 | 0.02 | 0.05 | 0 | 83.1 | -
E.M. Cuerpo, Inc. | 30963 | L |  |  |  | Construction of Eight(8) Five storey Low Rise Buildings with Land Development and Survey Works, Tala, Phase II | Tala, Caloocan City | 2014-05-09 | 3rd | NHA | LF | 266.494 | 514 | 2012-12-22 | 2014-05-19 | -4.89 | O | 0.3893 | 0.3 | 0.101 | 0.03 | 0.06 | 0.033 | 91.33 | -
E.M. Cuerpo, Inc. | 30963 | L |  |  |  | Construction of Eight(8) Five storey Low Rise Buildings with Land Development and Survey Works, Tala, Phase II | Tala, Caloocan City | 2013-10-31 | 2nd | NHA | LF | 266.494 | 514 | 2012-12-12 | 2013-12-16 | -4 | O | 0.3792 | 0.2828 | 0.11 | 0.03 | 0.065 | 0.05 | 91.7 | -
E.M. CUERPO, INC. /LADY OF ASSUMPTION ENTERPRISES JOINT VENTURE | 25360 | L | - | - | - | Widening of Daang Maharlika, K0955+589 - K0958+804 (Section ID: S00083LT), Mac Arthur, Leyte | Mac Arthur, Leyte | 2015-06-30 | 1st | Regional Office No. VIII | LF | 120.196 | 260 | 2015-02-03 | 2015-10-20 | - | O | 0.365 | 0.235 | 0.15 | 0.03 | 0.05 | 0.033 | 86.3% | -
E.M. PALOMARES CONSTRUCTION | 23471 | L | B | SB | GB | Construction of Academic Rooms/School Building Nagtupacan | San Vicente, Ilocos Sur | 2015-06-05 | 1st | Ilocos Sur 1st DEO | LF | 3.755 | 120 | 2015-03-04 | 2015-07-01 | 18.59% | O | 0.38 | 0.227 | 0.15 | 0.03 | 0.047 | 0.033 | 86.7% | -
E.M. Palomares Construction | 23471 | L | B | SB |  | Resto/ Rehab of Banaoang PIP (Package 1) | San Ildefenso, Ilocos Sur | 2016-04-16 | 1st | NIA | LF | 11.861 | 150 | 2015-10-19 | 2016-03-19 | -19.89 | O | 0.2727 | 0.2427 | 0 | 0.012 | 0.049 | 0.0333 | 60.97 | -
E.M.L Construction & Trading | 10151 | L | B | MA | GE1 | Rehabilitation of Angeles-Porac-Floridablanca-Dinalupihan Road |  | 2009-05-18 | 1st | III |  | 19.053 | 75 |  |  |  | O | 0.368 | 0.211 | 0.15 | 0.03 | 0.035 | 0.05 | 84.4 | -
E.P. Manantan Construction and Development Corporation | 6457 |  |  |  |  | Rehabilitation and Minor Improvement of Km. 9, Sagayen-Sawata Provincial Road Phase 2 | San Isidro, Davao del Norte | 2015-05-29 | 1st | Provincial Government of Davao del Norte | LF | 18.417 | 150 | 2014-12-12 | 2014-06-22 | -9.76 | O | 0.127 | 0.053 | 0.052 | 0.03 | 0.03 | 0.033 | 32.5 | -
E.P. Manantan Construction and Development Corporation | 6457 |  |  |  |  | Rehabilitation and Minor Improvement of Km. 9, Sagayen-Sawata Provincial Road Phase 2 | San Isidro, Davao del Norte | 2015-06-25 | 2nd | Provincial Government of Davao del Norte | LF | 18.417 | 150 | 2014-12-12 | 2014-06-22 | -6.47 | O | 0.2715 | 0.0589 | 0.0854 | 0.03 | 0.0155 | 0 | 46.13 | -
E.P. Manantan Construction and Development Corporation | 6457 |  |  |  |  | Rehabilitation and Minor Improvement of Km. 9, Sagayen-Sawata Provincial Road Phase 2 | San Isidro, Davao del Norte | 2015-08-26 | Final | Provincial Government of Davao del Norte | LF | 18.565 | 237 | 2014-12-12 | 2015-08-05 | 0 | F | 0.45 | 0.1 | 0.3 | - | - | - | 85 | **57.60% Poor
E.P. MANANTAN CONSTRUCTION AND DEVELOPMENT CORPORATION | 6457 | L | A | MA | GE | Widening (Additional Two Lanes) at Surigao Sur Boundary to Davao Oriental Coastal Road, Km. 1585+040-Km. 1585+725, Lambajon, Baganga, Davao Oriental | Km. 1585+040-Km. 1585+725, Lambajon, Baganga, Davao Oriental | 2015-08-26 | 1st & Final | Davao Oriental First DEO | LF | 13.967 | 175 | 2015-02-17 | 2015-08-10 | - | C | 0.446 | 0.132 | 0.3 | - | - | - | 87.8% | *87.8% Satisfactory
E.P. MANANTAN CONSTRUCTION AND DEVELOPMENT CORPORATION | 6457 | L | A | MA | GE | Widening of Bangkerohan Bridge, Daang Maharlika (Agusan-Davao Road), Montevista, Compostela Valley Province | Montevista, Compostela Valley Province | 2015-11-12 | 1st | Compostela Valley DEO | LF | 2.2329e-05 | 258 | 2015-04-01 | 2015-12-14 | 0.012 | OG | 0.378 | 0.288 | 0.15 | 0.03 | 0.05 | 0.05 | 94.6% | 94.6% Very Satisfactory
E.P. MANANTAN CONSTRUCTION AND DEVELOPMENT CORPORATION | 6457 | L | A | 0 | GE | Widening/Additional Two (2) Lanes at Surigao del Sur Boundary-Davao Oriental Coastal Road, Km. 1676+600 to Km. 1677+060, Tarragona, Davao Oriental | Tarragona, Davao Oriental | 2015-11-10 | Final | Davao Oriental 1st DEO | LF | 9.885e-06 | 119 | 2015-02-17 | 2015-06-15 | -0.0514 | C | 0.482 | 0.2 | 0.146 | - | - | - | 82.8% | 82.8% Satisfactory
E.P. MANANTAN CONTRUCTION AND DEVELOPMENT CORPORATION | 6457 | L | A | MA | GB | Reconstruction of First District Engineering Office Building | First District, Davao Oriental | 2015-06-06 | Final | Davao Oriental 1st | LF | 10.889 | 300 | 2014-05-05 | 2015-02-28 | 0% | C | 0.468 | 0.133 | 0.3 | - | - | - | 90.1% | *82.96% Satisfactory
E.R. CONSTRUCTION | 19013 | L | B | MA | GE | Repair/Maint./Rehab. of Drainage System along Roman Expressway, Km. 135+000 to Km. 136+000 at Brgy. Reformista, Limay, Bataan | Limay, Bataan | 2015-06-04 | Final | Bataan Second DEO | LF | 1.89 | 60 | 2014-12-29 | 2015-02-26 | 0% | C | 0.471 | 0.187 | 0.3 | - | - | - | 95.8% | *95.8% Very Satisfactory
E.R. Rodriguez Construction | 12596 | L | A | MB | GE | Improvement of Earth dike along the Left Bank of Polo River, Sta. 0+000 to Sta. 1+471 | Valenzuela City | 2014-11-22 | 1st | NCR | LF | 44.4629 | 270 | 2014-09-07 | 2015-06-03 | 0.28% | O | 0.325 | 0.3 | 0.15 | 0.03 | 0.06 | 0.05 | 91.5% | 91.50% Very Satisfactory
E.R. Rodriguez Construction | 12596 | L | A | MA | GE1 | Road Upgrading (Gravel to Paved) of Catanduanes Circ. Road, Km. 149+000-Km. 152+000, Inalmasinan-Hitoma Sect. | Catanduanes | 2011-08-16 | 1st | V | LF | 44.097 | 240 | 2011-07-01 | 2012-02-25 | 0.4 | O | 0.323 | 0.133 | 0.15 | 0.01 | 0.028 | 0.033 | 67.7 | -
E.R. Rodriguez Construction | 12596 | L | A | MB | GE2 | Const. of Flood Control & Drainage | Panganiban, Catanduanes | 2013-07-30 | 1st | V | LF | 18.983 | 252 | 2013-02-13 | 2013-10-22 | 1 | O | 0.339 | 0.3 | 0.15 | 0.03 | 0.058 | 0.033 | 91 | -
E.R. Venson Construction/P K C S Construction & Hardware (JV) | JV-13-788 | L | B | MA | GE | Network Development - Widening of National Roads - Arterial Roads Widening of Gapan-San Fernando-Olongapo Road Bataan First District | Dinalupihan, Bataan | 2014-11-26 | 1st | III | LF | 22.0789 | 150 | 2014-09-15 | 2015-02-11 | 0.87% | O | 0.383 | 0.221 | 0.15 | 0.03 | 0.037 | 0.033 | 85.4% | 85.40% Satisfactory
E.R. VENZON CONSTRUCTION (Formerly Lion Construction) | 19013 | L | B | MA | GE | Cluster 3: Repair/Maintenance of Flood Control and Drainage Structure Projects, Bataan 2nd District, Talisay RC (Catmon Section): Reformista RC (Reformista Section): Pangulisanin RC (Cabcaben Section); Tenejero RC (Ibayo-Tenejero Section); Tenejero RC (Maite Section); Dangcol and Tuyo River, Bataan | Bataan | 2015-08-28 | 1st & Final | Bataan Second DEO | LF | 13.248 | 149 | 2015-02-13 | 2015-07-11 | - | C | 0.411 | 0.133 | 0.3 | - | - | - | 84.4% | *84.4% Satisfactory
E.R. VENZON CONSTRUCTION (Formerly: Lion Construction) | 19013 | L | B | MA | GE | Construction of Road, Bayangin Road, Brgy. Alas-Asin, Mariveles, Bataan, 2nd LD | Mariveles, Bataan, 2nd LD | 2015-11-12 | Final | Bataan Second DEO | LF | 7.2777 | 149 | 2015-06-01 | 2015-10-27 | - | C | 0.486 | 0.133 | 0.3 | - | - | - | 91.9% | 91.9% Very Satisfactory
E.S. Almuete Construction | 5131 | L | C | SB | GB1 | Const. of Classroom, Bonfal NHS | Bayombong, Nueva Vizcaya | 2013-08-13 | 1st | II | LF | 6.084 | 180 | 2013-04-10 | 2013-10-06 | -8.44 | O | 0.385 | 0.24 | 0.066 | 0.033 | 0.029 | 0.033 | 78.6 | -
E.S. DE GUZMAN CONSTRUCTION | 17494 | L | B | MA | GB | Construction of Classroom in Areas Experiencing Acute Classroom Shortage, Cordon E/S, One (1) Storey, One (1) Classroom S/B Cordon | Cordon, Kasibu, Nueva Vizcaya | 2015-06-09 | Final | Nueva Vizcaya 2nd DEO | LF | 1.142 | 90 | 2014-07-15 | 2014-10-12 | 0% | C | 0.487 | 0.2 | 0.3 | - | - | - | 98.7% | *88.83% Satisfactory
E.S.R Construction and Supplies | 10451 | L | AA | LA | GE2 | Gadakinsur CIP |  | 10/6-10/08 | 1st | MOPIO |  | 10.74 | 270 |  |  |  | O | 0.36 | 0.16 | 0.1 | 0.02 | 0.04 | 0.2 | 88 | -
E.S.R Construction and Supplies | 10451 | L | AA | LA | GE2 | Gadakinsur Communal Irrigation Project, Package II |  | 10/6-10/08 | 1st | MOPIO |  | 13.049 | 977 |  |  |  | O | 0.3711 | 0.16 | 0.05 | 0.01 | 0.05 | 0.2 | 84.11 | -
E.T.V.R Trading and Construction | 14581 | L | A | MA | GB1 | Rehab./Impvt. of DPWH Office Bldg., Regional Office |  | 2008-12-04 | 1st | XI |  | 19.25 | 300 |  |  |  | O | 0.389 | 0.3 | 0.1 | 0.03 | 0.058 | 0.1 | 97.7 | -
E.T.V.R. Trading & Construction | 14581 | L | A | MA | GE | Widening (Paving of Shoulder) - Seal Widening of Calapan South Road K0014+692.60 - K0015+175.30 along Managpi Section | Calapan City, Oriental Mindoro | 2014-08-11 | 1st | IV-B | LF | 9.964 | 86 | 2014-05-21 | 2014-08-14 | 16.35 | O | 0.356 | 0.221 | 0.15 | 0.03 | 0.055 | 0.05 | 86.2 | -
E.U. JINGO CONSTRUCTION | 31486 | L | A | SB | GE | Completion of Eco-Tourism Pavilion Lulugayan Falls | Brgy. Literon Calbiga, Western Samar | 2015-10-29 | Final | TIEZA | LF | 7 | 180 | 2013-12-24 | 2014-12-14 | 0 | C | 0.468 | 0.177 | 0 |  |  |  | 64.6 | 83.70% Satisfactory
EA-EC Construction | 15737 |  |  |  |  | Const. of Classroom S/B Catasan E/S |  | 2010-08-23 |  | V |  | 0.54 | 90 |  |  |  | O | 0.337 | 0.3 | 0.15 | 0.03 | 0.029 | 0.033 | 87.9 | -
Eaglerock Construction & Development Corporation |  | L |  |  | GB1 | Construction of 3-Storey, 15 Classroom School Bldg. | Southville 8C, Brgy San Jose, Rodriguez, Rizal/Region IV | 2012-09-07 | 2nd | NHA | LF | 22.123 | 180 | 2012-04-18 | 2012-10-14 | 6.06 | O | 0.3641 | 0.1782 | 0.15 | 0.02 | 0.05 | 0.05 | 81.23 | -
Eaglerock Construction & Development Corpporation |  | L |  |  | GB1 | Construction of 3-Storey, 15 Classroom School Bldg. | Southville 8C, Brgy San Jose, Rodriguez, Rizal/Region IV | 2012-07-05 | 1st | NHA | LF | 22.123 | 180 | 2012-04-18 | 2012-10-14 | 33.71 | O | 0.3182 | 0.2248 | 0.15 | 0.02 | 0.035 | 0.05 | 79.8 | -
Eaglerock Construction and Development Corp. | 32286 | L |  |  |  | Primetown III Yolanda Permanent Housing Project | Brgy. Sacme, Tanauan, Leyte | 05/29/15 | 1st | NHA | LF | 99.246 | 220 | 11/22/14 | 08/22/15 | 22.23 | O | 0.3318 | 0.2571 | 0.15 | 0.03 | 0.06 | 0.05 | 87.89 | -
Eaglerock Construction and Development Corporation | 32286 | L | A |  |  | Construction of Core Housing Units (701 Units) of Kinamaligan Resettlement Project Phase I | Brgy. Maingaran, Masbate City/ Region V, Bicol | 09/29/2014-10/03/2014 | 1st | NHA | LF | 73.394 | 270 | 2013-11-17 | 2014-08-13 | -6.286 | Delayed | 0.3124 | 0.3 | 0.15 | 0.01 | 0.05 | 0.05 | 87.24 | -
Eaglerock Construction and Development Corporation | [5 empty] | Primetown 3 | Brgy. Sacme, Tanauan, Leyte | 2016-04-23 | 2nd & Final | NHA | LF | 99.246 | 220 | 2014-11-22 | 2015-09-07 | -2.02 | C | 0.4388 | 0.2 | 0.2394 | - | - | - | 87.82 | 87.87% Satisfactory
EAST ASIA CONSTRUCTION INC. | 1904 | L | A | MA | GB | Construction of 2 Storey - 6 Class Senior High School Classrooms, Barotac Viejo NHS, Barotac Viejo, Iloilo | Barotac Viejo, Iloilo | 2015-11-14 | 1st | Iloilo 3rd | LF | 8.5328 | 150 | 2015-07-20 | 2015-12-17 | (+) 1.66% | OG | 0.328 | 0.223 | 0.15 | 0.03 | 0.038 | 0.05 | 81.9% | 81.9% Unsatisfactory
EAST ASIA CONSTRUCTION, INC. | 1904 | L | A | MA | GE | Widening of National Roads, Mandurriao-San Miguel Road - K0008+165 - K0009+280 | Mandurriao, Iloilo City | 2015-08-24 | 1st | Iloilo City | LF | PHP 26,099,682.40 | 191 | 2015-04-15 | 2015-10-22 | 17.17% | O | 0.367 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 89.2% | -
EC Samonte Construction | 31019 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Paved) Int. Sect., Liloy-Siocon Rd., K1982+124-K1983+130 | Zamboanga del Norte | 2013-08-12 | 2nd | IX | LF | 27.747 | 118 | 2013-02-04 | 2013-06-01 | -49.41 | O | 0.303 | 0.3 | 0 | 0.012 | 0.033 | 0.033 | 68.1 | -
EC Samonte Construction | 31019 | L | C | SB | GE1 | Rd. Upgrading (Gravel to Paved) Int. Sect., Liloy-Siocon Rd., K1982+124-K1983+130 | Zamboanga del Norte | 2013-03-16 | 1st | IX | LF | 27.747 | 93 | 2013-02-04 | 2013-05-07 | 6.08 | O | 0.397 | 0.225 | 0.15 | 0.03 | 0.035 | 0.05 | 88.7 | -
EC Samonte Construction | 31019 | L | C | SB | GE1 | Rd. Upgrading (Gravel to Paved) Int. Sect., Siocon-Sirawai-Sibucon Limpapa Rd., K2097+000-K2099+200 | Zamboanga del Norte | 2013-03-17 | 1st | IX | LF | 27.908 | 93 | 2013-02-04 | 2013-05-07 | 3.12 | O | 0.365 | 0.232 | 0.15 | 0.03 | 0.04 | 0.033 | 85 | -
EC Samonte Construction | 31019 | L | B | MA | GE1 | Concreting of Pathway Liloy Central School |  | 2009-06-01 | 1st | IX |  | 0.962 | 88 |  |  |  | O | 0.387 | 0.24 | 0.15 | 0.03 | 0.047 | 0.05 | 90.4 | -
EC Samonte Construction | 31019 | L | B | MA | GE1 | Const. of Liloy-Siocon Road, Dansalan-Lopoc |  | 2009-03-09 | 2nd | IX |  | 28.654 | 311 |  |  |  | O | 0.369 | 0.281 | 0.15 | 0.03 | 0.035 | 0.05 | #VALUE! | -
EC STRUCTURAL COMPOSITES INC. | 31961 | L | B | SB | GE | Rehabilition/Reconstruction/Replacement/Retrofitting of Tripa de Gallina, Pasay City | Pasay City | 2015-03-19 | 1st | South Manila DEO | LF | 8.726 | 90 | 2015-03-18 | 2015-06-15 | (+) 29.94 | O | 0.4 | 0.225 | 0.15 | 0.03 | 0.025 | 0.05 | 88% | -
EC Structural Composites, Inc. | 31961 | L | B | SB | GE | Rehab./Reconst./Replacement/Retrofitting of Tripa de Gallina Bridge (NB) along Gil Puyat Ave. | Pasig City | 2015-03-19 | 1st | NCR | LF | 8.7261 | 90 | 2014-03-18 | 2014-06-15 | 29.94% | O | 0.4 | 0.225 | 0.15 | 0.03 | 0.025 | 0.033 | 86.3% | 86.30% Satisfactory
EC STRUCTURAL COMPOSITES, INC. | 31961 | L | B | MA | GE | Retrofitting/Strengthening of Tiolas Bridge (B00148PN) along Tiolas-Sinugbuhan Road | K0060+(-177), San Joaquin, Iloilo | 2015-06-03 | Final | Iloilo First DEO | LF | 9.3 | 75 | 2015-02-16 | 2015-05-01 | 0% | C | 0.5 | 0.133 | 0.3 | - | - | - | 93.3% | *93.3% Very Satisfactory
EC STRUCTURAL COMPOSITES, INC. | 31961 | L | B | MA | GE | Rehabilitation/Major Repair of Permanent Bridge Mancatian Bridge along Angeles-Porac-Floridablanca-Dinalupihan Road, Porac, Pampanga | Porac, Pampanga | 2015-09-05 | 1st | Pampanga Second DEO | LF | 8.937 | 190 | 2015-03-16 | 2015-09-21 | 3.32% | O | 0.328 | 0.28 | 0.15 | 0.02 | 0.047 | 0.05 | 87.5% | -
EC STRUCTURAL COMPOSITES, INC. | 31961 | L | B | MA | GE | Retrofitting/Strengthening of Permanent Bridges, Tanza Bridge (BO175LZ) along Road to Tanza, Navotas City | Navotas City | 2015-12-11 | Final | Malabon-Navotas DEO | LF | 8.9255 | 162 | 2015-03-06 | 2015-08-14 | 0.00% | C | 0.492 | 0.133 | 0.3 | - | - | - | 92.5% | 92.5% Very Satisfactory
ECCON DEV'T CORPORATION (FORMERLY: E. CANEDA CONSTRUCTION) | 22168 | L | B | MA | GE | Concreting of NJR - Cagwait White Beach Road | Cagwait, Surigao Del Sur | 2015-06-08 | 1st | SURIGAO DEL SUR FIRST DEO | LF | 8.676 | 131 | 2015-03-10 | 2015-07-18 | (+) 4.79% | O | 0.38 | 0.225 | 0.15 | 0.03 | 0.05 | 0.05 | 88.5% | -
ECCON DEV'T CORPORATION (Formerly: E. Caneda Construction) | 22168 | L | B | SB | GB | Construction of Multi-Purpose Buildiing, Tayud, Lilo-an, Cebu | Tayud, Lilo-an, Cebu | 2015-11-14 | Final | Cebu 5th | LF | 0.95914 | 45 | 2015-07-03 | 2015-08-16 | 0.0667 | C | 0.493 | 0.133 | 0.3 | - | - | - | 92.6% | 92.6% Very Satisfactory
ECCON DEV'T. CORPORATION (Formerly: E. Caneda Construction) | 22168 | L | B | SB | GB | Construction of 2 Storey - 4 Classroom at Lataban NHS | Lilo-an, Cebu | 2015-09-02 | 1st | Cebu 5th | LF | 6.099 | 120 | 2015-07-20 | 2015-07-20 | 0.02% | O | 0.323 | 0.279 | 0.15 | 0.03 | 0.052 | 0.05 | 88.4% | -
Edanna Construction | 25492 | L |  |  |  | Emergebcy Repair of Damaged Container Yard-Back-Up Area caused by 7.2 Magnitude Earthquake | Port of Tagbilaran, Bohol | 2015-04-10 | 1st | PPA | L | 31.233 | 256 | 2014-05-23 | 2015-03-20 | 7.89 | O | 0.379 | 0.3 | 0.15 | 0.03 | 0.06 | 0.05 | 96.9 | -
Edanna Construction | 25492 | L |  |  |  | Emergency Repair of Damaged Container Yard/ Back-Up Area caused by 7.2 Magnitude Earthquake | Port of Tagbilaran | 2014-11-15 | 1st | PPA | L | 31.233 | 300 | 2014-05-25 | 2015-03-20 | 18.282 | O | 0.379 | 0.3 | 0.15 | 0.03 | 0.06 | 0.05 | 96.9 | -
EDANNA CONSTRUCTION | 25492 | L | B | MA | GE | Rehabilitation/Reconstruction/Upgrading of Damage Paved National Roads including Drainage Based on Pavement Management System/Highway Development and Management-4 (HDM-4), (Intermittent Sections), Liloy - Siocon Road, K1967+888 to K1968+300, Zamboanga del Norte | Zamboanga del Norte | 2015-06-03 | Final | Zamboanga del Norte DEO | LF | 3 | 93 | 2015-02-28 | 2015-05-31 | 0% | C | 0.459 | 0.134 | 0.3 | - | - | - | 89.3% | *89.3% Very Satisfactory
EDANNA CONSTRUCTION | 25492 | L | B | MA | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads Including Drainaged based on Pavement Management System/Highway Development and Management-4 (HDM-4)(Intermittent Sections) Liloy-Siocon Road, K1967+888-K1968+300, Liloy, Zamboanga del Norte | Liloy-Siocon Road, K1967+888-K1968+300, Liloy, Zamboanga del Norte | 2015-08-26 | 1st & Final | Zamboanga del Norte 2nd | LF | 2.999 | 92 | 2015-02-28 | 2015-05-30 | - | C | 0.446 | 0.133 | 0.3 | - | - | - | 87.9% | *87.9% Satisfactory
Eddie G. Guillen Builders | 14174 | L | A | MA | GE2 | Repair/Rehab. Of Damaged Revetment & Seawall @ Brgy. San Antonio & Maura under POPSTIRP, Flood Control Component | Aparri, Cagayan | 2011-08-02 | 1st | II / MFCP II- PMO | FA | 14.314 | 102 | 2011-04-25 | 2011-08-04 | 9.9 | O | 0.267 | 0.3 | 0.15 | 0.02 | 0.042 | 0.033 | 81.2 | -
Eddmari Const. & Trading / Cholo Const. & Trading (JV) | JV-07-091 | L | AA | MB | GE1 | Candaba-San Miguel Road |  | 2009-02-24 | 1st | III |  | 25.964 | 234 |  |  |  | O | 0.335 | 0.3 | 0.15 | 0.03 | 0.042 | 0.05 | #VALUE! | -
Eddmari Construction & Trading | 20301 |  |  |  |  | Construction of 4 Units Health/Day Care Center and 2 Units Police Center, NV 3, 4A,4B and 5A |  | 2010-06-04 |  | NHA |  | 8.989 | 90 |  |  |  | O | 0.4 | 0.3 | 0.15 | 0.026 | 0.051 | 0.05 | 97.7 | -
Eddmari Construction & Trading | 20301 |  |  |  |  | Construction of 1-Unit Health/Day Care Center |  | 2010-06-04 |  | NHA |  | 1.998 | 90 |  |  |  | O | 0.4 | 0.3 | 0.15 | 0.024 | 0.049 | 0.05 | 97.3 | -
Eddmari Construction & Trading | 20301 |  |  |  |  | Construction of 1-Unit Police Center |  | 2010-06-04 |  | NHA |  | 0.498 | 90 |  |  |  | O | 0.4 | 0.3 | 0.15 | 0.024 | 0.049 | 0.05 | 97.3 | -
Eddmari Construction & Trading |  | L |  |  | GB1 | Const. of 1 Unit 3-Storey School Building | Lake Breeze, Brgy. Looc, Calamba, Laguna | 2012-08-29 | 1st | NHA | LF | 22.132 | 180 | 2012-04-23 | 2012-10-19 | -26.93 | O | 0.3684 | 0.3 | 0 | 0.02 | 0.0573 | 0.0333 | 77.9 | -
Eddmari Construction and Trading | 20301 | L | AAA | MA | GE2 | Repair/Rehab. of Slope Protection along Sapangbalen @ P. Bulu | Angeles City | 2013-08-06 | 1st | III | LF | 13.622 | 150 | 2013-04-01 | 2013-08-28 | 3.33 | O | 0.369 | 0.24 | 0.15 | 0.03 | 0.047 | 0.033 | 86.9 | -
Eddmari Construction and Trading | 20301 | L | AA | MB | GE1 | Candaba-San Miguel Road |  | 2009-02-24 | 1st | III |  | 45.764 | 193 |  |  |  | O | 0.379 | 0.299 | 0.15 | 0.03 | 0.037 | 0.05 | #VALUE! | -
EDDMARI CONSTRUCTION AND TRADING | 20301 | L | AAA | MA | GE | Widening/Improvement of Manila North Road including Drainage System, San Fernando City Section, 3rd Legislative District, City of San Fernando, Pampanga | City of San Fernando, Pampanga | 2015-06-01 | Final | Pampanga 1st DEO | LF | 46.333 | 206 | 2014-09-30 | 2015-04-22 | 0% | C | 0.353 | 0.2 | 0.3 | - | - | - | 85.3% | *85.3% Satisfactory
Eddmari Construction and Trading/ William Uy Construction Corporation - JV | [5 empty] | Land Development and Construction of Housing Units (St. James Ville) | Brgy. Old Sagay, Sagay, Negros Occidental | 2016-06-04 | Final | NHA | LF | 289.47 | 405 | 2015-03-23 | 2016-04-30 | -0.32 | C | 0.4492 | 0.1937 | 0.2904 | - | - | - | 93.33 | 86.06% Satisfactory
Eddmari Construction and Trading/ William Uy Construction Corporation (JV) | [5 empty] | Land Development and Construction of Housing Units (St. James Ville) | Brgy. Old Sagay, Sagay, Negros Occidental | 2015-11-28 | 1st | NHA | LF | 289.47 | 405 | 2015-03-23 | 2016-04-30 | -2.09 | O | 0.3783 | 0.2103 | 0.1291 | 0.015 | 0.0467 | 0.05 | 82.94 | -
EDISON DEVELOPMENT & CONSTRUCTION | 2400 | L | AAA | LB | GE | Road Upgrading (Unpaved to Paved) of Zamboanga del Sur Coastal Road, Chainage 8290-Chainage 8868.63, Chainage 8981-Chainage 11000, Dumalinao, Zamboanga Del Sur | Dumalinao, Zamboanga Del Sur | 2015-11-12 | 1st | Regional Office | LF | 112.3701 | 312 | 2015-07-06 | 2016-05-12 | 1.02% | OG | 0.334 | 0.24 | 0.15 | 0.03 | 0.051 | 0.05 | 85.5% | 85.5% Satisfactory
EDISON DEVELOPMENT & CONSTRUCTION/EGB CONSTRUCTION (Joint Venture) | JV-14-718 | L | AAA | LB | GE | National Road Network Services - Network Development: Widening of National Roads Arterial Roads and National Road 1 (N1)/Daang Maharlika/Asian Highway-26, K0408+797 to K0415+529 (w/ Exception), K0428+000 to K0429+700, Tumauini and Ilagan, Isabela | Tumauini and Ilagan, Isabela | 2015-08-27 | 1st | Regional Office No. II | LF | 131.113 | 270 | 2015-03-30 | 2015-12-24 | 16.03% | O | 0.382 | 0.238 | 0.15 | 0.03 | 0.051 | 0.05 | 90.1% | -
Edison Development and Construction | [5 empty] | Greendale Residences 2 | Brgy. San Isidro (Suhi), Tacloban City | 2016-06-25 | 1st | NHA | LF | 245.672 | 365 | 2014-12-22 | 2016-08-25 | -13.26 | O | 0.3496 | 0.2629 | 0.0174 | 0.03 | 0.0653 | 0.0332 | 75.84 | -
Edison Development Construction | 2400 | L | AAA | MB | GE | Construction/Rehabilitation of Drainage Slope Protection Along Jct. Dumalinao-Margosatubig K1702+000 - K1705+180 (Intermittent Section) | Zamboanga del Sur | 2014-10-26 | 1st | IX | LF | 8.3042 | 270 | 2014-07-09 | 2015-04-04 | 67.84% | O | 0.279 | 0.286 | 0.15 | 0.03 | 0.045 | 0.033 | 82.3% | 82.30% Satisfactory
EDISON DEVELOPMENT CORPORATION | 2400 | L | AAA | LB | GE | Construction/Rehabilitation of Drainage/Slope Protection along Jct. Dumalinao - Margosaubig Road, K1702+000 to K1705+180, Intermittent Section, Zamboanga del Sur | Zamboanga del Sur | 2015-06-07 | Final | Zamboanga del Sur 3rd DEO | LF | 8.304 | 270 | 2014-07-09 | 2015-04-04 | 11.84% | C | 0.452 | 0.133 | 0.3 | - | - | - | 88.5% | *88.5% Satisfactory
EDMOND RAY CONSTRUCTION & SUPPLY | 33167 | L | C | SB | GE | Concreting of Road Barangay Agusan, Cagayan de Oro City | Barangay Agusan, Cagayan de Oro City | 2015-08-26 | 1st & Final | Cagayan de Oro City Second DEO | LF | 5.163 | 150 | 2015-03-30 | 2015-08-26 | 24.14% | C | 0.474 | 0.136 | 0.3 | - | - | - | 91% | *91.00% Very Satisfactory
Edmond Ray Construction and Supply | 33167 | L | C | SB | GB1 | Const. of Sch. Bldg., Montol NHS | Ozamis City | 2013-08-16 | 1st | X | LF | 2.195 | 137 | 2013-03-27 | 2013-08-10 | -5 | O | 0.376 | 0.3 | 0.056 | 0.03 | 0.05 | 0.033 | 84.5 | -
EDROX CONSTRUCTION INC. (Formerly: Edrox Construction and Supply) | 10926 | L | B | MA | GE | Concreting of Barangay Road | Haluban, Lupi, Camarines Sur | 2015-06-05 | Final | Camarines Sur 5th | LF | 1.926 | 90 | 2015-01-21 | 2015-04-20 | 3.33% | C | 0.455 | 0.148 | 0.3 | - | - | - | 90.3% | *90.3% Very Satisfactory
Edwin Erwin Sison Construction | 20162 | L | D | SB | GB | Construction of Classroom at Bayombong Central School | Bayombong, Nueva Vizcaya | 2014-10-29 | 1st | II | LF | 3.8608 | 110 | 2014-09-09 | 2014-12-27 | 42.93% | O | 0.334 | 0.3 | 0.15 | 0.03 | 0.029 | 0.033 | 87.6% | 87.60% Satisfactory
EDWIN ERWIN SISON CONSTRUCTION | 20162 | L | D | SB | GB | Construction of Classroom, Bayombong C/S | Bayombong, Nueva Vizcaya | 2015-06-09 | Final | Nueva Vizcaya 1st DEO | LF | 3.861 | 110 | 2014-09-09 | 2014-12-27 | 8.73% | C | 0.462 | 0.154 | 0.3 | - | - | - | 91.6% | *88.94% Satisfactory
EDWIN ERWIN SISON CONSTRUCTION | 20162 | L | D | SB | GE | Local Infrastructure Program - Construction of Baragngay Road, Villa Florentino Road, Diadi, Nueva Vizcaya | Villa Florentino Road, Diadi, Nueva Vizcaya | 2015-11-18 | Final | NUEVA VIZCAYA 1ST DEO | LF | 0.93426 | 120 | 2015-04-03 | 2015-07-31 | - | C | 0.469 | 0.138 | 0.3 | - | - | - | 90.7% | 90.7% Very Satisfactory
EGB Construction | 13722 | L | A | MA | GE1 | Rehab./Strengthening of Minanga Bridge, Minanga | Tumaini, Isabela | 2013-03-13 | 1st | II | LF | 9.133 | 123 | 2013-01-28 | 2013-05-30 | 1.2 | O | 0.353 | 0.194 | 0.15 | 0.03 | 0.056 | 0.05 | 83.3 | -
EGB Construction | 13722 |  |  |  |  | Conc. of Ilagan-Bigao-Palanan Rd. |  | 2010-05-29 |  | II |  | 14.475 | 110 |  |  |  | O | 0.38 | 0.24 | 0.15 | 0.03 | 0.056 | 0.033 | 88.9 | -
EGB Construction | 13722 |  |  |  |  | Const./Impvt. of Public Market |  | 2010-05-28 |  | II |  | 2.406 | 120 |  |  |  | O | 0.378 | 0.24 | 0.15 | 0.03 | 0.051 | 0.033 | 88.2 | -
EGB Construction | 13722 | L | A | MA | GE2 | Repair of Flood Control Project, Baculud | Amulung, Cagayan | 2012-08-03 | 1st | II | LF | 20.37 | 210 | 2012-03-15 | 2012-10-10 | 0.12 | O | 0.34 | 0.3 | 0.15 | 0.03 | 0.04 | 0.05 | 91 | -
EGB CONSTRUCTION | 13722 | L | A | MA | GE | Repair/Rehabilitation/Improvement of Daang Maharlika, Ilagan Isabela | K0405+155 - K0407+000 with exceotions, Ilagan, Isabela | 2015-06-04 | Final | Isabela 1st DEO | LF | 10.89 | 157 | 2014-11-20 | 2015-04-25 | 0% | C | 0.336 | 0.2 | 0.3 | - | - | - | 83.6% | *83.6% Satisfactory
EGB CONSTRUCTION | 13722 | L | A | MA | GB | Construction of Multi-Purpose Building in Tumauini, Tumauini, Isabela | Tumauini, Isabela | 2015-08-27 | 1st | Isabela 1st DEO | LF | 18.798 | 280 | 2015-03-26 | 2015-12-30 | 12.36% | O | 0.358 | 0.239 | 0.15 | 0.03 | 0.058 | 0.05 | 88.5% | -
EGB CONSTRUCTION | 13722 | L | A | MA | GE | Construction/Upgrading/Rehabilitation of Drainage along Cagayan-Apayao Road, K0488+358 - K0488+021, K0488+043 - K0488+203, K0488+621 - K0488+801, Abulug, Cagayan | Abulug, Cagayan | 2015-11-11 | Final | CAGAYAN 3RD DEO | LF | 8.7268 | 270 | 2015-04-21 | 2016-01-15 | (+) 57.53 | C | 0.492 | 0.133 | 0.3 | - | - | - | 92.5% | 92.5% Very Satisfactory
EGB CONSTRUCTION/KATHA BUILDERS & SUPPLIES JOINT VENTURE | JV-14-760 | L | A | MA | GE | Tangaoan-Pallas Road Leading to Paraiso Ecotourism Project Eco & Reforestation Project, Piddig, Ilocos Norte | Piddig, Ilocos Norte | 2015-08-25 | 1st | Ilocos Norte 1st DEO | LF | 39.856 | 224 | 2015-03-24 | 2015-11-02 | (+)6.8 | O | 0.342 | 0.234 | 0.15 | 0.03 | 0.035 | 0.05 | 84.1% | -
El Kapitan Construction Service | 33123 | L | C | SB | GB1 | Const./Conc./Rehab./Completion of Sto. Tomas Multi-purpose Bldg. |  | 2009-08-24 | 1st | III |  | 0.475 | 35 |  |  |  | O | 0.356 | 0.24 | 0.15 | 0.03 | 0.051 | 0.05 | 87.7 | -
EL TENA CONSTRUCTION | 37244 | L | D | SB | GE | Construction of Multi Purpose Building | Brgy. Banguinge, Kiangan, Ifugao | 2015-06-06 | 1st | Ifugao 1st DEO | LF | 1.881 | 120 | 2015-04-15 | 2015-08-12 | (+) 2.54 | O | 0.308 | 0.3 | 0.15 | 0.03 | 0.047 | 0.05 | 88.52% | -
EL-JAKE BUILDERS | 38162 | L | B | SB | GE | Concreting of Barangay Road leading to Katipunan Elementary, Guipos, Zamboanga del Sur | Guipos, Zamboanga del Sur | 2015-06-07 | Final | Zamboanga del Sur 2nd DEO | LF | 13.695 | 48 | 2015-02-27 | 2015-04-15 | 4.17% | C | 0.432 | 0.138 | 0.3 | - | - | - | 87% | *87% Satisfactory
EL-JAKE BUILDERS | 38162 | L | B | SB | GE | Rehabilitation/Major Repair of Nilo Bridge (BO0547MN) along Pagadian City - Zamboanga City Road, Brgy. Nilo, Tigbao, Zamboanga Del Sur | Brgy. Nilo, Tigbao, Zamboanga Del Sur | 2015-11-12 | Final | Zamboanga Del Sur 2nd DEO | LF | 0.97777 | 25 | 2015-02-27 | 2015-03-23 | - | C | 0.452 | 0.133 | 0.3 | - | - | - | 88.5% | 88.5% Satisfactory
ELKANKONSTRAK DEVELOPMENT CORPORATION (Formerly: Elkan Konstrak & Aggregates) | 26220 | L | A | MA | GE | Cluster 1 - Local Infrastructure Program-Construction of Local Road (Road Opening) & Drainage Canal & Slope Protection, Daraga, Albay | Daraga, Albay | 2015-11-11 | Final | Albay Second DEO | LF | 14.2048 | 158 | 2015-02-09 | 2015-07-16 | 0.63% | C | 0.4 | 0.128 | 0.3 | - | - | - | 82.8% | 82.8% Satisfactory
ELKANKONSTRAK DEVELOPMENT CORPORATION (Formerly: Elkan Konstrak & Aggregates) | 26220 | L | A | MA | GE | Construction of Flood Mitigation Structures (Daplian River Control) at Daplian | San Jacinto, Masbate | 2015-06-11 | 1st | Masbate 3rd | LF | 9.293 | 140 | 2015-03-11 | 2015-07-28 | -1.9% | O | 0.326 | 0.29 | 0.131 | 0.022 | 0.04 | 0.033 | 84.2% | -
EM PAULE CONSTRUCTION AND TRADING | 19006 | L | A | MA | GE | Widening of National Road, Paving of Shoulder, Uyugan-Mahatao Road | Uyugan-Mahatao, Batanes | 2015-06-12 | 1st | Batanes DEO | LF | 14.669 | 240 | 2015-03-02 | 2015-10-27 | 33.76% | O | 0.368 | 0.244 | 0.15 | 0.03 | 0.047 | 0.033 | 87.2% | -
EML Construction & Trading | 10151 | L | B | MA | GE | Reconstruction of Damaged Paved National Roads Inlcuding Drainage based on PMS/HDM-4 (Intermittent Section) Bigaa-Plaridel via Bulacan and Malolos Road K0040+500 to K0041+500 & K0045+1006 to K0049+381 | Malolos City, Bulacan | 2014-11-24 | 1st | III | LF | 28.4218 | 300 | 2014-05-16 | 2015-03-11 | -0.84% | O | 0.323 | 0.3 | 0.142 | 0.03 | 0.037 | 0.033 | 86.5% | 86.50% Satisfactory
EML Construction & Trading | 10151 | L | B | MA | GE | Widening of Old Cagayan Valley Road (Baliuag Section) Km. 46+284 to Km. 52+985 | Baliuag, Bulacan | 2014-11-07 | 1st | III | LF | 25.6856 | 241 | 2014-06-03 | 2015-01-29 | 2.84% | O | 0.348 | 0.24 | 0.15 | 0.03 | 0.045 | 0.033 | 84.6% | 84.60% Satisfactory
EML CONSTRUCTION & TRADING | 10151 | L | B | MA | GE | Widening of Old Cagayan Valley Road (Baliuag Section), Km 46+284 to Km 52+985, Baliuag, Bulacan | Baliuag, Bulacan | 2015-06-12 | Final | Bulacan 1st DEO | LF | 25.685 | 241 | 2014-06-03 | 2015-01-29 | 0% | C | 0.432 | 0.2 | 0.3 | - | - | - | 93.2% | *93.2% Very Satisfactory
EMRA Construction and Supply Services | 36624 | L | D | SB | GE | Tourist Information Center and Tourist Rest Area (Green Restroom) | Sto. Domingo, Albay | 2016-03-17 | 1st | TIEZA | LF | 4 | 120 | 2015-12-02 | 2016-03-31 |  | O | 0.377 | 0.3 | 0.086 | 0.03 | 0.044 | 0.05 | 88.7
EMRA Construction and Supply Services | 36624 | L | D | SB | GE | Tourist Information Center and Tourist Rest Area (Green Restroom) | Sto. Domingo, Albay | 2016-05-19 | Final | TIEZA | LF | 4 | 120 | 2015-12-02 | 2016-03-31 |  | C | 0.444 | 0.196 | 0.3 |  |  |  | 94 | 90.29 Very Satisfactory
ENC ENTERPRISES | 29819 | L | D | SB | GB | Construction of One (1) Storey, Two (2) CL School Building, Balian NHS (Galalan Annex) Pangil, Laguna | Pangil, Laguna | 2015-11-18 | Final | LAGUNA 1ST DEO | LF | 2.2088 | 60 | 2015-09-03 | 2015-11-01 | 0 | C | 0.351 | 0.2 | 0.3 | - | - | - | 85.1% | 85.1% Satisfactory
ENRIQUE A. FLORES, JR. CONTRACTOR | 2421 | L | A | MA | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads including Drainage Based on Pavement Management System/Highway Development and Management-4 (HDM-4) (Intermittent Section), Gen. Luna Rd., K0251+(-866) to K0251+(-404), Baguio City | Baguio City | 2015-09-04 | 1st & Final | Baguio City DEO | LF | 10.108 | 120 | 2015-02-06 | 2015-06-05 | 0% | C | 0.421 | 0.133 | 0.3 | - | - | - | 85.4% | *85.4% Satisfactory
EPL General Construction and Supply | 15559 | L | A | MA |  | CONSTRUCTION OF TWO(2) STOREY REGIONAL OFFICE BUILDING P-1, RO-V | Naga City | 2015-04-17 | 1st | NIA | L | 24.779 | 300 | 2014-03-21 | 2015-05-16 | -11.88 | O | 0.3437 | 0.3 | 0.0906 | 0.0646 | 0.02 | 0.05 | 86.89 | -
EPN Builders & Developers | 30341 | L |  | SB | GE2 | Colocol Integrated CIS Rehabilitation & Extension Project | Bayombong, nueva Vizcaya | 11/07-12/11 | 1st | NIA | LF | 9.525 | 180 | 2011-06-06 | 2011-12-02 | -1.74 | O | 0.3779 | 0.2437 | 0.1326 | 0.024 | 0.07 | 0.05 | 89.82 | -
Equi-Parco Construction | 14332 | L | AAA | LB | GE-2 | UMAYAM RIVER IRRIGATION PROJECT | LA PAZ-LORETO, AGUSAN DEL SUR, REGION XIII | 2015-09-12 | 1st | NIA | LF | 25.695 | 541 | 2014-03-14 | 2015-09-05 | 0.26 | O | 0.3243 | 0.24 | 0.15 | 0.015 | 0.06 | 0.05 | 83.93 | -
Equi-Parco Construction |  | L | AAA | LB | DE-2 | UMAYAM RIVER IRRIGATION PROJECT | LA PAZ-LORETO, AGUSAN DEL SUR, REGION XIII | 2015-09-12 | 1st | NIA | LF | 246.4 | 670 | 2014-09-24 | 2016-07-24 | 20.93 | O | 0.3403 | 0.24 | 0.15 | 0.015 | 0.06 | 0.05 | 85.53 | -
Equi-Parco Construction |  | L | AAA | LB | GE2 | PIDP/Batutu River Irrigation System PIDP11-C-BRISN-1 | Compostela Valley/Region 11 | 2014-05-17 | 1st | NIA | LF | 76.047 | 469 | 2013-06-24 | 2014-06-24 | 11.16 | O | 0.3471 | 0.2705 | 0.15 | 0.03 | 0.055 | 0.05 | 90.26 | -
Equi-Parco Construction |  | L | AAA | LB | GE2 | PIDP/Batutu River Irrigation System PIDP11-C-BRISN-2 | Compostela Valley/Region 11 | 2014-05-17 | 1st | NIA | LF | 76.325 | 469 | 2013-06-24 | 2014-10-05 | 22.05 | O | 0.2764 | 0.3 | 0.15 | 0.03 | 0.065 | 0.05 | 87.14 | -
Equi-Parco Construction | 14332 | L | AAA | LB | GE1 | Conc. of Misamis Oriental-Bukidnon-Agusan Road |  | 2009-06-10 | 2nd | X |  | 91.466 | 330 |  |  |  | O | 0.271 | 0.3 | 0.15 | 0.03 | 0.043 | 0.05 | 84.4 | -
Equi-Parco Construction | 14332 | L | AAA | LB | GE1 | Conc. of Misamis Oriental-Bukidnon-Agusan Road |  | 2009-03-19 | 1st | X |  | 91.466 | 330 |  |  |  | O | 0.347 | 0.3 | 0.1 | 0.03 | 0.045 | 0.05 | #VALUE! | -
Equi-Parco Construction | 14332 | L | AAA | LB | GE1 | Rehab./Reconst. of Butuan City-Cagayan De Oro City- Iligan Road |  | 2009-09-09 | 1st | X |  | 145.175 | 405 |  |  |  | O | 0.357 | 0.3 | 0.15 | 0.03 | 0.056 | 0.05 | 94.3 | -
Equi-Parco Construction | 14332 | L | AAA | LB | GE1 | Rehab./Reconst. of Butuan City-Cagayan de Oro City-Iligan City (BCIR) Road |  | 2009-09-07 | 1st | X |  | 474.722 | 360 |  |  |  | O | 0.378 | 0.248 | 0.15 | 0.03 | 0.07 | 0.05 | 92.6 | -
Equi-Parco Construction | 14332 | L | AAA | LB | GE1 | Conc. of Agusan del Norte-Surigao del Sur (Cabadbaran-Puting Bato Section) |  | 2009-03-03 | 2nd | XIII |  | 95.698 | 540 |  |  |  | O | 0.335 | 0.3 | 0.15 | 0.03 | 0.056 | 0.05 | #VALUE! | -
Equi-Parco Construction | 14332 | L | AAA | LB | GE1 | Construction of Butuan City By-Pass Road, Bonbon-Kinamlutan Section |  | 2009-03-19 | 1st | XIII |  | 24.594 | 195 |  |  |  | O | 0.353 | 0.3 | 0.15 | 0.03 | 0.042 | 0.05 | #VALUE! | -
Equi-Parco Construction | 14332 | L | AAA | MB | GE2 | Rechanneling of Cabadbaran River, Putting Bato, Phase 1 |  | 2009-03-03 | 1st | XIII |  | 19.28 | 180 |  |  |  | O | 0.334 | 0 | 0.2 | 0.05 | 0.067 | 0.25 | #VALUE! | -
Equi-Parco Construction | 14332 | L | AAA | LB | GE1 | Upgrading of Agusan-Bukidnon National Rd. |  | 2009-09-01 | 2nd | XIII |  | 14.326 | 210 |  |  |  | O | 0.394 | 0.216 | 0.15 | 0.03 | 0.05 | 0.05 | 89 | -
Equi-Parco Construction | 14332 | L | AAA | LB | GE1 | Upgrading of Agusan-Bukidnon National Road |  | 2009-05-25 | 1st | XIII |  | 14.326 | 210 |  |  |  | O | 0.393 | 0.3 | 0.15 | 0.03 | 0.047 | 0.05 | 97 | -
Equi-Parco Construction | 14332 | L | AAA | LB | GE1 | Rehab./Reconst. of Buenavista-Bunaguit Road Section |  | 2009-05-25 | 1st | XIII |  | 7.572 | 180 |  |  |  | O | 0.376 | 0.3 | 0.15 | 0.03 | 0.047 | 0.05 | 95.3 | -
Equi-Parco Construction | 14332 | L | AAA | LB | GE1 | Concreting of Butuan City-Masao Port Rd., Jct. Doongan Bridge |  | 2009-09-16 | 1st | XIII |  | 14.213 | 195 |  |  |  | O | 0.378 | 0.24 | 0.15 | 0.03 | 0.06 | 0.05 | 90.8 | -
Equi-Parco Construction | 14332 | L | AAA | LB | GE1 | Const./Conc. of SDCR(Lingig Boundary-Boston Sect.) along Bislig-Boston Sect. |  | 2009-09-11 | 1st | XIII |  | 325.527 | 585 |  |  |  | O | 0.383 | 0.225 | 0.15 | 0.03 | 0.065 | 0.05 | 90.3 | -
Equi-Parco Construction Company | 3507 | L | AAA |  | GE-5 | Wharf Extension Project | Port of Masao, Butuan City | 2015-12-04 | 1st | PPA | LF | 130.911 | 390 | 2015-07-21 | 2016-08-14 | 65.189 | O | 0.3991 | 0.3 | 0.15 | 0.03 | 0.0607 | 0.05 | 98.98 | -
Equi-Parco Construction Company | 24715 | L |  |  |  | Lipata Port Expansion & Improvement Project | Brgy. Lipata, Surigao del Norte | 2014-09-26 | 1st | PPA | LF | 75.531 | 390 | 2013-09-10 | 2014-10-04 | -1.797 | O | 0.371 | 0.3 | 0.15 | 0.03 | 0.061 | 0.05 | 96.2 | -
Equi-Parco Construction Company | 14332 | L | AAA | LB |  | San Jose Airport Development Project | Brgy. San Roque Dos, San Jose, Occ. Mindoro/ Region IV-B | 2015-03-13 | 2nd | DOTC | L | 88.404 | 398 | 2014-03-18 | 2015-06-15 | 1.88 | O | 0.3972 | 0.3 | 0.15 | 0.03 | 0.0445 | 0.05 | 97.17 | -
Equi-Parco Construction Company | 14332 | L | AAA | LB | GE-1 | San Jose Airport Development Project | San Jose, Occidental Mindoro/Region IV-B | 2014-11-29 | 1st | DOTC | LF | 88.404 | 360 | 2014-03-18 | 2015-06-15 | 1.09 | O | 0.4 | 0.3 | 0.15 | 0.03 | 0.055 | 0.05 | 98.5 | -
Equi-Parco Construction Company | 14332 | L | AAA | LB | GE1 | Caminawit Port Development Project | Brgy Caminawit, San Jose, Occidental Mindoro / Region IV - B | 2014-03-12 | 2nd | DOTC | LF | 73.313 | 270 | 2013-05-05 | 2014-05-13 | 1.07 | O | 0.3937 | 0.3 | 0.15 | 0.03 | 0.038 | 0.05 | 96.17 | -
Equi-Parco Construction Company | 14332 | L | AAA | LB | GE2 | Const. of Cagayan de Oro Coastal Rd. (By-Pass Rd.) inc. ROW, K1434+820-K01436+180.00 | Cagayan de Oro City | 2013-08-16 | 2nd | X | LF | 137.944 | 328 | 2012-09-24 | 2013-08-16 | -3.42 | O | 0.314 | 0.3 | 0.116 | 0.03 | 0.053 | 0.033 | 84.6 | -
Equi-Parco Construction Company | 14332 | L | AAA | LB | GE1 | Widening/Conc. of Butuan City-Cagayan de Oro City-Iligan City Rd. (Opol-Laguindingan-Airport Sect.) Km.1466+282.80-Km.1467+282.80 | Laguindingan, Misamis Oriental | 2013-03-12 | 2nd | X | LF | 83.789 | 330 | 2012-07-11 | 2013-06-05 | 2.18 | O | 0.35 | 0.3 | 0.15 | 0.02 | 0.045 | 0.033 | 89.8 | -
Equi-Parco Construction Company | 14332 | L | AAA | LB | GE1 | Widening/Conc. of Butuan City-Cagayan de Oro-Iligan City Rd. (Opol-Laguindingan Airport Sect.) Km.1466+282.80-Km.1467+282.80 | Laguindingan, Misamis Oriental | 2012-11-23 | 1st | X | LF | 83.789 | 330 | 2012-07-11 | 2013-06-05 | 0.93 | O | 0.366 | 0.246 | 0.15 | 0.03 | 0.045 | 0.05 | 88.7 | -
Equi-Parco Construction Company | 14332 | L | AAA | LB | GE2 | Const. of Slope Protection at Iponan River (Downstream of Iponan Bridge I & II) Bulua Side, along BCIR, Phase I | Cagayan de Oro City | 2013-03-11 | 2nd | X | LF | 15.412 | 183 | 2012-09-21 | 2013-03-22 | 0.17 | O | 0.314 | 0.27 | 0.15 | 0.03 | 0.042 | 0.05 | 85.6 | -
Equi-Parco Construction Company | 14332 | L | AAA | LB | GE2 | Cons. of Slope Protection at Iponan River (Downstream of Iponan Bridge I and II) Bulua side along BCIR, Phase I | Cagayan de Oro City | 2012-11-24 | 1st | X | LF | 15.412 | 153 | 2012-09-21 | 2013-02-20 | 1.74 | O | 0.3 | 0.3 | 0.15 | 0.03 | 0.04 | 0.033 | 85.3 | -
Equi-Parco Construction Company | 14332 | L | AAA | LB | GE1 | Rehab./Replacement of Mandulog Bridges I Bridge ID: B00606MN along Highway Secondary Diversion Rd., Rd. ID: R01497MN, Sect. ID: S00961MN, Km.1522+(-484) const. of 2 lanes 240m conc. bridge w/ 6 spans @ 40m per span | Iligan City | 2013-03-15 | 2nd | X | LF | 137.639 | 360 | 2012-05-28 | 2013-05-22 | 2.03 | O | 0.293 | 0.292 | 0.15 | 0.015 | 0.047 | 0.033 | 83 | -
Equi-Parco Construction Company | 14332 | L | AAA | LB | GE1 | Rehab./Replacement of Mandulog Bridge I, Bridge: ID: B00606MN, along Highway Secondary Diversion Rd., Rd. ID: R01497MN Sect. ID: S00961 MN Location: K1522+(-484) Const. of Two (2) Lanes 240 m. Concrete Bridge with 6 Spaces @ 40 m. per Span | Lanao del Norte | 2012-11-26 | 1st | X | LF | 137.639 | 210 | 2012-05-28 | 2012-12-23 | 0.54 | O | 0.335 | 0.3 | 0.15 | 0.03 | 0.04 | 0.033 | 88.8 | -
Equi-Parco Construction Company | 14332 | L | AAA | LB | GE2 | Cagayan de Oro River Basin | Cagayan de Oro City | 2013-03-18 | 2nd | X | LF | 46.562 | 240 | 2012-07-27 | 2013-03-23 | 5.98 | O | 0.268 | 0.246 | 0.15 | 0.03 | 0.051 | 0.05 | 79.5 | -
Equi-parco Construction Company | 14332 | L | AAA | LB | GE1 | Rehab./Reconst./Upgrading Damaged Paved Nat'l Rd., Butuan City-Cagayan De Oro City-Iligan Rd a.)Km.1459+980-Km.1459+1002.35 & b.)Km.1460+0-Km.1460+1000 | Alubijid, Misamis Oriental | 2011-08-13 | 1st | X | LF | 13.09 | 165 | 2011-04-07 | 2011-09-18 | 9.43 | O | 0.375 | 0.24 | 0.15 | 0.03 | 0.05 | 0.033 | 87.8 | -
Equi-Parco Construction Company | 14332 | L | AAA | LB | GE1 | Rehab./Reconst./Strengthening of Bridges along Nat'l Rds., Kibaluyot Bridge along BCIR | Gingoog City | 2012-11-22 | 2nd | X | LF | 26.234 | 330 | 2012-03-09 | 2013-02-01 | 1.47 | O | 0.4 | 0.2 | 0.15 | 0.03 | 0.045 | 0.033 | 85.8 | -
Equi-Parco Construction Company | 14332 | L | AAA | LB | GE2 | Const. of Cagayan de Oro Coastal Rd. (By-Pass Rd.), inc. ROW | Cagayan de Oro City | 2012-11-24 | 1st | X | LF | 137.944 | 269 | 2012-09-24 | 2013-06-18 | 9.78 | O | 0.371 | 0.227 | 0.15 | 0.03 | 0.04 | 0.033 | 85.1 | -
Equi-Parco Construction Company | 14332 | L | AAA | LB | GE2 | Cagayan de Oro River Basin | Cagayan de Oro City | 2012-11-24 | 1st | X | LF | 46.077 | 210 | 2012-07-27 | 2013-02-21 | 17.12 | O | 0.27 | 0.3 | 0.15 | 0.03 | 0.04 | 0.033 | 82.3 | -
Equi-Parco Construction Company | 14332 | L | AAA | LB | GE1 | Repair/Rehab./Strengthening of Bridges along Nat'l Rds., Kibaluyot Bridge along BCIR | Gingoog City | 2012-08-14 | 1st | X | LF | 26.234 | 330 | 2012-03-09 | 2013-02-01 | 0.04 | O | 0.343 | 0.3 | 0.15 | 0.03 | 0.045 | 0.033 | 90.1 | -
Equi-Parco Construction Company | 14332 | L | AAA | LB | GE | Road Upgrading (Gravel to Concrete) of Buenavista-Bunaguit Road, K1261+822.33 - K1262+520.33, K1267+360 - K1271+919, K1273+520 - K1274+000, K1276+486.27 - K1277+063 | Buenavista, Agusan del Norte | 2014-10-30 | 1st | XIII | LF | 120.3759 | 270 | 2014-04-14 | 2015-01-08 | 0.38% | O | 0.372 | 0.251 | 0.15 | 0.022 | 0.047 | 0.05 | 89.2% | 89.20% Very Satisfactory
Equi-Parco Construction Company | 14332 | L | AAA | LB | GE | Construction of Butuan City Bypass Road (Lemon - NRJ - Antongalon Section), K1237+894 - K1234+720 | Butuan City | 2014-10-10 | 1st | XIII | LF | 123.5064 | 270 | 2014-05-15 | 2015-02-08 | 23.52% | O | 0.31 | 0.3 | 0.15 | 0.022 | 0.047 | 0.05 | 87.9% | 87.90% Satisfactory
Equi-Parco Construction Company | 14332 | L | AAA | LB | GE | Rehabilitation/Reconstruction/Replacement/Retrofitting of Pandanon Bridge along Daang Maharlika (Surigao-Agusan Road) | Cabadbaran City, Agusan del Norte | 2014-10-20 | 1st | XIII | LF | 19.7938 | 280 | 2014-02-05 | 2014-11-11 | 2.62% | O | 0.343 | 0.259 | 0.15 | 0.022 | 0.042 | 0.05 | 86.6% | 86.60% Satisfactory
Equi-Parco Construction Company | 14332 | L | AAA | LB | GE2 | Impvt. of Drainage Facilities along Butuan City-Malaybalay Rd. Montilla Blvd. Sect. | Butuan City | 2013-08-23 | 1st | XIII | LF | 16.739 | 220 | 2013-03-28 | 2013-11-02 | 2.63 | O | 0.392 | 0.24 | 0.15 | 0.03 | 0.04 | 0.05 | 90.2
Equi-Parco Construction Company | 14332 | L | AAA | LB | GE1 | Widening/Conc. of Add'l Lane along Daang Maharlika (Agusan-Surgao Rd.), Ampayon Sect. | Butuan City | 2013-03-21 | 1st | XIII | LF | 37.027 | 192 | 2013-01-30 | 2013-08-09 | 9.66 | O | 0.274 | 0.3 | 0.15 | 0.03 | 0.06 | 0.05 | 86.4 | -
Equi-Parco Construction Company | 14332 | L | AAA | LB | GE1 | Widening of Butuan-Cagayan de Oro-Iligan (Agusan-Misamis Oriental Rd.), Agusan del Norte, Dumalagan to Bdry. Sect. | Butuan City | 2013-03-21 | 1st | XIII | LF | 27.791 | 150 | 2013-01-30 | 2013-06-28 | 61.29 | O | 0.382 | 0.205 | 0.15 | 0.03 | 0.055 | 0.033 | 85.5 | -
Equi-Parco Construction Company | 14332 | L | AAA | LB | GE1 | Rehab. of Damaged Paved Nat'l Rd. along Daang Maharlika Road (Surigao-Agusan Section) a.Kitcharao-Cabadbaran Sect.; b.Luna Bad-as Sect. | Surigao del Norte | 2012-08-07 | 1st | XIII | LF | 110.082 | 120 | 2012-04-24 | 2012-08-21 | 0.46 | O | 0.354 | 0.3 | 0.15 | 0.03 | 0.055 | 0.033 | 92.2 | -
Equi-Parco Construction Company |  | L | AAA | LB |  | PIDP/BATUTU RIVER IRRIGATION SYSTEM PIDP11-C-BRISN-1 | Compostela Valley/ Region 11 | 2015-11-28 | Final | NIA | LF | 76.047 | 702 | 2013-06-26 | 2015-05-29 | 0 | C | 0.393 | 0.2 | 0.3 | - | - | - | 89.3 | 89.20% V. Satisfactory
Equi-Parco Construction Company |  | L | AAA | LB |  | PIDP/BATUTU RIVER IRRIGATION SYSTEM PIDP11-C-BRISN-2 | Compostela Valley/ Region 11 | 2015-11-28 | Final | NIA | LF | 76.325 | 705 | 2013-06-24 | 2014-05-29 | 0 | C | 0.44 | 0.2 | 0.3 | - | - | - | 94 | 89.87% V. Satisfactory
Equi-Parco Construction Company |  | L | AAA | LB |  | PIDP/BATUTU RIVER IRRIGATION SYSTEM PIDP11-C-BRISN-3 | Compostela Valley/ Region 11 | 2015-11-28 | 1st | NIA | LF | 80.501 | 788 | 2013-09-26 | 2015-11-23 | -6.56 | O | 0.3795 | 0.3 | 0.0844 | 0.03 | 0.07 | 0.05 | 91.39 | -
Equi-Parco Construction Company | 3507 |  | AAA |  |  | Wharf Extension Project | Port of Masao, Butuan City | 2016-03-04 | 2nd | PPA | LF | 130.911 | 390 | 2015-07-21 | 2016-08-14 | 50.187 | O | 0.39 |  | 0.15 | 0.03 | 0.065 | 0.05 | 68.5 | -
EQUI-PARCO CONSTRUCTION COMPANY | 14332 | L | AAA | LB | GE | Rehabilitation /Reconstruction/ Upgrading of Damaged Paved along Daang Maharlika (Surigao-Agusan Section) | K1180+1440 - K1181+500, K1179+000 - K1179+976, Kitcharo, Agusan Del Norte | 2015-06-02 | 1st | AGUSAN DEL NORTE DEO | LF | 23.778 | 141 | 2015-02-12 | 2015-07-02 | (+) 0.83% | O | 0.396 | 0.239 | 0.15 | 0.03 | 0.05 | 0.05 | 91.5% | -
EQUI-PARCO CONSTRUCTION COMPANY | 14332 | L | AAA | LB | GE | Construction of Cagayan de Oro City Coastal Road (By-Pass Road), Including RROW, K1434+820 - K1438+195, Cagayan de Oro City 2nd LD | K1434+820 - K1438+195, Cagayan de Oro City 2nd LD | 2015-06-10 | 1st | Regional Office X | LF | 206.329 | 366 | 2015-04-21 | 2016-04-20 | - | O | 0.358 | 0.291 | 0.15 | 0.03 | 0.07 | 0.05 | 94.9% | -
EQUI-PARCO CONSTRUCTION COMPANY | 14332 | L | AAA | LB | GE | Construction of Cagayan de Oro City Coastal Road (By-Pass Road), Including RROW, K1434+820- K1438+195, Cagayan de Oro City | K1434+820- K1438+195, Cagayan de Oro City | 2015-09-05 | 2nd | Regional Office No. X | LF | 206.329 | 366 | 2015-04-21 | 2016-04-20 | 44.68% | O | 0.394 | 0.239 | 0.15 | 0.03 | 0.06 | 0.05 | 92.3% | -
EQUI-PARCO CONSTRUCTION COMPANY | 14332 | L | AAA | LB | GE | Construction/Improvement of Misamis Oriental-Bukidnon-Agusan Road (Buenavista-Simbalan-Bukidnon Boundary Section), Including RROW | Buenavista, Agusan del Norte | 2015-09-02 | Final | Regional Office No. XIII | LF | 49.655 | 180 | 2015-02-27 | 2015-08-25 | (+) 23.44% | C | 0.433 | 0.2 | 0.3 | - | - | - | 93.3% | *93.12% Very Satisfactory
Equi-Parco Construction Company | 3507 |  | AAA |  |  | Wharf Extension Project | Port of Masao, Butuan City | 2016-10-19 | 3rd & Final | PPA | LF | 141.446 | 466 | 2016-07-21 | 2016-10-28 | 0.663 | C | 0.4803 | 0.2 | 0.3 | - | - | - | 98.03 | 98.41% Outstanding
EQUI-PARCO CONSTRUCTION COMPANY | 14332 | L | AAA | LB | GE | Construction of Cagayan de Oro City Coastal Road (By-Pass Road), Including RROW, K1434+820 - K1438+195, Cagayan de Oro City | Cagayan de Oro City | 2015-11-10 | 2nd | Regional Office | LF | 206.3292 | 366 | 2015-04-21 | 2016-04-21 | (+) 28.18% | OG | 0.389 | 0.237 | 0.15 | 0.03 | 0.058 | 0.05 | 91.4% | 91.4% Very Satisfactory
EQUI-PARCO CONSTRUCTION COMPANY | 14332 | L | AAA | LB | GE | Rehabilitation/Reconstruction of Road Slip along Daang Maharlika (Surigao-Agusan Section), K1239+155 - K1239+220, K1239+536 - K1239+565, K1240+540 - K1240+610, Butuan City | Butuan City | 2015-11-18 | 1st | Butuan City DEO | LF | 45.9641 | 334 | 2015-03-10 | 2016-02-06 | (+) 17.54 | OG | 0.311 | 0.3 | 0.15 | 0.03 | 0.058 | 0.05 | 89.9% | 89.9% Very Satisfactory
Equi-Parco Construction Company | 14332 | L | AAA | LB | GE5 | Caminawit Port Development Project | Brgy. Caminawit, San Jose, Occidental Mindoro/Region IV-B | 2013-11-13 | 1st | DOTC | L | 73.313 | 270 | 2013-05-05 | 2014-01-30 | 0.05 | O | 0.3932 | 0.3 | 0.15 | 0.03 | 0.028 | 0.05 | 95.12 | -
Equi-Parco Construction Construction / Gicar Construction (JV) | JV-08-062 |  |  |  |  | Conc. of Dinagat Island Road Network, Dinagat-Loreto Road (Basilisa-Albor Section) |  | 2010-06-02 |  | XIII |  | 161.113 | 447 |  |  |  | O | 0.283 | 0.3 | 0.15 | 0.03 | 0.055 | 0.033 | 85.1 | -
Equi-Parco Construction Corporation | 14332 | L | AAA | LB | GE | Preventive Maintenance along Daang Maharlika Rd. (Agusan - Davao Sect.), K1245+450 - K1245+617, K1259+463 - K1259+527, K1272+000 - K1273+040, K1288+960 - K1290+849, K1297+960 - K1298+960 | Bayugan - Prosperidad Section, Agusan del Sur | 2014-08-06 | 1st | XIII | LF | 58.6551 | 120 | 2014-05-15 | 2014-09-11 | 20.53 | O | 0.37 | 0.222 | 0.15 | 0.03 | 0.051 | 0.05 | 87.3 | -
Equi-Parco Construction Corporation | 14332 | L | AAA | LB | GE | Road Upgrading (Gravel to Concrete) of NRJ Bayugan - Calaitan Road, K1286+720 - K1287+000, K1284+279 - K1286+720, K1291+200 - K1291+500 | Bayugan, Agusan del Sur | 2014-08-06 | 1st | XIII | LF | 66.8902 | 240 | 2014-03-13 | 2014-11-07 | 12.2 | O | 0.392 | 0.292 | 0.15 | 0.03 | 0.032 | 0.05 | 94.6 | -
Equi-Parco Construction Corporation | 14332 | L | AAA | LB | GE | Rehab./Reconstruction/Replacement/Retrofitting of Pandanon Bridge along Daang Maharlika (Surigao - Agusan Road) | Cabadbaran City, Agusan del Norte | 2014-08-05 | 1st | XIII | LF | 17.0068 | 252 | 2014-02-05 | 2014-10-14 | 14.91 | O | 0.354 | 0.249 | 0.15 | 0.03 | 0.046 | 0.05 | 87.9 | -
Equi-Parco/Adfil Joint Venture | JV-09-023 |  |  |  |  | Conc./Impv't. of Tiniwisan-Maguinwall Rd. (Lemon-Pigdanlan Section) |  | 2010-02-23 |  | XIII |  | 335.031 | 51 |  |  |  | O | 0.37 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 89 | -
Ercobal Construction Corp. | 32812 | L | D | SB | GE | Rehab./Reconst./Upgrading of Damaged Paved National Roads including Drainage Based on Pavement Management System/Highway Development and Management 4 (HDM-4) along Nicanor Padilla St. | San Miguel, Manila | 2014-11-24 | 1st | NCR | LF | 7.1607 | 201 | 2014-05-16 | 2014-12-02 | 6.16% | O | 0.361 | 0.3 | 0.15 | 0.008 | 0.041 | 0.017 | 87.7% | 87.70% Satisfactory
ERIC VAN P. SESBRENO CONSTRUCTION | 26243 | L | A | MA | GE | Daang Maharlika (LZ), K0257+500, K0284+572, K0287+200, K0287+380 & K0296+515 | Bayombong, Bagabag, Diadi, Nueva Vizcaya | 2015-06-09 | 1st | Nueva Vizcaya 1st DEO | LF | 37.694 | 240 | 2015-02-12 | 2015-10-09 | 8.38% | O | 0.383 | 0.244 | 0.15 | 0.03 | 0.047 | 0.033 | 88.7% | -
ERIC VAN P. SESBRENO CONSTRUCTION | 26243 | L | A | MA | GE | Construction of Slope Protection along Daang Maharlika K0249+114.50, Bambang, Quezon, Nueva Vizcaya | Bambang, Quezon, Nueva Vizcaya | 2015-11-18 | 2nd | NUEVA VIZCAYA 1ST DEO | LF | 17.4161 | 280 | 2015-02-12 | 2015-12-03 | (-) 2.11 | OG | 0.306 | 0.24 | 0.129 | 0.03 | 0.058 | 0.033 | 79.6% | 79.6% Unsatisfactory
ERIC VAN P. SESBREÑO CONSTRUCTION | 26243 | L | A | SB | GB | Construction of Barangay Multi-Purpose Buildings, Solano, Nueva Vizcaya | Solano, Nueva Vizcaya | 2015-09-02 | 1st | NV 1st DEO | LF | 1.881 | 240 | 2015-02-11 | 2015-10-08 | 0.33% | O | 0.375 | 0.3 | 0.15 | 0.03 | 0.047 | 0.05 | 95.2% | -
ERIC VAN P. SESBREÑO CONSTRUCTION | 26243 | L | A | MA | GE | Construction of Slope Protection along Daang Maharlika, K0249+114.50, Bambang, Nueva Vizcaya | Bambang, Nueva Vizcaya | 2015-09-02 | 1st | NV 1st DEO | LF | 16.745 | 255 | 2015-02-12 | 2015-10-24 | 0.11% | O | 0.323 | 0.266 | 0.15 | 0.03 | 0.06 | 0.05 | 87.9% | -
ERIC VAN P. SESBREÑO CONSTRUCTION | 26243 | L | A | SB | GE | Daang Maharlika, K0263+538 to K0263+880, Bayumbong, Nueva Vizcaya | Bayumbong, Nueva Vizcaya | 2015-09-02 | 1st & Final | NV 1st DEO | LF | 2.848 | 135 | 2015-02-20 | 2015-07-04 | 0% | C | 0.357 | 0.2 | 0.3 | - | - | - | 85.7% | *85.7% Satisfactory
Eric Van P. Sesbreno Construction / C.T. Leoncio Construction and Trading (JV) | JV-11-340 | L | A | MB | GE1 | Replacement/Const. of Burnay Bridge & Approaches inc. Const. of Detour Bridge | Lagawe, Ifugao | 2013-08-05 | 2nd | CAR | LF | 19.91 | 253 | 2012-07-17 | 2013-03-26 | -25.74 | O | 0.33 | 0.3 | 0 | 0.03 | 0.05 | 0.033 | 74.3 | -
Eric Van P. Sesbreno Construction / C.T. Leoncio Construction and Trading (JV) | JV-11-340 | L | A | MB | GE1 | Replacement/Const. of Burnay Bridge & Approaches inc. Const. of Detour Bridge | Lagawe, Ifugao | 2013-03-17 | 1st | CAR | LF | 19.911 | 253 | 2012-07-17 | 2013-03-26 | -27.97 | O | 0.364 | 0.3 | 0 | 0.03 | 0.061 | 0.033 | 78.8 | -
ES De Guzman Construction | 17494 | L | B | MB | GB1 | Const. of NVGCHS, 6CL,3-Storey Building, Bontal Annex |  | 2009-08-28 | 1st | II |  | 1.604 | 90 |  |  |  | O | 0.325 | 0.24 | 0.15 | 0.03 | 0.018 | 0.05 | 81.3 | -
ESR CONSTRUCTION AND SUPPLIES | 10451 | L | AAA | LA | GE | Replacement of Permanent Weak Bridge, Guitran Bridge (B00127MN) Completion, Sindangan-Siayan-Dumingag-Mahayag Road, (Mahayag-Dumingag), Dumingag, Zamboanga del Sur | Dumingag, Zamboanga del Sur | 2015-08-29 | 1st | Zamboanga del Sur 1st | LF | 47.516 | 285 | 2015-05-11 | 2016-02-19 | (+)43.42 | O | 0.32 | 0.299 | 0.15 | 0.03 | 0.055 | 0.05 | 90.4% | -
ESR CONSTRUCTION AND SUPPLIES | 10451 | L | AAA | LA | GE | Widening of National Roads Lanao-Pagadian-Zamboanga City Road, Section 1:Sta. 1756+560-Sta.1758+260, Section 2:Sta. 1797+600-Sta.1799+300, Section 3:Sta. 1802+940-Sta. 1803+760, Section 4: Sta. 1849+600-sta. 1850+560, Zamboanga Sibugay | Zamboanga Sibugay | 2015-08-24 | 1st | Regional Office No. IX | LF | 163.673 | 270 | 2015-05-18 | 2016-02-11 | (+)3.96% | O | 0.368 | 0.24 | 0.15 | 0.022 | 0.06 | 0.05 | 89% | -
ESR CONSTRUCTION AND DEVELOPMENT CORPORATION (Formerly: ESR CONSTRUCTION & SUPPLIES) | 10451 | L | AAA | MA | GE | Construction/Rehabilitation of Flood Control Projects at Kapalaran and Balugo Flood Control, Tambulig, Zamboanga del Sur | Tambulig, Zamboanga del Sur | 2015-06-06 | Final | Zamboanga del Sur 1st DEO | LF | 15.68 | 167 | 2014-03-31 | 2014-09-13 | 0% | C | 0.473 | 0.133 | 0.3 | - | - | - | 90.6% | *90.6% Very Satisfactory
ESR Construction and Supplies | 10451 | L | AAA | MA | GE | Construction/Rehabilitation of Tukuran Flood Control | Tukuran, Zamboanga Del Sur | 2014-08-13 | 1st | IX | LF | 14.8961 | 170 | 2014-03-31 | 2014-09-16 | 1.29 | O | 0.289 | 0.295 | 0.15 | 0.03 | 0.055 | 0.05 | 86.9 | -
ESR Construction and Supplies | 10451 | L | AA | LA | GE1 | Rd. Upgrading (Gravel to Paved) Crossing Sta. Clara-Sandayong Rd., Km.1800+920-Km.1802+000 | Zamboanga Sibugay | 2013-08-09 | 1st | IX | LF | 24.653 | 170 | 2013-03-01 | 2013-08-17 | 0.49 | O | 0.371 | 0.3 | 0.15 | 0.02 | 0.033 | 0.033 | 90.7 | -
ESR Construction and Supplies | 10451 | L | AA | LA | GE1 | Rehab./Reconst./Strengthening of Bridges along Nat'l Rds. Guintoloan Bridge along Nat'l Rds' Guintoloan Bridge Crossing Sta. Clara-Sandayong Rd., Km.1782+017-Km.1782+047 | Zamboanga Sibugay | 2013-08-09 | 2nd | IX | LF | 21.915 | 510 | 2012-04-02 | 2013-08-24 | 0.91 | O | 0.357 | 0.268 | 0.15 | 0.024 | 0.033 | 0.033 | 86.5 | -
ESR Construction and Supplies | 10451 | L | AA | LA | GE1 | Rehab./Reconst./Strengthening of Bridges along Nat'l Rds. Guintoloan Bridge Crossing Sta. Clara-Sandayong Rd., Km.1782+017-Km.1782+047 | Zamboanga Sibugay | 2013-03-15 | 1st | IX | LF | 21.915 | 360 | 2012-04-02 | 2013-03-27 | -2.67 | O | 0.373 | 0.24 | 0.123 | 0.03 | 0.047 | 0.033 | 84.6 | -
ESR Construction and Supplies | 10451 | L | AA | LA | GE1 | Rd pgrading (Gravel to Paved) Int. Sect., Sindangan-Siayan-Dumingag-Mahayag Rd., K1683+500-K1685+000 | Zamboanga del Sur | 2013-08-17 | 2nd | IX | LF | 35.886 | 259 | 2013-02-25 | 2013-11-10 | 26.95 | O | 0.323 | 0.3 | 0.15 | 0.018 | 0.037 | 0.033 | 86.1 | -
ESR Construction and Supplies | 10451 | L | AA | LA | GE1 | Rd. Upgrading (Gravel to Paved) Int. Sect. Sindangan-Siayan-Dumingag-Mahayag Rd., K1678+150-K1679+817 | Zamboanga del Sur | 2013-08-17 | 2nd | IX | LF | 46.795 | 186 | 2013-02-15 | 2013-08-29 | 7.27 | O | 0.353 | 0.254 | 0.15 | 0.012 | 0.033 | 0.05 | 85.2 | -
ESR Construction and Supplies | 10451 | L | AA | LA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rds. Int. Sect. Sindangan-Liloy Rd. Km.1958+750-Km.1960+503 Re: Upgrading (Asphalt Paved to Concrete Paved) along Liloy-Ipil Rd. Km.1988+000-Km.1991+020 | Liloy, Zamboanga del Norte | 2013-08-12 | 1st | IX | LF | 29.101 | 179 | 2013-02-21 | 2013-08-19 | -3.87 | O | 0.325 | 0.289 | 0.111 | 0.03 | 0.042 | 0.033 | 83 | -
ESR Construction and Supplies | 10451 | L | AA | LA | GE1 | Imprv't./Concrete Paving of Shoulders Dumalinao-Margosatubig Rd. | Zamboanga del Sur | 2013-03-19 | 1st | IX | LF | 135.589 | 402 | 2012-02-23 | 2013-03-30 | 0.23 | O | 0.342 | 0.3 | 0.15 | 0.03 | 0.05 | 0.05 | 92.2 | -
ESR Construction and Supplies | 10451 | L | AA | LA | GE1 | Reconst./Upgrading of Damaged Paved Nat'l Rds. Int. Sect., Liloy-Ipil Rd., K1991+020-K1992+397 | Zamboanga del Norte | 2013-03-15 | 1st | IX | LF | 23.05 | 109 | 2013-02-04 | 2013-05-23 | 10.14 | O | 0.367 | 0.24 | 0.15 | 0.03 | 0.04 | 0.05 | 87.7 | -
ESR Construction and Supplies | 10451 | L | AA | LA | GE1 | Rd. Upgrading (Gravel to Paved) Int. Sect., Sindangan-Siayan-Dumingag-Mahayag Rd., K1683+500-K1685+000 | Zamboanga del Sur | 2013-03-21 | 1st | IX | LF | 34.586 | 110 | 2013-02-25 | 2013-06-14 | 1.47 | O | 0.358 | 0.225 | 0.15 | 0.03 | 0.043 | 0.05 | 85.6 | -
ESR Construction and Supplies | 10451 | L | AA | LA | GE1 | Prev. Maint./Asphalt Overlay of Lanao-Pagadian-Zamboanga City Rd., (Basalem-Pob., Bulig Sect.), Km.1726+308.65-Km.1729+170 | Buug, Zamboanga Sibugay | 2013-03-18 | 1st | IX | LF | 28.261 | 80 | 2013-02-22 | 2013-05-12 | 14.43 | O | 0.4 | 0.2 | 0.15 | 0.03 | 0.038 | 0.033 | 85.1 | -
ESR Construction and Supplies | 10451 | L | AA | LA | GE1 | Rd. Upgrading (Gravel to Paved) Int. Sect. Sindangan-Siayan-Dumingag-Mahayag Rd., K1678+150-K1679+817 | Zamboanga del Sur | 2013-03-21 | 1st | IX | LF | 46.795 | 126 | 2013-02-25 | 2013-06-30 | 0.09 | O | 0.367 | 0.225 | 0.15 | 0.03 | 0.038 | 0.033 | 84.3 | -
ESR Construction and Supplies | 10451 |  |  |  |  | Dumingag-Siayan Road (Road Upgrading Gravel to Concrete) |  | 2010-03-06 |  | IX |  | 46.778 | 300 |  |  |  | O | 0.295 | 0.3 | 0.15 | 0.03 | 0.047 | 0.033 | 85.5 | -
ESR Construction and Supplies | 10451 |  |  |  |  | Completion of Kagawasan, Dimataling-Pitogo Provincial Road Sta. 0+000 - Sta. 3+540 with exception |  | 2010-03-04 |  | IX |  | 27.575 | 263 |  |  |  | O | 0.3 | 0.281 | 0.15 | 0.03 | 0.042 | 0.05 | 85.3 | -
ESR Construction and Supplies | 10451 |  |  |  |  | Dapitan-Dakak Rd. (Taguilon Sect.) Phase V |  | 2010-06-13 |  | IX |  | 55.05 | 300 |  |  |  | O | 0.392 | 0.256 | 0.15 | 0.03 | 0.04 | 0.033 | 90.1 | -
ESR Construction and Supplies | 10451 |  |  |  |  | Dapitan-Dakak Rd. (Taguilon Sect.), Phase V, Dapitan City |  | 2010-08-25 |  | IX |  | 55.05 | 300 |  |  |  | O | 0.369 | 0.24 | 0.15 | 0.03 | 0.047 | 0.05 | 88.6 | -
ESR Construction and Supplies | 10451 | L | AA | LA | GE1 | Road Upgrading (Gravel to Concrete) Dipolog-Punta-Dansullan-SergionOsmeña, Zambo. Del Norte-Sur Bdry., Km.1876+000-Km.1877+000, De Venta Perla Section |  | 2009-06-08 | 1st | IX |  | 18.674 | 120 |  |  |  | O | 0.39 | 0.238 | 0.15 | 0.01 | 0.037 | 0.05 | 87.5 | -
ESR Construction and Supplies | 10451 | L | AA | LA | GE1 | Road Upgrading (Gravel to Concrete) , Jct. Blancia-Molave-Josefina Road |  | 2009-06-04 | 1st | IX |  | 46.47 | 300 |  |  |  | O | 0.342 | 0.24 | 0.15 | 0.03 | 0.051 | 0.05 | 86.3 | -
ESR Construction and Supplies | 10451 | L | AA | LA | GE1 | Conc./Widening of Jct. Dumalinao-Margosatubig Intermittent Section |  | 2009-09-09 | 1st | IX |  | 18.073 | 247 |  |  |  | O | 0.372 | 0.3 | 0.15 | 0.03 | 0.04 | 0.033 | 92.5 | -
ESR Construction and Supplies | 10451 | L | AA | LA | GE1 | Rehab./Impvt. of Dipolog-Punta-Dansullan-Sergio Osmeña Road (De Venta Perla-Poblacion Alto Section) |  | 2009-09-14 | 1st | IX |  | 28.12 | 210 |  |  |  | O | 0.36 | 0.3 | 0.15 | 0.03 | 0.045 | 0.033 | 91.8 | -
ESR Construction and Supplies | 10451 | L | AA | LA | GE1 | Reblocking/Asphalt Overlaying of Junction Dumalinao-Margosatubig Road, Margosatubig Section, Sta. 1714+920.00-Sta. 1719+739.10 with exception |  | 2009-09-10 | 1st | IX |  | 20.215 | 168 |  |  |  | O | 0.384 | 0.3 | 0.1 | 0.03 | 0.04 | 0.033 | 88.7 | -
ESR Construction and Supplies | 10451 | L | AA | LA | GE1 | Roads to Address Critical Bottleneck: Widening of Pagadian-Zamboanga City Road K1675+(-31)-K1678+52 Re-Aligned to Widening of Pagadian-Zamboanga City Road K1675+980-K1676+692 | Zamboanga del Sur | 2012-03-26 | 1st | IX | LF | 18.34 | 105 | 2012-02-22 | 2012-06-15 | 5.16 | O | 0.321 | 0.3 | 0.15 | 0.03 | 0.043 | 0.05 | 89.4 | -
ESR Construction and Supplies | 10451 | L | AA | LA | GE1 | Upgrading/Concrete Paving of Sindangan-Siayan-Dumingag-Mahayag Rd. | Zamboanga del Norte | 2012-11-28 | 1st | IX | LF | 127.987 | 349 | 2012-02-14 | 2013-01-27 | 1.39 | O | 0.304 | 0.292 | 0.15 | 0.03 | 0.059 | 0.05 | 88.5 | -
ESR Construction and Supplies | 10451 | L | AA | LA | GE1 | Impvt./Upgrading (Gravel to Paved) of Rizal to Dapitan City Coastal Loop R., Guimputian-Tag-ulo Sect., Sta.1852+377.00-Sta.1853+960.00 w/ exceptions | Dapitan City, Zamboanga del Norte | 2012-11-30 | 2nd | IX | LF | 62.89 | 255 | 2012-05-23 | 2013-02-01 | 1.05 | O | 0.365 | 0.225 | 0.15 | 0.03 | 0.043 | 0.033 | 84.6 | -
ESR Construction and Supplies | 10451 | L | AA | LA | GE1 | Impvt./Upgrading (Gravel to Paved) of Rizal to Dapitan City Coastal Loop Rd., Guimputian-Tag-ulo Sect. | Dapitan City, Zamboanga del Norte | 2012-08-25 | 1st | IX | LF | 62.89 | 225 | 2012-05-23 | 2013-01-02 | 10.71 | O | 0.394 | 0.226 | 0.15 | 0.022 | 0.043 | 0.033 | 86.8 | -
ESR Construction and Supplies | 10451 | L | AA | LA | GE1 | Widening/Upgrading/Concrete Paving of Jct. Tiguma-Pagadian Airport Rd., Sta.1663+060-Sta.1664+300 | Pagadian City, Zamboanga del Sur | 2012-11-23 | 1st | IX | LF | 44.465 | 216 | 2012-05-14 | 2012-12-15 | 12.1 | O | 0.234 | 0.3 | 0.15 | 0.03 | 0.059 | 0.05 | 82.3 | -
ESR Construction and Supplies | 10451 | L | AA | LA | GE1 | Rd. Upgrading (Gravel to Paved) Along Imelda-Bayog-Kumalarang-Lapuyan-Margosatubig Rd. (Brgy. San Jose Sect.) | Imelda, Zamboanga Sibugay | 2012-08-28 | 2nd | IX | LF | 45.59 | 240 | 2012-01-31 | 2012-09-26 | -0.17 | O | 0.367 | 0.3 | 0.148 | 0.03 | 0.04 | 0.033 | 91.8 | -
ESR Construction and Supplies | 10451 | L | AA | LA | GE1 | Road Upgrading (Gravel to Concrete) IS, Jct. Blancia-Molave-Josefina Rd, K1693+000-K1685+000, Bagon Ariosa | Molave, Zamboanga del Sur | 2012-08-18 | 1st | IX | LF | 42.835 | 180 | 2012-02-28 | 2012-08-26 | 0.14 | O | 0.388 | 0.24 | 0.15 | 0.03 | 0.038 | 0.033 | 87.9 | -
ESR Construction and Supplies | 10451 | L | AA | LA | GE1 | Rd. Upgrading (Gravel to Concrete) IS, Sindangan-Siayan-Dumingag (Mahayag-Dumingag) Mahayag-Ditulan | Zamboanga del Sur | 2012-08-16 | 1st | IX | LF | 32.148 | 180 | 2012-02-28 | 2012-08-26 | 0.6 | O | 0.359 | 0.232 | 0.15 | 0.03 | 0.043 | 0.033 | 84.7 | -
ESR Construction and Supplies | 10451 | L | AAA | MA | GE | Restoration of Slope Protection at Agusan Canyon Bridge, along S.H. - Manolo Fortich - Libona - Indahag Road | Manolo Fortich, Bukidnon |  | 1st | X | LF | 14.0405 | 149 | 2014-07-10 | 2014-12-05 | 25.8% | O | 0.342 | 0.259 | 0.15 | 0.01 | 0.042 | 0.033 | 83.6% | 83.60% Satisfactory
ESR CONSTRUCTION AND SUPPLIES | 10451 | L | AAA | LA | GE | Replacement of Permanent Weak Bridge, Guitran Bridge along (B00127MN) Sindangan-Siayan-Dumingag-Mahayag Road, Dumingag, Zamboanga del Sur | Dumingag, Zamboanga del Sur | 2015-11-13 | 2nd | Zamboanga Del Sur 1st DEO | LF | 47.5156 | 285 | 2015-05-11 | 2016-02-19 | - | OG | 0.34 | 0.285 | 0.15 | 0.02 | 0.042 | 0.05 | 88.7% | 88.7% Satisfactory
ESR CONSTRUCTION AND SUPPLIES | 10451 | L | AAA | LA | GB | Construction of Multi-Purpose Building at Brgy. Poblacion, Buug, Zamboanga Sibugay | Buug, Zamboanga Sibugay | 2015-11-11 | Final | Zamboanga Sibugay 1st DEO | LF | 1.9499 | 60 | 2015-02-23 | 2015-04-23 | 0.20% | C | 0.403 | 0.133 | 0.3 | - | - | - | 83.6% | 83.6% Satisfactory
EST CONSTRUCTION AND SUPPLIES | 10451 | L | AAA | LA | GE | Rehab./Reconst./Upgrading of Damaged Paved National Road including Draiange Based on Pavement Management System/Highway Development & Management-4 (HDM-4) along Sindangan - Siayan - Dumingag - Mahayag Road, Km. 1934+722 to Km. 1935+092, Zamboanga del Norte | Zamboanga del Norte | 2015-06-04 | 1st | Zamboanga Del Norte 1st DEO | LF | 6.99 | 113 | 2015-02-24 | 2015-06-17 | 0.01% | O | 0.363 | 0.221 | 0.15 | 0.03 | 0.045 | 0.033 | 84.2% | -
ETHAN PROPERTY DEVELOPER | 36181 | L | B | SB | GE | Concreting of Road at Barangay Payao | Binalbagan, Negros Occidental | 2015-08-27 | 1st & Final | Negros Occidental 2nd | LF | 1.679 | 43 | 2015-06-11 | 2015-07-23 | 0% | C | 0.47 | 0.126 | 0.3 | - | - | - | 89.6% | *89.6% Very Satisfactory
ETHAN PROPERTY DEVELOPER | 36181 | L | B | SB | GE | Rehabilitation of Permanent Bridges along National Road Cabadiaran Bridge (B00274NR) K0128+914, along Dancalan Candoni Damutan Valley Road, Brgy. East, Candoni, Negros Occidental | Brgy. East, Candoni, Negros Occidental | 2015-11-14 | 1st | Negros Occidental 3rd DEO | LF | 6.86 | 314 | 2015-02-27 | 2016-01-06 | (+)9.48 | OG | 0.386 | 0.161 | 0.15 | 0.03 | 0.047 | 0.05 | 82.4% | 82.4% Satisfactory
Everlast Construction | 2364 | L | A | MA | GE1 | Const. of Multi-Purpose Pvmt. @ Brgy. Pasonanca (Mayor C. Climaco Park) | Zamboanga Sibugay | 2013-08-06 | 4th | IX | LF | 9.175 | 570 | 2012-01-18 | 2013-08-09 | -4 | O | 0.355 | 0.3 | 0.11 | 0.02 | 0.037 | 0.033 | 85.5 | -
Everlast Construction | 2364 | L | A | MA | GE1 | Const. of Multi-Purpose Pvmt. at Brgy. Pasonanca (Mayor C. Climaco Park) | Zamboanga City | 2013-03-11 | 3rd | IX | LF | 9.175 | 315 | 2012-01-18 | 2012-11-27 | 1 | O | 0.384 | 0.24 | 0.15 | 0.03 | 0.037 | 0.05 | 89.1 | -
Everlast Construction | 2364 | L | A | MB | GB1 | Const. of Zamboanga City Schools Division Office |  | 2009-09-01 | 2nd | IX |  | 14.182 | 305 |  |  |  | O | 0.37 | 0.3 | 0.15 | 0.03 | 0.035 | 0.033 | 91.8 | -
Everlast Construction | 2364 | L | A | MA | GE1 | Const. of Multi-Purpose Pavement at Brgy. Pasonanca (Mayor C. Climaco Park) | Zamboanga City | 2012-11-19 | 2nd | IX | LF | 9.175 | 315 | 2012-01-18 | 2012-11-27 | 1 | O | 0.339 | 0.224 | 0.15 | 0.023 | 0.045 | 0.05 | 83.1 | -
Everlast Construction | 2364 | L | A | MA | GE1 | Const. of Multi-Purpose Pavement at Brgy. Pasonanca (Mayor C. Climaco Park) | Zamboanga City | 2012-08-14 | 1st | IX | LF | 8.699 | 255 | 2012-01-18 | 2012-09-28 | 1.26 | O | 0.374 | 0.231 | 0.15 | 0.03 | 0.041 | 0.033 | 85.9 | -
EVTR TRADING AND CONSTRUCTION | 14581 | L | A | MA | GE | Conc. of Malinao-Sta. Isabel-Dao Road leading to Naujan Lake National Park | Naujan, Oriental Mindoro | 2015-11-20 | Final | Mindoro Oriental DEO | LF | 37.3553 | 150 | 2016-05-26 | 2016-10-22 | 0.17 | C | 0.427 | 0.133 | 0.3 | - | - | - | 86% | 86% Satisfactory
Excelssius Engr'ng. Services & C.T. Leoncio Construction & Trading JV |  | L |  |  | GB1 | Construction of 3-Storey School Bldg. | HeroesVille1, Gaya-Gaya, SJDM, Bulacan/Region 3 | 2012-07-10 | 2nd | NHA | LF | 22.132 | 180 | 2012-02-06 | 2012-08-03 | -0.7342 | O | 0.395 | 0.269 | 0.143 | 0.03 | 0.056 | 0.05 | 94.3 | -
Excelssius Engr'ng. Services & C.T. Leoncio Construction & Trading JV |  | L |  |  | GB1 | Construction of 3-Storey School Bldg. | HeroesVille1, Gaya-gaya, SJDM, Bulacan/Region 3 | 2012-05-08 | 1st | NHA | LF | 22.132 | 180 | 2012-02-06 | 2012-08-03 | - | O | 0.391 | 0.2639 | 0.15 | 0.024 | 0.058 | 0.05 | 93.69 | -
EZJONES CONSTRUCTION INC | 34462 | L | AA | MA | GE | Construction/Maintenance of Flood Mitigation Structures and Drainage Systems, Rehabilitation/Improvement of Flood Control Structures along Daguitan-Marabong River Including Dredging/Desilting (Downstream), Brgy. Dao, Dulag, Leyte | Brgy. Dao, Dulag, Leyte | 2015-11-12 | 1st | Regional Office No. VIII | LF | 133.3803 | 318 | 2016-06-08 | 2017-04-21 | (+)11.37% | OG | 0.385 | 0.3 | 0.15 | 0.03 | 0.07 | 0.05 | 98.5% | 98.5% Outstanding
Ezjones Construction Inc. | 34462 | L | D | SB | GB1 | Const. of 2-Storey, 2-CL SB San Jose ES | Lavezares, Northern Samar | 2013-08-10 | 1st | VIII | LF | 2.428 | 180 | 2013-03-27 | 2013-09-22 | -5.46 | O | 0.38 | 0.3 | 0.095 | 0.03 | 0.058 | 0 | 86.3 | -
Ezjones Construction Inc. | 34462 | L | D | SB | GB1 | Const. of 2-Storey, 2-CL SB San Isidro ES | Bobon, Northern Samar | 2013-08-10 | 1st | VIII | LF | 2.299 | 170 | 2013-03-27 | 2013-09-12 | -9.11 | O | 0.372 | 0.3 | 0.059 | 0.03 | 0.064 | 0.025 | 85 | -
EZJONES CONSTRUCTION INC. | 34462 | L | A | MB | GE | Construction of Tacloban City By-Pass Road, (Including ROW), Sta. 3+400 - Sta. 6+400, Brgy. Caibaan, Tacloban City, Leyte | Tacloban City, Leyte | 2015-06-30 | 1st | Regional Office No. VIII | LF | 126.052 | 300 | 2015-02-06 | 2015-12-02 | - | O | 0.39 | 0.253 | 0.15 | 0.03 | 0.051 | 0.033 | 90.7% | -
F & J CONSTRUCTION AND SUPPLY CORPORATION | 31963 | L | B | SB | GE | Protection Works along Dinagat - Loreto Road | Dinagat, Dinagat Islands | 2015-06-11 | Final | DINAGAT ISLANDS DEO | LF | 4.189 | 90 | 2015-02-05 | 2015-05-05 | (+) 1.14% | C | 0.464 | 0.133 | 0.3 | - | - | - | 89.7% | *89.7% Very Satisfactory
F. Guerrea Construction, Inc./ Jr. Builders Co., Inc. | JV-14-1100 |  | AAA |  | GE | Construction of Back-Up Area and Fastcraft Pier | Port of Calapan, Oriental Mindoro | 2016-04-29 | 1st | PPA | LF | 183.523 | 480 | 2015-09-11 | 2017-01-02 | 2.147 | O | 0.38 | 0.3 | 0.15 | 0.03 | 0.07 | 0.05 | 98 | -
F. GURREA CONSTRUCTION INCORPORATED | 6995 | L | AAA | MB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Secondary Roads, La Paz Deep Sea Water Port Road | A) Chainage 0000-Chainage 0514 & B) Chainage 0514-Chainage 0856, Iloilo City | 2015-06-02 | Final | Iloilo City DEO | LF | 14.895 | 200 | 2014-05-16 | 2014-12-01 | 11.42% | C | 0.419 | 0.2 | 0.3 | - | - | - | 91.9% | *91.9% Very Satisfactory
F. Gurrea Construction, Inc. | 6995 | L | AAA | LA | GE | Extension of RC Wharf Project | ICPC, Iloilo | 2016-08-05 | 2nd & Final | PPA | LF | 271.6 | 570 | 2015-02-09 | 2016-08-31 | 0 | C | 0.484 | 0.2 | 0.3 | - | - | - | 98.4 | 96.62% Outstanding
F. GURREA CONSTRUCTION, INC. | 9665 | L | AAA | MA | GE | Construction of Flood Control, Brgy. Bulwang, Numancia, Aklan | Brgy. Bulwang, Numancia, Aklan | 2015-11-11 | 2nd | Aklan | LF | 11.8926 | 191 | 2015-05-18 | 2015-11-25 | (-) 1.85% | OG | 0.3793 | 0.2831 | 0.1315 | 0.03 | 0.051 | 0.033 | 90.8% | 90.8% Very Satisfactory
F. Gurrea Construction, Inc./ JR Builders Co., Inc. | JV-14-1100 |  | AAA |  |  | Construction of Back-Up Area and Fastcraft Pier | Port of Calapan, Oriental Mindoro | 2016-11-23 | 2nd | PPA | LF | 183.523 | 480 | 2015-09-11 | 2017-01-02 | -19.191 | O | 0.382 | 0.3 | 0 | 0.03 | 0.061 | 0.05 | 82.3 | -
F. Gurrea Construction, Incorporated | 6995 | L | AAA | MB | GB1 | Iloilo City PCG Annex Building Development Project | Brgy. Obrero Lapuz, Iloilo City | 2013-07-23 | 1st | DOTC | L | 10.116 | 240 | 2013-03-15 | 2013-11-10 | 0.83 | O | 0.347 | 0.3 | 0.15 | 0.03 | 0.031 | 0.05 | 90.8 | -
F. Gurrea Construction, Incorporated | 6995 | L | AAA | LA | GE5 | Barbaza Port Development Project | Barbaza, Antique | 2013-07-24 | 1st | DOTC | L | 10.999 | 150 | 2013-03-11 | 2013-08-08 | 2.19 | O | 0.333 | 0.3 | 0.15 | 0.03 | 0.038 | 0.05 | 90.1 | -
F. Gurrea Construction, Incorporated | 6995 | L | AAA |  | GE-5 | Extension of RC Wharf, ICPC | ICPC, Loboc, La Paz, Iloilo City | 2015-11-24 | 1st | PPA | LF | 271.6 | 570 | 2015-02-09 | 2016-08-31 | 30.987 | O | 0.36 | 0.2944 | 0.15 | 0.03 | 0.07 | 0.05 | 95.44 | -
F. Gurrea Construction, Incorporated | 6995 | L | AAA |  | GE2 | Maayon CIP Package 2 ( Canal Structures) | Maayon CIP | 02/7-10/12 | 1st | NIA | LF | 14.741 | 320 | 2011-09-07 | 2012-07-24 | 1.4 | O | 0.316 | 0.258 | 0.15 | 0.024 | 0.051 | 0.05 | 84.9 | -
F. Gurrea Construction, Incorporated | 6995 | L | AAA |  | GE2 | Const. of Maayon CIP (Package 1- Diversion Works) | Maayon CIP | 2013-04-13 | 1st | NIA | LF | 60.137 | 540 | 2011-09-02 | 2013-07-01 | -3.43 | O | 0.374 | 0.243 | 0.116 | 0.024 | 0.056 | 0.033 | 84.6 | -
F. Gurrea Construction, Incorporated | 6995 | L | AAA | LA | GE | Widening of Iloilo East Coast-Estancia Wharf Road K0179+040 - K0180+340 | Estancia, Iloilo | 2014-10-29 | 1st | VI | LF | 30.7273 | 224 | 2014-04-24 | 2014-12-03 | 7.2% | O | 0.368 | 0.222 | 0.15 | 0.03 | 0.054 | 0.033 | 85.7% | 85.70% Satisfactory
F. Gurrea Construction, Incorporated | 6995 | L | AA | MB | GE1 | Completion of Anahawon |  | 2008-12-01 | 1st | VI |  | 9.423 | 180 |  |  |  | O | 0.381 | 0.223 | 0 | 0.022 | 0.043 | 0.067 | 73.6 | -
F. Gurrea Construction, Incorporated | 6995 | L | AAA | MB | GE1 | Conc. of Oton-Mambog-Caboloan-Abilay-SanJose-San Miguel Road leading to Iloilo International Airport Km. 11+436.25-Km. 15+96.25 w/ exception |  | 2009-05-25 | 2nd | VI |  | 57.85 | 462 |  |  |  | O | 0.295 | 0.3 | 0.15 | 0.03 | 0.065 | 0.05 | 89 | -
F. Gurrea Construction, Incorporated | 6995 | L | AA | MB | GE1 | Conc. of Oton-Mambog-Caboloan-Abilay-San Jose-San Miguel Road leading to Iloilo International Airport Km. 11+436.25-Km.15+96.25 w/ exception |  | 2009-09-10 | 3rd | VI |  | 57.894 | 467 |  |  |  | O | 0.314 | 0.3 | 0.15 | 0.03 | 0.06 | 0.05 | 90.4 | -
F. Gurrea Construction, Incorporated | 6995 |  |  |  |  | Conc. of Iloilo East West Road, San Rafael-Passi Section |  | 2010-09-06 |  | VI |  | 18.915 | 210 |  |  |  | O | 0.375 | 0.24 | 0.15 | 0.03 | 0.037 | 0.033 | 86.5 | -
F. GURREA CONSTRUCTION, INCORPORATED | 6995 | L | AAA | MA | GE | Construction of Flood Control | Brg. Bulwang, Numancia, Aklan | 2015-09-01 | 1st | Aklan | LF | 11.893 | 191 | 2015-05-18 | 2015-11-24 | 4.57% | O | 0.39 | 0.233 | 0.15 | 0.03 | 0.051 | 0.05 | 90.4% | -
F.A Asprer Construction | 21579 |  |  |  |  | Dipolog Airport Development Project (Construction o Terminal Building) |  | 2010-11-10 |  | DOTC |  | 12.977 | 180 |  |  |  | O | 0.361 | 0.3 | 0.15 | 0.02 | 0.035 | 0.017 | 88.3 | -
F.A Sison Trading and Construction | 27150 |  |  |  |  | Rehab./Upgrading of Damaged National Roads (PMS/HDM-4) Mindoro Oriental/Occidental East Coastal Road |  | 2010-08-27 |  | IVB |  | 7.522 | 200 |  |  |  | O | 0.361 | 0.055 | 0.15 | 0.03 | 0.055 | 0.033 | 68.4 | -
F.A. Asprer Construction | 21579 | L | D | SB | GE1 | Conc. of Brgy. Road @ Laoang | Tarlac City | 2012-11-23 | 1st | III | LF | 7.242 | 75 | 2012-09-17 | 2012-11-30 | 2 | O | 0.305 | 0.3 | 0.15 | 0.03 | 0.03 | 0.033 | 84.8 | -
F.A. Torres Construction/Three W Builders, Inc. Joint Venture | JV-11-254 | L | B | MA | GE1 | Replacement of Tepassy Bridge along Bulalacao-San Jose Jct. Mapaya Rd., Brgy. Mayapa | San Jose, Occidental Mindoro | 2012-08-08 | 2nd | IVB | LF | 9.498 | 210 | 2012-01-27 | 2012-08-23 | -5 | O | 0.372 | 0.295 | 0.1 | 0.03 | 0.05 | 0.017 | 86.4 | -
F.B. Bantales Engineering Construction | 31045 | L | D | SB | GE2 | Clustered Restoration Proj., Bokod & Tuba | Benguet | 2013-03-13 | 1st | CAR | LF | 7.338 | 105 | 2013-01-21 | 2013-05-05 | 5.71 | O | 0.14 | 0.21 | 0.15 | 0.03 | 0.035 | 0.033 | 59.8 | -
F.B. BANTALES ENGINEERING CONSTRUCTION | 31045 | L | B | MA | GE | Construction/Maintenance of Flood Mitigation Structures along La Trinidad Flood Control System | La Tridad, Benguet | 2015-06-02 | 1st | Benguet 1st DEO | LF | 45.4 | 180 | 2015-04-01 | 2015-09-27 | (+) 0.20% | O | 0.363 | 0.282 | 0.15 | 0.03 | 0.029 | 0.05 | 90.4% | -
F.B. BANTALES ENGINEERING CONSTRUCTION | 31045 | L | B | MA | GE | Construction/Maintenance of Flood Mitigation Structures along La Trinidad Flood Control System, La Trinidad, Benguet | La Trinidad, Benguet | 2015-09-03 | 1st | Benguet 1st DEO | LF | 45.399 | 210 | 2015-04-01 | 2015-10-27 | 1.12% | O | 0.369 | 0.225 | 0.15 | 0.023 | 0.042 | 0.05 | 85.9% | -
F.B. BANTALES ENGINEERING CONSTRUCTION | 31045 | L | B | MA | GE | Off-Carriageway Improvement along Baguio - Bontoc Road, K0320+000 to K0332+000, K0334+000 to K0339+000, Buguias, Benguet | Buguias, Benguet | 2015-09-02 | 1st | Benguet 2nd DEO | LF | 48.001 | 242 | 2015-02-24 | 2015-10-23 | -11.42% | O | 0.378 | 0.3 | 0.036 | 0.03 | 0.051 | 0.033 | 82.8% | -
F.F Cruz & Co., Inc. / Filipinas (Prefab. Bldg.) System, Inc. (JV) | JV-08-138 | L | AAA | LB | GE1 | Conc. of Mindoro Oriental East Coastal Road (Intermittent Sections), Mansalay-Bdry. Mindoro Occidental Sect. |  | 2009-09-05 | 1st | IVB |  | 192.3997 | 562 |  |  |  | O | 0.363 | 0.3 | 0.15 | 0.03 | 0.042 | 0.033 | 91.8 | -
F.F. Rosales General Contractor | 8814 | L | B | MA | GE1 | Rd. Upgrading (Concrete Paving) of Mulanay-San Francisco Road, K0297+082 - K0298+082, Brgy. Ilayang Yuni | Mulanay, Quezon | 2013-08-06 | 1st | IVA | LF | 22.043 | 180 | 2013-03-11 | 2013-09-06 | 0.12 | O | 0.316 | 0.253 | 0.15 | 0.03 | 0.04 | 0.033 | 82.2 | -
F.H. Gopiteo Construction & Supply | 21336 | L | B | MA | GE2 | Const. of Drainage Lined Canal at Carpenter Hill Sect. along Marbel-Makar Rd. | Koronadal City, South Cotabato | 2012-08-07 | 2nd | XII | LF | 15.061 | 268 | 2011-11-29 | 2012-08-29 | 0.15 | O | 0.392 | 0.24 | 0.15 | 0.03 | 0.047 | 0.05 | 90.9 | -
F.H. GOPITEO CONSTRUCTION & SUPPLY | 21336 | L | B | MA | GE | Construction/Upgrading/Rehabilitation of Drainage along National Roads, Digos-Makar Road K1653+765-K1654+425 | Tupi, South Cotabato | 2015-06-12 | 1st | South Cotabato 2nd DEO | LF | 18.33 | 172 | 2015-03-15 | 2015-09-02 | 23.17% | O | 0.318 | 0.24 | 0.15 | 0.03 | 0.06 | 0.05 | 84.8% | -
F.H. GOPITEO CONSTRUCTION & SUPPLY | 21366 | L | B | MA | GE | Construction/Upgrading/Rehabilitation of Drainage along Nat'l Roads, Digos-Makar Road K1653+765 to K1654+425 | General Santos City | 2016-11-18 | Final | South Cotabato Second DEO | LF | 19.6 | 227 | 2015-03-15 | 2015-10-27 | 0.00% | C | 0.45 | 0.146 | 0.3 | - | - | - | 89.6% | 89.6% Very Satisfactory
F.R Ignacio Construction Incorporated | 687 | L | A | MB | GB1 | Pasay City LTO District Office Building Project |  | 2009-09-18 | 1st | DOTC |  | 11.937 | 255 |  |  |  | O | 0.384 | 0.3 | 0.15 | 0.03 | 0.039 | 0.05 | 95.3 | -
F.S. SUGAY CONSTRUCTION & SUPPLIES | 28489 | L | C | SB | GE | Impv't./Rehab. of Barangay Wawa River | Calapan City, Oriental Mindoro | 2015-11-20 | Final | Mindoro Oriental DEO | LF | 1.4113 | 90 | 2015-07-06 | 2015-10-03 | 0 | C | 0.4 | 0.133 | 0.3 | - | - | - | 83.3% | 83.3% Satisfactory
Fairchild Builders & Developers, Inc. | 10024 | L | B | MA | GE1 | Rehab. along Tacloban-Baybay South Road along Tacloban South Road |  | 2009-05-28 | 1st | VIII |  | 9.486 | 150 |  |  |  | O | 0.336 | 0.239 | 0.15 | 0.03 | 0.037 | 0.033 | 82.5 | -
FAIRCHILD BUILDERS AND DEVELOPERS, INCORPORATED (Formerly: Fairchild Marketing & Construction) | 10024 | L | B | MA | GB | Construction/Rehabilitation/Repair of Multi-Purpose Building-PDEA, Region VIII, Tacloban City | Tacloban City | 2015-11-11 | Final | Tacloban City DEO | LF | 1.9939 | 60 | 2015-07-08 | 2015-09-05 | (+)41.67 | C | 0.486 | 0.133 | 0.3 | - | - | - | 91.9% | 91.9% Very Satisfactory
FEAJ Construction and General Services | 13609 | L | B | SB | GE2 | Repair/Rehab./Imprv't. of Puerto Galera Drainage, Calapan North Rd. | Puerto Galera, Oriental Mindoro | 2013-03-18 | 1st | IVB | LF | 9.893 | 160 | 2012-08-30 | 2013-03-27 | 1 | O | 0.35 | 0.24 | 0.15 | 0.03 | 0.045 | 0.033 | 84.8 | -
Ferdstar Builders Contractors | 4965 | L | B | MA | GE1 | Conc. of Barangay Road, Barangay Pag-asa (Phase I) | Orani, Bataan | 2011-08-04 | 1st | III | LF | 9.315 | 109 | 2011-05-27 | 2011-09-12 | 1.34 | O | 0.229 | 0.225 | 0.15 | 0.03 | 0.048 | 0.05 | 73.2 | -
Ferdstar Builders Contractors | 4965 | L | A | MA | GB1 | Const. of Multi-Purpose Building at San Roque |  | 2009-08-25 | 1st | III |  | 5.254 | 93 |  |  |  | O | 0.384 | 0.24 | 0.15 | 0.03 | 0.051 | 0.033 | 88.8 | -
Ferdstar Builders Contractors | 4965 | L | B | MA | GE1 | Road Upgrading/Conc. of Capas-San Jose-Mayantoc-Malacampa Rd. (Capas Section), K0116+701-K0118+874 w/ exception | Capas, Tarlac | 2012-08-06 | 1st | III | LF | 26.781 | 120 | 2012-04-18 | 2012-08-15 | 2.48 | O | 0.305 | 0.3 | 0.15 | 0.03 | 0.03 | 0.05 | 86.5 | -
Ferdstar Builders Contractors | 4965 | L | B | MA | GE1 | Repair/Rehab./Const. of Drainage System along Gov't. Center Rd. Network, Maharlika Highway & Pawing-Campetic Rd., Brgy. Candahug to Brgy. Pawing | Palo, Leyte | 2013-08-22 | 1st | VIII | LF | 37.215 | 300 | 2013-02-20 | 2013-12-16 | 10.76 | O | 0.4 | 0.24 | 0.15 | 0.012 | 0.045 | 0.05 | 89.7 | -
Ferdstar Builders Contractors | 4965 | L | B | MA | GE1 | Rehab./Reconst. of Biliran Circ. Rd., Esperanza-Looc Rd. Sect., Km.1104+000-Km.1104+520 | Biliran Province | 2013-03-12 | 1st | VIII | LF | 9.259 | 78 | 2013-01-04 | 2013-03-23 | 0.1 | O | 0.368 | 0.225 | 0.15 | 0.03 | 0.05 | 0.05 | 87.3 | -
Ferdstar Builders Contractors | 4965 |  |  |  |  | Rehab./Impvt. of Daang Maharlika, Calbiga-Tacloban Rd. Sect. Km.897+200 - Km.901+200 w/ exceptions, Leyte Side |  | 2010-06-09 |  | VIII |  | 28.322 | 95 |  |  |  | O | 0.339 | 0.258 | 0.15 | 0.03 | 0.037 | 0.033 | 84.7 | -
Ferdstar Builders Contractors | 4965 | L | B | MA | GE1 | Repair of Calbiga Steel Bridge along Daang Maharlika-Calbiga-San Juanico Bridge Sect. | Calbiga, Samar | 2012-08-07 | 1st | VIII | LF | 17.375 | 261 | 2012-01-20 | 2012-10-06 | 0.83 | O | 0.354 | 0.235 | 0.15 | 0.03 | 0.04 | 0.033 | 84.2 | -
FERDSTAR BUILDERS CONTRACTORS | 4965 | L | B | MA | GE | Replacement/Rehabilitation/Strengthening of Permanent Bridges Generated from Bridge Management System (BMS) at San Antonio Bridge along Gapan - San Fernando - Olongapo Road, Mexico, Pampanga | Mexico, Pampanga | 2015-06-01 | Final | Pampanga 1st DEO | LF | 17.953 | 455 | 2014-02-18 | 2015-05-18 | 0% | C | 0.473 | 0.2 | 0.3 | - | - | - | 97.3% | *97.3% Outstanding
FERDSTAR BUILDERS CONTRACTORS | 4965 | L | B | MA | GE | MFO 1 - National Road Network Services, Construction and Maintenance of Bridges along National Roads, Replacement of Permanent Weak Bridges, Construction of Lagnas Bridge along Daang Maharlika, Tiaong, Quezon Province | Tiaong, Quezon Province | 2015-11-16 | 1st | QUEZON 2ND DEO | LF | 75.2235 | 300 | 2015-04-07 | 2016-02-01 | -0.0108 | OG | 0.332 | 0.282 | 0.139 | 0.018 | 0.033 | 0.017 | 82.1% | 82.1% Satisfactory
FERDSTAR BUILDERS CONTRACTORS | 4965 | L | B | MA | GE | Rehabilitation/Major Repair of Permanent Bridges, Rizal Bridge (B000S9LT), Along Bagahupi Babatngon-Sta. Cruz-Baguro-Carigara Road, K0914+528, Palo, Leyte | Palo, Leyte | 2015-11-09 | Final | Leyte First DEO | LF | 12.8947 | 160 | 2015-01-30 | 2015-07-08 | - | C | 0.497 | 0.133 | 0.3 | - | - | - | 93% | 93% Very Satisfactory
Ferrer Construction and Engineering Services | 16711 | L | B | MA | GB1 | Proposed Exterior Repainting of PAZ Mendoza & Med. Lib. |  | 2009-03-20 | 1st | U.P. |  | 751.116 | 120 |  |  |  | O | 0.366 | 0.3 | 0 | 0.03 | 0.054 | 0.05 | 80 | -
Ferreze Construction Supply & Manufacturing | 26968 | L | D | SB | GB1 | Const. of MPB (Renov./Rehab. of Psychiatric Ward) Zamboanga City Medical Center |  | 2009-09-02 | 2nd | IX |  | 5.22 | 126 |  |  |  | O | 0.327 | 0.3 | 0.15 | 0.03 | 0.053 | 0.05 | 91 | -
FF Cruz & Co. Inc./Filipinas (Prefab. Bldg.) Systems, Inc. JV | JV-08-139 | L | AAA | LB | GE1 | Impvt./Const. of Roads and Bridges along Baler-Casiguran Road (CP1) |  | 2009-09-09 | 2nd | III |  | 1703.612 | 450 |  |  |  | O | 0.378 | 0.3 | 0.15 | 0.03 | 0.05 | 0.05 | 95.8 | -
FFJJ CONST/RDY BUILDERS CONST & GEN. MERCHANDISE (Joint Venture) | 16712 | L | AAA | LB | GE | Const/Upgrading/Rehab. Of Drainage along National Roads at Mactan Circumferential Road K0028+000-K0028+740, K0030+228-K0030+355, Cordova Section, Cordova, Cebu | Cordova Section, Cordova, Cebu | 2015-06-01 | 1st | Cebu Sixth DEO | LF | 11.618 | 210 | 2015-03-30 | 2015-10-25 | 0.52% | O | 0.394 | 0.22 | 0.15 | 0.022 | 0.045 | 0.033 | 86.4% | -
FFJJ Construction | 16712 | L | AAA | LB | GE | Const. of Maluos Bridge II along Bukidnon - Davao city Road, Sinuda | Kitaotao, Bukidnon | 2014-10-23 | 1st | X | LF | 27.2047 | 252 | 2014-01-23 | 2014-10-01 | -4.5% | O | 0.333 | 0.295 | 0.105 | 0.03 | 0.042 | 0.033 | 83.8% | 83.80% Satisfactory
FFJJ Construction | 16712 | L | AAA | LB | GE | GAA - Widening of Agusan-Davao Road, K1458+680 - K1460+1258, Davao del Norte 1st LD DPWH CY-2014 (Widening of Agusan-Davao Road, K1458+680 - K1460+1087.48) | Tagum City, Davao del Norte | 2014-10-25 | 1st | XI | LF | 44.2071 | 195 | 2014-02-03 | 2014-08-16 | 0.91% | O | 0.398 | 0.193 | 0.3 |  |  |  | 89.1% | 89.10% Very Satisfactory
FFJJ Construction | 15712 | L | AAA | LB | GE | Construction/Improvement of Access Road to Declared Tourism Destination at Brgy. San Agustin, Km. 1607+480 - Km. 1609+592.793 | Sta. Maria, Davao del Sur | 2014-10-22 | 1st | XI | LF | 46.2802 | 208 | 2014-03-03 | 2014-09-26 |  | O | 0.291 | 0.218 | 0.104 | 0.022 | 0.04 | 0.017 | 69.2% | 69.20% Poor
FFJJ Construction | 16712 | L | AAA | LB | GE | Road Upgrading (gravel to paved) along Davao-Sarangani Coastal Road, (Malalag-Malita-JAS Road), km. 1678+776 to km. 1679+860, Calian Section | Davao del Sur | 2014-08-07 | 2nd | XI | LF | 42.7236 | 179 | 2013-03-07 | 2013-09-01 | 0 | O | 0.023 | 0.3 | 0 | 0.03 | 0.019 | 0 | 37.2 | -
FFJJ Construction | 16712 | L | AAA | LB | GE1 | Rd. Upgrading (gravel to paved) along Davao-Sarangani Coastal Rd., (Malalag-Malita-JAS Rd.), Km.1678+776-Km.1679+860, Calian Sect. | Davao del Sur | 2013-08-07 | 1st | XI | LF | 42.724 | 179 | 2013-03-07 | 2013-09-01 | 2.87 | O | 0.315 | 0.15 | 0.15 | 0.03 | 0.023 | 0.033 | 70.1 | -
FFJJ Construction | 16712 | L | AAA | LB | GE1 | Const./Widening/Upgrading/Rehab. of Access Rd. to declare Tourism Destination, Brgy. Lacaron | Malita, Davao del Sur | 2013-08-10 | 2nd | XI | LF | 45.264 | 227 | 2013-01-14 | 2013-08-28 | -1.94 | O | 0.397 | 0.292 | 0.131 | 0.01 | 0.023 | 0.033 | 88.6 | -
FFJJ Construction | 16712 | L | AAA | LB | GE1 | Cons./Widening/Upgrading of Access Rd. to Declared Tourism Destination, Brgy. Lacaron | Malita, Davao del Sur | 2013-03-14 | 1st | XI | LF | 45.264 | 179 | 2013-01-14 | 2013-07-11 | 56.27 | O | 0.36 | 0 | 0.15 | 0 | 0.03 | 0.05 | 59 | -
FFJJ Construction | 16712 | L | AAA | MA | GE2 | Const. of Caraga River Protection, San Jose | Caraga, Davao Oriental | 2013-08-17 | 1st | XI | LF | 14.405 | 247 | 2013-01-29 | 2013-10-02 | -8.5 | O | 0.347 | 0.3 | 0.065 | 0.03 | 0.02 | 0.033 | 79.5 | -
FFJJ Construction | 16712 | L | A | MB | GE1 | Const. of Kinangan Bridge and Approaches |  | 2008-09-02 | 3rd | XI |  | 18.593 | 332 |  |  |  | O | 0.304 | 0.24 | 0.07 | 0.015 | 0.035 | 0.1 | 76.4 | -
FFJJ Construction | 16712 | L | AAA | LB | GE1 | Widening of Tagum-Panabo Circ. Rd., 1st District Pob. Kapalong Sect., Km.1477+273-Km.1478+420 | Kapalong, Davao del Norte | 2013-03-18 | 1st | XI | LF | 18.563 | 133 | 2013-01-25 | 2013-06-06 | 0.1 | O | 0.337 | 0.235 | 0.15 | 0.03 | 0.05 | 0.033 | 83.5 | -
FFJJ Construction | 16712 | L | AA | LA | GE1 | Conc. of Davao del Sur-Sarangani Coastal Road, Kitayo-Balangonan Section |  | 2008-11-22 | 1st | XI |  | 28.9 | 300 |  |  |  | O | 0.274 | 0.241 | 0.1 | 0.022 | 0.035 | 0.067 | 73.9 | -
FFJJ Construction | 16712 | L | AA | LA | GE1 | Const. of Pangian Bridge II and Approaches |  | 2008-11-23 | 2nd | XI |  | 22.868 | 454 |  |  |  | O | 0.307 | 0.151 | 0.1 | 0.03 | 0.03 | 0.067 | 68.5 | -
FFJJ Construction | 16712 | L | AAA | LA | GE1 | Rehab./Recons/Upgrading of Digos-Makar Road, Baluyan-Tagansule Section, Km. 1587+500-Km. 1589+000 |  | 2009-05-28 | 1st | XI |  | 19.289 | 210 |  |  |  | O | 0.32 | 0.225 | 0.15 | 0.03 | 0.046 | 0.05 | 82.1 | -
FFJJ Construction | 16712 | L | AA | LA | GE1 | Rehab/Conc. of Road Jct. Mana-Ticulon Lagumit Little Baguio Road |  | 2009-03-04 | 1st | XI |  | 19.293 | 262 |  |  |  | O | 0.279 | 0.252 | 0.11 | 0.03 | 0.048 | 0.033 | #VALUE! | -
FFJJ Construction | 16712 | L | AAA | MA | GE2 | Const. of Bank Protection along Hijo River, Apokon Sect. Tagum City, (Surigao-Davao Coastal Rd.) | Davao del Norte | 2012-11-23 | 1st | XI | LF | 18.341 | 150 | 2012-07-30 | 2012-12-27 | 0.24 | O | 0.36 | 0.24 | 0.15 | 0.03 | 0.035 | 0.05 | 86.5 | -
FFJJ Construction | 16712 | L | AAA | MA | GE2 | Repair/Rehab. of Protection Works, Pamana | Malita, Davao del Sur | 2012-11-21 | 1st | XI | LF | 9.25 | 159 | 2012-07-31 | 2013-01-05 | -1.6 | O | 0.385 | 0.24 | 0.134 | 0.03 | 0.03 | 0.033 | 85.2 | -
FFJJ Construction | 14268 | L | AAA | LB | GE | Widening of Cotabato-Marbel Road, K1712+398.30 - K1717+000 (w/ exception), Bishop's Palace-Paraiso Section | South Cotabato | 2014-08-04 | 1st | XII | LF | 46.743 | 180 | 2014-02-10 | 2014-08-08 | 0.23 | O | 0.322 | 0.24 | 0.15 | 0.03 | 0.057 | 0.05 | 84.9 | -
FFJJ Construction | 16712 | L | AAA | LB | GE1 | Replacement of (Temp. to Perm.) NIA Bridge (15LM FSB) along Kidapawan-Calunasan-M'lang Rd. C021+958-C022+438 | M'lang, Cotabato | 2013-03-18 | 2nd | XII | LF | 11.439 | 316 | 2012-02-06 | 2012-12-17 | - | O | 0.329 | 0.3 | 0 | 0.03 | 0.04 | 0.033 | 73.2 | -
FFJJ Construction | 16712 | L | AAA | LB | GE1 | Rds. to Address Critical Bottlenecks Nat'l Bridges, Widening/Rehab./Strengthening of Permanent Bridges, Luayan Bridge along Midsayap-Marbel Rd. | South Cotabato | 2013-08-05 | 1st | XII | LF | 4.854 | 190 | 2013-02-05 | 2013-08-13 | 1.11 | O | 0.369 | 0.24 | 0.15 | 0.02 | 0.037 | 0.033 | 84.9 | -
FFJJ Construction | 16712 | L | AAA | LB | GE1 | Rehab./Conc. of FMR at Brgy. Poblacion to Brgy. Benolen | Datu Odin Sinsuat, Maguindanao | 2011-08-08 | 1st | XII | LF | 9.503 | 75 | 2011-02-12 | 2011-04-28 | - | O | 0.284 | 0.2 | 0 | 0.02 | 0.035 | 0.033 | 57.2 | -
FFJJ Construction | 16712 |  |  |  |  | Conc. of Cotabato City Circumferential Road |  | 2010-06-01 |  | XII |  | 27.563 | 150 |  |  |  | O | 0.32 | 0.201 | 0.15 | 0.03 | 0.042 | 0.033 | 77.6 | -
FFJJ Construction | 16712 | L | AA | LA | GE1 | Const. of Kiblis Bridge with Bridge and Approaches, Sarangani-Sultan Kudarat Coastal Road |  | 2008-09-02 | 2nd | XII |  | 21.574 | 280 |  |  |  | O | 0.342 | 0.273 | 0 | 0.03 | 0.028 | 0.067 | 74 | -
FFJJ Construction | 16712 | L | AAA | LA | GE1 | Concreting of Paco-Roxas-Arakan Valley Road, New Pontevedra Section |  | 2009-05-30 | 2nd | XII |  | 15.095 | 206 |  |  |  | O | 0.327 | 0.3 | 0 | 0.024 | 0.045 | 0.033 | 72.9 | -
FFJJ Construction | 16712 | L | AA | LA | GE1 | Conc. of Paco-Roxas-Arakan Rd. (New Ponteverdra Section) |  | 2009-03-10 | 1st | XII |  | 15.095 | 150 |  |  |  | O | 0.378 | 0.3 | 0 | 0.03 | 0.06 | 0.033 | #VALUE! | -
FFJJ Construction | 16712 | L | AAA | LB | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Arterial Rd. along Makilla-Ala Valley Rd. K1611+979-K1614+456 | Makilala, Cotabato | 2012-11-20 | 2nd | XII | LF | 37.131 | 345 | 2012-01-31 | 2013-01-09 | 0.55 | O | 0.384 | 0.248 | 0.15 | 0.03 | 0.045 | 0.033 | 89 | -
FFJJ Construction | 16712 | L | AAA | LB | GE1 | Rehab./Reconst./Upgrading along Makilala-Ala Valley Rd., K1611+979-K1614+456 | Makilala, Cotabato | 2012-08-10 | 1st | XII | LF | 33.756 | 270 | 2012-01-31 | 2012-10-26 | 5 | O | 0.352 | 0.249 | 0.15 | 0.03 | 0.051 | 0.033 | 86.5 | -
FFJJ Construction | 16712 | L | AAA | LB | GE1 | Replacement of (Temp. to Perm.) NIA Bridge (15 LM FSB) along Kidapawan-Calunasan-M'lang Rd., C021+958-C022+438 | M'lang, Cotabato | 2012-08-11 | 1st | XII | LF | 10.407 | 226 | 2012-02-06 | 2012-09-18 | 2.42 | O | 0.321 | 0.269 | 0.15 | 0.03 | 0.051 | 0.033 | 85.4 | -
FFJJ Construction | 16712 | L | AAA | LB | GE1 | Replacement of (Temp. to Perm.) of Binay Bridge along Nowa-Doroluman-Greenfield Nat'l Rd., Magpet | M'lang, Cotabato | 2012-08-10 | 1st | XII | LF | 24.828 | 244 | 2012-01-31 | 2012-09-30 | -5 | O | 0.379 | 0.24 | 0.1 | 0.03 | 0.042 | 0.033 | 82.4 | -
FFJJ Construction | 16712 | L | AAA | LB | GE | Rehab./Reconst./Upgrading of Damaged Paved Road along NRJ Cuevas - Sta. Josefa Road, K1371+541 - K1373+000 | Trento, Agusan del Sur | 2014-08-08 | 1st | XIII | LF | 22.263 | 206 | 2014-02-06 | 2014-08-30 | -1.87 | O | 0.303 | 0.29 | 0.131 | 0.03 | 0.051 | 0.033 | 83.8 | -
FFJJ Construction | 16712 | L | AAA | LB | GE1 | Roadslip/Protection along Surigao-Davao Coastal Rd., Lingig, Brgy. Mahayahay, Lingig Km.1478+500-Km.1478+545, (Km.1478+46-Km.1478+244.50) | Surigao del Sur | 2013-03-17 | 2nd | XIII | LF | 23.39 | 245 | 2012-07-23 | 2013-03-25 | 0.1 | O | 0.321 | 0.225 | 0.15 | 0.03 | 0.05 | 0.05 | 82.6 | -
FFJJ CONSTRUCTION | 16712 | L | AAA | MB | GE | Cluster III - Construction of Multi-Purpose Building (Gym) and Repair & Imprvt. Of Multi-Purpose Gym | Kinablangan, Baganga, Davao Oriental | 2015-06-06 | Final | Davao Oriental 1st | LF | 2.454 | 90 | 2015-02-18 | 2015-05-18 | 0% | C | 0.407 | 0.133 | 0.3 | - | - | - | 84% | *84% Satisfactory
FFJJ CONSTRUCTION | 31713 | L | AAA | MA | GE | Construction of Flood Control Structure along Davao River Basin: Davao River Flood Control (Gem Village) | Brgy. Maa, 1st District, Davao City | 2015-06-12 | Final | Davao City | LF | 9.385 | 117 | 2014-11-29 | 2015-03-25 | 0% | C | 0.407 | 0.133 | 0.3 | - | - | - | 84% | *84% Satisfactory
FFJJ CONSTRUCTION | 16712 | L | AAA | LB | GE | Widening of Cotabato-Marbel Road, K1712+398.39- K1712+000 (w/ exception), Bishop's Palace-Paraiso Section | South Cotabato | 2015-06-02 | Final | South Cotabato DEO | LF | 46.743 | 210 | 2014-02-10 | 2014-09-08 | 0% | C | 0.428 | 0.133 | 0.3 | - | - | - | 86.1% | *86.1% Satisfactory
FFJJ CONSTRUCTION | 16712 | L | AAA | LB | GE | Concreting of Road from Libuton, New Bataan to Camp Uno (1) Leading to White Peak (Mt. Pandadagsaan), Brgy. Andap, New Bataan, Compostela Valley Province | Brgy. Andap, New Bataan, Compostela Valley Province | 2015-08-28 | 1st | Regional Office No. XI | LF | 83.695 | 220 | 2015-05-10 | 2015-12-15 | 2.37% | O | 0.391 | 0.239 | 0.15 | 0.03 | 0.06 | 0.05 | 92% | -
FFJJ CONSTRUCTION | 16712 | L | AAA | LB | GE | Upgrading (Asphalt to Concrete) of Dipolog-Sindangan-Liloy Road, 1891+000 to 1893+880.00, with exceptions, Jose Dalman, Zamboanga del Norte | 1891+000 to 1893+880.00, with exceptions, Jose Dalman, Zamboanga del Norte | 2015-11-15 | 1st | Regional Office | LF | 72.1482 | 316 | 2015-04-29 | 2016-03-09 | -13.88% | OG | 0.364 | 0.3 | 0.011 | 0.03 | 0.047 | 0.033 | 78.5% | 78.5% Unsatisfactory
FFJJ CONSTRUCTION | 16712 | L | AAA | MB | GB | Construction of Two Storey 4 - CL School Building, Tablon NHS, Barangay Tablon, Cagayan de Oro City | Barangay Tablon, Cagayan de Oro City | 2015-11-15 | 1st | Cagayan de Oro City 2nd | LF | 5.9922 | 105 | 2015-09-14 | 2015-12-28 | (+) 0.62% | OG | 0.388 | 0.24 | 0.15 | 0.03 | 0.041 | 0.05 | 89.9% | 89.9% Very Satisfactory
FFJJ CONSTRUCTION | 16712 | L | AAA | LB | GE | Rehab./Major Repair of Bangoy Bridge, Montevista-Compostela-Mati Boundary Road, Compostela Valley | Compostela Valley | 2015-11-12 | Final | Compostela Valley DEO | LF | 8.284e-06 | 127 | 2015-02-18 | 2015-06-24 | 0.4 | C | 0.469 | 0.183 | 0.3 | - | - | - | 95.2% | 95.2% Very Satisfactory
FFJJ CONSTRUCTION | 16712 | L | AAA | MB | GB | Construction of Multi-Purpose (Gym) and Repair and Improvement of Multi-Purpose (Gym), Municipality of Baganga, Davao Oriental | Baganga, Davao Oriental | 2015-11-10 | Final | Davao Oriental 1st DEO | LF | 4.778e-06 | 90 | 2015-02-18 | 2015-05-18 | -0.046 | C | 0.49 | 0.2 | 0.162 | - | - | - | 85.2% | 85.2% Satisfactory
FFJJ CONSTRUCTION | 16712 | L | AAA | 0 | GE | Widening of National Rd. K1655+1653 to K1656+000 along Matalam- M'lng-Bagontapay Junction Rd., Mlng. Cotabato | Mlang, Cotabato | 2015-01-11 | 1st | Cotabato First DEO | LF | 19.293 | 224 | 2015-03-06 | 2015-10-15 | (-) 9.00% | OG | 0.354 | 0.16 | 0.06 | 0 | 0 | 0 | 57.4% | 57.4% Poor
FFJJ CONSTRUCTION | 16712 | L | AAA | MA | GE | Construction of Slope/Bank Protecction of Bahayan River Protecting Salvacion Bridge along Cuevas-Bislig Road, K0+410.20 - K0+470.60, Trento, Agusan del Sur | Trento, Agusan del Sur | 2015-11-11 | 1st | Agusan del Sur 2nd DEO | LF | 14.475 | 282 | 2015-02-12 | 2015-11-20 | (+) 0.25 | OG | 0.341 | 0.3 | 0.15 | 0.03 | 0.06 | 0.033 | 91.4% | 91.4% Very Satisfactory
FFJJ CONSTRUCTION | 16712 | L | AAA | LB | GE | Road Upgrading (Unpaved to Paved) Jct. Gamut San Miguel - Bayugan (K1320+060.00 - K1320+300.00, K1320+876.65 - K1321+415.88, K1321+770.68 - K1322+847.40) | Tago - San Miguel, Surigao Del Sur | 2015-06-08 | 1st | SURIGAO DEL SUR FIRST DEO | LF | 36.363 | 143 | 2015-03-20 | 2015-08-09 | (+) 18.04% | O | 0.388 | 0.238 | 0.15 | 0.03 | 0.05 | 0.05 | 90.6% | -
FFJJ Construction | 16712 | L | AAA | LB | GE1 | Rd. Slip/Protection along Surigao-Davao Coastal Rd., Lingig Brgy. Mahayahay, Lingig, Km. 1478+500-Km. 1478+545 (Km. 1478+46-Km. 1478+244.50) | Surigao del Sur | 2012-11-25 | 1st | XIII | LF | 23.392 | 210 | 2012-07-23 | 2013-02-18 | 0.21 | O | 0.32 | 0.225 | 0.15 | 0.022 | 0.06 | 0.05 | 82.7 | -
FFJJ CONSTRUCTION/ REYDAN BUILDERS JOINT VENTURE | JV-14-598 | L | AAA | LB | GE | Constructrion of New Permanent Bridges, Matti Bridge 2 along Davao-Cotabato Road (Jct. Digos-Cotabato Section) | Davao del Sur | 2015-06-05 | 1st | Davao del Sur 1st | LF | 26.615 | 210 | 2015-03-03 | 2015-09-28 | (+)0.09% | O | 0.38 | 0.194 | 0.15 | 0.03 | 0.051 | 0.05 | 85.5% | -
FFJJ Construction/JMT Construction -Joint Venture | JV-13-400 | L | AAA | LB | GE | Road Upgrading (Gravel to Concrete) of Jct. Magsaysay - Cagdianao Road, Chainage 000 - Chainage 468.70, K0005+520 - K0016+680 with Exception | Cagdianao, Dinagat Province | 2014-08-14 | 1st | XIII | LF | 81.7898 | 235 | 2014-03-14 | 2014-11-03 | -4.91 | O | 0.394 | 0.25 | 0.101 | 0.03 | 0.042 | 0.033 | 85 | -
FFJJ CONSTRUCTION/J-ONE BUILDERS JOINT VENTURE | JV-14-355 | L | AAA | MA | GE | Construction of Flood Control Project along Libungan River, Nicaan Flood Control | Nicaan, Libungan, Cotabato | 2015-06-05 | 1st | Cotabato 2nd DEO | LF | 18.506 | 215 | 2015-02-20 | 2015-09-23 | 45.81% | O | 0.349 | 0.24 | 0.15 | 0.03 | 0.037 | 0.033 | 83.9% | -
FFJJ CONSTRUCTION/RDEN CONSTRUCTION & SUPPLY JOINT VENTURE | JV-14-380 | L | AAA | MA | GE | Construction of Flood Control Project along Libungan River, Mirasol Flood Control | Libungan, Cotabato | 2015-08-28 | 1st & Final | Cotabato 2nd | LF | 18.526 | 215 | 2015-02-23 | 2015-09-25 | (+)47.79% | C | 0.375 | 0.2 | 0.3 | - | - | - | 87.5% | *87.5% Satisfactory
FGM Builders Resources & Development Corporation | 31807 | L | C | SB | GB1 | Const. of 2-Storey, 2-Cl @ V. Corcuera ES, Package Z | Davao City | 2013-08-19 | 1st | XI | LF | 2.215 | 240 | 2013-03-27 | 2013-11-21 | 3.12 | O | 0.358 | 0.285 | 0.15 | 0.03 | 0.038 | 0.05 | 91.1 | -
Fiat Construction Services | 5463 | L | AAA | LB | GE | Road Upgrading (Gravel to Paved) of San Isidro - Daja Road K1018+(-497)……... | San Isidro, Leyte | 2014-08-08 | 1st | VIII | LF | 45.3343 | 237 | 2014-01-30 | 2014-09-23 | 0.78 | O | 0.29 | 0.238 | 0.15 | 0.022 | 0.045 | 0.033 | 77.8 | -
Fiat Construction Services | 5463 | L | AAA | LB | GE1 | Rd. Upgrading (Gravel to Paved) of Tabango-Catmon-La Fortuna-Manlawaan-Gimarco Rd., Km.1040+297-Km.1042+307 | Tabango, Leyte | 2013-08-12 | 2nd | VIII | LF | 44.04 | 223 | 2013-01-07 | 2013-08-17 | -4.48 | O | 0.362 | 0.24 | 0.105 | 0.018 | 0.042 | 0.017 | 78.4 | -
Fiat Construction Services | 5463 | L | AAA | LB | GE1 | Rd. Upgrading (Gravel to Paved) of Tabango-La Fortuna-Manlawaan-Gimarco Rd. Km.1040+297-Km.1042+307 | Tabango, Leyte | 2013-03-13 | 1st | VIII | LF | 44.04 | 210 | 2013-01-07 | 2013-08-04 | 12.04 | O | 0.27 | 0.24 | 0.15 | 0.03 | 0.04 | 0.033 | 76.3 | -
Fiat Construction Services | 5463 | L | AAA | LB | GE1 | Conc. of Dinagat Island Resort Road Network (San Jose-Basilisa Sect.) with One (1) Bridge and One (1) Box Culvert) | Dinagat Island | 2011-08-11 | 5th | XIII | LF | 188.938 | 567 | 2009-06-07 | 2011-08-21 | -3.768 | O | 0.389 | 0.267 | 0.112 | 0.03 | 0.047 | 0.017 | 86.2 | -
Fiat Construction Services | 5463 |  |  |  |  | Conc. of Dinagat Island Road Network (San Jose-Basilisa Section with One (1) Bridge and One (1) Box Culvert |  | 2010-08-26 |  | XIII |  | 188.939 | 525 |  |  |  | O | 0.38 | 0.287 | 0.064 | 0.03 | 0.047 | 0.017 | 82.5 | -
Fiat Construction Services | 5463 | L | AAA | LA | GE1 | Conc. of Dinagat Island Rd. Network(San Jose-Basilisa Sect. with 1 Bridge and 1 Box Culvert) |  | 2009-09-05 | 1st | XIII |  | 188.939 | 465 |  |  |  | O | 0.382 | 0.253 | 0.15 | 0.03 | 0.047 | 0.033 | 89.5 | -
Fiat Construction Services | 5463 | L | AAA | LB | GE1 | Conc. of Dinagat-Loreto Road (San Jose-Basilisa Sect.) | Province of Dinagat Islands | 2011-08-11 | 3rd | XIII | LF | 190.877 | 549 | 2010-03-31 | 2011-09-30 | -7.661 | O | 0.372 | 0.297 | 0.073 | 0.03 | 0.054 | 0.017 | 84.3 | -
Fiat Construction Services | 5463 | L | AAA | LB | GE1 | Conc. of Dinagat-Loreto Road (San Jose-Basilisa Sect) | Province of Dinagat | 2011-04-07 | 2nd | XIII | LF | 190.877 | 450 | 2010-03-31 | 2011-07-23 | -1.2 | O | 0.374 | 0.247 | 0.138 | 0.03 | 0.055 | 0.05 | 89.4 | -
Fiat Construction Services | 5463 |  |  |  |  | Conc. of Dinagat-Loreto Road (San Jose Basilisa Section) |  | 2010-08-26 |  | XIII |  | 190.878 | 420 |  |  |  | O | 0.36 | 0.262 | 0.15 | 0.03 | 0.047 | 0.033 | 88.2 | -
Fiat Construction Services | 5463 |  |  |  |  | Conc. of Butuan City-Paining-Tandag Road |  | 2010-06-12 |  | XIII |  | 26.285 | 195 |  |  |  | O | 0.343 | 0.3 | 0.15 | 0.03 | 0.04 | 0.033 | 89.6 | -
FIAT Construction Services & B.M. Marketing (JV) | 9852 | L | AAA | MB |  | Tacloban Airport Development Project | Brgy. San Jose, Tacloban City, Leyte | 2014-03-13 | 2nd | DOTC | LF | 176.112 | 360 | 2013-04-25 | 2014-05-25 | 2.04 | O | 0.341 | 0.3 | 0.15 | 0.03 | 0.056 | 0.05 | 92.7 | -
Fiat Construction Services / 3K Rock Engineering (JV) | JV-11-420 | L | AAA | LB | GE1 | Rd. Upgrading (gravel to concrete) of Gurel-Bokod-Kabayan-Buguias-Abatan Rd., K0312+500-K0330+000 (I.S.) | Bokod, Benguet | 2012-11-20 | 1st | CAR | LF | 132.763 | 387 | 2012-04-19 | 2013-05-10 | 12.57 | O | 0.376 | 0.24 | 0.15 | 0.015 | 0.038 | 0.033 | 85.2 | -
Fiat Construction Services / KVC Construction (JV) | JV-11-012 | L | AAA | LB | GE1 | Rd. Upgrading (Gravel to Conc.) along Gurel-Bokod-Kabayan-Buguias-Abatan Rd., K0303+600-K0312+600 (IS) Abat-Bila Sect. | Bokod, Benguet | 2012-07-31 | 1st | CAR | LF | 113.005 | 330 | 2011-09-05 | 2012-07-30 | -2 | O | 0.356 | 0.3 | 0.13 | 0.008 | 0.037 | 0.033 | 86.4 | -
Fiat Construction Services / MG Samidan Construction (JV) | JV-11-321 | L | AAA | LB | GE1 | Rd. Upgrading (gravel to concrete) of Mt. Province-Ilocos Sur via Kayan Rd. K0385+995-K0391+000 | Bunga, Tadian, Mt. Province | 2012-11-22 | 2nd | CAR | LF | 83.201 | 327 | 2012-03-12 | 2013-02-01 | -5.07 | O | 0.371 | 0.289 | 0.099 | 0.03 | 0.059 | 0.033 | 88.1 | -
Fiat Construction Services / MG Samidan Construction (JV) | JV-11-321 | L | AAA | LB | GE1 | Rd. Upgrading (Gravel to Conc.) along Mt. Province-Ilocos Sur Rd. via Kayan Rd., K0385+995-K0391+000, Burgos | Tadian, Mt. Province | 2012-08-03 | 1st | CAR | LF | 83.201 | 270 | 2012-03-12 | 2012-12-06 | -2.85 | O | 0.326 | 0.3 | 0.122 | 0.03 | 0.051 | 0.033 | 86.2 | -
FIAT CONSTRUCTION SERVICES/ALCEL CONSTRUCTION (JV) | JV-12-649 | L | AAA | LB | GE | Road Upgrading (Gravel to Paved) of Gurel - Bokod - Kabayan - Buguias - Abatan Road K0341+478.38 - K0352+558.38 (With Exceptions) | Benguet | 2015-02-26 | Final | CAR | LF | 144.719 | 534 | 2013-04-02 | 2014-09-17 | (+) 1.03% | C | 0.402 | 0.2 | 0.3 | - | - | - | 90.2% | *90.2% Very Satisfactory
Filipinas (Prefabricated Bldg.) Systems, Inc. | 5562 | L | AAA | LB | GB1 | Const. of Four (4) Storey with Roof Deck for DBM Building |  | 2008-11-26 | 3rd | Sp. Bldgs. |  | 445.429 | 710 |  |  |  | O | 0.372 | 0.3 | 0.1 | 0.03 | 0.061 | 0.067 | 93 | -
Firmabuilt Construction | 30175 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of Damaged Nat'l Rd., (Int. Sect.) Jct. MWCR (Bagong Silang)-Cabacao, Diversion Rd., K0424+(-)399 to K0424+(-)029, Brgy. Cabagao | Abra de Ilog, Occidental Mindoro | 2013-07-29 | 1st | IVB | LF | 6.96 | 138 | 2013-02-11 | 2013-06-28 | - | O | 0.332 | 0.3 | 0 | 0.015 | 0.025 | 0 | 67.2 | -
Firmabuilt Construction / Marcbilt Construction, Inc. Joint Venture | JV-09-256 |  |  |  |  | Road Upgrading at Abre de Ilog-San Jose Road (Marilao-Bagong Silang Sect.), Brgy. New Dagupan |  | 2010-08-27 |  | IVB |  | 19.192 | 180 |  |  |  | O | 0.355 | 0.054 | 0.15 | 0.03 | 0.025 | 0.033 | 64.7 | -
Firmabuilt Construction / Performance Builders & Developers Corporation (JV) | JV-12-257 | L | B | MA | GE1 | Replacement/Reconst. of Mangat Bridge along Mindoro West Coastal Rd., Brgy. San Pedro | Rizal, Occidental Mindoro | 2013-07-30 | 1st | IVB | LF | 6.736 | 220 | 2012-12-09 | 2013-07-16 | -4 | O | 0.355 | 0.3 | 0.046 | 0.03 | 0.037 | 0.033 | 80.1 | -
FIRST BUILDERS AND DEVELOPERS | - | - | - | - | - | Repair/ Renovation/ Expansion/ Completion of Rural Health Unit | Poblacion, Medellin, Cebu | 2015-09-01 | 1st & Final | Cebu 1st | LF | 1.459 | 60 | 2014-10-08 | 2014-12-06 | 0% | C | 0.489 | 0.108 | 0.3 | - | - | - | 89.7% | *89.7% Very Satisfactory
FIRST BUILDERS AND DEVELOPERS | 31124 | L | B | SB | GE | Flood Contol - Riprapping, Barangay Sapangdaku, Cebu City | Cebu City | 2015-11-20 | Final | Cebu City | LF | 1.9643 | 90 | 2015-08-21 | 2015-11-18 | 0 | C | 0.483 | 0.133 | 0.3 | - | - | - | 91.6% | 91.6% Very Satisfactory
FIRST GRANDEUR BUILDERS | 35388 | L | D | SB | GE | Opening of Road, Brgy. Pasil Road to Looc, Santander, Cebu | Santander, Cebu | 2015-11-11 | Final | Cebu 4th | LF | 4.7845 | 45 | 2015-06-16 | 2015-07-30 | 0 | C | 0.489 | 0.133 | 0.3 | - | - | - | 92.2% | 92.2% Very Satisfactory
FIRST NORTHWAY DEVELOPMENT AND CONSTRUCTION | 11645 | L | B | MA | GE | Construction/Maintenance of Flood Control Mitigation Sturcture and Drainage System, Oaig-Daya-San Nicolas Flood Control | Candon City, Ilocos Sur | 2015-06-02 | 1st | Ilocos Sur 2nd DEO | LF | 13.783 | 149 | 2015-02-05 | 2015-07-03 | 10.85% | O | 0.306 | 0.29 | 0.15 | 0.03 | 0.045 | 0.033 | 85.4% | -
First Northway Development and Construction Corporation | 11645 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of Damage Paved Nat'l Rd. Jct. Santiago Banayo-Lidlidda-San Emilio-Quirino Rd. a)K0369+129-K0370+242 b)K0270+477-K0370+587, c)K0370+745-K0371+726 | Ilocos Sur | 2013-08-12 | 1st | I | LF | 36.423 | 203 | 2013-02-22 | 2013-09-12 | -3.97 | O | 0.335 | 0.3 | 0.11 | 0.03 | 0.037 | 0.033 | 84.5 | -
First Northway Development and Construction Corporation | 11645 |  |  |  |  | Completion of Candon-Salcedo Road |  | 2010-02-18 |  | I |  | 14.32 | 225 |  |  |  | O | 0.279 | 0.129 | 0.15 | 0.03 | 0.051 | 0.05 | 68.9 | -
First R + J Builders Phil's Corporation | 32530 | L |  | SB |  | Construction & Dev't of Linear Park along Pasig River: Beyond 3 Meter | Makati Poblacion | 2016-06-23 | 1st & Final | PRRC | LF | 4.533 | 180 | 2016-01-05 |  | 0 | C | 0.33 | 0.3 | 0.15 | 0.01 | 0.03 | 0.05 | 87 | *87.00% Satisfactory
FIT CONSTRUCTION | 35857 | L | D | SB | GB | Construction of Academic Rooms SB Guimod/School Building, Guimod E/S | Bantay, Ilocos Sur | 2015-06-05 | 1st | Ilocos Sur 1st DEO | LF | 1.886 | 120 | 2015-02-17 | 2015-06-16 | 4.53% | O | 0.356 | 0.215 | 0.15 | 0.03 | 0.052 | 0.033 | 83.6% | -
FIT CONSTRUCTION | 35857 | L | D | SB | GB | Construction of Academic Rooms School Bldg. and Repair of Vatious Academic Rooms/School Building, Lingsat E/S, Brgy. Lingsat, Bantay and San Vicente Integrated School, Brgy. Poblacion, San Vicente, Ilocos Sur | San Vicente, Ilocos Sur | 2015-11-14 | Final | ILOCOS SUR 1ST DEO | LF | 1.9336 | 120 | 2015-05-05 | 2015-09-01 | 0.3583 | C | 0.494 | 0.133 | 0.3 | - | - | - | 92.7% | 92.7% Very Satisfactory
FIVE MASSIVE INFRA & SUPPLY CORP. | 36876 | L | D | SB | GE | Concreting of Road at Sitio Sta. Cruz, Brgy. Malativas | Panabo City, Davao del Norte | 2015-06-10 | 1st | Davao del Norte | LF | 1.817 | 64 | 2015-04-14 | 2015-06-16 | (+)1.20% | O | 0.34 | 0.236 | 0.15 | 0.03 | 0.037 | 0.033 | 82.6% | -
FIVE MASSIVE INFRA & SUPPLY CORP. | 36876 | L | B | MA | GE | Concreting of Road Sitio Sta. Cruz, Brgy. Malativas, Panabo City, Davao del Norte | Brgy. Malativas, Panabo City, Davao del Norte | 2015-08-29 | Final | Davao del Norte DEO | LF | 1.817 | 47 | 2015-04-14 | 2015-05-30 | - | C | 0.44 | 0.113 | 0.3 | - | - | - | 85.3% | *83.68% Satisfactory
FIVE MASSIVE INFRA & SUPPLY CORP. | 36876 | L | A | SB | GB | Local Infrastructure Program-Completion of Multi-Purpose Building, Municipality of New Corella, Davao del Norte | Corella, Davao del Norte | 2015-11-13 | Final | Davao del Norte DEO | LF | 1.911e-06 | 90 | 2015-05-20 | 2015-08-17 | 0.0096 | C | 0.439 | 0.183 | 0.3 | - | - | - | 92.2% | 92.2% Very Satisfactory
Flordes Construction & Trading | 16916 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Paved) of Eastern Bulacan Rd., K098+000-K0100+000, Doña Remedios | Trinidad, Bulacan | 2013-03-20 | 1st | III | LF | 45.888 | 210 | 131/13 | 2013-08-29 | 31.51 | O | 0.381 | 0.238 | 0.15 | 0.01 | 0.04 | 0.05 | 86.9 | -
Flordes Construction & Trading | 16916 | L | B | MA | GE1 | Rehabilitation of NCR/Bulacan Boundary-Bigte Ipo Dam Road |  | 2009-06-01 | 1st | III |  | 42.9025 | 150 |  |  |  | O | 0.334 | 0.24 | 0.15 | 0.03 | 0.04 | 0.05 | 84.4 | -
Flordes Construction & Trading | 16916 | L | B | MA | GB1 | Const./Rehab./Replacement/ Completion and Repair of A. Regidor Elem. School |  | 2009-05-20 | 1st | NCR |  | 2.481 | 120 |  |  |  | O | 0.326 | 0.24 | 0.15 | 0.03 | 0.065 | 0.05 | 86.1 | -
Flordes Construction & Trading Corp. (Formerly: Flordes Construction & Trading) | 16916 | L | A | MA | GE | Preventive Maintenance Based on Pavement Management System/Highway Development and Management-4 (HDM-4) along Jones Bridge | Sta. Cruz, Manila | 2014-11-24 | 1st | NCR | LF | 13.9356 | 192 | 2014-06-30 | 2015-01-07 | -7.92% | O | 0.393 | 0.262 | 0.071 | 0.03 | 0.058 | 0.033 | 84.7% | 84.70% Satisfactory
FLORDES CONSTRUCTION & TRADING CORP. (Formerly: Flordes Construction & Trading) | 16916 | L | A | MB | GE | Local Infrastructure Program - Rehabilitation of Roads with Drainage Improvement (Sabino Padilla) Gandara St., Soler St. to Q. Paredes St., Binondo, Manila 3rd LD | Binondo, Manila 3rd LD | 2015-09-01 | 1st | NM DEO | LF | 9.253 | 150 | 2015-04-14 | 2015-09-10 | 0.05% | O | 0.381 | 0.24 | 0.15 | 0.03 | 0.06 | 0.05 | 91.1% | -
FLT Enterprises | 23039 | L |  | MA |  | REHAB OF VARIOUS NIS IN THE PROVINCE OF ILOILO, Package I - Santa Barbara RIS | Santa Barbara, Iloilo, Region 6 | 2014-04-05 | 1st | NIA | LF | 4.13 | 120 | 2013-04-02 | 2014-04-18 | 0 | O | 0.336 | 0.245 | 0.15 | 0.03 | 0.038 | 0.05 | 84.9 | -
FLT Enterprises | 23039 | L |  | MA | GE2 | Concreting of Various Canal Service RD Package 1 - Barotac Viejo RIS | Barotac Viejo, Iloilo/Region VI | 2013-08-31 | 1st | NIA | L | 4.869 | 120 | 2013-03-26 | 2013-07-30 | -77 | O | 0.28 | 0.24 | 0 | 0.025 | 0.056 | 0.05 | 65.1 | -
FLT Enterprises | 23039 | L |  | MA | GE2 | Rehab. Of Various NIS in the Province of Iloilo, Package 1-Sta Barbara RIS | Sta Barbara, Iloilo/Regon VI | 2013-11-13 | 1st | NIA | L | 4.13 | 120 | 2013-04-01 | 2013-08-06 | -85 | O | 0.3333 | 0.24 | 0 | 0.02 | 0.056 | 0.05 | 69.93 | -
FLT Enterprises | 23039 | L |  | MA | GE2 | Rehab. Of Various NIS in the Province of Iloilo, Package 3-Aganan RIS | San Miguel & Oton, Iloilo/Region VI | 2013-11-15 | 1st | NIA | L | 6.495 | 150 | 2013-04-01 | 2013-09-05 | -56.32 | O | 0.3429 | 0.24 | 0 | 0.02 | 0.056 | 0.05 | 70.89 | -
FLT Enterprises | 23039 | L |  |  | GB1 | Proposed JRMP-2 Office | Tacas, Jaro, Ilo-ilo City | 2013-11-15 | 1st | NIA | L | 4.384 | 82 | 2013-08-07 | 2013-10-28 | -21.59 | O | 0.383 | 0.268 | 0.059 | 0.03 | 0.06 | 0.05 | 85 | -
Fortstone Construction Enterprises | 31668 | L | B | SB | GB1 | Const. of Sch. Bldg. a. 1-storey 1-CL @ Migdolog ES; b. 1-storey 2-CL @ John Martin Johnson HS, Don Marcelino | Davao del Sur | 2013-08-17 | 1st | XI | LF | 1.019 | 135 | 2013-03-29 | 2013-08-10 | 0.59 | O | 0.375 | 0.3 | 0.15 | 0.03 | 0.025 | 0.033 | 91.3 | -
Foundation Specialists, Inc. | 7437 | L | AAA | LB | GE1 | Region I Contract Package (CP1)-CP1.1, Const. of Villamil Bridge & Approaches | Calasiao, Pangasinan | 2012-08-14 | 1st | PMO-Sp. Bridges | FA | 89.221 | 458 | 2011-11-25 | 2013-02-24 | -4.89 | O | 0.4 | 0.3 | 0.101 | 0.03 | 0.065 | 0.033 | 92.9 | -
FOUR BROTHERS CONSTRUCTION | 31614 | L | D | SB | GE | Local Infrastructure Program - Flood Control Structure Facilities, c.) Construction of Chico River Flood Control, Bontoc, Mt. Province | Bontoc, Mt. Province | 2015-09-01 | 1st & Final | Mountain Province DEO | LF | 1.85 | 42 | 2015-05-14 | 2015-06-24 | 0% | C | 0.394 | 0.133 | 0.3 | - | - | - | 82.7% | *82.7% Satisfactory
Framecon Builders | 22482 | L | B | SB | GB1 | Const. of Two-Storey Four CL Sch. Bldg. at Northville 9 Elem. Sch. | Calumpit, Bulacan | 2013-08-14 | 1st | III | LF | 4.592 | 150 | 2013-05-15 | 2013-10-11 | 2.1 | O | 0.342 | 0.24 | 0.15 | 0.02 | 0.047 | 0.033 | 83.2 | -
Framecon Builders | 22482 | L | B | MA | GE1 | Conc. of Road Brgy. Diversion of San Leonardo (1,162.75 L.M.) | San Leonardo, Nueva Ecija | 2012-03-20 | 1st | III | LF | 9.553 | 160 | 2011-06-07 | 2011-11-13 | -2 | O | 0.337 | 0.2 | 0.24 | - | - | - | 77.7 | 87.06% Satisfactory
FRAMECON BUILDERS | 22482 | L | B | MA | GE | Construction of Drainage Canal along Bigaa - Plaridel via Bulacan and Malolos Section, Km 44+000 to Km 48+000 w/ exceptions, City of Malolos, Bulacan | City of Malolos, Bulacan | 2015-06-12 | Final | Bulacan 1st DEO | LF | 16.262 | 300 | 2014-03-13 | 2015-01-06 | 0% | C | 0.41 | 0.2 | 0.3 | - | - | - | 91% | *91% Very Satisfactory
FRAMECON BUILDERS | 22482 | L | B | MA | GE | Construction of Digmala River Control Pesa Section, Bongabon, Nueva Ecija | Bongabon, Nueva Ecija | 2015-06-11 | Final | Nueva Ecija 2nd DEO | LF | 8.992 | 110 | 2015-05-07 | 2015-08-24 | 0% | C | 0.341 | 0.191 | 0.3 | - | - | - | 83.2% | *83.2% Satisfactory
FRAMECON BUILDERS | 22482 | L | B | MA | GE | MF01- National Road Network Services- Asset Preservation of National Roads, Construction/Upgrading/Rehabilitation of Drainage along National Roads | Rodriguez - San Jose Road, K0031+000 to K0031+400 | 2015-06-01 | 1st | Rizal 2nd DEO | LF | 9.017 | 151 | 2015-02-11 | 2015-07-11 | -0.97% | O | 0.308 | 0.3 | 0.14 | 0.03 | 0.035 | 0.033 | 84.6% | -
FRAMECON BUILDERS | 22482 | L | B | MA | GE | Rehabilitation of Local Road, Brgy. Baritan, Malabon City | Malabon City | 2015-06-05 | 1st | Malabon-Navotas DEO | LF | 7.417 | 121 | 2015-03-10 | 2015-07-08 | (+) 0.27 | O | 0.386 | 0.24 | 0.15 | 0.015 | 0.051 | 0.05 | 89.2% | -
FRAMECON BUILDERS | 22482 | L | B | SB | GB | Construction of Multi=Purpose Building, Barangay 117, Caloocan City | Caloocan City | 2015-06-07 | 1st | Metro Manila 3rd DEO | LF | 4.092 | 120 | 2015-03-18 | 2015-07-15 | (+) 10.07 | O | 0.358 | 0.24 | 0.15 | 0.015 | 0.043 | 0.05 | 85.6% | -
FRAMECON BUILDERS | 22482 | L | B | MA | GE | Repair/Rehabilitation/Improvement of Gapan-Fort Magsaysay Road, Phase I K0101+560-K0103+680 w/ Exception, Peñaranda, Nueva Ecija | Phase I K0101+560-K0103+680 w/ Exception, Peñaranda, Nueva Ecija | 2015-09-01 | 1st & Final | Nueva Ecija Second DEO | LF | 8.623 | 100 | 2014-12-05 | 2015-03-14 | 0.04% | C | 0.343 | 0.2 | 0.3 | - | - | - | 84.3% | *84.3% Satisfactory
FRAMECON BUILDERS | 22482 | L | B | MA | GE | MFO 1 - National Road Network Services - Asset Preservation of National Roads, Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads, Rodriguez-San Jose Road, K0 031+000 - K0 031+400 | Rodriguez, Rizal | 2015-08-25 | 1st | Rizal 2nd | LF | 9.017 | 181 | 2015-02-11 | 2015-08-10 | 1.32% | C | 0.461 | 0.133 | 0.3 | - | - | - | 89.4% | -
FRAMECON BUILDERS | 22482 | L | B | MA | GE | Pampanga River Flood Control, San Anton Section, San Leonardo, Nueva Ecija 4th LD | San Leonardo, Nueva Ecija 4th LD | 2015-11-14 | Final | Nueva Ecija Second DEO | LF | 9.251 | 100 | 2015-05-07 | 2015-08-14 | 0.21% | C | 0.491 | 0.133 | 0.3 | - | - | - | 92.4% | 92.4% Very Satisfactory
FTENN Construction Service | 34659 | L | D | SB | GB | Construction of Multi-Purpose Building w/ Boardwalk | Brgy. Ogod, Donsol, Sorsogon | 2016-01-28 | Final | TIEZA | LF | 5 | 165 | 2015-02-27 | 2015-09-17 | -14.03 | C | 0.477 | 0.195 | 0 |  |  |  | 67.2 | 71.40 Poor
FTENN CONSTRUCTION SERVICES | 34659 | L | D | SB | GB | Construction of Multi-Purpose Building with Boardwalk | Donsol, Sorsogon | 2015-08-06 | 1st | TIEZA | LF | 5 | 165 | 2015-02-27 | 2015-09-17 | -26.89 | O | 0.363 | 0.2476 | 0 | 0.015 | 0.056 | 0.05 | 73.19 | -
Futuristic Trading and Construction | 33597 |  | B | MA |  | Construction of Three (3) Storey Operating Room Complex, Phase 3 | Ospital ng Palawan, Puerto Princesa City | 2014-11-19 | 1st | DOH | L | 31.987 | 240 | 2013-01-04 |  | -13.33 | O | 0.35816 | 0.3 | 0.0167 | 0.03 | 0.0656 | 0.05 | 82.046 | -
FVPS CONSTRUCTION CORPORATION | 35075 | L | D | SB | GB | Construction of One (1) Storey, One (1) Classroom School Building, Guisijan Elementary School | Laua-an, Antique | 2015-06-04 | Final | Antique DEO | LF | 0.947 | 60 | 2015-01-12 | 2015-03-12 | 0% | C | 0.476 | 0.174 | 0.3 | - | - | - | 95% | *95% Very Satisfactory
G M PAJARILLAGA CONSTRUCTION & SUPPLY | 21760 | L | D | SB | GE | Construction of Brgy. Roads, Cabuaan Road, Bayombong, Nueva Vizcaya | Bayombong, Nueva Vizcaya | 2015-09-02 | 1st & Final | NV 1st DEO | LF | 0.71 | 180 | 2015-02-18 | 2015-08-16 | 0.01% | C | 0.427 | 0.133 | 0.3 | - | - | - | 86% | *86% Satisfactory
G. A. Flores Construction Inc. | 611 | L | A | MA |  | Roxas Airport Development Project | Roxas City, Capiz | 2016-10-20 | 2nd | DOTC | LF | 44.6786 | 300 | 2015-07-13 | 2017-01-10 | 4.4 | O | 0.392 | 0.3 | 0.15 | 0.03 | 0.054 | 0.05 | 97.6 | -
G. A. Flores Construction Inc. | 611 | L | A | MA |  | Laoag Airport Development Project | Laoag City, Ilocos Norte/ Region I | 2016-11-16 | 1st | DOTC | LF | 7.8922 | 120 | 2016-07-29 | 2016-11-25 | -2.67 | O | 0.3686 | 0.3 | 0.1233 | 0.03 | 0.0438 | 0.05 | 91.57 | -
G. A. Flores Construction Incorporated | 611 |  | A | MA |  | Roxas Airport Development Project | Brgy. Baybay, Roxas City, Capiz/ Region VI | 2016-03-09 | 1st | DOTC | LF | 44.68 | 270 | 2015-07-13 | 2016-07-28 | 1.22 | O | 0.3283 | 0.3 | 0.15 | 0.03 | 0.0467 | 0.05 | 90.5 | -
G. A. Flores Construction Incorporated | 611 |  | A | MA |  | Laoag International Airport Development Project | Laoag City, Ilocos Norte/ Region I | 2016-03-16 | 1st & Final | DOTC | LF | 5.869 | 120 | 2015-09-30 | 2016-02-18 | 0 | C | 0.4487 | 0.2 | 0.3 | - | - | - | 94.87 | *94.87% V. Satisfactory
G. C. Ballesteros Construction |  | L |  |  |  | Balbalungao Small Reservoir Irrigation Project | San Isidro, Lupao, Nueva Ecija | 2015-05-23 | 1st | NIA | L | 1.024 | 153 | 2014-12-29 | 2015-05-15 | -11.98 | O | 0.3838 | 0.3 | 0.0302 | 0.0225 | 0.0513 | 0.05 | 83.78 | -
G. F. Rovero Merchandising | 27268 | L | B | MA | GE | Construction of Revetment Wall, Poblacion | Makato, Aklan | 2014-10-10 | 1st | VI | LF | 4.7249 | 160 | 2014-07-11 | 2014-12-17 | 45.51% | O | 0.352 | 0.202 | 0.15 | 0.03 | 0.055 | 0.05 | 83.9% | 83.90% Satisfactory
G. F. ROVERO MERCHANDISING | 27268 | L | B | MA | GE | Construction of Farm to Market Road, Barangay Estancia, Kalibo, Aklan | Barangay Estancia, Kalibo, Aklan | 2015-11-11 | Final | Aklan | LF | 1.9336 | 37 | 2015-11-11 | 2015-12-18 | (+) 2.93% | C | 0.386 | 0.2 | 0.3 | - | - | - | 88.6% | 88.6% Satisfactory
G. G. Uy Construction & COCOTECH - JV | [5 empty] | Design and Build for Pasig River Greening Project - Package 1 | Guadalupe, Makati City and Baseco, City of Manila | 2015-10-26 | 1st & Final | PRRC | LF | 24.541 | 546 | 2013-09-03 | 2015-02-28 | 0 | C | 0.408 | 0.122 | 0.3 | - | - | - | 83 | *83.00% Satisfactory
G. UY CONSTRUCTION | 27999 | L | D | SB | GB | Construction of Multi-Purpose Building, Talanghauan Elemetary School, Barangay Talanghauan, Sta. Barbara, Iloilo | Barangay Talanghauan, Sta. Barbara, Iloilo | 2015-11-16 | Final | Iloilo 4th | LF | 2.3498 | 100 | 2015-02-26 | 2015-06-06 | 0.00% | C | 0.437 | 0.144 | 0.3 | - | - | - | 88.1% | 88.1% Satisfactory
G. UY CONSTRUCTION | 27999 | L | B | SB | GE | Construction/Improvement of Access Road Leading to Airport, Seaports and Declared Tourism Destinations, Access Road Leading to Sta. Barbara Airport, Improvement/Widening of Mandurriao-San Miguel-Alimodian-Maasin-Cabatuan Road, Poblacion, San Miguel, Iloil | Poblacion, San Miguel, Iloilo | 2015-11-16 | Final | Iloilo 4th | LF | 4.6517 | 80 | 2015-08-05 | 2015-10-24 | 0.00% | C | 0.425 | 0.191 | 0.3 | - | - | - | 91.6% | 91.6% Very Satisfactory
G. UY CONSTRUCTON | 27999 | L | D | SB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads Including Drainage Based on Pavement Management System/Highway Development Management-4 (HDM-4) (Intermittent Section), Passi-Calinog Road | K00052+700 to K00053+055, Passi City, Iloilo | 2015-06-10 | Final | Iloilo Second DEO | LF | 4.911 | 65 | 2015-03-09 | 2015-05-12 | 0% | C | 0.425 | 0.154 | 0.3 | - | - | - | 87.9% | *87.9% Satisfactory
G. UYMATIAO JR. CONSTRUCTION / BIGFOOT CONSTRUCTION AND SUPPLY JOINT VENTURE | JV-14-733 | L | AA | MB | GE | Network Development - Widening of National Roads - Secondary Roads: Dumaguete City - Valencia - Bacong Road - K008+(-505) - K0008+467.8 / K008+(-668) - K0008+304.80 | Valencia, Negros Oriental | 2015-08-25 | 1st | Negros Oriental 3rd | LF | 22.617 | 192 | 2015-03-10 | 2015-09-17 | 3.5% | O | 0.36 | 0.282 | 0.15 | 0.03 | 0.055 | 0.05 | 92.7% | -
G.A. Flores Construction, Inc | 611 | L | A | MA |  | Marinduque Airport Development Project | Gasan , Marinduque | 2014-04-02 | 1st | DOTC | LF | 19.929 | 180 | 2013-11-04 | 2014-05-02 | 1.73 | O | 0.359 | 0.3 | 0.15 | 0.03 | 0.063 | 0.05 | 95.2 | -
G.C.I Construction | 11346 | L | AAA | MB | GE1 | Const. of San Vicente-Gutan-Lubak-Anguib Road,Phase V |  | 2009-02-25 | 1st | II |  | 20.259 | 330 |  |  |  | O | 0.267 | 0.3 | 0.15 | 0.03 | 0.035 | 0.05 | #VALUE! | -
G.C.I Construction | 11346 |  |  |  |  | Road Upgrading (Gravel to Concrete) Gigmoto-Viga Rd., Phase II |  | 2010-08-17 |  | V |  | 74.1 | 285 |  |  |  | O | 0.334 | 0.3 | 0.15 | 0.022 | 0.042 | 0.05 | 89.8 | -
G.C.I Construction | 11346 |  |  |  |  | Road Upgrading (Gravel to Concrete) Gigmoto-Viga Road, Phase II |  | 2010-02-25 |  | V |  | 74.1 | 270 |  |  |  | O | 0.349 | 0.245 | 0.15 | 0.03 | 0.05 | 0.05 | 87.4 | -
G.C.I Construction | 11346 |  |  |  |  | Upgrading (Gravel to Concrete) along Jct. CCR Panganiban-Sabloyon Rd., Panganiban Sect. K0057+786 - K0060+755 w/ exception |  | 2010-08-17 |  | V |  | 48.17 | 269 |  |  |  | O | 0.337 | 0.3 | 0.15 | 0.022 | 0.035 | 0.05 | 89.4 | -
G.C.I Construction | 11346 | L | AAA | MA | GE2 | Libmanan-Cabusao Embankment (Poblacion Revetment) |  | 2008-08-26 | 1st | V |  | 10.523 | 270 |  |  |  | O | 0.282 | 0.2 | 0.1 | 0.03 | 0.028 | 0.2 | 84 | -
G.C.I Construction | 11346 | L | AAA | MB | GE1 | Road Upgrading of Libon-Bacolod-San Vicente-Marocmoc-Buga Road |  | 2009-05-28 | 1st | V |  | 19.23 | 134 |  |  |  | O | 0.326 | 0.24 | 0.15 | 0.03 | 0.04 | 0.05 | 83.6 | -
G.C.I Construction | 11346 | L | AAA | MB | GE1 | Rehab./Reconst. of Damaged National Road and Generated from Pavement Mgt. System (Highway Dev't & Mgt. HDM-4) Jct. Bato-Baras Road |  | 2009-03-04 | 1st | V |  | 19.18 | 301 |  |  |  | O | 0.361 | 0.3 | 0.15 | 0.03 | 0.061 | 0.05 | #VALUE! | -
G.C.I Construction | 11346 | L | AAA | MB | GE1 | Road Opening/Const. of Missing Links of Malinao-Buhi Road, (Buhi Side) |  | 2009-09-08 | 1st | V |  | 19.107 | 179 |  |  |  | O | 0.311 | 0.3 | 0.15 | 0.03 | 0.047 | 0.033 | 87.1 | -
G.C.I Construction | 11346 |  |  |  |  | Quinali-Talisay River Flood Control Embankment & Channelization |  | 2010-02-26 |  | V |  | 38.4 | 417 |  |  |  | O | 0.36 | 0.3 | 0.105 | 0.03 | 0.05 | 0.033 | 87.8 | -
G.C.I Construction | 11346 |  |  |  |  | Road Upgrading (Gravel to Concrete) Viga Panganiban-Bagamanoc Road |  | 2010-02-25 |  | V |  | 19.192 | 180 |  |  |  | O | 0.366 | 0.247 | 0.133 | 0.03 | 0.045 | 0.05 | 87.1 | -
G.E.A Construction Corp. | 10163 |  |  |  |  | Road Upgrading at Abre de Ilog-San Jose Road (San Pedro-Mangat Section) Brgy. San Pedro |  | 2010-08-27 |  | IVB |  | 6.808 | 90 |  |  |  | O | 0.293 | 0.24 | 0 | 0.03 | 0.014 | 0.017 | 59.4 | -
G.F Rovero Merchandising | 27268 | L | B | MA | GE1 | Impvt. of Access Road to Kalibo Airport |  | 2009-09-05 | 1st | VI |  | 8.032 | 244 |  |  |  | O | 0.378 | 0.3 | 0.15 | 0.03 | 0.025 | 0.033 | 91.6 | -
G.F. FALCIS CONSTRUCTION AND SUPPLY | 26147 | L | C | SB | GB | Construction of Multi-Purpose Building (GYM) | Brgy. Buntatala, Jaro, Iloilo City | 2015-06-02 | Final | Iloilo City DEO | LF | 2.364 | 60 | 2015-02-23 | 2015-04-23 | 0% | C | 0.413 | 0.2 | 0.3 | - | - | - | 91.3% | *91.3% Very Satisfactory
G.F. FALCIS CONSTRUCTION AND SUPPLY | 26147 | L | C | SB | GB | Completion of Multi-Purpose Building, Tiic | Molo, Iloilo City Lone District | 2015-08-24 | 1st & Final | Iloilo City | LF | 3.761 | 120 | 2015-04-15 | 2015-08-12 | 10.83% | C | 0.47 | 0.133 | 0.3 | - | - | - | 90.3% | *90.3% Very Satisfactory
G.F. ROVERO MERCHANDISING | 27268 | L | B | MA | GE | Widening of National Road, Arterial Roads Outside N1 Aklan East Road | K0286+004.54- K0286+823.04 with Drainage including RROW, Banga, Aklan | 2015-06-05 | 1st | Aklan DEO | LF | 22.131 | 179 | 2015-04-30 | 2015-10-25 | 20.65% | O | 0.338 | 0.289 | 0.15 | 0.015 | 0.04 | 0.05 | 88.2% | -
G.O. Marron General Contractor | 6844 |  |  | SB |  | Bacnotan Shallow Tube Wells | Bacnotan, La Union, Region 1 | 2015-01-28 | 1st | NIA | L | 10.716 | 180 | 2014-10-10 | 2015-04-26 | 14.66 | O | 0.25 | 0.3 | 0.15 | 0.03 | 0.06 | 0.05 | 84 | -
G.O. Marron General Contractor | 6844 | L | D | SB | GB1 | Const. of MPB | Alcala, Pangasinan | 2013-07-29 | 1st | I | LF | 1.94 | 100 | 2013-06-25 | 2013-10-02 | 48.18 | O | 0.333 | 0.24 | 0.15 | 0.03 | 0.037 | 0.05 | 84 | -
G.R. Bernales Construction & Supply | 35849 | L | D |  | GE2 | Construction of Canal Structures of Rizal CIS | Atimonan, Quezon/Region IV-A | 2013-09-07 | 1st | NIA | L | 1.655 | 90 | 2013-06-11 | 2013-09-17 | 0 | O | 0.3217 | 0.2966 | 0.15 | 0.012 | 0.028 | 0.05 | 85.83 | -
G.V Burton Builders | 26804 |  |  |  |  | Conc. of Aritao-Quirino Rd., Bitnong Sect. |  | 2010-06-07 |  | II |  | 9.646 | 180 |  |  |  | O | 0.345 | 0.3 | 0.15 | 0.024 | 0.042 | 0.033 | 89.4 | -
G.V. Burton Builders & Construction | 26804 | L |  | SB | GE2 | Colocol Integrated CIS Rehabilitation & Extension Project | Bayombong, Nueva Vizcaya | 10/24-29/11 | 1st | NIA | LF | 3.286 | 120 | 2011-06-06 | 2011-10-03 | - | O | 0.3642 | 0.2845 | 0.15 | 0.03 | 0.0327 | 0.05 | 91.14 | -
G.V. Burton Builders & Construction | 26804 | L |  | SB | GE2 | Colocol Integrated CIS Rehabilitation & Extension Project | Bayombong, Nueva Vizcaya | 11/07-12/11 | 1st | NIA | LF | 11.24 | 180 | 2011-06-06 | 2011-12-02 | -0.95 | O | 0.3782 | 0.24 | 0.1405 | 0.024 | 0.07 | 0.05 | 90.27 | -
G.V. Burton Construction | 26804 | L |  | SB | GE2 | Colocol Integrated CIS Rehabilitation & Extension Project | Bayombong, Nueva Vizcaya | 11/07-12/11 | 1st | NIA | LF | 6.464 | 150 | 2011-06-06 | 2011-11-02 | -6.82 | O | 0.3792 | 0.2649 | 0.0818 | 0.024 | 0.07 | 0.05 | 86.99 | -
GACUTAN CONSTRUCTION | 10789 | L | A | MA | GE | Local Infrastructure Program - Concreting of Dalakip - Cumu Barangay Road, Brgy. Dalakip, Agadanan, Isabela | Agadanan, Isabela | 2015-08-29 | 1st & Final | Isabela 3rd DEO | LF | 4.7 | 65 | 2015-02-18 | 2015-04-23 | 0% | C | 0.411 | 0.2 | 0.3 | - | - | - | 91.1% | *91.1% Very Satisfactory
GACUTAN CONSTRUCTION | 10789 | L | A | MA | GE | Local Infrastructure Progra - Concreting of Barangay Road, Barangay Amistad, Alicial, Isabela 3rd LD | Barangay Amistad, Alicial, Isabela 3rd LD | 2015-11-16 | Final | ISABELA 3RD DEO | LF | 4.7013 | 65 | 2015-03-05 | 2015-06-07 | (+) 2.70 | C | 0.441 | 0.16 | 0.3 | - | - | - | 90.1% | 90.1% Very Satisfactory
Gacutan Construction | 10789 | L |  |  | GE2 | MARIIS Division 3 - Improvement Projects | San Manuel, Isabela, Region 2 | 2012-07-27 | 1st | NIA | LF | 9.251 | 120 | 2012-04-18 | 2012-08-15 | -4.68 | O | 0.4 | 0.3 | 0.103 | 0.03 | 0.016 | 0.05 | 89.9 | -
Galeno Construction, Inc. | 3427 | L | A | MA | GB | Construction of Standard One Storey School Building @ Magsaysay ES | Ilog, Negros Occidental | 2014-10-25 | 1st | VI | LF | 1.0097 | 88 | 2014-08-13 | 2014-11-08 |  | O | 0.368 | 0.242 | 0.15 | 0.015 | 0.042 | 0.033 | 85% | 85.00% Satisfactory
Galeno Construction, Inc. | 3427 | L | A | MA | GE1 | Replacement of Alimango Bridge II along Bacolod South Rd. | Binalbagan, Negros Occidental | 2013-08-10 | 1st | VI | LF | 13.327 | 209 | 2013-02-01 | 2013-08-28 | 0.54 | O | 0.346 | 0.24 | 0.15 | 0.03 | 0.051 | 0.05 | 86.7 | -
Galeno Construction, Inc. | 3427 | L | A | MA | GE1 | Rehab./Reconst. of Guimbal-Tubungan Rd., Km.34+790-Km.35+290 | Guimbal, Iloilo | 2013-03-17 | 1st | VI | LF | 7.167 | 77 | 2013-01-31 | 2013-04-17 | 0.12 | O | 0.364 | 0.252 | 0.15 | 0.03 | 0.05 | 0.05 | 89.6 | -
GALENO CONSTRUCTION, INC. | 3427 | L | A | MA | GE | Construction/Replacement of Permanent Weak Bridges Along National Road, Binalayan Bridge (B00208NR) along Kabankalan Jct. Salong Tapi Dacongcogon Bantayan Road, K0108+972, Brgy. Tapi, Kabankalan City, Negros Occidental | K0108+972, Brgy. Tapi, Kabankalan City, Negros Occidental | 2015-11-14 | 1st | Negros Occidental 3rd DEO | LF | 10.094 | 306 | 2015-02-23 | 2015-12-25 | (+)4.90% | OG | 0.349 | 0.202 | 0.15 | 0.03 | 0.05 | 0.05 | 83.1% | 83.1% Satisfactory
GALENO CONSTRUCTION, INC. | 3427 | L | A | MA | GE | Construction/Replacement of Permanent Weak Bridges along National Road, Candiacap Bridge (B00207NR), along Kabankalan Jct. Salong Tapi Dacongcogon Bantayan Road, K0107+679, Brgy. Tapi, Kabankalan City, Negros Occidental | Brgy. Tapi, Kabankalan City, Negros Occidental | 2015-11-14 | 1st | Negros Occidental 3rd DEO | LF | 10.094 | 306 | 2015-02-23 | 2015-12-25 | (+)8.85 | OG | 0.356 | 0.212 | 0.15 | 0.03 | 0.05 | 0.05 | 84.8% | 84.8% Satisfactory
GATEWAY 21-25 CONSTRUCTION CORP. (Formerly: E.D. Denosta Construction and Supply) | 28355 | L | D | SB | GE | Construction of Farm to Market Road | Barangay Bariri, San Jose, Antique | 2015-06-04 | Final | Antique DEO | LF | 1.987 | 37 | 2015-03-04 | 2015-04-09 | 0% | C | 0.462 | 0.149 | 0.3 | - | - | - | 91.1% | *91.1% Very Satisfactory
Gaver General Merchandising | 24186 | L | C | SB | GE1 | Conc. of FMR, Estancia | Kalibo, Aklan | 2013-08-17 | 1st | VI | LF | 4.859 | 135 | 2013-04-06 | 2013-08-18 | 1.62 | O | 0.346 | 0.2 | 0.15 | 0.03 | 0.035 | 0.033 | 79.4 | -
GC Ballesteros Construction | 8598 | L |  |  | GE2 | Construction of New Canal with Lining @Buklod IA | Allaga, San Antonio, Nueva Ecija / Region III | 2013-07-27 | 1st | NIA | L | 4.746 | 75 | 2013-01-25 | 2013-07-31 | 0 | O | 0.3497 | 0.24 | 0.15 | 0.025 | 0.056 | 0.05 | 87.07 | -
GCI CONSTRUCTION | 11346 | L | AAA | LA | GE | National Road Network Services - Network Development: Widening of National Roads Arterial Roads and National Road 1 (N1)/Daang Maharlika/Asian Highway-26, K0440+000 to K0444+061, K0435+720 to K0439+980 (w/ exception), Cabagan, Isabela | Cabagan, Isabela | 2015-08-27 | 1st | Regional Office No. II | LF | 157.695 | 300 | 2015-05-06 | 2016-02-29 | 28.32% | O | 0.396 | 0.241 | 0.15 | 0.03 | 0.051 | 0.05 | 91.8% | -
GCI CONSTRUCTION AND DEVELOPMENT CORP. (Formerly: G.C.I Construction) | 11346 | L | AAA | MB | GE | Road Upgrading (Gravel To Concrete) Of NRJ Tagcatong-Vinapor Road, Carmen Leading To Nasipit Seaport, Jurassic Beach Resort, Bolihon Beach, Diwata Cave, The Rockin Bolihon, Top Of The Carmen | K1+600 - K7+580 With Exception, Agusan Del Norte | 2015-09-02 | 1st & Final | Regional Office No. XIII | LF | 133.362 | 357 | 2014-04-01 | 2015-03-23 | (+) 1.03% | C | 0.444 | 0.194 | 0.3 | - | - | - | 93.8% | *93.8% Very Satisfactory
GCI Construction and Development Corp. (Formerly: G.C.I. Construction) | 11346 | L | AAA | MB | GE2 | Rehab. of Sta. Margarita River Control along Taguntungan River Jct. Gattaran-Cumao-Capissayan-Sta. Margarita Bolos Point Rd. (JGCCS-MBPR) | Baggao, Cagayan | 2013-07-30 | 1st | II | LF | 13.567 | 169 | 2013-04-03 | 2013-09-18 | 11.69 | O | 0.397 | 0.24 | 0.15 | 0.03 | 0.043 | 0.033 | 89.3 | -
GCI Construction and Development Corp. (Formerly: G.C.I. Construction) | 11346 | L | AAA | MB | GE2 | Cagayan River Control Project, Brgy. Pata | Enrile, Cagayan | 2012-08-05 | 1st | II | LF | 75.084 | 306 | 2012-01-30 | 2012-12-12 | 0.15 | O | 0.348 | 0.3 | 0.15 | 0.03 | 0.045 | 0.05 | 92.3 | -
GCI Construction and Development Corp. (Formerly: G.C.I. Construction) | 11346 | L | AAA | MB | GE1 | Const. of Tuguegarao City By-Pass Rd., K0477+420-EQ=K0479+182.3 (BK) / K0484+248.833 (AH) | Cagayan | 2012-08-05 | 1st | II | LF | 74.479 | 285 | 2012-02-27 | 2012-12-07 | -7 | O | 0.37 | 0.3 | 0.08 | 0.03 | 0.055 | 0.033 | 86.8 | -
GCI CONSTRUCTION AND DEVELOPMENT CORP. (Formerly: G.C.I. Construction) | 11346 | L | AAA | MB | GE | MFO-1 National Road Network Services: Network Development-Widening of National Roads along National Road 1 (N1)/Daang Maharlika/Asian Highway-26 Daang Maharlika (LZ), K0440+000 - K0444+061, K0435+720 - K0439+980 (with exception) Cabagan, Isabela | Caabagan, Isabela | 2015-11-12 | 1st | REGIONAL | LF | 157.6953 | 300 | 2015-05-06 | 2016-02-29 | (+) 22.15 | OG | 0.38 | 0.23 | 0.15 | 0.03 | 0.042 | 0.05 | 88.2% | 88.2% Satisfactory
GCI Construction and Development Corp. (Formerly: GCI Construction) | 11346 | L | AAA | MB | GE | Construction/Rehabilitation/Improvement of Hibago Flood Control | Ocampo, Camarines Sur | 2014-08-08 | 1st | V | LF | 44.0755 | 179 | 2014-03-02 | 2014-08-27 | -6.46 | O | 0.307 | 0.3 | 0.085 | 0.02 | 0.061 | 0.033 | 80.6 | -
GCI. Construction and Development Corp. | 11346 | L | AAA | MB | GE1 | Road Upgrading (Gravel to Conc.) along CCR, San Andres Sect. K0169+277-K0173+300 | San Andres, Catanduanes | 2011-08-16 | 1st | V | LF | 48.17 | 264 | 2010-12-08 | 2011-08-28 | -0.5 | O | 0.342 | 0.3 | 0.145 | 0.012 | 0.033 | 0.017 | 84.9 | -
GCI. Construction and Development Corp. (Formerly: G.C.I. Construction) | 11346 | L | AAA | MB | GE1 | Rehab./Impvt. of Pili-Tigaon-Albay-Bdry. Rd., Pili-Ocampo Sect. | Camarines Sur | 2013-08-04 | 1st | V | LF | 73.338 | 293 | 2013-04-01 | 2014-01-18 | 5.95 | O | 0.35 | 0.24 | 0.15 | 0.03 | 0.055 | 0.033 | 85.8 | -
GCI. Construction and Development Corp. (Formerly: G.C.I. Construction) | 11346 | L | AAA | MB | GE1 | Conc. of Naga-Milaor Circ. & Road Right of Way Activities | Milaor, Camarines Sur | 2012-08-14 | 1st | V | LF | 47.043 | 180 | 2012-05-18 | 2012-11-13 | 2 | O | 0.374 | 0.24 | 0.15 | 0.03 | 0.065 | 0.033 | 89.2 | -
GEA Construction Corporation | 10163 | L | A | MA | GE1 | Laguindingan Airport Development Project |  | 2009-06-25 | 1st | DOTC |  | 22.36 | 180 |  |  |  | O | 0.4 | 0.3 | 0.15 | 0.02 | 0.039 | 0.05 | 95.9 | -
Geety Realty & Development Corporation | 30447 | L | B | MA | GE2 | Rd. Upgrading (Gravel to Paved) (Int. Sect.) Diversion Rd., Carcar Rotunda Heritage Area | Carcar City | 2013-08-05 | 1st | VII | LF | 17.643 | 209 | 2013-01-18 | 2013-08-14 | 11.25 | O | 0.349 | 0.236 | 0.15 | 0.03 | 0.045 | 0.05 | 86 | -
Geety Realty & Development Corporation | 30447 | L | B | MA | GE2 | Const. of Flood Control at Aloguinsan Bridge | Aloguinsan, Cebu | 2013-08-07 | 1st | VII | LF | 22.41 | 194 | 2013-02-18 | 2013-08-30 | 0.7 | O | 0.295 | 0.3 | 0.15 | 0.03 | 0.05 | 0.033 | 85.8 | -
GEETY REALTY & DEVELOPMENT CORPORATION | 30447 | L | B | MA | GE | Widening of Drainage along Cebu-Toledo Wharf Road (Junction Naga - Uling) K0029+(-234) - K0029+760, Brgy. Alimango | Toledo City, Cebu | 2015-08-29 | 1st | Cebu 3rd | LF | 11.469 | 128 | 2015-03-03 | 2015-07-08 | ##### | O | 0.314 | 0.217 | 0.09 | 0.03 | 0.03 | 0 | 68.1% | -
GEETY REALTY & DEVELOPMENT CORPORATION | 30447 | L | B | MA | GE | Widening with Drainage along Cebu-Toledo Wharf Road (Junction Naga-Uling), K0029+(-234) - K0029+760, Brgy. Alimango, Toledo City, Cebu | Brgy. Alimango, Toledo City, Cebu | 2015-11-12 | 1st | Cebu 3rd | LF | 11.4689 | 98 | 2015-03-03 | 2015-07-08 | -0.055 | OG | 0.399 | 0.24 | 0.095 | 0.024 | 0.05 | 0.033 | 84.1% | 84.1% Satisfactory
GEETY REALTY & DEVELOPMENT CORPORATION | 30447 | L | B | MA | GE | Rehabilitation of Slope Protection including Drainage along Santander - Barili - Toledo Road, K0154+656, Poblacion, Ginatilan, Cebu | Poblacion, Ginatilan, Cebu | 2015-11-11 | Final | Cebu 4th | LF | 9.6495 | 141 | 2015-08-18 | 2016-01-05 | 0.4397 | C | 0.473 | 0.133 | 0.3 | - | - | - | 90.6% | 90.6% Very Satisfactory
GELA CONSTRUCTION | 30655 | L | D | SB | GB | Construction/ Repair/ Rehabilitation of Multi-Purpose Building,Cantabaco, Toledo City, Cebu | Cantabaco, Toledo City, Cebu | 2015-11-12 | 1st | Cebu 3rd | LF | 1.4647 | 45 | 2015-10-26 | 2015-12-09 | 0.1488 | OG | 0.392 | 0.24 | 0.15 | 0.024 | 0.05 | 0.05 | 90.6% | 90.6% Very Satisfactory
Gemma Construction Supply Inc. (Formerly: Gemma Construction & Supply) | 5044 | L | AA | MB | GE1 | Rd. Upgrading (Gravel to Paved) along Demoloc-Little Baguio-Alabel Rd,. Km.1649+800-Km.1650+920, Tayudan Sect. | Malita, Davao del Sur | 2013-03-14 | 1st | XI | LF | 44.04 | 179 | 2013-03-07 | 2013-09-01 | 17.57 | O | 0.36 | 0 | 0.15 | 0.03 | 0.032 | 0.05 | 62.2 | -
Gemma Construction Supply Inc. (Formerly: Gemma Construction & Supply) | 5044 | L | AA | MA | GE | Construction of Revetment (River Bank Protection) along Cotobato City Circumferencial Road (Down Stream & Upstream at Bubong Bridge Approach) | Cotabato City | 2014-08-12 | 1st | XII | LF | 44.6379 | 217 | 2/21/134 | 2014-09-26 | 0.78 | O | 0.398 | 0.24 | 0.15 | 0.022 | 0.04 | 0.05 | 90 | -
Gemma Construction Supply Inc. (Formerly: Gemma Construction Supply) | 5044 | L | AA | MB | GE1 | Rd. Upgrading (Gravel to Paved) along Demoloc-Little Baguio-Alabel Rd., Km.1649+800-Km.1650+920, Tayudan Sect. | Malita, Davao del Sur | 2013-08-07 | 2nd | XI | LF | 44.04 | 179 | 2013-03-07 | 2013-09-01 | 9.22 | O | 0.333 | 0.3 | 0.15 | 0.03 | 0.03 | 0.033 | 87.6 | -
Gemma Construction Supply Inc. / Three W Builders, Inc. Joint Venture | JV-11-471 | L | AA | MB | GE1 | Rehab./Upgrading of Makilala-Allah Valley Junction Rd., Km 1634+324-Km 1635+225-Km 1634+444 ( with exceptions) | M'lang, Cotabato | 2012-11-20 | 1st | XII | LF | 73.256 | 290 | 2012-04-23 | 2013-02-06 | -12.78 | O | 0.372 | 0.3 | 0.022 | 0.03 | 0.06 | 0.05 | 83.4 | -
Gemma Construction Supply, Inc. | 5044 |  |  |  |  | Const. of Isulan Highway Junction Dukay-Bagumbayan Sen. Ninoy Aquino Road (D' Lotilla Section) |  | 2010-03-03 |  | XII |  | 14.139 | 175 |  |  |  | O | 0.373 | 0.24 | 0.15 | 0.03 | 0.05 | 0.033 | 87.6 | -
Gemma Construction Supply, Inc. (Formerly: Gemma Construction Supply) | 5044 | L | AA | MB | GE1 | Const. of Turn-Outs (Loading/Unloading Bay) along Kidapawan-Ala Jct. Rd., Bo. 2, Km.1677+525-Km.1677+925 | Tacurong City | 2013-03-11 | 1st | XII | LF | 5.822 | 95 | 2012-12-17 | 2013-03-21 | 1.49 | O | 0.341 | 0.29 | 0.15 | 0.03 | 0.045 | 0.033 | 88.9 | -
Gemma Construction Supply, Inc. (Formerly: Gemma Construction Supply) | 5044 | L | AA | MB | GE1 | Const. of Sebayor Bridge, Sta. Clara | Kalamansig, Sultan Kudarat | 2013-03-14 | 1st | XII | LF | 37.044 | 235 | 2012-11-27 | 2013-07-19 | 9.27 | O | 0.392 | 0.24 | 0.15 | 0.03 | 0.051 | 0.05 | 91.3 | -
Gemma Construction Supply, Inc. (Formerly: Gemma Construction Supply) | 5044 | L | AA | MB | GE1 | Rd. to Address Critical Bottlenecks Nat'l. Rd. Traffic Decongestion, Widening of Marbel-Cotabato Rd., K1724+200.6-K1727+100.6 | South Cotabato | 2013-03-20 | 1st | XII | LF | 42.8 | 137 | 2013-01-30 | 2013-06-15 | 1.88 | O | 0.349 | 0.284 | 0.15 | 0.03 | 0.055 | 0.033 | 90.1 | -
Gemma Construction Supply, Inc. (Formerly: Gemma Construction Supply) | 5044 | L | AA | MB | GE1 | Repair/Rehab./Impv't. along Kidapawan-Ala Jct. Rd. (EJC Montilla Sect.), Km.1677+525-Km.1677+785 (Right Side) and Km.1677+665-Km.1677+925 (Left Side) | Tacurong City | 2013-03-11 | 1st | XII | LF | 4.912 | 32 | 2013-02-25 | 2013-03-28 | 25.62 | O | 0.323 | 0.3 | 0.15 | 0.03 | 0.05 | 0.033 | 88.6 | -
Gemma Construction Supply, Inc. (Formerly: Gemma Construction Supply) | 5044 | L | AA | MB | GE1 | Prev. Maint. (Intermittent Sect.); Nat'l Arterial Rd.; Marbel-Makar Rd., K1699+000-K17000+019, K1700+019-K1701+007, K1703+1013-K1704+994 | South Cotabato | 2013-03-20 | 1st | XII | LF | 41.435 | 166 | 2013-01-30 | 2013-07-14 | 40 | O | 0.355 | 0.24 | 0.15 | 0.03 | 0.055 | 0.033 | 86.3 | -
Gemma Construction Supply, Inc. (Formerly: Gemma Construction Supply) | 5044 | L | AA | MB | GE1 | Prev. Maint. Marbel-Allah Valley-Cotabato Rd. (Km.1775+(-736)-Km.1775+1002 & Km.1777+000-Km.1780+047) | Esperanza, Sultan Kudarat | 2013-03-12 | 1st | XII | LF | 43.504 | 225 | 2013-02-07 | 2013-09-19 | 1.77 | O | 0.333 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 85.8 | -
Gemma Construction Supply, Inc. (Formerly: Gemma Construction Supply) | 5044 | L | AA | MB | GE1 | Prev. Maint. (Intermittent Sect.); Nat'l Secondary Rd.; Midsayap-Marbel Rd., K1785+997-K1786+992, K1786+992-K1789+028 | South Cotabato | 2013-03-20 | 1st | XII | LF | 27.897 | 100 | 2013-01-30 | 2013-05-09 | 9.26 | O | 0.34 | 0.24 | 0.15 | 0.03 | 0.055 | 0.033 | 84.8 | -
Gemma Construction Supply, Inc. / Three W Builder, Inc. (JV) | JV-12-164 | L | AAA | LB | GE1 | Rd. Upgrading (Gravel to Conc.) along Awang-Upi-Lebak-Kalamasig-Palimbang Rd. (Tambis-Sangay Sect.) K01963+400-K01965+860 w/ exceptions, K01963+520-K01963+660 | Kalamansig, Sultan Kudarat | 2013-03-14 | 1st | XII | LF | 121.17 | 390 | 2012-11-27 | 2013-12-21 | 8.6 | O | 0.399 | 0.299 | 0.15 | 0.03 | 0.037 | 0.033 | 94.8 | -
Gemma ConstructionSupply | 5044 | L | AA | LA | GB1 | Completion of MPB at Brgy. Kalanawi-I |  | 2009-06-02 | 1st | R-XII |  | 0.481 | 221 |  |  |  | O | 0.3 | 0.269 | 0.15 | 0.03 | 0.041 | 0.05 | 84 | -
GEMSTRONG CONSTRUCTION INC. | 38301 | L | D | SB | GB | Construction of ALS Center, Consolacion Central Elementary School, Consolacion, Cebu | Consolacion, Cebu | 2015-11-14 | Final | Cebu 6th | LF | 2.1478 | 110 | 2015-03-30 | 2015-07-17 | 0.0091 | C | 0.394 | 0.133 | 0.3 | - | - | - | 82.7% | 82.7% Satisfactory
Genetian Builders | 18052 | L | B | MA | GE | Construction/Rehabilitation of River/Flood Control Structure at Sabang River, Siquijor Circumferential Road, K0006+908 (Upstream/Extension) | Siquijor | 2014-10-28 | 1st | VII | LF | 14.161 | 151 | 2014-06-02 | 2014-10-30 | -13.01% | O | 0.349 | 0.248 | 0.02 | 0.022 | 0.042 | 0 | 68.1% | 68.10% Poor
Genetian Builders | 18052 | L | B | MA | GE | Const.Concreting of Road Brgy. Lapasan, Cagayan de Oro City | Cagayan de Oro City | 2014-08-04 | 1st | X | LF | 4.6995 | 97 | 2014-05-30 | 2014-09-03 | 39.61 | O | 0.382 | 0.3 | 0.15 | 0.03 | 0.05 | 0.05 | 96.2 | -
Genetian Builders | 18052 | L | A | MA | GE1 | Rehab./Reconst./Upgrading of Int. Sect., Jct. Aurora-Monte-Jct. Labangan Rd., K1650+923-K1650+993; K1651+000- K1652+290 & K1652+790-K1654+000 | Labangan, Zamboanga del Sur | 2013-08-17 | 2nd | IX | LF | 36.408 | 196 | 2013-02-25 | 2013-09-09 | 0.38 | O | 0.314 | 0.3 | 0.15 | 0.022 | 0.033 | 0.033 | 85.2 | -
Genetian Builders | 18052 | L | A | MA | GE1 | Rehab./Reconst./Upgrading of Int. Sect., Jct. Aurora-Monte-Jct. Labangan Rd., K1650+923-K1650+993; K1651+000-K1652+290 & K1652+790-K1654+000 | Zamboanga del Sur | 2013-03-21 | 1st | IX | LF | 36.408 | 106 | 2013-02-25 | 2013-06-11 | 5.16 | O | 0.38 | 0.24 | 0.15 | 0.03 | 0.038 | 0.033 | 87.1 | -
Genetian Builders | 18052 | L | A | MA | GE2 | Const./Rehab./Impv't. of Lower Sibuguey Flood Protection along Lanao-Pagadian-Zamboanga City Rd., Balucanan-Salinding Sect., Phase II, Km.2+240-Km.4+480 | Zamboanga Sibugay | 2013-03-15 | 2nd | IX | LF | 27.731 | 243 | 2012-07-23 | 2013-03-22 | -3 | O | 0.373 | 0.24 | 0.12 | 0.03 | 0.047 | 0.033 | 84.3 | -
Genetian Builders | 18052 | L | A | MA | GE2 | Const./Rehab./Impvt. of Lower Sibuguey Flood Protection along Lanao-Pagadian-Zamboanga City Rd., Balucanan-Salinding Sect., Phase II, km.2+240-Km.4+480 | Zamboanga Sibugay | 2012-11-26 | 1st | IX | LF | 27.731 | 170 | 2012-07-23 | 2013-01-08 | -12 | O | 0.351 | 0.3 | 0.03 | 0.03 | 0.059 | 0.033 | 80.3 | -
Genetian Builders | 18052 | L | A | MA | GE1 | Const. of Revetment Wall along Aklan River (Phase I) | Kalibo, Aklan | 2012-08-17 | 2nd | VI | LF | 17.014 | 275 | 2011-11-29 | 2012-09-08 | 1.74 | O | 0.358 | 0.24 | 0.15 | 0.03 | 0.035 | 0.05 | 86.3 | -
Genetian Builders | 18052 | L | A | MA | GE2 | Const./Installation of New Drainage System along Iligan City-Cagayan de Oro City-Butuan City (ICBR Rd.), Velez-Burgos Sect. | Cagayan de Oro City | 2012-08-06 | 2nd | X | LF | 15.484 | 265 | 2011-11-29 | 2012-08-19 | 4.72 | O | 0.331 | 0.3 | 0.15 | 0.02 | 0.035 | 0.05 | 88.6 | -
Genetian Builders | 18052 | L | A | MA | GE1 | Rehab./Const./Upgrading of Jimenez Old Route, Km.1724+1046-Km.1724+1287 | Jimenez, Misamis Occidental | 2012-08-21 | 1st | X | LF | 2.715 | 75 | 2012-02-02 | 2012-04-16 | -4.03 | O | 0.154 | 0.3 | 0 | 0.03 | 0.025 | 0.033 | 54.2 | -
GENETIAN BUILDERS | 18052 | L | B | MA | GE | Concreting of Brgy. Road, Brgy. Sugbay Dos - Brgy. Balong - Balong Road, Pitogo, Zamboanga Del Sur | Pitogo, Zamboanga Del Sur | 2015-06-07 | Final | Zamboanga del Sur 2nd DEO | LF | 3.841 | 60 | 2014-05-24 | 2014-07-25 | 0% | C | 0.437 | 0.138 | 0.3 | - | - | - | 87.5% | *87.5% Satisfactory
GENETIAN BUILDERS | 18052 | L | B | MA | GE | Const./Concreting of Road, Barangay Lapasan, Cagayan de Oro City | Barangay Lapasan, Cagayan de Oro City | 2015-06-12 | Final | Cagayan de Oro City Second DEO | LF | 4.7 | 97 | 2014-05-30 | 2014-09-03 | - | C | 0.459 | 0.2 | 0.3 | - | - | - | 95.93% | *96.09% Outstanding
GENETIAN BUILDERS | 18052 | L | B | MA | GB | Construction of Office of the Vice President (OVP) - Office Senior Citizens Affairs (OSCA) (Multi-Purpose Building) Center, Ozamis City, Misamis Occidental | Ozamis City, Misamis Occidental | 2015-11-19 | Final | Misamis Occidental 2nd | LF | 1.7802 | 60 | 2015-08-06 | 2015-10-05 | (+) 5.05% | C | 0.38 | 0.177 | 0.3 | - | - | - | 85.7% | 85.7% Satisfactory
GENETIAN BUILDERS/BAQ PRINCE CONSTRUCTION (JV) | JV-13-446 | L | A | MA | GB | Construction of Four (4) Storey, Twenty (20) Classroom School Building with Site Improvement at Imus NHS | Imus City, Cavite | 2015-06-13 | Final | Cavite 1st DEO | LF | 36.63 | 240 | 2013-12-02 | 2014-07-29 | 0% | C | 0.476 | 0.133 | 0.3 | - | - | - | 90.9% | *90.9% Very Satisfactory
Gerra Construction | 4326 |  |  | MA |  | Package X-G: Construction of Sub-laterals "N-6" (Sta. 4+500-Sta. 7+100) and "N-6E" (Sta. 0+000-Sta. 3+520) including related structures and supply, delivery and installation of steel gates | Guimba, Nueva Ecija | 2015-02-07 | 1st | NIA | L | 22.922 | 180 | 2014-08-01 | 2015-03-31 | 9.16 | O | 0.3244 | 0.2874 | 0.15 | 0.015 | 0.0233 | 0.05 | 85.01 | -
Gerra Construction | 29359 | L | D |  | GE2 | Dabubu River Irrigation Project | San Agustin, Isabela / Region 2 | 2013-04-27 | 1st | NIA | LF | 4.802 | 150 | 2013-02-18 | 2013-07-19 | 28.04 | O | 0.387 | 0.213 | 0.15 | 0.023 | 0.028 | 0.05 | 85.1 | -
GERSHLI CONSTRUCTION & SUPPLY/NBL CONSTRUCTION (JV) | JV-14-329 | L | C | SB | GE | Construction/Upgrading/Rehabilitation of Drainage along National Roads, Talisay - Laurel - Agoncillo Road, K0093+665 to K0094+229.5 | Laurel, Batangas | 2015-06-06 | 1st | Batangas 3rd DEO | LF | 13.644 | 210 | 2015-01-28 | 2015-08-25 | 14.96% | O | 0.294 | 0.276 | 0.15 | 0.03 | 0.04 | 0.033 | 82.3% | -
GES Construction | 30299 | L | D | SB | GE2 | Taripa CIS |  | 10/6-10/08 | 1st | PIO |  | 1.012 | 90 |  |  |  | O | 0.3588 | 0.2384 | 0.1 | 0.015 | 0.0292 | 0.1 | 84.14 | -
GES Construction | 30299 | L |  |  | GE2 | Basey Irrigation Project | Basey, Western Samar | 9/5-10/11 | 1st | NIA | LF | 5.017 | 110 | 2011-05-11 | 2011-09-12 | 1.89 | O | 0.3712 | 0.2592 | 0.15 | 0.0225 | 0.0573 | 0.0333 | 89.35 | -
GES CONSTRUCTION/AQUALINE CONSTRUCTION JOINT VENTURE | 11555 | L | B | MA | GE | Road Upgrading (Unpaved to Paved) Based on Gravel Road Strategies Traffic Benchmark for Upgrading to Paved Road Standards La Paz-Javier-Bito Road Chainage 2258-Chainage 2848, Chainage 2900-Chainage 3095, Chainage 3649-Chainage 3807, Chainage 4105-Chainage 4522, Chainage 4602-Chainage 5625, Chainage 5923-Chainage 6315, La Paz, Leyte | La Paz, Leyte | 2015-11-12 | Final | Leyte Second DEO | LF | 45.0991 | 205 | 2015-02-25 | 2015-09-17 | - | C | 0.389 | 0.135 | 0.3 | - | - | - | 82.4% | 82.4% Satisfactory
GESAVILLLE CONTRUCTION | 25345 | L | D | SB | GE | Rehabilitation/Major Repair of Permanent Brdiges, Pasuquin Bridge along MNR | Pasuquin, Ilocos Norte (KO505+858) | 2015-06-03 | Final | Ilocos Norte 1st DEO | LF | 1.045 | 68 | 2015-03-09 | 2015-05-14 | 0% | C | 0.428 | 0.2 | 0.3 | - | - | - | 92.8% | *92.8% Very Satisfactory
Gicar Construction Inc. (Formerly: Gicar Construction) | 12624 | L | A | MB | GE1 | Rd. Upgrading (Gravel to Paved) along Quezon-Mapawa-Capalayan-Espina-Navarro Rd. (Int. Sect.) Km.1133+652-Km.1134+585 | Surigao del Norte | 2013-08-08 | 1st | XIII | LF | 23.548 | 180 | 2013-02-12 | 2013-09-10 | 1.83 | O | 0.357 | 0.24 | 0.15 | 0.03 | 0.035 | 0.05 | 86.2 | -
Gicar Construction Inc. (Formerly: Gicar Construction) | 12624 | L | A | MB | GE1 | Rd. Upgrading (Gravel to Paved) Gingoog-Claveria-Villanueva Rd. K01330+520-K01334+315, K01334+336-K01337+096, K01337+311-K01338+500 | Misamis Oriental | 2012-08-13 | 1st | X | LF | 134.939 | 270 | 2012-05-29 | 2013-02-22 | 5.01 | O | 0.399 | 0.296 | 0.15 | 0.03 | 0.051 | 0.05 | 97.6 | -
GICAR CONSTRUCTION, INC. | 12624 | L | A | MB | GE | Widening of Bulua Bridge along Carmen-Patag-Bulua Road, Barangay Bulua, Cagayan de Oro City | Barangay Bulua, Cagayan de Oro City | 2015-06-11 | Final | Cagayan de Oro City First DEO | LF | 22.316 | 255 | 2014-02-21 | 2014-11-02 | - | C | 0.48 | 0.2 | 0.3 | - | - | - | 98% | *84.32% Satisfactory
Gicar Construction, Inc. (Formerly: Gicar Construction) | 12624 | L | A | MB | GE | Widening of Bulua Bridge along Carmen-Patag-Bulua-Road | Brgy. Bulua, Cagayan de Oro City | 2014-10-20 | 1st | X | LF | 22.3164 | 195 | 2014-02-21 | 2014-09-03 | -2.48% | O | 0.307 | 0.235 | 0.125 | 0.015 | 0.037 | 0.033 | 75.2% | 75.20% Unsatisfactory
Gicar Construction, Inc. (Formerly: Gicar Construction) | 12624 | L | A | MA | GE | Construction of Drainage System along Surigao City Wharf Road, Surigao City | Surigao City | 2014-10-26 | 1st | XIII | LF | 15.1006 | 239 | 2014-03-31 | 2014-11-24 | 9.81% | O | 0.322 | 0.272 | 0.15 | 0.02 | 0.037 | 0.05 | 85.1% | 85.10% Satisfactory
Gicar Construction, Inc. (Formerly: Gicar Construction) | 12624 | L | A | MB | GE | Construction/Improvement of Access Road Leading to Tourism Destinations, NRJ Lipata - Punta Bilar - Mabua Road, Leading to War Memorial Building and Pebbles Beach Resort | Brgy. Lipata, Punta, Bilar and Mabua, Surigao City | 2014-10-28 | 1st | XIII | LF | 45.3046 | 209 | 2014-05-29 | 2014-12-23 | 0.28% | O | 0.325 | 0.24 | 0.15 | 0.022 | 0.051 | 0.05 | 83.8% | 83.80% Satisfactory
Gicar Construction, Inc. (Formerly: Gicar Construction) | 12624 | L | A | MB | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rd., (IS) Surigao-Davao Coastal Rd. | Madrid-Carmen, Surigao del Norte | 2012-08-11 | 2nd | XIII | LF | 40.243 | 300 | 2012-01-23 | 2012-11-17 | 15.7 | O | 0.33 | 0.3 | 0.15 | 0.03 | 0.045 | 0.033 | 88.8 | -
Gicar Construction, Inc. (Formerly: Gicar Construction) | 12624 | L | A | MB | GE1 | Conc. of NRJ Quezon-Mapawa-Capalayan-Espina-Navarro Rd. | Surigao del Norte | 2012-08-11 | 1st | XIII | LF | 44.872 | 150 | 2012-03-15 | 2012-08-11 | -14.91 | O | 0.393 | 0.3 | 0.001 | 0.03 | 0.06 | 0.05 | 83.4 | -
GICAR CONSTRUCTION, INC. (FORMERLY: GICAR CONSTRUCTION) | 12624 | L | AA | LA | GE | Widening of National Roads, Arterial Roads along National Roads, Daang Maharlike/ Asian Highways - 26, (Lipata-Surigao Section) | K1114+(-608) to K1116+000, Surigao City | 2015-06-10 | 1st | SURIGAO DEL NORTE FIRST DEO | LF | 44.921 | 179 | 2015-03-09 | 2015-09-03 | (+) 3.42% | O | 0.393 | 0.238 | 0.15 | 0.03 | 0.05 | 0.033 | 89.4% | -
Gicar Construction, Inc. / Santech Builders (J.V.) | JV-12-391 | L | A | MB | GE1 | Impv't./Upgrading (Gravel to Concrete) of NRJ Lipata-Punta Bilar & Mabua Rd., K1+620-K4+295.75 | Surigao City, Surigao del Norte | 2013-08-08 | 1st | XIII | LF | 80.617 | 235 | 2013-03-19 | 2013-11-08 | 0.03 | O | 0.358 | 0.265 | 0.15 | 0.03 | 0.035 | 0.05 | 88.8 | -
GIMP VENTURES | 33025 | L | B | SB | GB | Construction/Expansion of Barangay Health Station (BHS), Brgy. 6 | Kabankalan City, Negros Occidental | 2014-10-24 | 1st | VI | LF | 0.96499 | 72 | 2014-09-03 | 2014-11-13 |  | O | 0.366 | 0.24 | 0.15 | 0.03 | 0.056 | 0.033 | 87.5% | 87.50% Satisfactory
GIMP VENTURES | 33025 | L | B | SB | GE | Construction of Farm to Market Road, Manjuyod, Negros Oriental | Manjuyod, Negros Oriental | 2015-11-10 | Final | Negros Oriental 1st DEO | LF | 4.8898 | 105 | 2015-03-25 | 2015-07-07 | (-)10% | C | 0.477 | 0.2 | 0 | - | - | - | 67.7% | 67.7% Poor
GIOVANNI CONSTRUCTION | 12168 | L | B | MA | GE | Rehabilitation/ Reconstruction of National Roads w/ Slips along Agusan-Malaybalay Road (Hawilian Section) | K1281+224 to K1281+250, K1287+197 to K1287+229, K1287+573 to K1287+714, Esperanza, Agusan Del Sur | 2015-06-04 | 1st | AGUSAN DEL SUR FIRST DEO | LF | 28.043 | 159 | 2015-03-03 | 2015-08-08 | (+) 7.77% | O | 0.39 | 0.237 | 0.15 | 0.03 | 0.06 | 0.05 | 91.7% | -
Giovanni Construction | 12168 | L | B | MA | GE | Widening of National Road along Daang Maharlika (Agusan - Davao Section) S00439MN K1307+493 - K1309+138.10 (Intermittent Section) | San Francisco, Agusan del Sur | 2014-10-23 | 2nd | XIII | LF | 36.6698 | 256 | 2014-03-19 | 2014-11-29 | 4.85% | O | 0.302 | 0.288 | 0.15 | 0.023 | 0.047 | 0.05 | 86% | 86.00% Satisfactory
Giovanni Construction | 12168 | L | B | MA | GE | Widening of National Road along Daang Maharlika (Agusan - Davao Section) K1307+493 - K1309+138.100 (Intermittent Section) | San Francisco, Agusan del Sur | 2014-08-08 | 1st | XIII | LF | 36.6698 | 226 | 2014-03-19 | 2014-10-30 | 0.65 | O | 0.345 | 0.216 | 0.15 | 0.02 | 0.035 | 0.05 | 81.6 | -
Giovanni Construction | 12168 | L | B | MA | GE | Construction of Crossing Luna Flood Control | Esperanza, Agusan del Sur | 2014-08-06 | 1st | XIII | LF | 36.6698 | 189 | 2014-02-11 | 2014-08-18 | 1.53 | O | 0.319 | 0.225 | 0.15 | 0.023 | 0.033 | 0.05 | 80 | -
Giovanni Construction | 12168 | L | B | MA | GE1 | Rd. Upgrading from gravel to concrete along Butuan City-Talacogon-Loreto-Veruela-Sta. Josefa Rd. K1332+897-K1333+869 | Talacogon, Agusan del Sur | 2012-11-28 | 1st | XIII | LF | 24.002 | 354 | 2012-01-31 | 2013-01-18 | -14.95 | O | 0.381 | 0.3 | 0.001 | 0.03 | 0.06 | 0 | 77.2 | -
GIOVANNIN CONSTRUCTION | 12168 | L | B | MA | GE | Rehabilitation/Reconstruction of National Roads with Slips along Agusan-Malaybalay Road (Hawilian Section), K1281+2240 - K1281+250, K1287+197 - K1287+229, K1287+573 - K1287+714, Esperanza, Agusan del Sur | Esperanza, Agusan del Sur | 2015-11-10 | 1st | Agusan del Sur 1st DEO | LF | 30.2232 | 273 | 2015-03-03 | 2015-11-03 | (+) 21.39 | OG | 0.376 | 0.2 | 0.3 | - | - | - | 87.6% | 87.6% Satisfactory
GJD CONSTRUCTION & SUPPLY | 25866 | L | D | SB | GB | Completion of Multi-Purpose Building, Brgy. Oyan, Sibutad, Zamboanga del Norte | Sibutad, Zamboanga del Norte | 2015-11-14 | Final | Zamboanga Del Norte 3rd DEO | LF | 1.8856 | 60 | 2015-05-11 | 2015-07-09 | - | C | 0.389 | 0.2 | 0.3 | - | - | - | 88.9% | 88.9% Satisfactory
GLS CONSTRUCTION & GENERAL MERCHANDISE | 34233 | L | A | SB | GE | Off-Carriageway-Improvement (Construction of Turn-outs) Ozamis City-Oroqiueta City Road K1733+100 ; K1741+950, Ozamis City-Oroquieta City | Ozamis City-Oroquieta City | 2015-06-04 | 1st | Misamis Occidental First DEO | LF | 3.8 | 119 | 2015-02-25 | 2015-06-23 | - | O | 0.321 | 0.29 | 0.052 | 0.03 | 0.041 | 0.017 | 75.1% | -
GLS CONSTRUCTION & GENERAL MERCHANDISE | 34233 | L | A | SB | GE | Concreting of Lutao-Punta Road (Phase II), Panaon, Misamis Occidental | Panaon, Misamis Occidental | 2015-11-20 | Final | Misamis Occidental 1st | LF | 2.8171 | 45 | 2015-03-30 | 2015-05-14 | 0.00% | C | 0.468 | 0.133 | 0.3 | - | - | - | 90.1% | 90.1% Very Satisfactory
GM PAJARILLAGA CONSTRUCTION & SUPPLY | 21760 | L | D | SB | GE | Local Infrastructure Program - Construction of Barangay Roads, (Masoc Road) Brgy. Bayombong, Bayombong, Nueva Vizcaya | Bayombong, Nueva Vizcaya | 2015-11-18 | Final | NUEVA VIZCAYA 1ST DEO | LF | 0.71008 | 180 | 2015-02-18 | 2015-08-16 | (+) 0.01 | C | 0.448 | 0.133 | 0.3 | - | - | - | 88.1% | 88.1% Satisfactory
Gold Rich Construction & Trading (Formerly: Gold Rich Construction) | 16489 | L | AAA | LA | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads including Drainage based on Pavement Management System/Highway Development and Management-4 (HDM-4) (Intermittent Sections), Quirino Highway (Baguio-Bauang Road), KO299+086-KO303+776 with exception | Baguio City | 2014-11-17 | 1st | CAR | LF | 42.0471 | 190 | 2014-07-04 | 2015-01-09 | 1.15% | O | 0.323 | 0.277 | 0.15 | 0.03 | 0.055 | 0.033 | 86.8% | 86.80% Satisfactory
Gold Rich Construction & Trading (Formerly: Gold Rich Construction) | 16489 | L | AAA | LA | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads including Drainage based on Pavement Management System/Highway Development and Management-4 (HDM-4) (Intermittent Sections), Rimando-Ambiong Road, Chainage 0000 -Chainage 2402 | Baguio City | 2014-11-17 | 1st | CAR | LF | 41.9614 | 190 | 2014-06-26 | 2015-01-01 | -22% | O | 0.346 | 0.275 | 0.15 | 0.03 | 0.05 | 0.033 | 88.4% | 88.40% Satisfactory
Gold Rich Construction & Trading (Formerly: Gold Rich Construction) | 16489 | L | AAA | LA | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads including Drainage based on Pavement Management System/Highway Development and Management-4 (HDM-4) (Intermittent Sections), Kennon Road, KO244+360-KO0247+300 with exception | Baguio City | 2014-11-17 | 1st | CAR | LF | 41.9511 | 215 | 2014-07-04 | 2015-02-03 | -13.5% | O | 0.348 | 0.258 | 0.15 | 0.03 | 0.05 | 0.05 | 88.6% | 88.60% Satisfactory
Gold Rich Construction & Trading (Formerly: Gold Rich Construction) | 16489 | L | AA | MB | GE1 | Opening/Impv't. of Baguio Circ. Rd. (Western Link), Sect. 1: Kennon Rd. Jct. to Montecillo, K0245+440-K0245+957, Sect. 2: Ciudad Grande to Saint Louis University, K0245+1748-K0245+1910, Sect. 3: Bakakeng to Balacbac, K0247+766-K0248+223.61, Sect. 4: Balacbac to Marcos Highway, (248+1875-248+2347) & Sect. 5: Happy Hallow (246+1690-246+3860) Eastern Link | Baguio City | 2013-03-24 | 1st | CAR | LF | 38.762 | 402 | 2012-02-24 | 2013-04-29 | 0.5 | O | 0.387 | 0.24 | 0.15 | 0.03 | 0.056 | 0.033 | 89.6 | -
GOLD RICH CONSTRUCTION & TRADING (Formerly: Gold Rich Construction) | 16489 | L | AAA | MB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Road including Drainage based on Pavement Management System/Highway Development & Management-4 (HDM-4) | Baguio City | 2015-06-12 | Final | Baguio City DEO | LF | 46.193 | 234 | 2014-07-04 | 2015-02-22 | 0% | C | 0.4 | 0.2 | 0.3 | - | - | - | 90% | *89.16% Very Satisfactory
Golden Ridge Enterprises and Engineering Services | 29946 | L | AA |  | GE5 | Sual Port Development Project | Brgy. Poblacion, Sual, Pangasinan | 2012-08-28 | 1st | PPA | LF | 80.608 | 390 | 2011-10-25 | 2012-11-12 | -6.471 | O | 0.393 | 0.3 | 0.112 | 0.03 | 0.0653 | 0.033 | 93.33 | -
Golden Tech Construction | 14820 | L | D | SB | GE2 | Addalam River Irrigation Project |  | 04/27/09 05/01/09 | 1st | NIA |  | 9.792 | 370 |  |  |  | O | 0.325 | 0.24 | 0.15 | 0.0225 | 0.0382 | 0.05 | 82.57 | -
Goldenville Realty and Development Corporation |  | L |  |  |  | Land Development and Construction of Housing Units (Villa Sofia) | Brgy. Tagpuro, Tacloban City, Leyte | 2015-05-03 | 1st | NHA | LF | 184.311 | 240 |  |  | 32.97 | O | 0.2828 | 0.1617 | 0.15 | 0.02 | 0.04 | 0.05 | 70.45 | -
Goldenville Realty and Development Corporation | [5 empty] | Land Development and Construction of Housing Units (Villa Sofia) | Brgy. Tagpuro, Tacloban City, Leyte | 2015-09-25 | 2nd | NHA | LF | 184.311 | 240 | 2015-04-24 | 2015-12-19 | 3.19 | O | 0.3345 | 0.2739 | 0.15 | 0.03 | 0.05 | 0.05 | 88.84 | -
Goldenville Realty and Development Corporation | [5 empty] | Villa Sofia Housing Project | Brgy. Tagpuro, Tacloban City, Leyte | 2016-04-16 | 3rd | NHA | LF | 184.311 | 240 | 2015-04-27 | 2016-04-09 | -8.37 | O | 0.3557 | 0.3 | 0.0663 | 0.03 | 0.049 | 0.033 | 83.4 | -
Goldrich Construction | 16489 | L | B | MA | GE5 | Masantol River Wharf (Phase 2) Improvement Project |  | 7/1-4/08 | 1st | PPA |  | 16.879 | 120 |  |  |  | O | 0.3617 | 0.24 | 0.1 | 0.015 | 0.035 | 0.0667 | 81.84 | -
Goldrich Construction | 31884 | L |  |  | GE5 | Repair of retaining Wall, Mooring and Fendering System | Jalandoni - Libertad Side of Iloilo River Wharf, Iloilo City (Phase II) | 10/25-27/11 | 1st | PPA | LF | 17.96 | 240 | 2011-02-13 | 2011-12-10 | -5.67 | O | 0.3737 | 0.2541 | 0.093 | 0.03 | 0.0467 | 0.05 | 84.75 | -
Goldrock Construction & Development Corp. | 5389 | L | AAA | LB | GE | Road Upgrading (Gravel to Concrete) of El Nido Junction - New Ibajay Road (Intermittent Section), Sta. 284+968 to Sta. 295+337.50 ( w/ exceptions) | E Nido Palawan | 2014-11-21 | 1st | IV | LF | 103.2307 | 346 | 2014-05-14 | 2015-04-24 | 14.74% | O | 0.379 | 0.24 | 0.15 | 0.03 | 0.043 | 0.05 | 89.2% | 89.20% Very Satisfactory
Goldrock Construction & Development Corp. | 5389 | L | AAA | LB | GE1 | Rd. Upgrading (Gravel to Paved) Jct. New Ibajay Rd. K0281+756 to K0284+810 | El Nido, Palawan | 2013-08-10 | 1st | IVB | LF | 41.168 | 271 | 2013-01-22 | 2013-10-19 | 0.86 | O | 0.36 | 0.235 | 0.15 | 0.03 | 0.06 | 0.05 | 88.5 | -
Goldrock Construction & Development Corp. | 5389 | L | AAA | LB | GE1 | Const./Widening/Upgrading/Rehab. of Access Rd. Conc. of Taytay (Pancol)-El Nido Rd. (Km.215+900-Km.217+240; Km.217+540-Km.220+881) w/ exception Taytay Sect. | Taytay, Palawan | 2013-08-09 | 4th | IVB | LF | 90.224 | 479 | 2012-04-30 | 2013-08-21 | -5.8 | O | 0.372 | 0.3 | 0.092 | 0.03 | 0.051 | 0.017 | 86.2 | -
Goldrock Construction & Development Corp. | 5389 | L | AAA | LB | GE1 | Const./Widening/Upgrading/Rehab. of Access Rd., Conc. of Taytay (Pancol)-El Nido Rd. (Km.215+000-Km.217+240; Km.217+540-Km.220+881 w/ exception), Taytay Sect. | Taytay, Palawan | 2013-03-12 | 3rd | IVB | LF | 90.224 | 420 | 2012-04-30 | 2013-06-23 | -9.98 | O | 0.362 | 0.3 | 0.05 | 0.03 | 0.055 | 0.05 | 84.7 | -
Goldrock Construction & Development Corp. | 5389 | L | AAA | LB | GE1 | Rd. Upgrading (gravel to paved) El Nido Jct., New Ibajay Rd., K0328+268-K0328+810.50 | El Nido, Palawan | 2013-08-10 | 1st | IVB | LF | 10.465 | 271 | 2013-01-22 | 2013-10-19 | 6.96 | O | 0.341 | 0.234 | 0.15 | 0.03 | 0.051 | 0.05 | 85.6 | -
Goldrock Construction & Development Corp. | 5389 | L | AAA | LB | GE1 | Const./Widening /Upgrading/Rehab. of Access Rd. Conc. of Taytay-El Nido Rd. (Km.254+910-Km.259+000 w/ exception) | El Nido, Palawan | 2013-08-09 | 2nd | IVB | LF | 93.176 | 509 | 2012-05-10 | 2013-09-30 | -12.28 | O | 0.372 | 0.3 | 0.027 | 0.03 | 0.051 | 0.017 | 79.7 | -
Goldrock Construction & Development Corp. | 5389 | L | AAA | LB | GE1 | Const./Widening/Upgrading/Rehab.on of Access Rd., Conc. of Taytay-El Nido Rd. (Km.254+910-Km.259+000 w/ exception) | El Nido, Palawan | 2013-03-12 | 1st | IVB | LF | 93.176 | 450 | 2012-05-10 | 2013-08-02 | -9.38 | O | 0.381 | 0.3 | 0.056 | 0.03 | 0.045 | 0.017 | 82.9 | -
Goldrock Construction & Development Corp. | 5389 | L | AAA | LB | GE1 | Rehab./Upgrading (Conc.) of Taytay-El Nido Road Km.210+557-Km.215+40 | El Nido, Palawan | 2012-03-15 | 1st | IVB | LF | 100.129 | 330 | 2011-11-16 | 2012-10-10 | 29.12 | O | 0.364 | 0.3 | 0.15 | 0.03 | 0.06 | 0.05 | 95.4 | -
Goldrock Construction & Development Corp. | 5389 | L | AAA | LB | GE1 | Rehab./Upgrading (Conc.) of Taytay-El Nido Rd. (Km.210+557-Km.215+406) | El Nido, Palawan | 2012-11-22 | 3rd | IVB | LF | 107.307 | 420 | 2011-11-16 | 2013-01-09 | 2.96 | O | 0.322 | 0.285 | 0.15 | 0.03 | 0.055 | 0.05 | 89.2 | -
Goldrock Construction & Development Corp. | 5389 | L | AAA | LB | GE1 | Const./Widening/Upgrading/Rehab. of Access Rd., Conc. of Taytay (Pancol)-El Nido Rd. (Km.215+900-Km.217+240; Km.217+540 -Km.220+881 w/ exceptions), Taytay Sect. | Taytay, Palawan | 2012-11-23 | 2nd | IVB | LF | 82.402 | 381 | 2012-04-30 | 2013-05-15 | -3.09 | O | 0.363 | 0.286 | 0.119 | 0.03 | 0.055 | 0.033 | 88.6 | -
Goldrock Construction & Development Corporation | 5389 | L | AAA | LB | GE1 | Rehab./Upgrading (Conc.) of Taytay-El Nido Rd. Km.210+557-Km.215+406 | El Nido, Palawan | 2012-08-03 | 2nd | IVB | LF | 100.129 | 349 | 2011-11-16 | 2012-10-29 | 1.31 | O | 0.296 | 0.3 | 0.15 | 0.03 | 0.04 | 0.033 | 84.9 | -
Goldrock Construction & Development Corporation | 5839 | L | AAA | LB | GE1 | Const./Widening/Upgrading/Rehab. of Access Road Conc. of Taytay (Pancol)-El Nido Road (Km.215+900-Km.217+240; Km.217+540-Km.220+881 w/ exception, Taytay Sect. | Taytay, Palawan | 2012-08-03 | 1st | IVB | LF | 82.402 | 330 | 2012-04-30 | 2013-03-25 | 0.05 | O | 0.367 | 0.3 | 0.15 | 0.03 | 0.045 | 0.033 | 92.5 | -
Gonzalo Construction | 1826 | L | A | MB | GE1 | Upgrading/Impv't. along Ambiong-Lubas Rd., (Benguet Sect.) K0253+560-K0259+035 (v.s.) | La Trinidad, Benguet | 2013-07-29 | 1st | CAR | LF | 45.596 | 209 | 2013-02-08 | 2013-09-04 | -6.98 | O | 0.379 | 0.3 | 0.08 | 0.03 | 0.055 | 0.033 | 87.7 | -
Gonzalo Construction | 1826 | L | A | MB | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rds. (Int. Sect.) (Package XIV-2012) | Kapangan, Benguet | 2013-07-31 | 1st | CAR | LF | 8.461 | 201 | 2013-02-11 | 2013-08-29 | -0.27 | O | 0.36 | 0.239 | 0.147 | 0.015 | 0.045 | 0.033 | 83.9 | -
Gonzalo Construction | 1826 | L | A | MB | GE1 | Replacement of Bolo Bridge along Gurel-Bokod-Kabayan-Buguias-Abatan Rd., K0300+569 | Bokod, Benguet | 2013-07-30 | 1st | CAR | LF | 22.037 | 225 | 2013-02-09 | 2013-09-21 | -10.5 | O | 0.377 | 0.24 | 0.045 | 0.023 | 0.05 | 0.017 | 75.2 | -
Gonzalo Construction | 1826 | L | A | MB | GE1 | Rehabilitation/Reconstruction of Damanged Road along Abra-Kalinga Road |  | 2009-02-25 | 1st | CAR |  | 14.328 | 200 |  |  |  | O | 0.159 | 0 | 0.114 | 0 | 0.025 | 0 | #VALUE! | -
GONZALO CONSTRUCTION | 1826 | L | A | MB | GE | Completion of Ambalideng Bridge along Acop - Kapangan - Kibungan - Bakun Road, K0316+016 | Kibungan, Benguet | 2015-06-03 | 1st | Benguet 2nd DEO | LF | 11.885 | 161 | 2015-02-16 | 2015-07-26 | (+) 5.94 | O | 0.32 | 0.3 | 0.15 | 0.022 | 0.04 | 0.033 | 86.5% | -
Gonzalodo Enterprises | 30681 | L | B | SB | GB1 | Const. of Three (3) Storey, Nine (9) Cl Sch. Bldg. at Basak Elem. Sch. | Lapu-Lapu City, Cebu | 2013-08-12 | 1st | VII | LF | 10.775 | 180 | 2013-03-27 | 2013-09-22 | 0.36 | O | 0.36 | 0.24 | 0.15 | 0.03 | 0.055 | 0.033 | 86.8 | -
GONZALODO ENTERPRISES | 30681 | L | B | MA | GE | Rehabilitation/Improvement of Road, Nangka-Tayud Road | Consolacion, Cebu | 2015-09-04 | 1st & Final | Cebu 6th | LF | 4.455 | 108 | 2015-02-16 | 2015-06-03 | 0% | C | 0.444 | 0.133 | 0.3 | - | - | - | 87.7% | *87.7% Satisfactory
Good Fortune International Incorporated | 9246 | L | B | MA | GE1 | Concreting of Lemery-San Rafael Road |  | 2009-09-08 | 2nd | VI |  | 28.639 | 430 |  |  |  | O | 0.312 | 0.3 | 0.15 | 0.023 | 0.05 | 0.05 | 88.5 | -
GOOD FORTUNE INTERNATIONAL, INC. | 9246 | L | B | MA | GE | Upgrading of Rizal Bridge Leading to Iloilo International Container Port | K0001+(-263) to K0001+(-238), Brgy. Rizal, Lapaz, Iloilo City | 2015-06-02 | Final | Iloilo City DEO | LF | 17.362 | 225 | 2014-02-12 | 2014-09-24 | 0% | C | 0.486 | 0.164 | 0.3 | - | - | - | 95% | *95% Very Satisfactory
Good Fortune International, Incorporated | 9246 | L | B | SB | GE2 | Aganan Sta. Barbara RIS (Rehabilitation of Aganan Sta. Barbara RIS Aganan Area Lateral D Bench Flume) |  | 01/10-15/2011 |  | NIA |  | 3.586 | 120 |  |  |  | O | 0.3816 | 0.24 | 0.0907 | 0.03 | 0.0509 | 0.05 | 84.32 | -
Good Fortune International, Incorporated | 9246 | L | B | MA | GE1 | Conc. of Lambunao-Inca Rd., Km.0057+031-Km.0057+814 | Lambunao, Iloilo | 2012-08-23 | 1st | VI | LF | 17.303 | 180 | 2012-03-19 | 2012-09-14 | 0.22 | O | 0.358 | 0.285 | 0.15 | 0.03 | 0.03 | 0.05 | 90.3 | -
GOOD FORTUNE INTERNATIONAL, INCORPORATED | 9246 | L | B | MA | GE | Improvement/Completion of Benigno S. Aquino Avenue (Iloilo-Jaro Diversion Road) including Off-Carriageway-Dungon IV Bridge and Approaches along Service Road, Sta. 5+078-Sta. 5+129, Iloilo City | Iloilo City | 2015-11-20 | Final | Regional Office | LF | 17.29 | 60 | 2015-08-26 | 2015-10-25 | 0.00% | C | 0.424 | 0.2 | 0.3 | - | - | - | 92.4% | 92.4% Very Satisfactory
Goodvibe Builders, Inc. | 32686 | L | D | SB | GE1 | Const. of Barangay Road at La Paz | Villasis, Pangasinan | 2013-03-13 | 1st | I | LF | 3.994 | 84 | 2013-01-11 | 2013-04-04 | 0.49 | O | 0.306 | 0.3 | 0.15 | 0.015 | 0.035 | 0.033 | 83.9 | -
Goodvibe Builders, Inc. | 32686 | L | D | SB | GE1 | Widening of MNR, Urdaneta-Villasis Section |  | 2009-05-19 | 1st | I |  | 7.237 | 620 |  |  |  | O | 0.367 | 0.218 | 0.15 | 0.03 | 0.03 | 0.05 | 84.5 | -
Gowil Builders | 18733 | L | B | MA | GE1 | Const. of Geometric Alignment of Roadway along Cebu-Balamban Transcentral Highway, K0038+(-47)-K0039+950, Int. Sect. (w/ exception) | Balamban, Cebu | 2013-08-08 | 2nd | VII | LF | 42.11 | 275 | 2013-01-24 | 1025/13 | 2.82 | O | 0.378 | 0.274 | 0.15 | 0.03 | 0.055 | 0.05 | 93.7 | -
Gowil Builders | 18733 | L | B | MA | GE1 | Const. of Geometric Alignment of Roadway along Cebu-Balamban Transcentral H-way, K0038+(-47)-K0039+950, Int. Sect. (w/ exception) | Balamban, Cebu | 2013-03-17 | 1st | VII | LF | 42.11 | 275 | 2013-01-24 | 2013-10-25 | 0.73 | O | 0.387 | 0.298 | 0.15 | 0.03 | 0.032 | 0.033 | 93 | -
Gowil Builders | 18733 | L | B | SB | GE2 | Const. of Storm Drainage & Canal along Toledo-San Remegio Rd., K0062+00-K0062+78 (Int. Sect.) | Cebu | 2013-03-17 | 2nd | VII | LF | 7.071 | 152 | 2012-09-21 | 2013-02-19 | - | O | 0.376 | 0.24 | 0 | 0.03 | 0.032 | 0.017 | 69.5 | -
Gowil Builders | 18733 | L | B | SB | GE2 | Const. of Storm Drainage & Canal along Toledo-San Remegio Rd., K0062+00-K0068+78 (IS) | Cebu | 2012-11-23 | 1st | VII | LF | 7.071 | 137 | 2012-09-21 | 2013-02-04 | -3.86 | O | 0.391 | 0.24 | 0.111 | 0.03 | 0.035 | 0.033 | 84 | -
GOWIL BUILDERS/WTG CONSTRUCTUON & DEVELOPMENT CORP. JOINT VENTURE | JV-14-854 | L | AAA | LA | GE | Construction/Upgrading/Rehabilitation of Drainage along National Roads at A.C. Cortes Ave., K0008(062) - K0009+118, Mandaue City, Cebu | Mandaue City, Cebu | 2015-11-15 | 1st | Cebu 6th | LF | 44.0984 | 416 | 2015-03-30 | 2016-05-19 | 0.2134 | OG | 0.365 | 0.24 | 0.15 | 0.03 | 0.02 | 0.05 | 85.5% | 85.5% Satisfactory
Grace Const. Corp./Dipolog Top Const. Dev't. Corp (JV) | JV-08-016 | L | AAA | LB | GE1 | Dipolog Airport Development Project |  | 2009-09-02 | 2nd | DOTC |  | 0.163 | 360 |  |  |  | O | 0.368 | 0.3 | 0.15 | 0.03 | 0.051 | 0.05 | 94.9 | -
Grace Construction Corporation | 14-02197 | L | AAA |  | GE-5 | Proposed Plaridel Port Improvement, Port of Plaridel | Plaridel, Misamis Occidental | 2015-12-04 | 1st | PPA | LF | 92.903 | 360 | 2015-04-02 | 2016-03-26 | -6.984 | O | 0.3969 | 0.3 | 0.1149 | 0.03 | 0.07 | 0.05 | 96.18 | -
Grace Construction Corporation | 3771 | L | AAA | LB | GE1 | Const. of Limpapa Bridge & Approaches |  | 2008-08-19 | 1st | IX |  | 60.097 | 360 |  |  |  | O | 0.226 | 0.24 | 0.1 | 0.03 | 0.047 | 0.1 | 74.3 | -
Grace Construction Corporation | 3771 | L | AAA | LB | GE1 | Impvt./Conc. Paving of Dapitan City-Dakak Road, Phase I |  | 2008-09-03 | 3rd | IX |  | 48.038 | 340 |  |  |  | O | 0.36 | 0.27 | 0.1 | 0.03 | 0.042 | 0.1 | 90.2 | -
Grace Construction Corporation | 3771 | L | AAA | LB | GE1 | Impv't/Conc. Paving of Dapitan City-Dakak Road, Phase II |  | 2009-03-17 | 1st | IX |  | 47.488 | 702 |  |  |  | O | 0.337 | 0.277 | 0.15 | 0.03 | 0.035 | 0.05 | #VALUE! | -
Grace Construction Corporation | 3771 | L | AAA | LB | GE1 | Const. of Opao Bridge and Approaches, Brgy. Opao |  | 2009-06-09 | 2nd | IX |  | 71.037 | 1067 |  |  |  | O | 0.373 | 0.3 | 0.132 | 0.03 | 0.047 | 0.033 | 91.5 | -
Grace Construction Corporation | 3771 | L | AAA | LB | GE1 | Const. of One (1) RCDG Bridge (Piacan) & (1) Spillway (Sibuco) along Zamboanga West Coast Road | Zamboanga del Norte | 2011-08-09 | 1st | IX | LF | 128.835 | 887 | 2009-04-06 | 2011-09-09 | 35.933 | O | 0.345 | 0.24 | 0.15 | 0.03 | 0.045 | 0.033 | 84.3 | -
Grace Construction Corporation | 3771 | L | AAA | LB | GE1 | Const. of Lobog Parallel Bridge and Approaches (Phase IV) |  | 2009-09-15 | 1st | X |  | 52.566 | 180 |  |  |  | O | 0.353 | 0.24 | 0.1 | 0.03 | 0.037 | 0.033 | 79.3 | -
Grace Construction Corporation | 3771 |  |  |  |  | Const. of Lobog Parallel Bridge and Approaches (Phase IV) |  | 2010-06-02 |  | X |  | 52.566 | 441 |  |  |  | O | 0.379 | 0.3 | 0.15 | 0.03 | 0.047 | 0.033 | 93.9 | -
Grace Construction Corporation | 3771 | L | AAA | LB | GE1 | Reconst. of Kalaw Bridge | Monkayo, Comval Province | 2011-08-18 | 2nd | XI | LF | 94.331 | 632 | 2010-03-24 | 2011-12-15 | -9.53 | O | 0.4 | 0.3 | 0.055 | 0.03 | 0.05 | 0.033 | 86.8 | -
Grace Construction Corporation | 3771 | L | AAA | LB | GE1 | Reconst. of Kalaw Bridge | Monkayo, Comval Province | 2011-04-10 | 1st | XI | LF | 94.331 | 632 | 2010-03-24 | 2011-12-15 | 0.03 | O | 0.377 | 0.3 | 0.15 | 0.03 | 0.06 | 0.05 | 96.7 | -
Grace Construction Corporation | 3771 |  |  |  |  | Const. of Upper Makar Bridge No.1 Phase IV (Completion of Abutment "A" and Const. of 4 spans, 30 LM PSCG Superstructure) along Circumferential Rd. |  | 2010-03-10 |  | XII |  | 47.371 | 240 |  |  |  | O | 0.343 | 0.253 | 0.15 | 0.03 | 0.04 | 0.033 | 84.9 | -
Grace Construction Corporation | 3771 | L | AAA | LB | GE1 | Const. of Upper Manakulil/Bridge (Phase I) along Cotabato City Circ. Rd. | Cotabato City | 2012-08-16 | 1st | XII | LF | 23.906 | 289 | 2011-11-28 | 2012-09-12 | -4.47 | O | 0.395 | 0.24 | 0.105 | 0.03 | 0.051 | 0.05 | 87.1 | -
Grace Construction Corporation | 3771 |  |  | MA |  | Plaridel Port Improvement Project | Plaridel, Misamis Occidental/ Region XII | 2016-04-15 | 2nd | PPA | LF | 92.903 | 433 | 2015-04-02 | 2016-07-17 | 0.083 | O | 0.394 | 0.2976 | 0.15 | 0.03 | 0.053 | 0.05 | 97.46 | -
GRACE CONSTRUCTION CORPORATION | 3771 | L | AAA | LB | GE | Rehab/Reconst/Upgrading of Damaged Paved National Roads Including Drainage Based on Pavement Management System/Highway Development and Management-4 (HDM-4) (Intermittent Section), Ozamis-Pagadian Road, K1673+000-K1674+127, K1681+001-K1682+247 | Ozamis-Pagadian Road, K1673+000-K1674+127, K1681+001-K1682+247 | 2015-08-31 | 1st | Misamis Occidental 2nd DEO | LF | 38.996 | 163 | 2015-05-07 | 2015-10-16 | 24.14% | O | 0.342 | 0.236 | 0.15 | 0.03 | 0.045 | 0.05 | 85.3% | -
Grace Construction Corporation/M. Montescalaros Enterprises, Inc. Joint Venture | JV-13-043 | L | AAA | LB | GE | Reconst. of Cabula Bridge/Nicdao Steel Utility Bridge, Sitio Maasin, Brgy. Nicdao | Baungon, Bukidnon | 2014-10-25 | 1st | X | LF | 197.2308 | 491 | 2014-09-05 | 2016-01-08 | 1.92% | O | 0.348 | 0.292 | 0.15 | 0.03 | 0.051 | 0.05 | 92.1% | 92.10% Very Satisfactory
GRACE CONSTRUCTION CORPORTION/M. MONTESCLaROS ENTERPRISES, INC. (JV) | SL--SN-007891/ JV-13-043 | L | AAA | LB | GE | Reconstruction of Cabula/Nicdao Utility Steel Bridge, Sitio Maasin, Barangay Nicdao, K1451+540-K1452+315, Baungon, Bukidnon | Sitio Maasin, Barangay Nicdao, Baungon, Bukidnon | 2015-06-10 | Final | Regional Office X | LF | 197.231 | 491 | 2013-09-05 | 2015-01-08 | - | C | 0.446 | 0.2 | 0.3 | - | - | - | 94.6% | *93.1% Very Satisfactory
Granby Trading and Construction | 27554 | L | AAA | SB | GB | Sto. Nino Shrine Heritage Rehabilitation | Tacloban City | 2016-01-27 | 1st | TIEZA | LF | 10 | 270 | 2015-04-14 | 2016-01-08 | -27.72 | O | 0.374 | 0.3 | 0 | 0.03 | 0.058 | 0.033 | 79.53
Granby Trading and Construction | 27554 | L | AAA | SB | GB | Sto. Nino Shrine Heritage Rehabilitation | Tacloban City | 2016-06-09 | Final | TIEZA | LF | 10 | 270 | 2015-04-14 | 2016-04-06 |  | C | 0.475 | 0.2 | 0.3 |  |  |  | 97.65 | 85.00 Satisfactory
Grand Builders | 6845 | L | A | MA | GE | Road Impv't from Highway leading to Pagayawan Falls 1) K1557+843-K1559+666.22 2) K0002+060-K0002+654.21; 3) K001+880-K002+148.436 | Bacolod, Lanao del Norte | 2014-10-29 | 1st | X | LF | 50.7534 | 210 | 2014-03-26 | 2014-10-21 | -6.69% | O | 0.275 | 0.296 | 0.083 | 0.007 | 0.033 | 0.033 | 72.7% | 72.70% Poor
Grand Builders | 6845 | L | A | MA | GE1 | Rehab./Const.Upgrading of Damaged Paved Nat'l Rds. (Int. Sect.) BCIR, Sugbongcogon-Binuangan-Ampenican-Lagonglong Sect., Misamis Oriental, K01364+299-K01365+000, K01368+798-K01370+000, K01372+000-K01373+000, K01379+798-K01380+000 | Misamis Oriental | 2013-08-21 | Final | X | LF | 51.907 | 225 | 2012-04-02 | 2012-11-12 | - | C | 0.374 | 0.2 | 0 | - | - | - | 57.4 | 70.96% Poor
Grand Builders | 6845 | L | A | SB | GE2 | Const. of Iligan Circ. Road | Iligan City | 2013-03-16 | Final | X | LF | 22.302 | 360 | 2011-09-27 | 2012-09-20 | 0 | C | 0.304 | 0.2 | 0.3 | - | - | - | 80.4 | 84.21% Satisfactory
Grand Builders | 6845 | L | A | MA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rd. (IS) BCIR, Sugbongcogon-Binuangan-Ampenican-Lagonglong Sect., Misamis Oriental, K01364+299-K01365+000, K01368+798-K01370+000, K01372+000-K1373+000, K01379+567-K01380+000 | Misamis Oriental | 2012-11-21 | 1st | X | LF | 51.907 | 225 | 2012-04-02 | 2012-11-12 | -14.7 | O | 0.373 | 0.3 | 0 | 0.03 | 0.047 | 0.05 | 80 | -
GRAND BUILDERS | 6845 | L | A | MA | GE | Road Improvement from Highway Leading to Pagayawan Falls, Bacolod, a) K1557+843.000-K1559+666.220; b) K0002+060.000-K0002+654.271; c) K0001+880.000-K0002+148.438, Lanao del Norte 1st Legislative District | Lanao del Norte 1st Legislative District | 2015-06-10 | Final | Regional Office X | LF | 50.712 | 270 | 2014-03-26 | 2014-12-20 | - | C | 0.439 | 0.2 | 0.3 | - | - | - | 93.9% | *81.18% Unsatisfactory
GRAND BUILDERS | 6845 | L | A | MA | GE | Construction of Tudela Bypass Road, Tudela, Misamis Occidental | Tudela, Misamis Occidental | 2015-06-05 | 1st | Misamis Occidental Second DEO | LF | 36.663 | 160 | 2015-02-27 | 2015-08-05 | - | O | 0.245 | 0.276 | 0.15 | 0.024 | 0.035 | 0.05 | 78% | -
GRAND BUILDERS | 6845 | L | B | MA | GE | Construction of Tudela By-Pass Road, Tudela, Misamis Occidental | Tudela, Misamis Occidental | 2015-08-31 | 2nd | Misamis Occidental 2nd DEO | LF | 36.663 | 189 | 2015-02-27 | 2015-09-03 | 0.25% | O | 0.367 | 0.236 | 0.15 | 0.03 | 0.058 | 0.05 | 89.1% | -
GREAT WALL ENGINEERING | 34573 | L | B | SB | GB | Construction of Five (5) C/L School Building, Alawihao National High School | Daet, Camarines Norte | 2015-06-08 | Final | Camarines Norte | LF | 4.515 | 90 | 2014-05-14 | 2014-08-11 | 0% | C | 0.457 | 0.15 | 0.3 | - | - | - | 90.7% | *90.7% Very Satisfactory
Greco Construction and Supply | 21884 | L | D | SB | GE | Construction/Rehabilitation of Flood Control Structures along Sarangani - Davao del Sur Coastal Road, Malapatan, Sarangani Province | Malapatan, Sarangani Province | 2014-10-29 | 1st & Final | XII | LF | 4.7463 | 100 | 2014-02-12 | 2014-05-22 | 0% | C | 0.421 | 0.133 | 0.3 | - | - | - | 85.4% | 85.40% Satisfactory
Greco Construction and Supply | 21884 | L | D | SB | GE1 | Replacement/Rehab./Strengthening of Permanent Bridges Gen. from Bridge Mgt. System (BMS) of Tambilil Bridge along Sarangani-Sultan Kudarat Coastal Rd. | Kiamba, Sarangani Province | 2013-08-19 | Final | XII | LF | 4.52 | 100 | 2013-01-31 | 2013-05-10 | 1.38 | C | 0.429 | 0.2 | 0.3 | - | - | - | 92.9 | 89.84% Very Satisfactory
Greco Construction and Supply | 21884 | L | D | SB | GE1 | Replacement/Rehab./Strengthening of Permanent Bridge Gen. from Bridge Mgt. System (BMS), Tambilil Bridge along Sarangani-Sultan Kudarat Coastal Rd. | Kiamba, Sarangani Province | 2013-03-22 | 1st | XII | LF | 4.52 | 100 | 2013-01-31 | 2013-05-10 | 8.84 | O | 0.358 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 87.8 | -
Green Horizon Landscapers & Developers, Inc. | 18802 | L | A | MA | GE1 | Impvt. (Conc. of Access Road @ Juction Pola Road Km 73+000 (leading to Pola Port) |  | 2009-09-03 | 1st | IVB |  | 35.603 | 240 |  |  |  | O | 0.337 | 0.288 | 0.15 | 0.03 | 0.051 | 0.05 | 90.6 | -
Green Horizon Landscapers & Developers, Inc. | 18802 | L | A | MA | GE1 | Completion of Calapan South Road, Tabtabong-Banti Section |  | 2009-09-05 | 1st | IVB |  | 38.059 | 238 |  |  |  | O | 0.359 | 0.24 | 0.15 | 0.03 | 0.042 | 0.05 | 87.1 | -
GREEN ISLAND ENTERPRISES | 36835 | L | C | SB | GE | Construction of Gabions Revetment Mansalay River Control | Mansalay, Oriental Mindoro | 2015-06-11 | Final | Southern Mindoro DEO | LF | 6.951 | 71 | 2015-02-18 | 2015-04-29 | 0% | C | 0.45 | 0.133 | 0.3 | - | - | - | 88.3% | *88.3% Satisfactory
Green Zone Construction & Supply | 35102 | L | D | SB | GE | Rehab/Reconst. Of Daang Maharlika (K0624+979 - K0625+062) with exception | Irosin, Sorsogon | 2014-08-12 | 1st & Final | V | LF | 1.1954 | 37 | 2014-01-24 | 2014-03-01 | 2.7 | C | 0.419 | 0.136 | 0.3 |  |  |  | 85.5 | 85.50% Satisfactory
Greenwall Construction | 14457 | L | D | SB | GE | Construction/Completion of Three (3) Storey, Nine (9) Classrooms School Buiding (Phase 2) at Bayanan Elementary School | Muntinlupa City, Metro Manila | 2014-11-17 | 1st | NCR | LF | 10.8387 | 180 | 2014-07-18 | 2015-01-13 | 0.55% | O | 0.309 | 0.3 | 0.15 | 0.03 | 0.058 | 0.05 | 89.7% | 89.70% Very Satisfactory
GREENWALL CONSTRUCTION | 14457 | L | D | SB | GB | Construction/Completion of Three (3) Storey, Nine (9) Classroom School Building (Phase 2) at Bayanan Elementary School, Muntinlupa City, Metro Manila | Muntinlupa City | 2015-06-10 | Final | Las Pinas-Muntinlupa | LF | 10.839 | 195 | 2014-07-18 | 2015-01-28 | - | C | 0.419 | 0.133 | 0.3 | - | - | - | 85.2% | *85.2% Satisfactory
Grelips Construction & Development | 34236 | L | C | SB | GB-1 | Legaspi City LTFRB Regional Office Project | Rawis, Legaspi City/Region V | 2015-04-27 | 2nd & Final | DOTC | LF | 6.199 | 210 | 2013-03-18 | 2014-11-23 | 0 | C | 0.4838 | 0.2 | 0.3 | - | - | - | 98.38 | 92.58% Very Satisfactory
Grelips Construction & Development | 34236 | L | C | SB | GB-1 | Legaspi City LTFRB Regional Office Building Project | Rawis, Legaspi City | 2014-09-03 | 1st | DOTC | LF | 6.199 | 210 | 2013-03-18 | 2014-11-23 | 22.94 | O | 0.369 | 0.3 | 0.15 | 0.015 | 0.05 | 0.017 | 90.1 | -
Gulf Canary Construction and Development, Inc. | 12522 | L | A |  |  | Z3R Rehabilitation Project - Mariki | Brgy. Mariki, Zamboanga City | 2015-08-07 | 2nd | NHA | LF | 137.834 | 459 | 08/29/14 | 2015-08-08 | 0.25 | O | 0.3708 | 0.2745 | 0.15 | 0.023 | 0.038 | 0.05 | 90.63 | -
Gulf-Canary Construction and Development Inc. | 12522 | L | AAA |  |  | Z3R Rehabilitation Project-Mariki | Brgy. Mariki, Zamboanga City | 2015-03-13 | 1st | NHA | L | 137.721 | 300 | 2014-08-29 | 2015-07-11 | 0.11 | O | 0.3857 | 0.2725 | 0.15 | 0.03 | 0.0269 | 0.05 | 91.51 | -
Gulf-Canary Construction and Development, Inc. | 12522 |  | A |  |  | Z3R Rehabilitation Project - Mariki | Brgy. Mariki, Zamboanga City | 2016-04-29 | 3rd & Final | NHA | LF | 137.721 | 300 | 2014-08-29 | 2016-01-22 | 0 | C | 0.4473 | 0.2 | 0.3 | - | - | - | 94.73 | 92.17% V. Satisfactory
GVDPM Construction Corp. (Formerly: ZM Construction) | 9052 | L | AA | LA | GE2 | Const. of Slope Protection/Flood Control, Kiling (North Side) | Cabangan, Zambales | 2013-03-15 | 1st | III | LF | 13.292 | 120 | 2013-01-23 | 2013-05-22 | 25.8 | O | 0.371 | 0.19 | 0.15 | 0.03 | 0.05 | 0.033 | 82.4 | -
GVDPM Construction Corp. (Formerly: ZM Construction) | 9052 | L | AA | LA | GE1 | Rehab./Reconst./Upgrading of Gapan-Olongapo Rd. | Bataan | 2013-03-22 | 1st | III | LF | 57.492 | 323 | 2012-06-05 | 2013-04-23 | 3.99 | O | 0.297 | 0.235 | 0.15 | 0.03 | 0.045 | 0.033 | 79 | -
GVDPM Construction/ E.A. Unabia Construction/ TECKCON Construction/ Kalinga Builders (J.V.) | JV-13-562 | L | A | MB | GE | Const./Rehab./ of Drainage Protection Works at Bulanao Flood Control, Tabuk City, Kalinga | Tabuk City, Kalinga | 2014-08-07 | 1st | CAR | LF | 37.8535 | 134 | 2014-03-10 | 2014-07-21 | #VALUE! | O | 0.373 | 0.24 | 0.15 | 0.024 | 0.05 | 0.05 | 88.7 | -
H C M Construction Corporation | 19382 | L | A | MB | GE1 | Const./Widening of Pres. C.P. Garcia Ave. (C-5) Ext., SLEX to Coastal Sect., Sta. 0+354.106-Sta. 0+660 | Las Piñas City | 2013-08-17 | Final | NCR | LF | 100.458 | 341 | 2012-05-02 | 2013-04-07 | 0.64 | C | 0.453 | 0.133 | 0.3 | - | - | - | 88.6 | 88.44% Satisfactory
H L J Construction & Enterprises | 18080 | L | A | MA | GE | Road Upgrading (gravel to paved) along Davao-Sarangani Coastal Road, (Malalag-Malita-JAS), km. 1689+648.732 to km. 1691+217.302 Lanipao Section, Don Marcelino | Davao del Sur | 2014-08-07 | 1st | XI | LF | 37.2044 | 179 | 2013-03-07 | 2013-09-01 | -13.87 | O | 0.277 | 0.3 | 0.011 | 0.03 | 0.019 | 0 | 63.7 | -
H. A. Pastor Construction Corporation | 34496 |  | A | SB |  | Continuation of the Rehabilitation of the Pierhead of tingloy Port | Tingloy, Batangas/ Region IV-A | 2015-10-29 | 1st | DOTC | LF | 8.74 | 150 | 2015-07-01 | 2015-09-27 | -53.03 | O | 0.3 | 0.3 | 0 | 0.02 | 0.0311 | 0.05 | 70.11 | -
H. A. Pastor Construction Corporation | 34496 |  | A | SB |  | Continuation of the Rehabilitation of Pierhead of Tingloy Port | Tingloy, Batangas/ Region IV-A | 2016-08-04 | 2nd & Final | DOTC | LF | 9.479 | 160 | 2016-07-01 | 2016-05-11 | 0 | C | 0.4568 | 0.2 | 0.3 | - | - | - | 95.68 | 80.34% Unsatisfactory
H. G. LOPEZ CONSTRUCTION | 17691 | L | A | MA | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads Along San Juan-San Gabriel Road, K0278+000 to K0278+872, San Juan, La Union | K0278+000 to K0278+872, San Juan, La Union | 2015-08-29 | 1st | La Union 1st DEO | LF | 11.047 | 246 | 2015-02-10 | 2015-10-14 | (+)25.7 | O | 0.365 | 0.267 | 0.15 | 0.023 | 0.045 | 0.05 | 90% | -
H.F. ENTERPRISES | 38649 | L | C | SB | GB | Local Infrastructure Program-Completion of Multi-Purpose Building, Lambunao, Iloilo 3rd Legislative District: D. Brgy. Gines (Completion of Covered Gym) Lambunao, Iloilo | Brgy. Gines, Lambunao, Iloilo | 2015-11-17 | Final | Iloilo 2nd | LF | 4.4246 | 60 | 2015-10-06 | 2015-12-05 | 16.56% | C | 0.465 | 0.133 | 0.3 | - | - | - | 89.8% | 89.8% Very Satisfactory
H.G. Lopez | 17691 | L | B | SB | GE | Construction of Drainage Structure along Manila North Road, San Fernando City Section | San Fernando City, La Union | 2014-10-25 | 1st & Final | I | LF | 9.6529 | 176 | 2014-02-12 | 2014-08-06 | 0% | C | 0.416 | 0.145 | 0.3 | - | - | - | 86.1% | 86.10% Satisfactory
H.G. Lopez Construction | 17691 | L | B | MA | GB | Construciton of 9-Cl, 3-Storey Building at La Union National High School | San Fernando City, La Union | 2014-08-04 | Final | I | LF | 10.8425 | 295 | 2013-03-27 | 2014-01-15 | 8.48 | C | 0.463 | 0.133 | 0.3 |  |  |  | 89.6 | 88.48% Satisfactory
H.G. Lopez Construction | 17691 | L | B | MA | GE1 | Prev. Maint. along San Fernando Port Rd., K0267+000-K0268+717 | La, Union | 2013-07-29 | Final | I | LF | 12.534 | 54 | 2013-01-21 | 2013-03-15 | 0 | C | 0.475 | 0.133 | 0.3 | - | - | - | 90.8 | 90.08% Very Satisfactory
H.G. Lopez Construction | 17691 | L | B | MA | GB1 | Const. of 9-Cl, 3-Storey Bldg. at La Union NHS | San Fernando City, La Union | 2013-07-30 | 1st | I | LF | 10.418 | 270 | 2013-03-27 | 2013-12-21 | 0.3 | O | 0.368 | 0.24 | 0.15 | 0.03 | 0.042 | 0.05 | 88 | -
H.G. Lopez Construction | 17691 | L | B | MA | GE1 | Prev. Maint. along San Fernando Port Rd., K0267+000-K0268+717 | La Union | 2013-03-11 | 1st | I | LF | 12.534 | 54 | 2013-01-21 | 2013-03-15 | 0.38 | O | 0.373 | 0.3 | 0.15 | 0.008 | 0.015 | 0.05 | 89.6 | -
H.G. LOPEZ CONSTRUCTION | 17691 | L | B | SB | GE | Rehabilitation/Improvement of Amburayan River Control Project, Up-uplas | Sudipen, La Union | 2015-06-06 | Final | La Union 1st DEO | LF | 9.304 | 127 | 2015-02-07 | 2015-06-13 | 6% | C | 0.417 | 0.133 | 0.3 | - | - | - | 85% | *85% Satisfactory
H.G. LOPEZ CONSTRUCTION | 17691 | L | A | MA | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved Roads along San Juan-San Gabriel Road K0287+000 - K0278+872, San Juan, La Union | San Juan, La Union | 2015-11-10 | Final | LA UNION 1ST DEO | LF | 11.0465 | 246 | 2015-02-10 | 2015-10-13 | 0.0969 | C | 0.484 | 0.133 | 0.3 | - | - | - | 91.7% | 90.26% Very Satisfactory
H.L.J Construction & Enterprises | 18080 | L | A | MA | GE1 | Conc. of Dancalan-Candoni-Damutan Valley Road, Caningay Section, Brgy. Caningay |  | 2009-05-30 | 1st | VI |  | 16.235 | 280 |  |  |  | O | 0.38 | 0.268 | 0.15 | 0.023 | 0.045 | 0.033 | 89.9 | -
H.L.J Construction & Enterprises | 18080 | L | A | MA | GE1 | Conc. of Dancalan-Candoni-Damutan Valley Road, Tabu Section, Brgy. Tabu |  | 2009-05-30 | 1st | VI |  | 18.335 | 280 |  |  |  | O | 0.366 | 0.251 | 0.15 | 0.023 | 0.05 | 0.033 | 87.3 | -
H.L.J Construction & Enterprises | 18080 | L | A | MA | GE1 | Conc. of Boracay Road (Lapus-Lapus, Fairways Sect.) |  | 2009-03-15 | 2nd | VI |  | 19.686 | 289 |  |  |  | O | 0.312 | 0.296 | 0.15 | 0.018 | 0.05 | 0.033 | #VALUE! | -
H.L.J Construction & Enterprises | 18080 | L | A | MA | GE1 | Rehab./Recons./Upgrading of Dumaguete North Rd., Polo-Tugas Rd. Sect. |  | 2009-09-12 | 1st | VII |  | 23.022 | 210 |  |  |  | O | 0.372 | 0.24 | 0.15 | 0.03 | 0.037 | 0.033 | 86.2 | -
H.L.J Construction & Enterprises | 18080 | L | A | MA | GE1 | Impvt. of Roads leading to the Twin Springs Project, Brgy. Bunga to Brgy. Baslay Road |  | 2008-11-25 | 1st | VII |  | 9.311 | 145 |  |  |  | O | 0.323 | 0.236 | 0.1 | 0.03 | 0.027 | 0.067 | 78.3 | -
H.L.J. Construction & Enterprises | 18080 | L | A | MA | GE1 | Reconst. of Bacolod South Kabankalan Road |  | 2009-03-03 | 1st | VI |  | 16.997 | 180 |  |  |  | O | 0.261 | 0.292 | 0.15 | 0.03 | 0.055 | 0.033 | #VALUE! | -
H.L.J. Construction & Enterprises | 18080 | L | A | MA | GE | Rehabilitation/Reconstruction/Replacement/Retrofitting of Existing Permanent Bridges Mambuloc Bridge 1 | Sto. Niño-Bango Road (South), Bacolod City | 2014-10-27 | 1st & Final | VI | LF | 5.6461 | 120 | 2014-02-13 | 2014-06-12 |  | C | 0.485 | 0.081 | 0.3 | - | - | - | 86.6% | 86.60% Satisfactory
H.L.J. Construction & Enterprises | 18080 | L | A | MA | GE | Construction/Improvement of Mabinay Leading to Crystal Cave | Mabinay, 2nd District, Negros Oriental | 2014-10-27 | 1st | VII | LF | 45.5676 | 239 | 2014-06-10 | 2015-02-04 | 0.76% | O | 0.329 | 0.226 | 0.15 | 0.024 | 0.061 | 0.05 | 84% | 84.00% Satisfactory
H.L.J. Construction & Enterprises | 18080 | L | A | MA | GB1 | Const. of DepEd Standard Type Sch. Bldg. @ Bulwangan NHS | Hinoba-an, Negros Occidental | 2013-08-09 | 1st | VI | LF | 2.842 | 90 | 2013-05-24 | 2013-08-21 | 12.04 | O | 0.388 | 0.24 | 0.15 | 0.03 | 0.032 | 0.033 | 87.3 | -
H.L.J. Construction & Enterprises | 18080 | L | A | MA | GE1 | Const./Widening/Upgrading/Rehab. of Access Rd. to Declared Tourism Destinations, Brgy. Punta-Taytay | Bacolod City, Negros Occidental | 2013-08-06 | 1st | VI | LF | 45.541 | 180 | 2013-02-19 | 2013-08-17 | 7.56 | O | 0.369 | 0.2 | 0.15 | 0.03 | 0.037 | 0.05 | 83.6 | -
H.L.J. Construction & Enterprises | 18080 | L | A | MA | GE1 | Reconst. of Martilo Bridge | La Libertad, Negros Oriental | 2013-08-22 | 1st | VII | LF | 11.731 | 192 | 2013-04-03 | 2013-10-11 | -1.32 | O | 0.347 | 0.3 | 0.137 | 0.023 | 0.045 | 0.017 | 86.9 | -
H.L.J. Construction & Enterprises | 18080 | L | A | MA | GE1 | Reconst. of Habag Bridge | La Libertad, Negros Oriental | 2013-08-22 | 1st | VII | LF | 11.354 | 222 | 2013-02-09 | 2013-09-18 | -6.62 | O | 0.388 | 0.3 | 0.084 | 0.023 | 0.045 | 0.017 | 85.7 | -
H.L.J. Construction & Enterprises | 18080 | L | A | MA | GE1 | Upgrading (Gravel to Concrete) Conc. of Hanay-Hanay Rd. leading to Twin Lake | San Jose, Negros Oriental | 2013-08-21 | 1st | VII | LF | 14.472 | 115 | 2013-03-18 | 2013-07-11 | -2 | O | 0.326 | 0.3 | 0 | 0.03 | 0.055 | 0.05 | 76.1 | -
H.L.J. Construction & Enterprises | 18080 | L | A | MA | GE1 | Rd. Upgrading (Gravel to Paved) along Davao-Sarangani Coastal Rd., (Malalag-Malita-JAS), km. 1689+648.732-km. 1691+217.302, Lanipao Sect., Don Marcelino | Davao del Sur | 2013-08-08 | 1st | XI | LF | 37.204 | 179 | 2013-03-07 | 2013-09-01 | -1.23 | O | 0.314 | 0.298 | 0.138 | 0.03 | 0.023 | 0.033 | 83.6 | -
H.L.J. Construction & Enterprises | 18080 | L | A | MA | GE1 | Road Upgrading (Gravel to Paved) Davao-Sarangani Coastal Rd., Malalag-Malita-JAS Rd., Biton Sect., Km.1669+180.5-Km.1670+080 | Davao del Sur | 2011-08-11 | 1st | XI | LF | 37.417 | 180 | 2011-07-12 | 2012-01-07 | 18.04 | O | 0.391 | 0.29 | 0.15 | 0.008 | 0.054 | 0.05 | 94.3 | -
H.L.J. Construction & Enterprises | 18080 | L | A | MA | GE1 | Road Upgrading (Gravel to Paved) Davao-Sarangani Coastal Road, Malalag-Malita-JAS Rd., Calian Sect. Km.1675+520 - Km.1677+683.960 | Davao del Sur | 2011-08-11 | 1st | XI | LF | 41.448 | 180 | 2011-06-20 | 2011-12-16 | 5.58 | O | 0.344 | 0.3 | 0.15 | 0.008 | 0.05 | 0.05 | 90.2 | -
H.L.J. CONSTRUCTION & ENTERPRISES | 18080 | L | A | MA | GE | Construction of Side Slope Protection along Ilo-ilo-Capiz Road (New Route) | Km. 075+000-Km.078+000 with exception Balucuan, Capiz | 2015-06-08 | Final | Capiz Second DEO | LF | 8.73 | 211 | 2014-03-27 | 2014-10-23 | 0.95% | C | 0.347 | 0.193 | 0.3 | - | - | - | 84% | *84% Satisfactory
H2 Landmark Builders, Inc. (Formerly: Landmark Builders) | 7400 | L | A | MA | GE | Road Upgrading (Gravel to Concrete) of Mati - Maragusan Road | Davao Oriental | 2014-08-07 | 1st | XI | LF | 70.0091 | 237 | 2014-03-05 | 2014-10-27 | 0.39 | O | 0.405 | 0.225 | 0.15 | 0.03 | 0.047 | 0.05 | 90.7 | -
H2 Landmark Builders, Inc. (Formerly: Landmark Builders) | 7400 | L | A | MA | GE1 | Road Upgrading (Gravel to Paved) along Mati-Maragusan Rd. a)Km.1518+200-Km.1518+552; b)Km.1531+209-Km.1532+850, Bactinan-Buso-Caguisokan Sect. | Davao Oriental | 2013-08-16 | Final | XI | LF | 33.116 | 149 | 2013-01-25 | 2013-06-22 | 0 | C | 0.344 | 0.2 | 0.3 | - | - | - | 84.4 | 84.70% Satisfactory
H2 Landmark Builders, Inc. (Formerly: Landmark Builders) | 7400 | L | A | MA | GE1 | Rd. Upgrading (Gravel to Paved) along Mati-Maragusan Rd. a)Km.1518+200-Km.1518+552; b)Km.1531+209-Km.1532+850, Bacatinan-Buso-Caguisokan Sect. | Davao Oriental | 2013-03-20 | 1st | XI | LF | 33.116 | 149 | 2013-01-25 | 2013-06-22 | 8.48 | O | 0.292 | 0.277 | 0.15 | 0.03 | 0.05 | 0.05 | 84.9 | -
Haidee Construction & Development Corp./B.P. Cruz Builders & Trading (JV) | JV-13-323 | L | AAA | LB | GE | Widening/Improvement of Manila North Road, including Drainage System, K0083+580 to K0094+000 (w/ exception), Angeles-Mabalacat Section | Angeles City | 2014-11-19 | 1st | III | LF | 41.0686 | 246 | 2014-04-01 | 2014-12-01 | 1% | O | 0.35 | 0.24 | 0.15 | 0.03 | 0.046 | 0.033 | 84.9% | 84.90% Satisfactory
Haidee Construction & Development Corp./Supreme ABF Construction & Construction Supply Company, Inc. (JV) | JV-11-527 | L | A | MB | GE1 | Impvt./Widening of McArthur Highway (MNR) Angeles-Mabalacat Sect. | Pampanga | 2012-11-23 | 1st | III | LF | 93.698 | 331 | 2012-03-15 | 2013-04-10 | 5.02 | O | 0.388 | 0.24 | 0.15 | 0.03 | 0.06 | 0.05 | 91.8 | -
Haidee Construction and Development Corp. | 10365 | L | AAA | LB | GE1 | Const. of Tagumbao Bridge & Approaches along Gerona-Sta. Ignacia Rd. | Gerona, Tarlac | 2013-08-08 | 1st | III | LF | 226.266 | 480 | 2013-02-22 | 2014-06-16 | 5.89 | O | 0.387 | 0.24 | 0.15 | 0.03 | 0.051 | 0.05 | 90.8 | -
Haidee Construction and Development Corporation | [5 empty] | Long-Term Permanent Works at Pasig-Potrero Bridge of SCTEX | Porac, Pampanga | 2015-02-04 | 1st | BCDA | L | 71.62 | 360 | 2014-08-18 | 2015-08-21 | 2.71 | O | 0.3918 | 0.3 | 0.15 | 0.03 | 0.0269 | 0.05 | 94.87 | -
Haidee Construction and Development Corporation | [5 empty] | Long-Term Permanent Works at Pasig-Potrero Bridge of SCTEX | Porac, Pampanga | 2015-04-29 | 2nd | BCDA | L | 71.62 | 360 | 2014-08-18 | 2015-08-21 | -1.28 | O | 0.392 | 0.2939 | 0.1372 | 0.03 | 0.0485 | 0.0167 | 91.83 | -
Haidee Construction and Development Corporation | 4846 | L |  |  |  | Construction of BCDA Remaining Infrastructure Works inside Bonifacio Global City, package 2 | Bonifacio Global City | 2014-12-15 | 1st | BCDA | L | 115.618 | 420 | 2014-01-23 | 2015-03-24 | 48.64 | O | 0.3893 | 0.3 | 0.0712 | 0.03 | 0.0431 | 0.05 | 88.36 | -
Hakkatan Konstruk & General Merchandise | 31610 | L | B | SB | GB | Const. of DepEd Standard Type School Building at Tabu NHS Ilog, Negros Occidental | Ilog, Negros Occidental | 2014-08-09 | Final | VI | LF | 3.331 | 85 | 2013-05-24 | 2013-07-22 | 0 | C | 0.435 | 0.2 | 0.3 |  |  |  | 93.5 | 84.82% Satisfactory
Hakkatan Konstruk & General Merchandise | 31610 | L | B | SB | GB1 | Const. of DepEd Standard Type Sch. Bldg. @ Tabu NHS | Ilog, Negros Occidental | 2013-08-09 | 1st | VI | LF | 3.331 | 95 | 2013-05-24 | 2013-08-26 | 3.67 | O | 0.326 | 0.24 | 0.15 | 0.03 | 0.032 | 0.033 | 81.1 | -
Hakkatan Konstruk & General Merchandise | 31610 |  |  |  |  | Const./Impvt. of DPWH Office Bldg., 3rd Negros Occidental District Engineering & Sitio Mojon, Brgy. I |  | 2010-06-05 |  | VI |  | 4.308 | 220 |  |  |  | O | 0.356 | 0.266 | 0.15 | 0.022 | 0.041 | 0.033 | 86.8 | -
Hakkatan Konstruk & General Merchandise | 31610 |  |  |  |  | Const./Impvt. of DPWH Bldg., 3rd Negros Occidental DEO at Sitio Mojon, Brgy. 1 |  | 2010-08-24 |  | VI |  | 4.474 | 220 |  |  |  | O | 0.369 | 0.24 | 0.15 | 0.03 | 0.035 | 0.033 | 85.7 | -
Halrey Construction Inc. | 2267 | L | AAA | MB | GE1 | Rd. Upgrading (Gravel to Paved) of Eastern Bulacan Rd., K0080+200-K0094+809, Doña Remedios | Trinidad, Bulacan | 2013-03-20 | 1st | III | LF | 19.706 | 150 | 2013-02-04 | 2013-07-03 | 10.53 | O | 0.369 | 0.24 | 0.15 | 0.02 | 0.04 | 0.05 | 86.9 | -
Halrey Construction Inc./ Three W Builders Inc. - JV |  | L |  |  |  | Guadalupe Heights 1 | Brgy. Suhi, Tacloban City, Leyte | 2015-10-09 | 1st | NHA | LF | 289.884 | 240 | 04/17/15 | 2016-12-12 | 4 | O | 0.28 | 0.28 | 0.15 | 0.03 | 0.038 | 0.05 | 82.8 | -
Halrey Construction, Inc. | 2267 | L | AAA | MB | GE | Widening of San Marcelino - San Antonio Road, K0153+000 - K0154+550 | San Marcelino, Zambales | 2014-11-27 | 1st & Final | III | LF | 30.3987 | 150 | 2014-01-14 | 2014-06-12 | 0% | C | 0.425 | 0.133 | 0.3 | - | - | - | 85.8% | 85.80% Satisfactory
Halrey Construction, Inc. | 2267 | L | AAA | MB | GE | Construction/Rehabilitation of Marilao-San Jose Road, San Jose Del Monte City | Bulacan | 2014-09-27 | 1st & Final | Special 3 | LF | 18.5729 | 120 | 2014-02-11 | 2014-06-10 | 0 | C | 0.405 | 0.133 | 0.3 |  |  |  | 83.8 | 83.80% Satisfactory
Halrey Construction, Inc. | 2267 | L | AAA | MB | GE1 | Rd. Upgrading (Gravel to Paved) of Eastern Bulacan Rd., K0080+200-K0094+809 Doña Remedios | Trinidad, Bulacan | 2013-08-15 | Final | III | LF | 19.706 | 150 | 2013-02-04 | 2013-07-04 | 10.14 | C | 0.41 | 0.133 | 0.3 | - | - | - | 84.3 | 85.86% Satisfactory
Halrey Construction, Inc. | 2267 | L | AAA | MB | GE1 | Impvt./Concrete Blocking along Epifanio delos Santos Ave. | Quezon City | 2011-03-31 | 1st | NCR | LF | 4.623 | 60 | 2011-02-11 | 2011-04-11 | 0.26 | O | 0.397 | 0.2 | 0.15 | 0.03 | 0.045 | 0.033 | 85.5 | -
HALREY CONSTRUCTION, INC. | 2267 | L | AAA | SB | GB | Construction of Multi-Purpose Building, Brgy. Bagong Nayon, Baliuag, Bulacan | Baliuag, Bulacan | 2015-06-12 | Final | Bulacan 1st DEO | LF | 4.254 | 180 | 2014-08-07 | 2015-02-02 | 0% | C | 0.473 | 0.2 | 0.3 | - | - | - | 97.3% | *97.3% Outstanding
HALREY CONSTRUCTION, INC. | 2267 | L | AAA | MB | GE | Widening of Permanent Bridge Sta. Maria Bridge 2 along Sta. Maria-By-Pass Road, Sta. Maria, Bulacan | Sta. Maria, Bulacan | 2015-08-30 | 1st & Final | Bulacan Second DEO | LF | 12.156 | 190 | 2014-02-11 | 2014-08-19 | - | C | 0.491 | 0.122 | 0.3 | - | - | - | 91.3% | *91.3% Very Satisfactory
HALREY CONSTRUCTION, INC. | 2267 | L | AAA | MB | GE | Rehab./Reconst/Replacement/Retrofitting of Existing Permanent Bridge, Dayapan Bridge along Batangas-Quezon Road | Ibaan, Batangas | 2015-08-29 | 1st & Final | Batangas 4th | LF | 32.944 | 360 | 2014-02-03 | 2015-01-28 | 0% | C | 0.41 | 0.13 | 0.3 | - | - | - | 84% | *84% Satisfactory
Hanjin Heavy Industries & Const. Co. Ltd. | FC-03-010 |  |  |  |  | CP No.1 Const. of Jaro Floodway & Imprv't. of Tigum & Aganan Rivers |  | 2010-03-03 |  | MFCP1 |  | 1979.449 | 1920 |  |  |  | O | 0.335 | 0.265 | 0.15 | 0.03 | 0.056 | 0.05 | 88.6 | -
Hanjin Heavy Industries & Const. Co. Ltd. | SL1-SN-004892 | F | AAA | LB | GE2 | Help for Catubig Agricultural Advancement Project (HCAAP) |  | 11/9-12/09 | 1st | NIA |  | 0.994 | 1253 |  |  |  | O | 0.393 | 0.288 | - | 0.024 | 0.037 | 0.037 | 77.9 | -
Hanjin Heavy Industries & Const. Co. Ltd. | 4892 |  |  |  |  | Help for Catubig Agricultural Advancement Project - Irrigation & Drainage Component (HCAAP-IDC) |  | 2010-09-27 |  | NIA |  | 749.759 | 1381 |  |  |  | O | 0.398 | 0.3 | - | 0.03 | 0.061 | 0.05 | 83.9 | -
Hanjin Heavy Industries & Construction Co., Ltd. (Korea) | FC-11-008 | F | AAA | LB | GE1 | Const. of Bacolod-Silay Airport Access Road (BSAAR) Proj. | Negros Occidental | 2012-11-27 | 1st | KEDCF | FA | 400.988 | 420 | 2012-02-14 | 2013-04-08 | -3.26 | O | 0.389 | 0.293 | 0.117 | 0.03 | 0.06 | 0.017 | 90.6 | -
Hanjin Heavy Industries & Construction, Co. Ltd. (Korean) | FC-11-008 | F | AAA | LB | GE1 | Const. of Bacolod-Silay Airport Access Rd. (BSAAR) Proj. | Bacolod-Silay, Negros Occidental | 2013-08-12 | 3rd | KEDCF-PMO | FA | 415.893 | 572 | 2012-02-14 | 2013-09-06 | -1.55 | O | 0.392 | 0.2 | 0.134 | 0.03 | 0.044 | 0.033 | 83.3 | -
Hanjin Heavy Industries & Construction, Co. Ltd. (Korean) | FC-11-008 | F | AAA | LB | GE1 | Const. of Bacolod-Silay Airport Access Rd. (BSAAR) Proj. | Negros Occidental | 2013-03-16 | 2nd | KEDCF-PMO | FA | 426.704 | 537 | 2012-02-14 | 2013-08-03 | 1.67 | O | 0.367 | 0.3 | 0.15 | 0.03 | 0.051 | 0.033 | 93.1 | -
Hanjin heavy Industries & Construction, Co., Ltd. | FC-08-005 | F | AAA | LB | GE1 | Central Mindanao Rd. Proj., Contract Package 2, Const./Impv't of North Upi-Maguindanao/Sultan Kudarat Bdry. | Province of Maguindanao | 2011-08-11 | 2nd | PMO-RRNDP | LF | 948 | 870 | 2009-06-19 | 2011-11-05 | 5.22 | O | 0.362 | 0.3 | 0.15 | 0.03 | 0.045 | 0.033 | 92 | -
Hanjin Heavy Industries and Construction Co., Ltd. | FC-08-005 | F | AAA | LB | GE1 | Central Mindanao Road Project, Contract Package 2, Const./Improvement of North Upi-Maguindanao/Sultan Kudarat Boundary | Province of Maguindanao | 2011-03-30 | 1st | RRNDP | FA | 892.399 | 782 | 2009-06-19 | 2011-08-09 | 0.06 | O | 0.363 | 0.24 | 0.15 | 0.03 | 0.047 | 0.033 | 86.3 | -
HARLEY CONSTRUCTION, INC. | 2267 | L | AAA | MB | GE | Construction/Upgrading/Rehabilitation of Drainage along Batasan Road, (K0018+181 - K0021+011) with exception, Quezon City | Quezon City | 2015-06-02 | 1st | Quezon City 1st | LF | 17.369 | 240 | 2015-04-06 | 2015-12-01 | (+) 73.75 | C | 0.397 | 0.24 | 0.15 | 0.022 | 0.055 | 0.05 | 91.4% | -
HAUSLAND CONSTRUCTION | 32378 | L | A | MA | GE | Restoration of Slope Protection at Critical Section Along Sapangbalen Creek, Brgy. San Roque, Magalang, Pampanga | Brgy. San Roque, Magalang, Pampanga | 2015-11-13 | Final | Pampanga Third DEO | LF | 17.183 | 180 | 2015-03-06 | 2015-09-01 | - | C | 0.488 | 0.133 | 0.3 | - | - | - | 92.1% | 87.78% Satisfactory
HCG BUILDERS AND SUPPLY | 17824 | L | A | MB | GE | Preventive Maintenance (Intermittent Section Arterial) Along Rolando Andaya Highway a.) K0305+042 to K0305+1002, b.) K0306+000 to K0306+1000, c.) K0309+500 to K0309+1000 | Camarines Sur | 2015-06-04 | Final | Camarines Sur 5th | LF | 35.335 | 151 | 2014-03-18 | 2014-06-15 | 0% | C | 0.445 | 0.181 | 0.3 | - | - | - | 92.6% | *92.6% Very Satisfactory
HCM Construction Corporation | 19382 | L | A | MB | GE1 | Const./Widening of Pres. Garcia Ave. (C-5) Ext., SLEX to Coastal Sect. | Las Piñas City, Metro Manila | 2012-11-24 | 1st | NCR | LF | 100.467 | 326 | 2012-05-02 | 2013-03-22 | -6.4 | O | 0.383 | 0.3 | 0.086 | 0.03 | 0.051 | 0 | 85 | -
Hebei Road and Bridge Group Co., Ltd. | FC-10-006 | F | AAA | LB | GE1 | Impvt. of Malalag-Malita-Jose Abad Santos Rd., CP-RI-2.6: Malita Don Marcelino Sect., Mindanao under the Nat'l Rds. Impvt. & Mgt. Program, Phase 2 (NRIMP-2) | Malita, Davao del Sur | 2012-11-21 | 2nd | NRIMP | FA | 588.815 | 731 | 2011-08-17 | 2013-08-16 | 12.08 | O | 0.36 | 0.281 | 0.15 | 0.03 | 0.051 | 0.05 | 92.2 | -
Hebei Road and Bridge Group Co., Ltd. | FC-10-006 | F | AAA | LB | GE1 | Impv't. of Malalag-Malita-Jose Abad Santos Rd., CP-RI-2.6: Malita-Don Marcelino Sect., Mindanao under NRIMP-2 | Malita, Davao del Sur | 2012-08-09 | 1st | NRIM-PMO | FA | 549.575 | 731 | 2011-08-17 | 2013-08-16 | 7.84 | O | 0.325 | 0.265 | 0.15 | 0.03 | 0.061 | 0.05 | 88.1 | -
Henry S. Oaminal Const. & General Merchandise | 10578 | L | AAA | LA | GB1 | Completion of Dormitory bldg. Phase I |  | 2008-11-26 | 1st | DOST |  | 5.829 | 150 |  |  |  | O | 0.32 | 0.3 | 0.128 | 0.017 | 0.043 | 0.023 | 74.8 | -
Henry S. Oaminal Const. & General Merchandise | 10578 | L | AA | LA | GE1 | Conc. of Jct. (LIR) Carmen-Sagbayan-Bacane Road |  | 2008-08-29 | 1st | VII |  | 22.646 | 250 |  |  |  | O | 0.293 | 0.222 | 0 | 0.02 | 0.032 | 0.1 | 66.7 | -
Henry S. Oaminal Construction & General Merchandise | 10578 | L | AAA | LA | GE1 | Rehab/Reconst./Upgrading of Damaged Paved Nat'l Rd. along Daang Maharlika Rd. (Surigao-Agusan Sect.) Km.1193+000-Km.1201+000 | Agusan del Norte | 2012-03-22 | 1st | XIII | LF | 58.915 | 315 | 2011-10-28 | 2012-09-06 | 1.17 | O | 0.303 | 0.3 | 0.15 | 0.03 | 0.04 | 0.05 | 87.3 | -
Henry S. Oaminal Construction and Geneneral Merchandise | 10578 | L | AAA | LB | GE1 | Rehab./Reconst./Upgrading of Bacolod Circ. Rd., Sta.3+019-Sta.9+424 w/ exception | Bacolod City | 2013-03-11 | 3rd | VI | LF | 97.511 | 553 | 2011-09-27 | 2013-04-02 | -5.05 | O | 0.307 | 0.3 | 0.1 | 0.024 | 0.055 | 0.05 | 83.6 | -
Henry S. Oaminal Construction and General Merchandise | 10578 | L | AAA | LA | GE1 | Rehab./Reconst./Upgrading of Bacolod South Circ. Rd., Sta.3+019-Sta.9+424 w/ exception | Bacolod City | 2012-11-20 | 2nd | VI | LF | 97.511 | 495 | 2011-09-27 | 2013-02-02 | -7.24 | O | 0.366 | 0.274 | 0.078 | 0.023 | 0.055 | 0.033 | 82.9 | -
Henry S. Oaminal Construction and General Merchandise | 10578 | L | AAA | LA | GE1 | Rehab./Reconst./Upgrading of Bacolod South Circ. Rd., Sta.3+019-Sta.9+424 (w/ exception) | Bacolod City | 2012-08-13 | 1st | VI | LF | 97.56 | 465 | 2011-09-27 | 2013-01-03 | 0.25 | O | 0.364 | 0.244 | 0.15 | 0.03 | 0.059 | 0.05 | 89.7 | -
Henry S. Oaminal Construction and General Merchandise | 10578 | L | AAA | LA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rd. (IS): Sayre Highway, Maluko-Damay Sect., Maluko | Manolo Fortich, Bukidnon | 2012-11-20 | 1st | X | LF | 59.428 | 225 | 2012-06-13 | 2013-01-23 | -7.35 | O | 0.334 | 0.3 | 0.077 | 0.03 | 0.05 | 0.017 | 80.8 | -
Henry S. Oaminal Construction and General Merchandise | 10578 | L | AAA | LA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rd. along Daang Maharlika Rd. (Surigao-Agusan Sect.) Km.1193+000Km.1201+000 | Agusan del Norte | 2012-08-07 | 2nd | XIII | LF | 58.915 | 315 | 2011-10-28 | 2012-09-06 | -9.9 | O | 0.341 | 0.3 | 0.051 | 0.03 | 0.06 | 0.05 | 83.2 | -
Henry S. Oaminal Construction and General Merchandise | 10578 | L | AAA | LA | GE1 | Rehab/Reconst./Upgrading of Damaged Paved Nat'l Rd. along Daang Maharlika Rd. (Surigao-Agusan Sect.) Km.1193+000-Km.1201+000 | Agusan del Norte | 2012-11-22 | 1st | XIII | LF | 58.915 | 315 | 2011-10-28 | 2012-12-30 | -4.2 | O | 0.348 | 0.297 | 0.108 | 0.03 | 0.05 | 0 | 83.3 | -
HENSCHA PHILS. INC. | 34164 | L | D | MB | GE | Construction/Upgrading/Rehabilitation of Drainage along National Road Lakandula Drive, K0531+(-058) to K0532+792, Legaspi City | Legaspi City | 2015-08-25 | 1st & Final | Albay Second DEO | LF | 9.261 | 170 | 2015-02-20 | 2015-08-08 | - | C | 0.498 | 0.133 | 0.3 | - | - | - | 93.1% | *93.1% Very Satisfactory
HENSO CONSTRUCTION (Formerly: Southports Construction) | 10720 | L | B | SB | GE | Concreting of Barangay San Jose - Fatima Farm to Market Road, Kalawit, Zamboanga del Norte | Kalawit, Zamboanga del Norte | 2015-11-17 | 1st | Zamboanga Del Norte 2nd DEO | LF | 9.532 | 60 | 2015-08-29 | 2015-10-27 | 2.25% | OG | 0.367 | 0.235 | 0.15 | 0.02 | 0.047 | 0.05 | 86.9% | 86.9% Satisfactory
Herbana Builders and Supply | 32523 | L | B | SB | GE-5 | Development of Kawayan Resort | Kawayan, Biliran/Region VIII | 2015-08-12 | 1st & Final | DOTC | LF | 4.999 | 120 | 2015-06-08 | 2015-10-05 | 43.79 | C | 0.4666 | 0.2 | 0.3 | - | - | - | 96.66 | 96.66% Very Satisfactory
Herbana Builders and Supply | 32523 | L | B | MA | GB-1 | Lipa LTO Regional Office Building Project | Lipa City, Batangas | 2015-05-29 | 2nd | DOTC | LF | 34.027 | 360 | 2014-09-16 | 2015-09-10 | 15.37 | O | 0.382 | 0.3 | 0.15 | 0.03 | 0.047 | 0.05 | 95.9 | -
Herbana Builders and Supply | 32523 | L | B | MA |  | Construction of LTO Building | Lipa City, Batangas/ Region IV-A | 2015-03-26 | 1st | DOTC | L | 34.027 | 360 | 2014-09-16 | 2015-09-10 | 6.58 | O | 0.3859 | 0.2681 | 0.15 | 0.03 | 0.0466 | 0.05 | 93.06 | -
Herbana Builders and Supply | 32523 | L | B | SB |  | Borongan Airport Development Project | Borongan, Eastern Samar | 2014-08-27 | 1st | DOTC | LF | 13.313 | 165 | 2014-03-19 | 2014-10-04 | 36.88 | O | 0.394 | 0.3 | 0.15 | 0.02 | 0.05 | 0.05 | 96.4 | -
Herbana Builders and Supply | 32523 | L | B | SB |  | Borongan Airport Development Project | Borongan, Eastern Samar | 2014-11-06 | 2nd & Final | DOTC | LF | 13.313 | 165 | 2014-03-19 | 2014-10-20 | 17 | C | 0.469 | 0.2 | 0.3 | - | - | - | - | 96.90% Outstanding
Herbana Builders and Supply | 32523 | L | B | MA | GE | Malabsay Falls Eco-Tourism Park Development | Brgy. Panicuason, Naga City | 2015-06-04 | 1st | TIEZA | LF | 24.7 | 180 | 2014-10-07 | 2015-06-30 | -3.25 | O | 0.322 | 0.234 | 0.12 | 0.02 | 0.058 | 0.033 | 78.7 | -
HERBANA BUILDERS AND SUPPLY | 32523 |  |  | MA |  | Lipa LTO Regional Office Building Project | Lipa City, Batangas | 2015-10-09 | 3rd & Final | DOTC | LF | 34.027 | 360 | 2014-09-16 | 2015-09-10 | 0 | C | 0.466 | 0.2 | 0.3 | - | - | - | 96.6 | 95.20% V. Satisfactory
HERBANA BUILDERS AND SUPPLY | 32523 |  |  | MA |  | Taytay Airport Development Project | Brgy. Sandoval, Taytay, Palawan/ Region IV-B | 2016-03-30 | 1st | DOTC | LF | 36.498 | 270 | 2015-11-23 | 2016-08-18 | 23.89 | O | 0.3646 | 0.3 | 0.15 | 0.02 | 0.035 | 0.0333 | 90.29 | -
Herbana Builders and Supply | 32523 | L | B | MA |  | Taytay Airport Development Project | Brgy. Sandoval, Taytay, Palawan/ Region IV-B | 2016-06-30 | 2nd | DOTC | LF | 36.498 | 270 | 2015-11-23 | 2015-08-18 | 26.42 | O | 0.3673 | 0.3 | 0.15 | 0.02 | 0.0431 | 0.05 | 93.04 | -
Herbana Builders and Supply | 32523 | L | B | MA |  | Taytay Airport Development Project | Brgy. Sandoval, Taytay, Palawan/ Region IV-B | 2016-09-21 | 3rd & Final | DOTC | LF | 36.4983 | 270 | 2015-11-23 | 2015-08-18 | 0 | C | 0.4573 | 0.2 | 0.3 | - | - | - | 95.73 | 93.29% Very Satisfactory
Herbana Builders and Supply | 32523 | L | B | MA |  | Maasin Airport Development Project | Maasin, Southern Leyte/ Region 8 | 2016-10-13 | 1st & Final | DOTC | LF | 12.4984 | 150 | 2016-05-17 | 2016-10-13 | 0 | C | 0.4216 | 0.2 | 0.3 | - | - | - | 92.16 | *92.16% Very Satisfactory
Herbana Builders and Supply | 32523 | L | B | MA |  | Surigao Airport Development Project | Surigao City, Surigao del Norte/ CARAGA | 2016-11-24 | 1st | DOTC | LF | 41.6676 | 285 | 2016-05-31 | 2017-05-12 | 3.56 | O | 0.343 | 0.3 | 0.15 | 0.03 | 0.058 | 0.033 | 91.4 | -
Hexamindz Constructor/s |  |  | AA |  |  | Rehabilitation and Development of Estero de Sampaloc - Package 02B | Sampaloc, City of Manila | 2016-04-26 | Final | PRRC | LF | 2.329 | 90 | 2015-07-12 | 2015-10-10 | 15 | C | 0.433 | 0.2 | 0.15 | - | - | - | 78.3 | 80.33% Unsatisfactory
Hexamindz Corporation | 31666 | L | A | MB | GE | Improvement/Upgrading (Gravel to Concrete) of Highway Jct. Santiago – Macopa – Pantad Leading to Pusan Point, Caraga, Davao Oriental | Davao Oriental | 2014-08-13 | 1st | XI | LF | 67.9805 | 209 | 2014-03-07 | 2014-10-01 | -3.5 | O | 0.262 | 0.3 | 0.115 | 0.03 | 0.039 | 0.05 | 79.6 | -
Hexamindz Corporation |  |  | AA |  |  | Rehabilitation and Development of Estero de Valencia P - 2 | Valencia, City of Manila | 2015-12-11 | 1st | PRRC | LF | 3.611 | 150 | 2015-07-18 | 2015-12-10 | 10.67 | O | 0.276 | 0.3 | 0.0433 | 0.024 | 0.037 | 0.033 | 71.33 | -
Hexamindz Corporation |  |  | AA |  |  | Rehabilitation and Development of Estero de Sampaloc - Package 02B | Sampaloc, City of Manila | 2015-12-10 | 1st | PRRC | LF | 2.329 | 90 | 2015-07-12 | 2015-10-10 | 7 | O | 0.365 | 0.3 | 0.08 | 0.018 | 0.033 | 0.016 | 81.2 | -
Hexamindz Corporation |  |  | AA |  |  | Rehabilitation and Development of Estero de Valencia P - 2 | Valencia, City of Manila | 2016-04-29 | 2nd & Final | PRRC | LF | 3.611 | 150 | 2015-07-18 | 2015-12-10 | 10.67 | C | 0.38 | 0.2 | 0.15 | - | - | - | 73 | 71.83% Poor
Hexamindz Corporation (Formerly: Kilusang Magkaibigan M.P. Cooperative (KMMPC)) | 31666 | L |  | MB | GE | Rehab./Reconst./Upgrading of Damaged Paved National Roads including Drainage based on PMS/HDM-4 (intermittent Section) Sindangan - Liloy Road a. K1941+000 - K1941+1000, b. K1955+771 - K1956+004, c. K1958+000 - K1959+002 | Zamboanga Del Norte | 2014-08-09 | 1st | IX | LF | 33.4865 | 193 | 2014-02-20 | 2014-08-31 | -2.88 | O | 0.353 | 0.3 | 0.121 | 0.03 | 0.045 | 0.017 | 86.6 | -
HEXAMINDZ CORPORATION (Formerly: Kilusang Magkaibigan M.P. Cooperative (KMMPC)) | 31666 | L | A | MB | GE | Rehab./Reconst./Upgrading of Damaged Paved National Roads including Drainage Based on PMS/HDM-4 (Intermittent Sections), Sindangan - Liloy Road, a) K1941+000 to K1941+1000, b) K1955+771 to K1956+004, c) K1958+000 to K1959+002, Zamboanga del Norte | Zamboanga del Norte | 2015-06-03 | Final | Zamboanga del Norte 2nd DEO | LF | 33.487 | 251 | 2014-02-20 | 2014-10-28 | 0% | C | 0.436 | 0.135 | 0.3 | - | - | - | 87.1% | *87.1% Satisfactory
HEXAMINDZ CORPORATION (Formerly: Kilusang Magkaibigan M.P. Cooperative (KMMPC)) | 31666 | L | A | MA | GE | Construction of Bank Protection along Tagbalaobao River along Surigao-Davao Coastal | Comval Province | 2015-06-09 | 1st | Compostela Valley | LF | 1.86 | 183 | 2015-06-09 | 2015-12-08 | (+)12.92% | O | 0.31 | 0.249 | 0.15 | 0.03 | 0.056 | 0.033 | 82.8% | -
HEXAMINDZ CORPORATION (Formerly: Kilusang Magkaibigan M.P. Cooperative KMMPC) | 31666 | L | AA | MB | GE | Rehab. Of Pangasawan Bridge 1 along Surigao del Sur Boundary-Davao Oriental Coastal Road, Manay, Davao Oriental | Manay, Davao Oriental | 2015-11-10 | Final | Davao Oriental 1st DEO | LF | 3.798e-06 | 70 | 2015-02-16 | 2015-04-26 | -0.0449 | C | 0.5 | 0.2 | 0.165 | - | - | - | 86.5% | 86.5% Satisfactory
HEXAMINDZ CORPORATION (Formerly: Kilusang Magkaibigan M.P. Cooperative KMMPC) | 31666 | L | AAA | MB | GB | Construction of Multi-Purpose (Gym) and Repair and Improvement of Multi-Purpose (Gym), Municipality of Boston, Davao Oriental | Boston, Davao Oriental | 2015-11-10 | Final | Davao Oriental 1st DEO | LF | 4.796e-06 | 90 | 2015-02-18 | 2015-05-18 | -0.0452 | C | 0.486 | 0.2 | 0.164 | - | - | - | 85% | 85% Satisfactory
HEXAMINDZ CORPORATION (Formerly: Kilusang Magkaibigan M.P. Cooperative KMMPC) | 31666 | L | AA | MB | GE | Construction of Slope Protection Hijo River, Agusan-Davao Road, Mawab, Compostela Valley | Mawab, Compostela Valley | 2015-11-13 | Final | Compostela Valley DEO | LF | 1.857e-05 | 183 | 2015-02-18 | 2015-08-19 | 0 | C | 0.395 | 0.138 | 0.3 | - | - | - | 83.3% | 83.3% Satisfactory
Hexamindz Corporation (Formerly: Kilusang Magkaibigan M.P. Cooperative, KMMPC) | 31666 | L | A | MB | GE | Rehab./Reconst./Upgrading of Damaged Paved National Roads including drainage based on PMS/HDM-4 (Intermittent Sect.), Sindangan-Liloy Road a.) K1941+000 - K1941+1000, b.) K1955+771 - K1956+004, c.) K1958+000 - K1956+004 | Zamboanga del Norte | 2014-10-24 | 1st | IX | LF | 33.4866 | 237 | 2014-02-20 | 2014-10-14 | -4.5% | O | 0.191 | 0.221 | 0.105 | 0.03 | 0.045 | 0.033 | 62.5% | 62.50% Poor
Hexamindz Corporation (Formerly: Kilusang Magkaibigan M.P. Cooperative, KMMPC) | 31666 | L | A | MA | GE | Widening of Road along Daang Maharlika (Agusan-Davao) Road, Poblacion Section | Mawab, Comval Province | 2014-10-26 | 1st & Final | XI | LF | 16.8908 | 110 | 2014-01-20 | 2014-05-09 |  | C | 0.339 | 0.197 | 0.3 | - | - | - | 83.6% | 83.60% Satisfactory
Hexamindz Corporation (Formerly: Kilusang Magkaibigan M.P. Cooperative, KMMPC) | 31666 | L | A | MB | GB | Cluster IV - Construction of San Isidro E/S | Cateel, Davao Oriental | 2014-10-29 | 1st & Final | XI | LF | 4.5524 | 60 | 2014-05-14 | 2014-07-12 |  | C | 0.467 | 0.133 | 0.3 | - | - | - | 90% | 90.00% Very Satisfactory
Hexamindz Corporation (Formerly: Kilusang Magkaibigan M.P. Cooperative, KMMPC) | 31666 | L | A | MB | GE | Asphalt Overlay with Concrete Blocking of Balete Drive, K0010+(-740) - K0010+420 | Quezon City | 2014-08-16 | 1st & Final | NCR | LF | 10.8911 | 135 | 2014-01-30 | 2014-06-13 | 35.24 | C | 0.494 | 0.133 | 0.3 |  |  |  | 92.7 | 92.70% Very Satisfactory
HEXAMINDZ CORPORATION (Formerly: Kilusang Magkakaibigan M.P. Cooperative (KMMPC)) | 31666 | L | AA | MB | GE | Rehabilitation of Pangawasan Bridge 1 (B00112MN) Surigao del Sur Bdry - Davao Oriental Coastal Road, Manay, Davao Oriental | Surigao del Sur Bdry - Davao Oriental Coastal Road, Manay, Davao Oriental | 2015-08-25 | 1st & Final | Davao Oriental First DEO | LF | 3.799 | 152 | 2015-02-16 | 2015-07-17 | -1.02% | C | 0.491 | 0.122 | 0.269 | - | - | - | 88.2% | *88.2% Satisfactory
HG III Construction & Development Corporation |  | L |  |  | GE5 | Puerto Princesa Port Expansion Project | Palawan | 2012-12-06 | 2nd | PPA | LF | [5 empty] | O | 0.395 | 0.289 | 0.15 | 0.03 | 0.061 | 0.05 | 97.5 | -
HG III Construction and Development Corporation | 8431 | L | AAA |  |  | Land Development and Construction of Housing Units (Viejo People's Village) | Site 1, Brgy. Vista Alegre, Barotac Viejo, Iloilo/Region VI | 2015-10-03 | 1st | NHA | LF | 289.175 | 360 | 2015-01-12 | 2016-04-24 | 51.67 | O | 0.344 | 0.2645 | 0.15 | 0.02 | 0.0607 | 0.05 | 88.92 | -
HG III Construction and Development Corporation | 8431 | L | AAA | LB | GE-4 | New Bohol (Panglao) Airport Development Project | Pangalo, Bohol/Region VII | 2015-05-20 | 2nd & Final | DOTC | LF | 69.364 | 270 | 2014-05-15 | 2015-02-08 | 0 | C | 0.468 | 0.2 | 0.3 | - | - | - | 96.8 | 93.70% Very Satisfactory
HG III Construction and Development Corporation | 8431 |  | AAA |  |  | Viejo People's Village | Site 1, Brgy. Vista Alegre, Barotac Viejo, Iloilo | 2016-02-19 | 2nd & Final | NHA | LF | 289.111 | 360 | 2015-01-12 | 2016-04-24 | 14.71 | C | 0.4648 | 0.1781 | 0.3 | - | - | - | 94.29 | 90.53% V. Satisfactory
HGG Builders & Supply | 17824 | L |  | MA |  | Completion of Administration Building | GOA, Camarines Sur | 2014-11-12 | Final | DOST | L | 9.519 | 150 | 2012-12-28 | 2013-06-26 | 0 | C | 0.479 | 0.2 | 0.3 | - | - | - | 97.9 | 98.11% Outstanding
HGG Builders and Supply | 17824 | L | A | MA | GE | Construction of Drainage System/Protection Works along Maharlika, Cam. Sur 2nd LD, K0397+(-060)-K0397+700 | Libmanan, Camarines Sur | 2014-11-10 | 1st & Final | V | LF | 16.448 | 158 | 2014-03-03 | 2014-08-07 | 0% | C | 0.439 | 0.133 | 0.3 | - | - | - | 87.2% | 87.20% Satisfactory
HGG Builders and Supply | 17824 | L | A | MA | GE | Preventive Maintenance (Intermittent Section Arterial) along Rolando Andaya Highway a. K0305+042 to K035+1002 | Rolando Andaya Highway | 2014-11-09 | 1st & Final | V | LF | 14.7931 | 151 | 2014-03-18 | 2014-08-15 | 1.33% | C | 0.453 | 0.133 | 0.3 | - | - | - | 88.6% | 88.60% Satisfactory
HGG Builders and Supply | 17824 | L | A | MA | GB | Construction of Water Sanitation Facilities at Pamukid Elem. School | San Fernando, Camarines Sur | 2014-08-07 | 1st & Final | V | LF | 0.30336 | 60 | 2013-11-04 | 2014-01-02 | 0 | C | 0.47 | 0.133 | 0.3 |  |  |  | 90.3 | 90.30% Very Satisfactory
HGG Builders and Supply | 17824 | L | A | MA | GE | Construction of Line Canal with Slope Protection along Rolando Andaya Highway, Zone 2, Brgy. Lower Sta. Cruz | Ragay, Camarines Sur | 2014-08-06 | Final | V | LF | 1.4577 | 119 | 2013-05-17 | 2013-09-12 | 33.33 | C | 0.4 | 0.2 | 0.3 |  |  |  | 90 | 87.78% Satisfactory
HGG Builders and Supply | 17824 | L | A | MA | GE2 | Const. of Line Canal w/ Slope Protection along Rolando R. Andaya Highway Zone 2, Brgy. Lower Sta. Cruz | Ragay, Camarines Sur | 2013-08-03 | 1st | V | LF | 1.458 | 119 | 2013-05-17 | 2013-09-12 | 1.52 | O | 0.375 | 0.24 | 0.15 | 0.03 | 0.035 | 0.033 | 86.3 | -
HGG BUILDERS AND SUPPLY | 17824 | L | A | MB | GE | Cluster Projects: Concreting of Roads at Lupi, San Fernando, Camarines Sur | San Fernando, Camarines Sur | 2015-08-29 | 1st & Final | Camarines Sur First DEO | LF | 0.935 | 180 | 2015-03-11 | 2015-09-06 | 46.08% | C | 0.495 | 0.172 | 0.3 | - | - | - | 96.7% | *96.7% Outstanding
HGG BUILDERS AND SUPPLY | 17824 | L | A | MA | GE | Construction/Rehabilitation/Improvement of CLUPA- Calauag Flood Control, Calauag, Naga City | Calauag, Naga City | 2015-11-14 | Final | Camarines Sur Second DEO | LF | 9.163 | 162 | 2015-02-11 | 2015-07-23 | - | C | 0.452 | 0.122 | 0.3 | - | - | - | 87.4% | 87.4% Satisfactory
HGG BUILDERS AND SUPPLY | 17824 | L | A | MA | GE | Construction/Rehabilitation of Milnalabac Flood Control, Minalabac, Camarines Sur | Minalabac, Camarines Sur | 2015-11-12 | Final | Camarines Sur First DEO | LF | 4.4396 | 115 | 2015-04-03 | 2015-07-26 | 2.24% | C | 0.416 | 0.133 | 0.3 | - | - | - | 84.9% | 84.9% Satisfactory
HGIII Construction | 3368 | L | AAA | LB |  | Rehabilitation/Upgrading of West Breakwater | Manila Bay, South Harbor, Manila | 2015-01-28 | 2nd & Final | PPA | L | 129.331 | 420 | 2013-12-14 | 2015-02-11 | 0 | C | 0.4643 | 0.2 | 0.3 | - | - | - | - | 97.33% Outstanding
HG-III Construction & Development Corporation | 8431 | L | AAA | LB |  | New Bohol (Pangalao) Airport Construction and Sustainable Environment Protection Project | Panglao, Bohol | 2014-11-13 | 1st | DOTC | LF | 65.748 | 240 | 2014-05-15 | 2015-01-09 | 0.18 | C | 0.39 | 0.3 | 0.15 | 0.02 | 0.014 | 0.05 | 92.4 | -
HG-III Construction & Development Corporation | 8431 | L | AAA | LB | GE5 | Rehabilitation/Upgrading of West Breakwater | South Harbor, Manila | 2014-06-27 | 1st | PPA | LF | 129.331 | 420 | 2013-12-19 | 2015-02-11 | 43.891 | O | 0.398 | 0.3 | 0.15 | 0.03 | 0.0513 | 0.05 | 97.93 | -
HG-III Construction and Development Corporation | 8431 |  |  | LB |  | Puerto Princesa Port Extension Project | Puerto Princesa, Palawan/ Region 4A | 2016-07-08 | 1st | PPA | LF | 309.389 | 480 | 2015-08-17 | 2016-12-08 | 9.455 | O | 0.3969 | 0.266 | 0.15 | 0.03 | 0.07 | 0.05 | 96.29 | -
HG-III Construction and Development Corporation | 8431 |  |  | LB |  | Puerto Princesa Port Expansion Project | Port of Puerto Princesa, Palawan | 2016-10-19 | 2nd & Final | PPA | LF | 309.389 | 480 | 2015-08-17 | 2016-12-08 | 4.588 | C | 0.4854 | 0.2 | 0.3 | - | - | - | 98.54 | 97.19% Outstanding
HG-III Construction and Development Corporation | 8431 |  | AAA |  |  | Supply of Labor and Materials Tools Equipment and Tech. Supervision for the Construction of Mainroad from MIRDC to Gen. Santos Avenue | NCR | 2016-12-07 | 1st & Final | DOST | LF | 9.484 | 115 | 2016-03-14 | 2016-07-06 | 0 | C | 0.48 | 0.2 | 0.3 | - | - | - | 98 | *98.00% Outstanding
HG-III Construction and Development Corporation |  | L | AAA |  | GE5 | Puerto Princesa Port Expansion Project | Port of Puerto Princesa, Palawan | 2013-06-21 | 3rd & Final | PPA | L | 290.489 | 540 | 2012-02-07 | 2013-07-30 | 4.89 | C | 0.496 | 0.2 | 0.3 | - | - | - | 99.6 | 95.39% Very Satisfactory
HG-III Construction and Development Corporation |  | L | AAA |  | GE5 | Puerto Princesa Port Expansion Project | Port of Puerto Princesa, Palawan | 2012-06-29 | 1st | PPA | LF | 290.489 | 540 | 2012-02-07 | 2013-07-30 | 45.968 | O | 0.3049 | 0.2995 | 0.15 | 0.03 | 0.06 | 0.033 | 87.74 | -
HGW = 3 Engineering & Construction | 34574 | L | D |  |  | Perimeter Fence & Gates PSHS CARC | Irisan, Baguio City | 2014-12-17 | 1st & Final | DOST | L | 9.442 | 231 | 2014-01-03 | 2014-08-21 | -1.27 | C | 0.489 | 0.2 | 0.2619 | - | - | - | 95.09 | 95.09 Very Satisfactory
HIGH INNOVATIVE CONSTRUCTION & DEVELOPMENT PHILS. CORP. (Formerly: JV Loreto Construction & Development Corp.) | 13120 | L | A | MB | GE | Construction of Palo West By-Pass Road, Including Bridge, Pawing-Campetic-Guindapunan-San Jose Arado, (Sta. 0+000-Sta. 2+956.19, with Exception), Palo, Leyte | Palo, Leyte | 2015-11-10 | 1st | Regional Office No. VIII | LF | 135.9131 | 389 | 2015-03-02 | 2016-03-24 | (+)12.95 | OG | 0.381 | 0.236 | 0.15 | 0.03 | 0.056 | 0.05 | 90.3% | 90.3% Very Satisfactory
High Strength Dev. Corporation | 31976 | L | A | SB | GE1 | Construction of Bantog-Balbaloto, FMR |  | 2009-05-22 | 1st | III |  | 1.879 | 79 |  |  |  | O | 0.294 | 0.3 | 0.15 | 0.02 | 0.03 | 0.05 | 84.4 | -
High Strength Development Corporation | 31976 | L | A | MA | GE | Preventive Maintenance along Tarlac - Sta. Rosa Road a.) K0136+(-045) - K0136+715 (Modified to : K0146+(-440.50) - K0147+627.50) | Tarlac | 2014-08-07 | 1st & Final | III | LF | 8.3557 | 30 | 2012-06-14 | 2012-07-13 | 3.33 | C | 0.335 | 0.198 | 0.3 |  |  |  | 83.3 | 83.30% Satisfactory
Hi-Tone Construction & Development Coporation | 23385 | L | AAA | LA |  | San Andres Port Development Project | San Andres, Catanduanes/ Region V | 2014-06-09 | 1st | DOTC | LF | 48.274 | 240 | 2013-03-29 | 2014-09-23 | 3.35 | O | 0.3283 | 0.3 | 0.15 | 0.03 | 0.035 | 0.05 | 89.33 | -
Hi-Tone Construction & Development Corporation | 23385 | L | AAA | LA | GE-5 | San Andres Port Development Project | San Andres, Catanduanes/ Region V | 2014-09-25 | 2nd & Final | DOTC | LF | 48.274 | 315 | 2013-03-29 | 2014-09-25 | 0 | C | 0.4592 | 0.2 | 0.3 | - | - | - | 95.92 | 91.97% Very Satisfactory
Hi-Tone Construction & Development Corporation | 8784 | L |  | LB |  | Construction of RC Wharf | Port of Masbate, Masbate City | 2014-10-23 | 2nd & Final | PPA | LF | 79.105 | 433 | 2013-06-18 | 2014-08-24 | 3.844 | C | 0.449 | 0.2 | 0.3 | - | - | - | - | 92.24% Very Satisfactory
Hi-Tone Construction & Development Corporation | 8784 | L |  |  |  | Construction of RC Wharf | Port of Masbate, Masbate City | 2014-06-20 | 1st | PPA | LF | 79.105 | 433 | 2013-06-18 | 2014-08-24 | -9.246 | O | 0.3972 | 0.3 | 0.0575 | 0.03 | 0.07 | 0.05 | 90.47 | -
Hi-Tone Construction & Development Corporation (Formerly: Lo-Tone Const. Supply) | 23385 | L | AAA | LA | GB1 | Corollary Works at Tagaytay Resettlement Project |  | 10/26-29/09 | 2nd | NHA |  | 19.985 | 120 |  |  |  | O | 0.3896 | 0.3 | 0.1284 | 0.03 | 0.056 | 0.033 | 93.7 | -
Hi-Tone Construction and Development (Formerly: Lo-Tone Constructio & Supply) | 23385 | L | AAA | MB | GE | Camarines Sur-Albay Diversion Road (San Fernando-Oas-Daraga Section of the Pan Philippine Highway (PPH) including Bridges, Albay Side, Road Opening/Upgrading of Caguiba-Bongabong-Taladong (Jct. National Road)-Comon-Inarado-Gapo-Dinoronan-Tabon-Tabon Section | Camalig & Daraga, Albay | 2014-08-16 | 1st | V | LF | 85.6755 | 313 | 2014-01-01 | 2014-11-09 | -3.47 | OG | 0.328 | 0.3 | 0.115 | 0.022 | 0.042 | 0.033 | 84 | -
Hi-Tone Construction and Development Corporation | 23385 | L | AAA | MB | GE1 | Road Upgrading (Gravel to Paved) Catanduanes Circ. Road, K0130+845-K0133+100, Mabini-San Jose Sect. | Caramoran, Catanduanes | 2011-08-16 | 1st | V | LF | 44.102 | 240 | 2011-07-04 | 2012-02-28 | 3 | O | 0.374 | 0.061 | 0.15 | 0.03 | 0.042 | 0.033 | 69 | -
Hi-Tone Construction and Development Corporation | 23385 | L | AAA | LB |  | Rehabilitation/ Upgrading of Damaged Wharf | Legazpi Baseport, Legazpi City, Albay, Region V | 2016-12-08 | 1st | PPA | LF | 154.702 | 480 | 8/24/15 | 12/15/16 | -62.25 | O | 0.4 | 0.3 | 0 | 0.03 | 0.065 | 0.033 | 82.8 | -
Hi-Tone Construction and Development Corporation (Formerly: Lo-Tone Construction & Supply) | 23385 | L | AAA | MA | GE2 | Rehab./Repair of Flood Control System Yawa River, Bogtong Sect., Bogtong | Legazpi City | 2013-08-10 | Final | V | LF | 9.682 | 90 | 2013-01-09 | 2013-04-08 | 0 | C | 0.462 | 0.133 | 0.3 | - | - | - | 89.5 | 86.14% Satisfactory
Hi-Tone Construction and Development Corporation (Formerly: Lo-Tone Construction & Supply) | 23385 | L | AAA | MB | GE2 | Rehab./Repair of Flood Control System Yawa River, Bogtong Sect., Bogtong | Legazpi City | 2013-03-16 | 1st | V | LF | 9.682 | 90 | 2013-01-09 | 2013-04-08 | 0.36 | O | 0.332 | 0.227 | 0.15 | 0.03 | 0.05 | 0.05 | 83.9 | -
Hi-Tone Construction and Development Corporation (Formerly: Lo-Tone Construction & Supply) | 23385 | L | AAA | MA | GE | Construction/Improvement of Yawa River Control Bogtong-Rawis Section | Legaspi City | 2014-11-15 | 1st & Final | V | LF | 45.7392 | 214 | 2014-10-18 | 2015-05-19 | 8.88% | C | 0.428 | 0.133 | 0.3 | - | - | - | 86.1% | 86.10% Satisfactory
Hi-Tone Construction and Development Corporation (Formerly: Lo-Tone Construction & Supply) | 23385 | L | AAA | MA | GE | Rehabilitation of Flood Control System along Lower Mabinit River | Legaspi City | 2014-11-15 | 1st & Final | V | LF | 15.9798 | 147 | 2014-11-05 | 2015-03-31 | 1.37% | C | 0.416 | 0.133 | 0.3 | - | - | - | 84.9% | 84.90% Satisfactory
Hi-Tone Construction and Development Corporation (Formerly: Lo-Tone Construction & Supply) | 23385 | L | AAA | MB | GE1 | Rehab./Impv't. of Bariw-Alimsog Rd. (Bariw Sect.) & Buhatan-Alimsog Rd. (Alimsog Sect.) | Sto. Domingo, Albay | 2013-03-18 | Final | V | LF | 1.42 | 140 | 2011-12-30 | 2012-05-17 | 7.86 | C | 0.396 | 0.2 | 0.3 | - | - | - | 89.6 | 87.02% Satisfactory
Hi-Tri Development Corporation | 1758 | L | AAA | LA | GE2 | Const. of Flood Control/Drainage Structures along Bogo-Curva-Medellin-Daanbantayan Rd., Paypay & Bitoon Sect., Daanbantayan & San Remegio | Cebu | 2013-08-10 | Final | VII | LF | 8.645 | 120 | 2012-09-28 | 2013-01-25 | 37.5 | C | 0.375 | 0.2 | 0.3 | - | - | - | 87.5 | 85.94% Satisfactory
Hi-Tri Development Corporation | 1758 | L | AAA | LA | GE2 | Const. of Flood Control/Drainage Structures along Bogo-Curva-Medellin-Daanbantayan Rd., Paypay & Bitoon Sect., Daanbantayan & San Remegio | Cebu | 2012-11-27 | 1st | VII | LF | 8.645 | 120 | 2012-09-28 | 2013-01-25 | 24.25 | O | 0.334 | 0.24 | 0.15 | 0.03 | 0.045 | 0.05 | 84.9 | -
Hi-Tri Development Corporation | 1758 | L | AAA | LB | GE1 | Rehab./Reconst./Upgrading Int. Sect. along Biliran-Cagayan de Oro-Iligan Rd. (BCIR) Sugbongcogon Sect. | Misamis Oriental | 2013-08-21 | Final | X | LF | 100.248 | 420 | 2011-12-22 | 2013-02-13 | 10.48 | C | 0.361 | 0.133 | 0.3 | - | - | - | 79.4 | 83.62% Satisfactory
Hi-Tri Development Corporation | 1758 | L | AAA | LB | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rd. (IS) along Biliran-Cagayan de Oro-Iligan Road (BCIR), Sugbongcogon Sect. | Misamis Oriental | 2012-11-21 | 3rd | X | LF | 100.248 | 420 | 2011-12-22 | 2013-02-13 | 1.32 | O | 0.364 | 0.239 | 0.15 | 0.03 | 0.055 | 0.033 | 87.1 | -
Hi-Tri Development Corporation | 1758 | L | AAA | LB | GE1 | Rehab./Reconst./Upgrading along Butuan-Cagayan de Oro-Iligan Rd. (BCIR), Sugbongcogon Sect., K1363+000 - K1376+704.25 with exception | Misamis Oriental | 2012-08-13 | 2nd | X | LF | 100.248 | 390 | 2011-12-22 | 2013-01-14 | 0.79 | O | 0.255 | 0.3 | 0.15 | 0.03 | 0.05 | 0.05 | 83.5 | -
Hi-Tri Development Corporation | 1758 | L | AAA | LB | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Roads Generated From HDM-4 (IS) along Butuan-Cagayan de Oro-Iligan Road (BCIR), Sugbongcon Sect., K1363+000-K1376+704.25 w/ exception | Misamis Oriental | 2012-03-29 | 1st | X | LF | 100.248 | 360 | 2011-12-22 | 2012-12-15 | 17.35 | O | 0.363 | 0.24 | 0.15 | 0.03 | 0.06 | 0.05 | 89.3 | -
Hi-Tri Development Corporation | 1758 | L | AAA | LB | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rd. (In. Sect.): Butuan City-Cagayan de Oro City-Iligan City Rd., Tagbocboc-Balingoan-Esperanza Sect. | Misamis Oriental | 2013-08-21 | Final | X | LF | 79.201 | 300 | 2012-04-03 | 2013-01-27 | 9 | C | 0.392 | 0.133 | 0.3 | - | - | - | 82.5 | 83.32% Satisfactory
Hi-Tri Development Corporation | 1758 | L | AAA | LB | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rd. (IS): Butuan City-Cagayan de Oro City-Iligan City R., Tagbocboc-Balingoan-Esperanza Sect. | Misamis Oriental | 2012-11-21 | 1st | X | LF | 79.201 | 300 | 2012-04-03 | 2013-01-27 | 6.87 | O | 0.321 | 0.238 | 0.15 | 0.03 | 0.05 | 0.033 | 82.2 | -
Hi-Tri Development Corporation | 1758 |  |  |  |  | Const./Road Opening of Zamboanga West Coast Rd., Sirawai-Sibuco Rd., Sitio Sibongon-Bato Tindog Sect. |  | 2010-08-24 |  | IX |  | 373.45 | 600 |  |  |  | O | 0.355 | 0.283 | 0.15 | 0.023 | 0.042 | 0.033 | 88.6 | -
Hi-Tri Development Corporation | 1758 | L | AAA | LB | GE1 | Upgrading/Concrete Paving of Dipolog-Punta-Dansullan Sergio Osmeña Zamboanga del Norte / Zamboanga del Sur Bdry. | Zamboanga del Norte | 2012-08-23 | 1st | IX | LF | 80.802 | 290 | 2012-04-02 | 2013-01-17 | 9.6 | O | 0.367 | 0.3 | 0.15 | 0.03 | 0.032 | 0.033 | 91.2 | -
HI-TRI DEVELOPMENT CORPORATION | 1758 | L | AAA | LA | GE | Construction/Upgrading/Rehabilitation of Drainage along National Roads at Cebu North Hagnaya Wharf Road, K0008+715 - K0011+015 (Right Side) | Mandaue City, Cebu | 2015-09-04 | 1st | Cebu 6th | LF | 44.922 | 417 | 2015-03-30 | 2016-05-19 | 14.1% | O | 0.375 | 0.239 | 0.15 | 0.03 | 0.04 | 0.05 | 88.4% | -
Hi-Tri Development Corporation | 1758 |  | AAA |  |  | Procurement of Fully Developed Lots and Complete Housing Units (572 Units) | Brgy. Timpas, Panit-an, Capiz | 2015-07-09 | 1st | NHA | LF | 165.835 | 285 | 2015-04-17 | 2016-09-28 | -38.17 | O | 0.3825 | 0.3 | 0 | 0.03 | 0.047 | 0.033 | 79.25 | -
HKP CONSTRUCTION AND SUPPLY | 34274 | L | D | SB | GE | Rehabilitation /Reconstruction/Upgrading of Damaged Paved National Roads Including Drainage Based on Pavement Management System/Highway Development and Management 4 (HDM-4) (Intermittent Sections) along Masbate-Milagros Road a. K0023+691-K0024+000 b. K0025+580- K0025+644, Milagros, Masbate | Milagros, Masbate | 2015-09-04 | 1st & Final | Masbate First | LF | 6.694 | 83 | 2015-06-09 | 2015-08-30 | - | C | 0.432 | 0.133 | 0.3 | - | - | - | 86.5% | *86.5% Satisfactory
HLJ Construction & Enterprises | 18080 | L | A |  |  | Completion of Dormitory Building | Irisan, Baguio City | 2014-12-17 | 1st & Final | DOST | L | 17.188 | 345 | 2014-01-03 | 2014-12-14 | 1 | C | 0.454 | 0.2 | 0.27 | - | - | - | 92.4 | 92.40% Very Satisfactory
HLJ Construction & Enterprises | 18080 | L | A | MA | GE | Const./Widening//Upgrading/Rehab. Of Access Road to Declared Tourism Destination Brgy. Punta Taytay | Bacolod City, Negros Occidental | 2014-08-11 | Final | VI | LF | 48.1053 | 180 | 2013-02-19 | 2013-08-17 | 0 | C | 0.395 | 0.2 | 0.3 |  |  |  | 89.5 | 85.96% Satisfactory
HLJ Construction & Enterprises | 18080 | L | A | MA | GB | Const. of DepEd Standard Type School Building at Bulwagan NHS, Hinoba-an, Negros Occidental | Hinoba-an, Negros Occidental | 2014-08-09 | Final | VI | LF | 2.8424 | 85 | 2013-05-24 | 2013-08-16 | 0 | C | 0.413 | 0.2 | 0.3 |  |  |  | 91.3 | 88.50% Satisfactory
HLJ Construction & Enterprises | 18080 | L |  |  | GE2 | Tabuc Norte PCIP | Panitan, Capiz / Region VI | 2013-10-19 | 1st | NIA | L | 10.085 | 180 | 2012-12-19 | 2013-06-16 | -44.85 | O | 0.3235 | 0.1624 | 0 | 0.018 | 0.025 | 0 | 52.89 | -
HLJ Construction & Enterprises | 18080 | L | A | MA | GE | Reconstruction of Martilo Bridge | La Libertad, Negros Oriental | 2014-08-15 | Final | VII | LF | 12.2973 | 222 | 2013-04-03 | 2013-11-10 | 0 | C | 0.479 | 0.147 | 0.3 |  |  |  | 92.6 | 89.18% Very Satisfactory
HLJ Construction & Enterprises | 18080 | L | A | MA | GE | Reconstruction of Habag Bridge | La Libertad, Negros Oriental | 2014-08-15 | Final | VII | LF | 12.0499 | 258 | 2013-02-09 | 2013-10-25 | 0 | C | 0.49 | 0.143 | 0.3 |  |  |  | 93.3 | 88.74% Satisfactory
HNR Construction and Supply | 22085 | L | B | MA | GE-1 | Roxas Airport Development Project | Brgy. Baybay, Roxas City, Capiz/ Region VI | 2014-09-24 | 1st & Final | DOTC | LF | 23.27 | 120 | 2014-04-11 | 2014-09-29 | 5.82 | C | 0.4336 | 0.2 | 0.3 | - | - | - | 93.36 | 93.36 Very Satisfactory
Homefixmix Builders Center | 29997 | L | D | SB | GE2 | Repair/Maint. (Existing Drainage/Flume) of Concrete Flume along MNR, K0269+000-K0270+700 w/ exception | San Fernando City, La Union | 2013-07-29 | 1st | I | LF | 3.764 | 120 | 2013-04-19 | 2013-08-16 | 2 | O | 0.389 | 0.24 | 0.15 | 0.03 | 0.037 | 0.033 | 87.9 | -
Homeflix Builders Center | 29997 | L | D | SB | GE | Repair/Maintenance (Existing Drainage/Flume) of Concrete Flume along Manila North Road K0269+000 - K0270+700 w/ exception | San Fernando City, La Union | 2014-08-04 | Final | I | LF | 3.9012 | 125 | 2013-04-19 | 2013-08-21 | 0.8 | C | 0.417 | 0.133 | 0.3 |  |  |  | 85 | 86.74% Satisfactory
Homeworld Construction Corp. (Formerly: Homeworld Engineering) | 14725 | L | A | MA | GE1 | Prev. Maint. (Int. Sect.) along Binalbagan-Isabela Rd. a)K0064+000-K0064+511, b)K0064+866-K0064+1250, c)K0067+034-K0067+200, d)K0068+342-K0068+426, e)K0072+000-K0072+695 | Binalbagan, Negros Occidental | 2013-08-10 | Final | VI | LF | 17.85 | 115 | 2013-01-28 | 2013-05-22 | 0 | C | 0.471 | 0.133 | 0.3 | - | - | - | 90.4 | 85.90% Satisfactory
Homeworld Construction Corporation | 14725 | L | A | MA | GE1 | Prev. Maint. (Int. Sect.) along Binalbagan-Isabela Rd., a)K0064+000-K0064+511, b)K0064+866-K0064+1250, c)K0067+034-K0067+200, d)K0068+342-K0068+426, e)K0072+000-K0072+695 | Binalbagan, Negros Occidental | 2013-03-12 | 1st | VI | LF | 16.23 | 92 | 2013-01-28 | 2013-04-29 | -4.06 | O | 0.338 | 0.297 | 0.109 | 0.022 | 0.03 | 0.033 | 82.9 | -
Homeworld Engineering | 14725 | L | B | MA | GE1 | Rehab./Reconst. of Damaged Paved Nat'l Roads Generated from PMS/HDM-4, Sum-ag-Abuanan Road |  | 2009-03-05 | 2nd | VI |  | 31.087 | 471 |  |  |  | O | 0.266 | 0.281 | 0.15 | 0.03 | 0.06 | 0.05 | #VALUE! | -
Honeyville Construction | 32160 | L | B | MA | GE | Individual Project Road Concreting, San Isidro-San Vicente | Buhi, Camarines Sur | 2014-11-12 | 1st & Final | V | LF | 9.1855 | 90 | 2014-03-21 | 2014-06-18 | 0% | C | 0.45 | 0.14 | 0.3 | - | - | - | 89% | 89.00% Satisfactory
Honeyville Construction | 32160 | L | B | MB | GE | Drainage Improvement along Trabajo Street (J.P.Rizal going to Pasig River), District I | Makati City, Metro Manila | 2014-11-19 | 1st | NCR | LF | 10.006 | 150 | 2014-07-31 | 2014-12-27 | 0.48% | O | 0.363 | 0.225 | 0.15 | 0.03 | 0.04 | 0.033 | 84.1% | 84.10% Satisfactory
Honeyville Construction | 32160 | L | A | MB |  | CONSTRUCTION OF OCINI CIS & HUYON-HUYON CIP | Tigaon, Camarines Sur | 2015-04-17 | 1st & Final | NIA | L | 18.823 | 180 | 2014-07-16 | 2014-01-11 | -3 | C | 0.4107 | 0.2 | 0.21 | - | - | - | - | 82.07% Satisfactory
Honeyville Construction | 32160 | L | C | SB | GE1 | Impvt. of San Rafael-Mampirao-San Jose Road, (Pugay-Mampirao Section) |  | 2009-05-30 | 1st | V |  | 18.817 | 215 |  |  |  | O | 0.335 | 0.3 | 0.15 | 0.03 | 0.04 | 0.05 | 90.5 | -
Honeyville Construction | 32160 | L | B | MA | GE1 | Impvt. of Goa-Digdigon-San Isidro Road, San Isidro Section |  | 2009-09-09 | 1st | V |  | 18.788 | 195 |  |  |  | O | 0.313 | 0.278 | 0.15 | 0.03 | 0.047 | 0.05 | 86.8 | -
HONEYVILLE CONSTRUCTION | 32160 | L | A | MB | GE | Construction/Upgrading/Rehabilitation of Drainage along GSO Road, K0125+250 to K0125+974, Olongapo City | Olongapo City | 2015-06-07 | 1st | Zambales 2nd DEO | LF | 18.081 | 195 | 2015-01-16 | 2015-07-29 | 7.53% | O | 0.354 | 0.3 | 0.15 | 0.024 | 0.042 | 0.05 | 92% | -
HONEYVILLE CONSTRUCTION | 32160 | L | A | MB | GE | Construction/Upgrading/Rehabilitation of Damaged Paved, Marikina - Infanta Road, K0028+760 to K0029+637.40 | Antipolo City, Rizal | 2015-06-02 | Final | Rizal 1st DEO | LF | 14.392 | 120 | 2015-01-29 | 2015-05-28 | 18.33% | C | 0.479 | 0.133 | 0.3 | - | - | - | 91.2% | *91.2% Very Satisfactory
HONEYVILLE CONSTRUCTION | 32160 | L | A | MB | GE | Construction of River Wall along Meycauayan River, Poblacion to Banga (Right Side), Phase 1, Sta. 01+805.60-Sta. 01+964.40, Meycauayan, Bulacan | Sta. 01+805.60-Sta. 01+964.40, Meycauayan, Bulacan | 2015-08-30 | 1st & Final | Bulacan Second DEO | LF | 29.384 | 170 | 2014-08-28 | 2015-02-13 | - | C | 0.42 | 0.133 | 0.3 | - | - | - | 85.3% | *85.3% Satisfactory
HONEYVILLE CONSTRUCTION | 32160 | L | A | MB | GE | Improvement of Culiat Creek (Commonwealth to Visayas Avenue), Brgy. Vasra, Quezon City | Brgy. Vasra, Quezon City | 2015-12-09 | 1st | QC 1st DEO | LF | 17.37 | 240 | 2015-08-13 | 2016-04-08 | (+)24.57% | OG | 0.35 | 0.225 | 0.15 | 0.03 | 0.029 | 0.05 | 83.4% | 83.4% Satisfactory
Hony Trading and Construction | 26898 | L | B | MA | GE | Construction of Slope Protection with Gabions as Foundation along Buli Creek (Villa Alegre), Pinagbuhatan, Pasig City, Sta. 0+000 to Sta. 0+562.57 | Pasay City | 2014-11-29 | 1st & Final | NCR | LF | 9.3465 | 180 | 2014-02-05 | 2014-08-03 | 0% | C | 0.431 | 0.133 | 0.3 | - | - | - | 86.4% | 86.40% Satisfactory
Hony Trading and Construction | 26898 | L | B | MA | GE | Slope Protection/Bank Improvement of Merville Creek Phase II, Barangay Sun Valley | Parañaque City, M.M. | 2014-11-19 | 1st & Final | NCR | LF | 8.6621 | 180 | 2014-02-21 | 2014-08-19 | 2% | C | 0.439 | 0.133 | 0.3 | - | - | - | 87.2% | 87.20% Satisfactory
HONY TRADING AND CONSTRUCTION | 26898 | L | B | MA | GE | Rehabilitation of Road, Olalia Road, Barangay Sta. Cruz | Antipolo City, Rizal | 2015-06-02 | Final | Rizal 1st DEO | LF | 6.501 | 90 | 2015-02-03 | 2015-05-03 | 27.78% | C | 0.382 | 0.15 | 0.3 | - | - | - | 83.2% | *83.2% Satisfactory
Horamabi Builders | 24129 | L | A | MA | GB1 | Const. of Two (2) CL Units, Three (3) CL Sch. Bldg. @ Payangan E/S | Dinalupihan, Bataan | 2011-04-01 | 1st | III | LF | 4.473 | 150 | 2011-01-04 | 2011-06-02 | 20.68 | O | 0.369 | 0.3 | 0.15 | 0.03 | 0.029 | 0.033 | 91.1 | -
Horamabi Builders | 24129 | L | A | MA | GE1 | Improvement/Rehabilitation of Roman Expressway |  | 2009-05-21 | 1st | III |  | 39.3288 | 90 |  |  |  | O | 0.348 | 0.3 | 0.15 | 0.03 | 0.037 | 0.05 | 91.5 | -
HORAMABI BUILDERS | 24129 | L | AAA | MA | GE | Cluster 2: Rehabilitation of River Control Projects, Bataan 2nd District, Talisay RC (Diwa & Nagwaling Section); Tenejero RC (Tenejero-Ibayo Section); and Tenejero RC (Maite Section), Tenejero, Bataan | Tenejero, Bataan | 2015-08-28 | 1st & Final | Bataan Second DEO | LF | 1.91 | 149 | 2014-12-29 | 2015-05-26 | - | C | 0.444 | 0.2 | 0.3 | - | - | - | 94.4% | *94.4% Very Satisfactory
HOUSEROCK BUILDERS & TRADING | 18822 | L | C | MB | GE | Local Infrastructure Program-Construction of Multi-Purpose Building, Brgy. 149 and 150 Zone 13, Manila City 2nd LD | Brgy. 149 and 150 Zone 13, Manila City 2nd LD | 2015-12-11 | Final | North Manila DEO | LF | 6.1215 | 238 | 2015-03-24 | 2015-11-19 | 0.00% | C | 0.481 | 0.133 | 0.3 | - | - | - | 91.4% | 91.4% Very Satisfactory
HPL Construction | 22289 | L | B | MA | GE | Widening/Improvement of DVSR (Mission-Sta. Ana Section) | Sta. Ana, Cagayan | 2012-08-05 | Final | II | LF | 44.6943 | 194 | 2012-10-22 | 2013-05-03 | 1.39 | C | 0.281 | 0.2 | 0.21 |  |  |  | 69.1 | 76.34% Unsatisfactory
HPL Construction | 22289 | L | B | MA | GE | Replacement of Naddungan Bridge No.2 along Magapit-Capissayan Road, Gattaran Section | Gattaran, Cagayan | 2014-08-05 | Final | II | LF | 20.018 | 285 | 2012-03-10 | 2012-12-19 | 0 | C | 0.412 | 0.2 | 0.026 |  |  |  | 63.8 | 72.74% Poor
HPL Construction | 22289 | L | B | MA | GE | Widening/Improvement of Dugo-San Vicente Road | Buguey, Cagayan | 2014-08-04 | Final | II | LF | 34.5438 | 194 | 2013-03-01 | 2013-09-10 | 0 | C | 0.3 | 0.195 | 0.21 |  |  |  | 70.5 | 69.30% Poor
HPL Construction | 22289 | L | B | MA | GE | Road Upgrading (Gravel to Paved) Junciton Magapit-Capissayn Road, Sta 557+932 to Sta. 561+616 (K0558+000 to K0561) with exception | Lal-lo, Cagayan | 2014-08-06 | Final | II | LF | 45.889 | 194 | 2013-02-22 | 2013-09-03 | 0 | C | 0.388 | 0.2 | 0 |  |  |  | 58.8 | 66.90% Poor
HPL General Construction | 22289 | L | B | MA | GE1 | Widening/Impv't. of DSVR (Mission-Sta. Ana Sect.) | Sta. Ana, Cagayan | 2013-07-31 | 3rd | II | LF | 44.694 | 179 | 2012-10-22 | 2013-04-18 | -31.57 | O | 0.359 | 0.239 | 0 | 0.03 | 0.047 | 0.033 | 70.8 | -
HPL General Construction | 22289 | L | B | MA | GE1 | Widening/Impv't. of Dugo-San Vicente Rd. | Buguey, Cagayan | 2013-07-31 | 1st | II | LF | 33.045 | 179 | 2013-03-01 | 2013-08-27 | -50.26 | O | 0.356 | 0.237 | 0 | 0.03 | 0.045 | 0.017 | 68.5 | -
HPL General Construction | 22289 | L | B | MA | GE | Construction of Flood Control Mitigation Structures and Drainage System along Cagayan River Basin, Cagayan Vallet 1st LD | Lal-lo, Cagayan | 2014-10-21 | 1st | II | LF | 28.842 | 150 | 2014-02-03 | 2014-07-02 | -5% | O | 0.305 | 0.3 | 0.1 | 0.03 | 0.028 | 0.033 | 79.6% | 79.60% Unsatisfactory
HPL General Construction | 22289 | L | B | MA | GE1 | Replacement of Naddungan Bridge No.2 along Magapit-Capissayan Rd., Gattaran Sect. | Gattaran, Cagayan | 2013-07-30 | 3rd | II | LF | 20.018 | 292 | 2012-03-10 | 2012-12-20 | -4.15 | O | 0.332 | 0.3 | 0 | 0.03 | 0.054 | 0.033 | 74.9 | -
HPL General Construction | 22289 | L | B | MA | GE1 | Replacement of Naddungan Bridge #2 along Magapit-Capissayan Rd., Gattaran Sect. | Gattaran, Cagayan | 2013-03-12 | 2nd | II | LF | 20.018 | 285 | 2012-03-10 | 2012-12-20 | - | O | 0.357 | 0.24 | 0 | 0.03 | 0.056 | 0.05 | 73.3 | -
HPL General Construction | 22289 | L | B | MA | GE1 | Replacement of Naddungan Bridge #2 along Magapit-Capissayan Rd., Gattaran Sect. | Gattaran, Cagayan | 2012-11-24 | 1st | II | LF | 20.018 | 255 | 2012-03-10 | 2012-12-20 | -5.04 | O | 0.387 | 0.281 | 0.1 | 0.03 | 0.048 | 0.033 | 87.9 | -
HPL General Construction | 22289 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Paved) Jct. Magapit-Capissayan Rd., Sta.557+932-Sta.561+616 (K0558+000-K0561+880) w/ exception | Lal-lo, Cagayan | 2013-07-31 | 1st | II | LF | 43.874 | 179 | 2013-02-22 | 2013-08-19 | -15.7 | O | 0.369 | 0.236 | 0 | 0.03 | 0.055 | 0.033 | 72.3 | -
HPL General Construction | 22289 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Paved) Sta.564+520-Sta.568+435 (K0565+059-K0569+226) Jct. Magapit-Capissayan Rd. w/ exception | Gattaran, Cagayan | 2013-07-31 | 1st | II | LF | 33.674 | 179 | 2013-02-22 | 2013-08-19 | -45.15 | O | 0.349 | 0.24 | 0 | 0.03 | 0.049 | 0.033 | 70.1 | -
HPL General Construction | 22289 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Paved), K0582+085-K0584+200, Jct. Gattaran-Cumao-Capissayan-Sta. Margarita, Bolos Point Rd. | Baggao, Cagayan | 2013-07-30 | 1st | II | LF | 30.035 | 179 | 2013-02-22 | 2013-08-19 | -54.16 | O | 0.331 | 0.24 | 0 | 0.03 | 0.054 | 0.017 | 67.2 | -
HPL General Construction | 22289 | L | B | MA | GE2 | Const. of Chico River Flood Control Proj. along Cagayan-Apayao Rd. | Piat, Cagayan | 2013-08-02 | Final | II | LF | 18.794 | 240 | 2012-09-14 | 2013-05-11 | - | C | 0.45 | 0.133 | 0.262 | - | - | - | 84.5 | 85.10% Satisfactory
HPL General Construction | 22289 | L | B | MA | GE2 | Const. of Chico River Flood Control Project along Cagayan-Apayao Rd. | Piat, Cagayan | 2013-03-12 | 2nd | II | LF | 18.794 | 240 | 2012-09-14 | 2013-05-11 | 2.59 | O | 0.267 | 0.3 | 0.15 | 0.03 | 0.051 | 0.033 | 83.1 | -
HPL General Construction | 22289 | L | B | MA | GE2 | Const. of Chico River Flood Control Project along Cagayan Apayao Rd. | Piat, Cagayan | 2012-11-25 | 1st | II | LF | 18.794 | 240 | 2012-09-17 | 2013-05-14 | 2.17 | O | 0.378 | 0.24 | 0.15 | 0.03 | 0.048 | 0.033 | 87.9 | -
HPL General Construction | 22289 | L | B | MA | GE1 | Widening/Impv't. of DSVR (Mission-Sta. Ana Sect.) | Sta. Teresita, Cagayan | 2013-03-11 | 2nd | II | LF | 44.694 | 179 | 2012-10-22 | 2013-04-18 | -13.92 | O | 0.388 | 0.3 | 0.011 | 0.03 | 0.056 | 0.033 | 81.8 | -
HPL General Construction | 22289 | L | B | MA | GE1 | Widening/Impvt. of DSVR (Mission-Sta. Ana Sect.) | Sta. Teresita, Cagayan | 2012-11-23 | 1st | II | LF | 44.694 | 179 | 2012-10-22 | 2013-04-19 | 7.31 | O | 0.348 | 0.3 | 0.15 | 0.03 | 0.048 | 0.033 | 90.9 | -
HPL General Construction | 22289 | L | B | MA | GE1 | Repair/Rehab. of Baculud Bridge & Approaches along CVR | Alcala, Cagayan | 2013-07-30 | Final | II | LF | 48.327 | 210 | 2011-11-03 | 2012-05-30 | - | C | 0.457 | 0.091 | 0 | - | - | - | 54.8 | 66.54% Poor
HPL General Construction | 22289 | L | B | MA | GE1 | Repair/Rehab. of Baculud Bridge & Approaches along CVR | Alcala, Cagayan | 2013-03-11 | 3rd | II | LF | 48.327 | 225 | 2011-11-03 | 2012-06-15 | - | O | 0.387 | 0.3 | 0 | 0.03 | 0.05 | 0 | 76.7 | -
HPL General Construction | 22289 | L | B | MA | GE1 | Repair/Rehab. of Baculud Bridge & Approaches along CVR | Alcala, Cagayan | 2012-11-23 | 2nd | II | LF | 48.327 | 210 | 2011-11-03 | 2012-05-31 | -4.34 | O | 0.382 | 0.3 | 0 | 0.03 | 0.048 | 0.033 | 79.3 | -
HPL General Construction | 22289 | L | B | MA | GE1 | Repair/Rehab. of Baculud Bridge & Approaches along CVR | Alcala, Cagayan | 2012-07-30 | 1st | II | LF | 48.327 | 210 | 2011-11-03 | 2012-05-31 | -25 | O | 0.35 | 0.235 | 0 | 0.023 | 0.03 | 0.033 | 67.1 | -
HRB Construction | 10528 | L | B | MA | GB1 | Land Development of Magarao Resettlement Project |  | 11/9-12/09 | 1st | NHA |  | 5.277 | 110 |  |  |  | O | 0.454 | 0.2 | 0.3 | - | - | - | 95.4 | -
HUMMING BIRD CONSTRUCTION & SUPPLY | 33810 | L | B | MA | GB | Construction of One (1) Storey Two (2) Classroom 7mx18m School Building at Teofilo Gensoli, Sr National High School, Bacolod City | Bacolod City | 2015-11-16 | Final | Bacolod City DEO | LF | 1.7112 | 45 | 2015-08-18 | 2015-10-01 | - | C | 0.485 | 0.064 | 0.3 | - | - | - | 84.9% | 84.9% Satisfactory
HUMMING BIRD CONSTRUCTION & SUPPLY | 33810 | L | B | MA | GB | Construction of One (1) Storey Three (3) Classroom 7mx27m School Building at Jovito H. Sayson National High School, Bacolod City | Bacolod City | 2015-11-16 | Final | Bacolod City DEO | LF | 2.6109 | 90 | 2015-08-18 | 2015-11-15 | - | C | 0.472 | 0.077 | 0.3 | - | - | - | 84.9% | 84.9% Satisfactory
Hunan Road & Bridge Corporation | FC-11-004 | F | AAA | LB | GE1 | CP-RI 2.1: Impv't. of Magapit-Sta. Ana Rd., Magapit-Mission Jct. Sect., Cagayan, Luzon, under the Nat'l Rds. Impv't & Mgt. Program, Phase II (NRIMP 2) | Magapit, Cagayan | 2013-03-17 | 1st | NRIM-PMO | FA | 383.327 | 22 months | 2012-06-08 | 2014-04-07 | 5.43 | O | 0.39 | 0.24 | 0.15 | 0.03 | 0.061 | 0.033 | 90.4 | -
Hunan Road & Bridge Corporation | FC-08-016 | F | AAA | LB | GE1 | NRIMP-2, CP-R12.9: Marcos Highway (Evangelista St. to Masinag Sect.) Pasig City, Marikina City, Cainta and Antipolo City | Metro Manila and Rizal | 8/13-14/11 | 1st | NRIM-PMO | FA | 969.223 | 630 | 2010-04-28 | 2012-01-17 | 2.56 | O | 0.359 | 0.3 | 0.15 | 0.03 | 0.07 | 0.05 | 95.9 | -
HVC Sagittarius Commercial and Construction | 12954 | L | B | SB | GB | Const./Completion in Area Expiriencing Acute Classroom Shortage, Lugan Central Elementary School | T'boli, South Cotabato | 2014-08-06 | 1st & Final | XII | LF | 9.4388 | 200 | 2013-12-20 | 2014-07-08 | 0 | C | 0.405 | 0.133 | 0.3 |  |  |  | 83.8 | 83.80% Satisfactory
HVC Sagittarius Commercial and Construction | 12954 | L | B | MA | GE1 | Sarangani-Davao del Sur Coastal Road, Punsad-Pangyan Section |  | 2009-06-11 | 1st | R-XII |  | 9.39 | 180 |  |  |  | O | 0.327 | 0.265 | 0.15 | 0.024 | 0.04 | 0.033 | 83.9 | -
HVC SAGITTARIUS COMMERCIAL AND CONSTRUCTION | 12954 | L | B | SB | GB | Construction of One (1) Storey Two (2) Classroom Building at Bo. Site Primary School | Maasim, Sarangani Province | 2015-09-02 | 1st & Final | Saranggani | LF | 1.631 | 70 | 2015-05-21 | 2015-07-29 | 0% | C | 0.496 | 0.133 | 0.3 | - | - | - | 92.9% | *92.9% Very Satisfactory
I & E Construction | 10410 | L | AA | MA | GE | Road Upgrading (Gravel to Paved) Bagac - Mariveles Road K0183+788 - K0185+624 | Mariveles, Bataan | 2014-08-13 | 1st & Final | III | LF | 47.4659 | 198 | 2013-03-20 | 2013-10-03 | 0 | C | 0.455 | 0.133 | 0.3 |  |  |  | 88.8 | 88.80% Satisfactory
I & E Construction | 10410 |  |  |  |  | Removal of Landslides and Restoration of Collapsed Stone Masonry, Tagaytay-Taal Lake Rd. (Intermittent Sect.) |  | 2010-06-03 |  | IVA |  | 14.46 | 115 |  |  |  | O | 0.4 | 0.3 | 0.15 | 0.03 | 0.03 | 0.033 | 94.3 | -
I & E Construction | 10410 | L | AA | MA | GE | Widening /Impv't along Maharlika Highway Km. 935+634 - Km. 945+500 (with exception) and Km. 951+800 - Km. 958+804 (with exception) | Dulag, Leyte | 2014-08-09 | 1st & Final | VIII | LF | 23.2995 | 134 | 2013-05-24 | 2013-10-04 | 0.75 | C | 0.432 | 0.159 | 0.3 |  |  |  | 89.1 | 89.10% Very Satisfactory
I & E CONSTRUCTION CORPORATION | 10410 | L | AA | MA | GE | Widening of Noveleta-Naic-Tagaytay Road Leading to Ternate-Nasugbu Road, Cavite II, Naic, K0 043+(-460) - K0 046+000.00 (Intermittent Section) Net Length = 2,240.00 L.M. | Cavite Province | 2015-09-05 | 1st & Final | Regional Office No. IV-A | LF | 54.6 | 390 | 2014-03-27 | 2015-04-20 | 4.83% | C | 0.463 | 0.133 | 0.3 | - | - | - | 89.6% | *89.6% Very Satisfactory
I & E CONSTRUCTION CORPORATION | 10410 | L | AA | MA | GE | MFO-2 Flood Management Services - Construction/Maintenance of Flood Mitigation Structures and Drainage Systems, Construction of Retaining Wall of Nangka River, Sta. 2+320 - Sta. 2+720 | Brgy. Banaba, San Mateo, Rizal | 2015-08-25 | 1st | Rizal 2nd | LF | 31.578 | 215 | 2015-03-10 | 2015-10-10 | 16.88% | O | 0.383 | 0.225 | 0.15 | 0.03 | 0.023 | 0.05 | 86.1% | -
I & E CONSTRUCTION CORPORATION | 10410 | L | AA | MA | GE | MFO 1 - National Road Network Services, Network Development Widening of National Roads, Rizal Province | Rizal Province | 2015-11-10 | 1st | REGIONAL OFFICE | LF | 92.7946 | 390 | 2015-03-23 | 2016-04-15 | 0.0354 | OG | 0.38 | 0.3 | 0.15 | 0.03 | 0.045 | 0.05 | 95.5% | 95.5% Very Satisfactory
I & E CONSTRUCTION CORPORATION (Formerly: I & E Construction) | 10410 | L | AA | MA | GE | MFO 1 - National Roads Network Services Network Development - Widening of National Roads - Arterial Roads Marikina - Infanta Road, K0031+170 to K0032+475 | Rizal Province | 2015-06-06 | 1st | Regional Office No. IV-A | LF | 92.795 | 330 | 2015-03-23 | 2016-02-15 | 19.2% | O | 0.371 | 0.236 | 0.15 | 0.03 | 0.047 | 0.05 | 88.4% | -
I & E CONSTRUCTION CORPORATION (Formerly: I & E Construction) | 10410 | L | AAA | MA | GE | Rehabilitation of Piers and Abutment Protection of Agas-Agas Bridge, Sogod, Southern Leyte | Sogod, Southern Leyte | 2015-08-30 | 1st | Southern Leyte DEO | LF | 45.849 | 194 | 2015-04-06 | 2015-10-16 | (+)49.25 | O | 0.333 | 0.24 | 0.15 | 0.03 | 0.04 | 0.05 | 84.3% | -
I&E Construction | 10410 | L | AA | MA | GE1 | Rd. Upgrading (Gravel to Paved) Bagac-Mariveles Rd. K0183+788-K0185+624 | Mariveles, Bataan | 2013-08-02 | 1st | III | LF | 45.112 | 175 | 2013-03-20 | 2013-09-10 | 0.12 | O | 0.377 | 0.24 | 0.15 | 0.023 | 0.045 | 0.033 | 86.8 | -
I&E Construction | 10410 | L | AA | MA | GE1 | Widening/Impv't. along Maharlika Highway, Km.935+634-Km.945+500 (w/ exceptions) & Km.951+800.00-Km.958+804.00 (w/ exceptions) | Leyte | 2013-08-19 | 1st | VIII | LF | 23.3 | 120 | 2013-05-24 | 2013-09-20 | 1.06 | O | 0.386 | 0.24 | 0.15 | 0.01 | 0.047 | 0.05 | 88.3 | -
I&E Construction Corporation (Formerly: I&E Construction) | 10410 | L | AAA | MA | GE | Network Development-Widening of National Roads, National Arterial Roads, Widening of Dasmariñas-Trece Martires City-Naic Road (Governor's Drive), Naic Section, leading to Ternate-Nasugbu Road | Cavite 7th LD, Cavite Province, K0054+622.3-K0056+920.00 (with exception) Net Length=2,281.60 L.M. | 2014-11-07 | 1st | IV | LF | 39.4547 | 286 | 2014-04-30 | 2015-02-09 | -2.44% | O | 0.334 | 0.3 | 0.126 | 0.03 | 0.047 | 0.033 | 87% | 87.00% Satisfactory
I. A. Bosque Construction Corporation | 12597 | L | B | MA | GE | Preventive Maintenance National Arterial Daang Maharlika, K0205+319 to K0207+319, K0207+319 to K208+000 | Quezon | 2014-08-11 | Final | IV-A | LF | 37.4132 | 245 | 2013-02-22 | 2013-10-24 | 0 | C | 0.435 | 0.2 | 0.3 |  |  |  | 93.5 | 85.58% Satisfactory
I.A. Bosque Construction Corp. | 12597 | L | B | MA | GE1 | Conc.g of Unisan-Jct.-Panaon Rd. (Balanacan Sect.), K0197+045-K0198+545 | Quezon | 2013-08-06 | Final | IVA | LF | 32.984 | 180 | 2012-12-03 | 2013-05-31 | 0 | C | 0.35 | 0.2 | 0.3 | - | - | - | 85 | 86.32% Satisfactory
I.A. Bosque Construction Corp. | 12597 | L | B | MA | GE1 | Conc. of Unisan Jct.-Panaon Rd. (Balanacan Sect.) K0197+045-K0198+545 | Quezon | 2013-03-17 | 1st | IVA | LF | 32.984 | 180 | 2012-12-03 | 2013-05-31 | 1.04 | O | 0.345 | 0.242 | 0.15 | 0.03 | 0.055 | 0.05 | 87.2 | -
I.A. Bosque Construction Corp. | 12597 | L | B | MA | GE1 | Prev. Maint. (MFO-1) (Int. Sect.), Nat'l Arterial Rd. (Prev. Maint.); 1. Daang Maharlika (LZ) E. K0205+319-K0207+319; K0207+319-K0208+000 | Quezon | 2013-08-06 | 2nd | IVA | LF | 35.424 | 144 | 2013-02-22 | 2013-07-15 | -16.97 | O | 0.349 | 0.296 | 0 | 0.03 | 0.025 | 0.017 | 71.7 | -
I.A. Bosque Construction Corp. | 12597 | L | B | MA | GE1 | Assets Preservation of Nat'l Rds. Intermittent Sect.; A. Prev. Maint.; 1. National Arterial (Prev. Maint.); 1. Daang Maharlika (LZ) E. K0205+319-K0207+319; F. K0207+319 - K0208+000 | Quezon | 2013-03-18 | 1st | IVA | LF | 35.424 | 144 | 2013-02-22 | 2013-07-15 | -1.86 | O | 0.384 | 0.251 | 0.131 | 0.03 | 0.06 | 0.033 | 88.9 | -
I.A. Bosque Construction Corp./W.J. Construction (JV) | JV-12-633 | L | B | MA | GE2 | Construction of Concrete Canal Lining of DUMACAA RIS | Pagbilao, Quezon | 2013-09-07 | 1st | NIA | L | 26.942 | 180 | 2013-04-15 | 2013-10-11 | 0 | O | 0.3568 | 0.2424 | 0.15 | 0.03 | 0.042 | 0.05 | 87.12 | -
I.A. Bosque Construction Corporation |  | L |  |  | GE5 | Mauban Port Improvement Project | Port of Mauban, Quezon Province | 04/11-15/11 | 2nd | PPA | LF | 32.798 | 403 | 2010-03-04 | 2011-04-10 | -9.734 | O | 34.75 | 30 | 5.266 | 3 | 7 | 1.667 | 81.683 | -
I.A. Bosque Construction Corporation |  | L |  | MA | GE5 | Const of Mauban Port Improvement Project (Ports & Harbor) | Port of Mauban, Quezon Province | 02/15-18/11 | 1st | PPA | LF | 32.797 | 403 | 2010-05-25 | 2011-04-10 | -6.29 | O | 0.3869 | 0.2913 | 0.0871 | 0.03 | 0.0642 | 0.0167 | 87.62 | -
I.D.A. Jr. Builders & Construction Supply | 32022 | L | D | SB | GE | Const. of Drainage Canal along Calubian San Isidro - Tabango - Villaba - Palompon Road Km.1027+900 - K1026+400 | Tabango & Villaba, Leyte | 2014-08-08 | 1st & Final | VIII | LF | 3.5512 | 100 | 2014-01-30 | 2014-05-09 | 0 | C | 0.4 | 0.133 | 0.3 |  |  |  | 83.3 | 83.30% Satisfactory
I.D.R. Construction | 33559 | L | B | SB | GE | Proposed Improvement of Road & Drainage along J. Posadas St., Zone 100 and Vicinity | Punta, Sta. Ana, Manila | 2014-11-20 | 1st | NCR | LF | 13.0971 | 140 | 2014-07-04 | 2014-11-20 | -26.44% | O | 0.336 | 0.3 | 0 | 0.008 | 0.025 | 0.017 | 68.6% | 68.60% Poor
I.F. BLANCO'S CONSTRUCTION | 25350 | L | B | MA | GE | Concreting of Roads, Brgy. Laway (Salcedo)-Sto. Niño | Bansud, Oriental Mindoro | 2015-06-11 | Final | Southern Mindoro DEO | LF | 1.24 | 90 | 2015-02-20 | 2015-05-20 | 0% | C | 0.474 | 0.133 | 0.3 | - | - | - | 90.7% | *90.7% Very Satisfactory
IA FERRER CONSTRUCTION & SUPPLY | 34709 | L | D | SB | GE | Rehab./Reconstruction/Upgrading of Damaged Paved National Roads including Drainage along Goa-Digdigon-San Isidro Road (San Juan Bautista-Tagongtong Section), KO488+(-165))-KO488+177 Goa, Camarines Sur | Goa, Camarines Sur | 2015-11-15 | Final | Camarines Sur Third DEO | LF | 5.2473 | 45 | 2015-02-10 | 2015-03-26 | - | C | 0.388 | 0.133 | 0.3 | - | - | - | 82.1% | 82.1% Satisfactory
IBC Intenational Builders Corporation | 8576 |  |  |  |  | New Iloilo Airport Development Project (Construction of Secondary Access Road) |  | 2010-08-05 |  | DOTC |  | 121.222 | 210 |  |  |  | O | 0.355 | 0.3 | 0.107 | 0.03 | 0.07 | 0.05 | 91.2 | -
IBC INTERNATIONAL BUILDERS CORPORATION (Formerly: IBC Iloilo Builders Corporation) | 8576 | L | AAA | LB | GE | Rehab./Major Repair of Balucuan Bridge along Iloilo-Capiz Road (New Route) (B00233 PN) | Balucuan, Capiz | 2015-06-08 | Final | Capiz Second DEO | LF | 1.193 | 30 | 2015-02-27 | 2015-03-28 | 0% | C | 0.394 | 0.133 | 0.3 | - | - | - | 82.7% | *82.7% Satisfactory
IBC INTERNATIONAL BUILDERS CORPORATION (Formerly: IBC Iloilo Builders Corporation) | 8576 | L | AAA | LB | GE | Rehab./Major Repair of Mait Bridge along Iloilo-Capiz Road (Old Route) | K0093+000-K0093+380.76, Dumalag, Capiz | 2015-06-08 | Final | Capiz Second DEO | LF | 1.775 | 22 | 2015-02-27 | 2015-03-20 | 0% | C | 0.438 | 0.133 | 0.3 | - | - | - | 87.1% | *87.1% Satisfactory
IBC International Builders Corporation | 8576 | L | AAA | LB | GE5 | Iloilo City Parola Ferry Terminal Development Project | Parola, Iloilo City / Region VI | 2014-03-20 | Final | DOTC | LF | 123.88 | 300 | 2013-05-21 | 2014-03-16 | 0 | C | 0.3861 | 0.2 | 0.3 | - | - | - | 88.61 | 91.26% Satisfactory
IBC International Builders Corporation | 8576 | L | AA | LA | GE1 | Widening of Dungon Bridge IV, Iloilo-Jaro Diversion Road |  | 2009-03-02 | 1st | VI |  | 14.389 | 436 |  |  |  | O | 0.303 | 0.24 | 0.15 | 0.03 | 0.055 | 0.033 | #VALUE! | -
IBC International Builders Corporation | 8576 | L | A | LB |  | Cagban Jetty Port Development Project | Malay, Aklan | 2016-04-19 | 1st | DOTC | LF | 23.4999 | 180 | 2013-12-16 | 2016-06-15 | -8.28 | O | 0.4 | 0.3 | 0.067 | 0 | 0 | 0 | 76.7 | -
IBC International Builders Corporation | 8576 | L | AAA | LB |  | Siargao Airport Development Project | Del Carmen, Surigao del norte | 2016-06-29 | 2nd | DOTC | LF | 24.148 | 329 | 2013-12-16 | 2016-08-06 | -23 | O | 0.399 | 0.3 | 0.058 | 0.03 | 0.061 | 0.05 | 89.8 | -
IBC International Builders Corporation | 8576 | L | AAA | LB |  | Siargao Airport Development Project | Brgy. Sayak, Del Carmen, Surigao del Norte/ CARAGA Region | 2016-09-22 | 3rd & Final | DOTC | LF | 24.1481 | 353 | 2013-12-16 | 2016-08-30 | 0 | C | 0.4758 | 0.2 | 0.3 | - | - | - | 97.58 | 94.05% Very Satisfactory
IBC International Builders Corporation | 85765 | L | A | LB |  | Cagban Jetty Port Development Project- Phase II | Malay, Aklan | 2016-10-17 | 1st | DOTC | LF | 38.7932 | 210 | 2015-04-27 | 2016-12-11 | -6.98 | O | 0.4 | 0.3 | 0.08 | 0 | 0.042 | 0 | 82.2 | -
IBC International Builders Corporation | 8576 | L | AAA | LB |  | Kalibo Airport Development Project | Kalibo, Aklan | 2015-06-16 | 1st & Final | DOTC | LF | 56.8 | 180 | 2014-04-07 | 2015-06-23 | 0 | C | 0.443 | 0.2 | 0.3 | - | - | - | 94.3 | 94.30% Very Satisfactory
IBC International Builders Corporation | 8576 | L | AAA | LB |  | Roxas Airport Development Project | Brgy. Baybay, Roxas City, Capiz/ Region VI | 2014-09-24 | 1st | DOTC | LF | 128.128 | 270 | 2014-05-05 | 2015-06-14 | 4.09 | O | 0.3395 | 0.3 | 0.15 | 0.03 | 0.07 | 0.05 | 93.95 | -
IBC International Builders Corporation | 8576 | L | AAA | LB |  | Roxas Airport Development Project | Roxas City, Capiz | 2014-11-20 | 2nd & Final | DOTC | LF | 128.128 | 270 | 2014-05-05 | 2015-01-29 | 25.93 | C | 0.452 | 0.2 | 0.3 | - | - | - | - | 94.90% Very Satisfactory
IBC International Builders Corporation | 8576 | L | AAA | LB |  | Siargao Airport Development Project | Del Carmen, Surigao del Norte | 2014-10-16 | 1st | DOTC | LF | 23.566 | 354 | 2013-12-16 | 2014-12-04 | 2.64 | O | 0.377 | 0.3 | 0.15 | 0.02 | 0.039 | 0.05 | 93.6 | -
IBC International Builders Corporation | 8576 | L | AAA | LB | GE5 | Iloilo City Parola Ferry Terminal | Iloilo City | 2013-12-11 | 1st | DOTC | L | 123.88 | 300 | 2013-05-21 | 2014-03-16 | 0.14 | O | 0.3604 | 0.3 | 0.15 | 0.03 | 0.04 | 0.05 | 93.04 | -
IBC International Builders Corporation |  | L |  |  | GE-5 | Dumangas Port Expansion Project | Port of Dumangas, Dumangas, Iloilo | 2015-11-25 | 1st | PPA | LF | 110.8 | 445 | 2015-01-15 | 2015-02-11 | -12.168 | O | 0.3968 | 0.2952 | 0.1295 | 0.03 | 0.07 | 0.0333 | 95.48 | -
IBC International Builders Corporation (Formerly: IBC Iloilo Builders Corporation) | 8576 | L | AAA | LB | GE1 | Prev. Maint. of Sara-Concepcion Rd., K0209+266-K0215+816 w/ exceptions | Sara and Concepcion, Iloilo | 2013-08-21 | Final | VI | LF | 20.3 | 91 | 2013-02-01 | 2013-05-02 | 0 | C | 0.482 | 0.133 | 0.3 | - | - | - | 91.5 | 87.84% Satisfactory
IBC International Builders Corporation (Formerly: IBC Iloilo Builders Corporation) | 8576 | L | AAA | LB | GE1 | Conc. of Buruanga-Libertad Rd. (Jct. Nabas-Buruanga/Libertan Rd. Sect.) inc. 3 bridges | Buruanga, Aklan | 2013-08-16 | 2nd | VI | LF | 136.8 | 600 | 2012-07-18 | 2014-03-09 | -2.65 | O | 0.369 | 0.24 | 0.124 | 0.03 | 0.037 | 0.033 | 83.3 | -
IBC International Builders Corporation (Formerly: IBC Iloilo Builders Corporation) | 8576 | L | AAA | LB | GE | Road Upgrading (Gravel to Paved) along Miag-ao-Cadre Road, Miag-ao, K0039+(-222) - K0039+(-199); K0039+351 - K0040+000 | Iloilo | 2014-10-20 | 1st & Final | VI | LF | 13.9012 | 217 | 2014-02-13 | 2014-09-17 | 11.58% | C | 0.419 | 0.133 | 0.3 | - | - | - | 85.2% | 85.20% Satisfactory
IBC International Builders Corporation (Formerly: IBC Iloilo Builders Corporation) | 8576 | L | AAA | LB | GE | Rehabilitation/Reconstruction of Oton-Pakiad-Mandurriao Road, K009+000-K009+278 (Section 1); K0010+898-K0010+963 (Section 2); K0011+036-K0011+386 (Section 3) | Oton, Iloilo | 2014-10-20 | 1st | VI | LF | 13.62 | 136 | 2014-06-27 | 2014-11-09 | 10.08% | O | 0.34 | 0.236 | 0.15 | 0.03 | 0.055 | 0.033 | 84.4% | 84.40% Satisfactory
IBC International Builders Corporation (Formerly: IBC Iloilo Builders Corporation) | 8576 | L | AAA | LB | GE | Rehabilitation/Reconstruction/Upgrading of Guimbal-Igbaras-Tubungan-Leon Road (with exception) | K0033+680-K0057+505 | 2014-10-20 | 1st | VI | LF | 113.3 | 315 | 2014-05-26 | 2015-04-05 | -4.73% | O | 0.37 | 0.3 | 0.103 | 0.03 | 0.04 | 0.033 | 87.6% | 87.60% Satisfactory
IBC International Builders Corporation (Formerly: IBC Iloilo Builders Corporation) | 8576 | L | AAA | LB | GE | Preventive Maintenance of National Secondary Road, Lacson Street, Bacolod City K0001+(-151) to K0001+508 | Bacolod City | 2014-10-27 | 1st & Final | VI | LF | 13.8639 | 69 | 2014-02-13 | 2014-04-22 |  | C | 0.467 | 0.133 | 0.3 | - | - | - | 90% | 90.00% Very Satisfactory
IBC International Builders Corporation (Formerly: IBC Iloilo Builders Corporation) | 8576 | L | AAA | LB | GE | Rehabilitation/Reconstruction/Retrofitting of Existing Permanent Bago Bridge along Bacolod South By Pass Road, K0022+352 - K0022+622 | Bago City, Negros Occidental | 2014-10-22 | 1st | VI | LF | 37.1213 | 180 | 2014-05-30 | 2014-11-25 | 5.5% | O | 0.391 | 0.225 | 0.15 | 0.03 | 0.055 | 0.05 | 90.1% | 90.10% Very Satisfactory
IBC International Builders Corporation (Formerly: IBC Iloilo Builders Corporation) | 8576 | L | AAA | LB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Road (Intermittent Section) along Bacolod South Road, K0066+961 - K0068+117 | Hinigaran, Negros Occidental & Himamaylan City, Negros Occidental | 2014-10-23 | 1st | VI | LF | 20.5417 | 192 | 2014-04-29 | 2014-11-06 | 0.09% | O | 0.358 | 0.248 | 0.15 | 0.03 | 0.05 | 0.05 | 88.6% | 88.60% Satisfactory
IBC International Builders Corporation (Formerly: IBC Iloilo Builders Corporation) | 8576 | L | AAA | LB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Road, Iloilo-Capiz Road (New Route), a) K0015+600 - K0017+000 and b) K0017+710 - K0018+043 | Zarraga, Iloilo | 2014-10-28 | 1st & Final | VI | LF | 25.7997 | 171 | 2014-03-26 | 2014-09-12 |  | C | 0.437 | 0.133 | 0.3 | - | - | - | 87% | 87.00% Satisfactory
IBC International Builders Corporation (Formerly: IBC Iloilo Builders Corporation) | 8576 | L | AAA | LB | GE1 | Replacement of Bridges along Nat'l Rds. Tangalan Bridge, along Aklan West Coast Rd. (Kalibo-Nabas) | Tangalan, Aklan | 2013-03-19 | Final | VI | LF | 36.3 | 330 | 2012-01-27 | 2012-12-21 | 0 | C | 0.437 | 0.17 | 0.3 | - | - | - | 90.7 | 88.09% Satisfactory
IBC International Builders Corporation (Formerly: IBC Iloilo Builders Corporation) | 8576 | L | AAA | LB | GE1 | Prev. Maint. (Int. Sect.) Jct. Bagonawa-La Carlota-Isabela Rd., Haguimit-La Granja Sect., K0051+713-K0054+204 w/ exception | La Carlota City, Negros Occidental | 2013-03-14 | 1st | VI | LF | 17 | 65 | 2013-01-24 | 2013-03-29 | 2 | O | 0.355 | 0.24 | 0.15 | 0.03 | 0.03 | 0.05 | 85.5 | -
IBC International Builders Corporation (Formerly: IBC Iloilo Builders Corporation) | 8576 | L | AAA | LB | GE1 | Prev. Maint. of Sara-Concepcion Rd., K0209+266-K0215+816, w/ exceptions | Sara and Concepcion, Iloilo | 2013-03-21 | 1st | VI | LF | 20.3 | 91 | 2013-02-01 | 2013-05-02 | 30.27 | O | 0.339 | 0.24 | 0.15 | 0.03 | 0.045 | 0.05 | 85.4 | -
IBC International Builders Corporation (Formerly: IBC Iloilo Builders Corporation) | 8576 | L | AAA | LB | GE1 | Const. of Floodway Bridge along Metro Iloilo Radial Rd., R-4 By-Pass over Jaro Floodway | Jaro, Iloilo | 2013-03-22 | 2nd | VI | LF | 45.87 | 385 | 2012-02-06 | 2013-02-24 | -1.45 | O | 0.381 | 0.298 | 0.082 | 0.03 | 0.035 | 0 | 82.6 | -
IBC International Builders Corporation (Formerly: IBC Iloilo Builders Corporation) | 8576 |  |  |  |  | Road Upgrading/Conc. of Tiolas-Sinugbuhan Rd. |  | 2010-02-23 |  | VI |  | 18.228 | 210 |  |  |  | O | 0.32 | 0.3 | 0.15 | 0.03 | 0.047 | 0.05 | 89.7 | -
IBC International Builders Corporation (Formerly: IBC Iloilo Builders Corporation) | 8576 |  |  |  |  | Rehab. (Asphalt Overlay) of Bacolod South Road (Tiling Sect.) at Brgy. Tiling |  | 2010-06-05 |  | VI |  | 15.827 | 117 |  |  |  | O | 0.364 | 0.24 | 0.15 | 0.022 | 0.037 | 0.033 | 84.6 | -
IBC International Builders Corporation (Formerly: IBC Iloilo Builders Corporation) | 8576 | L | AAA | LB | GE1 | Replacement of Bridges along Nat'l Rds., Tangalan Bridge, along Aklan West Coast Rd. (Kalibo-Nabas) | Tangalan, Aklan | 2012-11-25 | 2nd | VI | LF | 36.3 | 330 | 2012-01-27 | 2012-12-21 | -4.8 | O | 0.384 | 0.24 | 0.102 | 0.03 | 0.045 | 0.033 | 83.4 | -
IBC International Builders Corporation (Formerly: IBC Iloilo Builders Corporation) | 8576 | L | AAA | LB | GE1 | Const. of Floodway Bridge along Metro Iloilo Radial Rd., R-4 by Pass Over Floodway | Jaro, Iloilo | 2012-11-20 | 1st | VI | LF | 43.306 | 337 | 2012-02-06 | 2013-02-07 | -8.3 | O | 0.368 | 0.3 | 0.067 | 0.03 | 0.05 | 0.017 | 83.2 | -
IBC International Builders Corporation (Formerly: IBC Iloilo Builders Corporation) | 8576 | L | AAA | LB | GE1 | Conc. of Buruanga-Libertad Rd. (Jct. Nabas-Buruanga/Libertad Rd. Sect.) inc. 3 Bridges | Buruanga, Aklan | 2012-11-23 | 1st | VI | LF | 136.8 | 480 | 2012-07-18 | 2013-11-09 | -0.44 | O | 0.282 | 0.3 | 0.146 | 0.03 | 0.05 | 0.017 | 82.5 | -
IBC INTERNATIONAL BUILDERS CORPORATION (Formerly: IBC Iloilo Builders Corporation) | 8576 | L | AAA | MA | GE | Construction/Rehabilitation of Barotac Viejo River Control Brgy. Natividad, Barotac, Viejo, Iloilo | Brgy. Natividad, Barotac, Viejo, Iloilo | 2015-11-14 | Final | Iloilo 3rd | LF | 36.46 | 388 | 2014-01-28 | 2015-02-20 | 0.00% | C | 0.398 | 0.2 | 0.3 | - | - | - | 89.8% | 89.8% Very Satisfactory
IBC INTERNATIONAL BUILDERS CORPORATION (Formerly: IBC Iloilo Builders Corporation) | 85796 | L | AAA | LB | GE | Rehabilitation/ Major Repair of Guimbal Bridge (B00125PN) Iloilo-Antique Road, Guimbal, Iloilo | Iloilo-Antique Road, Guimbal, Iloilo | 2015-11-09 | 1st | Iloilo 1st | LF | 279 | 180 | 2015-09-03 | 2016-03-01 | (+) 0.18% | OG | 0.32 | 0.3 | 0.15 | 0.03 | 0.047 | 0.05 | 89.7% | 89.7% Very Satisfactory
IBC International Builders Corporation (Formerly: IBC Iloilo Builders) | 8576 | L | AAA | LB | GE1 | Prev. Maint. (Int. Sect.) Jct. Bagonawa-La Carlota-Isabela Rd., Haguimit-La Granja Sect., K0051+713-K0054+204 w/ exception | La Carlota City, Negros Occidental | 2013-08-11 | Final | VI | LF | 17 | 65 | 2013-01-24 | 2013-03-29 | 0 | C | 0.465 | 0.133 | 0.3 | - | - | - | 89.8 | 87.22% Satisfactory
IBC International Builders Corporation (Formerly: IBC Iloilo Builders) | 8576 | L | AAA | LB | GE1 | Const. of Jaro Floodway Bridge along Metro Iloilo Radial Rd., R-4 By Pass, Over Jaro Floodway | Jaro, Iloilo City | 2013-08-23 | Final | VI | LF | 45.87 | 415 | 2012-02-06 | 2013-03-26 | 2.4 | C | 0.468 | 0.133 | 0.3 | - | - | - | 90.1 | 85.78% Satisfactory
IBC International Builders Corporation/CCM Construction (JV) |  | L |  |  |  | Emergency Repair of Dam. Access Road Network and Back-Up Area Caused by 7.2 Magnitude Earthquake, Tagbilaran City | Port of Tagbilaran, Tagbilaran City, Bohol | 2014-08-15 | 1st | PPA | LF | 27.603 | 210 | 2014-11-26 | 2014-09-20 | 7 | O | 0.376 | 0.3 | 0.15 | 0.024 | 0.0513 | 0.05 | 95.13 | -
Icalina Builders and Construction Supply | 26889 | L | D | SB | GB1 | Const. of 3-CL (2-Storey Type) SB, Mancanhon E/S |  | 2009-05-25 | 2nd | X |  | 3.081 | 140 |  |  |  | O | 0.295 | 0.3 | 0.08 | 0.03 | 0.013 | 0.033 | 75.1 | -
Icalina Builders and Construction Supply | 26889 | L | D | SB | GB1 | Const. of 3 CL 2 Storey Sch. Bldg., Macanhan E/S |  | 2009-03-02 | 1st | X |  | 3.167 | 120 |  |  |  | O | 0.305 | 0.18 | 0.15 | 0.03 | 0.02 | 0.033 | #VALUE! | -
IKM Builders & Construction Supply | 30252 | L | D | SB | GE1 | Repair/Rehab. Of Box Culvert & Pangao Creek along Batangas-Quezon Road | Ibaan, Batangas | 2012-03-20 | 1st | IVA | LF | 4.988 | 120 | 2011-12-22 | 2012-04-19 | 0.58 | O | 0.344 | 0.283 | 0.15 | 0 | 0.032 | 0.027 | 83.6 | -
IKM BUILDERS & CONSTRUCTION SUPPLY / JASMIG CONSTRUCTION SUPPLY (JOINT VENTURE) | JV-14-519 | L | B | MA | GE | Off-Carriageway Improvement of Batangas-Quezon Road, K0116+663 to K0117+582 | Rosario, Batangas | 2015-08-29 | 1st | Batangas 4th | LF | 27.116 | 210 | 2015-02-06 | 2015-09-03 | 14% | O | 0.344 | 0.24 | 0.15 | 0.03 | 0.025 | 0.033 | 82.2% | -
IKM BUILDERS & CONSTRUCTION SUPPLY/JASMIG CONSTRUCTION SUPPLY (JV) | JV-14-519 | L | B | MA | GE | Off Carriageway Improvement of Batangas - Quezon Road, K0116+663 to K0117+582 | Rosario, Batangas | 2015-06-05 | 1st | Batangas 4th DEO | LF | 27.116 | 180 | 2015-02-06 | 2015-08-04 | 0.66% | O | 0.326 | 0.239 | 0.15 | 0.03 | 0.055 | 0.033 | 83.3% | -
ILBI Construction Supply & Services | 32021 | L | B | SB | GB | Construction of MPB st Sapu Padidu-Malapatan-Sarangani Province | Sarangani Province | 2014-10-29 | 1st & Final | XII | LF | 2.3378 | 80 | 2014-07-03 | 2014-09-20 | 0% | C | 0.494 | 0.134 | 0.3 | - | - | - | 92.8% | 92.80% Very Satisfactory
IM Construction Corporation | 20074 | L | B | MA | GE | Rehab./Reconstruction/Upgrading of Damaged Paved National Roads Based on Pavement Management System/Highway Development & Management - 4 (HDM-4) (Intermittent Section) along Adante Street | Malabon City | 2014-11-21 | 1st & Final | NCR | LF | 11.7418 | 121 | 2014-02-14 | 2014-06-14 | 4.13% | C | 0.425 | 0.133 | 0.3 | - | - | - | 85.8% | 85.80% Satisfactory
IM Construction Corporation | 20074 | L | B | MA | GE | Asphalt Overlay of BIR Road, K0012+346 - K0012+506, K0012+257 - K0012+(-287) | Quezon City | 2014-08-15 | 1st & Final | NCR | LF | 17.0201 | 120 | 2014-01-30 | 2014-05-29 | 43.33 | C | 0.479 | 0.133 | 0.3 |  |  |  | 91.2 | 91.20% Very Satisfactory
IM Construction Corporation | 20074 | L | B | MA | GB1 | Completion of MPB (Package A) R. Medina Compound, Brgy. San Dionisio |  | 2009-09-03 | 1st | NCR |  | 0.997 | 60 |  |  |  | O | 0.305 | 0.203 | 0.15 | 0.03 | 0.023 | 0.025 | 73.6 | -
IM CONSTRUCTION CORPORATION | 20074 | L | B | MA | GE | Repair/Rehabilitation of Barangay Road, Rodriguez Road, Barangay Panghulo, Malabon City | Brgy. Panghulo, Malabon City | 2015-06-05 | Final | Malabon-Navotas DEO | LF | 2.847 | 90 | 2015-03-10 | 2015-06-07 | (+) 13.33 | C | 0.485 | 0.133 | 0.3 | - | - | - | 91.8% | *91.8% Very Satisfactory
IM CONSTRUCTION CORPORATION | 20074 | L | B | MA | GE | Improvement of Roads with Drainage Along 6th St. (From 10th Avenue to C-3), Caloocan City | Caloocan City | 2015-08-28 | 1st | MM 3rd DEO | LF | 25.136 | 210 | 2015-05-25 | 2015-12-20 | 19.76% | O | 0.383 | 0.24 | 0.15 | 0.03 | 0.04 | 0.05 | 89.3% | -
Infra Builders & Sellers Phils. | 9391 | L | B | MA | GE1 | Conc. of Basud-Tagaytay-Baligang-Taladong-Comon-Inarado-Peñafrancia Road, Comon-Inarado Road Section |  | 2009-05-27 | 1st | V |  | 19.1 | 240 |  |  |  | O | 0.319 | 0.3 | 0.15 | 0.023 | 0.035 | 0.033 | 86 | -
Infra Builders & Sellers Phils. | 9394 | L | A |  | GE5 | Emergency Repair/ Replacement of Damaged RC Pier Deck | Port of Matnog, Sorsogon | 2013-05-24 | 1st | PPA | L | 39.614 | 180 | 2012-12-12 | 2013-08-08 | -3.8 | O | 0.371 | 0.3 | 0.112 | 0 | 0.04 | 0.05 | 87.3 | -
Infra Builders & Sellers Phils. | 9391 | L |  |  | GE5 | Emergency Repair/ Replacement of Damaged RC Pier Deck | Port of Matnog, Sorsogon | 2013-09-27 | Final | PPA | L | 39.614 | 240 | 2012-12-12 | 2013-08-08 | 0 | C | 0.483 | 0.2 | 0.3 | - | - | - | 98.3 | 91.68% Very Satisfactory
INFRA BUILDERS & SELLERS, PHILS | 9391 | L | A | MA | GE | Construction of Belen-Paolbo Seawall, Brgy. Paolbo, Calabanga, Camarines Sur | Brgy. Paolbo, Calabanga, Camarines Sur | 2015-08-30 | 1st | Camarines Sur Second DEO | LF | 45.422 | 283 | 2015-03-16 | 2015-12-23 | 10.27% | O | 0.354 | 0.24 | 0.15 | 0.03 | 0.06 | 0.05 | 88.4% | -
Infra Builders and Sellers Phils/Azulrem Constn. & Engineering Services | JV-14-189 | L |  | MA |  | Repair of Damaged Port Facilities | Port of San Andres, Quezon Province | 2015-03-19 | 1st & Final | PPA | L | 17.45 | 120 | 2014-11-12 | 2015-03-11 | 0 | C | 0.4851 | 0.155 | 0.3 | - | - | - | - | 94.01% Very Satisfactory
Interior-Philoworks Construction (JV) | JV-06-026 | L | AAA | LB | GE1 | Const./Impvt. of Libon-Marocmoc-Pantao Road |  | 2009-05-28 | 2nd | RRNDP |  | 22.89 | 566 |  |  |  | O | 0.363 | 0.3 | 0.137 | 0.03 | 0.045 | 0.05 | 92.5 | -
Interior-Philoworks Construction (JV) | JV-06-026 | L | AAA | LB | GE1 | Contract Package III, Libon-Marocmoc, Pantao Road |  | 2009-03-07 | 1st | RRNDP |  | 212.89 | 566 |  |  |  | O | 0.374 | 0.3 | 0.137 | 0.03 | 0.056 | 0.05 | #VALUE! | -
International Builders Corporation (IBC) | 5876 | L | AAA |  |  | Construction of Berthing Facilities | Iloilo River Wharf/Region VI | 2014-05-30 | 1st | PPA | LF | 108.8 | 450 | 2013-01-09 | 2014-04-03 | 0 | O | 0.398 | 0.3 | 0.15 | 0.03 | 0.07 | 0.05 | 99.8 | -
International Builders Corporation (IBC) | 5876 | L | AAA |  |  | Construction of Berthing Facilities | Iloilo River Wharf/Region VI | 2014-05-30 | Final | PPA | LF | 108.8 | 450 | 2013-01-09 | 2014-04-03 | 0 | C | 0.4823 | 0.2 | 0.3 | - | - | - | - | 99.17% Outstanding
International Builders Corporation (IBC) | 8576 |  | AAA | LB |  | Dumangas Port Expansion Project | Port of Dumangas, Iloilo | 2016-08-05 | Final | PPA | LF | 110.8 | 539 | 2015-01-15 | 2016-07-06 | 0 | C | 0.4419 | 0.2 | 0.3 | - | - | - | 94.19 | 94.96% V. Satisfactory
International Builders Corporation (IBC) | 8576 | L | AAA |  | GE5 | Construction of Berthing Facilities | Iloilo River Wharf, Iloilo City | 2013-06-28 | 1st | PPA | L | 108.8 | 450 | 2013-01-09 | 2014-04-03 | 14.08 | O | 0.398 | 0.3 | 0.15 | 0.03 | 0.07 | 0.05 | 99.8 | -
INTERNATIONAL BUILDERS CORPORATION (IBC) (Formerly: IBC Iloilo Builders Corporation) | 8576 | L | AAA | LB | GE | Construction/Upgrading/Rehabilitation of Drainage along National Road, Bacolod South Road, (Gen. Luna - Bago High School Road), Traversing Bacolod South By-Pass Road, K0021+160 - K0022+824 (S00158NR) and K0021+706 - K0022+352 (S00155NR) | Bago City, Negros Occidental | 2015-08-25 | 1st | Negros Occidental 4th | LF | 24.011 | 318 | 2015-05-18 | 2016-03-30 | 40.39% | O | 0.368 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 88.8% | -
International Builders Corporation/CCM Construction | SL 1-SN-008251 | L | AAA | LB |  | Emergency Repair of Damaged Access Road Network and Back-Up Area caused by 7.2 Magnitude Earthquake | Port of Tagbilaran, Bohol | 2014-11-15 | 2nd & Final | PPA | L | 27.603 | 210 | 2014-02-23 | 2014-09-20 | 0 | C | 0.476 | 0.2 | 0.3 | - | - | - | - | 96.11% Outstanding
IPM Construction and Development Corp. | [5 empty] | Estancia People's Village | Brgy. Calapdan, Estancia, Iloilo/ Reg. VI | 2016-05-21 | 1st | NHA | LF | 289.8 | 501 | 2015-05-15 | 2016-10-05 | -8.95 | O | 0.3854 | 0.2906 | 0.0605 | 0.03 | 0.0607 | 0.033 | 86.02 | -
IRC CONST. & SUPPLIES/AZUL BUILDERS (Joint Venture) | JV-14-033 | L | - | MA | GE | Construction of River Wall along Meycauayan River, Poblacion to Banga (right side), Phase IV, Sta. 02+339.8 to Sta. 02+471.80, Meycauayan, Bulacan | Meycauayan, Bulacan | 2015-06-13 | Final | Bulacan 2nd DEO | LF | 26.827 | 170 | 2014-08-29 | 2015-02-14 | 7.85% | C | 0.5 | 0.133 | 0.3 | - | - | - | 93.3% | *93.3% Very Satisfactory
Isaga Builders | 8652 | L | C | SB | GE1 | Proposed Rehab./Impvt. along Calanasan-Claveria Road, Magnas Section |  | 2009-02-27 | 1st | CAR |  | 9.272 | 416 |  |  |  | O | 0.282 | 0.287 | 0.15 | 0.03 | 0.043 | 0.033 | #VALUE! | -
Isaga Builders | 8652 |  |  |  |  | Rehab. / Impvt. along of Calanasan-Claveria Road, Magnas Section |  | 2009-09-05 |  | CAR |  | 9.12 | 438 |  |  |  | O | 0.368 | 0.24 | 0.15 | 0.03 | 0.056 | 0.033 | 87.7 | -
ISH Construction | 30407 | L | B | MA | GB1 | Const. of Multi-Purpose Covered Court, Function Hall and Day Care Center |  | 2009-07-24 | 1st | NHA |  | 14.742 | 120 |  |  |  | O | 0.3788 | 0.2592 | 0.15 | 0.03 | 0.07 | 0.05 | 93.8 | -
ISH Construction |  | L |  |  | GB1 | Construction of Three (3) Storey 15-Classroom School Bldg. | Southville 8C, Site 1, Barangay San Isidro, Rodriguez, Rizal | 03/24-11/24/11 | Final | NHA |  | 24.066 | 195 | 2010-06-07 | 2011-04-21 | - | O, delayed | 0.441 | 0.2 | 0.3 | - | - | - | 94.1 | 84.35% Satisfactory
ISH Construction Inc. | 30407 | L | B | MA | GB1 | Construction of Three-Storey School Building (12 Classrooms) |  | 2008-07-10 | 1st | SLB |  | 17.201 | 150 |  |  |  | O | 0.4 | 0.2455 | 0.1 | 0.02 | 0.0525 | 0.1 | 91.8 | -
ISH Construction, Inc. | 30407 |  |  |  |  | San Isidro Resettlement Project |  | 03/2-4/2010 |  | NHA |  | 13.266 | 150 |  |  |  | O | 0.3787 | 0.3 | 0.1058 | 0.03 | 0.05 | 0.05 | 91.45 | -
ITP Construction | 9392 | L | AAA |  |  | Sta. Josefa Pump Irrigation Project | Agusan del Sur/ Caraga Region | 2014-08-30 | Final | NIA | LF | 17.282 | 346 | 2012-09-19 | 2013-11-29 | 0 | C | 0.376 | 0.196 | 0.3 | - | - | - | - | 87.20% Satisfactory
ITP Construction Inc. | 9392 |  |  |  |  | Const. of 3-Storey 15-Classroom School Building |  | 2009-07-30 |  | NHA |  | 18.111 | 150 |  |  |  | O | 0.4 | 0.299 | 0.15 | 0.03 | 0.058 | 0.05 | 98.7 | -
ITP Construction Inc. | [5 empty] | Construction of Nine (9) Five-Storey Residential Buildings with Land Development | Paradise Heights, Balut, Tondo, Manila | 2015-09-23 | 4th & Final | NHA | LF | 444.887 | 270 | 2012-12-13 | 2015-08-15 | 0 | C | 0.4764 | 0.2 | 0.3 | - | - | - | 97.64 | 89.81% V. Satisfactory
ITP Construction Inc. |  | L | AAA |  | GB1 | Construction of Nine (9) Five (5) Storey Residential Bldg. w/ Land Development | Paradise Heights, Tondo, Manila | 2013-06-27 | 1st | NHA | L | 404.463 | 270 | 2012-12-13 | 2013-09-08 | -6.326 | O | 0.362 | 0.276 | 0.0867 | 0.03 | 0.038 | 0.033 | 82.57 | -
ITP Construction, Inc. | 9392 | L | AAA | SB | GB | Boracay Drainage Immediate Improvement Program (Phase 1) | Boracay Island, Malay, Aklan | 2015-02-06 | Final | TIEZA | LF | 91.9 | 665 | 2012-10-05 | 2014-08-01 |  | C | 0.481 | 0.2 | 0.3 |  |  |  | 98.1 | 89.22% Very Satisfactory
ITP Construction, Inc. | 9392 | L | AAA |  |  | Land Development of Butuan City, New Villages, Phase 2 | Brgy. Mahay, Butuan City | 2014-12-12 | Final | NHA | L | 36.571 | 359 | 2012-09-13 | 2014-10-01 | 0 | C | 0.4385 | 0.197 | 0.3 | - | - | - | 93.55 | 88.53% Satisfactory
ITP Construction, Inc. | 9392 | L | AAA |  |  | Land Development of Butuan City New Villages, Phase 2 | Brgy. Mahay, Butuan City | 2013-10-25 | 1st | NHA | LF | 36.571 | 345 | 2012-09-13 | 2014-03-12 | 9.37 | O | 0.298 | 0.3 | 0.15 | 0.03 | 0.0408 | 0.033 | 85.18 | -
ITP Construction, Inc. | 9392 | L | AAA |  |  | Construction of Five-Storey Resedential Buildings with Land Development (Bldg. No. 27, 29 and 30 only) | Paradise Heights, Balut, Tondo, Manila | 2014-09-18 | 3rd | NHA | L | 437.94 | 270 | 2012-12-13 | 2015-04-26 | 12.48 | O | 0.397 | 0.275 | 0.15 | 0.03 | 0.035 | 0.05 | 93.7 | -
ITP Construction, Inc. |  | L | AAA |  |  | Construction of (9) Five-Storey Resedential Buildings w/ Land Development | Paradise Heights, Tondo, Manila | 2013-09-19 | 2nd | NHA | LF | 404.463 | 270 | 2012-12-13 | 2013-11-28 | -9.6 | On-going (6 bldgs); Suspended (3 bldgs) | 0.397 | 0.282 | 0.054 | 0.03 | 0.035 | 0.033 | 83.1 | -
ITP Construction, Inc. | 9392 | L | AAA | SB | GB | Boracay Drainage Immediate Improvement Program (Phase 1) | Boracay Island, Malay, Aklan | 2014-03-11 | 1st | TIEZA | LF | 83.499 | 500 | 2012-10-05 | 2014-08-01 | -8.48 | O | 0.341 | 0.3 | 0.07 | 0.03 | 0.059 | 0.033 | 83.3
ITP Construction, Inc. | 9392 | L | AAA | LB | GB1 | Construction of One (1) unit Three-Storey School Building |  | 2008-09-24 | 2nd | NHA |  | 17.202 | 150 |  |  |  | O | 0.3947 | 0.286 | 0.03 | 0.02 | 0.0525 | 0.033 | 81.62 | -
ITP Construction, Inc. / R.C. Tagala Construction (JV) | JV-11-133 | L | AAA | LA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rd., Puerto Princesa South Rd. (Caramay-Aplian-Calasaguen Sect.) K0164+024-K0168+587.25 w/ exceptions | Española, Palawan | 2013-08-14 | Final | IVB | LF | 98.613 | 387 | 2012-03-20 | 2013-04-10 | 0 | C | 0.392 | 0.2 | 0.3 | - | - | - | 89.2 | 86.80% Satisfactory
ITP Construction, Inc. / R.C. Tagala Construction (JV) | JV-11-333 | L | AAA | LA | GE1 | Rehab./Reconst./Upgrading of Puerto Princesa South Rd., (Caramay-Aplian-Calasaguen Sect.) (K0164+024-K0168+587.25 w/ exceptions) | Española, Palawan | 2013-03-15 | 3rd | IVB | LF | 93.914 | 346 | 2012-03-20 | 2013-02-28 | -2.45 | O | 0.359 | 0.276 | 0.125 | 0.03 | 0.055 | 0.033 | 87.8 | -
Ivy Michelle Trading & Construction | 24093 | L | A | MB | GE | Improvement of Puerto Princesa South Road K0090+180 - K0091+210, Narra, Palawan | Narra, Palawan | 2014-08-05 | 1st & Final | IV-B | LF | 4.7807 | 82 | 2013-12-23 | 2014-03-14 | 0 | C | 0.406 | 0.133 | 0.3 |  |  |  | 83.9 | 83.90% Satisfactory
Ivy Michelle Trading & Construction | 24093 | L | A | MB | GE1 | Rd. Upgrading (Gravel to Concrete) of Puerto Princesa South Rd. Sta. 147+568-Sta.149+800-Sta.150+350-Sta.150+850, Sta.151+035-Sta.151+635.50 & Sta.151+672-Sta.158+368 | Sofronio, Palawan | 2013-08-13 | 1st | IVB | LF | 84.474 | 153 | 2013-06-11 | 2013-11-10 | 1.58 | O | 0.351 | 0.24 | 0.15 | 0.03 | 0.047 | 0.05 | 86.8 | -
Ivy Michelle Trading & Construction | 24093 | L | A | MB | GE1 | Rd. Upgrading (Gravel to Conc.) Conc. of Puerto Princesa South Rd. (Ipaputo-Labog Sect.) K0139+736-K0142+897.50 | Española, Palawan | 2013-03-14 | Final | IVB | LF | 75.556 | 316 | 2012-03-15 | 2013-01-24 | 3.74 | C | 0.443 | 0.133 | 0.3 | - | - | - | 87.6 | 85.98% Satisfactory
Ivy Michelle Trading & Construction | 24093 | L | A | MB | GE1 | Rd. Upgrading of Puerto Princesa South Rd. 1. K0119+816-K0120+472 2. K0124+396-K0124+515 | Palawan | 2013-03-15 | 1st | IVB | LF | 13.292 | 75 | 2013-01-30 | 2013-04-14 | 0.08 | O | 0.363 | 0.237 | 0.15 | 0.03 | 0.045 | 0.033 | 85.8 | -
Ivy Michelle Trading & Construction | 24093 |  |  |  |  | Conc. of PPSR Jct. Napsan-Apurawan Rd. |  | 2010-06-04 |  | IVB |  | 38.131 | 220 |  |  |  | O | 0.349 | 0.225 | 0.12 | 0.03 | 0.051 | 0.033 | 80.8 | -
IVY MICHELLE TRADING & CONSTRUCTION | 24093 | L | A | MB | GE | Off-Carriageway Improvement of PPSR Jct. (Abo-Abo) Quezon Road, K0128+055 - K0145+856 (w/ exception) | Quezon, Palawan | 2015-06-04 | 1st | Palawan 2nd DEO | LF | 16.74 | 111 | 2015-04-06 | 2015-07-25 | 0% | O | 0.374 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 89.9% | -
J & A Pimentel Construction | 7953 | L | A | MA | GE | Rehabilitation/Retrofitting of Existing Permanent Bridges, Canag-as Bridge along Jct. Gamut-San Miguel Road, Surigao del Sur 1st L.K12D. | Surigao del Sur | 2014-10-25 | 1st & Final | XIII | LF | 5.8467 | 138 | 2014-02-17 | 2014-07-04 | 68.04% | C | 0.379 | 0.176 | 0.3 | - | - | - | 85.5% | 85.50% Satisfactory
J & A Pimentel Construction | 7953 | L | A | MA | GE | Widening along Surigao-Davao Coastal Road, Tandag City, Surigao del Sur 1st LD (K1300+928 - K1301+729) | Tandag City, Surigao del Sur | 2014-10-25 | 1st & Final | XIII | LF | 11.2192 | 88 | 2014-03-18 | 2014-06-13 | 25.78% | C | 0.327 | 0.2 | 0.3 | - | - | - | 82.7% | 82.70% Satisfactory
J & A Pimentel Construction | 7953 | L | A | MA | GE | Widening along SCDR, Tandag City Surigao del Sur 1st LD, K1295+204-K1297+261, Tandag Bridge, Brgy. Dagocdoc, Jct. Tandag Airport Rd. & K1295+286.70-K1296+218.20 | Tandag City, Surigao del Sur | 2014-08-12 | 1st | XIII | LF | 42.9855 | 192 | 2014-03-18 | 2014-09-25 | 16.95 | O | 0.322 | 0.207 | 0.15 | 0.022 | 0.028 | 0.05 | 77.9 | -
J & A Pimentel Construction | 7953 | L | A | MA | GE | Widening along Surigao-Davao Coastal Road, Tandag City, Surigao del Sur 1st LD, K1300+928 - K1301+729, Jct. Tago-Tandag City | Tandag City, Surigao del Sur | 2014-08-12 | 1st & Final | XIII | LF | 11.2192 | 88 | 2014-03-18 | 2014-06-13 | 0 | C | 0.377 | 0.133 | 0.3 |  |  |  | 81 | 81.00% Unsatisfactory
J & A Pimentel Construction | 7953 | L | A | MA | GE1 | Replacement of Bridge along Nat'l Rds. Badjang Bridge along Surigao-Davao Coastal Rd. | Lanuza, Surigao del Sur | 2013-03-16 | Final | XIII | LF | 18.706 | 268 | 2012-01-24 | 2012-10-17 | 0 | C | 0.44 | 0.122 | 0.3 | - | - | - | 86.2 | 89.50% Very Satisfactory
J & A Pimentel Construction | 7953 |  |  |  |  | Impvt./Conc. of Telaje Road |  | 2010-06-09 |  | XIII |  | 6.47 | 120 |  |  |  | O | 0.381 | 0.24 | 0.15 | 0.03 | 0.04 | 0.033 | 87.4 | -
J & A Pimentel Construction | 7953 | L | A | MA | GE2 | Construction of Tandag Shoreline Protection Project (Phase II) |  | 2009-03-12 | 1st | XIII |  | 13.851 | 150 |  |  |  | O | 0.375 | 0.24 | 0.15 | 0.03 | 0.035 | 0.05 | #VALUE! | -
J & A PIMENTEL CONSTRUCTION | 7953 | L | A | MA | GE | Rehabilitation of Permanent Bridges Victoria Bridge along SDCR (B00696mn) | Tago, Surigao del Sur | 2015-06-08 | 1st | SURIGAO DEL SUR FIRST DEO | LF | 6.185 | 129 | 2015-03-09 | 2015-07-15 | (+) 45.90% | O | 0.383 | 0.209 | 0.15 | 0.03 | 0.05 | 0.05 | 87.2% | -
J E G CONSTRUCTION FIRM CORPORATION | 36486 | L | B | SB | GB | Completion of Multi-Purpose Building (New Municipal Building) | Barotac Nuevo, Iloilo 4th Legislative District | 2015-09-04 | 1st | Iloilo 2nd | LF | 5.791 | 70 | 2015-08-07 | 2015-10-15 | 14.5% | O | 0.38 | 0.253 | 0.15 | 0.03 | 0.058 | 0.05 | 92.1% | -
J. A. Construction | 35189 | L | D | SB | GE-5 | Villareal Port Development Project | Brgy. Banguel, Villareal, Samar | 2014-10-27 | 1st & Final | DOTC | LF | 1.928 | 60 | 2014-03-14 | 2014-05-12 | 0 | C | 0.4 | 0.2 | 0.3 | - | - | - | 90 | 90.00% Very Satisfactory
J. B.S. Construction, Inc. | 679 | L |  | MB |  | Rehabilitation and Development of Estero De Sampaloc | Estero De Sampaloc, City of Manila | 2014-08-01 | Final | PRRC | LF | 20.639 | 368 | 2013-01-07 |  | 0 | C | 0.467 | 0.2 | 0.3 | - | - | - | - | 95.92% Very Satisfactory
J. C Baac Construction Corporation | 25974 | L | B | A | GE1 | Impvt./Widening/Conc. of Bontoc-Tabuk-Tuguegarao Road, Phase II, Suyo-Tangadan Section |  | 2009-03-04 | 1st | CAR |  | 47.214 | 360 |  |  |  | O | 0.385 | 0.296 | 0.15 | 0.03 | 0.032 | 0.033 | #VALUE! | -
J. C Baac Construction Corporation | 25974 | L | B | MA | GE1 | Impv't/Rehab Larion Alto-Cabbo-Baliuag Road (going to Callao Alternate Route) |  | 2009-02-27 | 1st | II |  | 19.143 | 230 |  |  |  | O | 0.328 | 0.3 | 0.116 | 0.03 | 0.55 | 0.033 | #VALUE! | -
J. C Baac Construction Corporation | 25974 | L | B | MA | GE1 | Impvt./Rehab. of Balbalan-Pinukpuk Road |  | 2008-11-18 | 1st | CAR |  | 26.052 | 260 |  |  |  | O | 0.323 | 0.234 | 0.1 | 0.02 | 0.03 | 0.067 | 77.4 | -
J. C. Piñon Construction, Inc. | 20905 |  | A |  |  | Construction of RC Wharf, RoRo Ramp, and Back-Up Area, Balanacan Port | Port of Balanacan, Mogpog, Marinduque | 2015-04-29 | 1st | PPA | L | 76.672 | 360 | 2014-07-29 | 2015-07-04 | -6.46 | O | 0.4 | 0.3 | 0.0854 | 0.03 | 0.07 | 0.05 | 93.54 | -
J. C. Piñon Construction, Inc. | 20905 |  | A |  |  | Construction of RC Wharf, RoRo Ramp and Back-Up Area | Port of Balanacan, Mogpog, Marinduque | 2016-03-11 | 2nd & Final | PPA | LF | 76.815 | 538 | 2014-07-29 | 2016-02-17 | 0 | C | 0.498 | 0.2 | 0.3 | - | - | - | 99.8 | 95.12% Outstanding
J. Cordon Construction & Supply | 32982 | L | D | SB | GE | Construction and Maintenance of Bridge along National Roads, Nabitasan Bridge along Iloilo City - Dumangas Coastal Road | Leganes, Iloilo | 2014-10-28 | 1st & Final | VI | LF | 2.6391 | 150 | 2014-02-12 | 2014-07-11 |  | C | 0.446 | 0.093 | 0.3 | - | - | - | 83.9% | 83.90% Satisfactory
J. Cordon Construction & Supply | 32982 |  |  |  |  | Repair of School Bldg. at Leon National High School |  | 2010-03-05 |  | VI |  | 1.44 | 90 |  |  |  | O | 0.296 | 0.3 | 0.15 | 0.015 | 0.027 | 0.033 | 82.1 | -
J. Custorio Construction | 16237 | L | D | SB | GE | Construction of Bridge, Palanas Cara RCBC along Calbayog - Catarman | Calbayog City, Samar | 2014-10-22 | 1st & Final | VIII | LF | 5.9296 | 211 | 2014-02-21 | 2014-09-19 | 0.56% | C | 0.469 | 0.133 | 0.3 | - | - | - | 90.2% | 90.20% Very Satisfactory
J. Custorio Construction | 16237 | L | D | SB | GE1 | Const. of Catarman Bridge along Catarman-Laoang Road |  | 2009-09-14 | 2nd | VIII |  | 9.419 | 172 |  |  |  | O | 0.345 | 0.24 | 0.15 | 0.03 | 0.045 | 0.033 | 84.3 | -
J. Custorio Construction | 16237 | L | D | SB | GE1 | Const. of Catarman Bridge along Catarman-Laoang Road |  | 2009-05-26 | 1st | VIII |  | 9.419 | 150 |  |  |  | O | 0.36 | 0.24 | 0.15 | 0.03 | 0.05 | 0.033 | 86.3 | -
J. Custorio Construction | 16237 | L | D | SB | GE1 | Rehab./Reconst./Upgrading of Damaged Paved National Roads, along Catarman-Calbayog Road |  | 2009-05-26 | 1st | VIII |  | 9.425 | 120 |  |  |  | O | 0.331 | 0.233 | 0.15 | 0.03 | 0.05 | 0.033 | 82.7 | -
J. Custorio Construction | 16237 | L | D | SB | GE1 | Impvt./Rehab. of Dagansa-Libjo Road |  | 2009-03-07 | 1st | VIII |  | 4.797 | 60 |  |  |  | O | 0.314 | 0.3 | 0.05 | 0.02 | 0.037 | 0.05 | #VALUE! | -
J. D. Legaspi Construction | 9608 | L | AAA | LB |  | Jolo Port Development Project | Jolo, sulu | 2014-09-11 | 2nd & Final | DOTC | L | 86.428 | 587 | 2013-04-17 | 2014-11-24 | 0 | C | 0.461 | 0.2 | 0.3 | - | - | - | - | 96.00% Very Satisfactory
J. D. Legaspi Construction | 9608 | L | AAA | LB | GE-5 | Jolo Port Development Project | Jolo, Sulu | 2014-09-11 | 1st | DOTC | LF | 86.428 | 587 | 2013-04-17 | 2014-11-24 | 3.2 | O | 0.39 | 0.3 | 0.15 | 0.03 | 0.04 | 0.05 | 96 | -
J. D. Legaspi Construction | 9608 | L | AAA | LB | GE2 | Help for Catubig Agricultural Advancement Project HCAAPD-C-1 | Catubig Service Area/Northern Samar, Region 8 | 2014-03-15 | 1st | NIA | LF | 231.889 | 935 | 2011-09-22 | 2013-09-18 | -47.76 | O | 0.3637 | 0.277 | 0 | 0.3 | 0.07 | 0.05 | 79.02 | -
J. D. Legaspi Construction | 9608 |  | AAA |  |  | Construction of Twelve (12) 5-Storey Residential Buildings and Land Development; Camarin Residences 4 | Camarin, Caloocan City | 2016-01-07 | 1st | NHA | LF | 343.106 | 450 | 2015-02-15 | 2016-05-10 | -4.27 | O | 0.3711 | 0.242 | 0.1073 | 0.03 | 0.051 | 0.017 | 81.84 | -
J. D. Legaspi Construction/ D. L. Cervantes Const Corp | [5 empty] | Proposed Transfer and redevelopment of Dr. Jose Fabella Memorial Hospital | San Lazaro Compound, Sta. Cruz, Manila/ NCR | 2016-06-29 | 1st | DOH | LF | 800.612 | 840 | 2015-05-31 | 2017-05-23 | 0.41 | O | 0.395 | 0.254 | 0.15 | 0.02 | 0.051 | 0.05 | 92 | -
J. E. Manalo and Co., Inc. | 422 | L | AAAA | LA |  | Construction of RC Wharf and Two RoRo Ramps with Breasting Dolphins | Port of Zamboanga | 2014-08-08 | 2nd & Final | PPA | LF | 228.253 | 559 | 2012-11-29 | 2014-06-10 | 0.18 | C | 0.599 | 0.2 | 0.2 | - | - | - | - | 98.65% Outstanding
J. E. TICO CONSTRUCTION CO., INC. | 7063 | L | A | MA | GB | Completion of Academic Building, 6-Classroom, 2-Storey Building, Nanga Elementary School, Guimbal, Iloilo | Guimbal, Iloilo | 2015-11-09 | Final | Iloilo 1st | LF | 2.1626 | 106 | 2015-02-16 | 2015-06-02 | 0.00% | C | 0.374 | 0.2 | 0.3 | - | - | - | 87.4% | 87.4% Satisfactory
J. E. TICO CONSTRUCTION CO., INC. (Formerly: Jet Construction Supply) | 7063 | L | A | MB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved Road including Drainage of Guimaras Circumferential Road, K0103+413-K0105+292.93, K0108+411-K0108+711, Guimaras, Iloilo | Guimaras, Iloilo | 2015-11-20 | 1st | Regional Office | LF | 62.1339 | 181 | 2015-07-20 | 2016-01-17 | (+) 8.29% | OG | 0.336 | 0.3 | 0.15 | 0.03 | 0.05 | 0.05 | 91.6% | 91.6% Very Satisfactory
J. M. Luciano Construction, Inc. (Formerly: J. M. Luciano Const.) | 2083 | L | AAA | LB | GE | NRJ-Dumagnon-Enchanted River-Baculin Road Leading to Enchanted River, Talisay, Hinatuan, Surigao del Sur, Sta. 0+000 to Sta. 1+280, Sta. 3+760 to Sta. 4+600 | Hinatuan, Surigao del Sur | 2014-08-10 | 1st | XIII | LF | 41.9652 | 152 | 2014-04-22 | 2014-09-20 | 5.16 | O | 0.337 | 0.225 | 0.15 | 0.03 | 0.047 | 0.05 | 83.9 | -
J. M. Luciano Construction, Inc. (Formerly: J. M. Luciano Const.) | 2083 | L | AAA | LB | GE | Widening/Upgrading of Poblacion RTR - San Antonio - Tagnote Road with Bridge, K0+000 - K1+680, RTR, Agusan del Norte | RTR, Agusan del Norte | 2014-08-05 | 1st | XIII | LF | 57.3207 | 270 | 2014-04-08 | 2015-01-02 | 6.05 | O | 0.341 | 0.225 | 0.15 | 0.03 | 0.033 | 0.05 | 82.9 | -
J. M. MALIGAYA CONSTRUCTION & CONSTRUCTION SUPPLY | 15018 | L | B | MA | GE | National Road Network Services, Construction and Maintenance of Bridges along National Roads, Widening of Permanent Bridges to more than 2 lanes, Pasong Elo Bridge (B03062LZ) along Dasmariñas - Trece Martires City - Naic Road: MFO 1-National Road Network | Dasmariñas - Trece Martires City - Naic Road, Cavite Province | 2015-11-11 | Final | CAVITE 1ST DEO | LF | 20.1073 | 252 | 2015-03-26 | 2015-12-02 | 0.1046 | C | 0.294 | 0.3 | 0.15 | 0.03 | 0.065 | 0.05 | 88.9% | 88.9% Satisfactory
J.A. Achacoso Enterprises & General Services | 33229 | L | D | SB | GE1 | Rehab./Reconst. Of Damaged Paved Nat'l. Road along Ormoc-Albuera Diversion Rd., Km.10129+(930)-Km.1012+(-524) | Leyte | 2012-03-24 | 1st | VIII | LF | 4.921 | 90 | 2012-01-16 | 2012-04-14 | 22.12 | O | 0.328 | 0.232 | 0.15 | 0.03 | 0.035 | 0.05 | 82.5 | -
J.B. ALARCON ENTERPRISES | 18849 | L | D | SB | GB | Completion of Rehabilitation Center - Municipal Annex Building, Rizal Street | Luisiana, Laguna 4th LD | 2015-08-27 | 1st & Final | Laguna 1st | LF | 0.961 | 60 | 2015-07-07 | 2015-09-04 | 13.33% | C | 0.456 | 0.133 | 0.3 | - | - | - | 88.9% | *88.9% Satisfactory
J.B. Basallo Construction and Supplies | 17391 | L | D | SB | GB | Construction of Hospital Annex Building, Rosario District Hospital | Rosario, La Union | 2014-10-26 | 1st | I | LF | 11.2677 | 150 | 2014-10-16 | 2015-03-14 | 5.53% | O | 0.372 | 0.241 | 0.15 | 0.03 | 0.051 | 0.05 | 89.4% | 89.40% Very Satisfactory
J.B. BASALLO CONSTRUCTION AND SUPPLIES | 17391 | L | D | SB | GB | Construction of Hospital Annex Building | Rosario District Hospital, Rosario, La Union | 2015-06-07 | Final | La Union 2nd DEO | LF | 11.96 | 180 | 2014-10-16 | 2015-04-13 | 0% | C | 0.428 | 0.153 | 0.3 | - | - | - | 88.1% | *89.01% Very Satisfactory
J.B.S. Construction, Inc. | 679 | L |  | MB |  | Rehabilitation and Development of Estero De Sampaloc | Estero De Sampaloc, City of Manila | 02/28/14 | 1st | PRRC | LF | 20.639 | 368 | 2013-01-07 |  | 4.27 | O | 0.382 | 0.3 | 0.15 | 0.03 | 0.042 | 0.05 | 95.4 | -
J.C. Baac Construction Corporation | 25974 | L | B | MA | GE1 | Impvt./Rehab. Larion Alto-Cabbo-Baliuag Road (Going to Callao alternate Route) |  | 2009-05-18 | 2nd | II |  | 19.134 | 281 |  |  |  | O | 0.371 | 0.247 | 0.15 | 0.03 | 0.047 | 0.033 | 87.8 | -
J.C. Baac Construction Corporation | 25974 | L | A | MA | GE | Road Upgrading (Gravel to Paved) of Bulanao-Paracelis Road, Cudal Section | Tabuk City, Kalinga | 2014-11-27 | 1st | CAR | LF | 36.7916 | 231 | 2014-03-24 | 2014-11-09 | -5% | O | 0.329 | 0.282 | 0.1 | 0.03 | 0.055 | 0.05 | 84.6% | 84.60% Satisfactory
J.C. Baac Construction Corporation | 25974 | L | B | MA | GE1 | Replacement of Gaday Bridge along Kalinga-Abra Rd. | Pasil, Kalinga | 2012-11-26 | 1st | CAR | LF | 11.751 | 285 | 2012-01-16 | 2012-10-26 | -3.09 | O | 0.324 | 0.3 | 0.041 | 0.022 | 0.028 | 0.033 | 74.8 | -
J.C. BAAC CONSTRUCTION CORPORATION | 25974 | L | A | MA | GE | Road Upgrading of (Gravel to Paved) of Bulanao-Paracelis Road, Cudal Section, K0511+012 - K0511+313.73 and K0512+252 - K0513+400.862 | Tabuk City, Kalinga | 2015-06-09 | Final | Kalinga DEO | LF | 36.792 | 261 | 2014-03-24 | 2014-12-09 | 0% | C | 0.373 | 0.181 | 0.3 | - | - | - | 85.32% | *84.89% Satisfactory
J.C. Ferrer Construction | 11657 | L | B | MA | GB | Construction of One (1), 2-Storey, 6-Classroom, Bugallon IS | Bugallon, Pangasinan | 2014-08-14 | Final | I | LF | 6.4076 | 139 | 2013-03-27 | 2013-08-12 | 0 | C | 0.463 | 0.169 | 0.3 |  |  |  | 93.2 | 88.72% Satisfactory
J.C. Ferrer Construction | 11657 | L | B | SB | GB1 | Const. of One (1) Unit, 2-Storey, 6-Cl, Bugallon IS | Bugallon, Pangasinan | 2013-08-06 | 1st | I | LF | 6.408 | 139 | 2013-03-23 | 2013-08-12 | 0.06 | O | 0.384 | 0.229 | 0.15 | 0.03 | 0.042 | 0.033 | 86.8 | -
J.C. Piñon Constructionn | 20905 | L | A | MB | GE5 | Construction of Marshalling Yard and Paving of Exixting Back-Up Area | Port of Lucena, Dalahican, Lucena City | 2013-04-19 | 1st | PPA | LF | 32.95 | 300 | 2012-10-22 | 2013-08-10 | 1.12 | O | 0.3917 | 0.3 | 0.15 | 0.03 | 0.07 | 0.05 | 99.17 | -
J.D. Legaspi Construction | 9608 | L | AAA | LB | GE1 | Construction of Solano-Quezon Road |  | 2009-06-02 | 2nd | II |  | 62.893 | 540 |  |  |  | O | 0.373 | 0.3 | 0.15 | 0.03 | 0.051 | 0.05 | 95.4 | -
J.D. Legaspi Construction | 9608 | L | AAA | LB | GE1 | Construction of Solano-Quezon Road |  | 2009-03-12 | 1st | II |  | 62.893 | 540 |  |  |  | O | 0.365 | 0.3 | 0.15 | 0.03 | 0.055 | 0.05 | #VALUE! | -
J.D. Legaspi Construction | 9608 | L | AAA | LB | GE1 | Impvt./Conc. of Surigao Sur-Davao Oriental Coastal Road, (Manay-Boston) Baganga Section PhaseII, C P No. 7 |  | 2009-09-06 | 3rd | XI |  | 191.035 | 597 |  |  |  | O | 0.38 | 0.3 | 0.15 | 0.03 | 0.042 | 0.033 | 93.5 | -
J.D. Legaspi Construction | 9608 | L | AAA | LB | GE | Preventive Maintenance (MFO-1) Asphalt Overlay with Corrections along Naic Junction-Caylabne Road, Naic Section, K0049+786 to K0049+272, K0049+272 to K0051+076, 7th Legislative District | Naic, Cavite | 2014-08-05 | 1st & Final | IV-A | LF | 40.3498 | 105 | 2014-02-17 | 2014-06-01 | 0 | C | 0.43 | 0.2 | 0.3 |  |  |  | 93 | 93.00% Very Satisfactory
J.D. Legaspi Construction | 9608 | L | AAA | LB | GE2 | Repair/Restoration of Seawall along Roxas Blvd. | Manila | 2013-03-14 | Final | NCR | LF | 81.171 | 180 | 2012-01-25 | 2012-07-22 | 0 | C | 0.422 | 0.155 | 0.3 | - | - | - | 87.7 | 87.85% Satisfactory
J.D. Legaspi Construction | 9608 | L | AAA | LB | GE1 | Const. of Abaton-Maidland II Bridge & Approaches | Calapan City, Oriental Mindoro | 2013-03-19 | 2nd | IVB | LF | 129.171 | 420 | 2011-10-13 | 2012-12-05 | -7.5 | O | 0.378 | 0.3 | 0.075 | 0.03 | 0.054 | 0.05 | 88.7 | -
J.D. Legaspi Construction | 9608 | L | AAA | LB | GE1 | Rehab./Reconst./Upgrading of Damaged Pav't. of Nat'l Rd. (MFO-2) (IS) Rizal Bdry-Famy-Quezon Rd.,-K0080+831-K0081+988 | Laguna | 2012-08-06 | 1st | IVA | LF | 20.741 | 195 | 2012-01-31 | 2012-08-28 | -15 | O | 0.337 | 0.3 | 0 | 0.03 | 0.05 | 0.017 | 73.4 | -
J.D. Legaspi Construction | 9608 | L | AAA | LB | GE1 | Const. of Abaton-Maidland II Bridge & Approaches | Calapan City, Mindoro | 2012-08-07 | 1st | IVB | LF | 117.43 | 360 | 2011-10-13 | 2012-10-06 | -3.62 | O | 0.328 | 0.3 | 0.114 | 0.03 | 0.035 | 0.033 | 84 | -
J.D. Legaspi Construction | 9608 | L |  |  |  | BSP Butuan Branch Building | Liberty Street, Bututan City, Agusan Del Norte | 2015-08-18 | Final | BSP | LF | 262.712 | 297 | 2013-09-17 | 2014-06-26 | 0 | C | 0.307 | 0.2 | 0.3 | - | - | - | 80.7 | 82.10% Satisfactory
J.D. Legaspi Construction | 9608 | L |  |  |  | BSP Butuan Branch Building | Liberty Street, Bututan City, Agusan Del Norte | 2014-11-18 | 1st | BSP | LF | 262.712 | 297 | 41534 | 41816 | 0 | O | 0.317 | 0.3 | 0.105 | 0.03 | 0.05 | 0.025 | 82.7 | -
J.D. Madrid Construction | 30365 | L |  | SB |  | Proposed Philippine Air Force Fence Relocation and Guard House | Poro Point, San Fernando City, La Union | 2015-09-08 | 1st & Final | BCDA | LF | 3.599 | 135 | 2015-02-23 | 2015-07-07 | 0 | C | 0.476 | 0.2 | 0.3 | - | - | - | 97.6 | 97.60% Outstanding
J.E Arradaza Construction and Suppy | 33256 |  |  |  |  | Const. /Repair/Impvt. of MPB at Brgy. Pardo |  | 2010-09-02 |  | VII |  | 1.155 | 65 |  |  |  | O | 0.376 | 0.268 | 0.119 | 0.015 | 0.023 | 0.033 | 83.4 | -
J.E Manalo and Company, Inc. | 422 | L | AAA |  | GE5 | New Port of San Jose | Pot of San Jose, San Jose, Occ. Mindoro | 05/04-06/11 | 2nd | PPA | LF | 148.337 | 514 | 2010-05-19 | 2011-10-14 | 9.675 | O | 0.3651 | 0.2919 | 0.15 | 0.03 | 0.07 | 0.05 | 95.7 | -
J.E Manalo and Company, Inc. | 422 | L | AAA |  | GE5 | New Port of San Jose | Port of San Jose, San Jose, Occ. Mindoro | 10/04-06/11 | 3rd | PPA | LF | 148.337 | 514 | 2010-05-19 | 2011-10-14 | 1.4 | O | 0.4989 | 0.2 | 0.3 | - | - | - | 99.89 | 97.24% Outstanding
J.E Manalo and Company, Inc. | 422 | L | AAA |  | GE5 | Const. of Proposed New Port of San Jose (Ports & Harbor) | Port of San Jose, San Jose, Occidental Mindoro | 02/8-10/11 | 1st | PPA | LF | 148.336 | 514 | 2010-05-19 | 2011-10-14 | 16.35 | O | 0.3527 | 0.2997 | 0.15 | 0.03 | 0.07 | 0.05 | 95.24 | -
J.E Manalo and Company, Inc. | 422 | L | AAA | LA | GE-5 | Construction of RC Wharf and Two (2) RoRo Ramps w/ Breasting Dolphins | Port of Zamboanga, Zamboanga City | 2014-02-28 | 1st | PPA | LF | 228.253 | 559 | 2012-11-29 | 2014-01-24 | 2.066 | O | 0.392 | 0.299 | 0.15 | 0.03 | 0.057 | 0.05 | 97.8 | -
J.E. Tico Construction, Inc. (Formerly: Jet Construction Supply) | 7063 | L | A | MA | GB1 | Const. of Estancia NHS | Estancia, Iloilo | 2013-08-21 | 1st | VI | LF | 26.812 | 180 | 2013-04-16 | 2013-10-12 | 1.15 | O | 0.333 | 0.24 | 0.15 | 0.03 | 0.038 | 0.05 | 84.1 | -
J.E. Tico Construction, Inc. (Formerly: Jet Construction Supply) | 7063 | L | A | MA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rds. (Int. Sect.)(Nat'l Arterial Rd.) Guimaras Circ. Rd. K002+040-K0010+233 | Jordan & Buenavista, Guimaras | 2013-08-05 | Final | VI | LF | 38.631 | 187 | 2013-01-22 | 2013-07-27 | 41.71 | C | 0.34 | 0.2 | 0.3 | - | - | - | 84 | 83.64% Satisfactory
J.E. Tico Construction, Inc. (Formerly: Jet Construction Supply) | 7063 | L | A | MA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l. Rds. (Int. Sect.) (Nat'l. Arterial Rd.) Guimaras Circ. Rd., K0002+040-K0010+223, Jordan & Buenavista | Guimaras | 2013-03-16 | 1st | VI | LF | 37.259 | 160 | 2013-01-22 | 2013-06-30 | 35.99 | O | 0.377 | 0.2 | 0.15 | 0.022 | 0.035 | 0.05 | 83.4 | -
J.G. Garcia Construction | 21054 | L | B | MA | GE1 | Const./Impvt./Rehab. of FMR, Brgy. Babasit | Pangasinan | 2013-08-05 | Final | I | LF | 1.965 | 60 | 2013-02-07 | 2013-04-07 | 20 | C | 0.474 | 0.133 | 0.3 | - | - | - | 90.7 | 85.96% Satisfactory
J.G. Garcia Construction | 21054 | L | B | MA | GE1 | Const./Impv't./Rehab. of FMR, Brgy. Babasit | Manaoag, Pangasinan | 2013-03-16 | 1st | I | LF | 1.965 | 60 | 2013-02-07 | 2013-04-07 | 58.33 | O | 0.381 | 0.189 | 0.15 | 0.03 | 0.045 | 0.033 | 82.8 | -
J.G. Oranza Construction | 33370 | L | C | SB | GE2 | Const. of Lined Canal (Baluan Sect.) along Jct. Digos-Makar-Buayan Rd., Brgy. Baluan | General Santos City | 2013-03-23 | Final | XII | LF | 7.302 | 135 | 2012-08-30 | 2013-01-11 | 3.45 | C | 0.401 | 0.133 | 0.3 | - | - | - | 83.4 | 86.28% Satisfactory
J.H Pajara Construction Corp. | 1890 | L | AAA | LB | GE1 | CP 6, Restoration of Patapat Viaduct under the Arterial Road Links Dev. Project, Phase V |  | 2008-11-15 | 1st | PJHL |  | 187.597 | 395 |  |  |  | O | 0.379 | 0.3 | 0.1 | 0.03 | 0.07 | 0.1 | 97.9 | -
J.H Pajara Construction Corp. | 1890 | L | AAA | LB | GE1 | Const. of Calaba Bridge & Approaches (Phase I) |  | 2009-02-24 | 5th | Sp. Bridges |  | 177.68 | 1002 |  |  |  | O | 0.396 | 0.289 | 0 | 0.03 | 0.055 | 0.033 | #VALUE! | -
J.M. LUCIANO CONSTRUCTION INC. (Formerly: J.M. Construction) | 2083 | L | AAA | LB | GE | Widening/Upgrading of Poblacion RTR-San Antonio-Tagnote with Bridge | K0+000 - K1+680, RTR, Agusan del Norte | 2015-09-03 | 1st & Final | Regional Office No. XIII | LF | 57.321 | 330 | 2014-04-08 | 2015-03-03 | (+) 4.62% | C | 0.458 | 0.175 | 0.3 | - | - | - | 93.3% | *93.3% Very Satisfactory
J.M. Luciano Construction, Inc. (Formerly: J.M. Luciano Construction) | 2083 | L | AAA | LB | GE | Widening/Upgrading of Poblacion RTR - San Antonio - Tagnote Road with Bridge, K0+000 - K1+680 | RTR, Agusan del Norte | 2014-10-30 | 1st | XIII | LF | 57.3207 | 330 | 2014-04-08 | 2015-03-03 | 15.05% | O | 0.322 | 0.279 | 0.15 | 0.03 | 0.056 | 0.05 | 88.7% | 88.70% Satisfactory
J.M. Luciano Construction, Inc. (Formerly: J.M. Luciano Construction) | 2083 | L | AAA | LB | GE | Rehabilitation/Reconstruction of Road Slip Protection along Surigao-Davao Coastal Road, K1480+153 - K1480+207, (Intermittent Sections) | Mahayhay, Lingig, Surigao del Sur | 2014-10-24 | 1st & Final | XIII | LF | 5.7895 | 60 | 2014-06-23 | 2014-08-21 | 5.34% | C | 0.448 | 0.133 | 0.3 | - | - | - | 88.1% | 88.10% Satisfactory
J.M. Luciano Construction, Inc. (Formerly: J.M. Luciano Construction) | 2083 | L | AAA | LB | GE1 | Rd. Upgrading (Gravel to Conc.) of Jct. Lingig-Trento Rd., Pagmam-an to Boundary Cuevas Sect. with Bridge | Bislig, Surigao del Sur | 2013-03-07 | 1st | XIII | LF | 113.786 | 375 | 2012-04-27 | 2013-05-06 | 11.09 | O | 0.283 | 0.3 | 0.15 | 0.03 | 0.045 | 0.033 | 84.1 | -
J.M. Luciano Construction, Inc. (Formerly: J.M. Luciano Construction) | 2083 | L | AAA | LB | GE1 | Const./Impv't. along Surigao-Davao Coastal Rd. (SDCR) Cortes-Lanuza Sect. | Surigao del Sur | 2013-03-15 | Final | XIII | LF | 96.5 | 330 | 2011-11-08 | 2012-10-02 | 3.61 | C | 0.322 | 0.2 | 0.3 | - | - | - | 82.2 | 87.99% Satisfactory
J.M. Luciano Construction, Inc. (Formerly: J.M. Luciano Construction) | 2083 | L | AAA | LB | GE1 | Rehab./Reconst./Strengthening of Bridge @ Cabanahan Bridge | Lanuza, Surigao del Sur | 2012-08-14 | 1st | XIII | LF | 18.024 | 300 | 2012-01-30 | 2012-11-24 | 6.2 | O | 0.283 | 0.3 | 0.15 | 0.03 | 0.05 | 0.05 | 86.3 | -
J.M. Luciano Construction, Inc. (Formerly: J.M. Luciano Construction) | 2083 | L | AAA | LB | GE1 | Road Upgrading (Gravel to Concrete) Surigao-Davao Coastal Rd. (IS), Km.1268+404-Km.1269+200.50 | Lanuza, Surigao del Sur | 2012-08-14 | 2nd | XIII | LF | 21.734 | 210 | 2012-01-23 | 2012-08-19 | 0.05 | O | 0.32 | 0.254 | 0.15 | 0.03 | 0.05 | 0.05 | 85.4 | -
J.M. LUCIANO CONSTRUCTION, INC. (FORMERLY: J.M. LUCIANO CONSTRUCTION) | 2083 | L | AAA | LB | GE | Rehabilitation/ Reconstruction/ Upgrading of Damaged Paved along Butuan - Cagayan de Oro - Iligan (Agusan-Misamis Oriental Section) | K1258+535 - K1260+695, Nasipit, Agusan Del Norte | 2015-06-02 | 1st | AGUSAN DEL NORTE DEO | LF | 39.273 | 209 | 2015-02-15 | 2015-09-11 | (+) 5.15% | O | 0.389 | 0.239 | 0.15 | 0.03 | 0.05 | 0.033 | 89.1% | -
J.M. LUCIANO CONSTRUCTION, INC. (FORMERLY: J.M. LUCIANO CONSTRUCTION) | 2083 | L | AAA | LB | GE | Construction of Additional One (1) Span Hubo Bridge and Bank Protection along Surigao - Davao Coastal Road | San Agustin, Surigao Del Sur | 2015-06-07 | 1st | Regional Office No. XII | LF | 81.092 | 332 | 2014-09-09 | 2015-08-06 | -7.33% | O | 0.375 | 0.267 | 0.073 | 0.03 | 0.05 | 0.033 | 82.8% | -
J.M. LUCIANO CONSTRUCTION, INC. (Formerly: J.M. Luciano Construction) | 2083 | L | AAA | LB | GE | Construction of Tabon-Labisma Road Leading to Lawigan Port, Bislig City, Surugao del Sur 2nd L.D | Brgy. Labisma, Bislig City, Surigao del Sur | 2015-11-13 | Final | Surigao del Sur 2nd DEO | LF | 45.8228 | 194 | 2015-03-27 | 2015-10-06 | (+) 1.55 | C | 0.327 | 0.2 | 0.3 | - | - | - | 82.7% | 88.34% Satisfactory
J.M. Luciano Construction, Inc. (Formerly: Luciano Construction) | 2083 | L | AAA | LB | GE1 | Road Upgrading (Gravel to Concrete) of Jct. Lingig-Trento Rd., Pagmam-an to Boundary Cuevas Sect. w/ Bridge | Bisilig, Surigao del Sur | 2013-08-18 | Final | XIII | LF | 113.785 | 359 | 2012-04-27 | 2013-06-19 | 0 | C | 0.458 | 0.142 | 0.3 | - | - | - | 90 | 86.46% Satisfactory
J.M. Maligaya Construction & Construction Supply | 15018 | L | B | SB | GE | Construction of Flood Control along Crisanto M. Delos Reyes ave., | K0060+494-K0061+337, 6th Legislative District | 2014-11-07 | 1st & Final | IV | LF | 11.6239 | 180 | 2014-02-17 | 2014-08-15 | - | C | 0.454 | 0.133 | 0.3 | - | - | - | 88.7% | 88.70% Satisfactory
J.P. Aquino & Bros. (Engineers, Developers, Architects, Builders) | 13231 | L | B | SB | GE1 | Conc. of FMR @ Brgy. Tibagan | Tarlac City | 2012-11-24 | 1st | III | LF | 7.527 | 93 | 2012-09-17 | 2012-12-18 | 2.01 | O | 0.317 | 0.283 | 0.15 | 0.03 | 0.035 | 0.033 | 84.8 | -
J.P. Aquino Construction 7 Enterprises (Formerly: J.P. Aquino Bros. (Engineers, Developers, Architects, Builders) | 13231 | L | B | SB | GE | Concreting of Road at Carabaon - Calao Road | Mayantoc, Tarlac | 2014-08-06 | 1st & Final | III | LF | 8.223 | 130 | 2014-02-12 | 2014-04-22 | 18.24 | C | 0.425 | 0.133 | 0.3 |  |  |  | 85.8 | 85.80% Satisfactory
J.Q.G. Construction | 10530 | L | A | MB | GE | Construction of Roads, Amacalan - Bularit | Gerona, Tarlac | 2014-08-07 | 1st & Final | III | LF | 5.1205 | 45 | 2014-03-27 | 2027-05-10 | 0 | C | 0.437 | 0.133 | 0.3 |  |  |  | 87 | 87.00% Satisfactory
J.S General Contractor | 15258 | L | B | MA | GE1 | Concreting of Tanza-Trece Martirez City-Indang Road |  | 2009-06-03 | 1st | IV-A |  | 9.63 | 120 |  |  |  | O | 0.368 | 0.24 | 0.15 | 0.03 | 0.025 | 0.05 | 86.3 | -
J.S. General Contractor | 15258 | L | B | MA | GE1 | Reconst. of Convento Bridge along Naic Jct. Caylabne Rd. | Naic, Cavite | 2013-08-13 | Final | IVA | LF | 14.332 | 179 | 2012-07-24 | 2013-01-18 | 0 | C | 0.479 | 0.133 | 0.3 | - | - | - | 91.2 | 91.14% Very Satisfactory
J.S. General Contractor | 15258 | L | B | MA | GE1 | Reconst. of Convento Bridge along Naic Jct.-Caylabne Rd. | Naic, Cavite | 2012-11-26 | 1st | IVA | LF | 13.824 | 179 | 2012-07-24 | 2013-01-19 | 1.37 | O | 0.353 | 0.3 | 0.15 | 0.03 | 0.045 | 0.033 | 91.1 | -
J.T. Gamolo Construction | 15759 | L | B | MA | GE | Road Upgrading (Gravel to Concrete) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standard (HDM-4) Project Analysis) (Intermittent Sections) along Kibawe-Kadingilan-Kalilangan Road 1) K1592+000 - K1592+715; 2) K1593+172 - K1594+035 | Kadingilan, Bukidnon | 2014-10-22 | 1st & Final | X | LF | 45.8244 | 214 | 2014-01-23 | 2014-08-24 | 0% | C | 0.375 | 0.191 | 0.3 | - | - | - | 86.6% | 86.60% Satisfactory
J.T. Gamolo Construction | 15759 | L | B | MA | GE | Rehab./Reconst./Upgrading of Damaged Paved along Maramag - Maradugao Road, K1591+200 - K1592+780 | Pangatucan & Kalilangan, Bukidnon | 2014-08-08 | 1st & Final | X | LF | 24.1354 | 149 | 2014-01-28 | 2014-06-10 | 15.69 | C | 0.46 | 0.187 | 0.3 |  |  |  | 94.7 | 94.70% Very Satisfactory
J.T. Gamolo Construction | 15759 | L | B | MA | GB | Construction of Classroom Aglayan Elementary School, Lalawan Annex | Aglayan, Malaybalay City , Bukidnon | 2014-08-15 | Final | X | LF | 4.1851 | 210 | 2013-03-22 | 2013-10-17 | 0 | C | 0.498 | 0.2 | 0.3 |  |  |  | 99.8 | 89.16% Very Satisfactory
J.T. Gamolo Construction | 15759 | L | B | MA | GE | Road Upgrading (Gravel to Paved) of Junction Sayre Highway Aglayan - Zamboanguita Road, Capinonan & Iba Sections, a. K1538+1010 - K1540+100 b. K1547+134 - K1547+500, Cabanglasan | Cabanglasan, Bukidnon | 2014-08-05 | 1st | X | LF | 39.0864 | 180 | 2014-01-23 | 2014-07-21 | 3.99 | O | 0.383 | 0.296 | 0.11 | 0.03 | 0.041 | 0.033 | 89.3 | -
J.T. Gamolo Construction | 15759 | L | B | MA | GB | Cluster II - Construction of 2-Storey 4-CL of Old Nongnongan NHS | Old Nongnongan, Don Carlos, Bukidnon | 2014-08-07 | Final | X | LF | 4.42 | 214 | 2013-03-25 | 2013-10-24 | 0 | C | 0.435 | 0.2 | 0.3 |  |  |  | 93.5 | 91.33% Very Satisfactory
J.T. Gamolo Construction | 15759 | L | B | MA | GB | Cluster II - Construction of 2-Storey 4-CL of New Nongnongan NHS ( San Nicolas Annex) San Nicolas | Don Carlos, Bukidnon | 2014-08-07 | Final | X | LF | 4.8031 | 214 | 2013-03-25 | 2013-10-24 | 2.44 | C | 0.468 | 0.2 | 0.3 |  |  |  | 96.8 | 89.45% Very Satisfactory
J.T. Gamolo Construction | 15759 | L | B | MB | GE | Construction of Slope Protection (Upstream of Musuan Bridge) along Sayre Highway | Musuan, Maramag, Bukidnon | 2014-08-07 | Final | X | LF | 4.9398 | 60 | 2013-06-28 | 2013-09-10 | 0 | C | 0.492 | 0.2 | 0.3 |  |  |  | 99.2 | 90.20% Very Satisfactory
J.T. Gamolo Construction | 15759 | L | B | MB | GE | Rehab./Reconst./Upgrading of Damaged Paved National Roads including Drainage based on Pavement Management System/Highway Development and Management-4 (HDM-4) (Intermittent Section) K1547+000 - K1549+000 | along Dologon-Busco-Quezon Road, Bukidnon | 2014-08-06 | 1st | X | LF | 31.1187 | 143 | 2014-01-23 | 2014-07-29 | 0 | O | 0.374 | 0.3 | 0.107 | 0.03 | 0.05 | 0.05 | 91.1 | -
J.T. Gamolo Construction | 15759 | L | B | MA | GB1 | Cluster II - Const. of 2-Storey 4-CL of Old Nongnongan NHS Old Nongnongan | Don Carlos, Bukidnon | 2013-08-08 | 1st | X | LF | 4.42 | 214 | 2013-03-25 | 2013-10-24 | 2.44 | O | 0.371 | 0.279 | 0.15 | 0.03 | 0.041 | 0.033 | 90.4 | -
J.T. Gamolo Construction | 15759 | L | B | MA | GB1 | Cluster II - Const. of 2-Storey 4-CL of New Nongnongan NHS (San Nicolas Annex) San Nicolas | Don Carlos, Bukidnon | 2013-08-08 | 1st | X | LF | 4.803 | 214 | 2013-03-25 | 2013-10-24 | 2.44 | O | 0.369 | 0.24 | 0.15 | 0.03 | 0.041 | 0.033 | 86.3 | -
J.T. Gamolo Construction | 15759 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rd. Int. Sect. Sayre Highway Impalutao and Patpat Sect., K1485+230-K1486+000; K1496+000-K1496+290; K1496+700-K1497+000 w/ exception, Impasugong & Malaybalay City | Bukidnon | 2013-08-10 | Final | X | LF | 24.019 | 135 | 2013-01-18 | 2013-06-01 | 0.74 | C | 0.379 | 0.2 | 0.3 | - | - | - | 87.9 | 85.26% Satisfactory
J.T. Gamolo Construction | 15759 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of Intermittent Sect., Sayre Highway Impalutao and Patpat Sect., K1485+230-K1486+000; K1496+000-K1496+290; K1496+700-K1497+000 w/ exception, Impasugong & Malaybalay City | Bukidnon | 2013-03-19 | 1st | X | LF | 24.019 | 135 | 2013-01-18 | 2013-06-01 | 0.83 | O | 0.32 | 0.257 | 0.15 | 0.03 | 0.045 | 0.033 | 83.5 | -
J.T. Gamolo Construction | 15759 | L | B | MA | GB1 | Const. of Classroom at Aglayan ES | Malaybalay City, Bukidnon | 2013-08-09 | 1st | X | LF | 4.185 | 210 | 2013-03-22 | 2013-10-17 | 7.58 | O | 0.324 | 0.24 | 0.15 | 0.03 | 0.052 | 0.05 | 84.6 | -
J.T. Gamolo Construction | 15759 | L | B | SB | GE2 | Const. of Slope Protection (Upstream of Musuan Bridge) along Sayre Highway, Musuan | Maramag, Bukidnon | 2013-08-08 | 1st | X | LF | 4.94 | 60 | 2013-06-28 | 2013-08-26 | 0.52 | O | 0.32 | 0.24 | 0.15 | 0.03 | 0.052 | 0.05 | 84.2 | -
J.T. Gamolo Construction | 15759 | L | B | MA | GE1 | Road Upgrading (Gravel to Paved) Int. Sec. inc. Drainage & Rd. Facilities along Don Carlos-Kadilingan Rd. a)K158+(-107)-K158+329; b)K1587+(-323)-K1587+(-128) | Don Carlos, Bukidnon | 2013-08-08 | Final | X | LF | 14.376 | 142 | 2013-01-24 | 2013-06-15 | 0 | C | 0.375 | 0.183 | 0.3 | - | - | - | 85.8 | 83.94% Satisfactory
J.T. Gamolo Construction | 15759 | L | B | MA | GE1 | Upgrading of Rd. (Gravel to Paved), Traffic (Int. Sect.) inc. Drainage Facilities along Don Carlos-Kadingilan Rd., a)K1581+(-107)-K1581+329; b K1587+(-323)-K1587+(-128) | Don Carlos, Bukidnon | 2013-03-20 | 1st | X | LF | 14.376 | 70 | 2013-01-24 | 2013-04-03 | 0.84 | O | 0.28 | 0.284 | 0.15 | 0.03 | 0.05 | 0.033 | 82.7 | -
J.T. Gamolo Construction | 15759 | L | B | MA | GE1 | Rehab./Reconst./Upgrading (Asphalt to concrete) of S.H. Alae-Kisolon Rd., K1474+000-K1474+500, Kisolon | Sumilao, Bukidnon | 2013-08-06 | Final | X | LF | 8.534 | 113 | 2013-01-23 | 2013-05-15 | 23.21 | C | 0.39 | 0.133 | 0.3 | - | - | - | 82.3 | 83.08% Satisfactory
J.T. Gamolo Construction | 15759 | L | B | MA | GE1 | Rehab./Reconst./Upgrading (Asphalt to Concrete) of S.H.-Alae-Kisolon Rd., K1474+000-K1474+500, Kisolon | Sumilao, Bukidnon | 2013-03-21 | 1st | X | LF | 8.534 | 113 | 2013-01-23 | 2013-05-15 | 31.44 | O | 0.332 | 0.236 | 0.15 | 0.03 | 0.055 | 0.033 | 83.6 | -
J.T. Gamolo Construction | 15759 | L | B | SB | GE2 | Rehab./Reconst./Upgrading of Int. Sect., Jct. SH Impalambong-Old Casisang Rd. K1507+(-829)-K1507+153 | Malaybalay City, Bukidnon | 2013-08-09 | Final | X | LF | 13.658 | 124 | 2013-01-18 | 2013-05-21 | 0 | C | 0.332 | 0.2 | 0.3 | - | - | - | 83.2 | 82.78% Satisfactory
J.T. Gamolo Construction | 15759 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of Intermittent Sect. Jct. SH Impalambong-Old Casisang Rd. K1507+(-829)-K1507+153 | Malaybalay City, Bukidnon | 2013-03-19 | 1st | X | LF | 13.658 | 94 | 2013-01-18 | 2013-04-21 | 7.18 | O | 0.304 | 0.241 | 0.15 | 0.03 | 0.05 | 0.05 | 82.5 | -
J.T. GAMOLO CONSTRUCTION | 15759 | L | B | MA | GE | Rehab/Reconst/Upgrading of Damaged Paved National Roads Including Drainage Based on Pavement Management System/Highway Development and Management-4 (HDM-4) (Intermittent Section) Along Don Carlos-Kadingilan Road, K01587+000-K1587+412, Bocboc, Don Carlos, Bukidnon, K1587+000-K1587+295.50 | K01587+000-K1587+412, Bocboc, Don Carlos, Bukidnon, K1587+000-K1587+295.50 | 2015-08-27 | 1st & Final | Bukidnon 2nd DEO | LF | 7.483 | 70 | 2015-02-27 | 2015-05-07 | 0% | C | 0.469 | 0.139 | 0.3 | - | - | - | 90.8% | *90.80% Very Satisfactory
J.T. GAMOLO CONSTRUCTION | 15759 | L | B | MA | GE | Concreting of Road, Brgy. San Jose-Panamukan Road, Malaybalay City, Bukidnon | Malaybalay City, Bukidnon | 2015-08-28 | 1st | Bukidnon 1st DEO | LF | 28.198 | 120 | 2015-05-12 | 2015-09-08 | 0.01% | O | 0.38 | 0.236 | 0.15 | 0.03 | 0.058 | 0.05 | 90.4% | -
J.T. Gamolo Construction/Mafil Builders, Inc. (J.V.) | 15759 | L | B | MA | GE | Construction of Drainage System along Sayre Highway, Bukidnon 2nd LD, K1475+256 TO K1496+765 (with exception), Impasugong and Dalwangan | Malaybalay City, Bukidnon | 2014-08-06 | 1st | X | LF | 13.6609 | 195 | 2014-01-23 | 2014-08-05 | -3.5 | O | 0.383 | 0.3 | 0.115 | 0.008 | 0.023 | 0.033 | 86.2 | -
J.T. Gamolo Construction/RRN Construction (Joint Venture) | JV-13-166 | L | B | SB | GE | Construction of Drainage System along Sayre Highway, Bukidnon 2nd LD, Cabangahan Section, K1520+000 TO K1522+000 (with exception) | Malaybalay City, Bukidnon | 2014-08-05 | 1st & Final | X | LF | 13.7902 | 195 | 2014-01-23 | 2014-08-05 | 0 | C | 0.462 | 0.2 | 0.3 |  |  |  | 96.2 | 96.20% Outstanding
J.V Lagon Construction Corporation | 11561 | L | A | MA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved National Road along Marbel-Makar Road |  | 2009-06-06 | 1st | R-XII |  | 14.317 | 224 |  |  |  | O | 0.318 | 0.254 | 0.15 | 0.012 | 0.055 | 0.017 | 80.6 | -
J.V Lagon Construction Corporation | 11561 | L | A | MA | GE1 | Rehab./Reconst. of Damaged Roads Dulawan-Marbel (Tacuromg-New Carmen Section) |  | 2009-06-02 | 2nd | R-XII |  | 19.022 | 435 |  |  |  | O | 0.38 | 0.3 | 0 | 0.03 | 0.06 | 0.017 | 78.7 | -
J.W.D. Construction | 22291 | L |  |  | GE2 | Construction of MARIIS Main Canal, and Lateral under the PIDP | MARIIS Division IV - Service Area | 2012-07-27 | 1st | NIA | LF | 5.476 | 120 | 2012-04-01 | 2012-07-06 | -5 | O | 0.3709 | 0.2256 | 0.1 | 0.03 | 0.07 | 0.05 | 84.65 | -
JA Achacoso Enterprises & Gen. Services | 33229 | L | D | SB | GE | Rehab./Reconst. Of Critical Section along National Highway, Road Slip along Kananga - Tungonan Hot Spring Road, KO996+526 - KO996+649 | Brgy. Lim-aw, Kananga, Leyte | 2014-08-07 | 1st & Final | VIII | LF | 2.5586 | 90 | 2014-02-14 | 2014-06-13 | 0 | C | 0.456 | 0.133 | 0.3 |  |  |  | 88.9 | 88.90% Satisfactory
JA ACHACOSO ENTERPRISES & GENERAL SERVICES | 33229 | L | A | MA | GE | Widening of National Roads, Palompon-Isabel-Merida-Ormoc Road, K1106+907-K1107+093, Ormoc | Ormoc | 2015-11-14 | Final | Leyte Fourth DEO | LF | 15.2755 | 136 | 2015-02-05 | 2015-06-20 | - | C | 0.393 | 0.2 | 0.3 | - | - | - | 89.3% | 89.3% Very Satisfactory
JABEN GENERAL CONTRACTING & ENG'G SERVICES | 34934 | L | A | SB | GE | Road Upgrading (Unpaved to Paved) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standards (HDM-4 Project Analysis) (Intermittent Section) of Mt. Province - Ilocos Sur via Kayan Road, K0396+957 to K0397+100, K0397+203 to K0397+366, Mt. Province | Mt. Province | 2015-09-01 | 1st & Final | Mountain Province DEO | LF | 8.898 | 150 | 2015-02-24 | 2015-07-24 | 0% | C | 0.438 | 0.133 | 0.3 | - | - | - | 87.1% | *87.1% Satisfactory
Jacinto Gerona Construction | 8165 | L | B | MA | GE | Construction of TIEZA Building | Mandaue City, Cebu | 2014-09-25 | Final | TIEZA | LF | 29.701 | 330 | 2012-10-01 | 2013-08-26 | 0 | C | 0.462 | 0.155 | 0.3 |  |  |  | 91.7 | 91.70% Very Satisfactory
Jacinto Gerona Construction | 8165 | L | B | MA | GE | Construction and Improvement of Various Facilities - Phase II | GMETV, Cagayan de Oro City | 2016-02-04 | 1st | TIEZA | LF | 25 | 300 | 2015-08-10 | 2016-07-10 | -19.39 | O | 0.389 | 0.254 | 0 | 0.03 | 0.07 | 0.05 | 79.35
JADE EAST TRADING AND CONSTRUCTION | 180 | L | B | MA | GE | Rehab./Reconst./Replacement of Balud Bridge along CSR | Naujan, Oriental Mindoro | 2015-11-20 | Final | Mindoro Oriental DEO | LF | 5.5976 | 180 | 2015-04-07 | 2015-10-03 | 0 | C | 0.482 | 0.133 | 0.3 | - | - | - | 91.5% | 91.5% Very Satisfactory
Jagon Builders | 24748 | L | B | SB | GB1 | Const. of MPB Northville 1-B, Punturin | Valenzuela City, Metro Manila | 2011-03-29 | 1st | NCR | LF | 2.567 | 90 | 2011-01-21 | 2011-04-20 | 14.44 | O | 0.296 | 0.24 | 0.15 | 0.03 | 0.045 | 0.05 | 81.1 | -
Jagonbuild Construction Corp. | 24748 | L | B | MA | GE2 | Const. of Flood Control Wall along Meycauayan River in Brgy. Pangkera | Valenzuela City | 2013-03-18 | 1st | NCR | LF | 7.051 | 120 | 2013-01-24 | 2013-05-23 | 16.2 | O | 0.298 | 0.3 | 0.15 | 0.023 | 0.018 | 0.033 | 82.2 | -
Jagonbuild Construction Corp. ( Formerly: Jagon Builders) | 24748 | B | A | MA | GE | Rehab./Reconst./Upgrading of Damaged Paved National Roads including Drainage Based on Pavement Management -4 (HDM-4) along Reina, Binondo, Manila | Binondo, Manila | 2014-08-15 | 1st & Final | NCR | LF | 5.0402 | 75 | 2014-05-30 | 2014-08-12 | 0 | C | 0.461 | 0.133 | 0.3 |  |  |  | 89.4 | 89.40% Very Satisfactory
Jagonbuild Construction Corp. ( Formerly: Jagon Builders) | 24748 | L | B | MA | GE2 | Const. of Flood Control Wall along Meycauyan River, Brgy. Pangkera | Valenzuela City | 2013-08-13 | Final | NCR | LF | 7.051 | 120 | 2013-01-24 | 2013-05-23 | 22.5 | C | 0.444 | 0.133 | 0.3 | - | - | - | 87.7 | 84.40% Satisfactory
Jagonbuild Construction Corp. ( Formerly: Jagon Builders) | 24748 | L | B | MA | GE | Preventive Maintenance along Bigaa-Plaridel via Bulacan and Malolos Road (km. 31+(-032) to km. 32+000 | Balagtas, Bulacan | 2014-11-07 | 1st & Final | III | LF | 11.4605 | 80 | 2014-02-18 | 2014-05-08 | 0% | C | 0.466 | 0.133 | 0.3 | - | - | - | 89.9% | 89.90% Very Satisfactory
Jagonbuild Construction Corp. ( Formerly: Jagon Builders) | 24748 | L | B | MA | GE | Rehab./Reconstruction of Damaged Paved National Roads based on Pavement Management System/Highway Development & Management-4 (HDM-4) (Intermittent Section) along C-4 Road (S02153LZ) | Malabon City | 2014-11-21 | 1st & Final | NCR | LF | 6.6848 | 151 | 2014-03-14 | 2014-08-11 | 0.83% | C | 0.417 | 0.133 | 0.3 | - | - | - | 85% | 85.00% Satisfactory
JAGONBUILD CONSTRUCTION CORP. (Formerly: Jagon Builders) | 24748 | L | B | MA | GE | Retrofitting/Strengthening of Permanent Bridge, Dampalit Bridge (B03202LZ) along Don Bautista St., Malabon City | Malabon City | 2015-06-05 | Final | Malabon-Navotas DEO | LF | 8.739 | 162 | 2015-03-10 | 2015-08-18 | (+) 54.32 | C | 0.471 | 0.133 | 0.3 | - | - | - | 90.4% | *90.4% Very Satisfactory
JAGONBUILD CONSTRUCTION CORP. (Formerly: Jagon Builders) | 24748 | L | B | MA | GE | Rehabilitation of Local Roads (Araneta Avenue and Tuazon Street), Brgy. Potrero, Malabon City | Brgy. Potrero, Malabon City | 2016-09-04 | 1st | Mal-Nav DEO | LF | 17.846 | 180 | 2015-03-10 | 2015-09-05 | 0.49% | O | 0.384 | 0.24 | 0.15 | 0.03 | 0.04 | 0.05 | 89.4% | -
Jagonbuild Construction Corporation | 24748 | L | B | MA | GE | Rehab./Reconst./ of Damaged Paved National Road including Drainage, Chanage 0436 to 0872 | San Juan City | 2014-08-08 | 1st | NCR | LF | 18.7304 | 150 | 2014-02-12 | 2014-07-11 | 6.33 | O | 0.386 | 0.24 | 0.15 | 0.015 | 0.047 | 0.05 | 89.4 | -
Jaime B. Ching Enterprises | 4256 | L | A | MA | GE | Completion of Sto. Angel Central-Poblacion V Bridge, Sta. Cruz, Laguna | Sta. Cruz, Laguna | 2014-08-14 | 1st & Final | IV-A | LF | 32.9965 | 239 | 2013-05-03 | 2013-12-27 | 0 | C | 0.484 | 0.133 | 0.3 |  |  |  | 91.7 | 91.70% Very Satisfactory
Jaime B. Ching Enterprises | 4256 | L | A | MB | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rd., Nat'l Secondary Rd. a) Paete-Famy-Pob. Rd., K0104+400-K0104+700 | Laguna | 2011-08-11 | 1st | IVA | LF | 4.065 | 115 | 2011-06-16 | 2011-10-09 | 0.09 | O | 0.361 | 0.3 | 0.15 | 0.03 | 0.045 | 0.05 | 93.6 | -
Jaime B. Ching Enterprises | 4256 | L | A | MB | GE1 | Completion of Santisima Cruz Bridge (Santisimo/Sto. Angel Bridge w/ Approaches Drainage Slope Protection & Other Road Network inc. RROW Acquisition & other related activities | Sta. Cruz, Laguna | 2012-03-17 | 1st | IVA | LF | 70.199 | 360 | 2011-06-30 | 2012-06-24 | 5.16 | O | 0.395 | 0.278 | 0.15 | 0.03 | 0.045 | 0.05 | 94.8 | -
Jaime B. Ching Enterprises | 4256 | L | A | MB | GE | Rehabilitation/Upgrading/Widening/Concreting along Bacolod North Road, K0025+500 - K0026+537; K0026+644 - K0027+671 with exception | E.B. Magalona, Negros Occidental | 2014-10-21 | 1st & Final | VI | LF | 26.6738 | 163 | 2014-05-12 | 2014-10-21 |  | C | 0.428 | 0.133 | 0.3 | - | - | - | 86.1% | 86.10% Satisfactory
Jaime B. Ching Enterprises | 4256 | L | A | MB | GE | Rehab./Reconst./Upgrading of Damaged Paved National Roads (Intermittent Sections) National Arterial Road BSR (kabankalan - Hinoba-an Section) Brgy. Masaling & Brgy. Caliling KO123+550 - KO125+539 | Cauayan, Negros Occidental | 2014-08-09 | Final | VI | LF | 36.4117 | 224 | 2013-02-07 | 2013-08-04 | 0 | C | 0.392 | 0.2 | 0.3 |  |  |  | 89.2 | 86.71% Satisfactory
Jaime B. Ching Enterprises | 4256 | L | A | MB | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rds., (Int. Sect.) Nat'l Arterial Rd., Bacolod South Rd. (Kabankalan-Hinoba-an Sect.) Brgy. Masaling & Brgy. Caliling Sect., K0123+550-K0125+539 | Cauayan, Negros Occidental | 2013-08-09 | 2nd | VI | LF | 36.412 | 209 | 2013-02-07 | 2013-09-03 | 10.83 | O | 0.342 | 0.24 | 0.15 | 0.03 | 0.042 | 0.033 | 83.7 | -
Jaime B. Ching Enterprises | 4256 | L | A | MB | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l. Rds., (Int. Sect.) Nat'l. Arterial Rd., Bacolod South Rd. (Kabankalan-Hinoba-an Sect.), Brgy. Masaling & Brgy. Caliling Sect. K0123+500-K0125+539 | Cauayan, Negros Occidental | 2013-03-13 | 1st | VI | LF | 34.589 | 179 | 2013-02-07 | 2013-08-04 | 14.85 | O | 0.345 | 0.256 | 0.15 | 0.03 | 0.05 | 0.033 | 86.4 | -
Jaime B. Ching Enterprises | 4256 | L | A | MB | GE | Rehab./Reconst./Upgrading of Paved National Road (intermittent Section) along Bacolod South Road (a) K0065+635 - K0067+003 (b) K0072+000 - K0072+020 | Himamaylan City, Negros Occidental | 2014-08-08 | Final | VI | LF | 21.0323 | 201 | 2013-01-28 | 2013-08-16 | 0.23 | C | 0.349 | 0.2 | 0.3 |  |  |  | 84.9 | 84.21% Satisfactory
Jaime B. Ching Enterprises | 4256 | L | A | MB | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rd. (Int. Sect.) along Bacolod South Rd., a)K0065+635-K0067+003, b)K0072+000-K0072+020 | Himamaylan City, Negros Occidental | 2013-08-10 | 2nd | VI | LF | 21.032 | 201 | 2013-01-28 | 2013-08-16 | -1.08 | O | 0.332 | 0.24 | 0.139 | 0.03 | 0.035 | 0.05 | 82.6 | -
Jaime B. Ching Enterprises | 4256 | L | A | MB | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l. Rd. (Int. Sect.) along Bacolod South Rd., a)K0065+635-K0067+003, b)K0072+000-K0072+020 | Himamalayan City, Negros Occidental | 2013-03-12 | 1st | VI | LF | 21.032 | 171 | 2013-01-28 | 2013-07-17 | -1.91 | O | 0.384 | 0.248 | 0.131 | 0.018 | 0.035 | 0.033 | 84.9 | -
Jaime B. Ching Enterprises | 4256 |  |  |  |  | Reconst. of Jct. Bagonawa-La Castellana-Isabela Rd., Sta.64+877.90 - Sta.65+703.60 w/ exception |  | 2010-06-03 |  | VI |  | 9.453 | 96 |  |  |  | O | 0.372 | 0.24 | 0.15 | 0.022 | 0.047 | 0.033 | 86.4 | -
Jaime B. Ching Enterprises | 4256 | L | A | MB | GE1 | Rehab. of Bacolod South Road (Pilar-Marina Section) |  | 2009-05-28 | 1st | VI |  | 9.484 | 116 |  |  |  | O | 0.373 | 0.24 | 0.15 | 0.015 | 0.045 | 0.033 | 85.6 | -
Jaime B. Ching Enterprises | 4256 | L | A | MB | GE | Rehab./Reconst./Upgrading of Damaged Paved National Road Dumaguete North Road (DNR), K0097+042.20 to K0097+385.14, K0097+801.64 to K0097+980, K0098+038.14 to K0099+680.40 ……………. | Negros Oriental | 2014-08-14 | 1st & Final | VII | LF | 41.1195 | 200 | 2013-02-09 | 2013-08-27 | 0 | C | 0.419 | 0.147 | 0.3 |  |  |  | 86.6 | 86.60% Satisfactory
Jaime B. Ching Enterprises | 4256 | L | A | MB | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rd., Dumaguete North Rd. (DNR) K0097+042.20-K0097+385.14, K0097+801.64-K0097+980.14, K0098+038.14-K0099+680.40, K0110+076.4-K0110+225.90, K0110+239.40-K0110+475.84 | Negros Oriental | 2013-08-22 | 1st | VII | LF | 41.119 | 200 | 2013-02-09 | 2013-08-27 | -5.69 | O | 0.315 | 0.3 | 0.093 | 0.03 | 0.055 | 0.033 | 82.6 | -
Jaime B. Ching Enterprises | 4256 | L | A | MB | GE1 | Rd. Upgrading (Gravel to Paved) Int. Sect. at Mabina -Ayongon Rd. (MAR) Sec.1:K0126+764-K0128+385; Sec.2;K0131+862-K0132+282 | Negros Oriental | 2013-08-22 | 1st | VII | LF | 44.888 | 205 | 2013-02-09 | 2013-09-01 | -9.65 | O | 0.333 | 0.3 | 0.054 | 0.03 | 0.05 | 0.033 | 80 | -
JAIME B. CHING ENTERPRISES | 4256 | L | A | MB | GE | Widening of Sum-ag Abuanan Road | K0010+(-346)- K0010+825, Bacolod City | 2015-06-11 | Final | Bacolod City | LF | 26.891 | 160 | 2015-03-02 | 2015-08-08 | 62.5% | C | 0.426 | 0.147 | 0.3 | - | - | - | 87.3% | *87.3% Satisfactory
JAIME B. CHING ENTERPRISES | 4256 | L | A | MB | GE | Construction/Widening of Langa-og Bridge (B00152NR) along Bacolod North Road | Victorias City, Negros Occidental | 2015-08-25 | 1st | Negros Occidental 1st | LF | 9.293 | 210 | 2015-02-19 | 2015-09-16 | -4.76% | O | 0.379 | 0.24 | 0.102 | 0.03 | 0.05 | 0.033 | 83.4% | -
JAIME B. CHING ENTERPRISES | 4256 | L | A | MB | GE | "Cluster A" - Widening of Permanent Bridges 2) Pahanocoy Bridge 3 along Bacolod Circumferential Road (South), Bacolod City | Bacolod City | 2015-11-09 | 1st | Bacolod City DEO | LF | 18.0092 | 210 | 2015-03-02 | 2015-09-27 | - | C | 0.474 | 0.133 | 0.3 | - | - | - | 90.7% | 90.7% Very Satisfactory
JAIME B. CHING ENTERPRISES | 4256 | L | A | MB | GE | Construction/Widening of Langa-og Bridge (B00152NR) along Bacolod North Road, Victorias City, Negros Occidental | Victorias City, Negros Occidental | 2015-11-19 | Final | Negros Occidental 1st DEO | LF | 9.2926 | 210 | 2015-02-19 | 2015-09-16 | - | C | 0.473 | 0.082 | 0.3 | - | - | - | 85.5% | 84.24% Satisfactory
JAIME B. CHING ENTERPRISES | 4256 | L | A | MB | GE | Upgrading/Concreting (Gravel to Paved) of Prosperidad-Quezon-Cabaron Road, K0067+806 - K0069+697, San Carlos City, Negros Occidental | San Carlos City, Negros Occidental | 2015-11-18 | Final | Negros Occidental 1st DEO | LF | 40.7046 | 149 | 2015-02-13 | 2015-07-11 | - | C | 0.431 | 0.134 | 0.3 | - | - | - | 86.5% | 86.5% Satisfactory
Jakboa Builders |  |  |  | MB |  | Supply of Labor and Materials for the Retrofitting of ATD Building | NCR | 2016-12-07 | 1st & Final | DOST | LF | 3.866 | 100 | 2015-11-17 | 2016-02-27 | 0 | C | 0.49 | 0.2 | 0.3 | - | - | - | 99 | *99.00% Outstanding
Jakboa Builders (JB) | 31563 | L | B |  | GB1 | Renovation of Comfort Rooms at the Sports Science and Wellness Center | CAS, UP Manila | 2011-11-24 | 1st | UP | LF | 2.067 | 60 | 2011-06-30 | 2011-12-05 | 51.796 | O | 0.4 | 0.3 | 0 | 0.03 | 0.031 | 0.017 | 77.8 | -
JAM - C Builders | 32870 | L | B | SB | GE | Road Upgrading along Capas - San Jose - Mayantoc - Malacampa Road, a. K0144+193 - K0144+555 b. K0146+515 - K0146+524, Mayantoc, Tarlac, Modified to Rehab./Reconst./Upgrading of Damaged Paved National Roads 1. Capas - San Jose - Mayantoc - Malacampa Road, a. K0147+881 - K0149+122.50 with exception, Mayantoc Tarlac | Mayantoc, Tarlac | 2014-08-07 | 1st & Final | III | LF | 7.5213 | 120 | 2014-04-28 | 2014-08-25 | 16.67 | C | 0.447 | 0.133 | 0.3 |  |  |  | 88 | 88.00% Satisfactory
Jamari Construction (Formerly: FRAE Construction) | 21580 | L | B | MA | GE | Widening of Carmen-Patag-Bulua Road Section K1441+500-K1443+739.84 (both sides) | Cagayan de Oro City | 2014-10-20 | 1st | X | LF | 24.8247 | 227 | 2014-02-04 | 2014-09-18 | -0.47% | O | 0.361 | 0.253 | 0.145 | 0.022 | 0.028 | 0.033 | 84.2% | 84.20% Satisfactory
JAMARI CONSTRUCTION (Formerly: Frae Construction) | 21580 | L | B | MA | GE | Off-carriageway Improvement-Gingoog-Claveria-Villanueva Road, K1385+1041 (with exceptions), Villanueva, Misamis Oriental | Villanueva, Misamis Oriental | 2015-06-08 | 1st | Misamis Oriental Second DEO | LF | 27.678 | 171 | 2015-02-02 | 2015-07-22 | - | O | 0.328 | 0.3 | 0.102 | 0.03 | 0.039 | 0.033 | 83.2% | -
JAMARI CONSTRUCTION (Formerly: Frae Construction) | 21580 | L | B | MA | GE | Widening of Carmen-Patag-Bulua Road Section, K1441+500 to K1443+739.84 (both sides), Cagayan de Oro City | Cagayan de Oro City | 2015-06-11 | Final | Cagayan de Oro City First DEO | LF | 26.439 | 314 | 2015-02-04 | 2015-12-14 | - | C | 0.467 | 0.2 | 0.3 | - | - | - | 96.7% | *89.2% Very Satisfactory
JAMARI CONSTRUCTION (Formerly: Frae Construction) | 21580 | L | B | MA | GB | Construction of Four (4) Storey, Twelve (12) Classroom Building at Doña Juana E/S, Quezon City | Quezon City | 2015-06-02 | 1st | Quezon City 1st DEO | LF | 17.737 | 270 | 2015-01-19 | 2015-10-08 | (+) 2.97 | O | 0.38 | 0.24 | 0.15 | 0.015 | 0.02 | 0.05 | 85.5% | -
JAMARI CONSTRUCTION (Formerly: Frae Construction) | 21580 | L | B | MA | GE | Off-carriageway Improvement Gingoog - Claveria - Villanueva Road, K1385+1041 (with exceptions), Villanueva, Misamis Oriental | Villanueva, Misamis Oriental | 2015-09-04 | 1st | Misamis Oriental 2nd DEO | LF | 27.678 | 201 | 2015-02-02 | 2015-08-21 | (-14.7)% | O | 0.385 | 0.296 | 0.003 | 0.03 | 0.037 | 0 | 75.1% | -
JAMEETRIX Construction | 19176 | L | A | SB | GE | Concreting of Roads for Package B, Brgy. Centro | Davao City | 2014-10-30 | 1st & Final | XI | LF | 1.9802 | 130 | 2014-06-02 | 2014-10-09 |  | C | 0.416 | 0.123 | 0.3 | - | - | - | 83.9% | 83.90% Satisfactory
JAN ALEXIS BUILDERS AND DEVELOPER | 36457 | L | C | SB | GB | Construction of Multi Purpose Building | Barangay Namulditan, Hingyon, Ifugao | 2015-06-07 | 1st | Ifugao 1st DEO | LF | 1.902 | 90 | 2015-04-13 | 2015-07-11 | (+) 4.25 | O | 0.327 | 0.25 | 0.15 | 0.022 | 0.052 | 0.05 | 85.1% | -
Jann-Norris Construction and Supplies | 35880 | L | A | SB | GE | Const. of Bakir Flood Control along Nueva Vizcaya-Ifugao Road | Bagabag, Nueva Vizcaya | 2014-08-14 | Final | II | LF | 6.9437 | 75 | 2013-06-06 | 2013-08-19 | 0 | C | 0.385 | 0.143 | 0.3 |  |  |  | 82.8 | 85.56% Satisfactory
Jann-Norris Construction and Supplies | 35880 | L | A | SB | GE2 | Const. of Bakir Flood Control along Nueva Vizcaya-Ifugao Rd. | Bagabag, Nueva Vizcaya | 2013-08-13 | 1st | II | LF | 6.944 | 75 | 2013-06-06 | 2013-08-19 | -5.56 | O | 0.362 | 0.3 | 0.094 | 0.03 | 0.055 | 0.033 | 87.4 | -
JANN-NORRIS CONSTRUCTION AND SUPPLIES | 35880 | L | AAA | MA | GE | Daang Maharlika (LZ), K0247+558.98 to K0249+000 | Bambang, Nueva Vizcaya | 2015-06-09 | 1st | Nueva Vizcaya 1st DEO | LF | 33.387 | 195 | 2015-02-11 | 2015-08-24 | 1.15% | O | 0.352 | 0.3 | 0.15 | 0.022 | 0.045 | 0.033 | 90.2% | -
JANN-NORRIS CONSTRUCTION AND SUPPLIES | 35880 | L | A | MA | GE | Papaya - Malabing - Wangal - Binugawan - Tadji - Runruno Road, K0314+169 to K0314+747, K0316+879 to K0317+341, K0317+847 to K0318+050, Runruno, Quezon, Nueva Vizcaya | Runruno, Quezon, Nueva Vizcaya | 2015-09-02 | 1st & Final | NV 1st DEO | LF | 30.736 | 194 | 2015-02-11 | 2015-08-23 | 3.43% | C | 0.438 | 0.177 | 0.3 | - | - | - | 91.5% | *91.5% Very Satisfactory
JANN-NORRIS CONSTRUCTION AND SUPPLIES | 35880 | L | A | SB | GB | Local Infrastructure Program - Construction of Quezon Multi-Purpose Building, Quezon, Nueva Vizcaya | Quezon, Nueva Vizcaya | 2015-11-18 | Final | NUEVA VIZCAYA 1ST DEO | LF | 7.0159 | 210 | 2015-02-18 | 2015-09-15 | - | C | 0.44 | 0.2 | 0.3 | - | - | - | 94% | 94% Very Satisfactory
Jann-Norris Construction and Supplies/Mabuhay Conglomerate Asphalt Inc. (JV) | 35880 | L | A | MA | GE | Asset Preservation of National Roads. Preventive Maintenance, based on PMS/HDM-4, Intermittent Section, Aritao-Quirino Road, K0244+378 - K0246+000 and K0247+227 - K0247+545 | Dupax del Sur/Dupax del Norte, Nueva Vizcaya | 2014-10-30 | 1st & Final | II | LF | 15.8305 | 90 | 2014-01-29 | 2014-04-28 | 88.3% | C | 0.437 | 0.133 | 0.3 | - | - | - | 87% | 87.00% Satisfactory
Japuz-Jansol Enterprises | 22869 | L | D | SB | GE2 | Construction of Teruvian Dam & Canal System |  | 04/13-18/09 | 1st | NIA |  | 4.178 | 90 |  |  |  | O | 0.3515 | 0.18 | 0.15 | 0.03 | 0.064 | 0.05 | 82.55 | -
JAPUZ-JANSOL ENTERPRISES | 22869 | L | B | SB | GE | Construction of Water Supply Level II (Cluster 2), Taguilon, Dapitan City, Zamboanga del Norte | Taguilon, Dapitan City, Zamboanga del Norte | 2015-06-05 | Final | Zamboanga del Norte 3rd DEO | LF | 1.905 | 80 | 2015-03-12 | 2015-05-30 | 0% | C | 0.429 | 0.133 | 0.3 | - | - | - | 86.2% | *86.2% Satisfactory
Jargon Construction & Supply | 23474 | L | B | MA | GE | Road Upgrading (Gravel to paved) Based on Gravel Road Strategies Traffic Benchmark for Upgrading to Paved Road Standard (HDM-4) Project Analysis (Intermittent Section) along Maitum - Lake Sebu Road, K1777+(-127) - K1779+540 | Maitum, Sarangani Province | 2014-08-14 | 1st & Final | XII | LF | 47.9745 | 216 | 2013-01-31 | 2013-09-03 | 0 | C | 0.447 | 0.186 | 0.3 |  |  |  | 93.3 | 93.30% Very Satisfactory
Jargon Construction & Supply | 23474 | L | B | MA | GB1 | Const. of MPB at Phil. Science High Sch., Paraiso | Koronadal City, South Cotabato | 2013-08-06 | Final | XII | LF | 4.933 | 190 | 2012-10-23 | 2013-04-30 | 0.55 | C | 0.43 | 0.133 | 0.3 | - | - | - | 86.3 | 85.82% Satisfactory
Jargon Construction & Supply | 23474 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Paved), Intermittent Sect., along Maitum-Lake Seibu Rd., Km.1777+(-127)-Km.1779+540 | Maitum, Sarangani Province | 2013-03-22 | 1st | XII | LF | 45.583 | 175 | 2013-01-31 | 2013-07-24 | 25.79 | O | 0.383 | 0.28 | 0.15 | 0.03 | 0.033 | 0.033 | 90.9 | -
Jargon Construction & Supply | 23474 | L | B | MA | GB1 | Const. of MPB, Phil. Science School, Paraiso | Koronadal City, South Cotabato | 2013-03-20 | 1st | XII | LF | 4.933 | 190 | 2012-10-23 | 2013-04-30 | 1.32 | O | 0.352 | 0.24 | 0.15 | 0.03 | 0.05 | 0.033 | 85.5 | -
Jargon Construction & Supply | 23474 | L | B | MA | GE1 | Replacement of Temp. to Perm. Bridges, Luyong Bridge along Maitum-Lake Sebu Rd. | Maitum, Sarangani Province | 2013-03-21 | 1st | XII | LF | 8.206 | 140 | 2013-01-31 | 2013-06-19 | 13.4 | O | 0.368 | 0.24 | 0.15 | 0.03 | 0.033 | 0.033 | 85.4 | -
Jargon Construction & Supply | 23474 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Paved) along Awang-Upi Lebak-Kalamansig-Palimbang-Sarangani Rd. (NEP-Km.1958+389-Km.1960+000) realigned to (Km.2032+015-Km.2033+600) | Palimbang, Sultan Kudarat | 2013-03-13 | 1st | XII | LF | 34.764 | 278 | 2012-06-28 | 2013-04-01 | 10.42 | O | 0.348 | 0.228 | 0.15 | 0.03 | 0.045 | 0.05 | 85.1 | -
Jargon Construction & Supply | 23474 |  |  |  |  | Road Upgrading of Isulan Hwy. Jct. Dukay-Bagumbayan-Sen. Ninoy Aquino Road (Tayugo Section) |  | 2010-03-03 |  | XII |  | 13.257 | 155 |  |  |  | O | 0.374 | 0.243 | 0.15 | 0.03 | 0.05 | 0.033 | 88 | -
Jargon Construction & Supply | 23474 |  |  |  |  | Road Upgrading of Isulan Hwy. Jct. Dukay-Bagumbayan-Sen. Ninoy Aquino Road (Sitio Katipunan Section) |  | 2010-03-03 |  | XII |  | 10.456 | 128 |  |  |  | O | 0.32 | 0.24 | 0.15 | 0.03 | 0.05 | 0.033 | 82.3 | -
Jargon Construction & Supply | 23474 |  |  |  |  | Sarangani-Davao del Sur Coastal Road (Gumasa Section) |  | 2010-06-15 |  | XII |  | 9.606 | 150 |  |  |  | O | 0.274 | 0.3 | 0.15 | 0.03 | 0.047 | 0.033 | 83.4 | -
JARGON CONSTRUCTION & SUPPLY | 23474 | L | B | MA | GB | Rehabilitation of Upper Buayan Bridge along Digos-Makar Road | Malungon, Sarangani Province | 2015-06-12 | Final | Sarangani DEO | LF | 3.29 | 60 | 2014-02-23 | 2014-04-23 | 0% | C | 0.5 | 0.133 | 0.3 | - | - | - | 93.3% | *93.3% Very Satisfactory
JARGON CONSTRUCTION & SUPPLY | 23474 | L | B | MA | GE | Rehabilitation/Major Repair of Talok Bridge along Sarangani-Sultan Kudarat, Coastal Road | Kiamba, Sarangani Province | 2015-09-02 | 1st & Final | Saranggani | LF | 1.305 | 60 | 2015-03-11 | 2015-05-09 | 0% | C | 0.5 | 0.133 | 0.3 | - | - | - | 93.3% | *93.3% Very Satisfactory
Jargon Construction & Supply | 23474 | L |  | MA |  | Construction of Perimeter Fence/ Gates | PSHS-Caraga Campus, Ampayon, Butuan City | 2016-09-21 | Final | DOST | LF | 4.896 | 210 | 2015-12-23 | 2016-07-19 | 0 | C | 0.498 | 0.2 | 0.3 | - | - | - | 99.8 | 99.43% Outstanding
Jaro Builders & Construction Supply | 25560 | L | B | SB | GE | Construction of Minas River Control, Baco, Oriental Mindoro | Baco, Oriental Mindoro | 2014-08-11 | 1st & Final | IV-B | LF | 9.0121 | 78 | 2014-02-24 | 2014-05-12 | 0 | C | 0.414 | 0.133 | 0.3 |  |  |  | 84.7 | 84.70% Satisfactory
Jaro Builders & Construction Supply | 25560 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Paved) CSR Jct. Minas Rd., K0050+(-610)-K0050+228 | Victoria, Oriental Mindoro | 2013-08-01 | Final | IVB | LF | 9.45 | 90 | 2013-01-28 | 2013-04-27 | 1.11 | C | 0.367 | 0.2 | 0.3 | - | - | - | 86.7 | 87.84% Satisfactory
Jaro Builders & Construction Supply | 25560 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Paved) CSR Jct. Minas Rd., K0050+(-)610-K0050+228 | Victoria, Oriental Mindoro | 2013-03-19 | 1st | IVB | LF | 9.45 | 90 | 2013-01-28 | 2013-04-27 | 5.05 | O | 0.366 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 88.6 | -
Jasa Builders | 31330 | L | B | MA | GE | Widening of Urdaneta Jct.-Dagupan Road (calasiao Section) Km.205+522 to Km. 206+161 with exception | Calasiao, Pangasinan | 2014-08-12 | Final | I | LF | 17.8286 | 180 | 2013-01-16 | 2013-07-14 | 0 | C | 0.399 | 0.133 | 0.3 |  |  |  | 83.2 | 87.46% Satisfactory
Jasa Builders | 31330 | L | B | MA | GE1 | Widening of Urdaneta Jct.-Dagupan Rd. (Calasiao Sect.) Km. 205+522-Km. 206+161 w/ exception | Calasiao, Pangasinan | 2013-08-02 | 2nd | I | LF | 16.211 | 201 | 2013-01-16 | 2013-08-04 | 2.43 | O | 0.347 | 0.3 | 0.15 | 0.03 | 0.047 | 0.05 | 92.4 | -
Jasa Builders | 31330 | L | B | MA | GE1 | Widening of Urdaneta Jct.-Dagupan Rd. (Calasiao Sect.) Km.205+522-Km.206+161 w/ exception | Calasiao, Pangasinan | 2013-03-14 | 1st | I | LF | 16.211 | 180 | 2013-01-16 | 2013-07-14 | 16.45 | O | 0.355 | 0.3 | 0.15 | 0.024 | 0.02 | 0.033 | 88.2 | -
Jasa Builders | 31330 | L | A | MA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rd. along Pangasinan-Zambales Rd., K0333+500-K0335+000 | Pangasinan | 2013-08-08 | Final | I | LF | 17.674 | 126 | 2013-01-28 | 2013-06-02 | 1.59 | C | 0.489 | 0.133 | 0.3 | - | - | - | 92.2 | 86.38% Satisfactory
Jasa Builders | 31330 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rd. along Pangasinan-Zambales Rd., K0333+500-K0335+000 | Pangasinan | 2013-03-15 | 1st | I | LF | 17.674 | 96 | 2013-01-28 | 2013-05-03 | 8.42 | O | 0.289 | 0.3 | 0.15 | 0.018 | 0.035 | 0.033 | 82.5 | -
JASA BUILDERS | 31330 | L | A | MA | GE | Construction of River Bank Protection along Marusay River Talibaew Section | Calasiao, Pangasinan (Sta. 0+276 - Sta. 1+212) | 2015-06-10 | 1st | Pangasinan 4th DEO | LF | 18.217 | 208 | 2015-02-12 | 2015-09-07 | 32.53% | O | 0.352 | 0.24 | 0.15 | 0.03 | 0.04 | 0.033 | 84.5% | -
JASA BUILDERS | 31330 | L | A | MA | GE | Construction/Rehabilitation of Drainage along National Roads, San Carlos-Calasiao Road, K0.210+000 - K0.211+110 (with exception (B/S)), Calasiao, Pangasinan | Calasiao, Pangasinan | 2015-11-18 | 1st | PANGASINAN 4TH DEO | LF | 18.2254 | 220 | 2015-04-24 | 2015-11-29 | 0.0058 | OG | 0.387 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 91.2% | 91.2% Very Satisfactory
JASA BUILDER'S | 31330 | L | A | SB | GE | Construction of River Bank Protection along Marusay River, Sta. 0+276 to Sta. 1+212, Talibaew Section, Calasiao, Pangasinan | Sta. 0+276 to Sta. 1+212, Talibaew Section, Calasiao, Pangasinan | 2015-09-03 | Final | Pangasinan 4th DEO | LF | 18.217 | 208 | 2015-02-12 | 2015-09-08 | (+)38.61 | C | 0.381 | 0.2 | 0.3 | - | - | - | 88.1% | *85.94% Satisfactory
JASA BUILDER'S | 31330 | L | A | MA | GE | Rehab./Reconst./Upgrading of Pangasinan-Zambales Road(Widening), K0315+599 to K0316+909, Alaminos City, Pangasinan | K0315+599 to K0316+909, Alaminos City, Pangasinan | 2015-09-01 | 1st | Pangasinan 1st DEO | LF | 30.3 | 180 | 2015-05-21 | 2015-11-17 | (+)0.59 | O | 0.368 | 0.239 | 0.15 | 0.023 | 0.042 | 0.05 | 87.2% | -
Jasa Builders | 31330 | L | A | MA | GE | Rehab./Reconst'n./ Upgrading of Damaged Paved National Roads Including Drainage based on PMS/HDM-4(Intermittent Section); Pang-Zamb. Road K0302+000 to K0303+000/K0302+580- K0303+420(New Station);Pang.-Zamb. Road K0307+000 to K0308+000; Pang.-Zamb. Road K0309+000 to K0309+844; Pang. Zamb. Road K0313+331 to K0313+421 | Pangasinan-Zambales Road | 2014-10-27 | 1st & Final | I | LF | 43.4274 | 165 | 2014-01-29 | 2014-07-12 | 11.52% | C | 0.437 | 0.134 | 0.3 | - | - | - | 87.1% | 87.10% Satisfactory
Jasa Builders | 31330 | L | B | MA | GE2 | Const. of Palagao Flood Control Proj. along Jct. Ipil-Quirino Bdry. Rd., Sta.000+072-Sta.000+406, Palagao | Jones, Isabela | 2013-03-15 | Final | II | LF | 16.975 | 160 | 2012-10-08 | 2013-03-16 | 54.67 | C | 0.417 | 0.133 | 0.3 | - | - | - | 85 | 85.12% Satisfactory
JASA BUILDERS / ALCEL CONSTRUCTION (JV) | 31330 | L | A | SB | GE | Construction of Alaminos Gym | Poblacion, Alaminos City, Pangasinan | 2015-11-11 | 1st | TIEZA | LF | 19 | 262 | 2015-04-20 | 2016-01-09 | 0 | O | 0.387 | 0.3 | 0.15 | 0.03 | 0.041 | 0.05 | 95.8 | -
Jasa Builders / V.B. Manubay Construction (Joint Venture) | JV-12-055 | L | B | MA | GE2 | Const. of Flood Control Structures Pangal Sur Flood Control, Sta.000+000-Sta.000+528, Pangal Sur | Echague, Isabela | 2013-03-15 | Final | II | LF | 19.109 | 160 | 2012-08-17 | 2013-01-23 | 24.69 | C | 0.417 | 0.2 | 0.3 | - | - | - | 91.7 | 90.50% Very Satisfactory
Jasa Builders / V.B. Manubay Construction (Joint Venture) | JV-12-056 | L | B | MA | GE1 | Conc. of Jct. Ipil-Quirino Bdry. Rd. K0369+807-K0370+864, K0374+276-K0375+080 (w/ exceptions) | San Agustin, Isabela | 2013-03-15 | Final | II | LF | 17.179 | 180 | 2012-08-21 | 2013-02-16 | 0 | C | 0.436 | 0.133 | 0.3 | - | - | - | 86.9 | 88.82% Satisfactory
Jasa Builders /Alcel Construction (JV) | 31330 | L | A | SB | GE | Construction of Alaminos Gym | Poblacion, Alaminos City, Pangasinan | 2016-03-03 | 2nd | TIEZA | LF | 21 | 337 | 2016-04-20 | 2016-04-24 |  | O | 0.388 | 0.3 | 0.15 | 0.03 | 0.063 | 0.05 | 98.1
Jasmig Construction Supply | 26069 | L | B | MA | GE | Const./Rehab. Of Flood Control System along Palico-Balatan-Batangas City Road (Intermittent) Tuy & Balayan Sect. Tuy & Balayan | Tuy & Balayan, Batangas | 2014-08-06 | Final | IV-A | LF | 7.0499 | 279 | 2012-12-10 | 2013-09-14 | 0 | C | 0.475 | 0.2 | 0.3 |  |  |  | 97.5 | 90.69% Very Satisfactory
Jasmig Construction Supply | 26069 | L | B | MA | GE1 | Const./Rehab. Of Flood Control System along Palico-Balayan-Batangas City Rd. (Int.) Tuy & Balayan Sect. | Tuy & Balayan, Batangas | 2013-07-31 | 2nd | IVA | LF | 7.05 | 279 | 2012-12-10 | 2013-09-04 | -1.5 | O | 0.347 | 0.256 | 0.135 | 0.03 | 0.04 | 0.033 | 84.1 | -
Jasmig Construction Supply | 26069 | L | B | MA | GE2 | Const./Rehab. of Flood Control System along Palico-Balayan-Batangas City Road (Intermittent) Tuy & Balayan Sect. | Tuy & Balayan, Batangas | 2013-03-13 | 1st | IVA | LF | 7.05 | 171 | 2012-12-10 | 2013-05-29 | 8.46 | O | 0.382 | 0.24 | 0.15 | 0.03 | 0.047 | 0.033 | 88.2 | -
Jasmig Construction Supply | 26069 | L | B | MA | GE1 | Prev. Maint. (MFO-I) Int. Sect. of Secondary Rd., Batanagas-Lobo Rd. from K0117+258-K0105+(-459)-K0105+000 | Batangas City, Batangas | 2013-08-16 | Final | IVA | LF | 5.082 | 60 | 2013-02-12 | 2013-04-12 | 30 | C | 0.467 | 0.2 | 0.3 | - | - | - | 96.7 | 91.06% Very Satisfactory
Jasmig Construction Supply | 26069 | L | B | MA | GE1 | Prev. Maint. (MFO-1) Intermittent Sect. Secondary Rd. at Batangas-Lobo Rd. from K0117+258-K0105+(-459)-K0105+000 | Batangas City, Batangas | 2013-03-12 | 1st | IVA | LF | 5.082 | 60 | 2013-02-12 | 2013-04-12 | 23.42 | O | 0.348 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 87.3 | -
Jasmig Construction Supply | 26069 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rd. (MFO-2) (Int. Sect.) Sec. Rd. along Batangas-Quezon Rd., K0134+(-651)-K0134+000 | Batangas City | 2013-07-31 | Final | IVA | LF | 11.699 | 90 | 2013-02-12 | 2013-05-12 | 53.33 | C | 0.279 | 0.2 | 0.3 | - | - | - | 77.9 | 85.88% Satisfactory
Jasmig Construction Supply | 26069 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of (Int. Sect.) Secondary Rd. along Batangas-Quezon Rd., K0134+(-651)-K0134+000 | Batangas City | 2013-03-12 | 1st | IVA | LF | 11.699 | 90 | 2013-02-12 | 2013-05-12 | 36.33 | O | 0.387 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 91.2 | -
JASMIG CONSTRUCTION SUPPLY | 26069 | L | B | MA | GE | Widening of Manila - Batangas Road, K0096+(-120) to K0098+980 (with exceptions) including Drainage System | Batangas Province | 2015-06-02 | 1st | Regional Office No. IV-A | LF | 95.533 | 330 | 2014-10-08 | 2015-09-02 | 6.8% | O | 0.316 | 0.3 | 0.15 | 0.03 | 0.045 | 0.033 | 87.4% | -
Jasmin Construction | 9561 |  |  |  |  | Rehab./Reconst. Of Damaged Paved Nat'l. Rds., Baras-Gigmoto Rd. |  | 2010-08-17 |  | V |  | 12.085 | 205 |  |  |  | O | 0.328 | 0.286 | 0.1 | 0.02 | 0.03 | 0.05 | 81.4 | -
Jaykris Enterprises | 30906 | L | B | MA | GE1 | Repair/Rehab./Impv't. of Slipped Sect., along Lanao-Pagadian-Zamboanga City Rd., Basalem Sect., Sta.1724+940-Sta.1725+025, Basalem, Buug | Zamboanga Sibugay | 2013-03-18 | Final | IX | LF | 9.653 | 128 | 2012-08-24 | 2012-12-30 | 1.1 | C | 0.481 | 0.133 | 0.3 | - | - | - | 91.4 | 88.10% Satisfactory
JAYKRIS ENTERPRISES | 30906 | L | B | MA | GE | Concrete Paving of Shoulder with Drainage along Juction Diplahan - Malangas Port Road, K1740+270.9 to K1749+928, Both Sides w/ Exception, Zamboanga Sibugay | Zamboanga Sibugay | 2015-06-08 | 1st | Zamboanga Sibugay 1st DEO | LF | 44.549 | 162 | 2015-03-23 | 2015-08-31 | 9.11% | O | 0.378 | 0.24 | 0.15 | 0.03 | 0.05 | 0.033 | 88.1% | -
JAYKRIS ENTERPRISES | 30906 | L | B | SB | GB | Rehabilitation/Reconstruction of Slope Protection along Imelda-Bayog-Kumalarang-Margosatubig Road, K1751+101-K1751+146.55(RS); K1751+292-K1751+312.61(RS); K1751+981-K1752+123.55(RS); K1755+180-K1755+260.20(RS); K1755+352-K1755+553.77(RS),K1755+815-K1755+990.29(RS), Imelda, Zamboanga Sibugay | Imelda, Zamboanga Sibugay | 2015-11-11 | 2nd | Zamboanga Sibugay 1st DEO | LF | 13.9661 | 175 | 2015-03-23 | 2015-09-13 | 2.38% | OG | 0.382 | 0.237 | 0.15 | 0.02 | 0.033 | 0.05 | 87.2% | 87.2% Satisfactory
JAYKRIS ENTERPRISES & CONSTRUCTION (Formerly: Jaykris Enterprises) | 30906 | L | B | SB | GE | Rehabilitation/Reconstruction of Slope Protection along Imelda-Bayog-Kumalarang-Margosatubig Road, K1751+101-K1751+146.55 (RS); K1751+292-K1751+312.61 (RS); K1751+981-K1752+123.35 (RS);K1755+180-K1755+260.20 (RS), K1755+353-K1755+553.77 (RS) and K1755+815-K1755+990.29 (RS), Imelda, Zamboanga Sibugay | Imelda, Zamboanga Sibugay | 2015-09-01 | 1st | Zamboanga Sibugay 1st | LF | 13.966 | 228 | 2015-03-23 | 2015-11-05 | (+)0.987 | O | 0.3142 | 0.3 | 0.15 | 0.03 | 0.051 | 0.05 | 89.52% | -
JB & SONS TRADING & CONSTRUCTION | 30133 | L | B | SB | GE | Widening of Permanent Bridge from 1 lane to 2 lanes Caramay Bridge along Puerto Princesa South Road | Espanola, Palawan | 2015-11-10 | 1st | Palawan 2nd Deo | LF | 7.1255 | 215 | 2015-04-15 | 2015-11-15 | -0.03 | OG | 0.341 | 0.3 | 0.12 | 0.008 | 0.035 | 0.033 | 83.7% | 83.7% Satisfactory
JB & Sons Trading and Construction | 30133 | L | B | SB | GE2 | Const. of Tigaplan Flood Control along Puerto Princesa South Rd. | Brookes Point, Palawan | 2013-03-14 | Final | IVB | LF | 4.524 | 120 | 2012-09-07 | 2013-01-04 | 0 | C | 0.401 | 0.143 | 0.3 | - | - | - | 84.4 | 87.12% Satisfactory
JBA CONSTRUCTION AND BUILDERS | 36321 | L | D | SB | GE | Rehabilitation/Restoration of Aggoyo Flood Control, K0264.30 - K0+550 | Samoki, Bontoc, Mt. Province | 2015-06-05 | Final | Mountain Province DEO | LF | 3 | 94 | 2016-11-25 | 2017-02-26 | (+) 4.21% | C | 0.357 | 0.2 | 0.3 | - | - | - | 85.7% | *85.7% Satisfactory
J-Bros Construction | 27587 | L | AAA | LB | GB1 | Construction of 3-Storey 15-Classroom School Building |  | 2009-03-19 | 1st | NHA |  | 17.203 | 150 |  |  |  | O | 0.337 | 0.3 | 0 | 0.03 | 0.043 | 0 | 71 | -
J-Bros Construction | 27587 | L |  |  | GB1 | Construction of 1 Unit 3-Storey School Building | Southville 3, NBP, Muntinlupa City | 2009-09-26 | Final | NHA |  | 18.513 | 210 | 08//17/08 | 2009-09-26 | - | O | 0.453 | 0.118 | 0.3 | - | - | - | 87.1 | 75.83% Unsatisfactory
JC Pinon Construction | 2011-0959 | L |  |  | GE5 | Repair of Damaged RC Curb & Curtain Wall and Replacement of Dilapidated Mooring & Fendering System along Berth Nos. 1,3,4&5 | Port of Puerto Princesa, Palawan | 2012-12-07 | 1st | PPA | LF | 31.093 | 180 | 2012-10-15 | 2012-04-12 | 20.86 | O | 0.392 | 0.3 | 0.15 | 0.03 | 0.07 | 0.05 | 99.2 | -
JC Pinon Construction Inc. | 20905 | L | A | MB | GE5 | Construction of Marshalling Yard and Paving of Existing Back-Up Area | Dalahican, Port of Lucena, Lucena City | 2013-11-25 | Final | PPA | LF | 33.608 | 353 | 2012-10-15 | 2013-10-02 | 0 | C | 0.48 | 0.2 | 0.3 | - | - | - | 98 | 98.70% Outstanding
JC Pinon Construction Inc. | 20905 | L |  |  |  | Repair of Damaged RC Deck/Slab and Replacement of Delapidated Mooring and Fendering System | Port of Roxas, Roxas, Palawan | 2015-05-29 | 1st & Final | PPA | L | 32.025 | 300 | 2014-08-02 | 2015-05-25 | 0.37 | C | 0.4567 | 0.2 | 0.3 | - | - | - | - | 95.67% Very Satisfactory
JC Pinon Construction, Inc. |  | L |  | MB | GE5 | Repair of Damaged RC curb & curtain wall and replacement of dilapidated mooring and fendering system along berths 2, 3, 4, & 5 | Port of Puerto Princesa, Palawan | 2013-06-21 | 2nd & Final | PPA | L | 31.093 | 180 | 2012-10-15 | 2013-04-12 | 6.21 | C | 0.5 | 0.2 | 0.3 | - | - | - | 100 | 99.50% Outstanding
JDC Builders Branch | 32048 | L | B | SB | GE2 | Repair of Pagsangaan Flood Control Structure along Palompon-Isabel-Merida-Ormoc Road Section |  | 2009-03-10 | 1st | VIII |  | 6.69 | 402 |  |  |  | O | 0.274 | 0.245 | 0.15 | 0.02 | 0.021 | 0.05 | #VALUE! | -
JDE CONSTRUCTION | 19173 | L | B | MA | GB | Construction of two storey 6-CL School Building, Camaman-an National High Building, Barangay Camaman-an, Cagayan de Oro City | Barangay Camaman-an, Cagayan de Oro City | 2015-11-15 | 1st | Cagayan de Oro City 2nd | LF | 7.9282 | 120 | 2015-09-01 | 2015-12-30 | (+) 0.04% | OG | 0.376 | 0.211 | 0.15 | 0.03 | 0.047 | 0.05 | 86.4% | 86.4% Satisfactory
Jecel Construction Supply | 21956 | L | D | SB | GB1 | Construction of Multi-Purpose Building @ Poblacion Padada |  | 2009-05-29 | 1st | XI |  | 0.951 | 75 |  |  |  | O | 0.351 | 0.3 | 0.15 | 0.03 | 0.038 | 0.033 | 90.2 | -
JECEL CONSTRUCTION SUPPLY | 21956 | L | D | SB | GE | Construction of Multi-Purpose Building | DORECO Compound Hospital Compound, City of Mati, Davao Oriental | 2015-06-08 | Final | Davao Oriental 2nd | LF | 1.948 | 60 | 2015-03-13 | 2015-05-11 | 0% | C | 0.42 | 0.133 | 0.3 | - | - | - | 85.3% | *85.3% Satisfactory
Jeff Construction | 25599 | L | B | SB | GE-5 | Paombong Port Development Project | Brgy. San Jose, Bulacan | 2014-08-20 | 1st | DOTC | LF | 8.854 | 210 | 2014-04-03 | 2014-10-27 | 3.6 | O | 0.3688 | 0.3 | 0.15 | 0.03 | 0.0155 | 0.05 | 91.43 | -
Jeff Enterprises | 25599 | L | D | SB | GE-5 | Panganiban Port Development Project | Brgy. San Pedro, Panganiban, Catanduanes/ Region V | 07/27/15 | 1st | DOTC | LF | 8.615 | 150 | 02/18/15 | 2015-08-05 | -16.7 | O | 0.3815 | 0.3 | 0 | 0.03 | 0.0311 | 0.05 | 79.26 | -
Jeff Enterprises | 25599 | L | D | SB | GB-1 | Paombong Port Development Project | Brgy. San Jose, Paombong, Bulacan/ Region III | 2015-05-14 | 2nd & Final | DOTC | LF | 8.854 | 180 | 2014-04-03 | 2015-02-19 | 0 | C | 0.4371 | 0.2 | 0.3 | - | - | - | 93.71 | 92.11% Very Satisfactory
Jeff Enterprises | 25599 |  | D | SB |  | Panganabin Port Development Project | Brgy. San Pedro, Panganiban, Catanduanes/ Region V | 2015-11-26 | 2nd & Final | DOTC | LF | 8.615 | 150 | 2015-02-18 | 2015-10-02 | 0 | C | 0.4711 | 0.2 | 0.3 | - | - | - | 97.11 | 86.40% Satisfactory
Jegma Construction and Development Corporation | 14775 | L | A | MB | GE1 | Impvt./Conc. of Bogo-Curva-Medellin-Daan Bantayan Road Sta. 106+800-Sta. 112+911.80 |  | 2009-09-03 | 2nd | VII |  | 100.494 | 330 |  |  |  | O | 0.328 | 0.3 | 0.15 | 0.03 | 0.056 | 0.05 | 91.4 | -
Jegma Construction and Development Corporation | 14775 | L | A | MA | GE1 | Conc. of Liloy, Zamboanga del Norte-Ipil Zamboanga, Sibugay |  | 2008-11-21 | 1st | IX |  | 14.314 | 135 |  |  |  | O | 0.358 | 0.24 | 0.07 | 0.03 | 0.03 | 0.033 | 76.1 | -
Jegma Construction and Development Corporation | 14775 | L | A | MB | GE1 | Rehab./Reconst. of Damaged Paved Nat'l Rds. along Cebu North Hagnaya Wharf Rd. (Int. Sect.) K0050+000-K0050+448 | Catmon, Cebu | 2013-08-13 | Final | VII | LF | 7.635 | 54 | 2013-02-08 | 2013-04-02 | 0 | C | 0.468 | 0.133 | 0.3 | - | - | - | 90.1 | 84.64% Satisfactory
JEGMA CONSTRUCTION AND DEVELOPMENT CORP | 14775 | L | A | MB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads Including Drainage Based on Pavement Management System/Highway Development and Management-4 (HDM-4) at Plaridel St. | Chainage 2142-Chainage 2744, Mandaue City, Cebu | 2015-06-01 | 1st | Cebu Sixth DEO | LF | 44.5 | 278 | 2015-03-30 | 2016-01-01 | 0% | O | 0.381 | 0.244 | 0.15 | 0.03 | 0.045 | 0.05 | 90% | -
Jegma Construction and Development Corporation | 14775 | L | A | MB | GE1 | Rehab./Reconst. Of Damaged Paved Nat'l. Rds. along Cebu North Hagnaya Wharf Rd. (Intermittent Sect.) K0050+000-K0050+448 | Catmon, Cebu | 2013-03-19 | 1st | VII | LF | 7.635 | 54 | 2013-02-08 | 2013-04-03 | 61.83 | O | 0.365 | 0.2 | 0.15 | 0.03 | 0.032 | 0.033 | 81 | -
Jegma Construction and Development Corporation | 14775 | L | A | MB | GE | Construction of Drainage System along Cebu North Hagnaya Wharf Road, Sogod Section | Sogod, Cebu | 2014-10-21 | 1st | VII | LF | 18.6122 | 240 | 2014-01-31 | 2014-09-27 | -1.15% | O | 0.372 | 0.3 | 0.138 | 0.03 | 0.045 | 0.033 | 91.8% | 91.80% Very Satisfactory
Jegma Construction and Development Corporation | 14775 |  |  |  |  | Impvt./Conc. of Bogo-Curva-Medellin-Daan Bantayan-Maya Rd. |  | 2010-06-15 |  | VII |  | 60.795 | 300 |  |  |  | O | 0.306 | 0.237 | 0.15 | 0.03 | 0.06 | 0.05 | 83.3 | -
Jegma Construction and Development Corporation | 14775 | L | A | MA | GB1 | Improvement of Multi-Purpose Building |  | 2009-03-03 | 1st | VII |  | 0.949 | 50 |  |  |  | O | 0.319 | 0.173 | 0.15 | 0.02 | 0.019 | 0.033 | #VALUE! | -
JEGMA CONSTRUCTION AND DEVELOPMENT CORPORATION | 14775 | L | A | MA | GE | Construction of Flood Control and Drainage System along Cebu North Hagnaya Wharf Road, K17+000 - K18+300 (Intermittent Section), Lilo-an, Cebu | Lilo-an, Cebu | 2015-11-14 | Final | Cebu 5th | LF | 17.9901 | 210 | 2015-02-09 | 2015-09-06 | 0.0095 | C | 0.497 | 0.133 | 0.3 | - | - | - | 93% | 93% Very Satisfactory
JEJOR'S CONSTRUCTION CORP. | 5143 | L | AAA | MA | GE | Construction of Slope Protection along Butuan City-Cagayan de Oro City-Iligan City Road (Upstream of Villanueva Bridge), Villanueva, Misamis Oriental | Villanueva, Misamis Oriental | 2015-11-16 | Final | Misamis Oriental 2nd | LF | 42.876 | 225 | 2015-02-02 | 2015-09-15 | 0.00% | C | 0.481 | 0.2 | 0.3 | - | - | - | 98.1% | 95.04% Very Satisfactory
Jejor's Construction Corporation | 5143 | L |  |  |  | Land Development of NHA-CDO Bayanihan Village, Ph 1 | Macapaya, Camaman-an, Cagayan De Oro City | 2014-02-02 | 1st | NHA | LF | 26.059 | 180 | 2013-07-04 | 2013-12-30 | 23.83 | S | 0.3945 | 0.3 | 0 | 0.03 | 0.065 | 0.033 | 82.25 | -
Jejor's Construction Corporation | 5143 | L | A |  |  | Land Development of NHA-CDO Bayanihan Village, Ph 1 | Macapaya, Camaman-an, Cagayan De Oro City | 2014-08-14 | Final | NHA | LF | 26 | 254 | 2013-07-04 | 2014-07-12 | 0 | C | 0.5 | 0.2 | 0.3 | - | - | - | - | 100.00% Outstanding
Jejor's Construction Corporation | 5143 | L | A |  |  | Land Dvelopment of NHA-CDO Bayanihan Village, Ph 1 | Macapaya, Camaman-an, Cagayan de Oro City | 2014-02-07 | 1st | NHA | LF | 26.059 | 180 | 2013-07-04 | 2013-12-30 | 23.83 | S as of 12/06/2013 | 0.3945 | 0.3 | 0 | 0.03 | 0.065 | 0.033 | 82.25 | -
Jejor's Construction Corporation | 5143 | L | A |  |  | Rehabilitation/Upgrading of RC Pier, Port of Baligoan | Port of Baligoan, Misamis Oriental | 2015-02-10 | 2nd & Final | PPA | L | 23.233 | 240 | 2013-12-27 | 2015-01-04 | 0 | C | 0.4776 | 0.2 | 0.3 | - | - | - | - | 94.42% Very Satisfactory
Jejor's Construction Corporation | 5143 | L | A |  |  | Paving of Back-Up Area and Construction of RORO Ramp | Port of Benoni, Camiguin | 2015-02-10 | 2nd & Final | PPA | L | 53.954 | 331 | 2014-01-13 | 2014-12-09 | 0 | C | 0.4685 | 0.2 | 0.3 | - | - | - | - | 95.12% Very Satisfactory
Jejor's Construction Corporation | 5143 | L |  |  |  | Paving of Back-Up Area and Construction of RORO Ramp | Port of Benoni, Brgy. Benoni, Mahinog, Camiguin | 2014-08-30 | 1st | PPA | LF | 53.954 | 270 | 2014-01-13 | 2014-10-09 | -5.848 | O | 0.393 | 0.3 | 0.0965 | 0.03 | 0.07 | 0.05 | 93.95 | -
Jejor's Construction Corporation | 2011-1436 | L | A |  |  | Re-waterproofing of Roofdeck & Parapets Walls, Application of Water Repellant and Related Repair Works | BSP Ozamis Branch Building | 2014-10-29 | Final | BSP | L | 3.545 | 68 | 2013-09-26 | 2013-12-02 | 0 | C | 0.459 | 0.2 | 0.3 | - | - | - | 95.9 | 95.88% Very Satisfactory
Jejor's Construction Corporation | 5148 | L | A |  |  | Construction of Roof Garden on Covered Walk going to Gate 6 | BSP Main Complex | 2014-04-15 | 1st & Final | BSP | L | 1.995 | 60 | 2013-12-12 | 2014-02-11 | 0 | C | 0.4591 | 0.2 | 0.3 | - | - | - | - | 95.90% Very Satisfactory
Jejor's Construction Corporation | 1436 | L | A |  |  | Waterproofing of Roof Deck & Parapets, Application of Water Repellant and Related Repair Works | BPS General Santos Branch Building corner Daproza & Pendatun Avenue, General Santos City | 2014-03-05 | 1st & Final | BSP | LF | 3.478 | 60 | 2013-09-27 | 2013-12-05 | 0 | C | 0.5 | 0.147 | 0.3 | - | - | - | 94.7 | 94.70% Very Satisfactory
Jejor's Construction Corporation | 5143 | L | A | MA | GE5 | Balbagon Port Development Project | Brgy. Balbagon, Mambajao, Camiguin / Region X | 2014-01-29 | Final | DOTC | LF | 9.203 | 90 | 2013-03-29 | 2014-01-28 | 0 | C | 0.3967 | 0.2 | 0.3 | - | - | - | 89.67 | 89.67% Very Satisfactory
Jejor's Construction Corporation | 5143 | L | AA | MB | GE | Repair/Rehab./Impv't. of DPWH Building (Phase I) DPWH Regional Office Compound, R-X | Bulua, Cagayan de Oro City | 2014-10-27 | 1st & Final | X | LF | 37.1023 | 180 | 2013-06-10 | 2013-12-06 | 0% | C | 0.406 | 0.133 | 0.3 | - | - | - | 83.9% | 83.90% Satisfactory
Jejor's Construction Corporation | 5143 | L | A | MA | GE1 | Rehab./Reconst./Upgrading (Asphalt to Concrete) of Jct. S.H.-Manolo Fortich-Libona-Indahag Rd. (Agusan Canyon Sect.) K1458+649-K1460+635 | Manolo Fortich, Bukidnon | 2013-08-06 | Final | X | LF | 29.261 | 133 | 2013-01-23 | 2013-06-04 | 0 | C | 0.425 | 0.133 | 0.3 | - | - | - | 85.8 | 86.58% Satisfactory
Jejor's Construction Corporation | 5143 | L | A | MA | GE1 | Rehab./Reconst./Upgrading (Asphalt to Concrete) of Jct. S.H.-Manolo Fortich-Libona-Indahag Rd. (Agusan Canyon Sect.) K1458+649-K1460+635 | Manolo Fortich, Bukidnon | 2013-03-21 | 1st | X | LF | 29.261 | 119 | 2013-01-23 | 2013-05-21 | 31.29 | O | 0.328 | 0.28 | 0.15 | 0.03 | 0.05 | 0.033 | 87.1 | -
Jejor's Construction Corporation | 5143 | L | A | MA | GE2 | Const. of Slope Protection along Linamon-Zamboanga Road (Bulod River), Km.1586+596.90, Const. of 154.20m Flood Control using Pre-Cast Concrete Sheet Piles & Class A Grouted Riprap | Tubod, Lanao del Norte | 2013-08-17 | Final | X | LF | 12.806 | 255 | 2012-07-19 | 2013-03-30 | 0.39 | C | 0.451 | 0.2 | 0.3 | - | - | - | 95.1 | 82.11% Satisfactory
Jejor's Construction Corporation | 5143 | L | A | MA | GE2 | Const. of Slope Protection along Linamon-Zamboanga Rd. (Bulod River) Km.1586+956.90 Const. of 154.20m Flood Control using Pre-Cast Concrete Sheet Piles & Class A Grouted Riprap | Tubod, Lanao del Norte | 2013-03-15 | 2nd | X | LF | 12.806 | 225 | 2012-07-19 | 2013-02-28 | - | O | 0.221 | 0.3 | 0 | 0.01 | 0.051 | 0.05 | 63.2 | -
Jejor's Construction Corporation | 5143 | L | A | MA | GE2 | Const. of Slope Protection along Linamon-Zamboanga Rd. (Bulod River), Location: K1586+956.90, Const. of 150.20 meters Flood Control using Pre-Cast Concrete Sheet Piles & Class A Grouted Riprap | Tubod, Lanao del Norte | 2012-11-26 | 1st | X | LF | 12.806 | 210 | 2012-07-19 | 2013-02-13 | 0.4 | O | 0.349 | 0.225 | 0.15 | 0.03 | 0.05 | 0.033 | 83.7 | -
Jejor's Construction Corporation | 5143 | L | A | MA | GE1 | Rd. Upgrading (Gravel to Paved) (Int. Sect.) Cagayan de Oro City-Dominorog-Camp Kibaritan Rd. | Talakag, Bukidnon | 2013-03-22 | 2nd | X | LF | 50.364 | 259 | 2012-07-30 | 2013-04-14 | -5.45 | O | 0.271 | 0.3 | 0.096 | 0.02 | 0.025 | 0.033 | 74.5 | -
Jejor's Construction Corporation | 5143 | L | A | MA | GE1 | Rd. Upgrading (Gravel to Paved) (IS): Cagayan de Oro City-Dominorog-Camp Kibaritan Rd. | Talakag, Bukidnon | 2012-11-19 | 1st | X | LF | 50.364 | 150 | 2012-07-30 | 2012-12-26 | -8.13 | O | 0.358 | 0.3 | 0.069 | 0.03 | 0.045 | 0.033 | 83.5 | -
Jejor's Construction Corporation | 5143 | L | A | MA | GE1 | Rehab./Reconst. (Asphalt to Concrete) of Jct. S.H. Manolo Fortich Libona-Indahag Rd., (Gango Section) |  | 2009-09-04 | 2nd | X |  | 19.217 | 180 |  |  |  | O | 0.388 | 0.254 | 0.15 | 0.03 | 0.047 | 0.033 | 90.2 | -
JEJOR'S CONSTRUCTION CORPORATION | 5143 | L | AA | MA | GE | Construction of Slope Protection along Butuan City- Cagayan de Oro City-Iligan City Road (Upstream of Villanueva Bridge), Villanueva, Misamis Oriental | Villanueva, Misamis Oriental | 2015-06-09 | 1st | Misamis Oriental Second DEO | LF | 42.873 | 165 | 2015-02-02 | 2015-07-18 | - | O | 0.395 | 0.297 | 0.15 | 0.024 | 0.039 | 0.05 | 95.5% | -
JEJOR'S CONSTRUCTION CORPORATION | 5143 | L | AA | MB | GE | Construction of Bitan-ag Bridge and Approaches along Butuan City-Cagayan de Oro City-Iligan City Road (BCIR) and Improvement of Drainage, Lapasan Section, K1436+820- K1437+240, Cagayan de Oro City | K1436+820- K1437+240, Cagayan de Oro City | 2015-08-30 | 1st | Regional Office No. X | LF | 63.59 | 260 | 2015-03-09 | 2015-11-23 | 0.1% | O | 0.387 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 90.7% | -
JEJOR'S CONSTRUCTION CORPORATION | 5143 | L | AA | MA | GE | Construction of Slope Protection along Butuan City - Cagayan de Oro City - Iligan City Road (Upstream of Villanueva Bridge), Villanueva, Misamis Oriental | Villanueva, Misamis Oriental | 2015-09-03 | 2nd | Misamis Oriental 2nd DEO | LF | 42.873 | 225 | 2015-02-02 | 2015-09-14 | 0.01% | O | 0.374 | 0.285 | 0.15 | 0.024 | 0.047 | 0.05 | 93% | -
JELA CONSTRUCTION | 17902 | L | A | SB | GE | Off-Carriageway Improvement (Construction of Loading and Unloading Bay), Tabunok, Talisay City, Cebu Province | Tabunok, Talisay City, Cebu Province | 2015-11-09 | 1st | Cebu 2nd | LF | 9.1818 | 166 | 2015-06-15 | 2015-12-27 | 0.0896 | OG | 0.343 | 0.24 | 0.15 | 0.03 | 0.035 | 0.05 | 84.8% | 84.8% Satisfactory
JELM Construction | 33230 |  |  | MA |  | Tacloban Airport Development Project | Brgy. San Jose, Tacloban City/ Region VIII | 2016-08-18 | 1st | DOTC | LF | 6.167 | 180 | 2016-05-17 | 2016-11-13 | 26.49 | O | 0.3749 | 0.3 | 0.15 | 0.03 | 0.0388 | 0.05 | 94.37 | -
JELM Construction | 33230 | L | B | MA |  | Tacloban Airport Development Project | Brgy. San Jose, Tacloban City/ Region VIII | 2016-10-13 | 2nd & Final | DOTC | LF | 6.1671 | 180 | 2016-05-17 | 2016-11-13 | 14.33 | C | 0.4298 | 0.2 | 0.3 | - | - | - | 92.98 | 93.94% Very Satisfactory
Jelm Construction / Chu Construction (JV) | JV-12-198 | L | B | MA | GE1 | Conc. of Bagahupi-Babatngon-Sta. Cruz-Barugo-Carigara Rd., Brgy. Bacong, K0925+029.08-K0926+009.08 | Babatngon, Leyte | 2013-08-20 | Final | VIII | LF | 19.599 | 173 | 2013-01-14 | 2013-07-05 | 0.67 | C | 0.445 | 0.133 | 0.3 | - | - | - | 87.8 | 86.48% Satisfactory
Jelm Construction / Chu Construction (JV) | JV-12-198 | L | B | MA | GE1 | Conc. of Bagahupi-Sta. Cruz-Barugo-Carigara Rd., Sta.K0925+029.08-K0926+009.08, Brgy. Bacong | Babatngon, Leyte | 2013-03-22 | 1st | VIII | LF | 18.6 | 120 | 2013-01-14 | 2013-05-13 | 1.15 | O | 0.361 | 0.227 | 0.15 | 0.03 | 0.055 | 0.033 | 85.6 | -
Jemak Construction & Supply | 32056 | L | B | MA | GE1 | Conc. of Manila South Rd.-Jct. Lopez-Catanauan Rd. | Quezon | 2013-03-18 | 1st | IVA | LF | 86.608 | 323 | 2012-05-21 | 2013-04-09 | -1.95 | O | 0.377 | 0.24 | 0.13 | 0.03 | 0.056 | 0.033 | 86.6 | -
Jemak Construction & Supply | 32056 | L | B | MA | GE1 | Impvt. of Jct. Lucena-Diversion Rd., Lucena-Tayabas-Mauban Port Rd. | Lucena City | 2013-03-16 | Final | IVA | LF | 26.691 | 248 | 2012-05-15 | 2013-01-18 | 1.82 | C | 0.456 | 0.133 | 0.3 | - | - | - | 88.9 | 89.14% Very Satisfactory
Jemak Construction & Supply | 32056 | L | B | MA | GE1 | Impvt. of Jct. Lucena Diversion Rd., Lucena-Tayabas-Mauban Port Rd. | Lucena City | 2012-11-28 | 1st | IVA | LF | 26.691 | 250 | 2012-05-15 | 2013-01-18 | 0.8 | O | 0.375 | 0.255 | 0.15 | 0.03 | 0.033 | 0.05 | 89.3 | -
JEMAK CONSTRUCTION & SUPPLY | 32056 | L | B | MA | GE | Construction/Upgrading/Rehabilitation of Drainage along National Roads, Daang Maharlika (LZ), K0 114+500 - K0 115+300 | Sariaya, Quezon | 2015-09-02 | 1st | Quezon 2nd | LF | 13.523 | 310 | 2015-01-28 | 2015-12-03 | 0% | O | 0.362 | 0.24 | 0.15 | 0.03 | 0.035 | 0.033 | 85% | -
Jerry R. Santiago Construction | 18453 | L | B | MA | GE | Widening of National Roads, Daang Maharlika Road, KO119+767 - KO123+119 with exception | Cabanatuan City | 2014-09-25 | 1st & Final | Special 3 | LF | 33.3892 | 132 | 2014-05-31 | 2014-10-09 | 0.5 | C | 0.383 | 0.138 | 0.3 |  |  |  | 82.1 | 82.10% Satisfactory
Jet Construction Supply | 7063 |  |  |  |  | Road Upgrading (Gravel to Paved) Mandurriao-Jaro Rd. |  | 2010-05-31 |  | VI |  | 4.405 | 150 |  |  |  | O | 0.329 | 0 | 0.15 | 0.015 | 0.019 | 0.017 | 53 | -
Jet Construction Supply | 7063 |  |  |  |  | Conc. of Sibalom-Pis-anan Road |  | 2010-09-02 |  | VI |  | 33.164 | 150 |  |  |  | O | 0.357 | 0.24 | 0 | 0.03 | 0.042 | 0.033 | 70.2 | -
Jetver Trading & Construction | 25501 |  |  |  |  | Const. of Multi-Purpose Building, Brgy. Alfonso XIII |  | 2010-03-03 |  | IVB |  | 0.676 | 60 |  |  |  | O | 0.311 | 0.3 | 0.15 | 0.023 | 0.037 | 0.05 | 87.1 | -
JFJ Construction and Supply, Inc. | 32107 | L | D | SB | GB | Alibuag Spring Development Project | Brgy. Duka, Medina, Misamis Oriental | 2014-04-10 | 1st | TIEZA | LF | 4.993 | 300 | 2013-11-15 | 2014-02-28 | -9.875 | O | 0.342 | 0.289 | 0.051 | 0.015 | 0 | 0 | 69.7 | -
JFJ Construction and Supply, Inc. | 32107 | L | D | SB | GB | Alibuag Spring Development Project | Brgy. Duka, Medina, Misamis Oriental | 2014-06-17 | Final | TIEZA | LF | 4.992 | 300 | 2013-11-15 | 6/31/2014 | -9.875 | C | 0.402 | 0.193 | 0 |  |  |  | 59.5 | 66.60% Poor
JFJ Construction and Supply, Inc. | 32107 | L | D | SB | GE-5 | Sipalay Port Development Project | Brgy.2 Pana-on, Sipalay, Negros Occidental | 2014-07-09 | 1st & Final | DOTC | LF | 1.74 | 60 | 2014-05-01 | 2014-06-29 | 0 | C | 0.4478 | 0.2 | 0.3 | - | - | - | 94.78 | 94.78% Very Satisfactory
JFR CONSTRUCTION | 35890 | L | D | SB | GE | Local Infrastructure Program-Construction of Riprapping, Brgy. San Joaquin, Calbayog City, Samar1st LD | Calbayog City, Samar1st LD | 2015-09-02 | 1st & Final | Samar 1st DEO | LF | 5.062 | 87 | 2015-02-04 | 2015-05-01 | (+)1.15 | C | 0.398 | 0.133 | 0.3 | - | - | - | 83.1% | *83.1% Satisfactory
JGC Construction & Enterprises | 34305 | L | D | SB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Road aling Ipil-Liloy-Sindangan Road Km. 1998+208 - Km. 1998+622 Namnama Road Section | Titay, Zamboanga Sibugay | 2014-08-07 | Final | IX | LF | 7.0644 | 185 | 2014-03-01 | 2014-09-01 | 0 | C | 0.385 | 0.2 | 0.3 |  |  |  | 88.5 | 86.76% Satisfactory
JGC Construction & Enterprises | 30305 | L | D | SB | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rd. along Ipil-Liloy Sindangan Rd., Km.1998+208-Km.1998+622, Namnama Rd. Sect. | Titay, Zamboanga Sibugay | 2013-08-08 | 1st | IX | LF | 7.064 | 185 | 2013-03-01 | 2013-09-01 | 0 | O | 0.348 | 0.241 | 0.15 | 0.02 | 0.047 | 0.05 | 85.6 | -
JH Pameron Construction & Enterprises | 18792 | L | B | SB | GE2 | Proposed Drainage/Protection at Simukoy Bridge & Approaches, Km.1946+834 along Sindangan-Liloy Rd. | Salug, Zamboanga del Norte | 2013-03-16 | Final | IX | LF | 2.326 | 54 | 2012-10-15 | 2012-12-08 | 0 | C | 0.491 | 0.133 | 0.3 | - | - | - | 92.4 | 92.76% Very Satisfactory
JH Pameron Construction & Enterprises | 18792 | L | B | SB | GE2 | Proposed Drainage/Protection at Cocob Sect. along Gutalac-Baliguian Rd., Km.2012+850-Km.2015+900 | Gutalac, Zamboanga del Norte | 2013-08-13 | Final | IX | LF | 3.595 | 200 | 2012-10-15 | 2013-05-02 | 2 | C | 0.404 | 0.184 | 0.3 | - | - | - | 88.8 | 87.30% Satisfactory
JH Pameron Construction & Enterprises | 18792 | L | B | SB | GE2 | Proposed Drainage/Protection at Cocob Sect. along Gutalac-Baliguian Rd., Km.2012+850-Km.2015+900 | Gutalac, Zamboanga del Norte | 2013-03-16 | 2nd | IX | LF | 3.596 | 195 | 2012-10-15 | 2013-04-27 | 11.19 | O | 0.373 | 0.24 | 0.15 | 0.03 | 0.033 | 0.05 | 87.6 | -
JH Pameron Construction & Enterprises | 18792 | L | B | SB | GE2 | Proposed Drainage/Protection at Cocob Sect. along Gutalac-Baliguian Rd. Km.2012+850-Km.2015+900 | Gutalac, Zamboanga del Norte | 2012-11-28 | 1st | IX | LF | 3.597 | 157 | 2012-10-15 | 2013-03-20 | 0.3 | O | 0.323 | 0.243 | 0.15 | 0.03 | 0.054 | 0.05 | 85 | -
Jhall Marketing & Services | 15760 | L |  |  | GE2 | Rehabilitation of Various NIS | Barotac Nuevo, Iloilo / Region 6 | 2012-07-21 | 1st | NIA | LF | 6.331 | 150 | 2012-03-23 | 2012-08-19 | -10.58 | O | 0.3946 | 0.3 | 0.0442 | 0.0075 | 0.025 | 0.05 | 82.13 | -
JHI CONSTRUCTION AND SUPPLY | 19317 | L | D | SB | GE | Construction of Bank Protection, Agno River Basin Flood Control Project (Phase III) Brgy. Amisdad, Tayug, Pangasinan | Tayug, Pangasinan | 2015-11-16 | 1st | PANGASINAN 3RD DEO | LF | 7.411 | 135 | 2015-08-26 | 2016-01-07 | 0.0019 | OG | 0.377 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 89.7% | 89.7% Very Satisfactory
JHJ Construction | 3781 | L | A | SB | GB1 | Const. of MPB at Kirayan NHS | Miag-ao, Iloilo City | 2013-08-14 | 1st | VI | LF | 3.319 | 130 | 2013-03-02 | 2013-06-09 | - | O | 0.361 | 0.23 | 0 | 0.03 | 0.027 | 0.033 | 68.1 | -
JHJ Construction | 3781 | L | A | MA | GE1 | Conc./Reblocking of Ilolilo-Capiz (Old Route) Rd., K0056+341-K0064+192.50 | Calinog, Iloilo | 2012-08-23 | 1st | VI | LF | 13.226 | 210 | 2012-01-31 | 2012-08-28 | -4.56 | O | 0.377 | 0.289 | 0.104 | 0.03 | 0.03 | 0.033 | 86.3 | -
JHJ CONSTRUCTION | 3781 | L | A | MA | GE | Widening of Manila Bridge along Iloilo-Antique Road | Km. 0035+122, Miag-ao, Iloilo | 2015-06-03 | 1st | Iloilo First DEO | LF | 6.5 | 143 | 2015-02-16 | 2015-07-08 | 0.18% | O | 0.339 | 0.286 | 0.15 | 0.03 | 0.035 | 0.05 | 89% | -
JHJ CONSTRUCTION | 3781 | L | A | MA | GE | Concreting of Barotac Viejo-NIPSC Road | Barotac Viejo, Iloilo | 2015-06-08 | 1st | Iloilo Third DEO | LF | 16.026 | 130 | 2015-02-16 | 2015-06-25 | 0.64% | O | 0.344 | 0.282 | 0.15 | 0.022 | 0.044 | 0.05 | 89.2% | -
JHJ CONSTRUCTION | 3781 | L | A | MA | GE | Concreting of Barotac Viejo - NIPSC Road, Barotac Viejo, Iloilo | Barotac Viejo, Iloilo | 2015-11-14 | Final | Iloilo 3rd | LF | 16.0265 | 100 | 2015-02-16 | 2015-05-27 | (+) 2.24% | C | 0.379 | 0.2 | 0.3 | - | - | - | 87.9% | 87.9% Satisfactory
JHJ CONSTRUCTION | 3781 | L | A | MA | GE | Rehabilitation of Road, Guimbal National High School Road, Guimbal, Iloilo | Guimbal, Iloilo | 2015-11-12 | Final | Iloilo 1st | LF | 4.6462 | 74 | 2015-02-16 | 2015-05-01 | 0.00% | C | 0.381 | 0.175 | 0.3 | - | - | - | 85.6% | 85.6% Satisfactory
JIJOMER Construction | 33867 | L | D |  |  | Construction of Magat River Flood Protection Dike | Brgy. Pulay, Cordon, Isabela | 2015-04-17 | 1st & Final | NIA | L | 9.841 | 120 | 2014-03-07 | 2014-07-04 | 0 | C | 0.5 | 0.16 | 0.3 | - | - | - | - | 96.00% Very Satisfactory
Jimberns Builders & Construction Supply | 36875 | L | D | SB | GB | Construction of Multi-Purpose Building | Poblacion, Esperanza, Agusan del Sur | 2014-10-22 | 1st | XIII | LF | 1.9109 | 60 | 2014-09-09 | 2014-11-07 | 3.75% | O | 0.289 | 0.3 | 0.15 | 0.02 | 0.032 | 0.05 | 84.1% | 84.10% Satisfactory
Jimwen Construction & General Merchandise | 330 | L |  |  |  | UMAYAM RIVER IRRIGATION PROJECT | LA PAZ & LORETO, AGUSAN DEL SUR | 2015-09-12 | 1st & Final | NIA | LF | 13.095 | 347 | 2014-08-05 | 2015-07-17 | 0 | C | 0.3995 | 0.1333 | 0.3 | - | - | - | 83.28 | 83.28% Satisfactory
Jimwen Construction & General Merchandise | 53066 | L | D | SB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads Including Drainage Based on Pavement Management System (Highway Development and Management-4 (HDM-4)(Intermittent Section) National Secondary Road along Jct. Dumalinao-Margosatubig Road, K1718+1005.30 - K1718+1240 | Zamboanga del Sur | 2014-10-26 | 1st & Final | IX | LF | 4.879 | 99 | 2014-02-07 | 2014-05-16 | 0% | C | 0.35 | 0.194 | 0.3 | - | - | - | 84.4% | 84.40% Satisfactory
Jimwen Construction & General Merchandise |  | L |  |  |  | Sta. Josefa Pump Irrigation Project | Agusan del Sur/ Caraga Region | 2014-08-30 | Final | NIA | LF | 14.885 | 441 | 2012-08-31 | 2013-11-14 | 0 | C | 0.3713 | 0.1931 | 0.3 | - | - | - | - | 86.40% Satisfactory
JIMWEN CONSTRUCTION & GENERAL MERCHANDISE | 33066 | L | D | SB | GE | Concreting of Barangay Road, Brgy, Poblacion-Brgy. Sinclot Road, Guipos, Zamboanga Del Sur | Guipos, Zamboanga Del Sur | 2015-11-12 | Final | Zamboanga Del Sur 2nd DEO | LF | 4.655 | 32 | 2015-02-27 | 2015-03-30 | - | C | 0.434 | 0.133 | 0.3 | - | - | - | 86.7% | 86.7% Satisfactory
JIMWEN CONSTRUCTION & GENERAL MERCHANDISE | 33066 | L | D | SB | GE | Road Concreting of Brgy Upper Dumalinao-Brgy. Cuatro-Cuatro Road (Phase IV), Dumalinao, Zamboanga Del Sur | Dumalinao, Zamboanga Del Sur | 2015-11-12 | Final | Zamboanga Del Sur 2nd DEO | LF | 7.4483 | 48 | 2015-02-27 | 2015-04-15 | - | C | 0.422 | 0.133 | 0.3 | - | - | - | 85.5% | 85.5% Satisfactory
Jirk Construction | 29918 | L | C | SB | GB | Construction of TESDA Multi-Purpose Building, San Isidro, Luna, Apayao | San Isidro, Luna, Apayao | 2014-08-10 | Final | CAR | LF | 3.9808 | 150 | 2013-07-17 | 2013-12-13 | 0 | C | 0.428 | 0.133 | 0.3 |  |  |  | 86.1 | 85.75% Satisfactory
Jirk Construction | 29918 | L | C | SB | GB | Construction of San Juan PS, Sta. Marcela, Apayao | Sta. Marcela, Apayao | 2014-08-10 | Final | CAR | LF | 2.5525 | 120 | 2013-05-27 | 2013-09-23 | 0 | C | 0.474 | 0.133 | 0.3 |  |  |  | 90.7 | 86.78% Satisfactory
Jirk Construction | 29918 | L | C | SB | GB1 | Const. of TESDA MPB, San Isidro | Luna, Apayao | 2013-08-12 | 1st | CAR | LF | 3.909 | 120 | 2013-07-17 | 2013-11-14 | 18.5 | O | 0.37 | 0.24 | 0.15 | 0.015 | 0.047 | 0.033 | 85.5 | -
Jirk Construction | 29918 | L | C | SB | GB1 | Const. of San Juan PS | Sta. Marcela, Apayao | 2013-08-12 | 1st | CAR | LF | 2.553 | 120 | 2013-05-27 | 2013-09-24 | 1.84 | O | 0.366 | 0.24 | 0.15 | 0.015 | 0.047 | 0.033 | 85.1 | -
Jits Construction Corp. | 13232 | L | AAA | LA | GB1 | Construction of 3-Storey 15-Classroom School Building |  | 2009-07-31 | 2nd | NHA |  | 18.108 | 150 |  |  |  | O | 0.34 | 0.171 | 0.15 | 0.02 | 0.051 | 0.05 | 78.2 | -
JJ & J Construction and General Supply | 30231 | L | B | MA | GE | Repair/Rehabilitation of Mactan Airport Road, Lapu-Lapu Section, K0018+634 - K0019+936, Lapu-Lapu City | Lapu-Lapu City, Cebu | 2014-10-21 | 1st & Final | VII | LF | 16.2041 | 60 | 2014-05-09 | 2014-07-07 | 5% | C | 0.443 | 0.147 | 0.3 | - | - | - | 89% | 89.00% Satisfactory
JJ & J CONSTRUCTION AND GENERAL SUPPLY | 30231 | L | B | MA | GE | Rehab/Reconst/Upgrading of Damaged Paved Nat'l Rd Incl Drainage Based on Pavement Management System/Highways Development and Management-4 (HDM-4) at Mactan Circumferential Road, K0025+000 to K0025+627, Lapu-lapu City | Lapu-lapu City, Cebu | 2015-06-01 | 1st | Cebu Sixth DEO | LF | 12.559 | 120 | 2015-02-16 | 2015-06-15 | 0.67% | O | 0.371 | 0.295 | 0.15 | 0.03 | 0.05 | 0.05 | 94.6% | -
JJ & J CONSTRUCTION AND GENERAL SUPPLY | 30231 | L | B | MA | GE | Construction/Upgrading/Rehabilitation of Drainage along National Roads at Cebu Mactan Circumferential Road, K0034+00 - K0034+524; Chainage 0000-0780, Lapu-lapu City | Lapu-Lapu City | 2015-11-14 | 1st | Cebu 6th | LF | 45.1463 | 330 | 2015-03-30 | 2016-02-22 | 0 | OG | 0.342 | 0.24 | 0.15 | 0.03 | 0.03 | 0.05 | 84.2% | 84.2% Satisfactory
JJ & J CONSTRUCTION AND GENERAL SUPPLY | 30231 | L | B | MA | GB | Construction of Multi-Purpose Building, Yati, Lilo-an, Cebu | Yati, Lilo-an, Cebu | 2015-11-14 | Final | Cebu 5th | LF | 2.8747 | 90 | 2015-04-15 | 2015-07-13 | 0.0333 | C | 0.498 | 0.15 | 0.3 | - | - | - | 94.8% | 94.8% Very Satisfactory
JJA Construction and Supply | 22676 | L | B | SB | GE | Package I. a. Maintenance of National Road along Abbut-Conner-Kabugao Road, K0559+120 - K0568+100 (Intermittent Sections) b. Maintenance of National Roads along Conner-Kabugao Road, K0567+127 - K0567+270 (Intermittent Section) | Conner & Kabugao, Apayao | 2014-11-28 | 1st & Final | CAR | LF | 3.1926 | 90 | 2014-08-14 | 2014-11-11 | 0% | C | 0.461 | 0.133 | 0.3 | - | - | - | 89.4% | 89.40% Very Satisfactory
JJA Construction and Supply | 35459 | L | B | SB | GB | "Cluster A" Expansion of Health Station a) Talagutong; b) West Lamidan; c) Lawa | Don Marcelino, Davao del Sur | 2014-10-23 | 1st & Final | XI | LF | 1.9401 | 60 | 2014-04-11 | 2014-06-09 |  | C | 0.374 | 0.168 | 0.3 | - | - | - | 84.2% | 84.20% Satisfactory
JJJ-A CONSTRUCTION AND SUPPLIES | 37143 | L | D | SB | GB | Construction of One-Storey, One-Classroom at Saclit National High | Sadanga, Mountain Province | 2015-06-05 | Final | Mountain Province DEO | LF | 1.122 | 87 | 2014-10-08 | 2015-01-02 | 0% | C | 0.455 | 0.168 | 0.3 | - | - | - | 92.3% | *92.3% Very Satisfactory
JJJARNS Construction | 35952 | L | D | SB | GE | Concreting of Lucban Farm-to-Market Road | Abulug, Cagayan | 2014-08-06 | 1st & Final | II | LF | 4.8189 | 77 | 2013-05-27 | 2013-08-11 | -1.3 | C | 0.448 | 0.135 | 0.261 |  |  |  | 84.4 | 84.40% Satisfactory
JJJARNS Construction | 35952 | L | D | SB | GE1 | Conc. of Lucban FMR | Abulug, Cagayan | 2013-08-02 | 1st | II | LF | 4.819 | 90 | 2013-05-27 | 2013-08-24 | 6.66 | O | 0.35 | 0.225 | 0.15 | 0.03 | 0.045 | 0.033 | 83.3 | -
JLA Construction and Supplies | 24503 | L | D | SB | GE2 | Repair/Maint. of Tres de Mayo Revetment | Digos City, Davao del Sur | 2013-03-16 | Final | XI | LF | 1.993 | 56 | 2012-10-08 | 2012-12-02 | 0 | C | 0.393 | 0.133 | 0.3 | - | - | - | 82.6 | 87.16% Satisfactory
JLA Construction and Supplies | 24503 | L | D | SB | GE1 | Package 10 - Const. FMR at 1) Brgy. Dacudao & Brgy. Talomo River, Calinan District | Davao City | 2013-03-11 | 1st | XI | LF | 1.949 | 40 | 2013-02-14 | 2013-03-25 | 0.24 | O | 0.327 | 0.234 | 0.15 | 0.03 | 0.054 | 0.05 | 84.5 | -
JLA CONSTRUCTION AND SUPPLIES | 24503 | L | B | SB | GE | Construction/ Rehabilitation of Flood Control Mitigation Facilities along Major River Basins: Concrete Revetment along Talomo River, Kadayawan Homes | Brgy. Talomo, Davao City | 2015-06-12 | Final | Davao City | LF | 3.435 | 80 | 2014-12-16 | 2015-03-05 | 0% | C | 0.425 | 0.133 | 0.3 | - | - | - | 85.8% | *85.8% Satisfactory
JLP Construction & Supply | 26983 | L | B | MA | GB1 | Academic Building 3 |  | 05/14-15/09 | 1st | DOST |  | 8.294 | 120 |  |  |  | O | 0.383 | 0.295 | 0.15 | 0.03 | 0.062 | 0.05 | 97 | -
JLP Construction and Supply (Formerly JLP Construction) | 26983 | L | B | SB | GB | Expansion, Batac Main Health Center I | Batac City, Ilocos Norte | 2014-10-22 | 1st & Final | I | LF | 3.4634 | 171 | 2014-01-02 | 2014-06-21 | 3.74% | C | 0.47 | 0.177 | 0.3 | - | - | - | 94.7% | 94.70% Very Satisfactory
J-Marbel Construction and Supply | 24268 | L | B | MA | GB1 | Construction of Auditorium |  | 2009-03-19 | 1st | DOST |  | 13.961 | 169 |  |  |  | O | 0.35 | 0.293 | 0.062 | 0.03 | 0.0525 | 0.033 | 82.05 | -
JMBM Construction | 32955 | L | D | SB | GB | Construction of 1-Storey 2-Classroom Building at Bungro-Sucoc Integrated School | Luna, La Union | 2014-10-25 | 1st & Final | I | LF | 1.8184 | 90 | 2014-06-18 | 2014-09-15 | 0% | C | 0.466 | 0.182 | 0.3 | - | - | - | 94.8% | 94.80% Very Satisfactory
JM-Cofer Construction and Supply | 36143 | L | D | SB | GE | Construction of Drainage System along Baao-Iriga City-Nabua Road, Baao Section | Baao, Camarines Sur | 2014-08-10 | 1st | V | LF | 1.8965 | 186 | 2014-02-14 | 2014-08-18 | -4.02 | O | 0.332 | 0.3 | 0.11 | 0.02 | 0.033 | 0.033 | 82.8 | -
JM-COFER CONSTRUCTION AND SUPPLY | 36143 | L | D | SB | GE | Construction of Drainage System along Baao - Iriga City - Nabua Road, K0467+000 to K0468+000 & K0474+050, both w/exception | Baao, Camarines Sur and Iriga City | 2015-06-03 | Final | Camarines Sur 4th | LF | 1.896 | 157 | 2014-02-14 | 2014-07-20 | 0% | C | 0.442 | 0.168 | 0.3 | - | - | - | 91% | *91% Very Satisfactory
JMD-68 BUILDERS | 36943 | L | D | SB | GB | Construction/Completion of Multi-Purpose Building, Guribang, Diffun, Quirino | Guribang, Diffun, Quirino | 2015-08-30 | 1st & Final | Quirino DEO | LF | 2.616 | 60 | 2015-02-19 | 2015-04-19 | 0% | C | 0.489 | 0.133 | 0.3 | - | - | - | 92.2% | *92.2% Very Satisfactory
JMT Construction | 14186 | L | B | MA | GE | Reconstruction of SCDR (Placer - Bacuag Road Section), K1152+903.30 to K01160+940, along SCDR, Placer | Placer, Surigao del Norte | 2014-06-13 | 1st & Final | XIII | LF | 55.9417 | 276 | 2013-03-19 | 2013-12-19 | 0% | C | 0.332 | 0.2 | 0.3 | - | - | - | 83.2% | 83.20% Satisfactory
JMT Construction | 14186 | L | B | MA | GB | Construction of One-Storey, One Classroom School Building, C.V. Diez Memorial Central Elementary School | Surigao City | 2014-10-28 | 1st & Final | XIII | LF | 1.0751 | 66 | 2014-07-30 | 2014-10-03 | 14.8% | C | 0.427 | 0.133 | 0.3 | - | - | - | 86% | 86.00% Satisfactory
JMT Construction | 14186 | L | B | MA | GE | Rehab./Reconst./Improvement of Damaged Paved National Roads including Drainage based on PMS/HDM-4, National Arterial Road, Km. 1149+000 to Km. 1151+000 | Surigao del Norte | 2014-10-26 | 1st | XIII | LF | 30.689 | 253 | 2014-02-26 | 2014-11-05 | -0.27% | O | 0.338 | 0.238 | 0.147 | 0.022 | 0.051 | 0.05 | 84.6% | 84.60% Satisfactory
JMT Construction | 14186 | L | B | MA | GE | Road Upgrading (Gravel to Paved) Jct. Gamut-San Miguel-Bayugan Road (K1319+746 - K1320+718) | Tago, Surigao del Sur | 2014-10-25 | 1st & Final | XIII | LF | 25.2053 | 205 | 2014-03-18 | 2014-10-08 | -1.28% | C | 0.384 | 0.2 | 0.262 | - | - | - | 84.6% | 84.60% Satisfactory
JMT Construction | 14186 | L | B | MA | GE | Road Upgrading (Gravel to Paved) Jct. Gamut - San Miguel - Bayugan Road, K1319+746.00 - K1320+718 | Tago, Surigao del Sur | 2014-08-06 | 1st | XIII | LF | 25.5106 | 125 | 2014-03-18 | 2014-07-20 | -33.99 | O | 0.358 | 0.23 | 0 | 0.015 | 0.028 | 0.05 | 68.1 | -
JMT Construction | 14186 | L | B | MA | GE | Const./Improvement of Access Roads Leading to Declared Tourism Destinations, Calderon Village Sittio Tagbasingan Rd. Leading to Mamanwa Cultural Village and Eco Park & Surigao City's Highest Peak Mts. | Brgy. Mat-I, Surigao City | 2014-08-13 | 1st & Final | XIII | LF | 9.1405 | 90 | 2014-04-16 | 2014-07-14 | 12.34 | C | 0.367 | 0.2 | 0.3 |  |  |  | 86.7 | 86.70% Satisfactory
JMT Construction | 14186 | L | B | MA | GE | Concreting of Jct. Mabini - Tubajon Road, Km. 085+(-1362) to Km. 085+(-875), Km. 085+000 to Km. 086+375 | Tubajon, Dinagat Island | 2014-08-14 | 1st | XIII | LF | 41.7655 | 235 | 2014-03-21 | 2014-11-10 | -9.12 | O | 0.392 | 0.265 | 0.059 | 0.03 | 0.047 | 0.033 | 82.6 | -
JMT Construction | 14186 | L | B |  | GE5 | Repair of Concrete Pavement at Area J and Portion of 6th Street | Port of Cagayan de Oro, Cagayan de Oro City/ Region X | 2014-03-14 | 1st | PPA | LF | 27.707 | 165 | 2013-12-09 | 2014-05-23 | 23.12 | O | 0.395 | 0.24 | 0.15 | 0.03 | 0.047 | 0.05 | 91.2 | -
JMT Construction | 14186 | L |  |  |  | Repair of Concrete Pavement at Area J and Portion of 6th Street | Port of Cagayan de Oro, Cagayan de Oro City/ Region X | 2014-08-30 | 2nd & Final | PPA | LF | 27.707 | 165 | 2013-12-09 | 2014-05-23 | 0 | C | 0.458 | 0.2 | 0.3 | - | - | - | - | 93.05% Very Satisfactory
JMT Construction | 14186 | L | B |  | GE5 | Repair of Concrete Pavement at Area J and Portion of 6th Street | Port of Cagayan de Oro, Cagayan de Oro City/ Region X | 2014-03-14 | 1st | PPA | LF | 27.707 | 165 | 2013-12-09 | 2014-05-23 | 23.12 | O | 0.395 | 0.24 | 0.15 | 0.03 | 0.047 | 0.05 | 91.2 | -
JMT Construction | 14186 | L | B | MA | GE1 | Rehab./Reconst./Strengthening of Hinatigan Bridge along Surigao-Davao Coastal Rd., Brgy. Hinatigan | Placer, Surigao del Norte | 2013-08-08 | Final | XIII | LF | 20.721 | 442 | 2012-01-13 | 2013-03-29 | 0.25 | C | 0.491 | 0.133 | 0.3 | - | - | - | 92.4 | 86.94% Satisfactory
JMT Construction | 14186 | L | B | MA | GE1 | Rehab./Reconst./Strengthening of Hinatigan Bridge along Surigao-Davao Coastal Rd., Brgy. Hinatigan | Placer, Surigao del Norte | 2013-03-14 | 1st | XIII | LF | 15.662 | 442 | 2012-01-13 | 2013-03-30 | 1.75 | O | 0.362 | 0.225 | 0.15 | 0.02 | 0.026 | 0.05 | 83.3 | -
JMT Construction | 14186 | L | B | MA | GE1 | Reconst. of SDCR (Placer-Bacuag Rd. Sect.) along SDCR, K1152+903.30-K1160+940 | Placer, Surigao del Norte | 2013-08-08 | 1st | XIII | LF | 50.94 | 237 | 2013-03-19 | 2013-11-10 | 1.06 | O | 0.361 | 0.233 | 0.15 | 0.03 | 0.035 | 0.05 | 85.9 | -
JMT Construction | 14186 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Arterial Rd., Daang Maharlika (Surigao-Agusan Sect.) a)Km.1123+(-847)-Km.1123+000; b)Km.113+000-Km.1131+092, Brgy Luna & Brgy. Quezon | Surigao City | 2013-03-14 | Final | XIII | LF | 36.061 | 363 | 2012-01-13 | 2013-01-09 | 4.8 | C | 0.326 | 0.2 | 0.3 | - | - | - | 82.6 | 84.40% Satisfactory
JMT Construction | 14186 | L | B | MA | GE1 | Replacement of Cabongbongan Bridge 2 along Jct. Magsaysay-Cagdianao Rd. | Dinagat Islands | 2013-03-13 | 3rd | XIII | LF | 6.272 | 212 | 2012-03-20 | 2012-10-17 | - | O | 0.333 | 0.171 | 0 | 0.015 | 0.01 | 0 | 52.9 | -
JMT Construction | 14186 | L | B | MA | GE1 | Rd. Upgrading ( Gravel to Concrete) Surigao-San Juan Coastal Rd. |  | 2009-09-06 | 1st | XIII |  | 9.485 | 210 |  |  |  | O | 0.368 | 0.2 | 0.15 | 0.03 | 0.055 | 0.033 | 83.6 | -
JMT Construction | 14186 | L | A | MA | GE1 | Replacement of Cabongbongan Bridge 2 along Jct. Magsaysay-Cagdianao Rd. | Dinagat Islands | 2012-11-22 | 2nd | XIII | LF | 6.272 | 212 | 2012-03-20 | 2012-10-17 | -12.4 | O | 0.364 | 0.3 | 0 | 0.03 | 0.05 | 0.017 | 76.1 | -
JMT Construction | 14186 | L | B | MA | GE1 | Replacement of Cabongbongan Bridge 2 along Jct. Magsaysay-Cagdianao Rd. | Dinagat Islands | 2012-08-10 | 1st | XIII | LF | 5.869 | 150 | 2012-03-20 | 2012-08-16 | -2.8 | O | 0.341 | 0.3 | 0.122 | 0.03 | 0.055 | 0.033 | 88.1 | -
JMT Construction | 14186 | L | B | MA | GE1 | Rehab./Repair of Daywan Bridge (Surigao-Davao Coastal Rd.), Brgy. Daywan | Claver, Surigao del Norte | 2012-08-08 | 2nd | XIII | LF | 13.159 | 300 | 2011-11-14 | 2012-09-08 | 8.12 | O | 0.328 | 0.247 | 0.15 | 0.03 | 0.055 | 0.033 | 84.3 | -
JMT CONSTRUCTION | 14186 | L | B | MA | GE | Rehabilitation/ Reconstruction/ Upgrading of Damaged Paved National Road (Intermittent Section) along Jct. Capalayan-Cabongbongan Road | K1136+(-243) to K1141+621, Surigao City | 2015-06-10 | 1st | SURIGAO DEL NORTE FIRST DEO | LF | 20.466 | 132 | 2015-04-24 | 2015-09-02 | (+) 7.50% | O | 0.386 | 0.24 | 0.15 | 0.03 | 0.06 | 0.05 | 91.6% | -
JMT CONSTRUCTION | 14186 | L | B | SB | GE | Construction of Daywan River Control Along Surigao-Davao Coastal Road | Km. 1175+676, Daywa, Claver, Surigao del Norte | 2015-09-01 | 1st & Final | Surigao del Norte 1st | LF | 7.247 | 120 | ###### | 2015-03-25 | (+) 29.80% | C | 0.454 | 0.141 | 0.3 | - | - | - | 89.5% | *89.5% Very Satisfactory
JMT Construction | 10029 | L |  |  | GE5 | Repair of Reinforced Concrete Deck at Berth 6 & 7 | Port of Cagayan de Oro, Cagayan de Oro City | 2013-05-31 | Final | PPA | L | 24.85 | 240 | 2012-11-07 | 2013-07-05 | 59.39 | C | 0.495 | 0.2 | 0.3 | - | - | - | 99.5 | 96.58% Outstanding
JMT Construction | 14186 | L |  |  | GE5 | Repair of Reinforced Concrete Deck at Berth 6 & 7 | Port of Cagayan de Oro, Cagayan de Oro City / CARAGA | 2013-02-14 | 1st | PPA | LF | 24.85 | 240 | 2012-11-07 | 2013-07-05 | 57.16 | O | 0.366 | 0.3 | 0.15 | 0.03 | 0.05 | 0.05 | 94.6 | -
J'ner Cepada Construction | 30212 | L | B | SB | GE | Road Upgrading (Gravel to Paved) of Jct. Himay-angan-Silago - Abuyog Bdry. Road Km.1122+546.10 - Km.1122+919.70, Km.1124+705.50 - Km.1125+085.50 | Silago, Southern Leyte | 2014-08-05 | 1st | VIII | LF | 11.9101 | 180 | 2014-02-14 | 2014-09-11 | 20.01 | O | 0.355 | 0.3 | 0.15 | 0.008 | 0.05 | 0.033 | 89.6 | -
J'ner Cepada Construction | 30212 | L | B | SB | GE2 | Canturing Flood Control @ Bdry. So. Leyte-Maasin-Macrohon-Sogod Jct. Daang Maharlika | Maasin City, Southern Leyte | 2013-03-16 | Final | VIII | LF | 6.654 | 150 | 2012-07-17 | 2012-12-13 | 0 | C | 0.445 | 0.118 | 0.3 | - | - | - | 86.3 | 84.26% Satisfactory
J'ner Cepada Construction | 30212 |  |  |  |  | Maintenance/Rehab./Impvt. of National Arterial Secondary Rd., Macrohon-P.Burgos Rd., Km.1154+000 - Km.1170+000 |  | 2010-06-07 |  | VIII |  | 9.543 | 180 |  |  |  | O | 0.372 | 0.3 | 0.06 | 0.03 | 0.037 | 0.033 | 83.2 | -
J'ner Cepada Construction | 30212 | L | B | MA | GE1 | Impvt. (Concreting) of Access Road to Maasin Port |  | 2009-05-27 | 1st | VIII |  | 1.833 | 120 |  |  |  | O | 0.4 | 0.24 | 0.15 | 0.03 | 0.047 | 0.05 | 91.7 | -
JO Builders | 34470 | L | B | MA |  | Clark Airport Development Project | Clark Field, Angeles City, Pampanga | 2015-01-15 | 2nd & Final | DOTC | L | 19.853 | 195 | 2014-03-18 | 2014-09-28 | 0 | C | 0.4682 | 0.2 | 0.3 | - | - | - | - | 94.29% Very Satisfactory
JO Builders | 34470 | L | B | MA | GB-1 | Clark Airport Development Project | Clarkfield, Pampanga | 2014-08-14 | 1st | DOTC | LF | 19.853 | 195 | 2014-03-18 | 2014-09-28 | 10.87 | O | 0.369 | 0.3 | 0.15 | 0.03 | 0.05 | 0.033 | 93.2 | -
Joan Construction | 13840 | L | B | MA | GB | Construction of Multi-Purpose Building (CSWD Office) at Brgy. Tandang Sora, Butuan City | Butuan City | 2014-10-29 | 1st & Final | XIII | LF | 1.998 | 75 | 2014-07-08 | 2014-09-20 | 0% | C | 0.463 | 0.133 | 0.3 | - | - | - | 89.6% | 89.60% Very Satisfactory
Jobel Enterprises | 19799 | L | B | MA | GE | Widening of Sta. Cruz Poblacion Road including Drainage/Outfall, K0085+220 to K0090+480 (with exception), Laguna 4th LD | Sta. Cruz Poblacion, Laguna | 2014-11-26 | 1st & Final | IV | LF | 17.316 | 211 | 2014-02-14 | 2014-09-12 | - | C | 0.344 | 0.2 | 0.3 | - | - | - | 84.4% | 84.40% Satisfactory
Jobel Enterprises | 19799 | L | B | SB | GE | Construction/Improvement of Drainage System along Pagsanjan-Lucban Road, Pagsanjan-Laguna 4th LD | Pagsanjan, Laguna | 2014-08-14 | 1st & Final | IV-A | LF | 2.8198 | 75 | 2014-02-14 | 2014-04-29 | 0 | C | 0.437 | 0.2 | 0.3 |  |  |  | 93.7 | 93.70% Very Satisfactory
Jobel Enterprises | 19799 | L | B | MA | GE1 | Widening of Daang Maharlika, K0083+036.35-K0085+304.43 (Intermittent Sect.) | San Pablo City, Laguna | 2013-03-15 | Final | IVA | LF | 22.586 | 224 | 2012-02-21 | 2012-10-01 | 0 | C | 0.45 | 0.133 | 0.3 | - | - | - | 88.3 | 82.06% Satisfactory
Jobel Enterprises | 19799 | L | B | MA | GE1 | Widening of Daang Maharlika, K0083+036.35-K0085+304.43 (IS) | San Pablo City, Laguna | 2012-11-29 | 2nd | IVA | LF | 22.596 | 224 | 2012-02-21 | 2012-10-01 | - | O | 0.297 | 0.3 | 0 | 0.03 | 0.05 | 0.033 | 71 | -
Jobel Enterprises | 19799 | L | B | MA | GE1 | Widening of Daang Maharlika K0083+036.35-K0085+304.43 (IS) | San Pablo City, Laguna | 2012-08-08 | 1st | IVA | LF | 22.596 | 200 | 2012-02-21 | 2012-09-07 | 2.7 | O | 0.285 | 0.3 | 0.15 | 0.03 | 0.05 | 0.033 | 84.8 | -
JOBEL ENTERPRISES | 19799 | L | B | SB | GB | Construction of Multi-Purpose Building, Brgy. Zone 3 | Luisiana, Laguna | 2015-08-27 | 1st & Final | Laguna 1st | LF | 4.742 | 100 | 2015-02-12 | 2015-05-22 | 0% | C | 0.469 | 0.133 | 0.3 | - | - | - | 90.2% | *90.2% Very Satisfactory
John Arne Construction | 24621 | L | D | SB | GE2 | Talibon SRIS Extension | Talibon, Bohol, Region 7 | 2013-07-13 | 1st | NIA | L | 4.024 | 140 | 2012-09-04 | 2013-02-05 | -15.59 | O | 0.38 | 0.24 | 0 | 0.02 | 0.06 | 0.03 | 73 | -
John Dee B. Bustamante Construction | 30458 | L | D | SB | GE | Construction & Maintenance of Bridges along National Roads Rehab./Reconst./ Replacement/Retrofitting of Existing Permanent Bridges along Nueva Ecija - Aurora Road | Auroa | 2014-08-08 | 1st & Final | III | LF | 3.9372 | 90 | 2014-02-17 | 2014-06-17 | 0 | C | 0.444 | 0.133 | 0.3 |  |  |  | 87.7 | 87.70% Satisfactory
John Dee B. Bustamante Construction | 30458 | L | D | SB | GE | Road Upgrading (Gravel to Paved) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standards (HDM-4 Project Analysis), National Arterial Road, Nueva Ecija - Aurora Road | Aurora | 2014-08-08 | 1st & Final | III | LF | 5.9596 | 154 | 2014-02-17 | 2014-04-22 | 3.08 | C | 0.433 | 0.133 | 0.3 |  |  |  | 86.6 | 86.60% Satisfactory
JOHN DEE B. BUSTAMANTE CONSTRUCTION | 30458 | L | D | SB | GB | Construction of Multi-Purpose Building, Brgy. North Poblacion, Dipaculao, Aurora | Dipaculao, Aurora | 2015-06-11 | Final | Aurora DEO | LF | 4.14 | 60 | 2014-03-02 | 2014-05-01 | 0% | C | 0.351 | 0.2 | 0.3 | - | - | - | 85.1% | *85.1% Satisfactory
JOHN RAY DEVELOPER AND SUPPLIES | 20795 | L | D | SB | GB | Construction of Multi-Purpose Bldg. (Kid. City Cultural & Recreation Center) | Poblacion, Kidapawan City | 2015-11-11 | 1st | Cotabato First DEO | LF | 6.5001 | 177 | 2015-08-07 | 2016-01-30 | (-) 9.86% | OG | 0.354 | 0.16 | 0.051 | 0.003 | 0 | 0.016 | 58.4% | 58.4% Poor
JOJO CONSTRUCTION AND DEVELOPMENT CORPORATION (Formerly: Jojo Construction) | 13174 | L | D | SB | GE | Rehabilitation of Slope Protection along Pansipit Creek, Pasig City | Pasig City | 2015-06-04 | Final | Metro Manila 1st DEO | LF | 6.512 | 120 | 2015-03-26 | 2015-07-23 | (+) 70.00 | C | 0.482 | 0.133 | 0.3 | - | - | - | 91.5% | *91.5% Very Satisfactory
JOMARCANN GENERAL CONSTRUCTION | 30599 | L | A | MA | GB | Completion/Rehabilitation of Multi-Purpose Building, Consolacion | Agoo, La Uion | 2015-06-07 | Final | La Union 2nd DEO | LF | 16.257 | 210 | 2015-02-20 | 2015-09-17 | 54.76% | C | 0.498 | 0.133 | 0.3 | - | - | - | 93.1% | *93.1% Very Satisfactory
JOMARCANN GENERAL CONSTRUCTION | 30599 | L | A | MA | GE | Road Upgrading (Unpaved to Paved) along Kabugao-Pudtol-Luna-Cagayan Boundary Road, K0643+086 - K0643+592 | Mataguisi Section, Pudtol, Apayao | 2015-06-10 | 1st | Apayao 2nd DEO | LF | 19.636 | 170 | 2015-03-03 | 2015-08-19 | (+) 0.54% | O | 0.356 | 0.291 | 0.15 | 0.024 | 0.04 | 0.05 | 91.1% | -
JOMARCANN GENERAL CONSTRUCTION | 30599 | L | A | MA | GE | Widening with Drainage and Reblocking on Poor and Bad Sections along Baguio-Bontoc Road, K0255+380 - K0256+172 | La Tridad, Benguet | 2015-06-02 | 1st | Benguet 1st DEO | LF | 44.484 | 182 | 2015-02-20 | 2015-08-20 | (-) 3.85% | O | 0.325 | 0.298 | 0.112 | 0.03 | 0.05 | 0.033 | 84.8% | -
JOMARCANN GENERAL CONSTRUCTION | 30599 | L | A | MA | GE | Widening with Drainage and Reblocking on Poor and Bad Sections along Baguio - Bontoc Road, K0255+380 to K0256+172, La Trinidad, Benguet | La Trinidad, Benguet | 2015-09-03 | 1st | Benguet 1st DEO | LF | 44.848 | 212 | 2015-02-20 | 2015-09-19 | -2.42% | O | 0.375 | 0.225 | 0.125 | 0.03 | 0.056 | 0.033 | 84.4% | -
JOMARCANN GENERAL CONSTRUCTION | 30599 | L | A | MA | GE | Construction of Flood Control Structure along Bued River, Camp 7 to Camp 8 to Gabriela Silang, Baguio City | Baguio City | 2015-09-04 | 1st | Baguio City DEO | LF | 46.505 | 230 | 2015-02-22 | 2015-10-09 | 0.43% | O | 0.339 | 0.251 | 0.15 | 0.03 | 0.055 | 0.05 | 87.5% | -
JOMARCANN GENERAL CONSTRUCTION | 30599 | L | A | MA | GE | Road Upgrading (Unpaved to Paved) along Kabugao - Pudtol - Luna - Cagayan Bdry. Road, K0643+086 to K0643+592, Mataguisi Section, Pudtol, Apayao | Pudtol, Apayao | 2015-08-26 | 1st | Apayao 2nd DEO | LF | 19.636 | 220 | 2015-03-03 | 2015-10-08 | 0.2% | O | 0.347 | 0.231 | 0.15 | 0.03 | 0.051 | 0.05 | 85.9% | -
JOMARCANN GENERAL CONSTRUCTION | 30599 | L | A | MA | GE | Road Upgrading (Unpaved to Paved) Along Kabugao-Pudtol-Luna-Cagayan Bdry. Road, K0643+006-K0643+592, Mataguisi Section | Pudtol, Apayao | 2015-11-15 | 1st | Apayao 2nd | LF | 20.1954 | 290 | 2015-03-03 | 2015-12-17 | 10.00% | OG | 0.335 | 0.24 | 0.15 | 0.022 | 0.045 | 0.033 | 82.5% | 82.5% Satisfactory
JOMARCANN GENERAL CONSTRUCTION | 30599 | L | A | MA | GE | Widening with Drainage and Reblocking on Poor and Bad Sections along Baguio-Bontoc Road, K0255+380-K0256+172 | La Trinidad, Benguet | 2015-11-09 | Final | Benguet 1st | LF | 44.8484 | 237 | 2015-02-20 | 2015-10-14 | - | C | 0.448 | 0.198 | 0.3 | - | - | - | 94.6% | 88.48% Satisfactory
JOMARCANN GENERAL CONSTRUCTION | 30599 | L | A | MA | GE | Construction of Flood Control Structure Along Bued River, Camp 7 to Camp 8 to Gabriela Silang | Gabriela Silang, Baguio City Lone District | 2015-11-09 | Final | Baguio City | LF | 46.5055 | 230 | 2015-02-22 | 2015-10-09 | - | C | 0.416 | 0.179 | 0.3 | - | - | - | 89.5% | 88.3% Satisfactory
Jomzki Construction and Supply | 32703 | L | D | SB | GB | Rehabilitation & Reconstruction of MPC Structure (Covered Court) Brgy. Taludtod | Balayan, Batangas | 2014-11-08 | 1st & Final | IV | LF | 3.5 | 105 | 2014-04-07 | 2014-07-20 | 6% | C | 0.323 | 0.2 | 0.3 | - | - | - | 82.3% | 82.30% Satisfactory
J-One Builders | 32509 | L | B | SB | GE2 | Reconst. of Approaches & Bank Protection, Olandang Bridge IV (57.60 lin.m.), Olandang | Midsayap, Cotabato | 2013-03-16 | Final | XII | LF | 10.623 | 175 | 2012-01-23 | 2012-07-16 | 0.57 | C | 0.467 | 0.133 | 0.3 | - | - | - | 90 | 87.78% Satisfactory
J-ONE BUILDERS | 32509 | L | B | MA | GE | Road Concreting, Poblacion 3 | Pigcawayan, Cotabato | 2015-11-06 | Final | Cotabato 2nd DEO | LF | 1.878 | 36 | 2015-02-19 | 2015-03-27 | 30.56% | C | 0.422 | 0.133 | 0.3 | - | - | - | 85.5% | *85.5% Satisfactory
J-ONE BUILDERS | 32509 | L | B | MA | GE | Repair/Rehabilitation/Improvement (Additional Pavement Width) along Awang-Upi-Lebak-Kalamansig-Palimbang-Sarangani Road S00732MN K1951+100 - K1952+000 w/ exception (K1951+254 - K1951+442.55; K1951+445.86 - K1951+771.53; K1951+790.27 -K1952+000) Kalamansig, Sultan Kudarat | Kalamansig, Sultan Kudarat | 2015-11-16 | 1st | Sultan Kudarat Second DEO | LF | 8.0861 | 95 | 2015-08-24 | 2015-11-26 | (-) 49.42% | OG | 0.39 | 0.16 | 0 | 0 | 0.014 | 0 | 56.4% | 56.4% Poor
Jonik Trading & Construction | 20612 | L | D | SB | GB | Construction of 1-Storey 1-Classroom School Bldg., Pangascasan Integrated School | Sual, Pangasinan | 2014-10-27 | 1st & Final | I | LF | 1.0734 | 60 | 2014-07-15 | 2014-09-12 | -1.67% | C | 0.489 | 0.166 | 0.3 | - | - | - | 95.5% | 95.50% Very Satisfactory
Jonik Trading & Construction | 20612 | L | D | SB | GE | Construction/Rehabilitation of Caranglaan River Bank Slope Protection along Pangasinan-Zambales Road | Mabini, Pangasinan | 2014-08-14 | 1st & Final | I | LF | 3.8 | 85 | 2014-01-29 | 2014-04-23 | 27.06 | C | 0.403 | 0.133 | 0.3 |  |  |  | 83.6 | 83.60% Satisfactory
Joselle Construction | 16243 | L | D | SB | GB | Construction of Multi-Purpose Building at Brgy. Lingayao, Las Nieves, Agusan del Norte | Las Nieves, Agusan del Norte | 2014-10-29 | 1st & Final | XIII | LF | 1.9827 | 45 | 2014-04-12 | 2014-05-26 | 0% | C | 0.383 | 0.2 | 0.3 | - | - | - | 88.3% | 88.30% Satisfactory
Jotcresm Engineering & Enterprises | 32417 | L |  | SB |  | CONSTRUCTION OF DORMITORY I | LIME KILN IRISAN, BAGUIO CITY | 2014-01-28 | Final | DOST | LF | 10.951 | 277 | 2013-01-05 | 2014-09-29 | 0 | C | 0.441 | 0.2 | 0.3 | - | - | - | - | 87.80% Satisfactory
Jovic Construction & Supply | 35703 | L | C | SB | GB | Const of Various Flood Control Nayon Flood Control (Upstream of Bannit Briodge) | Nayon, Lamut, Ifuago | 2014-08-05 | 1st & Final | CAR | LF | 0.58634 | 113 | 2014-04-25 | 2014-08-15 | 63.72 | C | 0.4 | 0.133 | 0.3 |  |  |  | 83.3 | 83.30% Satisfactory
JP Chan Construction | 23789 | L | B | SB | GB | Talisayan Seaside Blvd. Baywalk | Talisayan, Misamis Oriental | 2015-01-08 | Final | TIEZA | LF | 2.5 | 90 | 2013-10-13 | 2014-02-05 |  | C | 0.471 | 0.2 | 0.3 |  |  |  | 97.1 | 97.10% Outstanding
JQD Construction and General Services | 18852 | L | B | SB | GB1 | Const. of Tigbao E/S, 2-CL | Libagon, Southern Leyte | 2013-08-05 | Final | VIII | LF | 1.142 | 90 | 2013-01-03 | 2013-04-02 | 0 | C | 0.389 | 0.133 | 0.3 | - | - | - | 82.2 | 85.14% Satisfactory
JQD Construction and General Services | 18852 | L | B | SB | GB1 | Const. of Tigbao E/S, 2-CL | Libagon, Leyte | 2013-03-16 | 1st | VIII | LF | 1.142 | 90 | 2013-01-03 | 2013-04-02 | 0.14 | O | 0.381 | 0.225 | 0.15 | 0.03 | 0.035 | 0.05 | 87.1 | -
JQD CONSTRUCTION AND GENERAL SERVICES | 18852 | L | B | SB | GE | Rehab/Major Repair of Permanent Bridges, Dinahugan Bridge, Along Bdry. Souther Leyte- Maasin-Macrohon-Sogod-Daang Maharlika, Padre Burgos, Southern Leyte | Along Bdry. Souther Leyte- Maasin-Macrohon-Sogod-Daang Maharlika, Padre Burgos, Southern Leyte | 2015-06-03 | 1st | Southern Leyte DEO | LF | 4.732 | 150 | 2015-02-02 | 2015-07-01 | - | O | 0.304 | 0.205 | 0.15 | 0 | 0.06 | 0.05 | 76.9% | -
JQD CONSTRUCTION AND GENERAL SERVICES | 18852 | L | A | MA | GE | Rehab./Major Repair of Permanent Bridges, Dinahugan Bridges I along Bdry. Southern Leyte-Maasin-Machoron-Sogod-Daang Maharlika (BOO310LT), Padre Burgos, Southern Leyte | Padre Burgos, Southern Leyte | 2015-08-30 | Final | Southern Leyte DEO | LF | 4.732 | 150 | 2015-02-02 | 2015-07-01 | (+)21.75 | C | 0.365 | 0.191 | 0.3 | - | - | - | 85.6% | *80.38% Unsatisfactory
JQM CONSTRUCTION AND TRADING | 36354 | L | D | SB | GE | MFO-1 NRNW - Rehabilitaion/Reconstruction/Upgrading of Damaged Paved National Roads including Drainage Based on Pavement Management System/Highway Development and Management-4 (HDM-4) (Intermittent Section) along Mc Arthur Bridge Service Road Chainage 0 - Chainage 234, Manila City 3rd LD | Manila City 3rd LD | 2015-12-11 | Final | North Manila DEO | LF | 4.8923 | 150 | 2015-05-07 | 2015-10-03 | 0.00% | C | 0.498 | 0.133 | 0.3 | - | - | - | 93.1% | 93.1% Very Satisfactory
J-R3 CONSTRUCTION AND SUPPLY | 36440 | L | D | SB | GE | Construction/ Upgrading of Local Road, Barangay Poblacion | Jabonga, Agusan Del Norte | 2015-06-02 | Final | AGUSAN DEL NORTE DEO | LF | 2.802 | 48 | 2015-03-27 | 2015-05-13 | (+) 58.33% | C | 0.471 | 0.133 | 0.3 | - | - | - | 90.4% | *90.4% Very Satisfactory
JRD Construction and Supply | 37318 | L | D | SB | GE | Road Upgrading (Gravel to Concrete) of Barangay Duit - Baggo - Nungawa Road | Asipulo, Ifugao | 2014-11-24 | 1st & Final | CAR | LF | 1.8134 | 77 | 2014-07-16 | 2014-09-30 | 0% | C | 0.439 | 0.133 | 0.3 | - | - | - | 87.2% | 87.20% Satisfactory
JRD-D2 Enterprises | 18291 | L | B | MA | GB | Construction of Two (2) Storey, Eight (8) Classroom School Building at Sampaloc National High School | Tanay, Rizal | 2014-11-27 | 1st & Final | IV | LF | 9.0532 | 180 | 2013-11-07 | 2014-05-05 | 21.67% | C | 0.47 | 0.133 | 0.3 | - | - | - | 90.3% | 90.30% Very Satisfactory
JRY Construction | 10943 | L | AA | MB |  | Emergency Repair of Damaged Access Road Causeway Caused by 7.2 Magnitude Earthquake on October 15, 2013 | Port of Tubigon, Tubigon, Bohol | 2015-08-07 | 2nd & Final | PPA | LF | 35.353 | 360 | 2014-06-09 | 2015-06-03 | 0 | C | 0.5 | 0.2 | 0.3 | - | - | - | 100 | 96.22% Outstanding
JRY Construction | 10943 | L | AA | MB |  | Emergency Repair of Damaged Access Road Causeway caused by 7.2 Magnitude Earthquake | Port of Tubigon, Bohol | 2014-11-15 | 1st | PPA | L | 35.247 | 360 | 2014-06-09 | 2015-06-03 | 11.6 | O | 0.369 | 0.288 | 0.15 | 0.024 | 0.056 | 0.05 | 93.7 | -
JRY Construction | 10943 | L |  | MB | GE5 | Construction of Passenger Terminal Building and Back-Up Area | Port of Tubigon, Bohol | 2013-05-09 | 1st | PPA | LF | 69.999 | 360 | 2012-10-29 | 2013-10-23 | -3.33 | O | 0.3931 | 0.2672 | 0.1167 | 0.03 | 0.07 | 0.05 | 92.7 | -
JRY Construction Corporation | 10943 |  | AA |  |  | Construction of PTB & Back-Up Area | Port of Tubigon, Bohol | 2014-08-15 | 2nd & Final | PPA | LF | 73.929 | 360 | 2012-10-29 | 2014-08-09 | 0 | C | 0.4936 | 0.2 | 0.3 | - | - | - | - | 94.70% Very Satisfactory
JT GAMOLO CONSTRUCTION | 15759 | L | B | MA | GE | Concreting of Road, San Jose-Panamukan Road, Brgy. San Jose, Malaybalay City, Bukidnon | Malaybalay City, Bukidnon | 2015-11-12 | Final | Bukidnon 1st | LF | 28.1982 | 150 | 2015-05-12 | 2015-10-09 | 0.00% | C | 0.466 | 0.137 | 0.3 | - | - | - | 90.3% | 90.48% Very Satisfactory
JTA Builders | 1801 | L | A | MB | GB1 | Const. of 2-CL 7.0m x 1.0 m Dulong E/S |  | 2009-09-09 | 1st | X |  | 1.033 | 60 |  |  |  | O | 0.379 | 0.191 | 0.15 | 0.03 | 0.043 | 0.033 | 82.6 | -
JTA BUILDERS | 18401 | L | A | MA | GB | Construction of Multi-Purpose Building, Barangay Poblacion | Culasi, Antique | 2015-08-31 | 1st | Antique | LF | 2.992 | 120 | 2015-05-21 | 2015-09-17 | 0.29% | O | 0.348 | 0.24 | 0.15 | 0.03 | 0.048 | 0.05 | 86.6% | -
JTA Builders/G.M. Pajarillaga Construction & Supply (JV) | JV-13-357 | L | A | MA | GE | Widening of Nueva Vizcaya-Ifugao Road, K0284+250 - K0284+920 | Bagabag, Nueva Vizcaya | 2014-10-29 | 1st & Final | II | LF | 19.5 | 190 | 2014-01-28 | 2014-08-05 |  | C | 0.405 | 0.134 | 0.3 | - | - | - | 83.9% | 83.90% Satisfactory
JTC Cruz Construction Co. Inc. | 32479 | L | C | SB | GE | Preventive Maintenance (MFO-1) Liliw-Majayjay Road, K0103+368 to K0105+405 | Liliw-Majayjay Road | 2014-08-15 | 1st & Final | IV-A | LF | 15.0867 | 53 | 2014-02-14 | 2014-04-07 | 0 | C | 0.411 | 0.2 | 0.3 |  |  |  | 91.1 | 91.10% Very Satisfactory
JTC Cruz Construction Co., Inc. | 32479 | L | C | SB | GE | Preventive Maintenance (Intermittent Section), 7th Avenue East | Caloocan City | 2014-11-22 | 1st & Final | NCR | LF | 9.7117 | 90 | 2014-05-02 | 2014-07-30 | 0% | C | 0.433 | 0.133 | 0.3 | - | - | - | 86.6% | 86.60% Satisfactory
JTC Cruz Construction Co., Inc. | 32479 | L | B | MA | GE | Cluster I for the Preventive Maintenance (MFO-1) of Calamba-Sta. Cruz-Famy Jct. Road, A. K0109+-078 to K0109+000; B. K0109+450 to K0109+989 | Laguna | 2014-11-26 | 1st & Final | IV | LF | 9.2459 | 33 | 2014-02-14 | 2014-03-18 | 6.37% | C | 0.316 | 0.2 | 0.3 | - | - | - | 81.6% | 81.60% Unsatisfactory
JUCONS CONSTRUCTION & SUPPLY | 32051 | L | B | SB | GE | Base Concreting/Opening-15IE-0007-From Sitio Abo-Abo, Sambulayan, Barangay Libas, Leyte, Leyte | Sambulayan, Barangay Libas, Leyte, Leyte | 2015-11-13 | Final | Leyte Third DEO | LF | 4.5119 | 90 | 2015-02-06 | 2015-05-06 | - | C | 0.425 | 0.14 | 0.3 | - | - | - | 86.5% | 86.5% Satisfactory
JUF Construction | 17987 | L | A | MA | GE | Rehabilitation/Reconstruction of Roadslip along Dimakiling J.P. St. | Calbayog City, Samar | 2014-10-23 | 1st & Final | VIII | LF | 18.0482 | 180 | 2014-02-24 | 2014-08-22 | 1.33% | C | 0.462 | 0.133 | 0.3 | - | - | - | 89.5% | 89.50% Very Satisfactory
JUF Construction | 17987 | L | A | SB | GE | Rehab./Impv't. of Flood Control along Calbayog - Catarman Road (Phase II) | Calbayog City, Samar | 2014-08-11 | Final | VIII | LF | 7.7829 | 150 | 2013-04-19 | 2013-09-14 | 2.25 | C | 0.443 | 0.2 | 0.3 |  |  |  | 94.3 | 85.66% Satisfactory
JUF Construction | 17987 | L | A | SB | GE2 | Rehab./Impv't. of Flood Control along Catarman-Calbayog Rd., Brgy. Oquendo | Calbayog City, Samar | 2013-08-13 | 1st | VIII | LF | 7.785 | 89 | 2013-04-19 | 2013-07-16 | -35 | O | 0.386 | 0.3 | 0 | 0.03 | 0.05 | 0.033 | 79.9 | -
JUF Construction | 17987 | L | A | MA | GE1 | Rehab./Repair of Jibatang Bridge along Daang Maharlika (SM) (San Isidro-San Juanico Bridge), Brgy. Lonoy | Calbayog City, Samar | 2013-03-19 | Final | VIII | LF | 27.644 | 240 | 2012-01-31 | 2012-09-26 | 0.42 | C | 0.431 | 0.114 | 0.3 | - | - | - | 84.5 | 83.75% Satisfactory
Juldan Builders | 22810 | L | C | SB | GB | Construction of 3 Classroom at Daang Sarile Integrated School | Cabanatuan City | 2014-11-07 | 1st & Final | III | LF | 1.8674 | 75 | 2014-07-03 | 2014-09-03 | 0% | C | 0.43 | 0.133 | 0.3 | - | - | - | 86.3% | 86.30% Satisfactory
Junjing Construction | 32636 | L | D | SB | GB1 | Const. of Sch. Bldg., Ozamiz City Sch. of Arts and Trades | Ozamis City | 2013-08-16 | 1st | X | LF | 4.842 | 137 | 2013-03-27 | 2013-08-10 | -5.16 | O | 0.399 | 0.203 | 0.055 | 0.03 | 0.059 | 0.033 | 77.9 | -
Junjing Construction & General Merchandise | 32636 | L | B | MA | GB | Construction of School Building, Ozamis City School of Arts and Trades | Ozamis City | 2014-08-14 | Final | X | LF | 4.8419 | 84 | 2013-03-27 | 2013-06-18 | -5.16 | C | 0.442 | 0.2 | 0.145 |  |  |  | 78.7 | 78.14% Unsatisfactory
Junjing Construction & General Merchandize | 32636 | L |  |  |  | Construction/Fit-out of DBP Villaueva Branch | National Highway, Katipunan, Villanueva, Misamis Oriental | 4/18/2016 | 1st | PICE-CDO | LF | 12.813 | 45 | 1/19/16 | 2016-03-04 | 0 | O | 0.39 | 0.321 | 0.123 | 0.03 | 0.065 | 0.05 | 97.9 | -
Junjing Construction & General Merchandize | 32636 | L |  |  |  | Construction, Renovation and Fit-out of DBP Ozamis Branch | Burgos Zamora Sts. Ozamis City, Region X | 3/20/16 | Final | PICE-CDO | LF | 11.511 | 165 | 2015-06-05 | 2015-11-17 | 0 | C | 0.494 | 0.2 | 0.3 | - | - | - | 99.4 | -
Junjing Construction & General Merchandize | 32636 |  |  |  |  | Construction and Fit-out of DBP - Siquijor Branch | Multipurpose Community Hall, Mun. of Siquijor, Siquijor | 2016-10-12 | 1st | DBP | LF | 13.964 | 150 | 2016-06-13 | 2016-11-09 | 0.6 | O | 0.3739 | 0.2 | 0.15 | 0.0225 | 0.0636 | 0.05 | 86 | -
Juntan Construction and Supplies | 26024 | L | B | MA | GE | Construction of Roads-Municipality of San Luis | San Luis, Batangas | 2014-12-06 | 1st & Final | IV | LF | 3.9937 | 90 | 7/10/114 | 2014-10-07 | 0% | C | 0.448 | 0.133 | 0.3 | - | - | - | 88.1% | 88.10% Satisfactory
Jupa Construction | 23577 | L | B | MA | GE | Rehabilitation/Reconstruction of Critical Section along National Roads such as Slips/Emergency/Protection Works, Secondary Roads, Road Slip along Rawis-Catubig-Las Navas Road under Cluster Roadslip - 2014-01 1.)K0803+000-k0804+000 (with exceptions), Catubig-Las Navas Section | Northern Samar | 2014-10-20 | 1st & Final | VIII | LF | 19.4059 | 170 | 2014-03-17 | 2014-09-02 | 0.36% | C | 0.443 | 0.133 | 0.3 | - | - | - | 87.6% | 87.60% Satisfactory
Jupa Construction | 23577 | L | B | MA | GE | Road Widening of National Road along Catarman (Boundary) Rawis Road Section KO771+000 - KO773+000 with exception Preventive Maintenance along Catarman - Laoang Road - San Roque Pambujan Section, KO773+000 - KO774+000 with exception | San Roque, Northern Samar | 2014-08-12 | 1st & Final | VIII | LF | 6.2791 | 150 | 2013-03-25 | 2013-08-21 | 0.95 | C | 0.39 | 0.133 | 0.3 |  |  |  | 82.3 | 82.30% Satisfactory
Jupa Construction | 23577 | L | B | MA | GE1 | Rd. Widening of Nat'l Rd. along Catarman (Boundary) Rawis Rd. Sect., K0771+000-K0773+000 w/ exception | San Roque, Northern Samar | 2013-08-06 | 1st | VIII | LF | 6.279 | 150 | 2013-03-25 | 2013-08-21 | 8.2 | O | 0.366 | 0.24 | 0.15 | 0.03 | 0.055 | 0.033 | 87.4 | -
JUPA CONSTRUCTION | 23577 | L | B | MA | GE | Off-Carriageway Improvement, Concreting of Road Shoulder Rawis-Catubig Road, K0794+800 - K0796+150, 2nd District, Northern Samar | K0794+800 - K0796+150, 2nd District, Northern Samar | 2015-09-04 | 1st & Final | Northern Samar 2nd DEO | LF | 9.143 | 60 | 2015-02-25 | 2015-04-25 | (+)2.86 | C | 0.388 | 0.2 | 0.3 | - | - | - | 88.8% | *88.8% Satisfactory
JUPA CONSTRUCTION | 23577 | L | B | SA | GE | Off-Carriageway Improvement, Concreting of Road Shoulder, Rawis Catubig Road, K0793+500 - K0794+800, 2nd District, Northern Samar | K0793+500 - K0794+800, 2nd District, Northern Samar | 2015-06-26 | Final | Northern Samar Second DEO | LF | 18.136 | 120 | 2015-02-25 | 2015-06-24 | - | C | 0.332 | 0.2 | 0.3 | - | - | - | 83.2% | *83.2% Satisfactory
JV CONSTECH | 35974 | L | C | SB | GB | Construction of Multi-Pupose Building (Mini Gym) at Barurao II | Lebak, Sultan Kudarat | 2015-08-27 | 1st & Final | Sultan Kudarat 2nd | LF | 1.562 | 90 | 2015-03-06 | 2015-06-03 | (+)36.67% | C | 0.448 | 0.133 | 0.3 | - | - | - | 88.1% | *88.1% Satisfactory
JV Lagon Construction Corporation | 11561 | L | A | MA | GE1 | Sarangani-Davao Del Sur Coastal Road, Sapu Masla-Kapatan Section Malapatan-Glan |  | 2009-09-16 | 1st | XII |  | 7.01 | 90 |  |  |  | O | 0.35 | 0 | 0 | 0.01 | 0.015 | 0 | 37.5 | -
JV Lagon Construction Corporation | 11561 | L | A | MA | GB1 | Rehab./Reconst. of Damaged Roads Dulawan Marbel (Tacurong-New Carmen Section) |  | 2009-03-13 | 1st | XII |  | 19.022 | 435 |  |  |  | O | 0.365 | 0.3 | 0.099 | 0.03 | 0.035 | 0.05 | #VALUE! | -
JV Loreto Const. & Development Corp. / Viguz Const. Corp. (JV) | JV-09-091 |  |  |  |  | Rehab./Reconst. of Daang Maharlika, Dulag-McArthur Rd. Sect. |  | 2010-06-10 |  | VIII |  | 47 | 192 |  |  |  | O | 0.373 | 0.25 | 0.15 | 0.03 | 0.047 | 0.05 | 90 | -
JV Loreto Construction & Development Corp. | 13120 | L | A | MB | GE1 | Rehab./Reconst. Along Daang Maharlika, K0995+000-K0997+000 w/ exceptions | Mahaplag, Leyte | 2012-03-27 | 1st | VIII | LF | 11.937 | 160 | 2012-01-30 | 2012-07-07 | 0.38 | O | 0.312 | 0.232 | 0.15 | 0.03 | 0.03 | 0.05 | 80.4 | -
JWD Construction | 22291 |  | A |  |  | Construction of RMMC-RM5 Pumping Station | Brgy. District 1, Reina Mercedes, Isabela | 2015-04-17 | 1st & Final | NIA | L | 16.518 | 353 | 2014-04-21 | 2015-04-05 | 0 | C | 0.4451 | 0.16 | 0.3 | - | - | - | - | 90.51% Very Satisfactory
JYM Construction & Supply | 34595 | L | C | SB | GE2 | Ibong Sapa Flood Control | Virac, Catanduanes | 2013-07-30 | Final | V | LF | 4.845 | 64 | 2013-02-15 | 2013-04-19 | 0 | C | 0.409 | 0.2 | 0.3 | - | - | - | 90.9 | 87.24% Satisfactory
JYM Construction & Supply | 34595 | L | C | SB | GE2 | Ibong Sapa Flood Control | Virac, Catanduanes | 2013-03-17 | 1st | V | LF | 4.845 | 60 | 2013-02-15 | 2013-04-15 | -4.99 | O | 0.342 | 0.3 | 0.1 | 0.03 | 0.043 | 0.033 | 84.8 | -
K.A BUILDERS | 27821 | L | B | MA | GE | Road Concreting, Villarica-Macao Street | Midsayap, Cotabato | 2015-06-06 | Final | Cotabato 2nd DEO | LF | 1.87 | 36 | 2015-03-04 | 2015-04-09 | 0% | C | 0.461 | 0.133 | 0.3 | - | - | - | 89.4% | *89.4% Very Satisfactory
K.A. BUILDERS | 27821 | L | B | SB | GB | Construction of office of the Vice President (OVP) Office of the Senior Citizens Affairs (OSCA) (Multi-Purpose Building) Center, Midsayap, North Cotabato | Midsayap, Cotabato | 2015-11-12 | 1st | Cotabato Second DEO | LF | 1.8992 | 79 | 2015-10-29 | 2015-01-16 | (+) 20.89% | OG | 0.373 | 0.24 | 0.15 | 0.02 | 0.023 | 0.05 | 85.6% | 85.6% Satisfactory
Kajima Corporation | FC-04-023 | F | AAA | LB | GE1 | Const. of Segment 3B-2, Subway (Tunnel) Section at Cebu City, MCDP III, Cebu South Coastal Road |  | 2009-06-06 | 4th | MCDP |  | 1367.069 | 1247 |  |  |  | O | 0.357 | 0.3 | 0.15 | 0.03 | 0.07 | 0.05 | 95.7 | -
Kajima Corporation | FC-04-023 |  |  |  |  | Const. of Cebu South Coastal Rd., Project Segment 3B-2 (Tunnel Sect.) |  | 2010-06-19 |  | MCDP |  | 1625.321 | 1367 |  |  |  | O | 0.299 | 0.3 | 0 | 0.03 | 0.07 | 0.05 | 74.9 | -
Kamagong Builders and Developers Corporation | 1720 | L | AAA | MB | GE | Const./Rehab of Drainage Protection Works along National Roads and Bridges/Secondary Roads/Const?Rehab of Drainage System along Kawit-Noveleta Diversion Road, Cavite 1st LD | Kawit | 2014-08-05 | 1st | IV-A | LF | 46.5495 | 200 | 2014-05-03 | 2014-11-18 | 0.69 | O | 0.362 | 0.24 | 0.15 | 0.015 | 0.038 | 0.033 | 83.8 | -
KANE CONSTRUCTION INC. | 2888 | L | A | MB | GE | Off Carriageway Improvement Dulag-Julita-Burauen Road, K0944+214-K0947+000, Carigara, Leyte | K0944+214-K0947+000, Carigara, Leyte | 2015-08-25 | 1st | Leyte 2nd DEO | LF | 34.607 | 190 | 2015-03-12 | 2015-09-17 | (+)0.02 | O | 0.36 | 0.3 | 0.15 | 0.01 | 0.045 | 0.05 | 91.5% | -
KANE CONSTRUCTION, INC | 2888 | L | A | MB | GE | Off-Carriageway Improvement Dulag - Julita - Burauen Road, K0944+214 to K0947+000, Dulag, Leyte | K0944+214 to K0947+000, Dulag, Leyte | 2015-06-08 | 1st | Leyte Second DEO | LF | 34.607 | 145 | 2015-03-12 | 2015-08-03 | - | O | 0.387 | 0.246 | 0.15 | 0.03 | 0.047 | 0.05 | 91% | -
Kane Construction, Inc. | 2888 | L | A | MB | GE1 | Restoration of Rd./Damaged Drainage Facilities along Gov. Pack Rd. (POPSTIRP Proj.) | Baguio City | 2013-03-24 | Final | CAR | LF | 9.673 | 409 | 2011-04-07 | 2012-05-20 | - | C | 0.464 | 0.2 | 0 | - | - | - | 66.4 | 70.36% Poor
Kane Construction, Inc. | 2888 | L | A | MB | GE1 | Restoration of Collapsed Retaining Wall along Kennon R.d, Km.244+00 -Km.244+186 (POPSTIRP Proj.) | Baguio City | 2013-03-24 | Final | CAR | LF | 5.88 | 409 | 2011-04-07 | 2012-05-20 | - | C | 0.465 | 0.2 | 0 | - | - | - | 66.5 | 67.22% Poor
Kane Construction, Inc. | 2888 | L | A | MB | GE1 | Restoration of Overhang Revetment Wall & Collapsed Retaining Wall along Kennon Rd., Km.241+000-Km.241+093.5 w/ exception | Baguio City | 2013-03-24 | Final | CAR | LF | 5.811 | 409 | 2011-04-07 | 2012-05-20 | - | C | 0.32 | 0.2 | 0 | - | - | - | 52 | 61.66% Poor
KANE CONSTRUCTION, INC. | 2888 | L | A | MB | GE | Construction of Baroro River Control Project along Baroro River | San Juan, San Gabriel, La Union | 2015-06-06 | 1st | La Union 1st DEO | LF | 18.607 | 145 | 2015-02-07 | 2015-07-01 | 0.07% | O | 0.372 | 0.24 | 0.15 | 0.03 | 0.045 | 0.033 | 87% | -
KANE CONSTRUCTION, INC. | 2888 | L | A | MB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads including Drainage Based on Pavement Management System/Highway Development and Management-4 (HDM-4) (Intermittent Sections), P. Burgos, Chainage 0000 to Chainage 0497 and K0251+(-445) to K0251+535, Baguio City | Baguio City | 2015-09-04 | 1st | Baguio City DEO | LF | 26.039 | 192 | 2015-03-02 | 2015-09-09 | 0.2% | O | 0.375 | 0.231 | 0.15 | 0.03 | 0.047 | 0.05 | 88.3% | -
KANE CONSTRUCTION, INC. | 2888 | L | A | MB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads including Drainage Based on Pavement Management System/Highway Development and Management-4 (HDM-4) (Intermittent Sections) P. Burgos, Chainage 0000 - Chainage 0497 (S00490LZ) and K0251+(-445) - K0251+535 (S04685LZ), | P. Burgos, Baguio City | 2015-11-09 | Final | Baguio City | LF | 26.0395 | 192 | 2015-03-02 | 2015-09-09 | 0.00% | C | 0.45 | 0.2 | 0.3 | - | - | - | 95% | 89.96% Very Satisfactory
KANE CONSTRUCTION, INC. | 2888 | L | A | MB | GE | Off Carriageway Improvement Dulag-Julita-Burauen Road, K0944+214-K0947+000, Dulag, Leyte | Dulag, Leyte | 2015-11-12 | Final | Leyte Second DEO | LF | 34.607 | 190 | 2015-03-12 | 2015-09-17 | - | C | 0.413 | 0.2 | 0.3 | 0 | 0 | 0 | 91.3% | 91.27% Very Satisfactory
KANE CONSTRUCTION, INC./H. G. LOPEZ CONSTRUCTION (JV) | JV-14-243 | L | A | MB | GE | Rehabilitation/Improvement of Amburayan River Flood Control, Barangay Ipet and Barangay Ilocano and Old Central, Sudipen, La Union | Barangay Ipet and Barangay Ilocano and Old Central, Sudipen, La Union | 2015-08-29 | 1st | La Union 1st DEO | LF | 18.616 | 233 | 2015-02-11 | 2015-10-02 | (+)1.51 | O | 0.367 | 0.252 | 0.15 | 0.023 | 0.05 | 0.05 | 89.2% | -
KCS Construction & Supply | 19641 |  |  |  |  | Conc. of Alianza Road |  | 2010-06-08 |  | V |  | 4.719 | 90 |  |  |  | O | 0.304 | 0.3 | 0.15 | 0.03 | 0.035 | 0.033 | 85.2 | -
KCS Construction & Supply | 19641 | L | B | MA | GE1 | Impvt. of Lagonoy-Presentacion Road, Km. 499+491-Km.528+00 with exceptions |  | 2009-09-09 | 1st | V |  | 14.142 | 231 |  |  |  | O | 0.346 | 0.24 | 0.15 | 0.03 | 0.042 | 0.05 | 85.8 | -
Kejamarenik Construction & Construction Supplies | 33742 | L | D | SB | GB | Construction of Multi-Purpose Building at Brgy. 7, Mamburao | Mamburao, Occidental Mindoro | 2014-08-14 | Final | IV-B | LF | 9.6882 | 210 | 2012-12-16 | 2013-07-13 | -9.52 | C | 0.429 | 0.2 | 0.014 |  |  |  | 64.3 | 75.22% Unsatisfactory
Kejamarenik Construction & Construction Supplies | 33742 | L | D | SB | GB1 | Const. of MPB at Brgy. 7 | Mamburao, Occidental Mindoro | 2013-07-29 | 1st | IVB | LF | 9.699 | 210 | 2012-12-16 | 2013-07-13 | -2.47 | O | 0.349 | 0.3 | 0.049 | 0.03 | 0.038 | 0.033 | 79.9 | -
KEJAMARENIK CONSTRUCTION & CONSTRUCTION SUPPLIES | 33742 | L | D | SB | GB | Cluster 2014 BEFF-10: Construction of Various ES Building: a) Adela ES, 1Stry 3 CL | Rizal, Occidental Mindoro | 2015-06-08 | Final | Occidental Mindoro DEO | LF | 2.883 | 130 | 2014-09-22 | 2015-01-31 | 0% | C | 0.48 | 0.133 | 0.3 | - | - | - | 91.3% | *91.3% Very Satisfactory
Kenbe Construction & Supply | 34290 | L | B | SB | GB | Rehab./Reconstruction/Upgrading/Concreting of Jct. New Sagay - Old Sagay Road, K0088+000 - K0088+320 | Sagay City, Negros Occidental | 2014-10-21 | 1st & Final | VI | LF | 5.9676 | 78 | 2014-05-12 | 2014-07-28 |  | C | 0.398 | 0.133 | 0.3 | - | - | - | 83.1% | 83.10% Satisfactory
KENBE CONSTRUCTION & SUPPLY | 34290 | L | B | SB | GB | Rehabilitation of Multi-Purpose Building, Oton Multi Purpose Building, Oton, Iloilo | Oton, Iloilo | 2015-11-09 | Final | Iloilo 1st | LF | 3.2896 | 150 | 2015-02-16 | 2015-07-16 | 0.00% | C | 0.437 | 0.164 | 0.3 | - | - | - | 90.1% | 90.1% Very Satisfactory
KENT MARKETING GROUP OF COMPANIES, INC. | 37716 | L | C | B | SB | Rehabilitation/Concreting of Poblacion Farm to Market Road, Sta. 0+003.50 - 0+560, Brgy. Poblacion, San Francisco, Surigao del Norte | Brgy. Poblacion, San Francisco, Surigao del Norte | 2015-11-15 | 1st | Surigao del Norte 1st DEO | LF | 4.7488 | 65 | 2015-08-26 | 2015-10-29 | - | OG | 0.33 | 0.2 | 0.3 | - | - | - | 83% | 83% Satisfactory
Kenwood Construction Enterprises | 22186 | L | B | MA | GE2 | Const. of Lateral Drainage along Urdaneta Jct.-Dagupan Rd., Km.200+727-Km.201+110, Sta. Barbara Sect. w/ exception & Km.205+82 -Km.206+161, Calasiao Sect. w/ exception | Sta. Barbara & Calasiao, Pangasinan | 2013-03-14 | Final | I | LF | 8.031 | 120 | 2012-10-03 | 2013-01-30 | 0 | C | 0.484 | 0.133 | 0.3 | - | - | - | 91.7 | 92.54% Very Satisfactory
Kenwood Construction Enterprises | 22186 | L | B | SB | GB1 | Impvt./Rehab. of DPWH-Sub DEO |  | 2009-05-31 | 1st | I |  | 2.892 | 180 |  |  |  | O | 0.357 | 0.264 | 0.15 | 0.03 | 0.045 | 0.033 | 87.9 | -
Kenwood Construction Enterprises | 22186 | L | B | MA | GE1 | Widening/Concreting of McArthur Highway (MNR) including Traffic Management |  | 2009-05-19 | 2nd | I |  | 10.06 | 138 |  |  |  | O | 0.35 | 0.201 | 0 | 0.03 | 0.05 | 0.033 | 66.4 | -
Kenwood Construction Enterprises/Oriental Sales Center & Contractor(JV) | JV-14-629 | L | B | MA | GE | Rehabilitation/Reconstruction/Upgrading Along Sta. Barbara-Mangaldan Road, K0202+600 to K0203+260, Sta. Barbara, Pangasinan | K0202+600 to K0203+260, Sta. Barbara, Pangasinan | 2015-09-04 | 1st | Pangasinan 4th DEO | LF | 15.462 | 151 | 2015-04-24 | 2015-09-22 | (+)1.18 | O | 0.354 | 0.268 | 0.15 | 0.023 | 0.047 | 0.05 | 89.2% | -
KENWOOD CONSTRUCTION ENTERPRISES/ORIENTAL SALES CENTER AND CONTRACTOR (JV) | JV-14-629 | L | B | MA | GE | Rehabilitation/Reconstruction/Upgrading along Sta. Barbara/Mangaldan Road, KO202+600 - KO203+260 | Sta. Barbara, Pangasinan | 2015-06-10 | 1st | Pangasinan 4th DEO | LF | 15.462 | 121 | 2015-04-24 | 2015-08-22 | 4.14% | O | 0.349 | 0.287 | 0.15 | 0.03 | 0.045 | 0.033 | 89.4% | -
KGD Builders | 21960 | L | B | MA | GE | Repair/Imprv't. of Flood Control and Drainage Structurein Brgy. Tinagacan | General Santos City | 2014-08-16 | Final | XII | LF | 7.6559 | 120 | 2013-06-09 | 2013-09-07 | 4.4 | C | 0.467 | 0.135 | 0.3 |  |  |  | 90.2 | 87.20% Satisfactory
KGD Builders | 21960 | L | B | SB | GE2 | Repair & Impv't. of Flood Control & Drainage Structure in Brgy. Tinagacan | General Santos City | 2013-08-22 | 1st | XII | LF | 7.656 | 120 | 2013-06-09 | 2013-10-06 | 11.84 | O | 0.376 | 0.24 | 0.15 | 0.02 | 0.033 | 0.033 | 85.2 | -
KHADEEM CONSTRUCTION | 32211 | L | D | SB | GE | Construction of Drainage Facilities Luyahan, Pasonanca, Zamboanga City | Pasonanca, Zamboanga City | 2015-09-03 | 1st & Final | Zamboanga City | LF | 1.894 | 85 | 2015-04-06 | 2015-06-29 | - | C | 0.424 | 0.2 | 0.3 | - | - | - | 92.4% | *92.4% Very Satisfactory
Khan Kon Chi Construction | 33442 | L |  | MA |  | Emergency Repair of Damaged Open Storage/Back-up Area Caused by 7.2 Magnitude Earthquake on October 15, 2013 | Port of Tagbilaran, Bohol | 2015-04-10 | 1st & Final | PPA | L | 19.7 | 194 | 2014-09-28 | 2015-03-25 | 0.06 | C | 0.452 | 0.2 | 0.3 | - | - | - | - | 95.20% Very Satisfactory
Kilusang Magkaibigan M.P. Cooperative (KMMPC) | 31666 | L | A | MA | GE1 | Rehab./Reconst./Upgrading of Sumulong Highway | Antipolo City | 2013-08-15 | 2nd | IVA | LF | 22.522 | 223 | 2013-01-29 | 2013-09-08 | -14.23 | O | 0.333 | 0.24 | 0 | 0.03 | 0.04 | 0 | 64.3 | -
Kilusang Magkaibigan M.P. Cooperative (KMMPC) | 31666 | L | A | MA | GE1 | Rehab./Reconst./Upgrading of Sumulong Highway | Antipolo City | 2013-03-22 | 1st | IVA | LF | 22.522 | 179 | 2013-01-29 | 2013-07-26 | -20.06 | O | 0.354 | 0.3 | 0 | 0.03 | 0.05 | 0.017 | 75.1 | -
Kilusang Magkaibigan Multi-Purpose Cooperative (KMMPC) | 31666 | L | A | MA | GE1 | Rd. Upgrading of Cateel-Compostela Rd. (Davao Oriental Side) Km.1559+607-Km.1561+680 (w/ exception) | Cateel, Davao Oriental | 2012-08-17 | 1st | XI | LF | 28.108 | 180 | 2012-03-15 | 2012-09-10 | -2.24 | O | 0.372 | 0.24 | 0.128 | 0.03 | 0.047 | 0.033 | 85 | -
Kim Harold Trading, Manufacturing & Construction | 28019 | L | B | SB | GE2 | Repair/Maint. of Puerto Princesa-Malvar Rd., Drainage Canal Km.02+189-Km.02+434 Malvar Rd. | Puerto Princesa City | 2013-08-15 | Final | IVB | LF | 2.766 | 150 | 2012-11-16 | 2013-04-15 | - | C | 0.48 | 0.2 | 0 | - | - | - | 68 | 67.64% Poor
Kim Harold Trading, Manufacturing & Construction | 28019 | L | B | SB | GE2 | Repair/Maint. of Puerto Princesa-Malvar Rd., Drainage Canal, Km.02+189-Km.02+434, Malvar Rd. | Puerto Princesa City, Palawan | 2013-03-16 | 1st | IVB | LF | 2.766 | 120 | 2012-11-16 | 2013-03-16 | -20.04 | O | 0.321 | 0.24 | 0 | 0.03 | 0.05 | 0.033 | 67.4 | -
Kim-Harold Trading, Manufacturing & Construction | 28019 | L | B | SB | GE | Construction of Drainage/Slope Protection Works along Puerto Princesa North Road with Road Widening Roxas - Taytay Road Section, K0174+810 - K0174+960; K0161+680 - K0161+730 (Intermittent) | Roxas, Palawan | 2014-08-06 | 1st | IV-B | LF | 11.103 | 121 | 2014-05-25 | 2014-09-22 | -0.22 | O | 0.37 | 0.229 | 0.148 | 0.022 | 0.052 | 0.017 | 83.8 | -
Kim-Harold Trading, Manufacturing & Construction | 28019 | L | B | SB | GE | Construction Drainage/Slope Protection Works along Puerto Princesa North Road with Road Widening Roxas -Taytay Road Section, K174+810-K174+960;K0161+680-K0161+730 (Intermittent) | Roxas, Palawan | 2014-11-21 | 2nd | IV | LF | 11.512 | 191 | 2014-05-25 | 2014-12-01 | 0% | C | 0.416 | 0.133 | 0.3 | - | - | - | 84.9% | 84.24% Satisfactory
KING'S BUILDERS & DEVELOPMENT CORP. | 29199 | L | B | MA | GE | Construction of Gabions Revetment, Villa Pag-asa River Control | Bansud, Oriental Mindoro | 2015-06-10 | Final | Southern Mindoro DEO | LF | 14.254 | 126 | 2015-02-20 | 2015-06-25 | 0% | C | 0.469 | 0.133 | 0.3 | - | - | - | 90.2% | *90.2% Very Satisfactory
King's Builders & Development Corporation | 29199 | L | B | MA | GE | Construction of Bucayao River Control | Calapan City, Oriental Mindoro | 2014-11-26 | 1st & Final | IV | LF | 18.1163 | 140 | 2014-02-24 | 2014-07-13 | 0% | C | 0.42 | 0.2 | 0.3 | - | - | - | 92% | 92.00% Very Satisfactory
King's Builders & Development Corporation | 29199 | L | B | MA | GE | Construction of Longos-River Control along NCR | Calapan City, Oriental Mindoro | 2014-11-28 | 1st & Final | IV | LF | 5.8633 | 79 | 2014-06-18 | 2014-09-04 | 0% | C | 0.494 | 0.133 | 0.3 | - | - | - | 92.7% | 92.70% Very Satisfactory
King's Builders & Development Corporation | 29199 | L | B | MA | GE | Construction/Rehabilitation of Villa Pag-asa River Control, Bansud, Oriental Mindoro | Bansud, Oriental Mindoro | 2014-08-12 | 1st & Final | IV-B | LF | 9.2397 | 104 | 2014-02-12 | 2014-05-26 | 5.2 | C | 0.419 | 0.133 | 0.3 |  |  |  | 85.2 | 85.20% Satisfactory
King's Builders & Development Corporation | 29199 | L | B | MA | GE | Widening (Paving of Shoulder) - Seal Widening of Calapan South Road K0008+537.50 - K0008+860 along Bayanan I E/S Section | Calapan City, Oriental Mindoro | 2014-08-11 | 1st & Final | IV-B | LF | 3.6749 | 79 | 2014-04-30 | 2014-07-17 | 0 | C | 0.405 | 0.133 | 0.3 |  |  |  | 83.8 | 83.80% Satisfactory
King's Builders & Development Corporation | 29199 | L | B | MA | GE | Repair/Rehabilitation/Improvement of Calapan South Road, Masipit Section (Left Side) Km. 5+415 - Km. 7+250 with exceptions | Calapan City, Oriental Mindoro | 2014-08-11 | 1st & Final | IV-B | LF | 9.8995 | 140 | 2014-01-09 | 2014-05-28 | 10.71 | C | 0.415 | 0.133 | 0.3 |  |  |  | 84.8 | 84.80% Satisfactory
King's Builders & Development Corporation | 29199 | L | B | SB | GE-5 | Bansud Port Development Project | Bansud, Oriental Mindoro | 2014-08-13 | 1st & Final | DOTC | LF | 3.816 | 90 | 2013-08-18 | 2014-06-11 | 0 | C | 0.4295 | 0.2 | 0.3 | - | - | - | 92.95 | 92.95% Very Satisfactory
Kirskat Venture | 32042 | L | A |  | GE2 | Maayon CIP | Maayon, Capiz | 2012-02-07 | 1st | NIA | LF | 24.335 | 463 | 2011-01-31 | 2012-04-14 | 7.79 | O | 0.351 | 0.246 | 0.15 | 0.024 | 0.051 | 0.05 | 87.2 | -
KIT'Z CONSTRUCTION AND SUPPLY | 36392 | L | D | SB | GE | Widening of National Road, Concreting of Lambunao-Inca Road | K0061+(-239) to K0061+000, Lambunao, Iloilo | 2015-06-10 | Final | Iloilo Second DEO | LF | 4.714 | 60 | 2015-04-01 | 2015-05-30 | 5.69% | C | 0.454 | 0.156 | 0.3 | - | - | - | 91% | *91% Very Satisfactory
KJC Construction & Supply | 33401 | L | B |  | GE2 | Const. of Rehabilitation of Aganan River Irrigation System (Irrigation & Flood Control) | Pavia, Iloilo | 2010-06-04 | 2nd | NIA | LF | 4.469 | 120 | 2010-06-24 | 2011-03-17 | 0.16 | O | 0.3469 | 0.3 | 0.15 | 0.02 | 0.032 | 0.05 | 89.89 | -
KJC Construction and Suppy | 6995 | L | AAA |  |  | CONSTRUCTION OF JOROG PIP | Lambunao, Iloilo | 2014-04-05 | 1st | NIA | LF | 1.809 | 662 | 2013-11-30 | 2014-04-27 | 9.59 | O | 0.367 | 0.258 | 0.15 | 0.024 | 0.047 | 0.033 | 87.9 | -
KLDS TRADING & CONSTRUCTION | 28091 | L | B | MA | GE | Concreting of Langkaan FMR, Dasmariñas City | Dasmariñas City, Cavite | 2015-06-13 | Final | Cavite 1st DEO | LF | 12.275 | 90 | 2014-11-29 | 2015-02-26 | - | C | 0.432 | 0.133 | 0.3 | - | - | - | 86.5% | *86.5% Satisfactory
KLDS TRADING & CONSTRUCTION | 28091 | L | B | MA | GE | Construction/Repair/Rehabilitation/Improvement of Various Infrastructure including Local Projects - Sectional Reblocking of Roads at Dasmariñas Bagong Bayan Resettlement Area, Sta. 0+000 to Sta. 1+100, Congressional Avenue to Area C and Sta. 3+197 to Sta. | Dasmariñas City | 2015-11-11 | Final | CAVITE 1ST DEO | LF | 27.3045 | 130 | 2015-03-26 | 2015-08-02 | 0 | C | 0.457 | 0.133 | 0.3 | - | - | - | 89% | 89% Satisfactory
KMD Builders and Construction Supply | 33791 | L | A | SB | GE | Repair/Maintenance along Cordon-Aurora Bdry. Road, K0330+000 to K0335+000 | Cabarroguis, Quirino | 2014-08-13 | 1st & Final | II | LF | 2.028 | 50 | 2014-07-14 | 2014-09-01 | 50 | C | 0.463 | 0.133 | 0.3 |  |  |  | 89.6 | 89.60% Very Satisfactory
KMD BUILDERS AND CONSTRUCTION SUPPLY | 33971 | L | A | SB | GE | Concreting of Gundaway (Rizal Road) Farm to Market Road, Barangay Gundaway, Cabarroguiz, Quirino | Cabarroguiz, Quirino | 2015-08-30 | 1st & Final | Quirino DEO | LF | 4.893 | 37 | 2015-06-10 | 2015-07-16 | 0% | C | 0.458 | 0.135 | 0.3 | - | - | - | 89.3% | *89.3% Very Satisfactory
KRB Construction | 34197 | L | D | SB | GB | Expansion, Banna (Espiritu) RHU | Banna (Espiritu), Ilocos Norte | 2014-10-22 | 1st & Final | I | LF | 2.4726 | 130 | 2014-01-02 | 2014-05-11 | 0% | C | 0.471 | 0.167 | 0.3 | - | - | - | 93.8% | 93.80% Very Satisfactory
KRB Construction | 34197 |  | D | SB |  | Vigan Airport Development Project | Vigan City, Ilocos Sur/ Region I | 2015-10-29 | 1st & Final | DOTC | LF | 6.581 | 105 | 2015-05-03 | 2015-09-16 | 0 | C | 0.4213 | 0.2 | 0.3 | - | - | - | 92.13 | *92.13% V. Satisfactory
KRB CONSTRUCTION | 34197 | L | D | SB | GE | Concreting of Barangay Road, Brgy. Madanay, Sta. Rita | Sitio Madanay Paoay, Ilocos Norte | 2015-06-04 | Final | Ilocos Norte 2nd Deo | LF | 2.848 | 42 | 2015-02-11 | 2015-03-24 | 2.38% | C | 0.466 | 0.188 | 0.3 | - | - | - | 95.4% | *95.4% Very Satisfactory
KRBS CONSTRUCTION AND TRADING | - | L | - | - | GB | Construction of Two (2) Storey Multi Purpose Building, Kabisig Elementary School | Brgy. San Andres, Cainta, Rizal | 2015-06-02 | Final | Rizal 1st DEO | LF | 2.585 | 90 | 2014-11-06 | 2015-02-03 | 1.15% | C | 0.459 | 0.077 | 0.3 | - | - | - | 83.6% | *83.6% Satisfactory
Kuatako Construction Building and General Contractor | 11224 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Paved) Abra-Cervantes Rd., K0449+415-K0456+346, Pob. Sallapadan | Abra | 2013-08-14 | 1st | CAR | LF | 41.273 | 179 | 2013-01-21 | 2013-07-19 | -17 | O | 0.329 | 0.3 | 0 | 0.03 | 0.05 | 0.033 | 74.2 | -
Kumi Construction | 94969 | L | D | SB | GE | Improvement/Riprapping along Duyan-Duyan Creek (Mirriam College of Lagarian Creek) | Quezon City | 2014-08-15 | 1st & Final | NCR | LF | 4.6524 | 90 | 2013-01-21 | 2013-04-20 | 0 | C | 0.478 | 0.133 | 0.3 |  |  |  | 91.1 | 91.10% Very Satisfactory
Kumi Construction | 34969 | L | D | SB | GE2 | Impvt./Riprapping along Duyan-Duyan Creek (Mirriam College-Lagarian Creek) | Quezon City | 2013-08-09 | Final | NCR | LF | 4.652 | 90 | 2013-01-21 | 2013-04-20 | 0 | C | 0.457 | 0.2 | 0.3 | - | - | - | 95.7 | 83.64% Satisfactory
Kumi Construction | 34969 | L | D | SB | GE2 | Impv't./Riprapping along Duyan-Duyan Creek (Mirriam College-Lagarian Creek) | Quezon City | 2013-03-19 | 1st | NCR | LF | 4.652 | 90 | 2013-01-21 | 2013-04-20 | 7.23 | O | 0.24 | 0.3 | 0.15 | 0.023 | 0.018 | 0.025 | 75.6 | -
Kuntel Construction | 10234 | L | A | MA | GE | Rehab./Reconst./Upgrading of Damaged National Roads (Intermittent Sections) Bacolod South Road (kabankalan - Hinoba-an Section) A: Ko166+944 - KO167+932 & B: KO169+000 - KO0170+012 Brgy. Maricalum | Sipalay City, NegrosOccidental | 2014-08-09 | Final | VI | LF | 36.6306 | 253 | 2013-03-22 | 2013-09-16 | 0 | C | 0.425 | 0.2 | 0.3 |  |  |  | 92.5 | 85.42% Satisfactory
Kuntel Construction | 10234 | L | A | MA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rds. (Int. Sect.), Bacolod South Rd. (Kabankalan-Hinoba-an Sect.) A.K0166+944-K0167+932 & B.K0169+000-K0170+012, Brgy. Maricalum | Sipalay City, Negros Occidental | 2013-08-09 | 1st | VI | LF | 35.32 | 179 | 2013-03-22 | 2013-09-16 | -3.25 | O | 0.346 | 0.24 | 0.118 | 0.03 | 0.04 | 0.033 | 80.7 | -
KV Construction and Supply | 17509 | L | A | MA | GE1 | Const./Widening/Upgrading/Rehab. of Access Rds. to Major Airport, Daet-Airport Rd. | Daet, Camarines Norte | 2013-03-23 | 1st | V | LF | 46.06 | 180 | 2013-01-10 | 2013-07-08 | 32.64 | O | 0.292 | 0.29 | 0.15 | 0.024 | 0.035 | 0.033 | 82.4 | -
KV Construction and Supply | 17509 | L | A | MA | GE | Widening of Access Road Leading Daet-Airport Road Camarines Norte 2nd Legislative District | Daet, Camarines Sur | 2014-08-05 | 1st | V | LF | 46.3567 | 210 | 2014-03-13 | 2014-10-08 | 2.46 | O | 0.31 | 0.294 | 0.15 | 0.02 | 0.033 | 0.05 | 85.7 | -
KVC Construction | 28959 | L | B | MA | GE | Rehab./Reconst./Upgrading of Damaged Paved National Roads including Draiange based on Pavement Management System/ Highway Development and Management-4 (HDM-4) (Intermittent Sections) on National Secondary and National Arterial Roads (Package XVII-2013) | Kapangan and Atok, Benguet | 2014-11-20 | 1st | CAR | LF | 11.6101 | 222 | 2014-02-25 | 2014-10-04 | -18.37% | O | 0.377 | 0.243 | 0 | 0.03 | 0.05 | 0.05 | 75% | 75.00% Poor
KVC Construction | 28959 | L | B | MA | GE | Road Upgrading of Dantay - Sagada Road, KO390+520 - KO390+840 | Mt. Province | 2014-11-22 | 1st | CAR | LF | 7.7373 | 168 | 2014-05-26 | 2014-11-09 | -14% | O | 0.369 | 0.24 | 0.01 | 0.03 | 0.05 | 0.033 | 73.2% | 73.20% Poor
KVC Construction | 28959 | L | B | MA | GE1 | Rehab. of Moatong Bridge, K0301+743 | Bokod, Benguet | 2013-07-30 | Final | CAR | LF | 7.866 | 150 | 2013-02-09 | 2013-07-08 | 0 | C | 0.467 | 0.133 | 0 | - | - | - | 60 | 74.64% Poor
KVC Construction | 28959 | L | B | MA | GE1 | Road Upgrading/Rehab./Reconst. (Asphalt to Concrete) Acop-Kapangan-Kibuagan-Bakun Road, K0269+390-K0271+000 v.s. | Tublay, Benguet | 2011-08-16 | 1st | CAR | LF | 15.1 | 98 | 2011-07-25 | 2011-10-30 | -9.43 | O | 0.4 | 0.241 | 0.056 | 0.03 | 0.037 | 0.017 | 78.1 | -
KVC CONSTRUCTION | 28959 | L | A | MB | GE | Road Upgrading of Dantay-Sagada Road, K0390+520 - K0390+840 | Sagada, Mt. Province | 2015-06-05 | Final | Mountain Province DEO | LF | 7.737 | 168 | 2014-05-26 | 2014-11-09 | (-) 14.00% | C | 0.404 | 0.2 | 0 | - | - | - | 60.4% | *68.08% Poor
KVC Construction | 28959 | L | B | MA | GE1 | Rehab. of Moatong Bridge, K0301+743 | Bokod, Benguet | 2013-03-13 | 1st | CAR | LF | 7.866 | 120 | 2013-02-09 | 2013-06-08 | 4.54 | O | 0.291 | 0.3 | 0.15 | 0.023 | 0.047 | 0.033 | 84.4 | -
KVC Construction/3K Rock Engineering (JV) | JV-13-342 | L | A | MB | GE | Road Upgrading (Gravel to Concrete) of Asin - Nangalisan San Pascual Road, K0270+594-K0272+220 (i.s.) and K0275+5311-K0275+7178 (i.s.) | Tuba, Benguet | 2014-11-28 | 1st | CAR | LF | 97.5 | 274 | 2014-03-28 | 2014-12-26 | -1.09% | O | 0.37 | 0.238 | 0.139 | 0.03 | 0.055 | 0.05 | 88.2% | 88.20% Satisfactory
KVC CONSTRUCTION/3K ROCK ENGINEERING (JV) | JV-13-342 | L | A | MB | GE | Road Upgrading (Gravel to Concrete) of Asin-Nangalisan-San Pascual Road, K0270+594 - K0272+220 (Intermittent Sections) and K0275+53311 - K0275+7178(Intermittent Sections) | Tuba, Benguet | 2015-06-02 | Final | CAR | LF | 97.5 | 274 | 2014-03-28 | 2014-12-26 | 0% | C | 0.396 | 0.2 | 0.3 | - | - | - | 89.6% | *88.76% Satisfactory
KVCC Construction | 27179 |  |  |  |  | Const./Rehab./Impvt. of DPWH Biliran DEO |  | 2010-08-26 |  | VIII |  | 2.882 | 120 |  |  |  | O | 0.361 | 0.24 | 0.15 | 0.03 | 0.042 | 0.033 | 85.6 | -
Kyro Builders | 19567 | L | AAA |  |  | NIA- Participatory Irrigation Development Project | Mallig River Irrigation System, Mallig, Isabela, Region 2 | 2015-09-30 | 1st | NIA | LF | 70.128 | 800 | 2013-03-14 | 2016-01-16 | -14.96 | O | 0.359 | 0.3 | 0.004 | 0.024 | 0.06 | 0.05 | 79.7 | -
Kyro Builders |  | L | AAA | LA | GE-2 | UMAYAM RIVER IRRIGATION PROJECT | LA PAZ-LORETO, AGUSAN DEL SUR, REGION XIII | 2015-09-12 | 1st | NIA | LF | 173.037 | 848 | 2014-03-20 | 2016-07-14 | -2.47 | O | 0.2896 | 0.24 | 0.1402 | 0.015 | 0.06 | 0.05 | 79.48 | -
Kyro Builders |  |  | AAA |  |  | Package X-B: Construction of Sub-laterals "N-5D" (Sta. 7+800 - Sta. 12+855), "N-5C" (Sta. 0+000-5+765), and "N-5D" (Sta. 0+000-2+815) including related structures and supply, delivery and installation of steel gates | Guimba, Nueva Ecija | 2015-02-07 | 1st | NIA | L | 102.818 | 180 | 2014-09-24 | 2015-03-22 | 5.3 | O | 0.3164 | 0.2825 | 0.15 | 0.03 | 0.0233 | 0.05 | 85.22 | -
Kyro Builders | 19567 |  |  |  |  | Rehab./Reconst./Upgrading of Damaged Paved National road, Pias-Currimao-Balacad Road, Currimao-Paoay |  | 2010-08-20 |  | I |  | 18.977 | 180 |  |  |  | O | 0.374 | 0.24 | 0.15 | 0.03 | 0.048 | 0.033 | 87.5 | -
Kyro Builders | 19567 | L | AAA | MB | GE1 | Conc. of Talugtug-Muñoz Rd. Sta.2+061 to Sta.4+982.20 | Nueva Ecija | 2012-03-19 | Final | III | LF | 16.965 | 120 | 2011-06-09 | 2011-10-06 | 11.67 | C | 0.443 | 0.133 | 0.3 | - | - | - | 87.6 | 90.48% Very Satisfactory
Kyro Builders | 19567 | L | AAA | MB | GE1 | Impvt./Widening of Bacolod-Murcia-Don Salvador-Benedicto San Carlos Rd., Don Salvador Benedicto-San Carlos City Sect. Sta.37+025-Sta.37+540; Sta.45+000-Sta.48+060 w/ exception, Sta.83+916.60-Sta.85+796.60 | DS Benedicto/San Carlos City, Negros Occidental | 2012-11-27 | Final | VI | LF | 76.871 | 417 | 2011-08-01 | 2012-10-23 | 0 | C | 0.423 | 0.133 | 0.247 | - | - | - | 80.3 | 84.86% Satisfactory
Kyro Builders / Rachel Faye Const. (JV) | JV-10-039 | L | AAA | LA | GE2 | Rehab. Of Various Slope Protection along Baguio Bontoc Rd., (Halsema Highway) Km.265+000-Km.315+000 (I.S.) | Benguet | 2011-08-16 | 1st | CAR | LF | 28.948 | 240 | 2010-12-23 | 2011-08-19 | -2.85 | O | 0.31 | 0.3 | 0.122 | 0.03 | 0.047 | 0.033 | 84.2 | -
Kyro Builders, Inc. | 19567 | L | AAA |  |  | Jalaur River Multi-Purpose Project-II | Calinog, Passi City, Iloilo | 2015-11-13 | 1st | NIA | LF | 230.587 | 270 | 2015-03-17 | 2015-12-18 | -72.7 | O | 0.3948 | 0.2883 | 0 | 0.018 | 0.056 | 0.0333 | 79.04 | -
KYRO BUILDERS, INC. | 19567 | L | AAA | MB | GE | Construction/Improvement of Ibulao - Julongan Road Leading to Julongan Rice Terraces, Villages, Museum WWI Shrine (DSTD), Kiangan, Ifugao | Kiangan, Ifugao | 2015-08-31 | 1st & Final | CAR | LF | 135.584 | 403 | 2014-04-28 | 2015-06-04 | 0% | C | 0.458 | 0.133 | 0.3 | - | - | - | 89.1% | *89.1% Very Satisfactory
KYRO Builders, Inc. | 19567 |  | AAA |  |  | Jalaur River Multi-purpose Project-II | Calinog, Passi City, Iloilo | 2016-10-07 | 2nd | NIA | LF | 230.587 | 567 | 2016-03-17 | 2016-09-23 | -46.86 | O | 0.3972 | 0.2399 | 0 | 0.018 | 0.042 | 0.0167 | 71.38 | -
L M D Construction | 9410 | L | B | SB | GB1 | Construction of Multi-Purpose Building at Dumalinao Pilot School |  | 2009-06-20 | 1st | IX |  | 4.595 | 180 |  |  |  | O | 0.38 | 0.24 | 0.15 | 0.02 | 0.042 | 0.05 | 88.2 | -
L. A. CLAMOR CONSTRUCTION | 26413 | L | B | MA | GE | Widening of National Roads, Arterial Roads along National Road I (NI) Daang Maharlika/Asian Highway-26 MSR Diversion Road, K0 126+811 - K0 127+588, K0 130+903 - K0 131+536 | Lucena City | 2015-09-02 | 1st | Quezon 2nd | LF | 43.698 | 270 | 2015-01-28 | 2015-10-24 | 9.23% | O | 0.323 | 0.24 | 0.15 | 0.03 | 0.06 | 0.05 | 85.3% | -
L. A. CLAMOR CONSTRUCTION | 26413 | L | B | MA | GE | Widening of National Roads, Secondary Roads, MSR Old Route, K0132+076.30 - K0133+610, K0133+699 - K0234+156.30, Lucena City | Lucena City | 2015-11-16 | 1st | QUEZON 2ND DEO | LF | 45.8 | 330 | 2015-02-05 | 2015-12-31 | 0.0363 | OG | 0.344 | 0.187 | 0.15 | 0.03 | 0.06 | 0.05 | 82.1% | 82.1% Satisfactory
L. A. CLAMOR CONSTRUCTION | 26413 | L | B | MA | GE | Widening of National Roads, Arterial Roads along National Road I (NI) Daang Maharlika/Asian Highway-26, Daang Maharlika (LZ), K0120+705 - K0121+101, Sariaya Quezon | Sariaya Quezon | 2015-11-16 | Final | QUEZON 2ND DEO | LF | 17.9946 | 180 | 2015-01-28 | 2015-07-26 | 0.0056 | C | 0.471 | 0.133 | 0.3 | - | - | - | 90.4% | 90.4% Very Satisfactory
L. C. Ting Construction | 23666 |  |  |  |  | Rehab. of Gamut Steel Bridge along Surigao-Davao Coastal Road (Alternate Road) |  | 2010-06-09 |  | XIII |  | 9.617 | 60 |  |  |  | O | 0.352 | 0.3 | 0.109 | 0.03 | 0.04 | 0.033 | 86.4 | -
L. C. Ting Construction | 23666 |  |  |  |  | Rehab. of Paypay Twin Bridge |  | 2010-06-01 |  | XIII |  | 19.266 | 270 |  |  |  | O | 0.4 | 0.18 | 0.15 | 0.03 | 0.045 | 0.033 | 83.8 | -
L. C. Ting Construction | 23666 |  |  |  |  | Rehab./Reconst. of Damaged Paved National Road (Asphalt Overlay) Daang Maharlika Road (Surigao-Agusan Road) |  | 2010-06-07 |  | XIII |  | 14.077 | 90 |  |  |  | O | 0.355 | 0.24 | 0.15 | 0.023 | 0.035 | 0.033 | 83.6 | -
L. C. Ting Construction | 23666 | L | AAA | MA | GE | Construction of Flood Control Structure/Drainage along SDCR, Surigao del Sur 2nd LD, Wakat-Tagbina, Barobo, K1411+520 - K1412+000 | Barobo, Surigao del Sur | 2014-08-09 | 1st | XIII | LF | 11.1288 | 158 | 2014-02-11 | 2014-07-18 | -3.07 | O | 0.32 | 0.225 | 0.119 | 0.023 | 0.042 | 0.05 | 77.9 | -
L. C. Ting Construction | 23666 | L | AAA | MA | GE | Road Slip Protection along Surigao-Davao Coastal Road, Lingig, Brgy. Mahayhay, Lingig, Surigao del Sur 2nd LD, K1477+553.10 - K1477+606.10 | Lingig, Surigao del Sur | 2014-08-10 | Final | XIII | LF | 19.8261 | 190 | 2014-02-25 | 2014-09-02 | 2.67 | C | 0.39 | 0.124 | 0.3 |  |  |  | 81.4 | 85.18% Satisfactory
L. C. Ting Construction | 23666 | L | AAA | MA | GE | Rehabilitation/Retrofitting of Existing Permanent Bridges, Bihawan Bridge along SDCR, Surigao del Sur 1st LD | San Agustin, Surigao del Sur | 2014-08-11 | 1st | XIII | LF | 14.4558 | 185 | 2014-02-17 | 2014-08-20 | 0.69 | O | 0.334 | 0.2 | 0.15 | 0.03 | 0.037 | 0.05 | 80.1 | -
L. C. Ting Construction | 23666 | L | AAA | MA | GE | Rehab./Reconst./Upgrading of Damaged Paved Road along NRJ San Francisco - Bahi - Barobo Rd., Km. 1313+445 - Km. 1351+600 | San Francisco, Agusan del Sur | 2014-08-08 | 1st | XIII | LF | 23.3055 | 171 | 2014-02-06 | 2014-07-26 | -19.16 | O | 0.328 | 0.23 | 0 | 0.023 | 0.037 | 0.033 | 65.1 | -
L. C. Ting Construction | 23666 | L | AAA | MA | GE | Rehabilitation/Retrofitting of Lucena Bridge along NRJ - Bahbah - Talacogon Road | Prosperidad, Agusan del Sur | 2014-08-06 | 1st | XIII | LF | 15.3213 | 217 | 2014-02-11 | 2014-09-15 | -12.23 | O | 0.398 | 0.195 | 0.028 | 0.023 | 0.03 | 0.017 | 69.1 | -
L. N. R. Construction | 14148 | L | B | MA |  | Construction/Rehabilitation of Sabang Fishport | Sabang, Calabanga, Camarines Sur/ Region V | 2015-02-05 | 2nd | DOTC | L | 39.37 | 300 | 2014-03-26 | 2015-07-03 | 19.26 | O | 0.3437 | 0.3 | 0.15 | 0.03 | 0.05 | 0.0318 | 90.55 | -
L. N. R. Construction | 14148 | L |  |  |  | Repair of Port Facilities for Damages caused by the Typhoon Yolanda | Port of Tacloban, Tacloban City, Leyte | 2015-02-04 | 2nd & Final | PPA | L | 25.658 | 240 | 2014-05-14 | 2015-01-09 | 0 | C | 0.4973 | 0.2 | 0.3 | - | - | - | - | 98.86% Outstanding
L. N. R. Construction | 14148 | L |  |  |  | Repair of Port Facilities for damages caused by typhoon Yolanda | Tacloban, Leyte | 2014-08-22 | 1st | PPA | LF | 23.339 | 180 | 2014-05-14 | 2014-11-14 | 16.094 | O | 0.3966 | 0.3 | 0.15 | 0.03 | 0.0583 | 0.05 | 98.49 | -
L. N. R. Construction | 14148 | L | B | MA | GE-5 | New Construction of Vinsons Port | Calaguas Island, Camarines Norte | 2014-10-16 | 2nd & Final | DOTC | LF | 40.978 | 240 | 2014-04-02 | 2014-11-27 | 21.07 | C | 0.4791 | 0.2 | 0.3 | - | - | - | - | 93.92% Very Satisfactory
L. N. R. Construction | 14148 | L | B | MA |  | New Construction of Vinzons Port | Calaguas Island, Camarines Norte | 2014-06-25 | 1st | DOTC | LF | 40.978 | 240 | 2014-04-02 | 2014-11-27 | 21.88 | O | 0.3563 | 0.3 | 0.15 | 0.03 | 0.0431 | 0.0333 | 91.27 | -
L. N. R. Construction | 14148 | L | B | MA | GE-5 | Pilar Port Development Project | Pilar, Sorsogon | 2014-07-24 | 2nd & Final | DOTC | LF | 12.182 | 120 | 2013-11-12 | 2014-07-05 | 0 | C | 0.461 | 0.2 | 0.3 | - | - | - | 96.1 | 96.50% Outstanding
L. N. R. Construction | 14148 | L | B | MA | GE-5 | Sabang Port Development Project | Sabang, Calabanga, Camarines Sur | 2014-09-05 | 1st | DOTC | LF | 39.37 | 300 | 2014-03-26 | 2015-01-19 | 12.84 | O | 0.372 | 0.3 | 0.15 | 0.015 | 0.05 | 0.05 | 93.7 | -
L. N. R. Construction | 14148 | L | B | MA | GE5 | Corcuera Port Development Harbor | Corcuera, Romblon | 2014-02-26 | 1st & Final | DOTC | LF | 24.05 | 180 | 2013-01-31 | 2013-07-29 | 0 | C | 0.451 | 0.2 | 0.3 | - | - | - | 95.1 | 95.10% Very Satisfactory
L. N. R. Construction | 14148 | L | B | MA | GE5 | Kaputian Multi-Purpose Port Development Project | Kaputian, Island Garden of Samal, Davao del Norte | 2014-03-26 | Final | DOTC | LF | 2.943 | 90 | 2013-11-01 | 2014-01-28 | 0 | C | 0.437 | 0.2 | 0.3 | - | - | - | 93.7 | 93.70% Very Satisfactory
L. N. R. Construction | 14148 |  |  | MA |  | Dimasalang Port Development Project | Dimasalang, Masbate | 2016-01-26 | 1st | DOTC | LF | 29.03 | 240 | 2015-07-16 | 2016-03-11 | 15.29 | O | 0.376 | 0.3 | 0.15 | 0.03 | 0.06 | 0.05 | 96.6 | -
L. N. R. Construction | 14148 |  | B | MA |  | Construction of Can-avid Riverlanding | Brgy. Poblacion, Can-avid, Eastern Samar/ Region VIII | 2016-02-24 | 1st & Final | DOTC | LF | 9.552 | 150 | 2015-09-09 | 2016-02-05 | 6.67 | C | 0.4803 | 0.2 | 0.3 | - | - | - | 98.03 | *98.03% Outstanding
L. N. R. Construction | 14148 | L | B | MA |  | Dimasalang Port Development Project | Dimasalang, Masbate/ Region V | 2016-04-27 | 2nd & Final | DOTC | LF | 29.03 | 240 | 2015-07-16 | 2016-03-11 | 3.03 | C | 0.4885 | 0.2 | 0.3 | - | - | - | 98.85 | 97.50% Outstanding
L. R. TIQUI BUILDERS, INC. | 13810 | L | AAA | LB | GE | Rehabilitation/Improvement of Brgy. Roads, Dulong Bayan, Lone District, Bulacan, San Jose del Monte City, Bulacan | San Jose del Monte City, Bulacan | 2015-08-30 | 1st & Final | Bulacan Second DEO | LF | 27.9 | 180 | 2015-02-18 | 2015-08-17 | - | C | 0.42 | 0.2 | 0.3 | - | - | - | 92% | *92% Very Satisfactory
L. R. TIQUI BUILDERS, INC. | 13810 | L | AAA | LB | GE | Network Development - Construction of By-Passess/ Diversion Roads, Construction of Jct. Batasan - San Mateo - Rodriguez By-Pass, San Mateo, Rizal Province | San Mateo, Rizal Province | 2015-11-10 | 1st | REGIONAL OFFICE | LF | 85.3461 | 525 | 2014-08-28 | 2016-02-03 | -0.1047 | OG | 0.327 | 0.3 | 0.045 | 0.03 | 0.07 | 0.033 | 80.5% | 80.5% Unsatisfactory
L. T. DE GUZMAN CONSTRUCTION | 20964 | L | D | SB | GE | Off Carriageway Improvement, Gapan-San Fernando-Olongapo Road, K0096+825 to K0097+000, Cabiao, Nueva Ecija | K0096+825 to K0097+000, Cabiao, Nueva Ecija | 2015-09-01 | 1st & Final | Nueva Ecija Second DEO | LF | 1.482 | 30 | 2015-03-08 | 2015-04-06 | - | C | 0.377 | 0.2 | 0.3 | - | - | - | 87.7% | *87.7% Satisfactory
L.A Digao Construction | 15371 |  |  |  |  | Const./Impvt./Renovation of Public Market |  | 2010-08-29 |  | XIII |  | 3.775 | 120 |  |  |  | O | 0.356 | 0.24 | 0.15 | 0.03 | 0.035 | 0.033 | 84.4 | -
L.A. Arizola Construction & Supply | 31060 | L | B | SB | GE1 | Conc. of Kidapawan Magnet-Pangaon-an Road inc. Marbel Bridge and Approaches |  | 2009-03-09 | 1st | XII |  | 9.485 | 90 |  |  |  | O | 0.328 | 0.24 | 0.15 | 0.03 | 0.035 | 0.033 | #VALUE! | -
L.A. CLAMOR CONSTRUCTION | 26413 | L | B | MA | GE | Slope Protection Works at Brgy. Barra | Lucena City, Quezon | 2015-06-09 | Final | Quezon 2nd DEO | LF | 8.949 | 110 | 2015-01-23 | 2015-05-12 | 5.45% | C | 0.403 | 0.15 | 0.3 | - | - | - | 85.3% | *85.3% Satisfactory
L.A. Clamor Construction | 26413 | L | B |  | GE2 | Construction of Diversion Works & Canal Structures of Ilosong CIP | Plaridel, Quezon/Region IV-A | 2013-09-07 | 1st | NIA | L | 6.621 | 150 | 2013-03-05 | 2013-08-02 | 0 | O | 0.3429 | 0.2488 | 0.15 | 0.018 | 0.04 | 0.05 | 84.97 | -
L.A. Profugo Construction & Supply | 33609 | L | - | - | - | Construction and Maintenance of Bridges along National Roads-Major Repair/Maintenance of Existing Permanent Bridges, Arterial Road Quezon (First District) 1. Amao Br. Along Daang Maharlika (LZ) | Pagbilao, Quezon | 2014-11-26 | 1st & Final | IV | LF | 1.8518 | 30 | 2014-09-30 | 2014-10-29 | - | C | 0.464 | 0.133 | 0.3 | - | - | - | 89.7% | 89.70% Very Satisfactory
L.B. Leoncio Trading & Construction | 31587 | L | B | MA | GE | CP-02-14 Road Upgrading ( Gravel to Paved) of Irawan-Tagburos Road | K0012+1046-K0013-485 and K0016+754.80-K0016+801 Irawan- Tagburos Road, Puerto Princesa City | 2014-11-24 | 1st & Final | IV | LF | 12.1704 | 139 | 2014-04-04 | 2014-08-20 | 0.9% | C | 0.416 | 0.133 | 0.3 | - | - | - | 84.9% | 77.82% Unsatisfactory
L.B. Leoncio Trading & Construction | 31587 | L | B | MA | GE | Road Upgrading (Gravel to Paved) of Irawan - Tagburos Road, K0012+1046 - K0013+485 and K0016+754.80 - K0016+801 | Puerto Princesa City | 2014-08-08 | 1st | IV-B | LF | 11.244 | 109 | 2014-04-04 | 2014-07-21 | -10.4 | O | 0.373 | 0.219 | 0.046 | 0.03 | 0.03 | 0.033 | 73.1 | -
L.B. Leoncio Trading & Construction | 31587 | L | B | SB | GB | Construction of 2 Storey 6 CL, San Jose National High School | Puerto Princesa City | 2014-08-08 | Final | IV-B | LF | 6.3667 | 260 | 2013-04-02 | 2013-12-17 | 24.04 | C | 0.47 | 0.133 | 0.3 |  |  |  | 90.3 | 87.43% Satisfactory
L.B. Leoncio Trading & Construction | 31587 | L | B | SB | GB1 | Const. of 2 Storey 6 CL San Jose NHS | Puerto Princesa City | 2013-08-16 | 1st | IVB | LF | 6.286 | 260 | 2013-04-02 | 2013-12-18 | 34.2 | O | 0.381 | 0.228 | 0.15 | 0.02 | 0.033 | 0.05 | 86.2 | -
L.B. LEONCIO TRADING & CONSTRUCTION | 31587 | L | B | MA | GE | Repair/Improvement of Capitol-Canigaran Road Drainage Channel, K000+000 to K000+465, Right Side, Capitol- Canigaran Road | Puerto Princesa City | 2015-06-02 | Final | Palawan 3rd DEO | LF | 4.499 | 134 | 2015-01-08 | 2015-05-22 | 0% | C | 0.494 | 0.133 | 0.3 | - | - | - | 92.7% | *92.7% Very Satisfactory
L.B. LEONCIO TRADING & CONSTRUCTION | 31587 | L | B | MA | GE | Repair/Improvement of Capitol-Canigaran Road Drainage Channel, K0000+000 - K0000+465, Right Side, Capitol-Canigaran Road, Puerto Princesa City | Puerto Princesa City | 2015-08-29 | 1st & Final | Palawan III DEO | LF | 4.499 | 134 | 2015-01-08 | 2015-05-21 | 4.53% | C | 0.451 | 0.133 | 0.3 | - | - | - | 88.4% | *88.4% Satisfactory
L.C Construction | 7024 | L | C | MA | GE1 | Improvement of Access Road, Pagadian City Airport (Lumbia Sect.) |  | 2009-06-05 | 1st | IX |  | 15.346 | 195 |  |  |  | O | 0.375 | 0.238 | 0.15 | 0.02 | 0.042 | 0.05 | 87.5 | -
L.C Construction | 7024 | L | B | MA | GE1 | Rehab. of Cagayan de Oro Port Road |  | 2009-03-03 | 1st | X |  | 0.49 | 14.011 |  |  |  | O | 0.275 | 0.24 | 0.042 | 0.02 | 0.027 | 0.05 | #VALUE! | -
L.C Ting Construction | 23666 | L | AAA | MA | GE1 | Conc. of Butuan City-Pianing-Tandag Rd. |  | 2009-09-14 | 2nd | XIII |  | 19.195 | 255 |  |  |  | O | 0.282 | 0.281 | 0.15 | 0.03 | 0.06 | 0.033 | 83.6 | -
L.C Ting Construction / Davao L.A. Parts & Hardware Corporation Joint Venture | JV-07-102 | L | AAA | MB | GE1 | Impvt./Conc. of Surigao Sur-Davao Oriental Coastal Road (Manay-Boston) Manay Section |  | 2008-11-25 | 1st | XI |  | 47.225 | 166 |  |  |  | O | 0.272 | 0.298 | 0.1 | 0.03 | 0.055 | 0.067 | 82.2 | -
L.C. CONSTRUCTION | 7024 | L | B | MA | GE | Construction of Farm to Market Road at Barangay Poblacion to Kigay, Malangas, Zamboanga Sibugay | Malangas, Zamboanga Sibugay | 2015-06-08 | Final | Zamboanga Sibugay 1st DEO | LF | 1.974 | 40 | 2015-02-23 | 2015-04-03 | 0% | C | 0.476 | 0.095 | 0.3 | - | - | - | 87.1% | *87.1% Satisfactory
L.C. Construction | 7024 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Concrete) Jct. Tubod-Lakewood Rd., K1710+2000-K1710+3000 realigned to Rd. Upgrading to Paved Rd. Standard, Jct. Tubod-Lakewood Rd., K1710+990-K1711+735 | Lakewood, Zamboanga del Sur | 2012-11-21 | 2nd | IX | LF | 21.923 | 182 | 2012-02-22 | 2012-08-21 | - | O | 0.364 | 0.225 | 0 | 0.03 | 0.043 | 0.033 | 69.5 | -
L.C. Construction | 7024 | L | B | MA | GE1 | Road Upgrading (Gravel to Concrete), Jct. Tubod-Lakewwod Rd., K1710+2000-K1710+3000 Re-aligned to Rd. Upgrading to Paved Rd., Jct. Tubod-Lakewood Rd., K1710+990-K1711+735 | Lakewood, Zamboanga del Sur | 2012-08-16 | 1st | IX | LF | 21.923 | 182 | 2012-02-22 | 2012-08-22 | -2.75 | O | 0.392 | 0.24 | 0.122 | 0.03 | 0.038 | 0.033 | 85.5 | -
L.C. CONSTRUCTION | 7024 | L | B | MA | GB | Construction of Multi-Purpose Building at Brgy. Poblacion, Diplahan, Zamboanga Sibugay | Diplahan, Zamboanga Sibugay | 2015-11-11 | Final | Zamboanga Sibugay 1st DEO | LF | 1.4845 | 45 | 2015-02-23 | 2015-04-08 | - | C | 0.456 | 0.133 | 0.3 | - | - | - | 88.9% | 88.9% Satisfactory
L.C. CONSTRUCTION | 7024 | L | B | MA | GE | Construction of Farm to Market Road at Brgy. Poblacion to Kigay, Malangas, Zamboanga Sibugay | Malangas, Zamboanga Sibugay | 2015-11-11 | Final | Zamboanga Sibugay 1st DEO | LF | 1.9745 | 40 | 2015-02-23 | 2015-04-03 | - | C | 0.431 | 0.133 | 0.3 | - | - | - | 86.4% | 86.4% Satisfactory
L.C. CONSTRUCTION | 7024 | L | B | MA | GB | Construction of Multi-Purpose Building, Barangay Malaubang, Ozamis City, Misamis Occidental | Barangay Malaubang, Ozamis City, Misamis Occidental | 2015-11-19 | Final | Misamis Occidental 2nd | LF | 2.6185 | 90 | 2015-05-05 | 2015-08-03 | 0.00% | C | 0.463 | 0.133 | 0.3 | - | - | - | 89.6% | 89.6% Very Satisfactory
L.C. Ting Construction | 23666 | L | AAA | MA | GE | RehabilItation/Reconstruction of Road Slip along Butuan-Cagayan de Oro-Iligan Road (Agusan-Misamis Oriental), K1266+000 - K1266+044, K1266+110 - K1266+125) | Nasipit, Agusan del Norte | 2014-10-21 | 1st & Final | XIII | LF | 13.5971 | 194 | 2014-02-04 | 2014-08-16 | 0% | C | 0.356 | 0.197 | 0.3 | - | - | - | 85.3% | 85.30% Satisfactory
L.C. Ting Construction | 23666 | L | AAA | MA | GE | Replacement of Sabangahan Bridge along Misamis, Oriental - Bukidnon - Agusan Road | Malitbog, Bukdnon | 2014-08-09 | 1st | X | LF | 12.9695 | 214 | 2014-01-28 | 2014-08-29 | 12.48 | O | 0.397 | 0.3 | 0.025 | 0.023 | 0.041 | 0 | 78.6 | -
L.C. Ting Construction | 23666 | L | AAA | MA | GE1 | Road Slip/Protection along Surigao-Davao Coastal Rd., Mahayahay, K1477+533.10-K1477+606.10 | Lingig, Surigao del Sur | 2013-08-16 | 1st | XIII | LF | 19.826 | 190 | 2013-02-25 | 2013-09-02 | 2.46 | O | 0.372 | 0.24 | 0.15 | 0.03 | 0.035 | 0.05 | 87.7 | -
L.C. Ting Construction | 23666 | L | AAA | MA | GE1 | Replacement of Bridge along Nat'l Rds. Catugpas III along Surigao-Davao Coastal Rd. | Lanuza, Surigao del Sur | 2013-03-16 | 1st | XIII | LF | 11.186 | 139 | 2013-02-14 | 2013-07-02 | 19.82 | O | 0.383 | 0.232 | 0.15 | 0.03 | 0.025 | 0.033 | 85.3 | -
L.C. Ting Construction | 23666 | L | AAA | MA | GE1 | Reconst. of Critical Sect. along Nat'l Rds. Payasan-Los Arcos Rd. (Rd. Slip) Km.1389+820-Km.1389+920 | Lianga, Surigao del Sur | 2013-03-21 | Final | XIII | LF | 14.312 | 180 | 2012-05-24 | 2012-11-19 | -6.67 | C | 0.471 | 0.133 | 0.1 | - | - | - | 70.4 | 78.56% Unsatisfactory
L.C. Ting Construction/Road Edge Trading & Development Services (J.V.) | SL1-SN-008082 | L | B | MB | GE | Construction of Revetment along Butuan City-Cagayan de Oro City-Iligan City Road | Napaliran Revetment, Balingasag, Misamis Oriental | 2014-08-11 | 1st | X | LF | 34.7594 | 239 | 2014-01-20 | 2014-09-15 | 7.12 | O | 0.384 | 0.263 | 0.15 | 0.03 | 0.035 | 0.033 | 89.5 | -
L.C. TING CONSTRUCTION/ROAD EDGE TRADING & DEVELOPMENT SERVICES JOINT VENTURE | JV-13-228 | L | B | MA | GE | Const. of Mangalay Bridge Including Approaches along CDO-Airport Bukidnon Road, Lumbia-Uguiaban By-Pass Road, Cagayan de Oro City | CDO-Airport Bukidnon Road, Cagayan de Oro City | 2015-06-11 | Final | Cagayan de Oro City First DEO | LF | 16.728 | 220 | 2014-02-04 | 2014-09-11 | - | C | 0.348 | 0.2 | 0.3 | - | - | - | 84.8% | *83.16% Satisfactory
L.G. Lasacar Construction | 11960 | L | A | SB | GE2 | Const./Rehab. of Protection Works / Seawall, Looc Catarman |  | 2009-09-05 | 1st | X |  | 9.358 | 270 |  |  |  | O | 0.318 | 0.226 | 0.15 | 0.02 | 0.047 | 0.033 | 79.4 | -
L.G. Lasacar Construction | 11960 | L | A | MA | GE1 | Const./Impvt. of Mambajao-Catarman-Cross County Road (Phase 4) Mambajao-Catarman Section |  | 2009-09-05 | 2nd | X |  | 9.483 | 225 |  |  |  | O | 0.296 | 0.236 | 0 | 0.03 | 0.037 | 0.017 | 61.6 | -
L.G. Lasacar Construction | 11960 | L | A | MA | GE1 | Impvt./Rehab. of Camiguin Circumferential Road Tangub Section |  | 2009-09-06 | 1st | X |  | 19.004 | 352 |  |  |  | O | 0.368 | 0.012 | 0.15 | 0.02 | 0.037 | 0.017 | 60.4 | -
L.M.G CONSTRUCTION | 5719 | L | B | MA | GE | Construction of Slope Protection and Desilting of Creek along C-6, Brgy. Calzada-Tipas, Taguig City | Brgy. Calzada-Tipas, Taguig City | 2015-06-04 | Final | Metro Manila 1st DEO | LF | 17.368 | 180 | 2015-03-03 | 2015-08-29 | (+) 47.78 | C | 0.417 | 0.133 | 0.3 | - | - | - | 85% | *85% Satisfactory
L.M.G. Construction | 5719 | L | B | MA | GE1 | Repair/Rehab./Impv't. of Nueva Ecija-Aurora Rd., K0214+918-K0216+329 w/ exceptions | Aurora | 2013-08-10 | 1st | III | LF | 9.9 | 46 | 2013-03-27 | 2013-06-10 | -1.17 | O | 0.362 | 0.2 | 0 | 0.03 | 0.05 | 0.033 | 67.5 | -
L.M.G. CONSTRUCTION | 5719 | L | B | MA | GE | Rehab. of Flood Control Dikes, Banco River, Sta. 012+673.50 to Sta. 012+847.75, San Esteban, Rizal Avenue | San Esteban, Rizal Avenue | 2015-06-09 | Final | Nueva Ecija 1st DEO | LF | 18.404 | 105 | 2015-02-17 | 2015-06-01 | 0% | C | 0.498 | 0.133 | 0.3 | - | - | - | 93.1% | *93.1% Very Satisfactory
L.M.G. CONSTRUCTION | 5719 | L | B | MA | GE | Concreting/Widening and Drainage Improvement/Rehabilitation of DR. Lazcano St. Quezon City | Quezon City | 2015-06-03 | 1st | Quezon City 2nd | LF | 13.438 | 214 | 2015-02-20 | 2015-09-21 | (+) 3.59 | O | 0.395 | 0.24 | 0.15 | 0.022 | 0.05 | 0.05 | 90.7% | -
L.M.G. CONSTRUCTION | 5719 | L | B | MA | GE | Construction of Slope Protection and Desilting of Creek along C-6, Brgy. Wawa, Taguig City | Taguig City | 2015-06-04 | Final | Metro Manila 1st DEO | LF | 17.368 | 180 | 2015-03-02 | 2015-08-28 | (+) 47.22 | C | 0.425 | 0.133 | 0.3 | - | - | - | 85.8% | *85.8% Satisfactory
L.M.G. CONSTRUCTION | 5719 | L | B | MA | GE | Concreting/Widening and Drainage Improvement/Rehabilitation of Dr. Lazcano St., Quezon City | Quezon City | 2015-08-26 | Final | QC 2nd DEO | LF | 13.482 | 214 | 2015-02-20 | 2015-09-21 | 14.95% | C | 0.462 | 0.133 | 0.3 | - | - | - | 89.5% | *90.22% Very Satisfactory
L.M.G. CONSTRUCTION | 5719 | L | B | MA | GE | Construction of Gabions & Slope Protection along Talavera River, Brgy. Dolores, Sto. Domingo, Nueva Ecija, Sta.087+591 to Sta.087+736 | Brgy. Dolores, Sto. Domingo, Nueva Ecija, Sta.087+591 to Sta.087+736 | 2015-11-17 | Final | Nueva Ecija First DEO | LF | 18.026 | 120 | 2015-02-11 | 2015-06-10 | - | C | 0.497 | 0.133 | 0.3 | - | - | - | 93% | 93% Very Satisfactory
L.M.G. Construction / Z F Construction Joint Venture | JV-12-343 | L | B | MA | GE1 | Asset Preservation of Nat'l Rd. Gen. from Pvmt. Mgt. System/Highway Dev. & Mgt. System (HDM-4), Nueva Ecija-Aurora Rd., a)K0212+265-K0214+000; b)K0220+000-K0221+000; c)K0229+000-K0230+698 | Baler, Aurora | 2013-08-10 | 1st | III | LF | 13.927 | 150 | 2013-03-26 | 2013-08-22 | 23.33 | O | 0.366 | 0.2 | 0.15 | 0.03 | 0.05 | 0.033 | 82.9 | -
L.N. Salvador Construction | 16661 | L | B | MA | GE | Construction of Protection Works Calapan North Road K0042+000-K0043+000 (Intermittent Section) | Puerto Galera, Oriental Mindoro | 2014-11-28 | 1st & Final | IV | LF | 19.5341 | 166 | 2014-04-30 | 2014-10-12 | 9.75% | C | 0.496 | 0.133 | 0.3 | - | - | - | 92.9% | 92.90% Very Satisfactory
L.N. Salvador Construction | 16661 | L | B | MA | GE | Construction of Protection Works Calapan North Road, K0042+000 - K0043+000 (Intermittent Section) | Puerto Galera, Oriental Mindoro | 2014-08-11 | 1st | IV-B | LF | 18.0303 | 154 | 2014-04-30 | 2014-09-30 | 17.76 | O | 0.367 | 0.196 | 0.15 | 0.03 | 0.05 | 0.05 | 84.3 | -
L.N.R. Construction | 14148 | L | B | MA | GE5 | Development of Pilar Port Project | Pilar, Sorsogon/ Region V | 2014-04-24 | 1st | DOTC | LF | 12.182 | 120 | 2013-11-12 | 2014-07-05 | 31.66 | O | 0.4 | 0.3 | 0.15 | 0.03 | 0.0381 | 0.05 | 96.81 | -
L.N.R. Construction | 14148 | L | B | MA | GE-5 | Sabang Port Development Project | Sabang, Calabanga, Camarines Sur | 2015-09-24 | 2nd & Final | DOTC | LF | 43.293 | 360 | 2014-03-26 | 2015-10-23 | 8.06 | C | 0.477 | 0.2 | 0.3 | - | - | - | 97.7 | 95.30% Very Satisfactory
L.P. Engineering Services | 9823 | L |  |  | GE2 | Rehabilitation of Murcon Dam - Electro Mechanical Works | Minabuyoc, Talavera, Nueva Ecija / Region III | 2013-07-27 | 1st | NIA | L | 35.658 | 120 | 2013-01-11 | 2013-08-08 | 5.3 | O | 0.4 | 0.3 | 0.15 | 0.012 | 0.0233 | 0.05 | 93.53 | -
L.R. De Guzman Construction | 10263 | L | C | SB | GE1 | Const. of Road @ Brgy. Alangan | Alangan, Limay, Bataan | 2011-04-02 | 1st | III | LF | 3.205 | 88 | 2011-02-03 | 2011-05-01 | 3.34 | O | 0.28 | 0.293 | 0.15 | 0.011 | 0.015 | 0.017 | 76.6 | -
L.R. TIQUI BUILDERS INC. |  | L | - | - | GE | Repair/Rehabilitation/Improvement/Construction of Pedestrian Overpass along Marikina Diversion Road (Marcos Highway) near Vermont Royale, Antipolo City ( S03855LZ) K0017+754 | Antipolo City | 2015-06-02 | 1st | Rizal 1st DEO | LF | 16.435 | 165 | 2015-01-13 | 2015-06-26 | 0.99% | O | 0.314 | 0.3 | 0.15 | 0.03 | 0.041 | 0.033 | 86.8% | -
L.R. TIQUI BUILDERS INC. | 13810 | L | AAA | MB | GB | Rehabilitation/Improvement of Tullahan River, Phase II, Brgy. San Bartolome, Quezon City | Quezon City | 2016-06-02 | 1st | Quezon City | LF | 43.425 | 270 | 2014-12-17 | 2015-09-12 | (+) 2.01 | O | 0.369 | 0.24 | 0.15 | 0.024 | 0.056 | 0.05 | 88.9% | -
L.R. Tiqui Builders, Inc. | 13810 | L | AAA | LB | GE1 | Asphalt overlay of Daang Maharlika |  | 2009-03-13 | 1st | II |  | 39.996 | 80 |  |  |  | O | 0.388 | 0.225 | 0.15 | 0.03 | 0.059 | 0.05 | #VALUE! | -
L.R. Tiqui Builders, Inc. | 13810 |  |  |  |  | Const. of Palilihan Bridge and Approaches (Phase IV) |  | 2010-02-18 |  | III |  | 24.992 | 150 |  |  |  | O | 0.368 | 0.3 | 0.15 | 0.03 | 0.042 | 0.05 | 94 | -
L.R. Tiqui Builders, Inc. | 13810 |  |  |  |  | Rehab./Reconst./Upgrading of Damaged Paved National Road at Pulilan-Calumpit Rd. |  | 2010-03-02 |  | III |  | 47.735 | 120 |  |  |  | O | 0.353 | 0.3 | 0.15 | 0.03 | 0.051 | 0.033 | 91.7 | -
L.R. Tiqui Builders, Inc. | 13810 |  |  |  |  | Rehab./Reconst./Upgrading of Damaged Paved National Road at Bigaa-Plaridel via Bulacan & Malolos Rd. |  | 2010-06-09 |  | III |  | 28.694 | 110 |  |  |  | O | 0.389 | 0.3 | 0.15 | 0.015 | 0.032 | 0.033 | 91.9 | -
L.R. Tiqui Builders, Inc. | 13810 |  |  |  |  | Rehab./Reconst./Upgrading of Damaged Paved National Roads at Gen.Alejo Santos Highway |  | 2010-06-10 |  | III |  | 40.605 | 275 |  |  |  | O | 0.357 | 0.24 | 0.15 | 0.018 | 0.043 | 0.033 | 84.1 | -
L.R. Tiqui Builders, Inc. | 13810 | L | AAA | LB | GE1 | Traffic Management along Manila North Road from Meycauayan, Bulacan-Mabalacat, Pampanga (Package II) |  | 2009-06-02 | 2nd | III |  | 138.3168 | 269 |  |  |  | O | 0.315 | 0.3 | 0.15 | 0.03 | 0.06 | 0.05 | 90.5 | -
L.R. Tiqui Builders, Inc. | 13810 | L | AAA | LB | GE1 | Impvt./Rehab. of Norzagaray-Bigte Road, Bulacan 3rd Congressional District |  | 2009-06-03 | 1st | III |  | 57.8221 | 180 |  |  |  | O | 0.249 | 0.3 | 0.15 | 0.03 | 0.055 | 0.05 | 83.4 | -
L.R. Tiqui Builders, Inc. | 13810 | L | AAA | LB | GE1 | Impvt./Widening of McArthur Highway (MNR)-Phase V, Meycauayan (Bulacan) to Mabalacat (Pampanga)-Bocaue-Balgatas-Guiguinto Sect.)-CP II |  | 2009-09-05 | 1st | III |  | 88.724 | 180 |  |  |  | O | 0.371 | 0.3 | 0.15 | 0.03 | 0.056 | 0.033 | 94 | -
L.R. Tiqui Builders, Inc. | 13810 | L | AAA | LB | GE1 | Impvt./Widening/Concreting of Manila North Road (MNR)-Phase V (Malolos-Calumpit Section)-CP I |  | 2009-09-05 | 1st | III |  | 110.823 | 240 |  |  |  | O | 0.361 | 0.3 | 0.15 | 0.03 | 0.056 | 0.033 | 93 | -
L.R. Tiqui Builders, Inc. | 13810 | L | AAA | LB | GE1 | Impvt./Rehab. of General Alejo Santos Highway inc. Niugan Bridge No. 3 |  | 2009-09-09 | 2nd | III |  | 62.146 | 230 |  |  |  | O | 0.358 | 0.3 | 0.15 | 0.03 | 0.056 | 0.033 | 92.7 | -
L.R. Tiqui Builders, Inc. | 13810 | L | AAA | LB | GE1 | Impvt./Rehab. of Norzagaray-Bigte Road |  | 2009-09-09 | 2nd | III |  | 57.9 | 200 |  |  |  | O | 0.345 | 0.3 | 0.15 | 0.03 | 0.056 | 0.033 | 91.4 | -
L.R. Tiqui Builders, Inc. | 13810 | L | AAA | LB | GE1 | Rehab. of Bocaue-San Jose Road |  | 2009-09-07 | 1st | III |  | 1.905 | 73 |  |  |  | O | 0.379 | 0.24 | 0.15 | 0.03 | 0.042 | 0.033 | 87.4 | -
L.R. Tiqui Builders, Inc. | 13810 | L | AAA | LB | GE1 | Const. of Palilihan Bridge # 1 including approaches and Road Right-of-Way along Roman Expressway |  | 2009-02-27 | 1st | III |  | 90.181 | 240 |  |  |  | O | 0.351 | 0.3 | 0.15 | 0.03 | 0.056 | 0.05 | #VALUE! | -
L.R. Tiqui Builders, Inc. | 13810 | L | AAA | LB | GE1 | Impvt. (Widening/Conc.) of Mc Arthur Highway (MNR) Meycauayan to Mabalacat, Pampanga (Phase IV) Package II |  | 2009-03-06 | 2nd | III |  | 70.394 | 180 |  |  |  | O | 0.366 | 0.3 | 0.15 | 0.03 | 0.047 | 0.05 | #VALUE! | -
L.R. Tiqui Builders, Inc. | 13810 | L | AAA | LB | GE1 | NCR/Bulacan Bdry.-Bigte-Ipo Dam Road inc. Replacement of Kay Tialo Bridge |  | 2009-03-10 | 2nd | III |  | 47.641 | 210 |  |  |  | O | 0.366 | 0.3 | 0.15 | 0.03 | 0.038 | 0.05 | #VALUE! | -
L.R. Tiqui Builders, Inc. | 13810 | L | AAA | LB | GE1 | Impvt. (Widening/Conc.) of Mc Arthur Highway (MNR) Meycauayan to Mabalacat, Pampanga (Phase IV) Package 1 |  | 2008-11-21 | 1st | III |  | 188.051 | 270 |  |  |  | O | 0.376 | 0.3 | 0.1 | 0.03 | 0.06 | 0.1 | 96.6 | -
L.R. Tiqui Builders, Inc. | 13810 | L | AAA | LB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved Naitonal Roads (Intermittent Section) Gen. Alejo Santos Highway Km. 45+000 to Km. 55+671 to Km. 56+102 & Km. 56+102 to Km. 56+948 | Plaridel & Bustos, Bulacan | 2014-11-07 | 1st & Final | III | LF | 21.5701 | 161 | 2014-03-23 | 2014-08-30 | 0% | C | 0.478 | 0.131 | 0.3 | - | - | - | 90.9% | 90.90% Very Satisfactory
L.R. Tiqui Builders, Inc. | 13810 | L | AAA | MB | GE | Dredging/Deepening with Channel Improvement along Angat River | Bustos, Bulacan | 2014-11-07 | 1st & Final | III | LF | 13.8234 | 255 | 2013-03-28 | 2013-12-07 | 0% | C | 0.418 | 0.133 | 0.3 | - | - | - | 85.1% | 85.10% Satisfactory
L.R. Tiqui Builders, Inc. | 13810 | L | AAA | LB | GE | Widening of Daang Maharlika Road Km. 39+000 to Km. 41+1001 (Plaridel Section); Km. 45+033 to Km. 48+000 (Baliuag Section) | Plaridel & Baliuag, Bulacan | 2014-11-07 | 1st & Final | III | LF | 31.4869 | 230 | 2013-06-03 | 2014-01-18 | 0% | C | 0.37 | 0.2 | 0.3 | - | - | - | 87% | 87.00% Satisfactory
L.R. Tiqui Builders, Inc. | 13810 | L | AAA | LB | GE1 | Widening of Daang Maharlika (Doña Remedios Trinidad Sect.) Km.45+452-Km.52+722 w/ exceptions | Baliuag, Bulacan | 2013-08-13 | 1st | III | LF | 36.062 | 240 | 2013-02-22 | 2013-10-19 | 1.46 | O | 0.375 | 0.24 | 0.15 | 0.03 | 0.055 | 0.033 | 88.3 | -
L.R. Tiqui Builders, Inc. | 13810 | L | AAA | LB | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rds. (Int. Sect.) Gen. Alejo Santos Highway Km.45+000-Km.55+671, Km.55+671-Km.56+102 & Km.56+102-Km.56+948 | Plaridel & Bustos, Bulacan | 2013-08-14 | 1st | III | LF | 21.57 | 161 | 2013-03-23 | 2013-08-30 | -1.66 | O | 0.373 | 0.24 | 0.133 | 0.02 | 0.05 | 0.05 | 86.6 | -
L.R. Tiqui Builders, Inc. | 13810 | L | AAA | LB | GE1 | Const. of Tartaro Bridge | San Miguel, Bulacan | 2013-08-15 | Final | III | LF | 24.892 | 210 | 2012-12-17 | 2013-07-14 | 0 | C | 0.449 | 0.133 | 0.3 | - | - | - | 88.2 | 85.32% Satisfactory
L.R. Tiqui Builders, Inc. | 13810 | L | AAA | LB | GE1 | Const. of Tartaro Bridge | San Miguel, Bulacan | 2013-03-18 | 1st | III | LF | 24.862 | 180 | 2012-12-17 | 2013-06-14 | 22.79 | O | 0.37 | 0.185 | 0.15 | 0.024 | 0.055 | 0.05 | 83.4 | -
L.R. Tiqui Builders, Inc. | 13810 | L | AAA | MB | GE2 | Dredging/Deepening w/ Channel Impv't. along Angat River | Bustos, Bulacan | 2013-08-14 | 1st | III | LF | 13.893 | 135 | 2013-03-28 | 2013-08-09 | -1.61 | O | 0.353 | 0.265 | 0.134 | 0.023 | 0.045 | 0.033 | 85.3 | -
L.R. Tiqui Builders, Inc. | 13810 | L | AAA | LB | GE1 | Widening of McArthur Highway (Manila North Rd.) inc. Rehab./Impv't. of existing Pvmnt. Loading & Unloading Bays & ROW | Malolos City, Bulacan | 2013-03-18 | Final | III | LF | 47.515 | 344 | 2012-05-09 | 2013-04-17 | 2.25 | C | 0.359 | 0.133 | 0.3 | - | - | - | 79.2 | 87.78% Satisfactory
L.R. Tiqui Builders, Inc. | 13810 | L | AAA | LB | GE1 | Impvt/Widening of Aguinaldo Highway and other related road Phase II |  | 2008-11-11 | 2nd | IV-A |  | 60.022 | 360 |  |  |  | O | 0.274 | 0.3 | 0.1 | 0.03 | 0.028 | 0.1 | 83.2 | -
L.R. Tiqui Builders, Inc. | 13810 | L | AAA | LB | GE1 | Traffic Management along Manila North Road, MNR from Meycauayan, (Package 2) |  | 2009-03-09 | 1st | TEAM |  | 138.317 | 239 |  |  |  | O | 0.371 | 0.3 | 0.15 | 0.03 | 0.06 | 0.05 | #VALUE! | -
L.R. Tiqui Builders, Inc. | 13810 | L | AAA | MB | GE | Construction of Single Barrel Box Culvert along Sto. Rosario Street | Mandaluyong City | 2014-11-29 | 1st & Final | NCR | LF | 14.4495 | 180 | 2014-06-11 | 2014-12-07 | 6% | C | 0.412 | 0.187 | 0.3 | - | - | - | 89.9% | 89.90% Very Satisfactory
L.R. Tiqui Builders, Inc. | 13810 | L | AAA | MB | GE2 | Const. of Slope Protection for Marikina River along Brgy. Tumana, Eastbank Marikina City, 2nd District Sta. 6+120-Sta.6+621.10 | Marikina City | 2013-08-06 | Final | NCR | LF | 43.77 | 214 | 2013-01-09 | 2013-08-10 | 38.79 | C | 0.452 | 0.133 | 0.3 | - | - | - | 88.5 | 88.44% Satisfactory
L.R. Tiqui Builders, Inc. | 13810 | L | AAA | MB | GE2 | Const. of Slope Protection for Marikina River along Brgy. Tumana, Eastbank, 2nd District Sta.6+120 Sta.6+621.10 | Marikina City | 2013-03-22 | 1st | NCR | LF | 43.77 | 214 | 2013-01-09 | 2013-08-10 | 33.26 | O | 0.398 | 0.233 | 0.15 | 0.03 | 0.04 | 0.033 | 88.4 | -
L.R. Tiqui Builders, Inc. | 13810 | L | AAA | LB | GE1 | Rehab./Reconst./Raising of Damaged Paved Nat'l Rd. along M.H. Del Pilar St. | Valenzuela City | 2013-03-18 | Final | NCR | LF | 28.428 | 339 | 2012-01-24 | 2012-12-27 | 2 | C | 0.411 | 0.2 | 0.3 | - | - | - | 91.1 | 85.52% Satisfactory
L.R. TIQUI BUILDERS, INC. | 13810 | L | AAA | LB | GE | Widening of Daang Maharlika, K0039+000 to K0041+1001 (Plaridel Sections), Plaridel, Baliuag, Bulacan | Plaridel, Baliuag, Bulacan | 2015-06-12 | Final | Bulacan 1st DEO | LF | 31.487 | 230 | 2014-06-03 | 2015-01-18 | 0% | C | 0.463 | 0.2 | 0.3 | - | - | - | 96.3% | *96.3% Outstanding
L.S.D. Construction & Supplies | 8980 | L | AAA | LB | GE1 | Const. of Drainage System along Baguio-Bua-Itogon Rd., K0254+(-655)-K0268+055 (V.S.) | Itogon, Benguet | 2013-07-29 | 1st | CAR | LF | 18.556 | 150 | 2013-03-23 | 2013-08-19 | 1.83 | O | 0.357 | 0.24 | 0.15 | 0.015 | 0.045 | 0.05 | 85.7 | -
L.S.D. Construction & Supplies | 8980 | L | AAA | LB | GE1 | Rd. Upgrading (Gravel to Conc.) along Gurel-Bokod-Kabayan-Buguias-Abatan Rd., K0322+491-K0338+760 (IS) Kabayan Sect. | Kabayan, Benguet | 2013-07-30 | Final | CAR | LF | 95.365 | 455 | 2011-09-05 | 2012-12-02 | 0 | C | 0.435 | 0.133 | 0.3 | - | - | - | 86.8 | 84.19% Satisfactory
L.S.D. Construction & Supplies | 8980 | L | AAA | MB | GE2 | Const. of Typical Cross Drainage Structure (Dome/Cathedral Type) of various sect. along MNR w/n the district 1)Pob. Villasis Sect.; 2)Bacag Villasis Sect.; 3)Nancayasan, Urdaneta Sect.; 4)Anonas, Urdaneta Sect.; 5)Sumabot, Binalonan Sect.; 6)Pob. Binalonan Sect.; 7)Alipangpang, Pozorrubio Sect.; 8)Pob. Sision Sect.; 9)Paldit Sision Sect.; 10)Pob. Sision Sect. | Pangasinan | 2013-08-09 | 1st | I | LF | 30.303 | 247 | 2013-03-27 | 2013-11-28 | -3.93 | O | 0.378 | 0.3 | 0.111 | 0.03 | 0.037 | 0.033 | 88.9 | -
L.S.D. Construction & Supplies | 8980 | L | AAA | LB | GE1 | Rd. Upgrading along Capas-San Jose-Mayantoc-Malacampa Rd., K0145+283-K0147+-476, Mayantoc | Camiling, Tarlac | 2013-08-08 | 1st | III | LF | 35.686 | 182 | 2013-02-22 | 2013-08-22 | 0.5 | O | 0.382 | 0.254 | 0.15 | 0.03 | 0.059 | 0.05 | 92.5 | -
L.S.D. Construction & Supplies | 8980 | L | AAA | LB | GE1 | Road Upgrading (Gravel to Paved), along Awang-Upi Lebak-Kalamansig-Palimbang-Sarangani Rd. (Km.1963+471-Km.1977+121) realigned to Rd. Upgrading (Gravel to Paved) along Awang-Upi-Lebak-Kalamansig-Palimbang-Sarangani Rd. (Km.2012+961-Km.2014+656) | Sultan Kudarat | 2013-03-13 | 1st | XII | LF | 35.903 | 235 | 2012-07-06 | 2013-02-26 | -56.79 | O | 0.357 | 0.24 | 0 | 0.03 | 0.044 | 0.033 | 70.4 | -
L.S.D. Construction and Supplies | 8980 | L | AAA | LB | GE1 | Rd. Upgrading (gravel to concrete) along Gurel-Bokod-Kabayan-Buguis-Abatan Rd., K0322+491-K0338+760 (IS), Kabayan Sect. | Kabayan, Benguet | 2012-11-21 | 2nd | CAR | LF | 95.365 | 455 | 2011-09-05 | 2012-12-02 | 2.84 | O | 0.364 | 0.3 | 0.15 | 0.03 | 0.047 | 0.05 | 94.1 | -
La Torre Builders & Construction | 2010-0514 |  |  | SB |  | Calbiga Irrigation Project | Calbiga, Western Samar | 2014-11-22 | 1st & Final | NIA | L | 8.857 | 185 | 2013-04-08 | 2014-01-07 | 0 | C | 0.4555 | 0.2 | 0.297 | - | - | - | 95.25 | 95.25% Very Satisfactory
Labb Construction | 13524 | L |  | LA |  | PW-BHL-13-14 BOHOL EMERGENCY ROAD REPAIR AND REHABILITATION OF JCT.(LIR)-QUINOGUITAN-SEVILLA-HANOPOL ROAD | Sevilla, Bohol | 2015-05-15 | 1st & Final | Bohol | LF | 13.298 | 325 | 2014-06-05 | 2015-04-25 | 0 | C | 0.4884 | 0.2 | 0.3 | - | - | - | 98.84 | 98.84% Outstanding
Labb Construction | 13524 | L | B | MA | GE | Upgrading of Junction (LIR) - Buenavista, Carmen - Danao - Getafe Road, Sec 1: K0086+400 - K0086+982.72, Sec 2: K0087+091 - K0087+530.468, Sec 3: K0087+819 - K0087+183.97, Sec 4: K0090+576 - K0091+540 | Bohol Province | 2014-10-26 | 1st & Final | VII | LF | 88.8679 | 360 | 2013-02-28 | 2014-02-22 | 19.74% | C | 0.354 | 0.2 | 0.3 | - | - | - | 85.4% | 85.40% Satisfactory
Labb Construction | 13524 | L | B | MA | GE | Major Repair/Maintenance of Existing Permanent Bridges, Clarin Bridge along Tagbilaran East Road | Loay, Bohol | 2014-08-12 | 1st & Final | VII | LF | 3.024 | 140 | 2014-02-26 | 2014-07-15 | 0 | C | 0.424 | 0.2 | 0.3 |  |  |  | 92.4 | 92.40% Very Satisfactory
Labb Construction | 13524 | L | B | MA | GE | Access Road to Declared Tourism Destination (road Upgrading) Gravel to Paved of Jct. (TNR), Maribojoc - Antequera - Catagbacan (Loon) Road | Antequera, Bohol | 2014-08-13 | Final | VII | LF | 22.7399 | 255 | 2013-02-04 | 2013-11-18 | 0 | C | 0.45 | 0.141 | 0.3 |  |  |  | 89.1 | 91.98% Very Satisfactory
Labb Construction | 13524 | L |  | LA |  | PW-BHL-13-05 Emergency Repair & Rehabilitation of Hinawanan (LOAY)-Concepcion-Jct.(Loboc-Sikatuna) Road | Loay and Loboc, Bohol | 2015-01-20 | 1st | Bohol | L | 16.436 | 255 | 2014-05-26 | 2015-02-04 | -3.23 | O | 0.39 | 0.297 | 0.117 | 0.02 | 0.061 | 0.05 | 93.5 | -
Labb Construction | 13524 | L | B | SA |  | New Bohol (Panglao) Airport Development Project | Panglao, Bohol | 2014-11-13 | 1st & Final | DOTC | LF | 17.973 | 150 | 2014-03-18 | 2014-08-14 | 0 | C | 0.4 | 0.2 | 0.3 | - | - | - | 90 | 90.00% Very Satisfactory
Labb Construction | 13524 | L | B | MA | GE1 | Access Rd. to declared Tourism Destination (Rd. Upgrading-Gravel to Paved) @ Jct. (TNR) Maribojoc-Antequera-Catagbacan (Loon) Rd., Km.23+057-Km.23+993 | Antequera, Bohol | 2013-08-17 | 1st | VII | LF | 21.596 | 210 | 2013-02-04 | 2013-09-01 | 5.28 | O | 0.387 | 0.257 | 0.15 | 0.03 | 0.065 | 0.05 | 93.9 | -
Labb Construction | 13524 | L | B | MA | GE1 | Const. of Bridge along Concepcion, Danao-Buenavista Carmen Road |  | 2009-06-06 | 3rd | VII |  | 13.914 | 504 |  |  |  | O | 0.344 | 0.263 | 0.15 | 0.03 | 0.047 | 0.05 | 88.4 | -
Labb Construction | 13524 | L | D | SB | GE1 | Const. of Bridges along Concepcion-Danao-Buenavista Carmen Road |  | 2008-11-19 | 1st | VII |  | 9.564 | 350 |  |  |  | O | 0.343 | 0.238 | 0.1 | 0.03 | 0.037 | 0.1 | 84.8 | -
Labb Construction | 13524 | L | B | MA | GE1 | Concreting of La Union, Candijay-Mabini Road (Sta. 166+670-Sta. 166+846) |  | 2009-06-05 | 1st | VII |  | 2.636 | 125 |  |  |  | O | 0.359 | 0.3 | 0.131 | 0.03 | 0.042 | 0.033 | 89.5 | -
Labb Construction / Herbert Malmis General Merchandise & Contractor, Inc. (JV) | JV-11-093 | L | A | MA | GE1 | Conc./Widening of Rd. Balilihan-Hanopol-Batuan Rd., Hanopol | Balilihan, Bohol | 2013-03-12 | Final | VII | LF | 40.547 | 255 | 2011-12-29 | 2012-09-08 | 0 | C | 0.301 | 0.2 | 0.3 | - | - | - | 80.1 | 83.46% Satisfactory
Lady of Assumption Enterprises | 25360 | L | B | MA | GE | Rehabilitation/Reconstruction of Critical Sections along National Road Roadslip Along Tacloban-Baybay South Road K0990+500 - K0990+600, Mailhi Section | Baybay City and Mahalapag, Leyte | 2014-10-28 | 1st & Final | VIII | LF | 17.3698 | 179 | 2014-03-19 | 2014-09-14 | 6.55% | C | 0.493 | 0.133 | 0.3 | - | - | - | 92.6% | 92.60% Very Satisfactory
Lady of Assumption Enterprises | 25360 | L | B | MA | GE | Const. of Padre Burgos Flood Control along Bdry. Southern Leyte - Maain - Macrohon - Sogod - Daang Maharlika K1160+000 K1160+400 | Padre Burgos, Southern Leyte | 2014-08-05 | 1st | VIII | LF | 13.2503 | 175 | 2014-02-14 | 2014-08-07 | 4.24 | OG | 0.272 | 0.3 | 0.15 | 0.03 | 0.045 | 0.033 | 83 | -
Lady of Assumption Enterprises | 25360 | L | B | MA | GE1 | Rd. Leading to Danao Camp Tree Park | Maasin City, Southern Leyte | 2013-08-05 | Final | VIII | LF | 33.334 | 188 | 2013-01-18 | 2013-07-24 | 0.74 | C | 0.46 | 0.133 | 0.3 | - | - | - | 89.3 | 87.02% Satisfactory
Lady of Assumption Enterprises | 25360 | L | B | MA | GE1 | Road Leading to Danao Camp Tree Park | Maasin City, Southern Leyte | 2013-03-16 | 1st | VIII | LF | 33.334 | 128 | 2013-01-18 | 2013-05-25 | 14.69 | O | 0.305 | 0.26 | 0.15 | 0.03 | 0.06 | 0.05 | 85.5 | -
LADY OF ASSUMPTION ENTERPRISES | 25360 | L | B | MA | GE | Rehab/Major Repair of Permanent Bridges, Ichon Bridge, Along Bdry, S. Leyte-Maasin-Sogod-Daang Maharlika | Along Bdry, S. Leyte-Maasin-Sogod-Daang Maharlika | 2015-06-03 | 1st | Southern Leyte DEO | LF | 4.746 | 150 | 2015-02-02 | 2015-07-01 | 31.71% | O | 0.373 | 0.232 | 0 | 0.024 | 0.035 | 0.033 | 69.7% | -
LADY OF ASSUMPTION ENTERPRISES | 25360 | L | B | MA | GE | Construction/Improvement of Access Roads Leading to Declared Tourism Destinations, Ma. Clara-Cagnituan Road Leading to Massin City Tourism Loop (Monte Cueva, Danao Camp Tree Park, St. Francis Javier Shrine, Maasin City Zoo Theme Park, Maasin City, Southern Leyte | Maasin City, Southern Leyte | 2015-11-16 | 1st | Regional Office No. VIII | LF | 79.4722 | 260 | 2015-04-22 | 2016-01-06 | (+)3.97% | OG | 0.318 | 0.275 | 0.15 | 0.03 | 0.05 | 0.05 | 87.3% | 87.3% Satisfactory
LAHDETH CONSTRUCTION AND SUPPLY | 34833 | L | D | SB | GE | Rehab./ Reconst. Of National Roads with Slips, Slope Collapse & Landslide along Baao - Iriga City - -Nabua Road, Iriga City (K0475+000 - K0477+105) | Iriga City | 2015-06-03 | Final | Camarines Sur 4th | LF | 5.908 | 115 | 2015-02-06 | 2015-05-31 | 1.74% | C | 0.464 | 0.15 | 0.3 | - | - | - | 91.4% | *91.4% Very Satisfactory
LAHDETH CONSTRUCTION AND SUPPLY | 34833 | L | D | SB | GE | Cluster: Concreting of Barangay Roads at Brgy. Yabo | Sipocot, Camarines Sur | 2015-06-04 | Final | Camarines Sur 5th | LF | 1.868 | 60 | 2015-01-21 | 2015-03-21 | 3.33% | C | 0.431 | 0.146 | 0.3 | - | - | - | 87.7% | *87.7% Satisfactory
LAHDETH CONSTRUCTION AND SUPPLY | 34833 | L | D | SB | GE | Concreting of Barangay Roads, Sipocot, Camarines Sur | Sipocot, Camarines Sur | 2015-11-12 | Final | Camarines Sur Fifth DEO | LF | 1.8946 | 60 | 2015-01-23 | 2015-03-23 | 3.33% | C | 0.323 | 0.2 | 0.3 | - | - | - | 82.3% | 82.3% Satisfactory
LAJ TRUCKING AND BUILDERS | 36350 | L | B | SB | GB | Construction of Two Storey, 4 Classroom School Building, Balubal NHS, Barangay Balubal, Cagayan de Oro City | Barangay Balubal, Cagayan de Oro City | 2015-11-15 | 1st | Cagayan de Oro City 2nd | LF | 5.9922 | 105 | 2015-09-01 | 2015-12-15 | (+) 0.45% | OG | 0.383 | 0.24 | 0.15 | 0.03 | 0.047 | 0.05 | 90% | 90% Very Satisfactory
Lakewood Construction Company | 5294 | L | C | SB | GB | Rehabilitation of Multi-Purpose Building at Sitio Tigbungabong, San Pedro, Tungawan | Zamboanga, Sibugay | 2014-10-23 | 1st & Final | IX | LF | 3.9764 | 130 | 2014-04-04 | 2014-08-11 | 1.54% | C | 0.498 | 0.133 | 0.3 | - | - | - | 93.1% | 93.10% Very Satisfactory
LAK-K Builders | 1026 |  | B |  |  | Greendale Residences Phase 1 | Brgy. Suhi, San Isidro, Tacloban City, Leyte | 2015-10-02 | 1st | NHA | LF | 94.74 | 245 | 2015-04-01 | 2015-12-01 | 1.82 | O | 0.3114 | 0.281 | 0.15 | 0.03 | 0.047 | 0.05 | 86.94 | -
Lanao Builder and Enterprises | 15982 | L | A | MA | GE1 | Rehab./Reconst./Upgrading along Dobleston-Butadon Rd., Km.2004+098-Km.2006+336 | Kapatagan, Lanao del Norte | 2013-08-12 | 2nd | X | LF | 37.678 | 213 | 2013-01-18 | 2013-08-18 | 0.24 | O | 0.289 | 0.238 | 0.15 | 0.01 | 0.045 | 0.033 | 76.5 | -
Lanao Builder and Enterprises | 15982 | L | A | MA | GE1 | Rehab./Reconst./Upgrading along Dobleston-Butadon Rd., Kapatagan, Lanao del Norte, Km.2004+098-Km.2006+336 | Kapatagan, Lanao del Norte | 2013-03-14 | 1st | X | LF | 35.723 | 167 | 2013-01-18 | 2013-07-03 | 0.59 | O | 0.343 | 0.246 | 0.15 | 0.01 | 0.04 | 0.033 | 82.2 | -
Lanao Builder and Enterprises | 15982 |  |  |  |  | Rehab./Reconst./Upgrading of Linamon-Zamboanga Road |  | 2010-06-03 |  | X |  | 30.126 | 179 |  |  |  | O | 0.385 | 0.24 | 0.15 | 0.023 | 0.045 | 0.033 | 87.6 | -
Lanao Builder and Enterprises | 15982 | L | A | MA | GE1 | Rehab. of Linamon-Zamboanga Roads, Kauswagan Section |  | 2008-08-30 | 1st | X |  | 9.053 | 120 |  |  |  | O | 0.333 | 0.24 | 0.1 | 0.03 | 0.032 | 0.1 | 83.5 | -
Lanao Builders and Enterprises | 15982 | L | A | MA | GE | Road Upgrading (Gravel to Paved) Based on Gravel Road Strategies, Traffic benchmark for Upgrading to Paved Road STD (HDM-4 Project Analysis) (Intermittent Section) Lanao del Norte Interior Circumferential Road (LDNICR) Lala-Salvador-Tubod Road, Pantao Ragat Section K1548+250 - K1551+768 | Lanao del Norte | 2014-10-29 | 1st | X | LF | 77.2316 | 223 | 2014-03-10 | 2014-10-18 | -4.93% | O | 0.331 | 0.3 | 0 | 0.01 | 0.033 | 0.033 | 70.7% | 70.70% Poor
Lanao Builders and Enterprises | 15982 | L | A | MA | GB | Const. of Multi-Purpose Building at MSU-IIT MPC, Lambaguhon, Brgy. San Roque | Iligan City | 2014-10-29 | 1st & Final | X | LF | 7.0952 | 120 | 2014-05-30 | 2014-09-26 | 2% | C | 0.456 | 0.139 | 0.3 | - | - | - | 89.5% | 89.50% Very Satisfactory
Lanao Builders and Enterprises | 15982 | L | A | MA | GB | Repair/Rehab. Lanao Avenue, Tubod, Iligan City | Iligan City | 2014-10-29 | 1st | X | LF | 4.3296 | 80 | 2014-08-28 | 2014-11-15 | 15.18% | O | 0.312 | 0.284 | 0.15 | 0.01 | 0.032 | 0.05 | 83.8% | 83.80% Satisfactory
Lanao Builders and Enterprises | 15982 | L | A | MB | GB1 | Completion of ACA Bldg., I Phase (Construction) |  | 2008-11-26 | 1st | DOST |  | 11.364 | 270 |  |  |  | O | 0.339 | 0.289 | 0.0932 | 0.03 | 0.06 | 0.05 | 86.12 | -
Lanao Builders and Enterprises | 15982 | L | A | MB | GB1 | Completion of ACA Building I (Phase 3) |  | 2008-11-26 | 1st | DOST |  | 11.364 | 270 |  |  |  | O | 0.339 | 0.289 | 0.0932 | 0.03 | 0.06 | 0.05 | 86.12 | -
LANAO BUILDERS AND ENTERPRISES | 15982 | L | A | MA | GB | Repair/Rehabilitation of DPWH Lanao del Norte 1st District Engineering Office Building, Del Carmen, Iligan City | Del Carmen, Iligan City | 2015-06-06 | Final | Lanao del Norte First DEO | LF | 4.33 | 80 | 2014-08-28 | 2014-11-15 | - | C | 0.467 | 0.2 | 0.3 | - | - | - | 96.7% | *87.67% Satisfactory
LARSEN-DUTCHER CONSTRUCTOR | 29172 | L | A | MA | GE | Rehabilitation/Reconstruction of Canumay - Bignay Road, Valenzuela City 1st LD | Valenzuela City 1st LD | 2015-08-28 | 1st | MM 3rd DEO | LF | 17.286 | 201 | 2015-03-19 | 2015-10-05 | 3.28% | O | 0.368 | 0.24 | 0.15 | 0.03 | 0.035 | 0.05 | 87.3% | -
LASP MARKETING | 34650 | L | D | SB | GE | Completion of Multi-Purpose Building | Brgy. Igbucagay, Hamtic, Antique | 2015-08-31 | 1st & Final | Antique | LF | 0.498 | 60 | 2015-05-22 | 2015-07-20 | 42.73% | C | 0.441 | 0.133 | 0.3 | - | - | - | 87.4% | *87.4% Satisfactory
Latorre Builders & Construction | [5 empty] | WSIIMO Contract No. 11-2014 | Gandara, Western Samar | 2015-11-21 | 1st & Final | NIA | LF | 14.781 | 300 | 2014-08-29 | 2015-06-24 | 0 | C | 0.447 | 0.149 | 0.3 | - | - | - | 89.6 | *89.60% V. Satisfactory
Latorre Builders and Construction | 29538 | L |  | SB |  | Construction of Brgy. Burgos Wharf | Brgy. Burgos, Daram, Samar/ Region 8 | 2016-10-19 | 1st | DOTC | LF | 9.6558 | 240 | 2016-01-18 | 2017-01-10 | 0.46 | O | 0.3654 | 0.3 | 0.15 | 0.02 | 0.0263 | 0.05 | 91.17 | -
LC Ting Construction/Road Edge Trading & Development Services Joint Venture | JV-13-228 | L | B | MA | GE | Const. of Angalay Bridge including approaches along CDO-Airport-Bukidnon Road, Lumbia-Uguiban By-Pass Road | Cagayan de Oro City | 2014-10-20 | 1st | X | LF | 16.0778 | 220 | 2014-02-04 | 2014-09-11 | -2.5% | O | 0.345 | 0.3 | 0 | 0.015 | 0.047 | 0.033 | 74% | 74.00% Poor
LDV Construction | 35864 | L |  |  |  | Design and Built and Detailed Engineer Drawings and Construction of Internal Medicine Building | Kumintang Ibaba, Batangas City/ Region 4-A | 2014-11-05 | 1st | DOH | L | 49.95 | 365 | 2014-02-06 | 2015-02-06 | 0 | O | 0.38753 | 0.3 | 0.15 | 0.03 | 0.0646 | 0.05 | 98.213 | -
Le Reve Builders | 27312 | L | B | MA | GE | Rehabilitation/Reconstruction of Damaged Paved National Road, Sta. Rita - Camias, Old Road K0073+326 - K0073+1027 | San Miguel, Bulacan | 2014-09-27 | 1st & Final | Special 3 | LF | 8.7494 | 105 | 2014-02-11 | 2014-05-26 | 0 | C | 0.403 | 0.134 | 0.3 |  |  |  | 83.7 | 83.70% Satisfactory
Le Reve Builders | 27312 | L | B | MA | GB | Repair and Rehabiliation of Hanging Bridge | Biak-na-Bato National Park, San Miguel, Bulacan | 2014-12-05 | Final | TIEZA | LF | 1.079 | 60 | 2014-09-22 | 2014-11-01 | 0 | C | 0.498 | 0.025 | 0.3 |  |  |  | 82.3 | 82.30% Satisfactory
Lea & Sons Trading & Construction | 34959 | L | D | SB | GB1 | Repair/Maint.of DPWH Bldg. Office Quarter (PJHL Bldg.) | Roxas, Palawan | 2013-03-12 | 1st | IVB | LF | 0.516 | 45 | 2013-02-06 | 2013-03-23 | -11.64 | O | 0.344 | 0.24 | 0.034 | 0.03 | 0.041 | 0.05 | 73.9 | -
Lea & Sons Trading and Construction | 34959 | L | D | SB | GB1 | Repair/Maint. of DPWH Bldg. Office Quarter (PJHL Bldg.) | Roxas, Palawan | 2013-08-10 | Final | IVB | LF | 0.55 | 76 | 2013-02-06 | 2013-04-22 | 0 | C | 0.438 | 0.156 | 0.3 | - | - | - | 89.4 | 78.55% Unsatisfactory
Leadway Construction & Development Corp. (LCDC) | 4378 | L | AAA | LB | GE1 | Impvt./Widening/Conc. of MNR-Phase V-Meycauayan, Bulacan to Mabalacat, Pampanga-Completion of Tulaoc Bridge and Sto. Domingo Bridge and Approaches (CP VI) |  | 2009-08-28 | 1st | III |  | 31.028 | 171 |  |  |  | O | 0.361 | 0.3 | 0.15 | 0.03 | 0.05 | 0.05 | 94.1 | -
Leadway Construction & Development Corp. (LCDC) | 4378 | L | AAA | LB | GE1 | Const. of BASA Airbase Access Road (Floridablanca) leading to SCTEX Interchange |  | 2009-08-25 | 1st | III |  | 93.566 | 240 |  |  |  | O | 0.369 | 0.3 | 0.15 | 0.03 | 0.051 | 0.033 | 93.3 | -
Leadway Construction & Development Corp. (LCDC) | 4378 | L | AAA | LB | GE2 | CP 29 Repair of Checkgates along Bebe Anak Pampanga Delta and Sapang iBa under the Post Ondoy and Pepeng Short -Term Infrastructure Rehab. Project (POPSTIRP) | Masantol, Pampanga | 2012-03-14 | 1st | BOM / III | FA | 24.328 | 90 | 2011-11-23 | 2012-02-20 | 0.33 | O | 0.31 | 0.3 | 0.15 | 0.03 | 0.045 | 0.05 | 88.5 | -
Leamor Construction and Supply | 34928 | L | D | SB | GE1 | Const. of Bridge at Dahlia Street, Poblacion I | Bansalan, Davao del Sur | 2013-08-09 | Final | XI | LF | 1.944 | 60 | 2013-01-21 | 2013-03-21 | 0 | C | 0.442 | 0.133 | 0.3 | - | - | - | 87.5 | 87.50% Satisfactory
Leamor Construction and Supply | 34928 | L | D | SB | GE1 | Const. of Bridge at Dahlia St., Poblacion I | Bansalan, Davao del Sur | 2013-03-16 | 1st | XI | LF | 1.944 | 60 | 2013-01-21 | 2013-03-21 | 1.24 | O | 0.372 | 0.239 | 0.15 | 0.03 | 0.03 | 0.05 | 87.1 | -
Lechi Construction | 24196 | L | B | SB | GE2 | Construction of Flood Control (Seawall) |  | 2009-06-06 | 1st | VIII |  | 2.833 | 120 |  |  |  | O | 0.356 | 0.24 | 0.15 | 0.022 | 0.037 | 0.033 | 83.8 | -
Leda Construction Incorporated | 12229 | L | B | MA | GE1 | Jct. (LIR) Buenavista-Carmen-Danao-Getafe Rd. |  | 2009-09-09 | 2nd | VII |  | 12.184 | 450 |  |  |  | O | 0.344 | 0.24 | 0.15 | 0.03 | 0.037 | 0.033 | 83.4 | -
Leda Construction Incorporated (Formerly: Leda Construction) | 12229 | L | B | MA | GE | Const./Imrv't. of Conception - Danao - Buenavista - Carmen Road, K0071+820 to K0073+806.89 | Bohol Province | 2014-08-13 | Final | VII | LF | 64.2632 | 364 | 2013-04-22 | 2014-04-18 | 0 | C | 0.479 | 0.178 | 0.3 |  |  |  | 95.7 | 90.90% Very Satisfactory
Leda Construction Incorporated (Formerly: Leda Construction) | 12229 | L | B | MA | GE1 | Const./Impv't. of Concepcion-Danao-Buenavista, Carmen Rd., K0071+820-K0073+806.93 | Bohol Province | 2013-08-16 | 1st | VII | LF | 62.464 | 270 | 2013-04-22 | 2014-01-16 | 8.03 | O | 0.337 | 0.264 | 0.15 | 0.03 | 0.046 | 0.05 | 87.7 | -
Leda Construction Incorporated (Formerly: Leda Construction) | 12229 | L | B | MA | GE1 | Rehab./Strengthening/ Reconst. of Makapiko Bridge along Balilihan-Hanopol-Batuan Rd., Batuan Sect. | Batuan, Bohol | 2013-03-14 | 2nd | VII | LF | 34.152 | 488 | 2012-01-31 | 2013-06-01 | 14.56 | O | 0.39 | 0.275 | 0.15 | 0.03 | 0.055 | 0.033 | 93.3 | -
Leda Construction Incorporated (Formerly: Leda Construction) | 12229 | L | B | MA | GE1 | Reconst. of Makapiko Bridge along Balilihan-Hanopol-Batuan Rd., Batuan Sect. | Batuan, Bohol | 2013-03-14 | Final | VII | LF | 13.313 | 252 | 2012-01-02 | 2012-09-09 | 0.79 | C | 0.472 | 0.133 | 0.3 | - | - | - | 90.5 | 88.76% Satisfactory
Leda Construction Incorporated (Formerly: Leda Construction) | 12229 | L | B | MA | GE1 | Repair of Concrete Pavement & Const. of Box Culverts & Rd. Slope Protection along Jagna-Sierra Bullones Rd., Km.70.00-Km.94.200 w/ exception | Bohol | 2013-03-14 | 1st | VII | LF | 13.875 | 261 | 2012-07-31 | 2013-04-17 | 0.7 | O | 0.368 | 0.24 | 0.15 | 0.03 | 0.045 | 0.033 | 86.6 | -
Leda Construction Incorporated (Formerly: Leda Construction) | 12229 | L | B | MA | GE | Widening of Biliran Circumferential Road to Include Payment of RROW Damages (Virginia-Culaba Proper Section) Km.1067+000 - Km. 1068+300 | Culaba, Biliran Province | 2014-10-27 | 1st | VIII | LF | 24.8062 | 241 | 2014-02-06 | 2014-10-04 | -5.19% | O | 0.338 | 0.3 | 0.098 | 0.03 | 0.045 | 0.033 | 84.4% | 84.40% Satisfactory
Leda Construction Incorporated (Formerly: Leda Construction) | 12229 | L | B | MA | GE1 | Rd. Upgrading of Jaro-Dagami-Burauen-La Paz Rd., Km.0955+000-Km.0955+527; Km.0955+611-Km.0955+970; Km.0952+589-Km.0952+855; Km.0952+000-Km.0952+091 | Dagami, Leyte | 2013-08-17 | Final | VIII | LF | 12.141 | 205 | 2013-01-15 | 2013-08-07 | 0 | C | 0.454 | 0.133 | 0.3 | - | - | - | 88.7 | 89.36% Very Satisfactory
Leda Construction Incorporated (Formerly: Leda Construction) | 12229 | L | B | MA | GE1 | Rd. Upgrading of Jaro-Dagami-La Paz Rd., Km.0955+000-Km.0955+527; Km.0955+611-Km.0955+970; Km.9052+589-Km.0952+855; Km.0952+000-Km.0952+091 | Dagami, Leyte | 2013-03-11 | 1st | VIII | LF | 12.141 | 145 | 2013-01-15 | 2013-06-08 | 0.11 | O | 0.383 | 0.24 | 0.15 | 0.03 | 0.045 | 0.05 | 89.8 | -
Leda Construction Incorporated (Formerly: Leda Construction) | 12229 | L | B | MA | GE1 | Rehab./Strengthening of San Joaquin Bridge along Daang Maharlika, San Joaquin | Palo, Leyte | 2013-03-22 | 1st | VIII | LF | 31.64 | 180 | 2013-01-14 | 2013-07-12 | 2 | O | 0.4 | 0.225 | 0.15 | 0.03 | 0.029 | 0.033 | 86.7 | -
Leda Construction Incorporated (Formerly: Leda Construction) | 12229 | L | B | MA | GE1 | Concrete Paving of Biliran Circ. Rd. Salvacion-Bool Rd. Sect., Km.1061+870-Km.1064+197 w/ exception | Culaba, Biliran Province | 2013-03-12 | Final | VIII | LF | 48.021 | 310 | 2012-02-01 | 2012-12-07 | 0 | C | 0.406 | 0.137 | 0.3 | - | - | - | 84.3 | 85.92% Satisfactory
Leda Construction Incorporated (Formerly: Leda Construction) | 12229 | L | B | MA | GE1 | Rd. Upgrading of Kiling-Tanauan-Tabontabon-Julita Rd., K0932+477.5-K0934+175.40 | Tabontabon, Leyte | 2013-03-11 | Final | VIII | LF | 34.69 | 200 | 2012-01-24 | 2012-08-10 | 0 | C | 0.37 | 0.18 | 0.3 | - | - | - | 85 | 83.44% Satisfactory
Leda Construction Incorporated (Formerly: Leda Construction) | 12229 | L | B | MA | GE1 | Reconst. of Calbiga Bridge along Daang Maharlika Rd. | Calbiga, Samar | 2013-03-18 | 1st | VIII | LF | 47.269 | 350 | 2012-06-25 | 2013-06-09 | 0 | O | 0.331 | 0.24 | 0.15 | 0.03 | 0.04 | 0.033 | 82.4 | -
Leda Construction Incorporated (Formerly: Leda Construction) | 12229 |  |  |  |  | Rehab./Reconst. of Palo-Carigara-Ormoc Rd., Palo-Carigara-Ormoc Rd. Sect. |  | 2010-05-31 |  | VIII |  |  | 120 |  |  |  | O | 0.4 | 0.3 | 0.069 | 0.03 | 0.037 | 0.033 | 86.9 | -
LEDA CONSTRUCTION INCORPORATED (Formerly: Leda Construction) | 12229 | L | A | MB | GE | Road Upgrading (Gravel to Paved along Leyte-Samar Inter-Provincial Road, K0945+741-K0945+865; KO945+933-KO947+097; 50950+399-K0951+199, San Miguel, Leyte | K0909+363-KO0910+270; KO910+421-KO911+243; KO911+243-K0911+400, Babatngon, Leyte | 2015-08-24 | 1st & Final | Leyte 1st DEO | LF | 46.155 | 209 | 2015-01-30 | 2015-08-26 | (+)2.39 | C | 0.353 | 0.2 | 0.3 | - | - | - | 85.3% | *85.3% Satisfactory
LEDA CONSTRUCTION INCORPORATED (Formerly: Leda Construction) | 12229 | L | A | MA | GB | Rehabilitation/Improvement of Municipal Auditorium (Gymnasium), LGU, Tolosa, Leyte | Tolosa, Leyte | 2015-11-10 | 1st | Leyte First DEO | LF | 41.3795 | 275 | 2015-07-10 | 2016-04-09 | (+)2% | OG | 0.337 | 0.24 | 0.15 | 0.03 | 0.047 | 0.05 | 85.4% | 85.4% Satisfactory
Leda Construction Incorporation (Formerly: Leda Construction) | 12229 | L | B | MA | GE1 | Rehab./Strengthening/Reconst. of Makapiko Bridge along Bililihan-Hanopol-Batuan Rd., Batuan Sect. | Bohol | 2012-08-09 | 1st | VII | LF | 33.578 | 391 | 2012-01-31 | 2013-02-24 | 15.57 | O | 0.366 | 0.24 | 0.15 | 0.03 | 0.045 | 0.033 | 86.4 | -
LEDA CONSTRUCTION, INC. (Formerly:Leda Construction) | 12229 | L | B | MA | GE | Improvement of Concepcion, Danao-Buenavista, Carmen Road Leading to Danao Adventure Park Danao-Carmen, Bohol, Sta. 68+561.46 to Sta. 70+270 | Concepcion, Danao-Buenavista, Carmen Road | 2015-06-09 | Final | Regional Office No. VII | LF | 37.42 | 309 | 2014-05-02 | 2015-03-06 | 0% | C | 0.452 | 0.139 | 0.3 | - | - | - | 89.1% | *89.1% Very Satisfactory
LEDA CONSTRUCTION, INCORPORATED (Formerly: Leda Construction) | 12229 | L | AAA | MB | GE | Construction/ Improvement of Access Roads leading to Airports, Seaports and Declared Tourism Destinations along Jct. (TER) La Union - Mabini - Cabulao - Ubay Road (leading to beach areas at Anda and Ubay), Mabini, Bohol Province | Mabini, Bohol Province | 2015-11-15 | Final | Bohol 3rd | LF | 36.3174 | 179 | 2015-05-27 | 2015-11-21 | 0.0015 | C | 0.373 | 0.24 | 0.15 | 0.03 | 0.035 | 0.05 | 87.8% | 87.8% Satisfactory
LEDA CONSTRUCTION, INCORPORATED (Formerly: Leda Construction) | 12229 | L | B | MA | GE | Off-Carriageway Improvement (Cluster I): Concreting of Shoulder, Tagbilaran East Road (Tagbilaran-Jagna)Jagna Section, Jagna, Bohol | Jagna, Bohol | 2015-11-17 | Final | Bohol 3rd | LF | 3.7044 | 121 | 2015-02-20 | 2015-07-20 | 0 | C | 0.481 | 0.133 | 0.3 | - | - | - | 91.4% | 91.4% Very Satisfactory
Legacy Construction | 22465 | L | A | MA | GE | Construction of Slope Protection and Drainage System along Mandurriao-San Miguel-Alimodian-Maasin-Cabatuan Road, K0012+380-K0012+774.4 and K0013+091.5-K0014+781 | San Jose, San Miguel, Iloilo | 2014-10-28 | 1st & Final | VI | LF | 9.2032 | 140 | 2014-02-12 | 2014-07-01 |  | C | 0.409 | 0.133 | 0.3 | - | - | - | 84.2% | 84.20% Satisfactory
Legacy Construction | 22465 | L | A | MA | GE | Construction/Rehabilitation of Flood Mitigation Facilities along Major River Basin and Principal Rivers: Silway-Apopong-Sinawal River Basins (Polomolok) | Polomolok, South Cotabato | 2014-10-29 | 1st | XII | LF | 9.5712 | 145 | 2014-06-29 | 2014-11-20 | 0.2% | O | 0.345 | 0.199 | 0.15 | 0.03 | 0.055 | 0.05 | 82.9% | 82.90% Satisfactory
Legacy Construction | 22465 | L | A | MA | GE | Completion of Access Road to Mandurriao Bridge Mandurriao, Iloilo City Sta. 5+200 - Sta. 5+900 with exception | Iloilo City | 2014-08-04 | 1st & Final | VI | LF | 15.9939 | 174 | 2013-03-26 | 2013-07-03 | 0 | C | 0.395 | 0.2 | 0.3 |  |  |  | 89.5 | 89.50% Very Satisfactory
Legacy Construction | 22465 | L | A | MA | GE | Road Upgrading (Gravel to Paved) Based on Gravel Road Strategies Traffic Benchmark for Upgrading to Paved Road Standards (HDM-4) Project Analysis, Concreting of January - Badiangan - Tina Road K0040+151.50 - K0041+400 (K0040+151.50 - K0041+376) | Badiangan, Iloilo | 2014-08-15 | Final | VI | LF | 17.92 | 195 | 2013-02-06 | 2013-05-06 | 0 | C | 0.41 | 0.2 | 0.3 |  |  |  | 91 | 85.42% Satisfactory
Legacy Construction | 22465 | L | A | MA | GE1 | Rd. Upgrading (Gravel to Paved), Conc. of Janiuay-Badiangan-Tina Rd., K0040+151.50-K0041+400 (K0040+151.50-K0041+376) | Badiangan, Iloilo City | 2013-08-20 | 1st | VI | LF | 17.92 | 201 | 2013-02-06 | 2013-08-26 | 0.14 | O | 0.364 | 0.203 | 0.15 | 0.03 | 0.037 | 0.033 | 81.7 | -
Legacy Construction | 22465 | L | A | MA | GE1 | Rehab./Recons./Upgrading of Dumaguete North Rd. (Calo Rd. Sec.) |  | 2009-09-12 | 1st | VII |  | 26.856 | 200 |  |  |  | O | 0.386 | 0.24 | 0.15 | 0.03 | 0.037 | 0.033 | 87.6 | -
Legacy Construction | 22165 | L | A | MA | GE1 | Rehab./Upgrading (Conc.) of Boracay Circ. Rd. Sta.2+350-Sta.2+800, Bolabog-Tulubhan Sect., Boracay Island | Malay, Aklan | 2012-11-23 | 1st | VI | LF | 13.822 | 120 | 2012-10-15 | 2013-02-11 | -2.87 | O | 0.4 | 0.24 | 0.121 | 0.03 | 0.05 | 0.033 | 87.4 | -
LEGACY CONSTRUCTION | 22465 | L | A | MA | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Secondary Roads, Iznart-Ledesma-Molo Road | K0001+1000 to K0001+572, Iloilo City | 2015-06-02 | Final | Iloilo City DEO | LF | 16.631 | 145 | 2014-05-16 | 2014-10-07 | 2.88% | C | 0.354 | 0.2 | 0.3 | - | - | - | 85.4% | *85.4% Satisfactory
LEGACY CONSTRUCTION | 22465 | L | A | MA | GE | Rehab./Reconst./Upgrading of Bacolod Circumferential Road (South) | K004+536-K004+592, K0010+000-K0010+400 (Intermittent Section), Bacolod City | 2015-06-11 | 1st | Bacolod City | LF | 7.038 | 105 | 2015-03-02 | 2015-06-14 | 1.97% | O | 0.339 | 0.3 | 0.15 | 0.022 | 0.035 | 0.033 | 87.9% | -
LEGACY CONSTRUCTION | 22465 | L | A | MA | GE | Construction/ Upgrading/ Rehabilitation of Drainage along National Roads Daang Maharlika (MN) Tibungco Section | K1491+104 - K1492+000, Davao City | 2015-06-12 | 1st | Davao City | LF | 19.053 | 152 | 2015-03-09 | 2015-08-07 | (+)15.94% | O | 0.338 | 0.24 | 0.15 | 0.023 | 0.033 | 0.05 | 83.4% | -
LEGACY CONSTRUCTION | 22465 | L | A | MA | GE | Off-Carriageway Improvement along Davao-Sarangani Coastal Road, Poblacion Sta. Maria, Davao del Sur (Km. 1601+590-Km. 1604+000) | Poblacion Sta. Maria, Davao del Sur (Km. 1601+590-Km. 1604+000) | 2015-09-01 | 1st | Davao del Sur 2nd DEO | LF | 18.194 | 166 | 2015-04-13 | 2015-09-25 | 0.07% | O | 0.362 | 0.237 | 0.15 | 0.03 | 0.06 | 0.05 | 88.9% | -
LEGACY CONSTRUCTION | 22465 | L | A | MA | GE | 15NH 0024 Cantilan CIS, (Creek Improvement/Deepening of Alamio River Protection And Canalization) | Madrid & Cantilan, Surigao del Sur | 2015-08-28 | 1st | Surigao del Sur 1st | LF | 16.902 | 222 | 2015-06-11 | 2016-01-18 | (+) 19.96% | O | 0.358 | 0.259 | 0.15 | 0.022 | 0.04 | 0.05 | 87.9% | -
Legacy Construction | 22465 | L | A | MA | GE | Ibajay Eco-Tourism Project (Phase II) | Ibajay, Aklan | 2016-06-23 | 1st | TIEZA | LF | 7.5 | 150 | 2016-03-06 | 2016-08-03 |  | O | 0.376 | 0.203 | 0.15 | 0.03 | 0.07 | 0.05 | 88
LEGACY CONSTRUCTION | 22465 | L | A | MA | GE | Widening of Bacolod Circumferential Road (S), K0003+(-535)-K0003+(-335), K0005+062-K0006+000, Bacolod City | Bacolod City | 2015-11-09 | 1st | Bacolod City DEO | LF | 30.5613 | 225 | 2015-03-02 | 2015-10-12 | (-)1.5% | OG | 0.361 | 0.2 | 0.135 | 0.03 | 0.041 | 0.033 | 80% | 80% Unsatisfactory
LEGACY CONSTRUCTION | 22465 | L | A | MA | GE | Rehabilitation/Reconstruction/Upgrading of Bacolod Circumferential Road (South), K0004+536 - K0004+592, K0010+100 - K0010+400 (Intermittent Section) | Bacolod City | 2015-08-28 | Final | Bacolod City | LF | 7.038 | 75 | 2015-03-02 | 2015-05-15 | 0% | C | 0.457 | 0.133 | 0.3 | - | - | - | 89% | *88.88% Satisfactory
LEGACY CONSTRUCTION / MBM CONSTRUCTION (JV) | 0 | L | A | MA | GB | Construction of New Hospital Building (Phase II), Tapaz District Hospital Brgy. Switch, Tapaz, Capiz | Brgy. Switch, Tapaz, Capiz | 2015-11-13 | Final | Capiz 2nd | LF | 16.9072 | 224 | 2015-06-23 | 2016-02-02 | (+) 7% | C | 0.4 | 0.225 | 0.15 | 0.03 | 0.043 | 0.05 | 89.8% | 89.8% Very Satisfactory
Legazpi Premium Development Corp. / C. T. Leoncio Construction and Trading (JV) |  | L | AA | MA | GB1 | Construction of Passenger Terminal Building | Port of Masbate, Masbate City | 2012-07-06 | 1st | PPA | LF | 29.252 | 270 | 2011-12-07 | 2012-09-01 | 2.06 | O | 0.391 | 0.3 | 0.15 | 0.03 | 0.038 | 0.05 | 95.9 | -
Legazpi Premium Development Corporation | 20701 | L | AA | MB | GE | Replacement/Construction of Ibingan Bridge (BO4179LZ) along Bacon-Sawanga-Prieto Diaz Road (SO3736LZ) | San Ramon, Prieto Diaz, Sorsogon (Sta. 614+095.3-Sta.614+380) | 2014-11-06 | 1st & Final | V | LF | 17.0531 | 202 | 2014-02-13 | 2014-09-02 | 0% | C | 0.474 | 0.133 | 0.3 | - | - | - | 90.7% | 90.70% Very Satisfactory
Legazpi Premium Development Corporation | 20701 | L | AA | MB | GE1 | Cluster 16: Repair/Rehab./Impvt. of Legazpi-Punta de Jesus Rd. (S05860LZ) a)Repair/Rehab.Impvt. of Legazpi-Punta De Jesus Rd. ((Taysan Sect.) K0530+597-K0532+300 w/ exceptions; b)Repair/Rehab.Impvt. of Legazpi-Punta De Jesus Rd. (Taysan-Homapon Sect.) K0535+200-K0536+00 w/ exception | Legazpi City | 2013-08-11 | Final | V | LF | 19.446 | 56 | 2013-01-29 | 2013-03-25 | 25 | C | 0.392 | 0.196 | 0.3 | - | - | - | 88.8 | 88.86% Satisfactory
Legazpi Premium Development Corporation | 20701 | L | AA | MB | GE1 | Rehab./Reconst. Of Damaged Paved Nat'l Rds. (Int.Sect.) Bacon-Sawanga-Prieto Diaz Rd. | Sorsogon | 2013-08-13 | Final | V | LF | 70.792 | 290 | 2012-06-28 | 2013-04-13 | 0 | C | 0.323 | 0.2 | 0.3 | - | - | - | 82.3 | 88.06% Satisfactory
Legazpi Premium Development Corporation | 20701 | L | AA | MB | GE1 | Rehab./Reconst. Of Damaged Paved Nat'l Rds. (IS) Bacon-Sawanga-Prieto Diaz Rd. | Sorsogon | 2012-11-21 | 1st | V | LF | 68.44 | 240 | 2012-06-28 | 2013-02-22 | 0.41 | O | 0.351 | 0.3 | 0.15 | 0.03 | 0.055 | 0.033 | 91.9 | -
Legazpi Premium Development Corporation | 20701 | L | AA | MB | GE1 | Replacement (Temp. to Perm.) of Bridges along Nat'l Rds., Haya Bridge Jct. CCR-Panganiban-Sabloyon Rd. (K0074+830.05-K0074+851.05) | Panganiban, Catanduanes | 2013-07-30 | 1st | V | LF | 11.928 | 154 | 2013-02-15 | 2013-08-22 | -3.83 | O | 0.341 | 0.3 | 0.112 | 0.03 | 0.035 | 0.033 | 85.1 | -
Legazpi Premium Development Corporation | 20701 | L | AA | MB | GE1 | Cluster 16: Repair/Rehab./Impvt. of Legazpi-Punta de Jesus Rd. (S0586LZ) a) Repair/Rehab./Impvt. of Legazpi-Punta de Jesus Rd. (Taysan Sect.) K0530+597-K0532+300 w/ exceptions; b) Repair/Rehab./Impvt. of Legazpi-Punta de Jesus Rd. (Taysan-Homapon Sect.) K0535+200 -K0536+000 w/ exception | Legazpi City | 2013-03-16 | 1st | V | LF | 9.724 | 56 | 2013-01-29 | 2013-03-25 | 21.12 | O | 0.337 | 0.3 | 0.15 | 0.03 | 0.039 | 0.033 | 88.9 | -
Legazpi Premium Development Corporation | 20701 | L | AA | MB | GE1 | Road Upgrading (Gravel to Paved) Catanduanes Circ. Road, K0141+400-K0143+634, Milaviga Sect. | Caramoran, Catanduanes | 2011-08-16 | 1st | V | LF | 45.555 | 240 | 2011-07-04 | 2012-02-28 | 0 | O | 0.375 | 0.07 | 0.15 | 0.03 | 0.028 | 0.05 | 70.3 | -
Legazpi Premium Development Corporation | 20701 |  |  |  |  | Opening/ Impvt. of Sitio Tina-Sitio Nauasan Rd. (Phase I) |  | 2010-02-27 |  | VI |  | 40.515 | 310 |  |  |  | O | 0.382 | 0.3 | 0.129 | 0.02 | 0.028 | 0.017 | 87.6 | -
Legazpi Premium Development Corporation | 20701 |  |  |  |  | Const. of the Extension of Tabaco City Public Market |  | 2010-02-22 |  | V |  | 11.568 | 159 |  |  |  | O | 0.38 | 0.24 | 0.15 | 0.03 | 0.04 | 0.05 | 89 | -
LEGAZPI PREMIUM DEVELOPMENT CORPORATION | 20701 | L | AAA | LA | GE | Asset Preservation of National Road Generated from Pavement Management System/ Highway Development Management 4 (HDM-4) Preventive Maintenance (intermittent section) along Masbate Road | Masbate City | 2015-06-30 | Final | Masbate 1st | LF | 37.947 | 123 | 2014-06-30 | 2014-10-30 | 0% | C | 0.486 | 0.134 | 0.3 | - | - | - | 92% | *92% Very Satisfactory
Lehci Construction | 24196 | L | B | MA | GE | Off-carriageway Improvement Paving of Shoulders (Seal Widening) Palo-Carigara-Ormoc Road (K0948+250-K0951+450, Brgy. San Vicente-Brgy. Abango, Tunga-Barugo | Vicente-Brgy. Abango, Tunga-Barugo | 2014-10-29 | 1st & Final | VIII | LF | 25.2564 | 190 | 2014-03-28 | 2014-10-03 | -13.68% | C | 0.319 | 0.24 | 0.013 | - | - | - | 68.5% | 68.50% Poor
Lehci Construction | 24196 | L | B | MA | GE | Road Upgrading (Gravel to Paved) Bagahupi-Babatngon - Sta. Cruz Barugo, Carigara Road Leyte, KO934+049 - KO935+267.60 ; KO930+639 - KO931+420 | Leyte | 2014-08-09 | 1st & Final | VIII | LF | 39.33 | 221 | 2013-01-28 | 2013-09-04 | 0 | C | 0.448 | 0.133 | 0.3 |  |  |  | 88.1 | 88.10% Satisfactory
Lehci Construction | 24196 | L | B | MA | GE1 | Rd. Upgrading of (Gravel to Paved) Bagahupi-Babatngon-Sta. Cruz-Barugo-Carigara Rd., K0934+049-K0935+267.60; K0930+639-K0931+420 | Leyte | 2013-08-17 | 1st | VIII | LF | 39.33 | 221 | 2013-01-28 | 2013-09-05 | 1.9 | O | 0.385 | 0.178 | 0.15 | 0.023 | 0.035 | 0.05 | 82.1 | -
LEHCI CONSTRUCTION | 24196 | L | B | MA | GE | Off-Carriageway Improvement Jaro - Dagami - Bauen - Lapaz Road, K0969+500 to K0973+400, Leyte | K0969+500 to K0973+400, Leyte | 2015-06-09 | 1st | Leyte Second DEO | LF | 35.819 | 175 | 2015-02-23 | 2015-08-16 | - | O | 0.387 | 0.232 | 0.15 | 0.03 | 0.056 | 0.033 | 88.8% | -
Leza Construction and Supply | 25565 | L | D | SB | GE2 | Const. of Drainage Canal System at Tuliao |  | 2008-11-26 | 1st | I |  | 4.822 | 120 |  |  |  | O | 0.267 | 0.2 | 0.1 | 0.02 | 0.028 | 0.133 | 74.8 | -
LGC Trucking and Construction | 14464 | L | B | MA | GE1 | Const./Rehab. of Rd. Slip along Daang Maharlika (Agusan-Davao Rd.) Salvacion Sect., K1297+572.50-K1297+613.30; K1298+218.30-K1298+272.30 | Prosperidad, Agusan del Sur | 2013-03-20 | Final | XIII | LF | 11.345 | 270 | 2012-05-04 | 2013-01-28 | 15.18 | C | 0.372 | 0.2 | 0.3 | - | - | - | 87.2 | 87.56% Satisfactory
LGC Trucking and Construction | 14464 |  |  |  |  | Const. of MPB (SURSECO-1 Gym), Brgy. San Fernando |  | 2010-03-04 |  | XIII |  | 1.903 | 165 |  |  |  | O | 0.387 | 0.24 | 0.15 | 0.03 | 0.047 | 0.033 | 88.7 | -
LGC Trucking and Construction | 14464 |  |  |  |  | Const. of Flood Control Structures/Shoreline Protection, Guava Jct., Brgy. Poblacion |  | 2010-03-04 |  | XIII |  | 0.954 | 165 |  |  |  | O | 0.36 | 0.24 | 0.15 | 0.03 | 0.047 | 0.05 | 87.7 | -
LGC Trucking and Construction | 14464 | L | B |  |  | Rehab. Of San Jose - Aurora - Lucena Road | Prosperidad, Agusan del Sur | 2012-12-07 | 1st | Agusan del Sur | LF | 31.823 | 180 | 2012-05-21 | 2012-11-16 | -12.89 | O | 0.3474 | 0.244 | 0.0211 | 0.03 | 0.07 | 0.05 | 76.25 | -
LGC Trucking and Construction | 14464 | L | B |  |  | Rehab. Of San Jose - Aurora - Lucena Road | Prosperidad, Agusan del Sur | 2013-05-24 | Final | Agusan del Sur | LF | 34.741 | 365 | 2012-05-21 | 2013-05-20 | 0 | C | 0.49 | 0.2 | 0.3 | - | - | - | 99 | 85.39% Satisfactory
Librius Construction & Supply Corporation | 23580 | L | A | MA | GB | Construction of Two Storey Six Classroom RGR Type SB at Jacobo Zobel Memorial ES, Brgy. Poblacion | Calatagan, Batangas | 2014-08-06 | Final | IV-A | LF | 13.7113 | 180 | 2013-04-17 | 2013-10-13 | 3.33 | C | 0.487 | 0.2 | 0.3 |  |  |  | 98.7 | 89.32% Very Satisfactory
Librius Construction & Supply Corporation (Formerly: Librius Construction & Supply) | 23580 | L | A | MA | GB | Rehabilitation & Reconstruction of MPC Structure (Covered Court) Brgy. Halalang | Taal, Batangas | 2014-10-27 | 1st & Final | IV | LF | 4.7042 | 90 | 2014-04-07 | 2014-07-05 | 0.6% | C | 0.463 | 0.133 | 0.3 | - | - | - | 89.6% | 89.60% Very Satisfactory
Librius Construction & Supply Corporation (Formerly: Librius Construction & Supply) | 23580 | L | A | MA | GB1 | Const. of Two (2) Storey, (6) Cl. RGR Type Sch. Bldg., Jacobo Zobel Memorial Elem. Sch. Brgy. Pob. | Calatagan, Batangas | 2013-07-31 | 1st | IVA | LF | 13.711 | 180 | 2013-04-17 | 2013-10-13 | 6.28 | O | 0.335 | 0.264 | 0.15 | 0.03 | 0.041 | 0.033 | 85.3 | -
Lim General Contractor | 8482 | L | A | MB | GE1 | Conc. of Tablas Circ. Road, San Agustin-Calatrava Road (Can-Omiang-Cabulotan Section) |  | 2009-08-27 | 1st | IVB |  | 19.298 | 180 |  |  |  | O | 0.333 | 0.3 | 0.15 | 0.03 | 0.047 | 0.033 | 89.3 | -
Linear Construction Corporation |  | L | AA |  | GB1 | Const. of 1 Unit 3-Storey School Building | Southville 9, Package 2, Brgy. Pinugay, Baras, Rizal | 2012-08-24 | 1st | NHA | LF | 22.144 | 180 | 2012-03-04 | 2012-08-31 | -6.06 | O | 0.3936 | 0.3 | 0.0894 | 0.03 | 0.055 | 0.05 | 91.8 | -
Linear Construction Corporation | 3575 | L | AA |  | GB1 | Const. of 1 Init 3-Storey School Building | Southville 9, Package 2, Brgy. Pinugay, Baras, Rizal | 2012-05-10 | 1st | NHA | LF | 22.144 | 180 | 2012-03-04 | 2012-08-31 | 5.1 | O | 0.36 | 0.3 | 0.15 | 0.024 | 0.055 | 0.05 | 93.9 | -
Linear Construction Corporation | 3575 |  |  |  |  | Construction of 1 unit 3-Storey, 15-Classroom School Bldg. |  | 2010-06-16 |  | NHA |  | 22.107 | 150 |  |  |  | O | 0.396 | 0.3 | 0 | 0.03 | 0.07 | 0.05 | 84.6 | -
Linear Construction Corporation | 3575 |  |  |  |  | Construction of 1 unit 3-Storey, 15-Classroom School Building |  | 2010-04-12 |  | NHA |  | 21.655 | 249 |  |  |  | O | 0.398 | 0.3 | 0 | 0.03 | 0.07 | 0.05 | 84.8 | -
Linear Construction Corporation | 3575 |  |  |  |  | Construction of Two-Storey Multi-Purpose Center |  | 2010-06-16 |  | NHA |  | 4.989 | 90 |  |  |  | O | 0.4 | 0.3 | 0.075 | 0.03 | 0.07 | 0.05 | 92.5 | -
Linear Construction Corporation | 3575 |  | AA |  |  | Villa Victoria Site 2 | Brgy. 13 Lot 3B, Victorias City, Negros Occidental | 2016-04-02 | 1st | NHA | LF | 198.542 | 325 | 2015-07-07 | 2016-08-18 | 7.4 | O | 0.3054 | 0.2841 | 0.15 | 0.03 | 0.0485 | 0.05 | 86.8 | -
Lisa Construction | 24134 | L | B | MA | GE | Rehab./Reconst./Replacement/Retrofitting of Existing Permanent Bridges, Ft. Magsaysay Br. | Gapan-Fort Magsaysay Road | 2014-11-27 | 1st & Final | III | LF | 9.4348 | 75 | 2014-02-11 | 2014-04-26 | 0% | C | 0.498 | 0.133 | 0.3 | - | - | - | 93.1% | 93.10% Very Satisfactory
Lisa Construction | 24134 | L | B | MA | GE | Preventive Maintenance, Sumacab-San Josef-Bonifacion Road | Cabanatuan City | 2014-09-25 | 1st & Final | Special 3 | LF | 5.9402 | 37 | 2014-04-07 | 2014-05-13 | 0 | C | 0.477 | 0.133 | 0.3 |  |  |  | 91 | 91.00% Very Satisfactory
Lisa Construction | 24134 | L |  |  |  | Balbalungao Small Reservoir Irrigation Project | San Isidro, Lupao, Nueva Ecija | 2015-05-23 | 1st & Final | NIA | L | 1.482 | 153 | 2014-12-29 | 2015-05-31 | 0 | C | 0.3871 | 0.1604 | 0.3 | - | - | - | - | 84.75% Satisfactory
Lisa Construction | 24134 | L | B | MA | GE1 | Cabanatuan City-Carmen Road |  | 2009-06-02 | 1st | III |  | 28.57 | 120 |  |  |  | O | 0.391 | 0.206 | 0.15 | 0.02 | 0.03 | 0.05 | 84.7 | -
LISA CONSTRUCTION | 24134 | L | B | MA | GE | Rehabilitation/Reconstruction of Damaged Paved National Roads Including Drainage of Daang Maharlika Road, Nueva Ecija KO141+000 - KO160+597 - KO161+808, Talavera, Nueva Ecija | Talavera, Nueva Ecija | 2015-09-02 | 1st & Final | Nueva Ecija First DEO | LF | 29.042 | 150 | 2015-03-29 | 2015-08-25 | 13.21% | C | 0.455 | 0.133 | 0.3 | - | - | - | 88.8% | *88.8% Satisfactory
LJPM Builders & Construction Supply | 29981 | L | C | SB | GE | Construction of Road Brgy. Himarco, Palompon | Leyte | 2014-08-07 | 1st & Final | VIII | LF | 2.4127 | 37 | 2014-05-02 | 2014-06-07 | 32.43 | C | 0.405 | 0.133 | 0.3 |  |  |  | 83.8 | 83.80% Satisfactory
LJPM Builders & Construction Supply | 29981 | L | C | SB | GE1 | Rehab./Strengthening of Nailong Bridge 1 along Daang Maharlika, Pres. Roxas | Liloan, Southern Leyte | 2013-03-16 | 1st | VIII | LF | 3.73 | 83 | 2013-01-18 | 2013-04-10 | 1.08 | O | 0.285 | 0.28 | 0.15 | 0.03 | 0.035 | 0.033 | 81.3 | -
LJPM Builders & Construction Supply | 29981 | L | C | SB | GE1 | Rehab./Impvt. of National Road along Amaga-Liloan Road Section |  | 2008-11-21 | 2nd | VIII |  | 3.735 | 180 |  |  |  | O | 0.38 | 0.24 | 0.1 | 0.02 | 0.037 | 0.1 | 87.7 | -
LJPM Builders & Construction Supply | 29981 | L | C | SB | GE | Construction of Drainage Structure along Tanauan-Dagami Road, K0931+900, Brgy. Balilit Section | Dagami, Leyte | 2014-10-29 | 1st & Final | VIII | LF | 6.5754 | 220 | 2014-01-23 | 2014-08-30 | 8.64% | C | 0.42 | 0.133 | 0.3 | - | - | - | 85.3% | 85.30% Satisfactory
LL Construction | 34244 | L | D | SB | GB | Rehabilitation of Multi-Purpose Bldg. at Petit Barracks, Zone 4 | Zone 4, Zamboanga City | 2014-08-05 | 1st | IX | LF | 4.1323 | 126 | 2014-04-14 | 2014-08-17 | 5.01 | O | 0.369 | 0.202 | 0.15 | 0.03 | 0.041 | 0.05 | 84.2 | -
LL CONSTRUCTION | 34244 | L | D | SB | GE | Concreting of Road, Brgy. Dulian, Upper Pasonanca, Zamboanga City | Zamboanga City | 2015-11-19 | Final | Zamboanga City DEO | LF | 2.3578 | 62 | 2015-03-23 | 2015-05-23 | - | C | 0.413 | 0.133 | 0.3 | - | - | - | 84.6% | 84.6% Satisfactory
LLABAN CONSTRUCTION AND SUPPLY ( Formerly: Llaba construction & Trucking) | 29504 | L | B | MA | GE | Widening of National Roads K1620+048-K1621+768 along Davao-Cotabato Road (Jct. Digos-Cotabato Road), Kidapawan City, Limits K1620+048-K1621+768, L=1.72 Km. w/ Exemption (Malamote Br.) Exemption K1620+120+144, L=0.024 Km. | Kidapawan City | 2015-06-04 | 1st | Cotabato 1st DEO | LF | 35.523 | 198 | 2015-03-27 | 2015-10-10 | 0% | O | 0.349 | 0.24 | 0.15 | 0.03 | 0.047 | 0.03 | 84.6% | -
LLABAN CONSTRUCTION AND SUPPLY ( Formerly: Llaban Construction & Trucking) | 29504 | L | B | MA | GE | Rehabilitation/Reconstruction/Replacement/Retrofitting of Existing Permanent Buluan Bridge II along Davao-Cotabato Road (Jct. Digos- Cotabato Section) | Pigcawayan, Cotabato Km. 1711+164- Km 1711+182 (18 l.m.) | 2015-06-06 | Final | Cotabato 2nd DEO | LF | 33.451 | 282 | 2014-03-07 | 2014-12-14 | 0% | C | 0.387 | 0.133 | 0.3 | - | - | - | 82% | *82.6% Satisfactory
LLABAN CONSTRUCTION AND SUPPLY ( Formerly: Llaban Construction & Trucking) | - | L | B | MA | GE | Repair/Rehab./Impvt. Along Midsayap-Makar Road | Midsayap, Cotabato (K1695+000-K1699+500 with exception) | 2015-06-05 | Final | Cotabato 2nd DEO | LF | 11.976 | 104 | 2014-12-30 | 2015-04-13 | 0% | C | 0.391 | 0.133 | 0.3 | - | - | - | 82.4% | *82.4% Satisfactory
Llaban Construction and Supply (Formerly: Llaban Construction & Trucking) | 29504 | L | B | MA | GE | Rehab./Reconst./Replacement/Retrofitting of existing permanent Buluan Bridge II along Davao - Cotabato Road (Jct. Digos - Cotabato Section) Pigcawayan Cotabato, Km. 1711+164 - Km. 1711+182 | Pigcawayan, Cotabato | 2014-10-25 | 1st | XII | LF | 33.4514 | 252 | 2014-03-27 | 2014-12-03 | 0.61% | O | 0.355 | 0.225 | 0.15 | 0.022 | 0.045 | 0.033 | 83% | 83.00% Satisfactory
Llaban Construction and Supply (Formerly: Llaban Construction & Trucking) | 29504 | L | B | MA | GE | Road Upgrading (Gravel to Concrete) along Dualing - New Panay Midsayap Road, Upper Bulanan Section, Km.1714+505 to K1715+009.66 | Midsayap, Cotabato | 2014-08-11 | 1st & Final | XII | LF | 10.9585 | 65 | 2013-11-19 | 2014-01-23 | 2.88 | C | 0.407 | 0.2 | 0.3 |  |  |  | 90.7 | 90.70% Very Satisfactory
Llaban Construction and Supply (Formerly: Llaban Construction & Trucking) | 29504 | L | B | MA | GE | Rehab./Reconst./Replacement /Retrofitting of Existing Permanent Buluan Bridge II along Davao - Cotabato Road (Jct. Digos - Cotabato Section) | Pigcawayan, Cotabato | 2014-08-11 | 1st | XII | LF | 30.5722 | 252 | 2014-03-07 | 2014-11-14 | 0.2 | O | 0.388 | 0.25 | 0.15 | 0.03 | 0.03 | 0.05 | 89.8 | -
LLABAN CONSTRUCTION AND SUPPLY (Formerly: Llaban Construction & Trucking) | 29504 | L | B | MA | GE | Repair/Rehabilitation/Improvement (additional pavement width) Dualing-New Panay-Midsayap Road, ; (0.381 km) Km.1688+(-433) to Km.1691+500 with exception, Sta.Cruz Section, Aleosan, Cotabato | Sta.Cruz Section, Aleosan, Cotabato | 2015-11-12 | 1st | Cotabato Second DEO | LF | 9.8965 | 97 | 2015-08-25 | 2015-11-29 | (+) 1.25% | OG | 0.341 | 0.24 | 0.15 | 0.03 | 0.028 | 0.05 | 83.9% | 83.9% Satisfactory
Llaban Construction and Trucking | 29504 | L |  |  |  | MALITUBOG IRRIGATION PROJECT MIP-LMC-004 Package V | Pikit, Cotabato | 2014-06-06 | 1st & Final | NIA | LF | 37.808 | 503 | 2013-01-15 | 2014-06-02 | 0.91 | C | 0.344 | 0.1999 | 0.3 | - | - | - | 84.39 | 84.39% Satisfactory
Llaban Construction and Trucking | 29504 | L | B | MA | GE1 | Rehab./Reconst./Upgrading along Matalam-M'lang-Bagontapay Jct. Rd. Km.1652+000-Km.1653+855-Km.1655+000 (Clustered) | M'lang, Cotabato | 2013-03-18 | Final | XII | LF | 32.352 | 309 | 2012-01-31 | 2012-12-04 | 7.44 | C | 0.414 | 0.133 | 0.3 | - | - | - | 84.7 | 86.92% Satisfactory
Llaban Construction and Trucking | 29504 | L | B | MA | GE1 | Road Upgrading (Gravel to Conc.) along Kidapawan-Ilomavis Tourist Rd., K1630+000-K1631+820 | Kidapawan City | 2013-03-18 | Final | XII | LF | 39.86 | 320 | 2012-01-31 | 2012-12-15 | 0 | C | 0.401 | 0.133 | 0.3 | - | - | - | 83.4 | 86.70% Satisfactory
LLM Concrete Products | 14235 | L | B | MA | GE | Concrete Revetment on Steel Sheet Piles along Talomo River, Peñano Section, Calinan Districct, Third District, Davao City | Calinan District, Third District, Davao City | 2014-10-20 | 1st | XI | LF | 18.815 | 190 | 2014-08-05 | 2015-02-10 | -4% | O | 0.354 | 0.255 | 0.11 | 0.022 | 0.055 | 0.033 | 82.9% | 82.90% Satisfactory
LLM Concrete Products | 14235 | L | B | SB | GE | Construction of Roads in Kibao, Matanao | Davao del Sur | 2014-10-24 | 1st & Final | XI | LF | 1.8509 | 60 | 2014-04-29 | 2014-06-27 | 3.33% | C | 0.467 | 0.135 | 0.3 | - | - | - | 90.2% | 90.20% Very Satisfactory
LLM Concrete Products | 14235 | L | B | MA | GE | Construction of Concrete Revetment on Steel Sheet Piles at Kalye Apike Protecting Calinan - Baguio - Cadalian Road | Davao City | 2014-08-04 | 1st & Final | XI | LF | 11.7206 | 120 | 2014-02-10 | 2014-06-09 | 0 | C | 0.462 | 0.133 | 0.3 |  |  |  | 89.5 | 89.50% Very Satisfactory
LLM Concrete Products | 14235 | L | B | MA | GE2 | Const. of Drainage along Lapu-Lapu St. | Digos City, Davao del Sur | 2013-03-15 | Final | XI | LF | 8.87 | 150 | 2012-08-13 | 2013-01-09 | 0 | C | 0.456 | 0.133 | 0.3 | - | - | - | 88.9 | 85.84% Satisfactory
LLM CONCRETE PRODUCTS | 14235 | L | B | SB | GE | Tagum City Diversion Road, K1457+(-389) to K1457+(-022) (Widening of Tagum City Diversion Road), Davao del Norte | Davao del Norte | 2015-11-13 | Final | Davao del Norte DEO | LF | 8.734e-06 | 121 | 2015-02-05 | 2015-06-05 | 0 | C | 0.479 | 0.138 | 0.3 | - | - | - | 91.7% | 91.7% Very Satisfactory
LLM CONCRETE PRODUCTS/ P.J. SAN PEDRO CONSTRUCTION AND SUPPLY JOINT VENTURE | JV-13-386 | L | B | MA | GE | Concrete Revetment on Steel Sheet Piles along Lipadas River, Lizada-Marapangi Section | Toril District, Davao City | 2015-06-01 | Final | Davao City 2nd | LF | 27.708 | 216 | 2014-06-23 | 2015-01-24 | 0% | C | 0.438 | 0.133 | 0.3 | - | - | - | 87.1% | *85.06% Satisfactory
LLM Concrete Products//PJ San Pedro Construction and Supply (Joint Venture) | JV-13-836 | L | B | MA | GE | Concrete Revetment on Steel Sheet Piles along Lipadas River, Llizada-Marapangi Section, Toril District, Davao City | Toril District, Davao City | 2014-10-20 | 1st | XI | LF | 27.7083 | 217 | 2014-06-23 | 2015-01-25 | 0.87% | O | 0.377 | 0.207 | 0.15 | 0.015 | 0.055 | 0.033 | 83.7% | 83.70% Satisfactory
LM Construction and General Marketing | 33727 | L | B | MA | GE | Local Infrastructure Program-Construction of Local Road at Brgy. San Vicente I | Bislig City, Surigao del Sur | 2014-10-24 | 1st & Final | XIII | LF | 7.0475 | 92 | 2014-04-29 | 2014-07-29 | 0% | C | 0.393 | 0.2 | 0.235 | - | - | - | 82.8% | 82.80% Satisfactory
LMD Construction | 9410 | L | B | MA | GE | Road Upgrading (Gravel to Paved) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading Paved Road Standard (HDM-4 Project Analysis), Intermittent Sections, Eastern-Bobongan-Sominot-Midsalip-Dumingag Road K1649+549 - K1651+049 | Zamboanga Del Sur | 2014-08-12 | Final | IX | LF | 35.9317 | 165 | 2013-02-18 | 2013-08-01 | 0 | C | 0.398 | 0.2 | 0.3 |  |  |  | 89.8 | 83.71% Satisfactory
LMD Construction | 9410 | L | B | MA | GE | Road Upgrading of (Gravel to Paved) based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standard (HDM-4 Project Analysis) intermittent Section, ZJct. Blancia-Molave-osefina Road, K1684+500 - K1685+607 | Molave, Zamboanga del Sur | 2014-08-12 | Final | IX | LF | 34.8461 | 195 | 2014-02-18 | 2014-08-31 | 0 | C | 0.347 | 0.2 | 0.3 |  |  |  | 84.7 | 82.72% Satisfactory
LMD Construction | 9410 | L | B | MA | GE | Road Upgeading of (Gravel to Paved) Based on Gravel Road Strategies, Traffice Benchmark FOR Upgrading to Paved Road Standard (HDM-4 Project Analysis) Intermittent Section, Jct. Aurora-Ozamis City Road, K1644+000 - K1645+910 | Ramon Magsaysay, Zamboanga del Sur | 2014-08-12 | Final | IX | LF | 44.3693 | 206 | 2013-02-18 | 2013-09-11 | 0 | C | 0.417 | 0.2 | 0.3 |  |  |  | 91.7 | 87.62% Satisfactory
LMD Construction | 9410 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Paved) Int. Sect., Jct. Aurora-Ozamis City Rd., K1644+000-K1645+910 | Ramon Magsaysay, Zamboanga del Sur | 2013-08-17 | 2nd | IX | LF | 44.369 | 206 | 2013-02-18 | 2013-09-11 | 11.7 | O | 0.326 | 0.296 | 0.15 | 0.012 | 0.033 | 0.033 | 85 | -
LMD Construction | 9410 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Paved) Int. Sect., Jct. Aurora-Ozamis City Rd., K1644+000-K1645+910 | Zamboanga del Sur | 2013-03-21 | 1st | IX | LF | 44.369 | 116 | 2013-02-18 | 2013-06-13 | 0.75 | O | 0.367 | 0.225 | 0.15 | 0.03 | 0.043 | 0.033 | 84.8 | -
LMD Construction | 9410 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Paved), Int. Sect., Jct. Blancia-Molave-Josefina Rd., K1684+500-K1685+607 | Zamboanga del Sur | 2013-08-17 | 2nd | IX | LF | 34.846 | 255 | 2013-02-18 | 2013-10-30 | 13.78 | O | 0.302 | 0.254 | 0.15 | 0.03 | 0.028 | 0.033 | 79.7 | -
LMD Construction | 9410 | L | B | MA | GE1 | Road Upgrading (Gravel to Paved), Int. Sect., Eastern Bobongan-Sominot Midsalip-Dumingag Rd., K1649+549-K1651+049 | Zamboanga del Sur | 2013-08-17 | 2nd | IX | LF | 34.732 | 165 | 2013-02-18 | 2013-08-01 | - | O | 0.36 | 0.278 | 0 | 0.024 | 0.033 | 0.033 | 72.8 | -
LMD Construction | 9410 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Paved) Eastern Bobongan-Sominot Midsalip-Dumingag Rd., K1649+549-K1651+049 | Zamboanga del Sur | 2013-03-20 | 1st | IX | LF | 34.732 | 105 | 2013-02-18 | 2013-06-02 | 0.02 | O | 0.379 | 0.225 | 0.15 | 0.03 | 0.048 | 0.033 | 86.5 | -
LMD Construction | 9410 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Paved) Imelda-Bayog-Kumalarang-Lapuyan-Margosatubig Rd., La Victoria Sect., K1755+075.00-K1756+000.00 w/ equation | Imelda, Zamboanga Sibugay | 2013-08-14 | 2nd | IX | LF | 24.635 | 174 | 2013-02-22 | 2013-08-14 | -7.74 | O | 0.253 | 0.3 | 0.073 | 0.03 | 0.028 | 0.033 | 71.7 | -
LMD Construction | 9410 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Paved) Int. Sect., Jct. Blancia-Molave-Josefina Rd, K1684+500-K1685+607 | Zamboanga del Sur | 2013-03-21 | 1st | IX | LF | 33.795 | 105 | 2013-02-18 | 2013-06-02 | 8.68 | O | 0.35 | 0.225 | 0.15 | 0.03 | 0.043 | 0.033 | 83.1 | -
LMD Construction | 9410 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Paved) Imelda-Bayog-Kumalarang-Lapuyan-Margosatubig Rd. La Victoria Sect., K1755+075.00-K1756+000.00 w/ equations | Imelda, Zamboanga Sibugay | 2013-03-18 | 1st | IX | LF | 24.635 | 145 | 2013-02-22 | 2013-07-16 | 10.64 | O | 0.333 | 0.225 | 0.15 | 0.03 | 0.043 | 0.05 | 83.1 | -
LMG CONSTRUCTIO | 5719 | L | B | - | GB | Construction/Completion of Southville 3, Multi-Purpose Building, Brgy. Poblacion, Muntinlupa City | Muntinlupa City | 2015-06-10 | Final | Las Pinas-Muntinlupa | LF | 7.739 | 120 | 2014-09-15 | 2015-01-13 | - | C | 0.499 | 0.133 | 0.3 | - | - | - | 93.2% | *88.79% Satisfactory
LMG Construction | - | L | - | - | - | Construction/Completion of Southville 3, Multi-purpose Building, Barangay Poblacion | Muntinlupa City, Metro Manila | 2014-11-17 | 1st | NCR | LF | 7.739 | 120 | 2014-09-15 | 2015-01-12 | 0.32% | O | 0.339 | 0.24 | 0.15 | 0.03 | 0.06 | 0.05 | 86.9% | 86.90% Satisfactory
LMG Construction | 5719 | L | B | MA |  | Improvement of Lateral A, SDA | Sto. Domingo, Nueva Ecija | 2015-05-23 | 1st | NIA | L | 17.949 | 210 | 2014-07-18 | 2015-02-12 | -33.19 | S | 0.3796 | 0.3 | 0 | 0.015 | 0.0373 | 0.0333 | 76.52 | -
LMG Construction | 5719 | L | B | MA |  | Improvement of Lateral A-Extra, SDA, Talavera & Sto. Domingo | Sto. Domingo, Nueva Ecija | 2015-05-23 | 1st | NIA | L | 17.949 | 210 | 2014-07-18 | 2015-02-12 | -25.82 | S | 0.3796 | 0.3 | 0 | 0.015 | 0.0467 | 0.0333 | 77.46 | -
LMG Construction | [5 empty] | Package X-L: Construction of lateral "N" (Sta. 13+440-Sta. 14+500) and sub-lat. "N-10" (Sta. 0+000-Sta. 1+500) including related structures and supply, delivery and installation of steel gates | Guimba, Nueva Ecija | 2015-02-07 | 1st | NIA | L | 17.141 | 180 | 2014-07-25 | 2015-01-10 | 0.02 | O | 0.3229 | 0.292 | 0.15 | 0.03 | 0.014 | 0.05 | 85.89 | -
LMG Construction/Peter G. Chua Builders Joint Venture | JV-13-832 | L | B | MA | GE | Rehabilitation/Drainage Improvement and Concreting along Mo. Ignacio St. | Quezon City | 2014-11-27 | 1st | NCR | LF | 17.9716 | 198 | 2014-08-05 | 2015-02-18 | 0.82% | O | 0.352 | 0.292 | 0.15 | 0.03 | 0.05 | 0.033 | 90.7% | 90.70% Very Satisfactory
LMG CONSTRUCTION/PETER G. CHUA BUILDERS JOINT VENTURE | JV-13-832 | L | B | MA | GE | Rehabilitation/Drainage Improvement and Concreting along Mo. Ignacia St., Quezon City | Quezon City | 2015-06-03 | Final | Quezon City 2nd | LF | 17.972 | 228 | 2014-08-05 | 2015-03-19 | - | C | 0.488 | 0.133 | 0.3 | - | - | - | 92.1% | *91.26% Very Satisfactory
LOC CONSTRUCTION AND SUPPLY | 34764 | L | C | SB | GB | Construction of Alno MPB, La Trinidad (Phase 2) | Alno, La Trinidad, Benguet | 2015-06-02 | 1st | Benguet 1st DEO | LF | 1.867 | 120 | 2015-02-20 | 2015-06-19 | (-) 0.59 | O | 0.363 | 0.3 | 0.144 | 0.02 | 0.051 | 0.05 | 92.8% | -
Long Island Builders & Construction | 31730 | L | C | SB | GE1 | Repair/Maint. of Rd. Slip along Pagadian City-Zamboanga City Rd., K1722+276-K1722+430 Kamarin Sect. | Zamboanga City | 2013-08-16 | Final | IX | LF | 3.32 | 121 | 2012-10-11 | 2013-02-08 | 0 | C | 0.354 | 0.2 | 0.3 | - | - | - | 85.4 | 83.78% Satisfactory
Long Island Builders & Construction | 31730 | L | C | SB | GE1 | Repair/Restoration of Damage Rd. Slope along Jct. Dumalinao-Margosatubig Rd. (Tikwas Sect.) Int. Sect., K1683+240-K1684+000 | Dumalinao, Zamboanga del Sur | 2013-03-19 | Final | IX | LF | 3.517 | 93 | 2012-10-24 | 2013-01-25 | 0 | C | 0.426 | 0.133 | 0.3 | - | - | - | 85.9 | 87.82% Satisfactory
Long Island Builders & Construction | 31730 | L | C | SB | GE2 | Repair & Maint. of Balongating River Control (Downstream/Left Bank Slope) Balongating, Guipos | Zamboanga del Sur | 2013-03-19 | Final | IX | LF | 1.397 | 116 | 2012-10-24 | 2013-02-16 | -10.34 | C | 0.477 | 0.2 | 0 | - | - | - | 67.7 | 70.64% Poor
LONG ISLAND BUILDERS & CONSTRUCTION | 31730 | L | B | SB | GE | Construction/Repair/Rehabilitation/Improvement of Various Infrastructure Including Local Projects-Payapa at Masaganang Pamayanan (PAMANA) Program-Construction of Kaliantana Bridge and Approaches, Naga, Zamboanga Sibugay | Naga, Zamboanga Sibugay | 2015-08-25 | 1st | Zamboanga Sibugay 2nd | LF | 46.342 | 345 | 2015-04-21 | 2016-03-31 | (-)3.76 | O | 0.376 | 0.24 | 0.112 | 0.015 | 0.042 | 0.033 | 81.8% | -
LONG ISLAND BUILDERS & CONSTRUCTION | 31730 | L | B | MA | GB | Completion of Multi-Purpose Building at Brgy. Candiis, Malangas, Zamboanga Sibugay | Malangas, Zamboanga Sibugay | 2015-11-11 | Final | Zamboanga Sibugay 1st DEO | LF | 2.9405 | 75 | 2015-02-13 | 2015-04-28 | 0.20% | C | 0.479 | 0.133 | 0.3 | - | - | - | 91.2% | 91.2% Very Satisfactory
LONG ISLAND BUILDERS & CONSTRUCTION | 31730 | L | B | SB | GE | Construction/Repair/Rehabilitation/Improvement of Various Infrastructure Including Local Projects-Payapa at Masaganang Pamayanan (PAMANA) Program - Construction of Kalintana Bridge and Approaches, Naga, Zamboanga Sibugay | Naga, Zamboanga Sibugay | 2015-11-10 | 2nd | Zamboanga Sibugay 2nd DEO | LF | 46.342 | 345 | 2015-04-21 | 2016-03-30 | -1.67% | OG | 0.366 | 0.24 | 0.133 | 0.024 | 0.042 | 0.033 | 83.8% | 83.8% Satisfactory
Long Island Builders & Construction | 31730 | L | C | SB | GE1 | Repair/Maint. of Slip Shoulder along Pagadian City-Zamboanga City Rd., K1722+276-K1733+430, Kamarin Sect. | Kumalarang, Zamboanga del Sur | 2012-11-21 | 1st | IX | LF | 3.32 | 54 | 2012-10-11 | 2012-12-03 | -6.1 | O | 0.4 | 0.228 | 0.089 | 0.03 | 0.047 | 0.033 | 82.7 | -
Long Island Builders & Construction / NFH Construction & Supply (JV) | JV-11-269 | L | AAA | LB | GE1 | Rd. Upgrading (Gravel to Concrete) , Sindangan-Lakewood Nat'l Secondary Rd., (Lakewood Sect.) K1716+(-)234-K1716+820 | Lakewood, Zamboanga del Sur | 2012-11-21 | 2nd | IX | LF | 35.494 | 240 | 2012-02-01 | 2012-09-28 | - | O | 0.321 | 0.228 | 0 | 0.023 | 0.048 | 0.033 | 65.3 | -
Long Island Builders & Construction / NFH Construction & Supply (JV) | JV-11-269 | L | AAA | LB | GE1 | Rd. Upgrading (Gravel to Concrete), Sindangan-Lakewood Nat'l Secondary Rd. (Lakewood Sect.) K1716+(-234)-K1716+820 | Lakewood, Zamboanga del Sur | 2012-08-16 | 1st | IX | LF | 35.494 | 240 | 2012-02-01 | 2012-09-28 | 0.02 | O | 0.361 | 0.24 | 0.15 | 0.03 | 0.027 | 0.033 | 84.1 | -
Longwide Builders | 20196 |  |  |  |  | Repair/Rehab. of Damaged Pavement of Quezon Airport Road |  | 2010-06-09 |  | XIII |  | 7.287 | 129 |  |  |  | O | 0.329 | 0.287 | 0.15 | 0.03 | 0.04 | 0.033 | 86.9 | -
Lorenzo Construction and Development Corporation | 4284 | L | AAA | LB | GE1 | Impvt./Rehab. of Gapan-San Fernando-Olongapo Road |  | 2009-09-05 | 2nd | III |  | 42.155 | 180 |  |  |  | O | 0.224 | 0.3 | 0.15 | 0.03 | 0.05 | 0.033 | 78.7 | -
Lorenzo Construction and Development Corporation | 4284 | L | AAA |  |  | Package X-A: Construction of Super Diversion Canal (Sta. 41+560-Sta. 42+920); Lateral "N" and sub-laterals including related structures and supply, delivery and installation of steel gates | Talugtug & Guimba, Nueva Ecija | 2015-02-07 | 1st | NIA | L | 352.781 | 240 | 2014-07-24 | 2015-03-20 | 19.06 | O | 0.3586 | 0.2801 | 0.15 | 0.03 | 0.014 | 0.05 | 88.27 | -
Lorenzo Construction and Development Corporation | 4284 | L | AAA | LB | GE1 | Impvt./Rehab. of Gapan-San Fernando-Olongapo Road |  | 2009-06-03 | 1st | III |  | 42.155 | 180 |  |  |  | O | 0.317 | 0.3 | 0.15 | 0.03 | 0.03 | 0.05 | 87.7 | -
Lotiff Construction | 21962 | L | B | MA | GE1 | Rehab. of Mainit Sect., Tanjay, Dumaguete North Rd., Km.34+000 - Km.35+000 | Tanjay City, Negros Oriental | 2011-04-05 | 1st | VII | LF | 19.27 | 247 | 2010-12-17 | 2011-08-21 | 7.88 | O | 0.325 | 0.257 | 0.15 | 0.023 | 0.055 | 0.05 | 86 | -
Lotrim Construction | 12273 | L | A | MB | GB1 | Construction of DOST Caraga S & T Center |  | 2009-06-18 | 1st | DOST |  | 14.233 | 345 |  |  |  | O | 0.367 | 0.208 | 0.13 | 0.03 | 0.06 | 0.03 | 82.5 | -
Lotrim Construction, Incorporated (Formerly: Lotrim Construction) | 12273 | L | A | MA | GE | Widening of Calinan-Baguio-Cadalian Road, Baguio District km. 1688+302 to km. 1689+465 | Davao City | 2014-08-05 | Final | XI | LF | 15.2226 | 209 | 2013-02-26 | 2013-08-23 | 0 | C | 0.408 | 0.133 | 0.3 |  |  |  | 84.1 | 85.06% Satisfactory
Lotrim Construction, Incorporated (Formerly: Lotrim Construction) | 12273 | L | A | MA | GE1 | Widening of Calinan-Baguio-Cadalian Rd., Baguio District Km.1688+302-Km.1689+465 | Davao City | 2013-08-06 | 1st | XI | LF | 15.223 | 209 | 2013-02-26 | 2013-09-22 | -0.1 | O | 0.322 | 0.3 | 0.149 | 0.03 | 0.023 | 0.033 | 85.7 | -
Lotrim Construction, Incorporated (Formerly: Lotrim Construction) | 12273 | L | A | MA | GE | Improvement of JNR Mabuhay-Mabunga-Union-JNR Poblacion Road, MMURNEC ARC | Bansalan, Davao del Sur | 2014-08-06 | Final | XI | LF | 27.6639 | 245 | 2013-02-04 | 2013-10-07 | 0 | C | 0.318 | 0.19 | 0.3 |  |  |  | 80.8 | 82.66% Satisfactory
Lotrim Construction, Incorporated (Formerly: Lotrim Construction) | 12273 | L | A | MA | GE1 | Impv't. of JNR Mabuhay-Mabunga-Union-JNR Pob. Rd. MMURNEC ARC | Bansalan, Davao del Sur | 2013-08-09 | 1st | XI | LF | 27.664 | 214 | 2013-02-04 | 2013-09-06 | 1.17 | O | 0.279 | 0.3 | 0.15 | 0.03 | 0.03 | 0.05 | 83.9 | -
Lourbel Construction & Supply | 31370 | L | D | SB | GE | Improvement and Beautification of Kalayaan Park | Barriada, Gogon, Legazpi City, Albay | 2014-01-29 | Final | TIEZA | LF | 9.757 | 180 | 2014-01-23 | 2014-08-10 | 0 | C | 0.408 | 0.171 | 0.3 |  |  |  | 87.9 | 87.90% Satisfactory
Lourbel Construction & Supply |  | L |  |  |  | Improvement and Beautification of Kalayaan Park | Barriada, Gogon, Legazpi City, Albay | 2014-01-29 | 1st & Final | TIEZA | LF | 9.757 | 180 | 2013-01-23 | 2013-08-10 | 0 | C | 0.408 | 0.171 | 0.3 | - | - | - | 87.9 | 87.90% Satisfactory
Lourel Design & Construction |  | L |  |  |  | Development of Tibolo Eco-Cultural Village | Sta. Cruz, Davao del Sur | 2014-04-03 | 1st & Final | TIEZA | LF | 10.077 | 210 | 2013-01-24 | 2013-08-21 | 0 | C | 0.44 | 0.161 | 0.3 | - | - | - | 90.1 | 90.10% Very Satisfactory
Lourel Design & Construction | 17099 |  |  |  |  | Asphalt Overlay/Reblocking of Midsayap-Marbel Road, Km. Sta. 1779+000-Km. Sta. 1786+000, Dumadalig-New Iloilo Section |  | 2010-03-05 |  | XII |  | 9.649 | 110 |  |  |  | O | 0.306 | 0.3 | 0.15 | 0.023 | 0.05 | 0.033 | 86.2 | -
Lourel Design & Construction | 17099 |  |  |  |  | Asphalt Overlay/Reblocking of Marbel-Makar Rd., Km. Sta. 1701+000-Km. Sta. 1707+000, Sarawa - Bo. 6 Section |  | 2010-03-05 |  | XII |  | 9.644 | 110 |  |  |  | O | 0.314 | 0.286 | 0.15 | 0.023 | 0.05 | 0.033 | 85.6 | -
Lourel Design & Construction | 17099 | L | A | SB | GB | Development of Tibolo Eco-Cultural Village | Sta. Cruz, Davao del Sur | 2014-04-03 | Final | TIEZA | LF | 10.077 | 210 | 2013-01-24 | 2013-08-21 | 0 | C | 0.44 | 0.161 | 0.3 |  |  |  | 90.1 | 90.10% Very Satisfactory
Lourel Design & Construction | 17099 | L | A | SB | GB | Lake Lahit Sebu Development | Lake Sebu, South Cotabato | 2014-04-08 | Final | TIEZA | LF | 12.487 | 210 | 2013-02-27 | 2013-09-26 | 0 | C | 0.453 | 0.191 | 0.3 |  |  |  | 94.4 | 94.40% Very Satisfactory
Lourel Design & Construction | 17099 | L | A | SB | GB | Nasugbu Mini Convention and Visitors Center (Phase 1) | Nasugbu, Batanga | 2014-04-16 | Final | TIEZA | LF | 14.983 | 240 | 2014-05-10 | 2014-01-04 | 0 | C | 0.482 | 0.2 | 0.3 |  |  |  | 98.2 | 98.20% Outstanding
Lourel Design & Construction | 17099 | L | A | SB | GB | Bulusan Lake Development Project Installation of Underground Primary Lines | Bulusan Lake, Brgy. San Roque, Bulusan, Sorsoogon | 2014-12-16 | Final | TIEZA | LF | 10.891 | 105 | 2014-04-19 | 2014-11-10 | 0 | C | 0.45 | 0.2 | 0.3 |  |  |  | 95 | 95.00% Very Satisfactory
Lourel Development Corporation | 17099 | L | A | MA | GB | Alburquerque Sanitary Landfill (Phase 3) | Brgy. Dangay, Alburquerque, Bohol | 2015-03-17 | 1st | TIEZA | LF | 55.8 | 210 | 2014-09-15 | 2015-04-12 | -21.3 | O | 0.383 | 0.294 | 0 | 0.03 | 0.045 | 0.033 | 78.5 | -
Lourel Development Corporation | 17099 | L | A | MA | GB | Rehabilitation of Corregidor Lighthouse | Corregidor Island, Cavite City, Cavite | 2014-10-30 | Final | TIEZA | LF | 24.979 | 60 | 2013-11-27 | 2014-01-25 | 0 | C | 0.486 | 0.198 | 0.3 |  |  |  | 98.15 | 98.15% Outstanding
LOUREL DEVELOPMENT CORPORATION | 17099 | L | A | SB | GB | Alburquerque Sanitary Landfill Phase III | Alburquerque, Bohol | 2015-09-10 | 2nd | TIEZA | LF | 59 | 255 | 2014-09-15 | 2015-09-21 | 0 | O | 0.307 | 0.292 | 0.15 | 0.03 | 0.044 | 0.03 | 85.3 | -
Lourel Development Corporation | 17099 | L | A | MA | GB | Alburquerque Sanitary Landfill (Phase 3) | Brgy. Dangay, Alburquerque, Bohol | 2016-01-12 | Final | TIEZA | LF | 61 | 285 | 2014-09-15 | 2015-10-21 |  | C | 0.426 | 0.2 | 0.3 |  |  |  | 92.6 | 86.17 Satisfactory
LSD CONSTRUCTION & SUPPLIES/3K ROCK ENGINEERING -Joint Venture | JV-13-395 | L | AAA | MB | GE | Construction of La Trinidad Flood Control System, La Trinidad, Benguet | La Trinidad, Benguet | 2015-09-03 | 1st & Final | Benguet 1st DEO | LF | 47.499 | 433 | 2014-01-31 | 2015-04-08 | 0% | C | 0.426 | 0.181 | 0.3 | - | - | - | 90.7% | *90.7% Very Satisfactory
LSD Construction and Supplies | 8980 | L | AAA | LB | GE | Construction of Drainage System along Baguio-Bua-Itogon Road, K0254+(-655) To K0268+055 (v.s.), Itogon, Benguet | Itogon, Benguet | 2014-08-14 | Final | CAR | LF | 18.5565 | 180 | 2013-03-23 | 2013-09-18 | 0 | C | 0.452 | 0.133 | 0.3 |  |  |  | 88.5 | 86.82% Satisfactory
LSD Construction and Supplies | 8980 | L | AAA | LB | GE1 | Rd. Upgrading (Gravel to Concrete) along Gurel-Bokod-Kabayan-Buguias-Abatan Rd., K0322+491-K0338+760 (IS) Kabayan Sect. | Kabayan, Benguet | 2012-07-31 | 1st | CAR | LF | 95.365 | 359 | 2011-09-05 | 2012-08-29 | -12.4 | O | 0.313 | 0.3 | 0.026 | 0.008 | 0.028 | 0.033 | 70.8 | -
LSD Construction and Supplies / C.M Dancel Construction and Supply Joint Venture | JV-08-315 |  |  |  |  | Rehab./Reconst./Upgrading of Laoag-Sarrat-Piddig-Solsona Road |  | 2010-02-24 |  | I |  | 134.537 | 330 |  |  |  | O | 0.258 | 0.273 | 0.055 | 0.03 | 0.051 | 0.033 | 70 | -
LSD Construction and Supply | 8980 |  | AAA |  |  | Housing Construction & Land Development | Capoyuan Homes, Site 2 | 2016-04-22 | 1st | NHA | LF | 162.929 | 285 | 2015-04-30 | 2016-04-27 | 75.4 | O | 0.378 | 0.3 | 0 | 0.03 | 0.065 | 0.033 | 80.6 | -
LTDL BUILDERS | 38371 | L | D | SB | GE | Construction of Grouted Riprap along Nangka River,Balimbing Street, Brgy. Nangka, Marikina City | Marikina City | 2015-03-16 | Final | Metro Manila 1st DEO | LF | 3.08 | 60 | 2015-03-16 | 2015-05-14 | - | C | 0.466 | 0.133 | 0.3 | - | - | - | 89.9% | *89.9% Very Satisfactory
LTS Builders and Construction Supply | 33473 | L | D | SB | GB | Construction of Elementary/Secondary School Buildings | San Miguel, Bohol | 2014-08-11 | Final | VII | LF | 5.871 | 160 | 2013-03-25 | 2013-08-31 | 0 | C | 0.451 | 0.157 | 0.3 |  |  |  | 90.8 | 83.87% Satisfactory
LTS Builders and Construction Supply | 33473 | L | D | SB | GB1 | Const. of San Miguel Technical Vocational Sch. | San Miguel, Bohol | 2013-08-19 | 1st | VII | LF | 4.55 | 160 | 2013-03-25 | 2013-08-31 | -14.77 | O | 0.397 | 0.3 | 0.002 | 0.03 | 0.047 | 0.033 | 80.9 | -
LTS Builders and Construction Supply | 33473 | L | C | SB | GB1 | Const. of 2 CL School Building with toilet (7mx18m) Policarpio Dano H/S |  | 2009-09-05 | 1st | VII |  | 1.132 | 90 |  |  |  | O | 0.4 | 0.24 | 0.15 | 0.03 | 0.037 | 0.033 | 89 | -
Lucban Builders & Construction Supply Incorporated | 31336 | L | B | SB | GB1 | Const. of DPWH Building @ DPWH Quezon 1st DEO, Brgy. Abang |  | 2009-05-29 | 1st | IV-A |  | 4.148 | 150 |  |  |  | O | 0.36 | 0.24 | 0.15 | 0.03 | 0.023 | 0.033 | 83.6 | -
Luckwell Construction | 17510 | L | AA |  |  | MATNOG PORT EXPANSION PROJECT | PORT OF MATNOG, MATNOG, SORSOGON | 2014-05-23 | 3rd & Final | PPA | LF | 192.699 | 711 | 2012-03-06 | 2014-02-14 | 0 | C | 0.4398 | 0.1775 | 0.3 | - | - | - | - | 88.39% Satisfactory
Luckwell Construction | 17510 | L | AAA | LB |  | PORT OF GLAN IMPROVEMENT PROJECT | GLAN PORT, SARANGANI PROVINCE | 2015-10-09 | 1st | PPA | LF | 72.264 | 330 | 2014-12-10 | 2015-11-04 | 0.653 | O | 0.3914 | 0.2679 | 0.15 | 0.03 | 0.0646 | 0.05 | 95.39 | -
Luckwell Construction | 17510 | L | AAA |  |  | Repair of concrete pavement and gaps of PSC sheet piles and concrete blocks along Ro-Ro ramp at Port of Lamao, Limay, Bataan | Port of Lamao, Bataan | 2015-06-26 | 1st & Final | PPA | LF | 11.373 | 130 | 2015-01-16 | 2015-05-24 | 7.64 | C | 0.463 | 0.173 | 0.3 | - | - | - | 93.6 | 93.60% Very Satisfactory
Luckwell Construction | 17510 | L | AA |  |  | Construction of Back-Up Area and Widening of Causeway | Port of Catagbacan, Bohol | 2015-04-10 | 2nd & Final | PPA | L | 51.947 | 519 | 2013-05-23 | 2014-10-23 | 0 | C | 0.444 | 0.2 | 0.3 | - | - | - | - | 95.68% Very Satisfactory
Luckwell Construction | 15710 | L | AAA | LB |  | Port of Glan Improvement Project | Port of Glan, Sarangani Province | 2016-01-28 | Final | PPA | LF | 72.264 | 330 | 2014-12-10 | 2015-11-04 | 0 | F | 0.4999 | 0.2 | 0.3 | - | - | - | 99.99 | 97.20% Outstanding
Luck-Well Construction | 17510 | L | AA |  | GE5 | Construction of Back-Up Area and Widening of Causeway | Catagbacan, Port Bohol | 2014-05-28 | 1st | PPA | LF | 51.57 | 300 | 2013-05-23 | 2014-07-14 | 0.334 | O | 0.393 | 0.3 | 0.15 | 0.018 | 0.065 | 0.05 | 97.6 | -
Luck-Well Construction | 17510 |  |  |  |  | Paving of the Newly Constructed Back-up Area Project |  | 04/20-23/10 |  | PPA |  | 47.305 | 300 |  |  |  | O | 0.3657 | 0.3 | 0.1256 | 0.024 | 0.06 | 0.05 | 92.53 | -
Luck-Well Construction | 17510 | L | AA |  | GE5 | Repair of Old Wharf, Port of Danao | Escalante City, Negros Occidental | 2012-09-12 | 1st | PPA | LF | 11.985 | 200 | 2012-02-26 | 2012-09-12 | 0.67 | O | 0.357 | 0.3 | 0.15 | 0.03 | 0.047 | 0.017 | 90.1 | -
Luck-Well Construction | 17510 | L | AA |  | GE5 | Matnog Port Expansion Project | Port of Matnog, Sorsogon | 2013-03-08 | 1st | PPA | LF | 185.815 | 450 | 2012-03-06 | 2013-05-29 | -19.19 | O | 0.387 | 0.25 | 0 | 0.03 | 0.056 | 0.05 | 77.3 | -
Luck-Well Construction | 17510 | L | AA |  | GE5 | Matnog Port Expansion Project | Port of Matnog, Sorsogon | 2013-05-24 | 2nd | PPA | LF | 185.815 | 450 | 2012-03-06 | 2013-05-29 | -9.08 | O | 0.398 | 0.3 | 0.059 | 0.03 | 0.07 | 0.05 | 90.7 | -
Lucky Star Construction and Trading | 2011-0461 | L | AA |  |  | Construction of PSHSCLC ALA Building II, Phase I | Clark Polytechnique Compound Jose Abad Santos Ave., Clark FreePort Zone, Pampanga | 2014-09-11 | Final | DOST | L | 28.086 | 240 | 2013-09-06 | 2014-09-09 | 0 | C | 0.488 | 0.2 | 0.3 | - | - | - | 98.8 | 96.14% Outstanding
Lucky Star Construction and Trading | 2011-0461 | L | AA |  |  | Cons. Of PSHSCLC ALA Building II, Phase I-Lot 2 | Clark Polytechnique Compound Jose Abad Santos Ave., Clark Free PortZone, Pampanga | 2014-09-11 | Final | DOST | L | 8.516 | 120 | 2014-02-03 | 2014-06-24 | 0 | C | 0.445 | 0.2 | 0.3 | - | - | - | 94.5 | 94.60% Very Satisfactory
Lucky Star Construction and Trading | 2011-0461 | L | AA |  |  | Competion of PSHS CLC Building I Phase II | Clark Polytechnic Compound, Jose Abad Santos Ave. Clark, Freeport Zone, Pampanga | 2014-12-18 | Final | DOST | L | 10.238 | 230 | 2014-04-09 | 2014-11-25 | 0 | C | 0.482 | 0.2 | 0.3 | - | - | - | 98.2 | 97.01% Outstanding
Lug Konstract | 33783 | L | D | SB | GE2 | Const./Impv't. of Carigara Revetment | Carigara, Leyte | 2013-03-12 | 1st | VIII | LF | 5.43 | 180 | 2012-10-24 | 2013-04-21 | 8.89 | O | 0.343 | 0.24 | 0.15 | 0.03 | 0.06 | 0.05 | 87.3 | -
Lumel Glenn Construction |  | L |  |  | GE | Construction/Rehabilitation of Sinugdan River Control, Mansalay, Oriental Mindoro | Mansalay, Oriental Mindoro | 2014-08-13 | 1st & Final | IV-B | LF | 9.0957 | 112 | 2014-02-12 | 2014-06-03 | 0 | C | 0.42 | 0.133 | 0.3 |  |  |  | 85.3 | 85.30% Satisfactory
LUMEL GLENN CONSTRUCTION | 26817 | L | B | MA | GE | Construction of Gabions Revetment , Orconuma River Control (Upstream) | Bongabong, Oriental Mindoro | 2015-06-11 | Final | Southern Mindoro DEO | LF | 9.261 | 89 | 2015-02-20 | 2015-05-19 | 0% | C | 0.486 | 0.133 | 0.3 | - | - | - | 91.9% | *91.9% Very Satisfactory
LUMEL GLENN CONSTRUCTION | 26817 | L | B | MA | GE | Upgrading/Conc. of National Rd. (Cawacat Jct.) Balatasan leading to White Sand Coves and various beaches | Bulalacao, Oriental Mindoro | 2015-11-18 | 1st | Southern Mindoro DEO | LF | 36.4173 | 320 | 2015-08-13 | 2016-06-27 | 0.1532 | OG | 0.376 | 0.235 | 0.15 | 0.018 | 0.042 | 0.05 | 87.1% | 87.1% Satisfactory
LUMEL GLENN CONSTRUCTION | 26817 | L | B | MA | GE | Construction of Roads, Madrid Blvd., Brgy. Marfrancisco and Zone 3, Pinamalayan, Oriental Mindoro | Pinamalayan, Oriental Mindoro | 2015-08-28 | 1st & Final | Southern Mindoro DEO | LF | 9.288 | 147 | 2015-03-24 | 2015-08-17 | 11.5% | C | 0.446 | 0.133 | 0.3 | - | - | - | 87.9% | *87.9% Satisfactory
LUZVIMINDA Engineering | 13664 |  |  |  |  | Const. of Back-up Area, Roro Ramp, Site Development and Cargo Shed | Port of Dapa, Siargao Island, Surigao del Norte | 2016-09-09 | 1st | PPA | LF | 45.531 | 724 | 2014-07-14 | 2016-07-06 | -14.46 | O | 0.386 | 0.297 | 0.005 | 0.024 | 0.061 | 0.05 | 82.3 | -
LVRO Construction & Supply | 18116 | L | B | MA | GE1 | Repair/Rehab. along Dinagat-Loreto Road |  | 2009-03-04 | 2nd | XIII |  | 9.649 | 190 |  |  |  | O | 0.372 | 0.282 | 0.082 | 0.03 | 0.035 | 0.033 | #VALUE! | -
LVRO Construction & Supply | 18116 | L | B | MA | GE1 | Repair/Rehab. Along Dinagat-Loreto Road |  | 2008-11-19 | 1st | XIII |  | 9.649 | 160 |  |  |  | O | 0.307 | 0.168 | 0.1 | 0.023 | 0.038 | 0.1 | 73.6 | -
LVRO Construction & Supply | 18116 | L | B | MA | GE1 | Rehab./Reconstruction of Damaged Paved along Dinagat-Loreto Road |  | 2009-03-04 | 1st | XIII |  | 7.086 | 225 |  |  |  | O | 0.368 | 0.24 | 0.15 | 0.03 | 0.035 | 0.05 | #VALUE! | -
LVRO Construction & Supply | 18116 | L | B | MA | GE1 | Const. of Aguntayan-Hilong-Hilong FMR |  | 2009-05-26 | 1st | XIII |  | 8.473 | 175 |  |  |  | O | 0.39 | 0.274 | 0.15 | 0.03 | 0.047 | 0.033 | 92.4 | -
LVRO Construction & Supply | 18116 | L | B | SB | GE1 | Const./Rehab. of Agutayan-Hilong-hilong Rd.(Phase II) |  | 2009-09-01 | 1st | XIII |  | 4.72 | 90 |  |  |  | O | 0.388 | 0.215 | 0.15 | 0.03 | 0.06 | 0.033 | 87.6 | -
LVRO Construction and Supply | 18116 | L | B | MA | GE1 | Impvt./Upgrading (Gravel to Concrete)- NRJ Tagcatong-Vinapor Rd. | Carmen, Agusan del Sur | 2013-08-06 | 2nd | XIII | LF | 27.927 | 200 | 2013-01-24 | 2013-08-11 | -0.53 | O | 0.3 | 0.204 | 0.145 | 0.03 | 0.025 | 0.033 | 73.7 | -
LVRO Construction and Supply | 18116 | L | B | MA | GE1 | Impv't./Upgrading (Gravel to Concrete) - NRJ Tagcatong-Vinapor Rd. | Carmen, Agusan del Norte | 2013-03-12 | 1st | XIII | LF | 27.927 | 170 | 2013-01-24 | 2013-07-13 | 6.3 | O | 0.347 | 0.295 | 0.15 | 0.02 | 0.025 | 0.033 | 87 | -
LVRO Construction and Supply | 18116 | L | B | MA | GE1 | Conc. of Jct. Magsaysay-Cagdianao Rd. | Dinagat Islands | 2013-03-13 | 3rd | XIII | LF | 34.685 | 335 | 2012-02-28 | 2013-01-27 | - | O | 0.306 | 0.24 | 0 | 0.03 | 0.045 | 0.033 | 65.4 | -
LVRO Construction and Supply | 18116 | L | B | MA | GE1 | Conc. of Jct. Magsaysay-Cagdianao Rd. | Dinagat, Dinagat Islands | 2012-11-22 | 2nd | XIII | LF | 34.685 | 305 | 2012-02-28 | 2012-12-28 | -6.95 | O | 0.37 | 0.237 | 0.08 | 0.03 | 0.05 | 0.033 | 80 | -
LVRO Construction and Supply | 18116 | L | B | MA | GE1 | Conc. of Jct. Magsaysay-Cagdianao Road | Dinagat, Dinagat Islands | 2012-08-10 | 1st | XIII | LF | 31.813 | 270 | 2012-02-28 | 2012-11-23 | 1.36 | O | 0.343 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 86.3 | -
LVRO Construction and Supply | 18116 | L | B | MA | GE1 | Replacement of Maatas Bridge I along Jct. Magsaysay-Cagdianao Rd. | Dinagat Islands | 2013-03-13 | Final | XIII | LF | 6.296 | 195 | 2012-03-20 | 2012-09-30 | - | C | 0.396 | 0.2 | 0 | - | - | - | 59.6 | 68.27% Poor
LVRO Construction and Supply | 18116 | L | B | MA | GE | Impvt./Upgrading (Gravel to Paved) of NRJ - Tagcatong - Vinapor Rd. | Carmen, Agusan del Sur | 2014-08-06 | Final | XIII | LF | 22.9268 | 200 | 2013-01-24 | 2013-08-11 | 2.22 | C | 0.247 | 0.2 | 0.3 |  |  |  | 74.7 | 78.09% Unsatisfactory
LYD Construction | 37342 | L | D | SB | GB | Construction and Rehabilitation of Multi-Purpose Building | Damilag, Manolo Fortich, Bukidnon | 2014-08-09 | 1st | X | LF | 1.98 | 91 | 2014-05-28 | 2014-08-26 | 2.61 | O | 0.371 | 0.3 | 0.15 | 0.03 | 0.053 | 0.05 | 95.4 | -
M M Construction | 12012 |  |  |  |  | Rehab./Reconst./Upgrading of Damaged Paved National Rd. along Daang Maharlika Solano-Diadi Sect. w/ exception |  | 2010-06-10 |  | II |  | 9.645 | 80 |  |  |  | O | 0.36 | 0.3 | 0.15 | 0.03 | 0.042 | 0.033 | 91.5 | -
M M Construction | 12012 |  |  |  |  | Rehab./Reconst./Upgrading of Damaged Paved National Rd. along Daang Maharlika Villaros-Rosario Sect. w/ exception |  | 2010-06-10 |  | II |  | 14.47 | 90 |  |  |  | O | 0.358 | 0.276 | 0.15 | 0.03 | 0.042 | 0.033 | 88.9 | -
M M Construction | 12012 | L | B | MA | GE1 | Rehab./Reconst. of Damaged National Roads, Daang Maharlika, Poblacion Villaflores Section |  | 2009-03-11 | 2nd | II |  | 14.468 | 200 |  |  |  | O | 0.355 | 0.3 | 0.15 | 0.03 | 0.05 | 0.033 | #VALUE! | -
M M Construction | 12012 | L | B | MA | GE1 | Rehab./Reconst. of Damaged National Roads, Daang Maharlika, Poblacion Villaflores Section |  | 2008-11-28 | 1st | II |  | 14.468 | 200 |  |  |  | O | 0.374 | 0.24 | 0.1 | 0.03 | 0.047 | 0.067 | 85.8 | -
M M Construction Corporation (Formerly: MM Construction) | 12012 | L | B | MA | GE1 | Widening of Daang Maharlika, K0270+755.40-K0271+736.40 | Solano, Nueva Vizcaya | 2013-08-13 | Final | II | LF | 14.7 | 120 | 2013-01-28 | 2013-05-27 | 0 | C | 0.413 | 0.133 | 0.3 | - | - | - | 84.6 | 85.20% Satisfactory
M N Revelo Construction | 24789 |  |  |  |  | Reconst. of Lanao-Pagadian-2Z Road, Lumbog Sect. Km. 1743+900 |  | 2010-02-26 |  | IX |  | 4.035 | 123 |  |  |  | O | 0.275 | 0.285 | 0.15 | 0.02 | 0.047 | 0.05 | 82.7 | -
M. B. Eclar Trading and Construction | 32118 | L | A | MA | GB | Const. of 3-Storey, 9-CL and 2-Storey, 4-CL School Building, Naguilian National High School | Naguilian, La Union | 2014-08-05 | Final | I | LF | 14.5993 | 210 | 2014-03-25 | 2014-10-20 | 0 | C | 0.383 | 0.175 | 0.3 |  |  |  | 85.8 | 85.66% Satisfactory
M. B. Eclar Trading and Construction | 32118 | L | A | MA | GE | Road Upgrading (Gravel to Paved) Based on Gravel Road Strategies Traffic Benchmark, Agoo Beach Road | La Union | 2014-08-05 | 1st & Final | I | LF | 9.9075 | 121 | 2014-02-08 | 2014-06-09 | 0 | C | 0.398 | 0.133 | 0.3 |  |  |  | 83.1 | 83.10% Satisfactory
M. DEL ROSARIO CONSTRUCTION & TRADING | 30615 | L | B | SB | GE | Rehabilitation of Road Joyous Heights | Brgy. San Jose, Antipolo City | 2015-06-02 | Final | Rizal 1st DEO | LF | 4.628 | 90 | 2014-07-17 | 2014-10-14 | 1.11% | C | 0.433 | 0.133 | 0.3 | - | - | - | 86.6% | *86.6% Satisfactory
M. G. SALAZAR CONSTRUCTION CORP (Formerly: M. G. Salazar Construction | 4072 | L | A | MA | GE | Construction/Rehabilitation of Flood Control Structure/River Wall along Casili Creek, Phase I, Navotas City | Navotas City | 2015-08-28 | 1st | MM 3rd DEO | LF | 23.338 | 210 | 2015-06-08 | 2016-01-03 | 9.99% | O | 0.318 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 83.8% | -
M. G. SALAZAR CONSTRUCTION CORP (Formerly: M. G. Salazar Construction | 4072 | L | A | MA | GE | Construction of Riverwall along Navotas River, Navotas City | Navotas City | 2015-09-04 | 1st | Mal-Nav DEO | LF | 12.073 | 173 | 2015-04-15 | 2015-10-04 | 0.3% | O | 0.326 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 85.1% | -
M. G. SALAZAR CONSTRUCTION CORP. (Formerly M. G. Salazar Construction) | 4072 | L | A | MA | GE | Construction/Maintenance of Flood Mitigation Structures & Drainage System Flood Control along Angat River Poblacion, Plaridel, Bulacan | Plaridel, Bulacan | 2015-08-26 | 1st | Bulacan First DEO | LF | 13.98 | 200 | 2015-02-25 | 2015-09-12 | 0.91% | O | 0.39 | 0.3 | 0.15 | 0.03 | 0.035 | 0.05 | 95.5% | -
M. Montesclaros Enterprises Inc. (Formerly: Monteclaros Enterprises) | 6506 |  |  |  |  | Road Upgrading (Gravel to Paved) along Jct. SH Bangcud-Mailag Road (By-Pass Road) |  | 2010-06-15 |  | X |  | 16.923 | 150 |  |  |  | O | 0.348 | 0.24 | 0.15 | 0.03 | 0.055 | 0.033 | 85.6 | -
M. Montesclaros Enterprises Inc. (Formerly: Monteclaros Enterprises) | 6506 |  |  |  |  | Road Upgrading (Gravel to Paved) of Jct. S.H. Aglayan-Alanib-Ticalaan Road |  | 2010-06-13 |  | X |  | 28.843 | 150 |  |  |  | O | 0.345 | 0.24 | 0.15 | 0.03 | 0.055 | 0.033 | 85.3 | -
M. Montesclaros Enterprises Inc. (Formerly: Monteclaros Enterprises) | 6506 |  |  |  |  | Rehab. of Damaged Paved National Roads along Jct. Impalambong-Cadre Barracks Road |  | 2010-06-15 |  | X |  | 6.982 | 60 |  |  |  | O | 0.33 | 0.24 | 0.15 | 0.023 | 0.055 | 0.05 | 84.8 | -
M. Montesclaros Enterprises Inc. (Formerly: Monteclaros Enterprises) | 6506 |  |  |  |  | Rehab./Reconst./Upgrading of Don Carlos-Kadingilan Road, Don Carlos-Lalapoy Sect. |  | 2010-06-14 |  | X |  | 25.926 | 120 |  |  |  | O | 0.335 | 0.24 | 0.15 | 0.03 | 0.055 | 0.033 | 84.3 | -
M. Montesclaros Enterprises Inc. (Formerly: Monteclaros Enterprises) | 6505 | L | A | MB | GE1 | Road Upgrading/Gravel to Asphalt along Kibawe-Kadilingan Road (Sta. 1582+874-Sta. 1582+942.45 w/ exception) selective Sections, Kibawe-Kadilingan-Kalilangan |  | 2009-05-28 | 1st | X |  | 28.335 | 120 |  |  |  | O | 0.367 | 0.3 | 0.15 | 0.03 | 0.05 | 0.05 | 94.7 | -
M. Montesclaros Enterprises Inc. (Formerly: Monteclaros Enterprises) | 6506 | L | A | MB | GE1 | Rehab./Reconst./Upgrading of Damaged Paved National Roads along Maramag-Maradugo Road, Sta. 1558+538-Sta.1576+850 selected sections |  | 2009-05-29 | 1st | X |  | 6.731 | 120 |  |  |  | O | 0.31 | 0.245 | 0.15 | 0.03 | 0.054 | 0.05 | 83.9 | -
M. Montesclaros Enterprises Inc. (Formerly: Monteclaros Enterprises) | 6506 | L | AA | LA | GE1 | Const. of 135 l.m. Steel Bridge (Bridge Approaches) |  | 2009-09-04 | 3rd | X |  | 22.665 | 240 |  |  |  | O | 0.288 | 0.3 | 0.15 | 0.03 | 0.051 | 0.05 | 86.9 | -
M. Montesclaros Enterprises Inc. (Formerly: Monteclaros Enterprises) | 6506 | L | A | MB | GE1 | Const. of 135 L.M. Steel Bridge (Bridge Approaches) |  | 2009-05-28 | 2nd | X |  | 22.665 | 240 |  |  |  | O | 0.306 | 0.26 | 0.15 | 0.03 | 0.04 | 0.05 | 83.6 | -
M. Montesclaros Enterprises Inc. (Formerly: Monteclaros Enterprises) | 6506 | L | A | MB | GE1 | Const. of 135 lm Steel Bridge (Bridge Approaches |  | 2009-03-03 | 1st | X |  | 22.665 | 271 |  |  |  | O | 0.36 | 0.24 | 0.15 | 0.03 | 0.045 | 0.05 | #VALUE! | -
M. Montesclaros Enterprises, Inc. | 6506 | L | AA | MB | GE | Rehabilitation/Reconst./ Widening of Daang Maharlika (Surigao - Agusan Section), a.) K1235+000 - K1235+972; b.) K1236+000 - K1237+000; c.) K1237+000 - K1237+380, (Intermittent Section) | Butuan City | 2014-08-15 | 1st | XIII | LF | 25.5343 | 175 | 2014-03-21 | 2014-09-11 | 11.6 | O | 0.388 | 0.2 | 0.15 | 0.03 | 0.07 | 0.05 | 88.8 | -
M. Montesclaros Enterprises, Inc. | 6506 | L | AA | MB | GE | Rehabilitation/Reconst./Improvement of Butuan City - Cagayan de Oro - Iligan (Agusan - Misamis Or.) a.) K1234+091 - K1235+061 | Butuan City | 2014-08-15 | 1st & Final | XIII | LF | 16.8994 | 123 | 2014-03-19 | 2014-07-19 | 5.61 | C | 0.5 | 0.133 | 0.3 |  |  |  | 93.3 | 93.30% Very Satisfactory
M. MONTESCLAROS ENTERPRISES, INC. (Formerly M. Montesclaros Enterprises) | 6506 | L | AA | MB | GE | Road Upgrading (Unpaved to Paved) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standard (HDM-4 Project Analysis) (Intermittent Sections) Jct SH-Impasug-ong-Patulangan, By-Pass Road, K1482+997-K1483+006, K1483+250-K1484+602, K1486+015-K1486+096, K1487+699-K1488+089, K1484+802-K1484+941, Lantapan, Bukidnon | K1482+997-K1483+006, K1483+250-K1484+602, K1486+015-K1486+096, K1487+699-K1488+089, K1484+802-K1484+941, Lantapan, Bukidnon | 2015-06-10 | 1st | Regional Office X | LF | 60.914 | 198 | 2015-03-25 | 2015-10-08 | - | O | 0.352 | 0.3 | 0.15 | 0.03 | 0.065 | 0.05 | 94.7% | -
M. MONTESCLAROS ENTERPRISES, INC. (Formerly M. Montesclaros Enterprises) | 6506 | L | AA | MB | GE | Rehab./Reconst/Upgrading of Damaged Paved National Roads Including Drainage Based on Pavement Management System/Highway Dev't & Mgnt-4 (HDM-4) (I.S.) K1568+1152.00 - K1569+145.00; K1569+975 - K1572+333; K1574+000 - K1574+202; K1574+202 - K1575+058; K1582+978- K1583+420, Don Carlos-Kadingilan Road, Bukidnon | K1568+1152.00 - K1569+145.00; K1569+975 - K1572+333; K1574+000 - K1574+202; K1574+202 - K1575+058; K1582+978- K1583+420, Don Carlos-Kadingilan Road, Bukidnon | 2015-06-10 | Final | Regional Office X | LF | 99.755 | 255 | 2014-03-26 | 2014-12-05 | - | C | 0.425 | 0.2 | 0.3 | - | - | - | 92.5% | *94.12% Very Satisfactory
M. MONTESCLAROS ENTERPRISES, INC. (Formerly M. Monteclaros Enterprises) | 6506 | L | AA | LA | GE | Rehab/Reconst/Upgrading of Damaged Paved National Roads Including Drainage Based On Pavement Management System/Highway Development & Management-4 (HDM-4) (Intemrittent Sections), Sayre Highway (Bukidnon-Davao Jct to Cotabato Boundary), K1584+236-K1585+913, K1591+226-K1594+000, K1606+053-K1606+315, Bukidnon | K1584+236-K1585+913, K1591+226-K1594+000, K1606+053-K1606+315, Bukidnon | 2015-08-28 | 1st | Regional Office No. X | LF | 135.197 | 268 | 2015-03-25 | 2015-12-17 | 10.32% | O | 0.379 | 0.238 | 0.15 | 0.03 | 0.06 | 0.05 | 90.7% | -
M. Montesclaros Enterprises, Inc. (Formerly: M. Montesclaros Enterprises) | 6506 | L | AA | MB | GE | Road Upgrading (Gravel to Concrete) Based on Gravel Road Strategies Traffic Benchmark for Upgrading to Paved Road Standard (HDM-4 Project Analysis) (Intermittent Sections) along Jct. Dologon-Kisanday-Guinoyoran Road; a) K1547+855-K1549+343.564 b) K1549+603.48 - K1549+740 | Maramag, Bukidnon | 2014-10-23 | 1st & Final | X | LF | 47.3108 | 174 | 2014-01-23 | 2014-07-15 | 0% | C | 0.428 | 0.2 | 0.3 | - | - | - | 92.8% | 92.80% Very Satisfactory
M. Montesclaros Enterprises, Inc. (Formerly: M. Montesclaros Enterprises) | 6506 | L | AA | MB | GE | Const. of Valencia by-Pass Road Including RROW K1527+910-K1530+780, K1527+800-K1528+000 | Valencia City, Bukidnon | 2014-10-24 | 1st | X | LF | 86.2139 | 330 | 2014-03-10 | 2015-02-02 | 10.72% | O | 0.308 | 0.3 | 0.15 | 0.03 | 0.056 | 0.05 | 89.4% | 89.40% Very Satisfactory
M. Montesclaros Enterprises, Inc. (Formerly: M. Montesclaros Enterprises) | 6506 | L | AA | MB | GE1 | Rehab./Reconst./Upgrading @ Sayre Highway Rd., Impalutao Sect., K1483+(-233)-K1485+230.50 | Impasugong, Bukidnon | 2013-03-19 | Final | X | LF | 43.609 | 255 | 2012-01-30 | 2012-10-10 | 5 | C | 0.296 | 0.2 | 0.3 | - | - | - | 79.6 | 85.54% Satisfactory
M. Montesclaros Enterprises, Inc. (Formerly: M. Montesclaros Enterprises) | 6506 | L | AA | MB | GE1 | Preservation of Nat'l. Rds., BCIR a)K1447+000-K1448+000 b)K1448+297-K1451+383 c)K1452+000-K1452+681 d)K1455+000-K1455+390 e)K1456+671-K1457+000 f)K1465+214-K1466+000 | Laguindingan, Misamis Oriental | 2013-03-12 | Final | X | LF | 90.824 | 204 | 2012-06-11 | 2012-12-31 | 0 | C | 0.403 | 0.142 | 0.3 | - | - | - | 84.5 | 84.98% Satisfactory
M. Montesclaros Enterprises, Inc. (Formerly: M. Montesclaros Enterprises) | 6506 | L | AA | MB | GE1 | Prev. Maint. Sayre Highway, Pob. Malaybalay & Casisang Sect., a)K1505+(-287)-K1505+818 b)K1508+224-K1508+504 w/ exceptions | Malaybalay City | 2013-03-19 | 1st | X | LF | 21.931 | 92 | 2013-01-18 | 2013-04-19 | 15.25 | O | 0.355 | 0.2 | 0.15 | 0.03 | 0.045 | 0.05 | 83 | -
M. Montesclaros Enterprises, Inc. (Formerly: M. Montesclaros Enterprises) | 6506 | L | AA | MB | GE1 | Prev. Maint. along Maramag-Maradugao Rd., (Adtuyon Sect.) K1577+(-042)-K1578+944 | Pangantucan, Bukidnon | 2013-03-20 | 1st | X | LF | 24.92 | 139 | 2013-01-23 | 2013-06-10 | 83.86 | O | 0.346 | 0.207 | 0.15 | 0.03 | 0.045 | 0.05 | 82.8 | -
M. Montesclaros Enterprises, Inc. (Formerly: M. Montesclaros Enterprises) | 6506 | L | AA | MB | GE | Rehabilitation/Repair of Road Slip along Butuan City - Pianing - Tandang, K1234+900 to K1235+300 (Intermittent Section) | Pianing, Butuan City | 2014-10-29 | 1st & Final | XIII | LF | 12.8958 | 154 | 2014-03-19 | 2014-08-19 | 19.82% | C | 0.339 | 0.2 | 0.3 | - | - | - | 83.9% | 83.90% Satisfactory
M. MONTESCLAROS ENTERPRISES, INC. (Formerly: Monteclaros Enterprises) | 6506 | L | AA | LA | GE | Construction of New Dicklum Bridge including Access Road along Sayre Highway (Alae - Kisolon Road), Dicklum, Manolo Fortich, Bukidnon | Dicklum, Manolo Fortich, Bukidnon | 2015-09-03 | 1st | Bukidnon 3rd DEO | LF | 49 | 315 | 2015-02-10 | 2015-12-21 | 0.18% | O | 0.343 | 0.3 | 0.15 | 0.03 | 0.056 | 0.05 | 92.9% | -
M. Montesclaros Enterprises, Inc. (Formerly: Montesclaros Enterprises) | 6506 | L | AA | MB | GE1 | Prev. Maint.e of Sayre Highway, Pob. Malaybalay & Casisang Sect., a)K1505+(-287)-K1505+818; b)K1508+224-K1508+504 (w/ exception) | Malaybalay City, Bukidnon | 2013-08-09 | Final | X | LF | 21.931 | 92 | 2013-01-18 | 2013-04-19 | 0 | C | 0.424 | 0.2 | 0.3 | - | - | - | 92.4 | 86.76% Satisfactory
M. Montesclaros Enterprises, Inc. (Formerly: Montesclaros Enterprises) | 6506 | L | AA | MB | GE1 | Prev. Maint. along Maramag-Maragdao Rd. (Adtuyon Sect.) K1577+(-042)-K1578+944 | Bagontaas, Bukidnon | 2013-08-06 | Final | X | LF | 24.92 | 139 | 2013-01-23 | 2013-06-10 | 88.61 | C | 0.451 | 0.133 | 0.3 | - | - | - | 88.4 | 85.04% Satisfactory
M. Montesclaros Enterprises, Inc. (Formerly: Montesclaros Enterprises) | 6506 | L | AA | MB | GE1 | Road Upgrading (Gravel to Paved) (Int. Sect.) inc. Drainage & Rd. Facilities of Jct. S.H. Bangcud-Mailag Road (By-Pass Rd.) a)K1525+595-K1525+677; b)K1526+(-048)-K1526+747; c)K1528+231-K1530+(-385), Bangcud | Malaybalay City, Bukidnon | 2013-08-09 | 1st | X | LF | 36.329 | 189 | 2013-01-18 | 2013-07-25 | 5.45 | O | 0.306 | 0.236 | 0.15 | 0.03 | 0.05 | 0.05 | 82.2 | 82.20% Satisfactory
M. Montesclaros Enterprises, Inc. (Formerly: Montesclaros Enterprises) | 6506 | L | AA | MB | GE1 | Road Upgrading (Gravel to Paved) (Int. Sect.) inc. Drainage & Rd. Facilities along Dologon-Kisanday-Guinorayan Rd. c)K1546+(-035)-K0547+000; d)K1547+000-K1547+693 | Bukidnon | 2013-08-08 | 1st | X | LF | 41.336 | 198 | 2013-01-24 | 2013-08-10 | 1.75 | O | 0.31 | 0.215 | 0.15 | 0.03 | 0.045 | 0.033 | 78.3 | -
M. P. Villegas Construction | 16683 | L | A |  |  | Const. of PSHS Dormitory Building I Phase I | Clark Polytechnic Compound, Jose Abad Santos Ave. Clark, Freeport Zone, Pampanga | 2014-09-11 | Final | DOST | L | 8.195 | 120 | 2013-12-30 | 2014-06-23 | -14.51 | C | 0.31 | 0.2 | 0 | - | - | - | 51 | 82.00% Satisfactory
M. S. Cruz Builders and Trading | 33697 | L | C | SB | GE | Construction of Visitors Information Center and Rest Area | Baco, Orinetal Mindoro | 2015-06-16 | Final | TIEZA | LF | 2.5 | 90 | 2015-01-26 | 2015-06-05 | -2.52 | C | 0.436 | 0.178 | 0.225 |  |  |  | 83.8 | 83.80% Satisfactory
M. S. Cruz Builders and Trading | 33697 | L | C | SB | GE | Rehabilitation of Old Train Terminal | Brgy. Sto. Niño, San Fernando City, Pampanga | 2014-03-13 | Final | TIEZA | LF | 4.974 | 150 | 2011-03-18 | 2011-12-16 | 0 | C | 0.441 | 0.165 | 0.3 |  |  |  | 90.7 | 90.70% Very Satisfactory
M. S. Cruz Builders and Trading | 33697 | L | C | SB | GE | Visitor's Information Center and Rest Area | Pinamalayan, Oriental, Mindoro | 2014-07-09 | Final | TIEZA | LF | 2.499 | 90 | 2014-01-27 | 2014-06-18 | 0 | C | 0.477 | 0.196 | 0.3 |  |  |  | 97.3 | 97.30% Outstanding
M. S. Cruz Builders and Trading | 33697 | L | C | SB | GE | Visitor's Information Center and Rest Area | Bansud, Oriental, Mindoro | 2014-07-09 | Final | TIEZA | LF | 2.499 | 90 | 2014-01-27 | 2014-06-18 | 0 | C | 0.473 | 0.196 | 0.3 |  |  |  | 96.9 | 96.90% Outstanding
M. S. Cruz Builders and Trading | 33697 | L | C | SB | GE | Construction of Cottages | Sibang Cove, Calayan Island, Cagayan | 2014-09-12 | Final | TIEZA | LF | 9.99 | 345 | 2012-10-29 | 2014-05-21 | 0 | C | 0.4 | 0.176 | 0.3 |  |  |  | 87.65 | 87.65% Satisfactory
M. V. CALDO ENGINEERING CONSTRUCTION & SUPPLIES | 16938 | L | B | MA | GB | Local Infrastructure Program - Construction of Multi Purpose Building, Plaridel Elementary School, Manila City 2nd LD | Manila City 2nd LD | 2015-09-01 | 1st | NM DEO | LF | 4.811 | 195 | 2015-03-27 | 2015-10-08 | 0% | O | 0.353 | 0.3 | 0.1 | 0.03 | 0.055 | 0.033 | 87.1% | -
M.A.C. Torres Enterprise |  | L |  |  |  | Re-piping of sewr & Water Lines of CR | PGH | 2011-02-18 | 1st | UP | LF | 1.534 | 45 | 2011-12-23 | 2011-02-20 | - | O | 0.4 | 0.3 | 0 | 0.03 | 0.057 | 0.05 | 83.7 | -
M.B Ang Const. & Supply | 25001 | L | D | SB | GE1 | Conc. of Caibiran-Cabucgayan National Circ. Road (Uson-Gamay Section) |  | 2008-11-18 | 1st | VIII |  | 3.725 | 160 |  |  |  | O | 0.337 | 0.24 | 0.1 | 0.03 | 0.042 | 0.1 | 84.9 | -
M.B. Eclar Trading and Construction | 32118 | L | A | MA | GE | Road Upgrading (Gravel to Paved) Based on Gravel Road Strategies Traffic Benchmark, Agoo Beach Road, KO241+632 to KO242+155 | 2nd District La Union | 2014-10-26 | 1st & Final | I | LF | 9.9075 | 121 | 2014-02-08 | 2014-06-09 | 0% | C | 0.37 | 0.177 | 0.3 | - | - | - | 84.7% | 84.70% Satisfactory
M.C.B Zamora Construction & Supplies | 32006 |  |  |  |  | Const. of MPB at Barangay Matungao |  | 2010-02-15 |  | IVB |  | 0.891 | 90 |  |  |  | O | 0.302 | 0.3 | 0.15 | 0.03 | 0.023 | 0.033 | 83.8 | -
M.C.B Zamora Construction & Supplies | 32006 |  |  |  |  | Const. of MPB at Brgy. Zone II |  | 2010-05-28 |  | IVB |  | 0.897 | 90 |  |  |  | O | 0.388 | 0.298 | 0 | 0.03 | 0.041 | 0.017 | 77.4 | -
M.C.B Zamora Construction & Supplies | 32006 | L | D | SB | GB | Construction/Completion of Two (2) Storey Four (4) Classroom at Francisco G. Nepomuceno Memorial High School, Angeles City | Angeles City | 2014-08-22 | 1st & Final | III | LF | 4.4839 | 150 | 2013-12-23 | 2014-05-21 | 0 | C | 0.494 | 0.133 | 0.3 |  |  |  | 92.7 | 92.70% Very Satisfactory
M.Del Rosario Construction and Trading | 30615 | L | C | SB | GE | Rehabilitation of Road, Joyous Heights | Barangay San Jose, Antipolo City | 2014-11-28 | 1st & Final | IV | LF | 4.6275 | 90 | 2014-07-17 | 2014-10-14 | 0% | C | 0.47 | 0.133 | 0.3 | - | - | - | 90.3% | 90.30% Very Satisfactory
M.G Salazar Const. Corp. | 4072 | L | A | MB | GB1 | Construction of Girls Dormitory Bldg. |  | 2009-05-28 | 1st | DOST |  | 30.572 | 285 |  |  |  | O | 0.352 | 0.26 | 0.15 | 0.03 | 0.048 | 0.05 | 89 | -
M.G Salazar Const. Corp. | 4072 | L | A | MB | GE1 | Site Development Project |  | 2009-05-28 | 1st | DOST |  | 0.972 | 101 |  |  |  | O | 0.36 | 0.251 | 0.1 | 0.024 | 0.058 | 0.033 | 82.6 | -
M.G Salazar Const. Corp. | 4072 | L | A | MB | GE1 | Rehab/Reconst./Upgrading of Daang Maharlika Road (Baliuag & Plaridel Section) |  | 2009-05-29 | 1st | III |  | 42.9446 | 228 |  |  |  | O | 0.325 | 0.24 | 0.15 | 0.03 | 0.04 | 0.05 | 83.5 | -
M.G Salazar Const. Corp. | 4072 | L | A | MB | GE1 | Rehab./Reconst./Upgrading at Daang Maharlika Road (Baliuag & Plaridel Section) |  | 2009-09-04 | 2nd | III |  | 42.945 | 228 |  |  |  | O | 0.325 | 0.24 | 0.15 | 0.03 | 0.046 | 0.033 | 82.4 | -
M.G. JACINTO CONSTRUCTION | 20617 | L | B | SB | GE | Construction/Upgrading/Rehabilitation of Drainage/Protection Works along National Roads, Cagayan Valley Road, K00478+948 - K-478+998 - K0479-234 | Cagayan Valley Road | 2015-11-11 | Final | CAGAYAN 3RD DEO | LF | 2.2455 | 90 | 2015-02-17 | 2015-05-18 | (-) 20.00 | C | 0.482 | 0.133 | 0 | - | - | - | 61.5% | 61.5% Poor
M.G. Lualhati Construction | 35373 | L | A | MB | GE | Widening/Replacement/ Rehabilitation/ Strengthening of Permanent Bridge At Tabuyoc Bridge Along MNR, (Phase I & II) | Urdaneta City, Pangasinan | 2014-10-30 | 1st | I | LF | 43.2167 | 192 | 2104-07-17 | 2105-01-24 | 0% | O | 0.369 | 0.3 | 0.15 | 0.024 | 0.055 | 0.05 | 94.8% | 94.80% Very Satisfactory
M.G. Salazar Cons. Corp. (Formerly: M.G. Salazar Construction) | 4072 | L | A | MA | GE | Construction of River Wall along Tullahan River, Phase IX | Valenzuela City | 2014-11-22 | 1st | NCR | LF | 39.85 | 240 | 2014-07-31 | 2015-03-27 | 0.4% | O | 0.273 | 0.3 | 0.15 | 0.03 | 0.045 | 0.033 | 83.1% | 83.10% Satisfactory
M.G. SALAZAR CONS. CORP. (Formerly: M.G. Salazar Construction) | 4072 | L | A | MA | GE | Construction/Maintenance of Flood Control Mitigation Structures and Drainage Systems Flood control along Angat River Poblacion Plaridel, Bulacan | Plaridel, Bulacan | 2015-11-20 | Final | Bataan First DEO | LF | 13.98 | 200 | 2015-02-25 | 2015-09-12 | - | C | 0.5 | 0.133 | 0.3 | - | - | - | 93.3% | 94.62% Very Satisfactory
M.G. Salazar Construction Corporation | 4072 | L | A | MA | GE2 | Const. of Coastal Dike | Navotas City | 2013-08-12 | 1st | NCR | LF | 45.296 | 219 | 2013-03-27 | 2013-10-31 | 18.79 | O | 0.341 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 86.1 | -
M.G. Samidan Construction | 33234 | L | B | MA | GE1 | Road Upgrading (Gravel to Concrete) of National Roads along Gurel-Bokod-Kabayan-Buguias-Abatan Rd. K0355+000-K0356+100 (I.S.) | Buguias, Benguet | 2012-03-14 | 1st | CAR | LF | 17.245 | 194 | 2011-12-19 | 2012-06-30 | 3.96 | O | 0.374 | 0.24 | 0.15 | 0.03 | 0.045 | 0.05 | 88.9 | -
M.H Southern Construction | 5841 | L | A | MB | GE1 | Sarangani Davao del Sur Coastal Road, Cross Section |  | 2009-06-11 | 1st | R-XII |  | 7.457 | 150 |  |  |  | O | 0.297 | 0.249 | 0.15 | 0.024 | 0.045 | 0.05 | 81.5 | -
M.H Southern Construction | 5841 | L | A | MB | GE1 | Conc. of Road and Reblocking, Marbel-makar Road, Matin-ao Silway 8, (Km. 1662+800 - Km. 1663+740) |  | 2009-06-08 | 2nd | R-XII |  | 14.167 | 195 |  |  |  | O | 0.301 | 0.3 | 0 | 0.03 | 0.055 | 0.033 | 71.9 | -
M.H Southern Construction | 5841 | L | A | MB | GE1 | Conc. of Road & Reblocking, Marbel-Makar Road, Matinao Silway 8 |  | 2009-03-20 | 1st | XII |  | 14.169 | 180 |  |  |  | O | 0.346 | 0.3 | 0.15 | 0.03 | 0.04 | 0.05 | #VALUE! | -
M.H. Southern Construction | 5841 | L | A | MA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rd. (South Cotabato 2nd District), Marbel-Makar Rd., K1701+896-K1703+(-58), K1702+966-K1703+2 Modified to: K1702+307-K1702+966, K1702+966-K1703+066 | Koronadal City, South Cotabato | 2013-03-21 | Final | XII | LF | 14.394 | 225 | 2011-08-24 | 2012-04-04 | - | C | 0.435 | 0.2 | 0 | - | - | - | 63.5 | 70.46% Poor
M.J. Apin Builders | 12179 | L | A | MA | GB-1 | VARIOUS CONSTRACTION OF HOSPITAL FACILITIES | San Pedro, Cabusao, Camarines Sur/Region 5 | 2015-09-04 | 1st & Final | DOH | LF | 13.177 | 270 | 2014-09-24 | 2015-06-12 | 0 | O | 0.488 | 0.2 | 0.3 | - | - | - | 98.8 | 98.80% Outstanding
M.J. Apin Builders | 12179 | L | B | MA | GB | Construction of One-Storey, Three-Classroom School Building, Buyo Impact Elementary School | Goa, Camarines Sur | 2014-08-09 | Final | V | LF | 1.6017 | 150 | 2013-06-10 | 2013-11-06 | 0 | C | 0.434 | 0.133 | 0.3 |  |  |  | 86.7 | 86.56% Satisfactory
M.J. Apin Builders | 12179 | L | B | SB | GB1 | Const. of 1 Storey 3-Cl. Sch. Buildings, Buyo Impact Elem. Sch. | Buyo, Goa, Camarines Sur | 2013-08-02 | 1st | V | LF | 1.602 | 120 | 2013-06-10 | 2013-10-07 | 0.85 | O | 0.365 | 0.24 | 0.15 | 0.03 | 0.047 | 0.033 | 86.5 | -
M.K.U. CONSTRUCTION AND SUPPLY | 37674 | L | C | SB | GE | Repair/Maintenance of Damaged Grouted Riprap at Cabalagnan Bridge I, Bacolod South Road, K0006+951, Pahanocoy, Bacolod City | Pahanocoy, Bacolod City | 2015-11-17 | 1st | Bacolod City DEO | LF | 1.6489 | 90 | 2015-09-24 | 2015-12-22 | (+)45.4% | OG | 0.306 | 0.3 | 0.15 | 0.03 | 0.05 | 0.05 | 88.6% | 88.6% Satisfactory
M.K.U. CONSTRUCTION AND SUPPLY | 37674 | L | C | SB | GE | Repair/Maintenance of Damaged Grouted Riprap at Rabadilla Bridge, Bacolod Circumferential Road, K0004+801, Madalagan, Bacolod City | Madalagan, Bacolod City | 2015-11-18 | Final | Bacolod City DEO | LF | 3.395 | 90 | 2015-09-24 | 2015-12-22 | (+)31.19% | C | 0.447 | 0.133 | 0.3 | - | - | - | 88% | 88% Satisfactory
M.M. RODRIGUEZ TRADING AND CONSTRUCTION | 37228 | L | D | SB | GE | Construction of Flood Control Structures, Iraan Flood Control | Rizal, Palawan | 2015-06-04 | Final | Palawan 2nd DEO | LF | 4.632 | 90 | 2015-03-13 | 2015-06-10 | 0% | C | 0.457 | 0.133 | 0.3 | - | - | - | 89% | *89% Satisfactory
M.Montesclaros Enterprises, Inc. (Formerly: M.Montesclaros Enterprises) | 6506 | L | AA | MB | GE | Rehab./Reconst./Upgrading of Damaged Paved National Roads including Drainage based on Pavement Management System/Highway Development & Management-4 (HDM-4) (Intermittent Sections), Don Carlos-Kadingilan Road, Bukidnon 3rd LD, K1568+152.00 - K1569+145.00; K1569+975 - K1572+333; K1574+000 - K1574+202; K1574+202 - K1575+058; K1582+978 - K1583+420; with exceptions, Net Length=3.206km. | Bukidnon 3rd LD | 2014-08-08 | 1st | X | LF | 91.1416 | 255 | 2014-03-26 | 2014-12-05 | 4.82 | O | 0.367 | 0.291 | 0.15 | 0.024 | 0.07 | 0.05 | 95.2 | -
M.Montesclaros Enterprises, Inc. (Formerly: M.Montesclaros Enterprises) | 6506 | L | B | MA | GE | Road Upgrading (Gravel to paved) Based on Gravel Road Strategies Traffic Benchmark for Upgrading to Paved Road Standard (HDM-4) Project Analysis (Intermittent Section) including Drainage and Road Facilities of Junction S.H. Bangcud-Mailag Road (By-Pass Road) a. km1525+595 to K1526+677 b. K1526+(-048) - K1526+747 c. K1528+231 - K1530+(-385) | Bangcud, Malaybalay City | 2014-08-05 | Final | X | LF | 36.3286 | 219 | 2013-01-18 | 2013-08-24 | 0 | C | 0.462 | 0.2 | 0.3 |  |  |  | 96.2 | 87.80% Satisfactory
M.Montesclaros Enterprises, Inc. (Formerly: M.Montesclaros Enterprises) | 6506 | L | B | MA | GE | Widening of Sayre Highway Bukidnon 2nd LD Kalasungay & Casisang Sections, K1502+(-250) - K1503+000, K1509+(-400) - K1509+800 | Kalsungay & Casisang Section, Malaybalay City, Bukidnon | 2014-08-06 | 1st & Final | X | LF | 36.8628 | 179 | 2014-01-23 | 2014-07-20 | 0 | C | 0.462 | 0.2 | 0.3 |  |  |  | 96.2 | 96.20% Outstanding
M.Montesclaros Enterprises, Inc. (Formerly: M.Montesclaros Enterprises) | 6506 | L | AA | MA | GE | Road Upgrading (gravel to paved) based on Gravel Road Strategies, Traffic Benchmark, for Upgrading to Paved Road Standard (HDM-4 Project Analysis) (Intermittent Section) including Drainage and Road Facilities Along Dologon-Kisanday-Guinoyoran Road c)K1546+(-035) - K1547+000, d)K1547+000 - K1547+693 | Dologon-Kisanday-Guinoyoran Road | 2014-08-07 | Final | X | LF | 43.9183 | 220 | 2013-01-24 | 2013-08-31 | 0 | C | 0.466 | 0.187 | 0.3 |  |  |  | 95.3 | 85.10% Satisfactory
M.R Vargas Construction | 8215 | L | AAA | MB | GE5 | M'lang Airport Development Project |  | 2009-03-13 | Final | DOTC |  | 13.458 | 180 |  |  |  | O | 0.36 | 0.293 | 0.15 | 0.023 | 0.05 | 0.033 | 90.9 | -
M.R.C Bechaida Construction & Supply | 32821 | L | D | SB | GE1 | Conc. of Masagongsong Bridge Approaches |  | 2008-11-18 | 1st | VIII |  | 1.867 | 140 |  |  |  | O | 0.37 | 0.232 | 0.1 | 0.015 | 0.037 | 0.1 | 85.4 | -
M.S Ramos Construction | 31684 | L | A | MA | GE1 | Const./Impvt. of P. Antonio St. (Covered Walkway/Sidewalk/Curb & Gutter, Brgy. Ugong |  | 2009-09-10 | 1st | NCR |  | 5.254 | 90 |  |  |  | O | 0.398 | 0.225 | 0.15 | 0.02 | 0.035 | 0.05 | 87.8 | -
M.S. Cruz Builders & Trading | 33697 | L | C | SB | GE | Widening along Tacloban-Baybay South Road, Chainage 0+000 - Chainage 0+111 | Tacloban City | 2014-10-30 | 1st | VIII | LF | 4.5512 | 67 | 2014-09-16 | 2014-11-21 | -5% | O | 0.288 | 0.24 | 0.1 | 0.03 | 0.04 | 0.033 | 73.1% | 73.10% Poor
M.S. Cruz Builders & Trading | 33697 | L | C | SB | GE | Const. of Local Road at Brgy. Navaling, Magalang, Pampanga | Brgy. Nabaling, Magalang, Pampanga | 2014-08-23 | 1st | III | LF | 3.7392 | 50 | 2014-07-10 | 2014-08-22 | 2 | O | 0.372 | 0.238 | 0.15 | 0.03 | 0.055 | 0.05 | 89.5 | -
M.S. Ramos Construction | 31684 | L | A | MA | GE | Preventive Maintenance along Norzagaray-Bigte Road a) K0072+572 - K0072+915 b) K0073+000 - K0073+738 c) K0072+960 - K0072+1160 | Norzagaray, Bulacan | 2014-09-27 | 1st & Final | Special 3 | LF | 10.9225 | 30 | 2014-02-11 | 2014-03-12 | 0 | C | 0.483 | 0.131 | 0.3 |  |  |  | 91.4 | 91.40% Very Satisfactory
M.S. RAMOS CONSTRUCTION | 31684 | L | A | SB | GE | Repair/Rehabilitation/Improvement/Drainage Improvement Pinaglaban Road and Vicinity, San Juan City, Chainage 0006 to San Juan City | San Juan City | 2015-12-07 | 1st | First Metro Manila DEO | LF | 8.106 | 305 | 2015-03-12 | 2016-01-10 | (-)0.5% | OG | 0.342 | 0.233 | 0.15 | 0.03 | 0.035 | 0.05 | 84% | 84% Satisfactory
M.V. Caldo Engineering Construction and Supplies | 16938 | L | B | MA | GE1 | Reconst. of C. Palanca St., w/ Drainage Impv't. | Quiapo, Manila | 2013-07-29 | Final | NCR | LF | 3.837 | 90 | 2013-01-31 | 2013-04-30 | 0 | C | 0.444 | 0.133 | 0.3 | - | - | - | 87.7 | 86.44% Satisfactory
M.V. Caldo Engineering Construction and Supplies | 16938 | L | B | MA | GE1 | Reconst. of C. Palanca St. w/ Drainage Impv't. | Quiapo, Manila | 2013-03-20 | 1st | NCR | LF | 3.837 | 90 | 2013-01-31 | 2013-04-30 | 5.43 | O | 0.354 | 0.239 | 0.15 | 0.03 | 0.05 | 0.033 | 85.6 | -
M.V. GUBALLA CONSTRUCTION | 11722 | L | D | SB | GB | Package 2-Construction of Multi-Purpose Building (Covered Court) at Barangay Del Pilar, Castillejos, Zambales | Castillejos, Zambales | 2015-11-10 | Final | Zambales Second DEO | LF | 3.255 | 75 | 2015-01-12 | 2015-03-27 | - | C | 0.5 | 0.133 | 0.3 | - | - | - | 93.3% | 93.3% Very Satisfactory
M.V. Sabalburo Construction and Supply | 32561 | L | B | SB | GE1 | Rehab. of Drainage Canal along MNR, Km. 405+500-Km. 406+715 | Bantay, Ilocos Sur | 2013-08-13 | Final | I | LF | 9.69 | 128 | 2012-12-19 | 2013-04-25 | 0 | C | 0.47 | 0.133 | 0.3 | - | - | - | 90.3 | 92.88% Very Satisfactory
M.V. Sabalburo Construction and Supply | 32561 | L | B | SB | GE1 | Rehab. of Drainage Canal along MNR, Km.405+500-Km.406+715 | Bantay, Ilocos Sur | 2013-03-20 | 1st | I | LF | 9.69 | 100 | 2012-12-19 | 2013-03-28 | 3.98 | O | 0.388 | 0.3 | 0.15 | 0.03 | 0.045 | 0.033 | 94.6 | -
MA. GINA M. PADOR CONSTRUCTION | 25600 | L | D | SB | GE | Construction of Road Gabawan | Odiongan, Romblon | 2015-06-12 | Final | Romblon DEO | LF | 4.87 | 60 | 2015-04-08 | 2015-06-06 | 0% | C | 0.406 | 0.156 | 0.3 | - | - | - | 86.2% | *86.2% Satisfactory
Mabrak Construction | 33340 | L | D | SB | GE1 | Conc. of Nueva Vizcaya-Ifugao-Mt. Province Road |  | 2009-05-26 | 1st | CAR |  | 3.782 | 40 |  |  |  | O | 0.4 | 0.3 | 0 | 0.03 | 0.029 | 0.033 | 79.2 | -
Mac Builders | 7249 | L | AAA | LA | GE5 | Hindang Port Development Project | Hindang, Leyte / Region 8 | 2013-03-20 | Final | DOTC | LF | 14.432 | 105 | 2012-10-06 | 2013-01-22 | 3.39 | C | 0.465 | 0.2 | 0.3 | - | - | - | 96.5 | 96.30% Outstanding
Mac Builders | 7249 | L | AAA |  | GE1 | Hindang Port Development Project | Hindang, Leyte | 2012-12-05 | 1st | DOTC | LF | 14.432 | 105 | 2012-10-06 | 2013-01-22 | 15.78 | O | 0.37 | 0.3 | 0.15 | 0.03 | 0.062 | 0.05 | 96.2 | -
Mac Builders | 7249 | L | AAA | LB | GE-5 | Ormoc Airport Development Project | Ormoc City, Western Leyte/Region VIII | 2015-08-12 | 2nd | DOTC | LF | 95.418 | 420 | 2014-08-06 | 2015-11-11 | -11.07 | O | 0.3875 | 0.3 | 0.0393 | 0.02 | 0.05 | 0.0333 | 83.01 | -
MAC Builders | 7249 | L | AAA | LB |  | Ormoc Airport Development Project Construction of New Terminal | Ormoc City, Western Leyte/ Region VIII | 2015-02-17 | 1st | DOTC | L | 95.418 | 360 | 2014-08-06 | 2015-06-07 | 10.24 | O | 0.3694 | 0.3 | 0.15 | 0.02 | 0.0254 | 0.033 | 89.78 | -
Mac Builders | 7249 | L | AA | LB |  | Ormoc Airport Development Project | Ormoc City, Leyte | 2015-04-15 | 2nd & Final | DOTC | LF | 54.839 | 135 | 2014-06-01 | 2015-03-12 | 0 | C | 0.441 | 0.2 | 0.3 | - | - | - | 94.1 | 92.00% Very Satisfactory
Mac Builders | 7249 | L | AAA | LB |  | Ormoc Airport Development Project Asphalt Overlay of Runway | Ormoc City, Western Leyte/ Region VIII | 2015-02-17 | 1st | DOTC | L | 54.839 | 120 | 2014-07-01 | 2015-03-29 | 13.92 | O | 0.3611 | 0.3 | 0.15 | 0.02 | 0.0262 | 0.05 | 90.73 | -
Mac Builders | 7249 | L | AA |  | GE5 | Proposed Pier Extension and Passenger Terminal Building | Brgy. Maguino-o, Calbayog City / Region VII | 2013-03-01 | 2nd & Final | PPA | LF | 38.509 | 309 | 2011-10-25 | 2012-11-16 | - | C | 0.5 | 0.2 | 0 | - | - | - | 70 | 83.14% Satisfactory
Mac Builders | 7249 | L | AA |  | GE5 | Proposed Pier Extension & Passenger Terminal Building | Port of Maguino-o, Calbayog City Northern Samar | 2012-10-09 | 1st | PPA | LF | 38.591 | 309 | 2012-01-13 | 2012-11-16 | 11.513 | O | 0.328 | 0.3 | 0.15 | 0.03 | 0.061 | 0.05 | 91.9 | -
Mac Builders | 7249 |  |  |  |  | Construction of Back-Up Area and Roro Ramp on Fill | Port of Ormoc, Ormoc City | 2015-04-29 | 2nd & Final | PPA | L | 92.985 | 660 | 2012-10-20 | 2013-12-15 | 0 | C | 0.4998 | 0.2 | 0.3 | - | - | - | 99.98 | 99.00% Outstanding
Mac Builders | 7249 | L | AAA |  | GE5 | Construction of Back-up Area and RoRo Ramp on Fill | Port of Ormoc, Ormoc City, Leyte | 2013-05-17 | 1st | PPA | LF | 89.836 | 420 | 2012-10-22 | 2013-12-15 | 8.901 | O | 0.3893 | 0.3 | 0.15 | 0.03 | 0.0642 | 0.05 | 98.35 | -
Mac Builders | 7249 | L | AA | LA | GE1 | Cluster No. RB13: Rehab./Restoration of Rds. & Bridges along various Rd. Sect. in Palawan, POPSTIRP, Roads & Bridges Component | Puerto Princesa, Palawan | 2012-07-30 | Final | IVB / BOM | FA | 57.023 | 331 | 2011-05-17 | 2012-04-12 | 0 | C | 0.342 | 0.2 | 0.3 | - | - | - | 84.2 | 88.28% Satisfactory
Mac Builders | 7249 |  |  |  |  | Replacement of Old Ticud Bridge connecting Iloilo City-Dumangas Coastal Road |  | 2010-09-08 |  | V I |  | 47.804 | 140 |  |  |  | O | 0.36 | 0.24 | 0.15 | 0.03 | 0.037 | 0.033 | 85 | -
Mac Builders | 7249 | L | AAA | LB | GE | Asphalt Overlay along Daang Maharlika (SM) (San Isidro - San Juanico Bridge), K0701+050 - K0701+216 | Samar | 2014-10-23 | 1st & Final | VIII | LF | 10.5485 | 64 | 2014-02-24 | 2014-04-28 | 6.06% | C | 0.443 | 0.133 | 0.3 | - | - | - | 87.6% | 87.60% Satisfactory
Mac Builders | 7249 | L | AAA | LB | GE | Rehabilitation/Reconstruction/Replacement/Retrofitting of Existing Bridges Maypatag Bridge along Ormoc-Baybay-Southern Leyte Boundary Road | Baybay City, Leyte | 2014-10-28 | 1st & Final | VIII | LF | 12.5398 | 162 | 2014-02-03 | 2014-07-14 | 30.25% | C | 0.492 | 0.133 | 0.3 | - | - | - | 92.5% | 92.50% Very Satisfactory
Mac Builders | 7249 | L | AAA | LB | GE | Road Upgrading (gravel to Paved) Merida - Lundag - Putting Bato - Consolacion - Isabel Road K1121+162 - K1122+255 | Leyte | 2014-08-07 | Final | VIII | LF | 30.615 | 234 | 2013-01-28 | 2013-09-19 | -18.37 | C | 0.419 | 0.133 | 0 |  |  |  | 55.2 | 75.84% Unsatisfactory
Mac Builders | 7249 | L | AAA | LB | GE | Rehab./Reconst. Of Damaged Paved National Road including drainag along Calubian Jct. - San Isidro - Tabango - Villaba - Palompon Road Km……… | San Isidro & Tabango, Leyte | 2014-08-08 | 1st | VIII | LF | 25.5477 | 179 | 2014-01-30 | 2014-07-28 | 0.1 | O | 0.372 | 0.24 | 0.15 | 0.03 | 0.045 | 0.033 | 87 | -
Mac Builders | 7249 | L | AAA | LB | GE1 | Rd. Upgrading (Gravel to Pave) Merida-Lundag-Puting Bato-Consolacion-Isabel Rd., K1121+162-K1122+255 | Leyte | 2013-08-10 | 1st | VIII | LF | 30.615 | 234 | 2013-01-28 | 2013-09-19 | 0.49 | O | 0.382 | 0.24 | 0.15 | 0.018 | 0.056 | 0.05 | 89.6 | -
Mac Builders | 7249 | L | AAA | LB | GE1 | Prev. Maint. of Jaro-Dagami-Burauen-La Paz Rd., Km.0964+500-Km.0969+000 | Dagami, Leyte | 2013-08-17 | Final | VIII | LF | 30.857 | 174 | 2013-01-15 | 2013-07-07 | 1.15 | C | 0.477 | 0.133 | 0.3 | - | - | - | 91 | 85.78% Satisfactory
Mac Builders | 7249 | L | AAA | LB | GE1 | Rehab. & Impv't. of Naval-Caibiran, Cross Country Rd. (Major Rd. Slip), Km.1035+000-Km.1044+000 w/ exceptions | Biliran Province | 2013-08-15 | Final | VIII | LF | 8.921 | 208 | 2012-12-14 | 2013-07-10 | 0.67 | C | 0.478 | 0.133 | 0.3 | - | - | - | 91.1 | 85.82% Satisfactory
Mac Builders | 7249 | L | AAA | MA | GE2 | Rehab./Impv't. of Flood Control Proj., Dungca-an River Flood Control Works | Baybay City, Leyte | 2013-03-15 | 1st | VIII | LF | 17.856 | 170 | 2013-01-25 | 2013-07-14 | 17.52 | O | 0.38 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 90 | -
Mac Builders | 7249 | L | AAA | LB | GE1 | Upgrading/Concrete Paving of Gaps along Calbayog Diversion Rd. (inc. RROW), Sta.5+062-Sta.5+725.89 and Sta.7+178.86-Sta.11+009.48, Calbayog City & Sta. Margarita | Samar | 2013-03-19 | 1st | VIII | LF | 96.305 | 345 | 2012-05-23 | 2013-05-02 | 0.48 | O | 0.321 | 0.238 | 0.15 | 0.03 | 0.06 | 0.05 | 84.9 | -
Mac Builders | 7249 | L | AAA | LB | GE1 | Rehab./Repair of Kinawan Bridge along Daang Maharlika (SM) (San Isidro-San Juanico Bridge) Kinawan | Samar | 2013-03-19 | Final | VIII | LF | 27.286 | 210 | 2012-01-31 | 2012-08-27 | 0.95 | C | 0.442 | 0.133 | 0.3 | - | - | - | 87.5 | 84.56% Satisfactory
Mac Builders | 7249 | L | AAA | LB | GE1 | Road Leading to Leyte Golf and Country Club, Macabug-Mabini Rd. | Ormoc City | 2013-03-15 | 1st | VIII | LF | 25.125 | 174 | 2013-01-28 | 2013-07-20 | 0.07 | O | 0.331 | 0.24 | 0.15 | 0.03 | 0.04 | 0.05 | 84.1 | -
Mac Builders | 7249 | L | AAA | LB | GE1 | Rehab. & Impv't. of Naval-Caibiran, Cross Country Rd. (Major Rd. Slip), Km.1035+000-Km.1044+000 w/ exceptions | Biliran Province | 2013-03-12 | 1st | VIII | LF | 8.921 | 150 | 2012-12-14 | 2013-05-13 | 0.01 | O | 0.32 | 0.24 | 0.15 | 0.03 | 0.05 | 0.033 | 82.3 | -
Mac Builders | 7249 | L | AAA | LB | GE1 | Prev. Maint. of Jaro-Dagami-Burauen-La Paz Rd., Km.0964+500-Km.0969+000 | Dagami, Leyte | 2013-03-11 | 1st | VIII | LF | 30.857 | 144 | 2013-01-15 | 2013-06-07 | 2.26 | O | 0.314 | 0.239 | 0.15 | 0.03 | 0.04 | 0.05 | 82.3 | -
Mac Builders | 7249 |  |  |  |  | Road Upgrading (Gravel to Paved) of Belen-Consuegra Rd., Km.981+940 - Km.981+910 |  | 2010-06-04 |  | VIII |  | 18.54 | 240 |  |  |  | O | 0.334 | 0.3 | 0.15 | 0.03 | 0.037 | 0.033 | 88.4 | -
Mac Builders | 7249 |  |  |  |  | Concrete Paving of Critical Portion along Caibiran-Cabucgayan Rd. (Pawikan-Bunga Sect.) |  | 2010-06-02 |  | VIII |  | 19.18 | 300 |  |  |  | O | 0.343 | 0.28 | 0.15 | 0.03 | 0.042 | 0.033 | 87.8 | -
Mac Builders | 7249 | L | AAA | LB | GE1 | Conc. of Calubian Jct., San Isidro-Tabango-Villaba-Palompon Road |  | 2009-06-02 | 1st | VIII |  | 55.351 | 330 |  |  |  | O | 0.364 | 0.24 | 0.15 | 0.03 | 0.035 | 0.05 | 86.9 | -
Mac Builders | 7249 | L | AAA | LB | GE1 | Conc. of Calubian Jct. San Isidro-Tabango-Villaba-Palompon Road Tabango-San Isidro |  | 2009-09-05 | 1st | VIII |  | 55.351 | 330 |  |  |  | O | 0.357 | 0.245 | 0.15 | 0.03 | 0.04 | 0.05 | 87.2 | -
Mac Builders | 7249 | L | AAA | LB | GE1 | Rehab. (Conc.) of Cabungaan-Tabunok-Consuegra Road |  | 2009-09-05 | 1st | VIII |  | 14.052 | 180 |  |  |  | O | 0.34 | 0.245 | 0.15 | 0.03 | 0.04 | 0.05 | 85.5 | -
Mac Builders | 7249 |  |  |  |  | Rehab. of Damaged Paved National Roads along Daang Maharlika Abuyog Mahaplag Road Section (Balinsasayao-Hilusig Road Section) |  | 2010-09-02 |  | VIII |  | 47.049 | 240 |  |  |  | O | 0.364 | 0.24 | 0.15 | 0.03 | 0.042 | 0.033 | 85.9 | -
Mac Builders | 7249 | L | AA | LA | GE1 | Rehab./Strengthening/Reconst. of Can-avid Bridge Jct. Taft-Oras-San Policarpio-Arteche Rd. | Can-avid, Eastern Samar | 2012-08-19 | 2nd | VIII | LF | 46.374 | 360 | 2012-01-24 | 2012-01-18 | -1.02 | O | 0.322 | 0.3 | 0.14 | 0.03 | 0.038 | 0.033 | 86.3 | -
Mac Builders | 7149 | L | AA | LA | GE1 | Rehab./Strengthening/Reconst. Of Can-Avid Bridge Jct. Taft-Oras-San Policarpio-Arteche Road | Can-Avid, Eastern Samar | 2012-03-29 | 1st | VIII | LF | 46.374 | 251 | 2012-01-24 | 2012-09-30 | -5.97 | O | 0.4 | 0.3 | 0.09 | 0.023 | 0.04 | 0.033 | 88.6 | -
Mac Builders | 7249 | L | AA | LA | GE1 | Rehab./Const. of Drainage Lined Canal along Calbayog-Allen Road Sect., K0690+500-K0732+600 | Calbayog City | 2012-03-25 | 1st | VIII | LF | 45.983 | 180 | 2011-10-10 | 2012-04-07 | 0.47 | O | 0.355 | 0.225 | 0.15 | 0.03 | 0.03 | 0.033 | 82.3 | -
Mac Builders | 7249 | L | AA | LA | GE1 | Rehab./Strengthening/Reconst. Of Dolores Bridge, Jct. Taft-Oras-San Policarpio-Arteche Rd. | Dolores, Eastern Samar | 2012-08-20 | 2nd | VIII | LF | 18.568 | 235 | 2012-01-24 | 2012-09-14 | -7.77 | O | 0.354 | 0.3 | 0.072 | 0.03 | 0.038 | 0.033 | 82.7 | -
Mac Builders | 7249 | L | AA | LA | GE1 | Rehab./Strengthening/Reconst. of Dolores Bridge Jct. Taft-Oras-San Policarpio-Arteche Rd. | Dolores, Eastern Samar | 2012-03-29 | 1st | VIII | LF | 18.568 | 159 | 2012-01-24 | 2012-06-30 | -5.8 | O | 0.327 | 0.3 | 0.092 | 0.03 | 0.04 | 0.033 | 82.2 | -
Mac Builders | 7249 | L | AA | LA | GE1 | Rehab./Strenthening/Reconst. Of Quinapondan Bridge Jct. Buenavista-Lawaan-Marabut, | Quinapondan, Eastern Samar | 2012-03-29 | 1st | VIII | LF | 16.701 | 140 | 2012-01-24 | 2012-06-11 | -7.99 | O | 0.36 | 0.3 | 0.07 | 0.02 | 0.03 | 0.033 | 81.3 | -
Mac Builders | 7249 | L | AA | LA | GE | Rehab. of Daang Maharlika (Km.1037+971-Km.1047+107 (w/ exceptions) | Libangon, Southern Leyte | 2012-03-30 | 1st | VIII | LF | 43.951 | 260 | 2011-08-12 | 2012-04-28 | 8.47 | O | 0.348 | 0.203 | 0.15 | 0.03 | 0.035 | 0.05 | 81.6 | -
Mac Builders | 7249 | L | AAA | LB | GE1 | Rehab./Reconst. Of Damaged Paved Nat'l Road, Palo-Carigara-Ormoc Road, Km.1003+000-Km.1005+000 | Leyte | 2012-03-24 | 1st | VIII | LF | 26.547 | 197 | 2012-01-16 | 2012-07-30 | 5.35 | O | 0.269 | 0.24 | 0.15 | 0.03 | 0.05 | 0.033 | 77.2 | -
Mac Builders | 7249 | L | AA | LA | GE1 | Repair/Replacement of San Policarpio Bridge | San Policarpio, Eastern Samar | 2012-08-19 | 1st | VIII | LF | 21.275 | 265 | 2011-12-26 | 2012-08-27 | -0.3 | O | 0.373 | 0.3 | 0.147 | 0.03 | 0.035 | 0.033 | 91.8 | -
Mac Builders | 7249 | L | AA | LA | GE1 | Rd. Upgrading (Gravel to Paved) based on Gravel Rd. Strategies, Pangpang-Palapag-Mapanas-Gamay, Anito-Bag-ot Sect., K0835+531-K0838+000, w/ exceptions | Gamay, Northern Samar | 2012-08-17 | 1st | VIII | LF | 127.381 | 360 | 2012-01-19 | 2013-01-12 | -2.19 | O | 0.338 | 0.3 | 0.128 | 0.03 | 0.033 | 0.033 | 86.2 | -
MAC Builders | 7249 |  | AAA | LB |  | Ormoc Airport Development Project | Brgy. Airport, Ormoc City, Leyte | 2016-02-18 | 2nd | DOTC | LF | 95.411 | 450 | 2014-08-06 | 2016-05-16 | 2.34 | O | 0.374 | 0.3 | 0.103 | 0.03 | 0.063 | 0.05 | 92 | -
MAC BUILDERS | 7249 | L | - | - | - | Construction of Tagbas Flood Control, Albuera, Leyte | Albuera, Leyte | 2015-06-06 | 1st | Leyte Fourth DEO | LF | 15.603 | 155 | 2015-02-02 | 2015-07-06 | - | O | 0.187 | 0.211 | 0.15 | 0.03 | 0.045 | 0.05 | 67.3% | -
MAC BUILDERS | 7249 | L | AAA | MA | GE | Construction of Tabgas Flood Control, Albuera, Leyte | Albuera, Leyte | 2015-08-28 | Final | Leyte 4th DEO | LF | 15.603 | 155 | 2015-02-02 | 2015-07-06 | (+)7.10 | C | 0.381 | 0.152 | 0.3 | - | - | - | 83.3% | *73.7% Poor
MAC Builders | 7249 | L | AAA | LA |  | Western Visayas PCG SAR Bases Development Project | Brgy. Culasi, Roxas City, Capiz/Region VI | 2016-04-21 | 1st | DOTC | LF | 222.509 | 360 | 2014-06-13 | 2016-06-03 | -18.02 | O | 0.365 | 0.3 | 0 | 0.03 | 0.053 | 0.05 | 79.8 | -
MAC Builders | 7249 | L | AAA | LB |  | Ormoc Airport Development Project | Ormoc City, Western Leyte/ Region 8 | 2015-09-28 | 4th & Final | DOTC | LF | 95.4176 | 420 | 2014-08-06 | 2016-06-24 | 0 | C | 0.438 | 0.2 | 0.3 | - | - | - | 93.8 | 90.49% Very Satisfactory
MAC Builders / Ubas Construction (JV) | JV-05-021 | L | AAA | LB | GE1 | Impvt. of Allen-Malaga Section along Maharlika Highway, Ferry Terminal-Allen |  | 2008-08-30 | 1st | VIII |  | 46.652 | 260 |  |  |  | O | 0.354 | 0.24 | 0 | 0.022 | 0.054 | 0.067 | 73.7 | -
Macqueserg Construction & General Merchandise | 13903 | L |  |  |  | Design and Construction of the UP Cebu Arts & Sciences (A.S.) Extension Building | UP Cebu Campus | 2016-10-10 | 1st | UP | LF | 12.996 | 213 | 2016-04-19 | 2015-10-04 | 0 | O | 0.345 | 0 | 0 | 0 | 0 | 0 | 34.5 | -
Madyaw Construction & Dev. Corporation | 29598 | L | A | MA | GE1 | Road Upgrading from Gravel to Paved along Butuan City-Talacogon-Loreto-Veruela-Sta. Josefa Rd, (K1345+625-K1349+326) | Talacogon, Agusan del Sur | 2013-08-21 | 1st | XIII | LF | 44.76 | 209 | 2013-03-05 | 2013-09-29 | 1.45 | O | 0.355 | 0.222 | 0.15 | 0.03 | 0.035 | 0.033 | 82.5 | -
Madyaw Construction & Dev. Corporation | 29598 | L | A | MA | GE1 | Conc. of Butuan City-Talacogon-Veruela-Sta. Josefa Rd., Km.1357+837-Km.1358+424 | La Paz, Agusan del Sur | 2013-03-19 | 2nd | XIII | LF | 35.076 | 301 | 2012-01-31 | 2012-11-27 | - | O | 0.322 | 0.3 | 0 | 0.03 | 0.03 | 0.033 | 71.5 | -
Madyaw Construction & Dev. Corporation | 29598 | L | A | MA | GE1 | Conc. of Butuan City-Talavera-Loreto-Veruela-Sta. Josefa Rd., Km.1354+(-874)-Km.1354+916 | La Paz, Agusan del Sur | 2012-08-18 | 1st | XIII | LF | 38.292 | 260 | 2012-01-29 | 2012-10-14 | -3.51 | O | 0.365 | 0.24 | 0.115 | 0.03 | 0.055 | 0.033 | 83.8 | -
Madyaw Construction & Dev. Corporation | 29598 | L | A | MA | GE1 | Conc. of Butuan City-Talacogon-Loreto-Veruela-Sta. Josefa Rd., Km.1354+(-874)-Km.1354+916 | La Paz, Agusan del Sur | 2013-03-19 | 2nd | XIII | LF | 39.775 | 336 | 2012-01-29 | 2012-12-29 | - | O | 0.258 | 0.3 | 0 | 0.03 | 0.044 | 0.033 | 66.5 | -
Madyaw Construction & Dev. Corporation | 29598 | L | A | MA | GE1 | Conc. of Butuan City-Talacogon-Loreto-Veruela-Sta. Josefa Rd., Km.1357+837-Km.1359+424 | La Paz, Agusan del Sur | 2012-08-18 | 1st | XIII | LF | 33.474 | 220 | 2012-01-31 | 2012-09-07 | -4.2 | O | 0.388 | 0.24 | 0.108 | 0.03 | 0.05 | 0.033 | 84.9 | -
Madyaw Construction & Dev. Corporation | 29598 |  |  |  |  | Conc. of Manapa Provincial Rd. |  | 2010-02-23 |  | XIII |  | 28.879 | 300 |  |  |  | O | 0.379 | 0.239 | 0.15 | 0.03 | 0.045 | 0.033 | 87.6 | -
Madyaw Construction & Dev. Corporation | 29598 | L | A | MA | GE1 | Completion of San Luis Footbridge, Old Poblacion |  | 2008-12-01 | 1st | XIII |  | 5.722 | 210 |  |  |  | O | 0.324 | 0.3 | 0.1 | 0.03 | 0.032 | 0.1 | 88.6 | -
Madyaw Construction & Dev. Corporation | 29598 | L | A | MA | GE1 | Conc.of Talacogon-La Paz Road Section along Butuan City-Talacogon-La Paz-Loreto Veruela-Sta. Josefa Road |  | 2009-06-09 | 2nd | XIII |  | 19.247 | 416 |  |  |  | O | 0.35 | 0.3 | 0.15 | 0.03 | 0.051 | 0.05 | 93.1 | -
Madyaw Construction & Dev. Corporation | 29598 | L | A | SB | GE4 | Const./Impvt. of Water Supply System (Hydrolic Ram Pump), Brgy. M.J. Santos |  | 2009-06-11 | 1st | XIII |  | 1.856 | 133 |  |  |  | O | 0.339 | 0.3 | 0.15 | 0.03 | 0.048 | 0.05 | 91.7 | -
Maer Summit Konstructs, Co. | 25262 | L |  | MA |  | PIDP/Lupon Irrigation System | Lupon, Davao Oriental/ Region 11 | 2014-05-17 | 1st | NIA | LF | 32.72 | 490 | 2013-07-03 | 2014-09-28 | 0.35 | O | 0.3435 | 0.2605 | 0.15 | 0.0075 | 0.055 | 0.05 | 86.65 | -
Maer Summit Konstructs, Co. | 25262 |  |  | MA |  | PIDP/Lupon Irrigation System | Lupon, Davao Oriental/ Region 11 | 2015-11-28 | 1st | NIA | LF | 32.72 | 490 | 2013-07-03 | 2015-12-03 | -1.35 | O | 0.3243 | 0.2852 | 0.1365 | 0.015 | 0.0467 | 0.05 | 85.77 | -
Maer Summit Konstrukt Co. (Formerly: Summit Konstrukt) | 25262 | L | A | MB | GE | Construction/ Improvement of Access Road leading to Declared Tourism Destination, Fatimal-Parola-Cape San Agustin Road leading to Cape San Agustin Island | Gov. Generoso, Davao Oriental | 2014-10-27 | 2nd | XI | LF | 47.04 | 224 | 2014-03-07 | 2014-10-16 |  | O | 0.363 | 0.3 | 0 | 0.03 | 0.06 | 0.017 | 77% | 77.00% Unsatisfactory
Maer Summit Konstrukt Co. (Formerly: Summit Konstrukt) | 25262 | L | A | MB | GE | Construction/Impv't. of Access Road Leading to Declared Tourism Destinations Fatima - Parola - Cape San Agustin | Gov. Generoso, Davao Oriental | 2014-08-11 | 1st | XI | LF | 47.04 | 209 | 2014-03-07 | 2014-09-01 | -3.31 | O | 0.363 | 0.286 | 0.117 | 0.03 | 0.047 | 0.033 | 87.6
Maer Summit Konstrukt Co. (Formerly: Summit Konstrukt) | 25262 | L | A | MB | GE | Replacement/ Completion of Quarry Bridge along Mati - Maragusan Road | Lupon, Davao Oriental | 2014-10-27 | 1st | XI | LF | 23.5199 | 227 | 2014-02-03 | 2014-09-17 |  | O | 0.392 | 0.3 | 0.006 | 0.03 | 0.06 | 0.017 | 80.5% | 80.50% Unsatisfactory
Maer Summit Konstrukt Co. (Formerly: Summit Konstrukt) | 25262 | L | A | MA | GE | Replacement of Camogna Bridge & Approaches along Tibanban – Lavigan Road. | Davao Oriental | 2014-08-11 | Final | XI | LF | 21.7817 | 225 | 2013-01-25 | 2013-09-20 | 0 | C | 0.471 | 0.2 | 0.3 |  |  |  | 97.1 | 83.96% Satisfactory
Maer Summit Konstrukt Co. (Formerly: Summit Konstrukt) | 25262 | L | A | MA | GE1 | Replacement of Camogna Bridge & Approaches along Tibanban-Lavigan Rd. | Governor Generoso, Davao Oriental | 2013-08-15 | 1st | XI | LF | 21.782 | 224 | 2013-01-25 | 2013-09-05 | -9.25 | O | 0.303 | 0.3 | 0.058 | 0.03 | 0.028 | 0.033 | 75.2
Maer Summit Konstrukt Co. (Formerly: Summit Konstrukt) | 25262 | L | A | MA | GE | Road Upgrading (Gravel to Paved) Tibanban-Lavigan Road (Brgy. Tagabebe - Brgy. Pundaguitan Section) | Davao Oriental | 2014-08-15 | Final | XI | LF | 47.7802 | 266 | 2013-03-06 | 2013-09-02 | 0 | C | 0.372 | 0.2 | 0.3 |  |  |  | 87.2 | 86.24% Satisfactory
Maer Summit Konstrukt Co. (Formerly: Summit Konstrukt) | 25262 | L | A | MA | GE1 | Road Upgrading (Gravel to Paved) Tibanban-Lavigan Rd. (Brgy. Tagabebe - Brgy. Pundaguitan Sect.) | Davao Oriental | 2013-08-14 | 1st | XI | LF | 47.787 | 203 | 2013-03-06 | 2013-09-24 | -7.09 | O | 0.385 | 0.3 | 0.079 | 0.03 | 0.045 | 0.017 | 85.6
Maer Summit Konstrukt Co. (Formerly: Summit Konstrukt) | 25262 | L | A | MA | GE1 | Rd. Upgrading (Gravel to Paved) Tibanban-Lavigan Rd., Km.1803+281-Km.1804+840 Nangan Sect. | Governor Generoso, Davao Oriental | 2013-08-14 | Final | XI | LF | 42.924 | 199 | 2013-01-25 | 2013-08-11 | 0 | C | 0.404 | 0.2 | 0.3 | - | - | - | 90.4 | 84.82% Satisfactory
Maer Summit Konstrukt Co. (Formerly: Summit Konstrukt) | 25262 | L | A | MA | GE1 | Rd. Upgrading (Gravel to Paved) along Tibanban-Lavigan Rd. Sect., a)Km.1803+281-Km.1804+840, Nangan Sect. | Governor Generoso, Davao Oriental | 2013-03-19 | 1st | XI | LF | 42.924 | 169 | 2013-01-25 | 2013-07-12 | 1.32 | O | 0.326 | 0.225 | 0.15 | 0.03 | 0.03 | 0.05 | 81.1 | -
Maer Summit Konstrukt Co. (Formerly: Summit Konstrukt) | 25262 | L | A | MA | GE1 | Road Upgrading (Gravel to Paved) Tibanban-Lavigan Rd.; a)Km. 1795+399.2-Km. 1796+171; b)Km. 1797+142-Km1798+525 | Governor Generoso, Davao Oriental | 2013-08-15 | Final | XI | LF | 38.594 | 190 | 2013-01-25 | 2013-08-02 | 0 | C | 0.418 | 0.133 | 0.3 | - | - | - | 85.1 | 83.54% Satisfactory
Maer Summit Konstrukt Co. (Formerly: Summit Konstrukt) | 25262 | L | A | MA | GE1 | Road Upgrading (Gravel to Paved) along Tibanban-Lavigan Rd. Sect., a)Km.1795+399.20-Km.1796+171; b)Km.1797+142-Km.1798+525 | Governor Generoso, Davao Oriental | 2013-03-19 | 1st | XI | LF | 38.594 | 167 | 2013-01-25 | 2013-07-10 | 2.39 | O | 0.33 | 0.235 | 0.15 | 0.03 | 0.03 | 0.05 | 82.5 | -
Maer Summit Konstrukt Co. (Formerly: Summit Konstrukt) | 25262 |  |  |  |  | Road Upgrading of Tibangan-Lavigan Rd., Nangan Sect. |  | 2010-06-08 |  | XI |  | 9.639 | 100 |  |  |  | O | 0.385 | 0.24 | 0.15 | 0.03 | 0.045 | 0.033 | 88.3 | -
Maer Summit Konstrukt Co. (Formerly: Summit Konstrukt) | 25262 |  |  |  |  | Road Upgrading of Tibanban-Lavigan Rd., Luzon-Tiblawan Sect. |  | 2010-06-08 |  | XI |  | 19.283 | 120 |  |  |  | O | 0.349 | 0.24 | 0.15 | 0.03 | 0.045 | 0.033 | 84.7 | -
Maer Summit Konstrukt Co. (Formerly: Summit Konstrukt) | 25262 |  |  |  |  | Road Upgrading of Tibanban-Lavigan Rd., Tagabebe-Pundaguitan Sect. |  | 2010-06-08 |  | XI |  | 19.279 | 120 |  |  |  | O | 0.332 | 0.24 | 0.15 | 0.03 | 0.045 | 0.05 | 84.7 | -
Maer Summit Konstrukt Co. (Formerly: Summit Konstrukt) | 25262 | L | B | SB | GB1 | Construction of Multi-Purpose Building |  | 2009-06-05 | 1st | XI |  | 4.723 | 230 |  |  |  | O | 0.387 | 0.266 | 0.15 | 0.03 | 0.043 | 0.033 | 90.9 | -
MAER SUMMIT KONSTRUKT CO. (Formerly: Summit Konstrukt) | 25262 | L | A | MB | GE | Compl. of Camogna Bridge & Approaches (B01132MN) along Tibanban-Lavigan Road | Governor Generoso, Davao Oriental | 2015-06-07 | Final | Davao Oriental 2nd | LF | 9.701 | 155 | 2015-02-09 | 2015-07-13 | 0% | C | 0.409 | 0.133 | 0.3 | - | - | - | 84.2% | *84.2% Satisfactory
Mafil Builders, Inc. | 35845 | L | D | SB | GB | Const. of Multi-Purpose Building for Evacuation Center, Brgy. Mandaing Cabanglasan, Bukidnon | Cabanglasan, Bukidnon | 2014-10-24 | 1st & Final | X | LF | 1.8849 | 105 | 2014-06-19 | 2014-10-01 | 0% | C | 0.44 | 0.146 | 0.3 | - | - | - | 88.6% | 88.6% Satisfactory
Mafil Builders, Inc. | 35845 | L | D | SB | GE | MajorRepair/Maintenance of Existing Permanent Bridge along Kibawe-Kadingilan Road | Ukitan Bridge, K1592+407-K1592+427 (Bridge No.B01448MN) | 2014-08-07 | 1st & Final | X | LF | 4.745 | 60 | 2014-01-23 | 2014-05-02 | 0 | C | 0.281 | 0.113 | 0.3 |  |  |  | 69.4 | 69.40% Poor
MAFIL BUILDERS, INC. | 35845 | L | D | SB | GB | Construction of School Buildings at Impasug-ong NHS-Kapitan Bayong Annex, Impasug-ong, Bukidnon | Impasug-ong, Bukidnon | 2015-08-28 | 1st | Bukidnon 1st DEO | LF | 5.296 | 120 | 2015-07-27 | 2015-11-23 | 14.48% | O | 0.393 | 0.24 | 0.15 | 0.03 | 0.058 | 0.05 | 92.1% | -
MAFIL BUILDERS, INC. | 35845 | L | D | SB | GB | Construction of School Buildings at Impasug-ong NHS-Kapitan Bayong Annex, Impasug-ong, Bukidnon | Impasug-ong, Bukidnon | 2015-11-12 | 2nd | Bukidnon 1st | LF | 5.2958 | 120 | 2015-07-27 | 2015-11-24 | (+) 2.84% | OG | 0.395 | 0.2 | 0.15 | 0.03 | 0.047 | 0.05 | 87.2% | 87.2% Satisfactory
Mafil Enterprises | 27226 |  |  |  |  | Road Upgrading (Gravel to Paved) Jct. Dologon-Panadtalan Road |  | 2010-06-15 |  | X |  | 4.713 | 75 |  |  |  | O | 0.353 | 0.24 | 0.15 | 0.023 | 0.05 | 0.033 | 84.9 | -
MAG CORPORATION | 36929 | L | C | SB | GB | Construction of One Storey Three Classroom School Building with Toilet Attached Tagongon Elementary School, Tagbina, Surigao del Sur | Tagbina, Surigao del Sur | 2015-11-12 | 1st | Surigao del Sur 2nd DEO | LF | 2.9174 | 120 | 2015-09-08 | 2016-01-05 | (+) 6.01 | OG | 0.309 | 0.24 | 0.15 | 0.03 | 0.047 | 0.05 | 82.6% | 82.6% Satisfactory
Maghayup Construction | 21641 | L | D | SB | GE2 | Malinao Service Area | Biis, Bayongan Area, Bohol, Region 7 | 2013-07-13 | 1st | NIA | L | 4.592 | 120 | 2013-02-11 | 2013-06-25 | 2.31 | O | 0.27 | 0.3 | 0.15 | 0.02 | 0.07 | 0.03 | 84 | -
Maghuyop Construction | 21641 | L | D | SB | GB1 | Const./Renovation/Completion/ Expansion of MPB | Loay, Bohol | 2011-03-29 | 1st | VII | LF | 0.481 | 150 | 2010-12-16 | 2011-05-14 | 15.67 | O | 0.356 | 0.268 | 0.15 | 0.03 | 0.064 | 0.05 | 91.8 | -
MAGNA RICH TRADING & CONSTRUCTION | 29108 | L | B | MB | GB | Construction of Multi-Purpose Building | Brgy. Layug, Cavinti, Laguna | 2015-06-07 | Final | Laguna 1st DEO | LF | 4.046 | 90 | 2015-02-12 | 2015-05-12 | 0% | C | 0.397 | 0.133 | 0.3 | - | - | - | 83% | *83% Satisfactory
MAI CONSTRUCTION & SUPPLY | 30839 | L | D | SB | GE | Construction of River Control along Jimamala River, Jimamala, Lutay, Tayasan, Negros Oriental | Jimamala, Lutay, Tayasan, Negros Oriental | 2015-11-10 | Final | Negros Oriental 1st DEO | LF | 6.064 | 117 | 2014-11-19 | 2015-03-15 | - | C | 0.451 | 0.133 | 0.3 | - | - | - | 88.4% | 88.4% Satisfactory
MAI CONSTRUCTION & SUPPLY | 30839 | L | D | SB | GE | Road Upgrading (unpaved to paved) based on Gravel Road Strategies (HDM-4) Project Analysis (Intermittent) along Guihulngan - Baloc - Isabela Road (GBIR), Sec. 1: K0120+707-K0120+735, K0120+755-K0120+804; Sect. 2: K0122+007-K0122+092.5; Sect. 3: K0122+354-K0122+459; Sect. 4: K0124+553-K0124+593; Sect. 5: K0129+028-K0129+041, Negros Oriental | Negros Oriental | 2015-11-09 | Final | Negros Oriental 1st DEO | LF | 8.3237 | 123 | 2015-03-09 | 2015-07-09 | - | C | 0.462 | 0.134 | 0.3 | - | - | - | 89.6% | 89.6% Very Satisfactory
Makapa Builders | 30029 | L | A |  | GE5 | Construction of Back-up Area, RC Platform & RoRo Ramp | Port of Pio Duran, Albay | 2013-03-08 | 1st | PPA | LF | 64.309 | 360 | 2012-10-17 | 2013-10-11 | 4.913 | O | 0.397 | 0.24 | 0.15 | 0.03 | 0.065 | 0.05 | 93.2 | -
MAKAPA CONSTRUCTION | 30029 | L | AA | MA | GE | Const./Improvement of Donsol River Control (Major River), Donsol, Sorsogon | Donsol, Sorsogon | 2015-09-01 | 1st | Sorsogon First DEO | LF | 46.541 | 210 | 2015-02-20 | 2015-09-17 | 0.98% | O | 0.379 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 89.9% | -
MAKAPA CORP./ORIENT STAR CONST., INC.-J.V | 9037 | L | AA | MB | GE-5 | Bulalacao Port Expansion Project | Bulalacao, Oriental Mindoro | 2015-11-06 | 1st | PPA | LF | 108.606 | 420 | 2015-02-05 | 2015-03-30 | -10.406 | O | 0.4 | 0.3 | 0.046 | 0.03 | 0.07 | 0.033 | 87.9 | -
Makapa Corporation | 30029 | L | A |  | GE5 | Construction of Back-up Area, RC Platform and RoRo Ramp | Port of Pio Duran, Pio Duran, Albay | 2013-07-19 | 2nd | PPA | L | 64.309 | 360 | 2012-10-17 | 2013-11-11 | 0.111 | O | 0.394 | 0.3 | 0.15 | 0.03 | 0.06 | 0.033 | 96.7 | -
Makapa Corporation | 30029 | L | AA | MA | GE | Oas Flood Control, Busac Section | Oas, Albay | 2014-08-16 | 1st & Final | V | LF | 7.7886 | 200 | 2014-07-18 | 2015-02-02 | 1 | C | 0.341 | 0.2 | 0.3 |  |  |  | 84.1 | 84.10% Satisfactory
Makapa Corporation | 30029 | L | A |  | GE-5 | Construction of Back-Up Area, RC Platform and RoRo Ramp | Port of Pio Duran, Pio Duran, Albay | 2014-02-27 | 3rd & Final | PPA | LF | 65.426 | 419 | 2012-10-17 | 2013-12-08 | 0 | C | 0.438 | 0.2 | 0.3 | - | - | - | 93.8 | 94.29% Very Satisfactory
Makapa Corporation | 30029 | L | A | MA | GE1 | Road Upgrading (Gravel to Paved) (Intermittent Sect.), Albay West Coast Road, K0549+600-K0553+305.30 w/ exceptions | Albay | 2013-03-19 | Final | V | LF | 52.625 | 240 | 2012-07-06 | 2013-03-02 | 0 | C | 0.363 | 0.2 | 0.3 | - | - | - | 86.3 | 88.46% Satisfactory
Makapa Corporation | 30029 | L | A | MA | GE1 | Const./Upgrading of Malidong-Buenavista Rd. going to Tourist Destination (Butanding) | Pioduran, Albay | 2013-03-19 | Final | V | LF | 27.652 | 210 | 2012-02-10 | 2012-09-06 | 0 | C | 0.358 | 0.2 | 0.3 | - | - | - | 85.8 | 86.76% Satisfactory
Makapa Corporation | 30029 | L | A | MA | GE1 | Rehab./Reconst./Strengthening of Maonon Bridge along Albay West Coast Rd., Brgy. Maonon, Ligao City K0546+658- 0564+694, Brgy. Maonon | Ligao City, Albay | 2013-03-19 | Final | V | LF | 17.319 | 330 | 2012-03-16 | 2013-02-08 | 0 | C | 0.383 | 0.171 | 0.3 | - | - | - | 85.4 | 86.33% Satisfactory
MAKAPA CORPORATION | 30029 | L | AA | MB | GE | Const./Impvt. of Access Road Leading to Declared Tourism Destination/Upgrading of Donsol-Sta. Cruz Road Leading to Butanding, Donsol, Sorsogon | Donsol, Sorsogon | 2015-09-01 | 1st | Sorsogon First DEO | LF | 46.541 | 270 | 2015-03-26 | 2015-12-20 | 6.78% | O | 0.302 | 0.286 | 0.15 | 0.03 | 0.06 | 0.05 | 87.8% | -
MAKAPA CORPORATION | 30029 | L | AA | MA | GE | Const./Improvement of Donsol River Control (Major River), Donsol, Sorsogon | Donsol, Sorsogon | 2015-11-19 | Final | Sorsogon First DEO | LF | 46.5412 | 240 | 2015-02-20 | 2015-10-17 | 1.40% | C | 0.456 | 0.086 | 0.3 | - | - | - | 84.2% | 87.62% Satisfactory
Malta Construction & Supply | 29173 | L |  | SB | GB | Construction of Multi Purpose Building at Brgy. Sierra | Lapaz, Tarlac | 2014-08-05 | 1st & Final | III | LF | 2.6539 | 60 | 2014-05-13 | 2014-07-11 | 0 | C | 0.417 | 0.133 | 0.3 |  |  |  | 85 | 85.00% Satisfactory
Mamsar Construction & Industrial Corporation (Formerly: Mamsar Enterprises Agro-Industrial Corporation) | 15885 | L | AA | LA | GE | Const. & Maintenance of Bridges along National Roads: Rehab./Reconst./ Replacement/Retrofitting of Existing Permanent Bridges, (Bauyan Bridge along Malabang - Dobleston - Tukuran Road, Lanao del Norte) | SND, Lanao del Norte | 2014-08-13 | 1st | X | LF | 46.4839 | 207 | 2014-02-13 | 2014-09-07 | 0.94 | O | 0.4 | 0.3 | 0.15 | 0.018 | 0.047 | 0.05 | 96.5
Mamsar Construction & Industrial Corporation (Formerly: Mamsar Enterprises Agro-Industrial Corporation) | 15885 | L | AA | LA | GE | Preventive Maintenance Based on PMS/HDM-4 (Intermittent Section), Surigao - Davao Coastal Road, Km. 1147+(-910) - Km. 1148+000 | Placer, Surigao del Norte | 2014-08-13 | 1st & Final | XIII | LF | 16.1309 | 76 | 2014-02-24 | 2014-05-10 | 1.6 | C | 0.414 | 0.137 | 0.3 |  |  |  | 85.1 | 85.10% Satisfactory
Mamsar Construction & Industrial Corporation (Formerly: Mamsar Enterprises Agro-Industrial Corporation) | 6845 | L | AA | LA | GE | Road Upgrading (Gravel to Paved) along Butuan City - Talacogon - Loreto - Veruela - Sta. Josefa Road, K1389+(-407) - K1389+514 & K1389+514 - K1389+574 with Exception | Veruela, Agusan del Sur | 2014-08-08 | 1st | XIII | LF | 19.0421 | 177 | 2014-03-19 | 2014-09-11 | 13.77 | O | 0.35 | 0.205 | 0.15 | 0.03 | 0.042 | 0.05 | 82.7
MAMSAR CONSTRUCTION & INDUSTRIAL CORPORATION (Formerly: Mamsar Enterprises Agro-Industrial Corporation) | 15885 | L | AA | LA | GE | Construction & Maintenance of Bridges along National Roads, Rehabilitation/Reconstruction/Replacement/Retrofitting of Existing Permanent Bridges, Bauyan Bridge, Malabang-Dobleston-Tukuran Road, SND, Lanao del Norte | Malabang-Dobleston-Tukuran Road, SND, Lanao del Norte | 2015-06-07 | Final | Lanao del Norte First DEO | LF | 48.738 | 252 | 2014-02-13 | 2014-10-22 | - | C | 0.466 | 0.188 | 0.3 | - | - | - | 95.4% | *96.06% Outstanding
Mamsar Construction and Industrial Corporation | 15885 |  |  |  |  | Const. of Shore Protection including RC Pier /Wharf and Reclamation Area, DPWH, RES |  | 2010-03-09 |  | XI |  | 106.212 | 400 |  |  |  | O | 0.328 | 0.3 | 0.15 | 0.03 | 0.045 | 0.033 | 88.6 | -
Mamsar Construction and Industrial Corporation | 15885 | L | AA | LA | GE | Replacement of Del Mores Bridge along Mabini - Tubajon Road, Tubajon, Dinagat Islands | Tubajon, Dinagat Islands | 2014-10-27 | 1st | XIII | LF | 18.2218 | 220 | 2014-03-18 | 2014-10-23 | -19.63% | O | 0.337 | 0.3 | 0 | 0.02 | 0.056 | 0.033 | 74.6% | 74.6% Poor
Mamsar Construction and Industrial Corporation (Formerly: Mamsar Enterprises Agro-Industrial Corporation) | 15885 | L | AA | LA | GE1 | Const. of Iligan City Circ. Rd. (Phase II) incl. Protection Works Iligan City Circ. Road (C-3), K0+202-K0+640 (Sect. I-Scion), K0+300-K01+600 (Sect. 2 Ubaldo Sect. w/ exception) | Iligan City | 2013-08-17 | 1st | X | LF | 42.24 | 179 | 2013-01-28 | 2013-07-25 | 16.97 | O | 0.313 | 0.24 | 0.15 | 0.03 | 0.047 | 0.05 | 83
Mamsar Construction and Industrial Corporation (Formerly: Mamsar Enterprises Agro-Industrial Corporation) | 15885 | L | AA | MA | GE2 | Const. of Slope Protection along Linamon-Zamboanga Rd., Maigo, Lanao del Norte, Km.1562+577.85, Const. of 124.80m, Flood Control using Pre Cast Concrete Sheet Piles & Class A Grouted Riprap | Maigo, Lanao del Norte | 2013-03-15 | Final | X | LF | 11.905 | 210 | 2012-07-19 | 2013-02-13 | 8.95 | C | 0.415 | 0.144 | 0.3 | - | - | - | 85.9 | 86.08% Satisfactory
Mamsar Construction and Industrial Corporation (Formerly: Mamsar Enterprises Agro-Industrial Corporation) | 15885 | L | AA | LA | GE1 | Const. of Balo-i Bridge | Balo-i, Lanao del Norte | 2013-03-13 | Final | X | LF | 28.545 | 488 | 2011-08-15 | 2012-12-14 | 0 | C | 0.434 | 0.163 | 0.3 | - | - | - | 89.7 | 85.47% Satisfactory
Mamsar Construction and Industrial Corporation (Formerly: Mamsar Enterprises Agro-Industrial Corporation) | 15885 | L | AA | LA | GE1 | New Const./Completion/Continuation of Unfinished/On-going Bridge at Baloi across Agus Bridge River | Balo-I, Lanao del Norte | 2013-03-13 | Final | X | LF | 19.002 | 348 | 2012-01-24 | 2013-01-05 | 2.59 | C | 0.388 | 0.189 | 0.3 | - | - | - | 87.7 | 83.38% Satisfactory
Mamsar Construction and Industrial Corporation (Formerly: Mamsar Enterprises Agro-Industrial Corporation) | 15885 |  |  |  |  | Rehab./Reconst./Upgrading along Misamis Oriental-Ma.Cristina Bdry. Road Iligan City Central Section, Sta.1525+619.7 - Sta.1526+083.2 |  | 2010-07-07 |  | X |  | 13.899 | 148 |  |  |  | O | 0.388 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 91.3 | -
Mamsar Construction and Industrial Corporation (Formerly: Mamsar Enterprises Agro-Industrial Corporation) | 15885 | L | AA | LA | GE1 | Reconst. of Nat'l Arterial Rds. (Intermittent Sect.), Surigao-Davao Coastal Rd., Brgy. Pananay-an | Placer, Surigao del Norte | 2013-03-14 | 1st | XIII | LF | 6.741 | 45 | 2013-02-18 | 2013-04-03 | 48.33 | O | 0.292 | 0.3 | 0.15 | 0.03 | 0.045 | 0.033 | 85 | -
MAMSAR CONSTRUCTION AND INDUSTRIAL CORPORATION (Formerly: Mamsar Enterprises Agro-Industrial Corporation) | 15885 | L | AA | LA | GE | Construction of New Permanent Bridge, Maranding Bridge 2 along Linamon - Zamboanga Road, K1602+873.19 to K1602+935.69, Lanao del Norte | K1602+873.19 to K1602+935.69, Lanao del Norte | 2015-08-31 | 1st | Regional Office No. X | LF | 61.338 | 282 | 2015-03-25 | 2015-12-31 | 0.5% | O | 0.4 | 0.24 | 0.15 | 0.018 | 0.045 | 0.05 | 90.3% | -
MAMSAR CONSTRUCTION AND INDUSTRIAL CORPORATION (Formerly: Mamsar Enterprises Agro-Industrial Corporation) | 15885 | L | AA | LA | GE | Completion of Kabangahan Bridge along Sta. Felomina-Bonbonon-Digkilaaan-Rogongon Road, Brgy. Rogongon, Iligan City | Brgy. Rogongon, Iligan City | 2015-09-03 | 1st & Final | Lanao del Norte 2nd DEO | LF | 16.55 | 210 | 2015-02-18 | 2015-09-15 | 7.06% | C | 0.493 | 0.133 | 0.3 | - | - | - | 92.6% | *92.60% Very Satisfactory
MAMSAR CONSTRUCTION AND INDUSTRIAL CORPORATION (Formerly: Mamsar Enterprises Agro-Industrial Corporation) / GRAND BUILDERS JOINT VENTURE | JV-14-360 | L | AA | MA | GE | Construction/Rehabilitation of Revetment Upstream of Mandulog Bridge I, K03+113 to K00+260, Iligan City | K03+113 to K00+260, Iligan City | 2015-09-03 | 1st | Lanao del Norte 2nd DEO | LF | 35.707 | 221 | 2015-02-18 | 2015-09-26 | 0.74% | O | 0.366 | 0.277 | 0.15 | 0.024 | 0.055 | 0.05 | 92.2% | -
Mamsar Construction and Industrial Corpration (Formerly: Mamsar Enterprises Agro-Industrial Corporation) | 15885 | L | AA | LA | GE1 | Reconst. of Nat'l Arterial Rd. (Int. Sect.), Surigao-Davao Coastal Rd., Brgy. Pananay-an | Placer, Surigao del Norte | 2013-08-08 | Final | XIII | LF | 6.741 | 45 | 2013-02-18 | 2013-04-03 | 1.8 | C | 0.39 | 0.133 | 0.3 | - | - | - | 82.3 | 83.92% Satisfactory
Manuel A. Dela Torre, Jr. Builders | 31024 | L | B | SB | GE2 | Repair & Maint. of Slope Protection along Buga Creek | San Miguel, Bulacan | 2013-03-20 | Final | III | LF | 1.96 | 80 | 2012-10-04 | 2012-12-22 | 11.58 | C | 0.433 | 0.133 | 0.3 | - | - | - | 86.6 | 84.56% Satisfactory
Marbel Dynamic Builders | 6150 | L | D | SB | GE1 | Const. of Reinforced Concrete Box Culvert Rd.-CLS Rd., Brgy. Cabuling | Banga, South Cotabato | 2013-08-06 | Final | XII | LF | 4.29 | 120 | 2012-12-04 | 2013-04-02 | 0.62 | C | 0.434 | 0.133 | 0.3 | - | - | - | 86.7 | 90.30% V. Satisfactory
Marbel Dynamic Builders | 6150 | L | D | SB | GE1 | Const. of Reinforced Concrete Box Culvert-CLS Rd., Brgy. Cabuling | Banga, South Cotabato | 2013-03-20 | 1st | XII | LF | 4.29 | 120 | 2012-12-04 | 2013-04-02 | 1.33 | O | 0.359 | 0.3 | 0.15 | 0.03 | 0.055 | 0.033 | 92.7 | -
MARBEL DYNAMIC BUILDERS | 6150 | L | D | SB | GB | Construction of Multi-Purpose Building | Brgy. Lagao, General Santos City | 2015-08-29 | 1st & Final | South Cotabato II | LF | 2.955 | 75 | 2015-04-20 | 2015-07-03 | (+)1.50% | C | 0.424 | 0.133 | 0.3 | - | - | - | 85.7% | *85.7% Satisfactory
Marcbilt Construction, Inc. | 21844 | L | AAA | LB | GE1 | Const. of Manila-Cavite Coastal Rd. (Service Rd.) | Parañaque City, M.M. | 2013-03-21 | Final | NCR | LF | 36.789 | 328 | 2012-02-28 | 2013-01-20 | 2.13 | C | 0.451 | 0.107 | 0.3 | - | - | - | 85.8 | 86.22% Satisfactory
Marcbilt Construction, Inc. | 21844 | L | AAA | LB | GE1 | Rehab./Reconst. (Conc.) of Dasmariñas-Carmona Road |  | 2008-11-12 | 1st | IV-A |  | 28.92 | 180 |  |  |  | O | 0.341 | 0.202 | 0.1 | 0.03 | 0.037 | 0.1 | 81 | -
Marcbilt Construction, Inc. | 21844 | L | AAA | LB | GE | Widening of Cavite-Batangas Road, Silang Seciton Including Drainage System, K0041+000 to K0041+730, 5th Legislative District | Silang, Cavite | 2014-08-05 | 1st | IV-A | LF | 22.3729 | 171 | 2014-04-22 | 2014-10-09 | 21.8 | O | 0.386 | 0.3 | 0 | 0.03 | 0.059 | 0.033 | 80.8
Marcbilt Construction, Inc. | 21844 | L | AAA | LB | GE1 | Asphalt Overlay of Lucena-Tayabas-Mauban Port Rd., K0128+(-972)-K0128+000 | Lucena City | 2013-08-03 | Final | IVA | LF | 6.492 | 140 | 2013-02-06 | 2013-06-25 | 0 | C | 0.467 | 0.133 | 0.3 | - | - | - | 90 | 89.88% V. Satisfactory
Marcbilt Construction, Inc. | 21844 | L | AAA | LB | GE1 | Asphalt Overlay of Lucena-Tayabas-Mauban Port Rd., K0128+(-)972-K0128+000 | Lucena City | 2013-03-16 | 1st | IVA | LF | 6.492 | 140 | 2013-02-06 | 2013-06-25 | 34.23 | O | 0.34 | 0.3 | 0.15 | 0.03 | 0.045 | 0.033 | 89.8 | -
Marcbilt Construction, Inc. | 21844 |  |  |  |  | Const. (Opening/Widening/Conc.) of CALA-Daang Hari Rd. Bdry. (Pasong Buwaya 2 Sect. |  | 2010-05-31 |  | IVA |  | 37.952 | 215 |  |  |  | O | 0.349 | 0.3 | 0.15 | 0.03 | 0.045 | 0.033 | 90.7 | -
Marcbilt Construction, Inc. | 21844 | L | AAA | LB | GE1 | Road Upgrading (gravel to paved), MWCR, Sablayan-Sta. Cruz (Buenavista-Sto. Nino Section) KO 322+594- KO 323+465.65 to KO 323+622-KO 324+472 |  | 2009-08-31 | 2nd | IVB |  | 19.3 | 140 |  |  |  | O | 0.351 | 0.292 | 0.15 | 0.03 | 0.042 | 0.033 | 89.8 | -
Marcbilt Construction, Inc. | 21844 | L | AAA | LB | GE1 | Road Upgrading (Gravel to Paved) MWCR, Sablayan-Sta. Cruz (Buenavista-Sto. Nino Section) |  | 2009-05-29 | 1st | IV-B |  | 19.112 | 140 |  |  |  | O | 0.305 | 0.29 | 0.15 | 0.03 | 0.025 | 0.05 | 85 | -
Marcbilt Construction, Inc. | 21844 | L | AAA | LB | GE1 | Road Upgrading (gravel to paved), MWCR, (San Francisco Section) KO 332+300- KO 334+755 |  | 2009-08-30 | 2nd | IVB |  | 28.659 | 165 |  |  |  | O | 0.337 | 0.3 | 0.15 | 0.03 | 0.042 | 0.033 | 89.2 | -
Marcbilt Construction, Inc. | 21844 | L | AAA | LB | GE1 | Road Upgrading (Gravel to Paved) MWCR, (San Francisco Section) |  | 2009-05-29 | 1st | IV-B |  | 28.659 | 150 |  |  |  | O | 0.303 | 0.3 | 0.15 | 0.03 | 0.035 | 0.05 | 86.8 | -
MARCBILT CONSTRUCTION, INC. | 21844 | L | AAA | LB | GE | Asset Preservation of National Roads, Preventive Maintenance based on Highway Development & Management-4 (HDM-4), Cavite-Batangas Road | Cavite 5th LD, Cavite Province | 2015-09-05 | 1st & Final | Regional Office No. IV-A | LF | 91.888 | 294 | 2014-06-02 | 2015-03-22 | 0% | C | 0.398 | 0.133 | 0.3 | - | - | - | 83.1% | *83.1% Satisfactory
MARCBILT CONSTRUCTION, INC. | 21844 | L | AAA | LB | GE | National Road Network Services, Asset Preservation of National Roads, Network Development, Widening of National Roads, Secondary Roads, Carmona Division Road K0046+671 - K0047+598 (Rehabilitation) Carmona, Cavite | Carmona, Cavite | 2015-11-11 | Final | CAVITE 1ST DEO | LF | 21.0763 | 130 | 2015-07-02 | 2015-11-08 | - | C | 0.439 | 0.133 | 0.3 | - | - | - | 87.2% | 87.2% Satisfactory
MARCBILT CONSTRUCTION, INC. | 21844 | L | AAA | LB | GE | Off-Carriageway Impv't. Paving of Shoulder & Drainage Imprv't of Secondary N/R along Mindoro Oriental/Occidental East Coastal Road K0221+700 - K0223+500 | Magsaysay, Occidental Mindoro | 2015-11-18 | 1st | Mindoro Occidental DEO | LF | 40.3009 | 288 | 2015-03-30 | 2016-01-11 | -0.05 | OG | 0.378 | 0.3 | 0.1 | 0.018 | 0.035 | 0.033 | 86.4% | 86.4% Satisfactory
MARCBILT CONSTRUCTION, INC./ SAN MARCELINO BUILDERS, INC. (JOINT VENTURE) | JV-13-281 | L | AAA | LB | GE | Road Upgrading (Gravel to Paved) based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standard (HDM- 4 Project Analysis Intermittent Section) Secondary Road, Jct. MWCR (Bagong Silang)- Cabacao Diversion Road, K0425+633.7- K0427+746 | Abra de Ilog, Occidental Mindoro | 2015-06-08 | Final | Mindoro Occidental DEO | LF | 41.998 | 269 | 2014-06-01 | 2015-02-24 | 0% | C | 0.464 | 0.133 | 0.3 | - | - | - | 89.7% | *87.72% Satisfactory
Marcbilt Construction, Inc./Mirasol M. Medina Construction & Trading (JV) | - | L | - | - | - | Widening of Convento Bridge along Naic Junction-Caylabne Road | K0048+252, 7th Legislative District | 2014-11-07 | 1st | IV | LF | 21.6813 | 255 | 2014-04-07 | 2014-12-17 | 0.53% | O | 0.359 | 0.3 | 0.15 | 0.03 | 0.035 | 0.033 | 90.7% | 90.7% Very Satisfactory
Marcbilt Construction, Inc./San Marcelino Builders, Inc. Joint Venture | 21844 | L | AAA | LB | GE | Preventive Maintenance (Asphalt Overlay) along Lucena-Tayabas-Lucena-Sampaloc-Mauban Port Road, K0140+042 to K0141+565 and k0143+475 to K0144+455 | Sampaloc, Quezon | 2014-08-14 | 1st & Final | IV-A | LF | 36.5182 | 69 | 2014-02-20 | 2014-04-29 | 25 | C | 0.449 | 0.2 | 0.3 |  |  |  | 94.9 | 94.90% Very Satisfactory
Marcbilt Construction, Inc./San Marcelino Builders, Inc. Joint Venture | JV-13-281 | L | AAA | LB | GE | Road Upgrading ( Gravel to Paved) based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standard (HDM- 4 Project Analysis Intermittent Secion) Secondary Road, JCT. MWCR (Baging Silang)-Cabacao Diversion Road, K0425+690-K0427+059 | Abra de Ilog, Occidental Mindoro | 2014-11-25 | 1st & Final | IV | LF | 41.9976 | 239 | 2014-06-01 | 2015-01-25 | -7% | C | 0.282 | 0.286 | 0.08 | - | - | - | 76.6% | 76.6% Unsatisfactory
Marcbilt Construction, Inc./San Marcelino Builders, Inc. Joint Venture | JV-13-281 | L | AAA | LB | GE | Road Upgrading (Gravel to Paved) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standards (HDM-4 Project Analysis), Secondary Road, Jct. MWCR (Bagong Silang) - Cabacao Diversion Road, K0425+633.7 - K0427+746 | Abra de Ilog, Occidental Mindoro | 2014-08-14 | 1st | IV-B | LF | 38.7575 | 209 | 2014-06-01 | 2014-12-26 | 21.08 | O | 0.369 | 0.237 | 0.15 | 0.03 | 0.045 | 0.033 | 86.4
MARCIVAN CONSTRUCTION AND SUPPLY | 36958 | L | C | SB | GB | Const. of Multi-Purpose Building, Cabatuan, Buhi, Camarines Sur | Cabatuan, Buhi, Camarines Sur | 2015-11-16 | Final | Camarines Sur Fourth DEO | LF | 2.225 | 65 | 2015-02-09 | 2015-04-14 | 3.08% | C | 0.349 | 0.2 | 0.3 | - | - | - | 84.9% | 84.9% Satisfactory
Marcons Builder | 8044 | L | A | MB | GB1 | Const. of MPB, Caba NHS, Pob. Norte | Caba, La Union | 2013-08-01 | Final | I | LF | 4.914 | 238 | 2012-09-18 | 2013-05-14 | 22.27 | C | 0.474 | 0.133 | 0.3 | - | - | - | 90.7 | 88.74% Satisfactory
Marcons Builder | 8044 | L | A | MB | GB1 | Const. of Mpb, Caba NHS, Pob. Norte | Caba, La Union | 2013-03-12 | 2nd | I | LF | 4.699 | 238 | 2012-09-18 | 2013-05-14 | 11.05 | O | 0.395 | 0.3 | 0.15 | 0.01 | 0.032 | 0.033 | 92 | -
Marcons Builder | 8044 | L | A | MB | GE1 | Const. (Road Opening) of Missing Links of National Road, Sallapadan-Tubo, Abra-Cervantes, Ilocos Sur, Abra Side, Km.467+100 - Km.484+000 | Abra | 2011-03-30 | 1st | CAR | LF | 65.204 | 470 | 2010-09-02 | 2011-12-16 | 30.46 | O | 0.317 | 0.272 | 0.15 | 0.02 | 0.027 | 0.033 | 81.9 | -
Marcons Builder | 8044 | L | A | MA | GB1 | Const. of DPWH Regional Office Building, Phase V |  | 2009-03-13 | 2nd | CAR |  | 24.058 | 360 |  |  |  | O | 0.361 | 0.276 | 0.15 | 0.03 | 0.056 | 0.033 | #VALUE! | -
Marcons Builder | 8044 | L | A | MA | GB1 | Const. of DPWH Regional Office Building (Phase V) |  | 2008-08-29 | 1st | CAR |  | 24.059 | 360 |  |  |  | O | 0.376 | 0.3 | 0.1 | 0.03 | 0.047 | 0.1 | 95.3 | -
Marcons Builder | 8044 | L | A | MB | GB1 | Const. of MPB, Caba Nat'l High Sch., Pob. Norte | Caba, La Union | 2012-11-25 | 1st | I | LF | 4.699 | 238 | 2012-09-18 | 2013-05-13 | 4.56 | O | 0.317 | 0.3 | 0.15 | 0.02 | 0.018 | 0.033 | 83.8 | -
Marcons Builders | 8044 | L | A | MB | GE1 | Const. (Road Opening) of Missing Links of Nat'l Rd. Sallapadan-Tubo, Abra-Cervantes, Ilocos Sur, Abra Side Km.467+100-Km.484+000 | Abra | 2011-08-03 | 2nd | CAR | LF | 65.204 | 470 | 2010-09-02 | 2011-12-15 | 3.96 | O | 0.292 | 0.238 | 0.15 | 0.023 | 0.033 | 0.033 | 76.9 | -
MARCPHIL CONSTRUCTION/WAYCON BUILDERS & CONSTRUCTION SUPPLY (JV) | JV-14-610 | L | B | MA | GE | Road Upgrading (Concrete Paving) along Mulanay - San Francisco Road (S02057LZ) | Barangay Pakiing, Mulanay, Quezon | 2015-06-08 | 1st | Quezon 3rd DEO | LF | 44.247 | 180 | 2015-04-28 | 2015-10-24 | 25.16% | O | 0.347 | 0.239 | 0.15 | 0.03 | 0.056 | 0.033 | 85.5% | -
Marcus Construction | 12601 | L | A | MA | GE | Flood Control Structure at USM (Phase 2) along Kabacan River, USM, Kabacan, Cotabato Km. 1649+105.41 - Km. 1649+160 | Kabacan, Cotabato | 2014-10-25 | 1st & Final | XII | LF | 11.7587 | 178 | 2014-02-28 | 2014-08-24 | 1.74% | C | 0.473 | 0.133 | 0.3 | - | - | - | 90.6% | 90.6% Very Satisfactory
Marcus Construction | 12601 | L | A | MB | GE | Widening of Road along Davao - Cotabato - Road Katidtuan - Osias Section, Kabacan, Cotabato, Km. 1644+(-232) - Km. 1644+463.36 and Km. 1644+495.20 - Km. 1646+280 both sides | Kabacan, Cotabato | 2014-10-25 | 1st & Final | XII | LF | 47.2413 | 178 | 2014-02-28 | 2014-08-24 | 1.25% | C | 0.472 | 0.133 | 0.3 | - | - | - | 90.5% | 90.5% Very Satisfactory
Marcus Construction | 12601 | L | A | MB | GE | Widening of Road Davao-Cotabato Road, Katidtuan - Osias Section, Cotabato Road | Kabacan, Cotabato | 2014-08-11 | 1st | XII | LF | 47.2413 | 178 | 2014-02-28 | 2014-08-24 | 2.95 | O | 0.329 | 0.297 | 0.15 | 0.03 | 0.05 | 0.05 | 90.6
Marcus Construction | 12601 | L | A | MA | GE1 | Rehab./Impvt. of Bukidnon-Cotabato National Road (Tambad Sect.), Brgy. Tambad |  | 2009-09-03 | 1st | XII |  | 57.136 | 289 |  |  |  | O | 0.368 | 0.3 | 0.15 | 0.03 | 0.033 | 0.033 | 91.4 | -
Marcus Construction | 12601 | L | A | MA | GE1 | Const. of Slope Protection Works along Dualing-New Panay-Midsayap Road (Arizona Section) |  | 2009-09-04 | 1st | XII |  | 9.407 | 206 |  |  |  | O | 0.4 | 0.24 | 0.15 | 0.01 | 0.042 | 0.033 | 87.5 | -
MARCUS CONSTRUCTION | 12601 | L | A | MB | GE | Construction of Local Road | Brgy. Osias, Kabacan, Cotabato | 2015-06-07 | Final | Cotabato 2nd DEO | LF | 3.8 | 36 | 2015-02-19 | 2015-03-27 | 0% | C | 0.437 | 0.133 | 0.3 | - | - | - | 87% | *87% Satisfactory
Mar-Deb Construction & Development | 6718 | L | A | MA | GE | Preventive Maintenance (Intermittent Section) along Santiago-Tuguegarao Road, K0410+123 to K0410+577; K0416+246 to K0417+242 | Quezon, Isabela | 2014-08-09 | 1st & Final | II | LF | 20.3803 | 133 | 2014-02-12 | 2014-06-24 | 1.13 | C | 0.464 | 0.131 | 0.3 |  |  |  | 89.5 | 89.50% Very Satisfactory
Mar-Deb Construction & Development | 6715 | L | A | MA | GE | Repair/Improvement of Cagayan Rver Control, Dabburab | Cauayan City, Isabela | 2014-08-11 | Final | II | LF | 28.8494 | 230 | 2013-02-28 | 2013-10-15 | 3.04 | C | 0.298 | 0.2 | 0.3 |  |  |  | 79.8 | 83.10% Satisfactory
Mar-Deb Construction & Development | 6715 | L | A | MA | GE2 | Repair/Impv't. of Cagayan River Control, Dabburab | Cauayan City, Isabela | 2013-08-07 | 1st | II | LF | 28.85 | 200 | 2013-02-28 | 2013-09-15 | 0.78 | O | 0.355 | 0.24 | 0.15 | 0.03 | 0.045 | 0.033 | 85.3
Mar-deb Construction & Development | 6715 | L | A | MA | GE1 | Con. of Jct. Ipil-Quirino Bdry. Rd. San Agustin, Isabela, K0371+780-K0374+276 (w/ exceptions) Dappig-Laoag | San Agustin, Isabela | 2013-03-15 | Final | II | LF | 17.179 | 180 | 2012-08-21 | 2013-02-17 | 5.56 | C | 0.449 | 0.133 | 0.3 | - | - | - | 88.2 | 90.36% V. Satisfactory
Mar-deb Construction & Development | 6715 | L | A | MA | GE2 | Const. of Riverbank Protection Works, San Isidro & Sto. Domingo | Luna, Isabela | 2013-03-19 | Final | II | LF | 11.626 | 240 | 2012-06-13 | 2013-02-07 | 2.5 | C | 0.329 | 0.2 | 0.3 | - | - | - | 82.9 | 87.76% Satisfactory
Mar-deb Construction & Development | 6715 | L | A | MA | GE1 | Repair/Rehab. of Macalaoat Bridge along Santiago-Tuguegarao Rd. | Cabatuan, Isabela | 2013-03-19 | Final | II | LF | 17.576 | 225 | 2012-02-09 | 2012-09-20 | 0 | C | 0.437 | 0.133 | 0.3 | - | - | - | 87 | 87.48% Satisfactory
Mar-Deb Construction & Development | 6715 |  |  |  |  | Rehab./Reconst./Upgrading of Damaged Paved National Rd. KO 369+(-297) - KO 370+000 w/ exception |  | 2010-06-02 |  | II |  | 9.816 | 120 |  |  |  | O | 0.379 | 0.247 | 0.15 | 0.03 | 0.051 | 0.05 | 90.7 | -
Mar-Deb Construction & Development | 6715 | L | A | MA | GE1 | Completion of Turod-Banquero Concrete Overflow Bridge PhaseIII |  | 2008-08-14 | 1st | II |  | 9.879 | 300 |  |  |  | O | 0.351 | 0.26 | 0 | 0.03 | 0.037 | 0.1 | 77.8 | -
Mar-deb Construction & Development | 6715 | L | A | MA | GE | Preventive Maintenance Based on Pavement System/Highway Development Management-4 (HDM-4) MFO-1 along Santiago-Tuguegarao Road, KO360+000 - KO360+758 | Cabanatuan, Isabela | 2014-10-25 | 1st & Final | II | LF | 5.3103 | 60 | 2014-02-05 | 2014-04-05 |  | C | 0.447 | 0.133 | 0.3 | - | - | - | 88% | 88% Satisfactory
MAR-DEB CONSTRUCTION & DEVELOPMENT | 6715 | L | A | MA | GE | Rehabilitation/Construction of Dalibubon Bridge FC Structure, Approach "B" | Dalibubon, Jones, Isabela | 2015-06-07 | 1st | Isabela 4th DEO | LF | 26.884 | 240 | 2014-11-21 | 2015-07-18 | 1.59% | O | 0.293 | 0.3 | 0.15 | 0.03 | 0.047 | 0.033 | 85.3% | -
MAR-DEB CONSTRUCTION & DEVELOPMENT | 6715 | L | A | MA | GE | Construction of River Bank Protection, Magat River Flood Control Project, Aplat Section, Aurora, Isabela | Aurora, Isabela | 2015-11-14 | Final | ISABELA 2ND DEO | LF | 18.314 | 204 | 2015-02-25 | 2015-09-16 | (+) 0.02 | C | 0.35 | 0.1 | 0.3 | - | - | - | 75% | 75% Unsatisfactory
MAR-DEB CONSTRUCTION AND DEVELOPMENT | 6715 | L | A | MA | GE | Widening of National Roads - Secondary Road - Santiago - Tuguegarao By-Pass Road, K0363+(-383) - K0363+(-653), Cabanatuan, Isabela | K0363+(-383) - K0363+(-653), Cabanatuan, Isabela | 2015-11-16 | Final | ISABELA 3RD DEO | LF | 5.0399 | 92 | 2015-06-16 | 2015-09-17 | - | C | 0.489 | 0.16 | 0.3 | - | - | - | 94.9% | 94.9% Very Satisfactory
Margarita Construction | 20201 | L | D | SB | GE1 | Rehab. of Sta. Maria-By Pass Road |  | 2009-09-07 | 1st | III |  | 4.757 | 100 |  |  |  | O | 0.357 | 0.24 | 0.15 | 0.03 | 0.042 | 0.033 | 85.2 | -
MARGARITA CONSTRUCTION | 20201 | L | A | SB | GB | Construction of Multi-Purpose Building, Brgy. Makinabang, Baliuag, Bulacan | Baliuag, Bulacan | 2015-06-12 | Final | Bulacan 1st DEO | LF | 1.891 | 45 | 2014-10-02 | 2014-11-15 | 0% | C | 0.345 | 0.2 | 0.3 | - | - | - | 84.5% | *84.5% Satisfactory
MARGARITA CONSTRUCTION | 20201 | L | A | MA | GE | Construction/Maintenance of Flood Mitigation Structures and Drainage Systems Flood Control along Bocaue River Turo, Bocaue, Bulacan | Bocaue, Bulacan | 2015-08-26 | 1st & Final | Bulacan First DEO | LF | 15.824 | 160 | 2015-02-27 | 2015-08-05 | - | C | 0.458 | 0.2 | 0.3 | - | - | - | 95.8% | *95.8% Very Satisfactory
Marie-Kris Construction and Trading | 32418 |  | B | SB |  | Rehabilitation of Marabut Wharf | Marabut, Western Samar/ Region VIII | 2016-02-23 | 1st & Final | DOTC | LF | 4.226 | 90 | 2015-09-01 | 2015-11-29 | 0 | C | 0.4094 | 0.2 | 0.3 | - | - | - | 90.94 | *90.94% V. Satisfactory
Mark Anthony Construction & Supply | 34057 | L | D | SB | GE | Construction of Magdug Flood Control | Gov. Generoso, Davao Oriental Protecting Tibanban-Lavigan Road | 2014-10-27 | 1st & Final | XI | LF | 3.995 | 50 | 2014-02-03 | 2014-03-24 |  | C | 0.428 | 0.133 | 0.3 | - | - | - | 86.1% | 86.1% Satisfactory
Mark Anthony Construction & Supply | 34057 | L | D | SB | GE | Construction of Pundaguitan Flood Control Governor Generoso davao Oriental Protecting Tibanban-Lavigan Road | Davao Oriental | 2014-08-11 | 1st & Final | XI | LF | 2.995 | 50 | 2014-02-03 | 2013-03-24 | 0 | C | 0.429 | 0.133 | 0.3 |  |  |  | 86.2 | 86.20% Satisfactory
Mark Anthony Construction & Supply | 34057 | L | D | SB | GE1 | Rehab./Impv't. of Rd., Purok Roads | Mati City, Davao Oriental | 2013-03-19 | 1st | XI | LF | 4.995 | 37 | 2013-02-22 | 2013-03-30 | 39.38 | O | 0.336 | 0.24 | 0.15 | 0.03 | 0.048 | 0.05 | 85.4 | -
Mark Anthony Construction & Supply | 34057 | L | D | SB | GE1 | Const. of Sanghay Brgy. Bridge | Mati City, Davao Oriental | 2013-03-19 | Final | XI | LF | 2.999 | 90 | 2012-10-26 | 2013-01-23 | 0 | C | 0.285 | 0.19 | 0.3 | - | - | - | 77.5 | 81.88% Unsatisfactory
Markbilt Construction | 12522 | L | AAA |  |  | Sta. Josefa Pump Irrigation Project | Agusan del Sur/ Caraga Region | 2014-08-30 | 1st | NIA | LF | 204.785 | 1097 | 2009-09-23 | 2012-09-25 | -5.95 | O/Expired | 0.3602 | 0.2709 | 0 | 0.0075 | 0.0233 | 0.05 | 71.19 | -
Markbilt Construction | 12522 | L | AAA |  | GE3 | Const. of Small Reservoir Irrigation Project - Masidem Dam (Dam) | Bani, Pangasinan | 05/2-7/11 | 2nd | NIA | LF | 192.198 | 1098 | 2009-01-20 | 2012-01-19 | 10.26 | O | 0.3835 | 0.272 | 0.15 | 0.03 | 0.025 | 0.05 | 91.05 | -
Markbilt Construction | 12552 |  | AAA |  |  | Tangub SRIP | Brgy. Manga, Tagub City, Misamis Occidental | 2015-11-28 | 1st & Final | NIA | LF | 234.975 | 1874 | 2009-12-07 | 2015-01-23 | -0.38 | C | 0.4407 | 0.2 | 0 | - | - | - | 64.07 | *64.07% Poor
Markbilt Construction and Tokwing Construction Corporation |  | L | AAA |  |  | NIA-Participatory Irrigation Development Project | Apayao-Abulug RIS, Aparri, Cagayan, Region 2 | 2015-09-19 | 1st | NIA | LF | 286.232 | 800 | 2013-08-01 | 2015-10-09 | -55.18 | O | 0.39 | 0.3 | 0 | 0.03 | 0.055 | 0.05 | 82.5 | -
Markbilt Construction Trading & Development Corporation | 12522 | L | AAA |  |  | NIA-Participatory Irrigation Development Project | Lasam, Cagayan, Region 2 | 2015-09-19 | 1st | NIA | LF | 202.681 | 800 | 2013-09-04 | 2015-11-13 | -70.33 | O | 0.383 | 0.3 | 0 | 0.023 | 0.035 | 0.017 | 75.8 | -
Markbilt Construtcion/ R.D. Policarpio & Co. Inc. (JV) | JV-12-194 | L | AAA | LB |  | PIDPC-C-UCRIS-1 | Tabuk City, Kalinga/ CAR | 2015-10-17 | 1st | NIA | LF | 424.999 | 820 | 2013-09-23 | 2015-12-22 | -59.88 | O | 0.3585 | 0.3 | 0 | 0.03 | 0.065 | 0.05 | 80.35 | -
MARKNEST CONSTRUCTION & TRADING | 16818 | L | B | MA | GE | Paving of Shoulder/Rehabilitation/Improvement of Camp Dau Road, KO087+970 to KO088+286, Brgy. Dau, Mabalacat City, Pampanga 1st LD | KO087+970 to KO088+286, Brgy. Dau, Mabalacat City, Pampanga 1st LD | 2015-08-29 | 1st | Pampanga Third DEO | LF | 10.209 | 150 | 2015-04-21 | 2015-09-17 | 9% | O | 0.314 | 0.24 | 0.15 | 0.03 | 0.07 | 0.05 | 85.4% | -
Marknest Construction and Trading (Formerly: Marknest Const.) | 16818 | L | B | MA | GE1 | Road Upgrading of Mt. Arayat Park Road |  | 2009-05-19 | 1st | III |  | 11.429 | 90 |  |  |  | O | 0.356 | 0.3 | 0.15 | 0.02 | 0.033 | 0.05 | 90.9 | -
MARKNEST CONSTRUCTION AND TRADING (Formerly: Marknest Construction) | 16818 | L | B | MA | GE | Paving of Shoulder/Rehabilitation/Improvement of Camp Dau Road, K0087+970 to K0088+268, Brgy. Dau, Mabalacat, Pampanga | Brgy. Dau, Mabalacat, Pampanga | 2015-11-13 | Final | Pampanga Third DEO | LF | 10.209 | 150 | 2015-04-21 | 2015-09-18 | - | C | 0.494 | 0.133 | 0.3 | - | - | - | 92.7% | 88.32% Satisfactory
Marquin Construction | 13332 | L | D | SB | GB1 | Const. of 2-CL SB on top of the existing SB at Compostela NHS |  | 2009-09-14 | 1st | VII |  | 2.234 | 120 |  |  |  | O | 0.383 | 0.24 | 0.15 | 0.03 | 0.035 | 0.025 | 86.3 | -
Marquin Construction | 13332 | L | D | SB | GB1 | Construction of 2-CL SB at Mohon NHS |  | 2009-09-14 | 1st | VII |  | 1.212 | 120 |  |  |  | O | 0.332 | 0.24 | 0.15 | 0.03 | 0.035 | 0.025 | 81.2 | -
Marra Builders | 8784 |  | AAA |  |  | TACLOBAN PORT IMPROVEMENT/ REHABILITATION PROJECT PHASE 2 | Port of Tacloban, Tacloban City, Leyte | 2015-06-26 | 2nd & Final | PPA | LF | 235.5 | 480 | 2014-02-25 | 2015-06-19 | 0 | C | 0.4952 | 0.2 | 0.3 | - | - | - | 99.52 | 99.53% Outstanding
Marra Builders | 8784 | L | AAA |  |  | Tacloban Port Improvement/ Rehabilitation Project Ph-2 | Tacloban Port/ Tacloban, Leyte | 2014-08-22 | 1st | PPA | LF | 235.5 | 480 | 2014-02-25 | 2014-06-19 | 31.281 | O | 0.395 | 0.3 | 0.15 | 0.03 | 0.07 | 0.05 | 99.5 | -
Marra Builders | 8784 | L | AAA |  | GE5 | CONSTRUCTION OF BACK-UP AREA | ILOILO COMMERCIAL PORT COMPLEX (ICPC) | 2014-04-04 | 3rd & Final | PPA | LF | 195.531 | 540 | 2012-09-21 | 2014-03-11 | 0 | C | 0.4778 | 0.2 | 0.3 | - | - | - | 97.78 | 98.93% Outstanding
Marra Builders | 8784 | L | AAA |  | GE5 | Construction of Back-up Area | Iloilo Commercial Port Complex (ICPC) | 2013-02-08 | 1st | PPA | LF | 181.414 | 540 | 2012-09-21 | 2014-03-14 | 28.482 | O | 0.396 | 0.3 | 0.15 | 0.03 | 0.07 | 0.05 | 99.6 | -
MARRA BUILDERS INC. | 8784 |  | AAA |  |  | Tacloban Port Improvement/ Rehabilitation Project - Phase 3 | Port of Tacloban, Leyte/Region 8 | 2016-05-13 | 1st | PPA | LF | 375.297 | 540 | 2015-05-06 | 2016-10-26 | 8.011 | O | 0.3992 | 0.3 | 0.15 | 0.03 | 0.065 | 0.05 | 99.42 | -
Marra Builders Inc. | 8784 |  |  |  |  | Tacloban Port Improvement/ Rehabilitation Project - Phase 3 | Port of Tacloban, Leyte/ Region 8 | 2016-09-16 | 2nd | PPA | LF | 375.297 | 540 | 2015-05-06 | 2016-10-26 | 4.494 | O | 0.3892 | 0.3 | 0.15 | 0.03 | 0.065 | 0.05 | 98.42 | -
Marra Builders Inc. | 8784 |  | AAA |  |  | Tacloban Port Improvement/ Rehabilitation Project - Phase 3 | Port of Tacloban, Tacloban City, Leyte | 2016-11-25 | 3rd & Final | PPA | LF | 375.297 | 540 | 2015-05-06 | 2016-10-26 | 0.83 | C | 0.3943 | 0.2 | 0.3 | - | - | - | 89.43 | 95.12% Very Satisfactory
Marra Builders, Inc. | 8784 | L | AAA |  | GE5 | Construction of Back-up Area | Iloilo Commercial Port Complex (ICPC) | 2013-06-28 | 2nd | PPA | L | 181.414 | 540 | 2012-09-21 | 2013-03-14 | 34.73 | C | 0.398 | 0.3 | 0.15 | 0.03 | 0.07 | 0.05 | 99.8 | -
Mar-Vel Construction & Supply | 23722 | L | B | MA | GE | Construction of Bridges RCBC (Reinforced Concrete Box Culvert), Barangay San Ignacio, San Pablo City along Daang Maharlika (LZ) | San Pablo City, Laguna | 2014-08-15 | 1st | IV-A | LF | 12.2757 | 206 | 2014-02-08 | 2014-09-01 | 0 | O | 0.391 | 0.3 | 0.15 | 0.022 | 0.04 | 0.033 | 93.6
Mar-vel Construction & Supply (Formerly: Mar-vel Construction) | 23722 | L | B | MA | GE | Widening of Permanent Bridge, Masapang Bridge 2, along Calamba-Sta. Cruz-Famy Jct. Road | Laguna | 2014-11-27 | 1st & Final | IV | LF | 8.2799 | 208 | 2014-02-10 | 2014-09-05 | - | C | 0.444 | 0.2 | 0.3 | - | - | - | 94.4% | 94.4% Very Satisfactory
Mar-vel Construction & Supply (Formerly: Mar-vel Construction) | 23722 |  |  |  |  | Const. of Two Storey - Four CL School Bldg. at Cavite National High School |  | 2010-06-01 |  | IVA |  | 4.801 | 169 |  |  |  | O | 0.395 | 0.3 | 0.052 | 0.03 | 0.029 | 0.05 | 85.6 | -
Mar-Vel Construction & Supply/ C.T. Leoncio Construction & Trading (JV) | JV-13-503 | L | A | MB | GE | Widening of Sta. Rosa - Ulat - Tagaytay Road, K0045+500 to K0047+850 (with Exception) including RROW acquisition | Sta. Rosa City, Laguna | 2014-08-09 | 1st | IV-A | LF | 45.325 | 240 | 2014-02-21 | 2014-10-18 | 0.92 | O | 0.356 | 0.3 | 0.15 | 0.02 | 0.052 | 0.033 | 91.1
Masbate-Iloilo Construction | 26579 | L | D |  |  | Const. of Managopaya CIP | Brgy. Managopaya, Banate, Iloilo | 2014-04-05 | 1st & Final | NIA | LF | 2.6 | 90 | 2013-08-02 | 2013-11-22 | 0 | C | 0.466 | 0.164 | 0 | - | - | - | 63 | 63.00% Poor
Masbate-Iloilo Construction & Trading Corp. | 26579 | L | D | SB | GE | Replacement/Rehab./Strengthening of Permanent Bridge Management System (BMS) Construction of Siwalo Bridge along Mandurriao - San Miguel - Alimodian - Maasin - Cabatuan Road Brgy. Siwalo, K0030+001.60 - K0030+013.60 | Maasin, Iloilo City | 2014-08-15 | Final | VI | LF | 5.2529 | 181 | 2013-04-01 | 2013-09-28 | 0 | C | 0.355 | 0.2 | 0.3 |  |  |  | 85.5 | 84.6% Satisfactory
Masbate-Iloilo Construction & Trading Corp. | 26579 | L | D | SB | GE1 | Replacement/Rehab./Strengthening of Permanent Bridge Mgt. System (BMS), Const. of Siwalo Bridge along Mandurriao-San Miguel-Alimodian-Maasin-Cabatuan Rd., Brgy. Siwalo, K030+001.6-K0030+013.6 | Maasin, Iloilo City | 2013-08-20 | 1st | VI | LF | 4.957 | 170 | 2013-04-01 | 2013-09-18 | 3.61 | O | 0.347 | 0.238 | 0.15 | 0.03 | 0.042 | 0.033 | 84
MASBATE-ILOILO CONSTRUCTION AND TRADING CORP. | 26579 | L | D | SB | GB | Construction of Multi Purpose Building at San Luis Elementary School | Barangay San Luis, Culasi, Antique | 2015-06-04 | Final | Antique DEO | LF | 1.994 | 60 | 2015-03-04 | 2015-05-02 | 0% | C | 0.398 | 0.17 | 0.3 | - | - | - | 86.8% | *86.8% Satisfactory
Masulot Construction | 10716 | L | A | MB | GE | Road Upgrading (Gravel to Paved) along Demoloc-Little Baguio-Alabel Road, km. 1636+043.582 to km. 1637+113.30 Abbes-San Roque Section | Malita, Davao del Sur | 2014-08-07 | 3rd | XI | LF | 30.9664 | 179 | 2013-03-07 | 2013-09-01 | 0 | O | 0.009 | 0.3 | 0 | 0.03 | 0.02 | 0 | 35.9
Masulot Construction | 10716 | L | A | MB | GE1 | Rd. Upgrading (Gravel to Paved) along Demoloc-Little Baguio-Alabel Rd., Km.1636+043.582-Km.1637+113.30 Abbes-San Roque Sect. | Malita, Davao del Sur | 2013-08-08 | 2nd | XI | LF | 30.966 | 179 | 2013-03-07 | 2013-09-01 | 2.02 | O | 0.073 | 0.3 | 0.15 | 0.03 | 0.03 | 0.033 | 61.6
Masulot Construction | 10716 | L | A | MB | GE1 | Rd. Upgrading (Gravel to Paved) along Demoloc-Little Baguio-Alabel Rd,. Km.1636+043.582-Km.1637+113.30 Abbes-San Roque Sect. | Malita, Davao del Sur | 2013-03-14 | 1st | XI | LF | 30.966 | 179 | 2013-03-07 | 2013-09-01 | 0 | O | 0.242 | 0.236 | 0.15 | 0.03 | 0.032 | 0.05 | 74 | -
Masulot Construction | 10716 | L | A | MB | GE1 | Prev. Maint. (Int. Sect.) along Davao-Sarangani Coastal Rd., Km.1584+067-Km.1585+000 (w/ exception) Digos-Makar Rd., Km.1584+067-Km.1585+000 (w/ exception) | Davao del Sur | 2013-03-13 | 1st | XI | LF | 10.666 | 28 | 2013-01-31 | 2013-02-27 | - | O | 0.306 | 0.2 | 0 | 0.01 | 0.032 | 0 | 54.8 | -
Masulot Construction | 10716 | L | A | MB | GE1 | Const. (Opening) of Missing Links at Tubalan-Pangian-Pinalpalan-Alabel Road, Malita-Jose Abad Santos Road, Tubalan Section |  | 2009-05-28 | 1st | XI |  | 19.089 | 115 |  |  |  | O | 0.4 | 0.3 | 0.15 | 0.022 | 0.028 | 0.033 | 93.3 | -
Masulot Construction | 10716 | L | B | MB | GE1 | Road Upgrading of Mati-Maragusan Road (Buso-Taguibo Section) |  | 2009-06-05 | 1st | XI |  | 15.429 | 100 |  |  |  | O | 0.315 | 0.3 | 0.15 | 0.03 | 0.037 | 0.033 | 86.5 | -
Masulot Construction | 10716 | L | B | MB | GE1 | Road Upgrading of Mati-Maragusan Road (Don Martin Marundan-Menzi Section) |  | 2009-06-05 | 1st | XI |  | 19.289 | 120 |  |  |  | O | 0.313 | 0.3 | 0.15 | 0.03 | 0.037 | 0.033 | 86.3 | -
Masulot Construction | 10716 | L | A | MB | GE1 | Rehab./Recons./Upgrading of Digos-Makar Road, Kiblagon-Tagansule Section, Km. 1584+000-Km. 1584+750 |  | 2009-05-28 | 1st | XI |  | 9.649 | 180 |  |  |  | O | 0.363 | 0.237 | 0.15 | 0.03 | 0.037 | 0.033 | 85 | -
Masulot Construction | 10716 | L | A | MB | GE1 | Road Upgrading (Gravel to Paved) Demoloc-Little Baguio-Alabel Road, Km.1637+113.30-Km.1638+180 | Malita, Davao del Sur | 2012-03-21 | 1st | XI | LF | 23.548 | 120 | 2012-02-07 | 2012-06-05 | 0.93 | O | 0.4 | 0.263 | 0.15 | 0.02 | 0.028 | 0.033 | 89.4 | -
Masulot Construction | 10716 | L | A | MB | GE1 | Const. of Sabang Bridge along Arakan-Analopon-Napaliko-Katipunan Road (Steel Truss Component to be supplied by others) |  | 2009-09-05 | 2nd | XII |  | 9.217 | 150 |  |  |  | O | 0.336 | 0.3 | 0 | 0.01 | 0.028 | 0.033 | 70.7 | -
Masulot Construction | 10716 | L | A | MB | GE1 | Const. of Kidapawan-Magpet-Pangao-An Road, Mateo-Gubatan Sect.) |  | 2009-09-05 | 2nd | XII |  | 30.527 | 250 |  |  |  | O | 0.307 | 0.29 | 0 | 0.01 | 0.033 | 0.033 | 67.3 | -
Masulot Construction | 10716 | L | A | MB | GE1 | Rehab./Reconst. of Damaged Paved of Nat'l Road along Cotabato City Circ.Road (Western Sect.), K1867+000-K1867+1880 / K1859+641.45-K1860+641.45 | Cotabato City | 2012-03-19 | 1st | XII | LF | 27.818 | 260 | 2011-08-25 | 2012-05-11 | 5 | O | 0.315 | 0.24 | 0.15 | 0.03 | 0.059 | 0.05 | 84.4 | -
Masulot Construction | 10716 | L | A | MB | GE1 | Const. of Kidapawan-Magpet-Pangao-an Road, Mateo-Gubatan Section |  | 2009-06-01 | 1st | R-XII |  | 30.528 | 250 |  |  |  | O | 0.292 | 0.3 | 0 | 0.024 | 0.05 | 0.033 | 69.9 | -
Masulot Construction | 10716 | L | A | MB | GE1 | Const. of Sabang Bridge along Arakan-Anapolon-Napaliko-Katipunan Road |  | 2009-05-30 | 1st | R-XII |  | 9.218 | 150 |  |  |  | O | 0.308 | 0.3 | 0 | 0.018 | 0.035 | 0.033 | 69.4 | -
Masulot Construction/RAQI Builder Construction & Supply (J.V.) | 10716 | L | A | MA | GE | Road Upgrading (Gravel to Concrete) at Isulan Hwy Jct. Dukay-Bagumbayan-Sen. Ninoy Aquino-Kalamansig Road (Km. 1852+917 - | Kawa-Poblacion, Sen. Ninoy Aquino, Sultan Kudarat | 2014-10-27 | 1st | XII | LF | 38.9657 | 133 | 2014-02-19 | 2014-07-01 | -1.8% | O | 0.357 | 0.242 | 0.025 | 0.03 | 0.05 | 0.05 | 75.4% | 75.4% Unsatisfactory
MASULOT CONSTRUCTION/RAQI BUILDER CONSTRUCTION AND SUPPLY (JV) | JV-13-347 | L | A | MB | GE | Road Upgrading (Gravel to Concrete) along Isulan Highway Jct. Dukay- Bagumbayan- Sen. Ninoy Aquino- Kalamansig Road (Km 1852+917- Km 1855+084 with exception | Kawa-Poblacion, Sen. Ninoy Aquino, Sultan Kudarat | 2015-06-13 | Final | Sultan Kudarat 2nd DEO | LF | 38.966 | 133 | 2014-02-19 | 2014-07-01 | 0% | C | 0.46 | 0.133 | 0.3 | - | - | - | 89.3% | *89.3% Very Satisfactory
Maverick & Wee Eng Joint Venture | JV-07-105 | L | AAA | LB | GE1 | CP 8: Impvt./Conc. of Surigao Sur-Davao Oriental Coastal Road (Manay-Boston) Baganga-Cateel Section |  | 2008-11-25 | 1st | XI |  | 191.29 | 597 |  |  |  | O | 0.381 | 0.24 | 0.1 | 0.03 | 0.06 | 0.1 | 91.1 | -
Maverick & Wee Eng Joint Venture | SL1-SN-005102/JV-07-105 | L | AAA | LB | GE1 | Impvt./Conc. of Surigao Sur-Davao Oriental Coastal Road (Manay Boston) Banganga-Cateel Section |  | 2009-06-09 | 2nd | XI |  | 191.222 | 597 |  |  |  | O | 0.368 | 0.255 | 0.15 | 0.03 | 0.06 | 0.05 | 91.3 | -
Maverick Builders Incorporated | 14460 | L | AA | LA | GE1 | Rehab./Impvt. of Manay-Mati Section along Surigao Sur-Davao Oriental Coastal Road, Badas-Baso Section |  | 2009-06-05 | 2nd | XI |  | 48.132 | 161 |  |  |  | O | 0.381 | 0.3 | 0.15 | 0.03 | 0.051 | 0.033 | 94.5 | -
Maverick Builders Incorporated | 14460 | L | AA | LA | GE1 | Rehab./Impvt. of Manay-Mati Section along Surigao Sur-Davao Oriental Coastal Road, (Dawan-Tagamot Section) |  | 2009-06-05 | 1st | XI |  | 71.995 | 210 |  |  |  | O | 0.38 | 0.3 | 0.15 | 0.03 | 0.047 | 0.033 | 94 | -
Maverick Builders Incorporated | 14466 | L | AA | LA | GE1 | Rehab./Recons./Upgrading of Damaged Paved National Roads, for Package 1-A: a) Matina-Harana Section |  | 2009-06-11 | 1st | XI |  | 19.284 | 210 |  |  |  | O | 0.36 | 0.3 | 0.15 | 0.03 | 0.051 | 0.033 | 92.4 | -
Maverick Builders Incorporated | 31666 | L | AA | LA | GE1 | Concreting of Compostela-Cateel Road |  | 2009-06-08 | 4th | XI |  | 67.99 | 590 |  |  |  | O | 0.341 | 0.236 | 0.15 | 0.03 | 0.042 | 0.05 | 84.9 | -
Maverick Builders Incorporated (Formerly: Maverick Builders) | 14466 | L | AA | MB | GE | Const. of Sta. Fe Bridge along Surigao del Sur Bdry. - Davao Oriental Coastal Road | Caraga, Davao Oriental | 2014-10-29 | 1st & Final | XI | LF | 17.5042 | 192 | 2014-02-16 | 2014-08-26 |  | C | 0.412 | 0.131 | 0.3 | - | - | - | 84.3% | 84.3% Satisfactory
Maverick Builders Incorporated (Formerly: Maverick Builders) | 14466 | L | AA | MB | GE | Cluster I - Repair/Maint. of (Inst. of Fender Piles) at Bridges along Surigao del Sur Bdry. - Davao Oriental | Manay, Davao Oriental | 2014-10-29 | 1st & Final | XI | LF | 14.29 | 151 | 2014-02-16 | 2014-07-16 |  | C | 0.482 | 0.133 | 0.3 | - | - | - | 91.5% | 91.5% Very Satisfactory
Maverick Builders Incorporated (Formerly: Maverick Builders) | 14466 | L | AA | MB | GE | Rehabilitation/ Reconstruction/ Upgrading of Damaged Paved National Road Including Drainage along Digos-Makar Road (KO 1576+001 - KO 1577+705) | Padada, Davao del Sur | 2014-10-23 | 1st & Final | XI | LF | 31.3382 | 136 | 2014-02-05 | 2014-06-20 | 12.42% | C | 0.443 | 0.133 | 0.3 | - | - | - | 87.6% | 87.6% Satisfactory
Maverick Builders Incorporated (Formerly: Maverick Builders) | 14466 | L | AA | MB | GE | Improvement/Upgrading Const./Impv’t. of Access Road leading to Declared Tourism Destination Jct. Menzi-Dahican-Lawigan Section Road, with leading to Cinco Masao Beach Resort (Dahican Lawigan Section) | City of Mati, Davao Oriental | 2014-08-11 | 1st | XI | LF | 38.1491 | 220 | 2014-03-07 | 2014-10-12 | -1.35 | O | 0.3 | 0.3 | 0.137 | 0.03 | 0.043 | 0.05 | 86
Maverick Builders Incorporated (Formerly: Maverick Builders) | 14466 | L | AA | MB | GE1 | Impv't./Upgrading (Gravel to Concrete) along Jct. Menzi-Dahican-Lawigan Rd. (Dahican-Lawigan Sect.) | Mati, Davao Oriental | 2013-08-18 | Final | XI | LF | 93.624 | 297 | 2012-10-25 | 2013-08-17 | 0 | C | 0.357 | 0.2 | 0.3 | - | - | - | 85.7 | 83.12% Satisfactory
Maverick Builders Incorporated (Formerly: Maverick Builders) | 14466 | L | AA | MB | GE1 | Impv't./Upgrading (Gravel to Concrete) along Jct. Menzi-Dahican-Lawigan Rd., Dahican-Lawigan Sect. | Mati City, Davao Oriental | 2013-03-19 | 1st | XI | LF | 93.624 | 237 | 2012-10-25 | 2013-06-18 | 1.02 | O | 0.325 | 0.236 | 0.15 | 0.03 | 0.04 | 0.033 | 81.4 | -
Maverick Builders Incorporated (Formerly: Maverick Builders) | 14466 | L | AA | MB | GE1 | Asphalt Overlay/Repair & Rehab. of Tibanban-Lavigan Road, Km.1775+000 - Km.1775+740 w/ exception | Davao Oriental | 2011-08-19 | 1st | XI | LF | 1.643 | 40 | 2011-07-27 | 2011-09-04 | 21.16 | O | 0.38 | 0.2 | 0.15 | 0.03 | 0.059 | 0.05 | 86.9 | -
Maverick Builders Incorporated (Formerly: Maverick Builders) | 14466 | L | AA | MB | GE1 | Asphalt Overlay/Repair & Rehab. of Jct. Manikling, Brgy. Pob. | San Isidro, Davao Oriental | 2012-08-15 | Final | XI | LF | 8.24 | 120 | 2011-07-27 | 2011-11-23 | 4.17 | C | 0.414 | 0.133 | 0.3 | - | - | - | 84.7 | 84.82% Satisfactory
Maverick Builders Incorporated (Formerly: Maverick Builders) | 14466 | L | AA | MB | GE1 | Widening of Pres. Diosdado P. Macapagal Highway | Davao Oriental | 2013-08-18 | Final | XI | LF | 89.304 | 515 | 2013-03-27 | 2013-08-23 | 16.89 | C | 0.394 | 0.2 | 0.3 | - | - | - | 89.4 | 86.34% Satisfactory
Maverick Builders Incorporated (Formerly: Maverick Builders) | 14466 | L | AA | MB | GE1 | Widening of Pres. Diosdado Macapagal Highway | Davao Oriental | 2012-08-10 | 1st | XI | LF | 89.304 | 214 | 2012-03-27 | 2012-10-26 | -6.64 | O | 0.338 | 0.298 | 0.084 | 0.03 | 0.06 | 0.033 | 84.3 | -
MAVERICK BUILDERS INCORPORATED (Formerly: Maverick Builders) | 14466 | L | AA | MA | GE | Construction of Revetment/ Sheet Piles Taytayan Floof Control Structures | Cateel, Davao Oriental | 2015-06-06 | Final | Davao Oriental 1st | LF | 18.528 | 140 | 2015-02-16 | 2015-07-05 | (+)17.04% | C | 0.421 | 0.133 | 0.3 | - | - | - | 85.4% | *85.4% Satisfactory
MAVERICK BUILDERS INCORPORATED (Formerly: Maverick Builders) | 14466 | L | AA | LA | GE | Road Upgrading (Unpaved to Paved) Dahican-Lawigan Road, City of Mati, Davao Oriental | Mati, Davao Oriental | 2015-11-11 | Final | Davao Oriental 2nd DEO | LF | 1.5357e-05 | 99 | 2015-02-09 | 2015-05-18 | 0 | C | 0.42 | 0.133 | 0.3 | - | - | - | 85.3% | 85.3% Satisfactory
Maverick Builders Incorporated / Wee Eng Construction, Inc. (JV) | JV-11-425 | L | AAA | MB | GE2 | Const. of Flood Control at Padada River (Downstream) Guihing | Hagonoy, Davao del Sur | 2013-03-17 | Final | XI | LF | 32.599 | 212 | 2012-06-12 | 2013-01-09 | 0 | C | 0.374 | 0.2 | 0.3 | - | - | - | 87.4 | 88.48% Satisfactory
Maverick Builders, Incorporated | 14466 | L | AA | LA | GE1 | Concreting of Compostela-Cateel Road |  | 2009-09-12 | 5th | XI |  | 69.384 | 590 |  |  |  | O | 0.265 | 0.3 | 0.15 | 0.03 | 0.047 | 0.033 | 82.5 | -
Maverick Builders, Incorporated (Formerly: Maverick Builders) | 14466 | L | AA | LA | GE1 | Conc. of Compostela-Cateel Road |  | 2009-03-09 | 3rd | XI |  | 67.99 | 590 |  |  |  | O | 0.266 | 0.3 | 0.15 | 0.03 | 0.032 | 0.05 | #VALUE! | -
Maverick Builders, Incorporated (Formerly: Maverick Builders) | 14466 | L | AA | LA | GE1 | Rehab./Impv't. of Manay-Mati Sect. along Surigao Sur-Davao Oriental Coastal Road, Badas-Baso Section |  | 2009-03-11 | 1st | XI |  | 48.132 | 161 |  |  |  | O | 0.388 | 0.3 | 0.15 | 0.03 | 0.059 | 0.05 | #VALUE! | -
Maxnell Enterprises | 7170 | L | C | SB | GB | Completion of Engineering Building at University of Antique (Main Campus), Sibalom, Antique | Sibalom, Antique | 2014-08-13 | 2nd | VI | LF | 4.9836 | 90 | 2013-07-01 | 2013-08-29 | 0 | O | 0.355 | 0.3 | 0 | 0.03 | 0.023 | 0 | 70.8
Maxnell Enterprises | 7170 | L | B | MA | GB1 | Completion of Eng'g Bldg. at University of Antique, (Main Campus) | Sibalom, Antique | 2013-08-15 | 1st | VI | LF | 4.984 | 60 | 2013-07-01 | 2013-08-29 | 0.37 | O | 0.295 | 0.24 | 0.15 | 0.03 | 0.027 | 0.033 | 77.5
Mayhaligue Construction | 29586 | L |  | SB | GE2 | Colocol Integrated CIS Rehabilitation & Extension Project | Bayombong, Nueva Vizcaya | 10/24-29/11 | 1st | NIA | LF | 3.477 | 120 | 2011-06-06 | 2011-10-03 | - | O | 0.3671 | 0.2844 | 0.15 | 0.03 | 0.0327 | 0.05 | 91.42 | -
MB Eclar Trading & Construction | 32118 | L | A | MB | GE2 | Const. of Shore Protection/Flood Control in La Union 2nd District Rock Bulkhead & Slope Protection, Brgy. San Nicolas West | Agoo, La Union | 2013-07-31 | Final | I | LF | 16.878 | 180 | 2013-01-16 | 2013-07-14 | 41.67 | C | 0.4 | 0.133 | 0.3 | - | - | - | 83.3 | 88.28% Satisfactory
MB Eclar Trading & Construction | 32118 | L | A | MB | GE2 | Const. of Shore Protection/Flood Control in La Union 2nd Dist. Rock Bulkhead & Slope Protection, Brgy. San Nicolas West | Agoo, La Union | 2013-03-12 | 1st | I | LF | 16.879 | 180 | 2013-01-16 | 2013-07-14 | 53.59 | O | 0.393 | 0.3 | 0.15 | 0.01 | 0.03 | 0.033 | 91.6 | -
MB Eclar Trading & Construction | 32118 | L | A | MA | GB1 | Const. of 3-Storey, 9-Cl and 2-Storey, 4-Cl Sch. Bldg., Naguilian NHS | Naguilian, La Union | 2013-08-01 | 1st | I | LF | 14.599 | 210 | 2013-03-25 | 2013-10-21 | 0.3 | O | 0.37 | 0.24 | 0.15 | 0.03 | 0.033 | 0.033 | 85.6
MB Eclar Trading & Construction | 32118 | L | A | MB | GE2 | Const. of Rock Groins, Brgy. Alaska | Aringay, La Union | 2013-03-12 | 1st | I | LF | 22.546 | 163 | 2012-12-14 | 2013-05-25 | 25.17 | O | 0.365 | 0.3 | 0.15 | 0.015 | 0.014 | 0.033 | 87.7 | -
MB Eclar Trading & Construction | 32118 | L | A | MB | GE2 | Repair/Rehab. of Principe River Control | Agoo, La Union | 2013-03-12 | Final | I | LF | 17.405 | 280 | 2012-06-19 | 2013-03-26 | 22.5 | C | 0.33 | 0.2 | 0.3 | - | - | - | 83 | 85.46% Satisfactory
MBB Construction | 11363 | L | B | MA | GE | Rehab./Reconst./ Upgrading of Quirino-Panda Road a) K0407+(-480) to K0407+845, b) K0408+776 to K0409+235 | Bantay, Vigan City,Ilocos Sur | 2014-08-06 | Final | I | LF | 31.3373 | 206 | 2013-02-26 | 2013-09-19 | 0 | C | 0.489 | 0.2 | 0.03 |  |  |  | 71.9 | 82.04% Satisfactory
MBB Construction | 11363 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of Quirino-Pandan Rd. a)K0407+(-480)- K0407+845, b)K0408+776-K0409+225 | Bantay, Vigan City, Ilocos Sur | 2013-08-13 | 1st | I | LF | 31.337 | 176 | 2013-02-26 | 2013-08-20 | -5.24 | O | 0.38 | 0.3 | 0.098 | 0.03 | 0.047 | 0.033 | 88.8
MBB Construction | 11363 | L | B | MA | GE | Santa Flood Control along Manila North Road | Santa, Ilocos Sur | 2014-08-12 | Final | I | LF | 17.106 | 392 | 2013-01-17 | 2014-02-12 | 14.04 | C | 0.361 | 0.2 | 0.3 |  |  |  | 86.1 | 84.57% Satisfactory
MBB Construction | 11363 | L | B | MA | GE2 | Santa Flood Control along MNR | Santa, Ilocos Sur | 2013-08-12 | 2nd | I | LF | 17.106 | 383 | 2013-01-17 | 2013-02-03 | -14.7 | O | 0.394 | 0.3 | 0.003 | 0.03 | 0.051 | 0.033 | 81.1
MBB Construction | 11363 | L | B | MA | GE2 | Santa Flood Control along MNR | Santa, Ilocos Sur | 2013-03-19 | 1st | I | LF | 17.106 | 363 | 2013-01-17 | 2014-01-14 | 6.97 | O | 0.324 | 0.3 | 0.15 | 0.015 | 0.038 | 0.033 | 86 | -
MBB Construction | 11363 | L | B | MA | GE1 | Rehab./Reconst.Upgrading of Vigan-San Vicente Rd., K0408+(-1652)-K0408+201 | Ilocos Sur | 2013-03-20 | 1st | I | LF | 27.653 | 166 | 2013-02-26 | 2013-08-10 | 8.33 | O | 0.367 | 0.225 | 0.15 | 0.03 | 0.038 | 0.033 | 84.3 | -
MBB Construction | 11363 |  |  |  |  | Rehab./Reconst./Upgrading of Damaged Paved National Road along MNR |  | 2010-05-27 |  | I |  | 19.103 | 157 |  |  |  | O | 0.39 | 0.225 | 0.057 | 0.03 | 0.047 | 0.017 | 76.6 | -
MBB Construction | 11363 | L | B | MA | GB1 | Const. of Ilocos Sur 2nd DEO Bldg. |  | 2008-08-13 | 1st | I |  | 14.14 | 365 |  |  |  | O | 0.261 | 0.24 | 0.1 | 0.03 | 0.037 | 0.1 | 76.8 | -
MBB Construction | 11363 | L | B | MA | GB1 | Const. of Ilocos Sur 2nd DEO Bldg. |  | 2008-11-12 | 2nd | I |  | 14.14 | 365 |  |  |  | O | 0.251 | 0.115 | 0.03 | 0.022 | 0.025 | 0.067 | 51 | -
MBB Construction | 11363 | L | A | MA | GE1 | MNR, Candon-Santiago Section |  | 2008-11-12 | 1st | I |  | 18.92 | 200 |  |  |  | O | 0.338 | 0.034 | 0.1 | 0.022 | 0.022 | 0.067 | 58.3 | -
MBB CONSTRUCTION | 11363 | L | B | MA | GE | Construction/Maintenance of Flood Control Mitigation Structures and Drainage System San Esteban Flood Control | San Esteban, Ilocos Sur | 2015-06-02 | Final | Ilocos Sur 2nd DEO | LF | 9.225 | 158 | 2015-02-05 | 2015-07-12 | 25.32% | C | 0.3 | 0.2 | 0.3 | - | - | - | 80% | *80% Unsatisfactory
MBB CONSTRUCTION | 11363 | L | B | MA | GE | Construction of Vigan Bridge 3 Along Quirino-Pandan Road, Vigan City, Ilocos Sur | Vigan City, Ilocos Sur | 2015-08-25 | 1st | Ilocos Sur 1st DEO | LF | 9.117 | 192 | 2015-03-12 | 2015-09-20 | (+)1.34 | O | 0.353 | 0.266 | 0.15 | 0.023 | 0.047 | 0.05 | 88.9% | -
MBB CONSTRUCTION | 11363 | L | B | MA | GE | Construction of Vigas 3 along Quirino-Pandan Road, Vigan, Ilocos Sur | Vigan, Ilocos Sur | 2015-11-14 | Final | ILOCOS SUR 1ST DEO | LF | 9.117 | 192 | 2015-03-12 | 2015-09-19 | - | C | 0.461 | 0.13 | 0.3 | - | - | - | 89.1% | 88.5% Satisfactory
MBD General Construction | 9991 | L | A | MB | GE1 | Const. of Ozamiz City Coastal By-Pass Rd. | Misamis Occidental | 2013-08-16 | Final | X | LF | 51.314 | 270 | 2011-11-15 | 2012-08-10 | - | C | 0.495 | 0.133 | 0 | - | - | - | 62.8 | 75.07% Unsatisfactory
MBD General Construction | 9991 | L | A | MB | GE1 | Rehab. of Cebu North Hagnaya Wharf Rd., K0004+288-K0007+321 | Mandaue City | 2013-03-21 | Final | VII | LF | 36.636 | 240 | 2012-07-07 | 2013-03-04 | 12.5 | C | 0.481 | 0.133 | 0.3 | - | - | - | 91.4 | 88.94% Satisfactory
MBD General Construction | 9991 | L | A | MB | GE1 | Concreting of Calamba-Baliangao Road |  | 2009-06-08 | 2nd | X |  | 16.18 | 180 |  |  |  | O | 0.256 | 0.2 | 0 | 0.01 | 0.011 | 0 | 47.7 | -
MBD General Construction | 9991 | L | A | MB | GE1 | Conc. of Calamba-Baliangao Road |  | 2008-11-29 | 1st | X |  | 16.18 | 180 |  |  |  | O | 0.312 | 0 | 0.05 | 0.023 | 0.035 | 0.1 | 52 | -
MBD General Construction | 9991 | L | A | MB | GE1 | Conc. of Oroquieta-Calamba Mt. Road |  | 2009-09-15 | 4th | X |  | 7.146 | 120 |  |  |  | O | 0.253 | 0.244 | 0 | 0.03 | 0.028 | 0.033 | 58.8 | -
MBD General Construction | 9991 | L | A | MB | GE1 | Concreting of Oroquieta-Calamba Mt. Road |  | 2009-06-08 | 3rd | X |  | 7.146 | 120 |  |  |  | O | 0.292 | 0.3 | 0 | 0.01 | 0.011 | 0 | 61.3 | -
MBD General Construction | 9991 | L | A | MB | GE1 | Conc. of Oroquieta-Calamba Mt. Road |  | 2009-03-18 | 2nd | X |  | 7.146 | 219 |  |  |  | O | 0.313 | 0.24 | 0 | 0.03 | 0.045 | 0 | #VALUE! | -
MBD General Construction | 9991 | L | A | MB | GE1 | Conc. of Oroquieta-Calamba Mt. Road |  | 2008-11-29 | 1st | X |  | 7.146 | 120 |  |  |  | O | 0.258 | 0.085 | 0.1 | 0.023 | 0.025 | 0.1 | 59.1 | -
MBD General Construction | 9991 | L | A | MB | GB1 | Rehab./Upgrading od Jimenez Port Road and Concr. of Shoulders inc. Const. of Drainage Canal along Jimenez Old Route |  | 2009-09-15 | 1st | X |  | 13.349 | 150 |  |  |  | O | 0.392 | 0.252 | 0.15 | 0.02 | 0.051 | 0.033 | 89.8 | -
MBD General Construction | 9991 | L | A | MB | GE1 | Const. of Ozamis City Coastal By-Pass Road | Misamis Occidental II | 2012-03-26 | 1st | X | LF | 51.314 | 240 | 2011-11-15 | 2012-07-11 | 4.51 | O | 0.362 | 0.185 | 0.15 | 0.03 | 0.047 | 0.05 | 82.4 | -
MBD General Construction | 9991 | L | A | MB | GE1 | Const. of Ozamiz City Coastal By-Pass Rd. | Misamis Occidental | 2012-08-19 | 2nd | X | LF | 51.314 | 270 | 2011-11-15 | 2012-08-10 | -2.59 | O | 0.384 | 0.223 | 0.124 | 0.03 | 0.047 | 0.033 | 84.1 | -
MBD/LABB Joint Venture | JV-08-259 | L | A | MB | GE1 | Conc. of JCT TER, Jagna-Sierra Bullones Rd. Km. 76.526-Km.77.681;Km77.9163-Km.78.94995&Km.79.19182-Km.81.500 |  | 2009-09-04 | 1st | VII |  | 88.829 | 270 |  |  |  | O | 0.351 | 0.255 | 0.15 | 0.03 | 0.042 | 0.033 | 86.1 | -
MBM CONSTRUCTION | 37891 | L | C | SB | GB | Const. of Two (2)- Six (6) Classroom School Building at Sapian National High School | Sapian, Capiz | 2015-06-08 | 1st | Capiz Second DEO | LF | 7.908 | 180 | 2015-03-03 | 2015-08-29 | 3.57% | O | 0.273 | 0.3 | 0.15 | 0.03 | 0.035 | 0.033 | 82.1% | -
MBM CONSTRUCTION | 37891 | L | C | SB | GB | Construction of Two (2) Storey - Six (6) Classroom School Building at Sapian National High School | Sapian, Capiz | 2015-09-03 | 1st & Final | Capiz 2nd | LF | 7.908 | 210 | 2015-03-03 | 2015-09-28 | 26.19% | C | 0.486 | 0.133 | 0.3 | - | - | - | 91.9% | *91.9% Very Satisfactory
MC Engineering Incorporated | 497 | L | A |  |  | Rehabilitation of Buiding B, Module 10 Phase 2, Heating, Ventilating and Air Conditioning (HVAC) System | BSP, Security Plant Complex, East Ave., Quezon City | 2014-09-22 | Final | BSP | LF | 88.474 | 545 | 2012-11-12 | 2014-05-10 | 2.96 | C | 0.481 | 0.2 | 0.211 | - | - | - | 89.2 | 90.18% V. Satisfactory
MCB Construction & Supply | 12128 | L | B | MA | GE | Repair/Rehabilitation/ Improvement along Calasiao Old Road, Km.206+800-Km. 207+100 with Exception | Calasiao, Pangasinan | 2014-10-29 | 1st & Final | I | LF | 4.8035 | 65 | 2013-12-12 | 2014-02-14 | 0% | C | 0.439 | 0.133 | 0.3 | - | - | - | 87.2% | 87.2% Satisfactory
MCB Construction & Supply/WJP Construction & Supply -JV | JV-13-615 | L | B | MA | GE | Widening of Pangasinan- Nueva Ecija Road , K0179+000 to K0184+000 with Exceptions | Rosales, Pangasinan | 2014-10-30 | 1st & Final | I | LF | 23.0128 | 100 | 2014-03-20 | 2014-06-27 | 0% | C | 0.408 | 0.199 | 0.3 | - | - | - | 90.7% | 90.7% Very Satisfactory
MCB ZAMORA CONSTRUCTION & SUPPLY (Formerly: M.C.B. Zamora Construction & Supplies) | 32006 | L | B | SB | GE | Construction of Slope Protection, Lucanin Seawall, Mariveles, Bataan | Mariveles, Bataan | 2015-06-01 | Final | Bataan Second DEO | LF | 6.509 | 60 | 2015-06-01 | 2015-07-30 | - | C | 0.5 | 0.133 | 0.3 | - | - | - | 93.3% | 93.3% Very Satisfactory
MCMP CONSTRUCTION CORPORATION | 1761 | L | B | MA | GE | Concreting of Lubi-Binoog Road KO059+(-1034) - KO059+(1017) & KO059+(-046) - KO060+129, Tablas Island, Romblon | Tablas Island, Romblon | 2015-09-04 | 1st & Final | Romblon DEO | LF | 43.583 | 280 | 2014-03-28 | 2015-01-01 | - | C | 0.419 | 0.132 | 0.3 | - | - | - | 85.1% | *85.1% Satisfactory
MDEC Corporation |  | L |  |  | GB1 | Renovation of Service Wing Building | PGH Compound, Taft Av., Manila | 2011-02-17 | 1st | UP | LF | 8.989 | 180 | 2010-08-26 | 2011-03-23 | 0 | O | 0.303 | 0.3 | 0.15 | 0.015 | 0 | 0.05 | 81.8 | -
Mega M Builders | 20515 | L | B | MA | GE | Rehabilitation/Reconstruction/Upgrading Damage Paved National Road MSR Passing Poblacion K0082+500-K0083+000 (Intermittent Section) | San Pablo City, Laguna | 2014-11-27 | 1st & Final | IV | LF | 14.4868 | 30 | 2014-03-24 | 2014-04-22 | - | C | 0.434 | 0.2 | 0.3 | - | - | - | 93.4% | 93.4% Very Satisfactory
Mega M Builders | 20515 | L | B | MA | GE1 | Rehab. of Tiaong-Diversion Rd. inc. Slope Protection | Tiaong, Quezon | 2013-03-16 | Final | IVA | LF | 28.612 | 290 | 2012-03-14 | 2012-12-28 | 6.36 | C | 0.43 | 0.133 | 0.3 | - | - | - | 86.3 | 87.38% Satisfactory
MEGA M BUILDERS | 20515 | L | B | MA | GE | Concreting of Brgy. San Cristobal, San Pablo City, Laguna, Farm to Market Road | San Pablo City, Laguna | 2015-06-12 | Final | Laguna 3rd DEO | LF | 1.89 | 45 | 2015-01-08 | 2015-02-21 | 35.56% | C | 0.46 | 0.13 | 0.3 | - | - | - | 89% | *89% Satisfactory
MEGA M BUILDERS | 20515 | L | B | MA | GE | Construction of Bridge Brgy. San Isidro | San Pablo City, Laguna 3rd LD | 2015-08-29 | 1st & Final | Laguna 3rd | LF | 3.911 | 90 | 2015-04-17 | 2015-07-15 | 33.33% | C | 0.419 | 0.133 | 0.3 | - | - | - | 85.2% | *85.2% Satisfactory
Megabucks Construction & Development Corporation | 37554 | L |  |  |  | NIA MARIIS DRD INFRA 2014-003 | MARIIS DRD | 2015-04-17 | 1st & Final | NIA | L | 4.948 | 60 | 2014-08-11 | 2014-10-11 | 0 | C | 0.4524 | 0.2 | 0.3 | - | - | - | - | *95.24% V. Satisfactory
Megawide Construction Corporation |  | L |  |  |  | Construction of Ten (10) Five storey LRB with Land Development | Camarin, Caloocan City | 04/23/15 | Final | NHA | LF | 620.31 | 687 | 02/20/12 | 2015-01-07 | -1.04 | C | 0.4669 | 0.1215 | 0.2688 | - | - | - | 85.72 | 86.06% Satisfactory
Megawide Construction Corporation |  | L |  |  |  | Construction of Ten (10) Five storey Medium Rise Buildings with Land Development | Camarin, Caloocan City | 2014-05-09 | 2nd | NHA | LF | 610.294 | 623 | 2012-02-20 | 2014-11-04 | -0.77 | O | 0.3715 | 0.2313 | 0.1423 | 0.03 | 0.0607 | 0.05 | 88.58 | -
Megawide Construction Corporation |  | L |  |  |  | Construction of Ten(10) Five storey Medium Rise Buildings with Land Development | Camarin, Caloocan City | 2013-10-31 | 1st | NHA | LF | 592.93 | 540 | 2012-02-20 | 2014-08-13 | -5.59 | O | 0.3473 | 0.2728 | 0.0941 | 0.03 | 0.0607 | 0.0333 | 83.82
Megawide Construction Corporation |  | L |  |  |  | Construction of Ten (10) Five storey Medium Rise Buildings with Land Development | Camarin, Caloocan City | 2013-10-31 | 1st | NHA | LF | 592.93 | 540 | 2012-02-20 | 2014-08-13 | -5.59 | On-going; Partial Suspension on Bldgs. A, B, C & D | 0.3473 | 0.2728 | 0.0941 | 0.03 | 0.0607 | 0.033 | 83.79 | -
MEGAY CONSTRUCTION | 34354 | L | A | MA | GB | Tourist Information Center and Tourist Rest Area (Green Restroom) | Kalibo and Ibajay, Aklan | 2015-07-23 | 1st | TIEZA | LF | 7 | 120 | 2015-04-12 | 2015-08-09 | 0 | O | 0.357 | 0.273 | 0.15 | 0.03 | 0.044 | 0.05 | 90.4 | -
Megay Construction | 34354 | L | A | SB | GB | Shoring at Dungeon in Fort Santiago | Intramuros, Manila | 2015-02-10 | 1st | TIEZA | LF | 3.3 | 105 | 2014-09-21 | 2014-12-24 | -13.29 | O | 0.284 | 0.3 | 0.017 | 0.03 | 0.07 | 0.05 | 75.12
Megay Construction | 34354 | L | A | SB | GB | Completion of Camiguin Tourism Center Pavillon | Mambajao, Camiguin | 2015-06-23 | 1st | TIEZA | LF | 6.7 | 120 | 2015-03-16 | 2015-07-14 |  | O | 0.363 | 0.281 | 0.15 | 0.03 | 0.025 | 0.05 | 89.9
Megay Construction | 34354 | L | A | SB | GB | Sibul Spring Resort Development | Abucay, Bataan | 2014-02-12 | Final | TIEZA | LF | 4.996 | 150 | 2013-07-17 | 2013-12-18 | 0 | C | 0.432 | 0.189 | 0.3 |  |  |  | 92.13 | 92.13% Very Satisfactory
Megay Construction |  | L |  |  |  | Sibul Spring Development | Abucay, Bataan | 2014-02-12 | 1st & Final | TIEZA | LF | 4.838 | 150 | 2013-07-17 | 2013-12-13 | 0 | C | 0.4323 | 0.189 | 0.3 | - | - | - | 92.13 | *92.13% V. Satisfactory
MEGAY CONSTRUCTION / ILC SUMMIT CONSTRUCTION, INC. (JV) | 34354 | L | A | MA | GB | Establishment of First Easter mass Archaeological Historical Recreation Park | Brgy. Pinamanculan, Butuan City | 2015-10-01 | 3rd | TIEZA | LF | 10 | 195 | 2014-11-04 | 2015-05-18 | 0 | O | 0.37 | 0.274 | 0.15 | 0.03 | 0.058 | 0.05 | 93.27 | -
MEGAY CONSTRUCTION AND ILC SUMMIT COSNTRUCTION, INC. (JV) | 34354 | L | A | MA | GB | Establishment of First Easter Mass Archaeological Historical Recreation Park | Brgy. Pinamanculan, Butuan City | 2015-12-03 | Final | TIEZA | LF | 10.3 | 195 | 2014-11-04 | 2015-04-17 | 0 | C | 0.476 | 0.2 | 0.3 |  |  |  | 97.6 | 83.9% Satisfactory
MEGAY CONSTRUCTION AND SUPPLY | 34354 | L | A | MA | GB | Toutist Information Center and Tourist Rest Area (Green Rest Room) | Kalibo and Ibajay, Aklan | 2015-10-08 | Final | TIEZA | LF | 5.5 | 120 | 2015-04-12 | 2015-08-09 | 0 | C | 0.478 | 0.2 | 0.3 |  |  |  | 97.8 | 92.60% Very Satisfactory
MEGAY CONSTRUCTION AND SUPPLY | 34354 | L | A | MA | GB | Completion of Tourism Center | Mambajao, Camiguin | 2015-10-15 | Final | TIEZA | LF | 6.5 | 120 | 2015-03-16 | 2015-07-16 | 0 | C | 0.45 | 0.188 | 0.3 |  |  |  | 93.8 | 91.1% Very Satisfactory
MEGAY CONSTRUCTION AND SUPPLY | 34354 | L | A | MA | GB | Shoring of Dungeon at Fort Santiago | Intramuros, Manila | 2015-11-16 | Final | TIEZA | LF | 3 | 165 | 2014-09-21 | 2015-02-22 | -4.000 | C | 0.478 | 0.2 | 0.3 |  |  |  | 97.8 | 84.18% Satisfactory
Megay Construction/ILC Summit Construction, Inc. (JV) | 34354 | L | A | SB | GB | Establishment of First Easter Mass-Archaeological Historical Recreation Park | Brgy. Pinamanculan, Butuan City | 2015-04-08 | 1st | TIEZA | LF | 10.3 | 150 | 2014-11-04 | 2015-04-17 | -56.89 | O | 0.2849 | 0.2248 | 0 | 0.015 | 0.056 | 0.05 | 63.07
Megay Construction/ILC Summit Construction, Inc. (JV) | 34354 | L | A | SB | GB | Establishment of First Easter Mass-Archaeological Historical Recreation Park | Brgy. Pinamanculan, Butuan City | 2015-06-10 | 2nd | TIEZA | LF | 10.3 | 195 | 2014-11-04 | 2015-08-18 | -9.69 | O | 0.3569 | 0.274 | 0.0531 | 0.015 | 0.0467 | 0.0333 | 77.9
Mel Jean Construction Corporation (Formerly: Mel Jean Enterprises) | 16344 | L | A | MA | GE1 | Widening of Manila-Batangas Rd., inc. Drainage Structure, Bugtong-Maraouy Sect., Km.72+300-Km.73+330 (Int. Sect.) | Lipa City, Batangas | 2013-03-11 | 1st | IVA | LF | 18.158 | 150 | 2013-01-14 | 2013-06-12 | 5.97 | O | 0.348 | 0.24 | 0.15 | 0.023 | 0.04 | 0.033 | 83.4 | -
Mel-Jean Construction Corporation (Formerly: Mel Jean Enterprises) | 16344 |  |  |  |  | Rehab./Reconst./Upgrading of Damaged Roads along Manila-Batangas Rd., Maraouy-Inosluban Sect. |  | 2010-06-07 |  | IVA |  | 7.419 | 90 |  |  |  | O | 0.355 | 0.225 | 0.15 | 0.015 | 0.05 | 0.05 | 84.5 | -
Mel-Jean Construction Corporation (Formerly: Mel-Jean Enterprises) | 16344 | L | A | MA | GE1 | Widening of Manila-Batangas Road inc. Drainage Structure Bugtong-Maraouy Sect., Km.72+300 - Km.73+330 (Int. Sect.) | Lipa City, Batangas | 2013-07-29 | Final | IVA | LF | 19.098 | 180 | 2013-01-14 | 2013-07-12 | 18.02 | C | 0.437 | 0.133 | 0.3 | - | - | - | 87 | 84.84% Satisfactory
Melrobe Builders & Construction Supplies | 29752 | L | A | SB | GE | Construction of Access Road from National Highway to Banaybanay Port, Banaybanay, Davao Oriental | Davao, Oriental | 2014-08-11 | 1st & Final | XI | LF | 5.8176 | 110 | 2014-02-03 | 2014-03-18 | 0 | C | 0.361 | 0.2 | 0.3 |  |  |  | 86.1 | 86.10% Satisfactory
Melrobe Builders & Construction Supplies | 29752 | L | A | MA | GB1 | Const. of Multi-Purpose Building Covered Court) Brgy. Cabadiangan |  | 2009-06-10 | 1st | XI |  | 2.362 | 90 |  |  |  | O | 0.371 | 0.3 | 0.15 | 0.03 | 0.047 | 0.033 | 93.1 | -
MELROBE BUILDERS AND CONSTRUCTION SUPPLIES | 0 | L | - | - | GB | Construction/Concreting of Roads Leading to Davao Oriental State College of Science and Technology, City of Mati, Davao Oriental | Mati, Davao Oriental | 2015-11-11 | Final | Davao Oriental 2nd DEO | LF | 4.447e-06 | 33 | 2015-02-13 | 2015-03-17 | 0 | C | 0.352 | 0.188 | 0.3 | - | - | - | 84% | 84% Satisfactory
Menjer Construction | 22815 | L | C | SB | GB1 | Construction of Perimeter Fence |  | 2008-11-26 | 1st | DOST |  | 8.853 | 180 |  |  |  | O | 0.349 | 0.242 | 0.15 | 0.018 | 0.025 | 0.033 | 81.7 | -
Menjer Construction | 22815 | L | C | SB | GB1 | Construction of Perimeter Fence |  | 2008-11-26 | 1st | DOST |  | 8.853 | 180 |  |  |  | O | 0.349 | 0.242 | 0.15 | 0.018 | 0.025 | 0.033 | 74.1 | -
Menjer Construction | 22815 | L | C | SB | GE1 | Repair/Rehab. of Rd. Slip along Dobleston-Butadon Nat'l R. (Secondary Rd.) | Butadon, Kapatagan, Lanao del Norte | 2012-11-28 | 1st | X | LF | 3.451 | 36 | 2012-10-04 | 2012-11-08 | 1.11 | O | 0.374 | 0.222 | 0.15 | 0.03 | 0.023 | 0.033 | 83.2 | -
Mesagon Eng'g Builders | 13749 | L |  | SB | GB1 | Propose Multi-Purpose Bldg. (Completion of the Innovation & Packaging Devt. Center) | DMC Compound, Cor. Dumanlas & Friendship Rd., Bajada, Davao City | 2011-03-31 | 1st | DOST | LF | 3.85 | 195 | 2011-01-04 | 2011-05-08 | 0 | O | 0.339 | 0.3 | 0.15 | 0.03 | 0.051 | 0.05 | 92 | -
Meta Construction | 28882 | L | C | SB | GB | Construction of 1 Sty 3-Classroom, San Miguel Integrated School | San Miguel, Ramon, Isabela | 2014-10-27 | 1st & Final | II | LF | 2 | 100 | 2014-09-01 | 2014-12-09 | 50% | C | 0.484 | 0.135 | 0.3 | - | - | - | 91.9% | 91.9% Very Satisfactory
Meta Construction | 28882 | L | C | SB | GE | Widening along Santiago - Tuguegarao Road Isabela 4th LD, K0338+137 - K0339+000, K0340+600 - K0340+750, K0341+100 - K0341+926 | Ramon, Isabela | 2014-08-12 | 1st | II | LF | 12.9615 | 180 | 2014-02-21 | 2014-08-19 | 0.03 | O | 0.356 | 0.232 | 0.15 | 0.018 | 0.035 | 0.033 | 82.4
Meta Construction | 28882 | L | C | SB | GE1 | Opening/Rehab. of FTMR Pangal Sur | Echague, Isabela | 2013-03-15 | 1st | II | LF | 9.046 | 120 | 2013-02-12 | 2013-06-11 | 32.2 | O | 0.363 | 0.226 | 0.15 | 0.03 | 0.033 | 0.028 | 83 | -
Meta Construction | 28882 | L | D | SB | GB1 | Construction of Multi-Purpose Building |  | 2009-03-05 | 1st | II |  | 0.458 | 80 |  |  |  | O | 0.24 | 0.3 | 0.15 | 0.023 | 0.028 | 0.033 | #VALUE! | -
META CONSTRUCTION | 28882 | L | C | SB | GE | Widening along Santiago-Tuguegarao Road, Isabela 4th LD, K0338+137.09 to K0339+000, K0340+600 to K0340+750, K0341+100 to K0341+926 | Bugallon Norte - Oscariz, Isabela | 2015-06-06 | Final | Isabela 4th DEO | LF | 12.961 | 180 | 2014-02-21 | 2014-08-19 | 14.6% | C | 0.327 | 0.2 | 0.3 | - | - | - | 82.7% | *82.52% Satisfactory
META CONSTRUCTION/ALXM CONSTRUCTION JOINT VENTURE | 0 | L | 0 | 0 | GE | Widening of National Roads along Santiago-Tuguegarao Road, K0329+165-K0329+389 (RS), K0329+155-K0329+428 (LS), K0330+000-K0330+205, K0330+215-K0331+661.8 Rizal, Santiago City-Raniag, Ramon, Isabela | Rizal, Santiago City-Raniag, Ramon, Isabela | 2015-11-17 | 1st | ISABELA 4TH DEO | LF | 45.256 | 209 | 2015-04-27 | 2015-11-21 | (-) 10.00 | OG | 0.372 | 0.24 | 0.05 | 0.024 | 0.051 | 0 | 73.7% | 73.7% Poor
Metrics Construction & Trading | - | L | - | - | GE | Construction/Rehabilitation of 15th Avenue (P. Tuazon - Bonny Serrano) | Quezon City | 2014-11-27 | 1st & Final | NCR | LF | 8.8144 | 177 | 2014-06-09 | 2014-12-02 | 25.93% | C | 0.421 | 0.133 | 0.3 | - | - | - | 85.4% | 85.4% Satisfactory
MF Construction | 22192 | L | D | SB | GB1 | Const.of DPWH Siquijor District Engineering Office Building inc. Quarters |  | 2009-09-07 | 1st | VII |  | 2.892 | 189 |  |  |  | O | 0.373 | 0.24 | 0.15 | 0.03 | 0.037 | 0.033 | 86.3 | -
MG Samidan Construction/ Tadian General ConstructionADIAN GENERAL CONSTRUCTION | JV-13-286 | L | B | MA | GE | Road Upgrading (Gravel to Paved) of Mt. Province-Ilocos Sur via Tue Road, Section 1: K0388+900 - K0389+500, K0393+500 - K0393+856; Section 2: K0398+000 - K0398+578, K0399+728 - K0399+811; Section 3: K0412+165 - K0412+942, K0413+327 - K0413+354, K0413+368 - K0413+400 | Tue, Tadian & Otucan, Bauko, Mt. Province | 2014-11-23 | 1st | CAR | LF | 56.1278 | 270 | 2014-04-22 | 2015-01-16 | 1.97% | O | 0.337 | 0.28 | 0.15 | 0.03 | 0.055 | 0.05 | 90.2% | 90.2% Very Satisfactory
MG SAMIDAN CONSTRUCTION/TADIAN GENERAL CONSTRUCTION -Joint Venture | JV-14-858 | L | B | MA | GE | Road Upgrading (Unpaved to Paved) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standards (HDM-4 Project Analysis) (Intermittent Sections) of Mt. Province - Ilocus Sur via Tue Road, K0387+081 to K0387+054, K0387+462 to K0388+800, Mt. Province | Mt. Province | 2015-09-01 | 1st | Mountain Province DEO | LF | 44.641 | 204 | 2015-05-07 | 2015-11-26 | 8.24% | O | 0.366 | 0.225 | 0.15 | 0.03 | 0.056 | 0.05 | 87.7% | -
MG SAMIDAN CONSTRUCTION/TADIAN GENERAL CONSTRUCTION (JV) | JV-13-286 | L | B | MA | GE | Road Upgrading (Gravel to Paved) of Mt. Province - Ilocos Sur via Tue Road, Section 1: K0388+900 - K0389+500, K0393+500 - K0393+856; Section 2: K0398+000 - K0398+578, K0399+728 - K0399+811; Section 3: K0412+165 - K0412+942, K0413+327 - K0413++354, K0413+368 - K0413+400 | Tue, Tadian & Otucan, Bauko, Mt. Province | 2015-06-05 | Final | CAR | LF | 56.128 | 285 | 2014-04-22 | 2015-01-31 | 0% | C | 0.358 | 0.2 | 0.3 | - | - | - | 85.8% | *88.44% Satisfactory
MG1 CONSTRUCTION CORPORATION | 36909 | L | B | SB | GE | Sapang Buhay Bridge along Daang Maharlika, Brgy. San Juan, ACCFA, Cabanatuan City | Cabanatuan City | 2015-06-11 | Final | Nueva Ecija 2nd DEO | LF | 2.4 | 35 | 2015-03-02 | 2015-04-05 | 0% | C | 0.5 | 0.133 | 0.3 | - | - | - | 93.3% | *93.3% Very Satisfactory
MGBJ Rising Construction & Developer | 18656 | L | B | MA | GE | Preventive Maintenance (Asphalt Overlay) along Sarangani - Davao del Sur Coastal Road, K1654+(-291) - K1654+324, Alabel, Sarangani Province | Sarangani Province | 2014-10-29 | 1st & Final | XII | LF | 8.7882 | 60 | 2014-02-13 | 2014-04-13 | 0% | C | 0.474 | 0.133 | 0.3 | - | - | - | 90.7% | 90.7% Very Satisfactory
MGDJ Construction | 29352 | L | D | SB | GE1 | Widening/Rehab. of Bridge from Two (2) Lanes to Four (4) Lanes along Batangas-Quezon Rd., Bawi Bridge, Padre Garcia | Batangas | 2013-07-29 | Final | IVA | LF | 3.526 | 106 | 2013-01-21 | 2013-05-06 | 0 | C | 0.415 | 0.133 | 0.3 | - | - | - | 84.8 | 85.58% Satisfactory
MGDJ Construction | 29352 | L | D | SB | GE1 | Widening/Rehab. of Bridge Two (2) lanes to Four (4) Lanes along Batangas-Quezon Rd., Bawi Bridge | Padre Garcia, Batangas | 2013-03-11 | 1st | IVA | LF | 3.399 | 90 | 2013-01-21 | 2013-04-20 | 1.28 | O | 0.358 | 0.24 | 0.15 | 0.03 | 0.05 | 0.033 | 86.1 | -
MGDJ CONSTRUCTION | 29352 | L | D | SB | GE | Repair and Maintenance of Flood Control and Drainage Structures at Rosario - San Juan Road, K0137+400 to K0140+650 w/ exception | San Juan, Batangas | 2015-06-05 | Final | Batangas 4th DEO | LF | 3.752 | 90 | 2014-11-28 | 2015-02-25 | 0% | C | 0.472 | 0.133 | 0.3 | - | - | - | 90.5% | *90.5% Very Satisfactory
MGDJ CONSTRUCTION | 29352 | L | D | SB | GE | Construction/Upgrading/Rehabilitation of Drainage along National Roads Daang Maharlika (LZ), K0107+558.60 to K0108+366.60 | Candelaria, Quezon | 2015-06-10 | 1st | Quezon 2nd DEO | LF | 13.364 | 180 | 2015-01-28 | 2015-07-26 | 1.2% | O | 0.373 | 0.21 | 0.15 | 0.03 | 0.035 | 0.033 | 83.1% | -
MGDJ CONSTRUCTION | 29352 | L | AAA | MA | GE | Construction/Upgrading/Rehabilitation of Drainage along National Roads Daang Maharlika (LZ), K0 107+558.60 - K0 108+366.6 | Candelaria, Quezon | 2015-09-02 | 1st | Quezon 2nd | LF | 13.364 | 240 | 2015-01-28 | 2015-09-24 | 3.15% | O | 0.337 | 0.24 | 0.15 | 0.03 | 0.045 | 0.05 | 85.2% | -
MGT Builders & Supply | 33872 | L | D | SB | GB | Repair/Reconst./Upgrading of Damaged Paved National Secondary Road along Jct. Donsol-Banuang Gurang Road | Donsol, Sorsogon | 2014-08-13 | 1st & Final | V | LF | 3.924 | 50 | 2014-01-30 | 2014-03-20 | 12 | C | 0.421 | 0.1333 | 0.3 |  |  |  | 85.43 | 85.43% Satisfactory
MICKAJETTE CONSTRUCTION AND TRADING | 35239 | L | D | SB | GB | Local Infrastructure Program-Construction of Multi-Purpose Building, Colo Elementary School, Dinalupihan, Bataan | Dinalupihan, Bataan | 2015-11-11 | Final | Bataan First DEO | LF | 5.105 | 150 | 2015-03-03 | 2015-07-30 | - | C | 0.485 | 0.133 | 0.3 | - | - | - | 91.8% | 91.8% Very Satisfactory
MICRO ASIA BUILDERS CORPORATION | 26286 | L | B | MA | GB | Construction of Information Center with Restroom | Guimbal Port, Guimbal, Iloilo | 2015-09-17 | Final | TIEZA | LF | 3 | 150 | 2015-03-05 | 2015-08-01 | -26.42 | C | 0.441 | 0.197 | 0 |  |  |  | 63.8 | 84.40% Satisfactory
Micro-Asia Builders Corporation | 26286 | L | B | MA | GB | Construction of Information Center with Restroom | Guimbal Port, Guimbal, Iloilo | 2015-06-18 | 1st | TIEZA | LF | 2.6 | 150 | 2015-03-05 | 2015-08-01 | -2.98 | O | 0.3771 | 0.3 | 0.1201 | 0.03 | 0.056 | 0.05 | 93.32
Micro-Asia Builders Corporation | 26286 | L | B | MA | GB | Const. of DepEd Standard Type School Building at Tayum ES Cauayan, Negros Occidental | Cauayan, Negros Occidental | 2014-08-09 | Final | VI | LF | 2.3022 | 85 | 2013-05-24 | 2013-08-16 | 0 | C | 0.441 | 0.2 | 0.3 |  |  |  | 94.1 | 85.98% Satisfactory
Micro-Asia Builders Corporation | 26286 | L | B | MA | GB1 | Const. of DepEd Standard Type Sch. Bldg. @ Tuyom ES | Cauayan, Negros Occidental | 2013-08-09 | 1st | VI | LF | 2.302 | 85 | 2013-05-24 | 2013-08-16 | 30.81 | O | 0.334 | 0.24 | 0.15 | 0.03 | 0.038 | 0.033 | 82.5
Micro-Asia Builders Corporation |  | L |  |  |  | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Road, Bacolod Circumferential Road (S), K0010+424 - K0011+521 | Bacolod City | 2014-10-27 | 1st & Final | VI | LF | 11.473 | 120 | 2014-02-13 | 2014-06-12 |  | C | 0.417 | 0.133 | 0.3 | - | - | - | 85% | 85% Satisfactory
MIGHTY A'S CONSTRUCTION & HARDWARE SUPPLY | 34791 | L | D | SB | GE | Construction of Multi-Purpose Building Covered Court, Barangay 109, Tacloban City | Barangay 109, Tacloban City | 2015-09-01 | 1st | Tacloban City | LF | 4.98 | 60 | 2015-07-31 | 2015-09-28 | (+)50.00 | O | 0.236 | 0.3 | 0.15 | 0.03 | 0.041 | 0.05 | 80.7% | -
Mighty Construction & Supply | 34278 | L | C | SB | GB | Construction of Classroom in Areas Experiencing Acute Classroom Shortage, Lupa E/S, One (1) Classroom, SB, Lupa | Kasibu, Nueva Vizcaya | 2014-10-30 | 1st | II | LF | 1.1295 | 90 | 2014-07-15 | 2014-10-12 |  | O | 0.367 | 0.3 | 0.15 | 0.03 | 0.018 | 0.033 | 89.8% | 89.8% Very Satisfactory
MIGHTY CONSTRUCTION & SUPPLY | 34278 | L | C | SB | GB | Construction of Classroom in Areas Experiencing Acute Cl Shortage, Lupa E/S, One (1) Storey, One (1) Classroom S/B Lupa | Lupa, Kasibu, Nueva Vizcaya | 2015-06-08 | Final | Nueva Vizcaya 2nd DEO | LF | 1.13 | 90 | 2014-07-15 | 2014-10-12 | 0% | C | 0.482 | 0.2 | 0.3 | - | - | - | 98.2% | *92.32% Very Satisfactory
Migo Construction | 34663 | L | D | SB | GB | Construction of Two Units, One-Storey, One Classroom School Building at Sabang Elementary School | Surigao City | 2014-10-28 | 1st | XIII | LF | 2.1276 | 60 | 2014-09-30 | 2014-11-28 | 7.91% | O | 0.357 | 0.24 | 0.15 | 0.02 | 0.043 | 0.05 | 86% | 86% Satisfactory
Mikkil Construction | 37020 | L | D | SB | GE | Const. of Classroom (BEFF Batch 1) 1 Storey 1 CL Tula ES, 1 storey 2 CL Molocboloc PS | Alubijib, Misamis Oriental | 2014-10-27 | 1st & Final | X | LF | 3.07 | 75 | 2014-07-23 | 2014-10-05 | -2.04% | C | 0.358 | 0.161 | 0 | - | - | - | 51.9% | 51.9% Poor
MILAN GENERAL CONSTRUCTION CORPORATION | 41578 |  | AAA | LB |  | Continuation of the Rehabilitation of Lupon Port | Lupon, Davao Oriental | 2015-10-21 | 1st | DOTC | LF | 45.451 | 330 | 2015-04-30 | 2016-03-26 | 0.14 | O | 0.372 | 0.3 | 0.15 | 0.03 | 0.07 | 0.05 | 97.2 | -
MILAN GENERAL CONSTRUCTION CORPORATION | 41578 |  | AAA | LB |  | Continuation of the Rehabilitation of Lupon Port | Lupon, Davao Oriental | 2016-02-04 | 2nd | DOTC | LF | 45.451 | 330 | 2015-04-30 | 2016-03-26 | 1.91 | O | 0.383 | 0.3 | 0.15 | 0.03 | 0.07 | 0.05 | 98.3 | -
Milan General Construction Corporation | 41578 |  | AAA | LB |  | Continuation of the Rehabilitation of Lupon Port | Lupon, Davao Oriental | 2016-08-10 | 3rd & Final | DOTC | LF | 45.451 | 330 | 2015-04-30 | 2016-06-21 | 0 | C | 0.443 | 0.2 | 0.3 | - | - | - | 94.3 | 96.30% Outstanding
MILIGAN CONSTRUCTION AND GENERAL ENGINEERING | 37258 | L | C | SB | GB | Construction of Multi-Purpose Building at Brgy. Balaoa | Tadian, Mountain Province | 2015-06-04 | Final | Mountain Province DEO | LF | 2.5 | 115 | 2014-09-15 | 2015-01-08 | 0% | C | 0.388 | 0.2 | 0.3 | - | - | - | 88.8% | *88.8% Satisfactory
Min Construction | 14656 | L | B | MA | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads Including Drainage based on Pavement Management Analysis-4 (HDM-4 Project Analysis) Intermittent Section along Ipil-Liloy-Sindangan Road (Poblacion Muslim and Taway Section) K2004+497 to K2004+800; K2010+360 to K2011+420; and K2012+000 to K2012+790 with exception | Zamboanga Sibugay | 2014-10-23 | 1st & Final | IX | LF | 33.8409 | 225 | 2014-02-14 | 2014-09-26 | 0% | C | 0.423 | 0.133 | 0.3 | - | - | - | 85.6% | 85.6% Satisfactory
Min Construction | 14656 | L | B | MA | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Road including Drainage based on Pavement Management System/Highway Devt. & Management-4 (HDM-4 Project Analysis) Intermittent Section along Ipil-Liloy-Sindangan Road (Poblacion Muslim and Taway Section (K2004+497 to K2004+800; K2010+360 to K2011+420; and K2012+000 to K2012+790 with exception | Zamboanga Sibugay | 2014-08-08 | 1st | IX | LF | 31.1952 | 195 | 2014-02-14 | 2014-08-27 | -0.26 | O | 0.312 | 0.3 | 0.147 | 0.03 | 0.035 | 0.033 | 85.7
Min Construction | 14656 | L | B | MA | GE1 | Road Upgrading (Gravel to Concrete) at Sindangan-Siayan-Dumingag-Mahayag Road (Denoyan-Pob.-Siayan Section) | Siayan, Zamboanga del Norte | 2011-04-13 | 1st | IX | LF | 33.841 | 385 | 2010-06-22 | 2011-07-11 | 8.12 | O | 0.328 | 0.3 | 0.15 | 0.03 | 0.038 | 0.05 | 89.6 | -
Min Construction | 14656 | L | B | MA | GE1 | Proposed Conc. of Liloy-Siocon Road (Kipit-Gutalac Section) |  | 2008-08-28 | 1st | IX |  | 19.125 | 168 |  |  |  | O | 0.317 | 0.24 | 0.1 | 0.03 | 0.047 | 0.1 | 83.4 | -
Min Construction | 14656 | L | B | MA | GE1 | Proposed Conc. of Liloy-Siocon Road (Kipit-Gutalac Section) |  | 2008-11-25 | 2nd | IX |  | 19.125 | 213 |  |  |  | O | 0.327 | 0.239 | 0.1 | 0.03 | 0.025 | 0.067 | 78.8 | -
Min Construction | 14656 | L | B | SB | GE1 | Rd. Upgrading (Gravel to Paved) Sindangan-Siayan-Dumingag-Mahayag Rd. (Suguilon Sect.), Km.1933+000-Km.1934+841 Modified to Km.1949+613-Km.1951+425 | Zamboanga del Norte | 2012-11-28 | 2nd | IX | LF | 39.43 | 180 | 2012-06-06 | 2012-12-02 | 0 | O | 0.286 | 0.3 | 0.15 | 0.03 | 0.043 | 0.033 | 84.2 | -
Min Construction | 14656 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Paved), Sindangan-Siayan-Dumingag-Mahayag Rd. (Suguilon Sect.) Km.1933+000-Km.1934+841 Modified to Km.1949+613-Km.1951+425 | Zamboanga del Norte | 2012-08-25 | 1st | IX | LF | 39.43 | 150 | 2012-06-06 | 2012-11-02 | 3 | O | 0.33 | 0.3 | 0.15 | 0.03 | 0.032 | 0.033 | 87.5 | -
Min Construction | 14656 | L | B | MA | GE1 | Conc. of Jct. Imelda-Alicia Rd. (Lutimon-Lambuyugon Sect.) | Alicia, Zamboanga Sibugay | 2012-08-28 | 2nd | IX | LF | 42.706 | 261 | 2011-12-23 | 2012-09-08 | -0.84 | O | 0.357 | 0.232 | 0.142 | 0.03 | 0.035 | 0.033 | 82.9 | -
MIN CONSTRUCTION | 14656 | L | B | MA | GE | Rehab./Reconst./Upgrading of Damaged Paved National Roads including Drainage Based on Pavement Management System/HDM-4 (Project Analysis)(Intermittent Section) along Ipil - Liloy - Sindangan Road, Brgy. Camanga, Titay - Taway, K2004+497 to K2004+733, K2010+360 tp K2011+420.20, K2012+000 to K2012+790, Ipil, Zamboanga Sibugay | Ipil, Zamboanga Sibugay | 2015-06-10 | Final | Zamboanga Sibugay 2nd DEO | LF | 33.285 | 315 | 2014-02-14 | 2014-12-25 | 0.78% | C | 0.398 | 0.2 | 0.3 | - | - | - | 89.8% | *89.8% Very Satisfactory
MINDANAO CONSTRUCTION SERVICES & LAND DEVELOPMENT CORPORATION | 34147 | L | C | SB | GE | Concreting of Road at Brgy. San Vicente | Panabo City (Gala-Gala to Poblacion), Davao del Norte | 2015-06-10 | Final | Davao del Norte | LF | 1.911 | 44 | 2015-04-14 | 2015-05-27 | 0% | C | 0.414 | 0.133 | 0.3 | - | - | - | 84.7% | *84.7% Satisfactory
Mindanao Construction Services and Development Corporation | 34147 | L | C | SB | GE | Conctruction of Road-Lika to Cemetery under Local Infrastructure | M'Lang Cotabato | 2014-08-09 | 1st & Final | XII | LF | 4.5781 | 77 | 2014-04-22 | 2014-07-07 | 0 | C | 0.473 | 0.133 | 0.3 |  |  |  | 90.6 | 90.60% Very Satisfactory
Mindanao Rock | 23479 | L | A | MA |  | Ozamis Airport Development Project | Ozamis City/ Region X | 07/16/15 | Final | DOTC | LF | 67.141 | 330 | 2014-07-25 | 09/30/15 | 18.92 | C | 0.4124 | 0.2 | 0.3 | - | - | - | 91.24 | *92.29% V. Satisfactory
Mindanao Rock | 23479 | L | A | MA |  | Ozamis Airport Development Project | Ozamis City, Zamboanga Del Norte | 2015-04-28 | 2nd | DOTC | LF | 67.141 | 270 | 2014-05-18 | 2015-04-20 | 3.14 | O | 0.366 | 0.3 | 0.15 | 0.03 | 0.044 | 0.05 | 94 | -
Mindanao Rock | 23479 | L | A | MA |  | Ozamis Airport Development Project | Ozamis City, Zamboanga del Norte | 2014-12-10 | 1st | DOTC | LF | 67.141 | 270 | 2014-05-18 | 2015-02-11 | 1.78 | O | 0.356 | 0.3 | 0.15 | 0.02 | 0.044 | 0.05 | 92 | -
Mindanao Rock | 23479 | L | B | MA | GE1 | Const. of Ozamis City Coastal By-Pass Road |  | 2009-06-09 | 1st | X |  | 42.951 | 240 |  |  |  | O | 0.309 | 0.258 | 0.15 | 0.02 | 0.043 | 0.05 | 83 | -
Mindanao Rock | 23479 | L | B | MA | GE1 | Const. of Ozamis City Coastal By Pass Road |  | 2009-09-16 | 2nd | X |  | 42.95 | 240 |  |  |  | O | 0.308 | 0.257 | 0.15 | 0.03 | 0.051 | 0.033 | 82.9 | -
Mindanao Rock / GLS Construction and General Merchandise | JV-12-510 | L | A | MA | GE1 | Widening/Impv't. of Ozamiz-Oroquieta Rd. (Clarin-Sinacaban) Km.1705+979-Km.1721+184, w / exceptions | Misamis Occidental | 2013-08-16 | 1st | X | LF | 25.944 | 140 | 2013-03-27 | 2013-08-13 | 5.67 | O | 0.32 | 0.2 | 0.072 | 0.03 | 0.025 | 0.033 | 68
MINROCK MULTI-BUILDERS | 15845 | L | B | SB | GB | Cluster MP-2 c) Const of MPB at Brgy. Midtapok | Lambayong, Sultan Kudarat | 2015-08-31 | 1st & Final | Sultan Kudarat 1st | LF | 2.463 | 138 | 2015-03-04 | 2015-07-19 | 0% | C | 0.49 | 0.133 | 0.3 | - | - | - | 92.3% | *92.3% Very Satisfactory
Mivico Builders and Developers | 20551 | L | B | MA | GE | Rehab./Reconst./Upgrading of Damaged Paved National Road, Sumacab-San Josef-Bonifacio Road | Cabanatuan City | 2014-09-26 | 1st & Final | Special 3 | LF | 12.6751 | 90 | 2014-04-17 | 2014-07-15 | 8.09 | C | 0.323 | 0.2 | 0.3 |  |  |  | 82.3 | 82.30% Satisfactory
Mivico Builders and Developers | 20551 |  |  |  |  | Upgrading of Nueva Ecija-Pangasinan Rd. |  | 2010-06-07 |  | III |  | 24.003 | 90 |  |  |  | O | 0.369 | 0.198 | 0.15 | 0.03 | 0.048 | 0.033 | 82.8 | -
MJ Barcelona Construction and Supply | 34723 |  |  | SB |  | Construction of San Rafael Communal Irrigation Project Contract Reference No. NIA R6-ARISP-RAFAEL-CW14-14 | Dumalag, Capiz | 2015-02-19 | 1st | NIA | L | 10.783 | 150 | 2014-09-12 | 2015-03-13 | 2.6 | O | 0.3816 | 0.2626 | 0.15 | 0.03 | 0.0636 | 0.05 | 93.78 | -
MJ Barcelona Construction and Supply | 71781 | L |  |  | GE2 | Rehab. Of Jalaur-Saugue RIS (Suague Area) Bench Flume, Lat B3 NIAR6-NIS Extn. 13-JSRIS-CW32-13 | Pototan, Iloilo | 2013-11-15 | 1st | NIA | L | 4.666 | 90 | 2013-05-22 | 2013-10-07 | -45.54 | O | 0.355 | 0.126 | 0 | 0.01 | 0.028 | 0.033 | 55.2 | -
MJ TIONGSON CONSTRUCTION | 24202 | L | B | MA | GE | Widening of National Roads, Digos-Makar Road, 0-175 | General Santos City | 2015-06-12 | 1st | South Cotabato 2nd DEO | LF | 3.441 | 105 | 2015-03-15 | 2015-06-27 | -0.16% | O | 0.345 | 0.24 | 0.148 | 0.03 | 0.05 | 0.03 | 84.3% | -
MJ TIONGSON CONSTRUCTION (Formerly MJT Builders) | 24202 | L | B | MA | GB | Widening of National Roads, Digos-Makar Road, O-175 | General Santos City | 2015-09-04 | 1st & Final | South Cotabato II | LF | 3.441 | 135 | 2015-09-04 | 2016-01-16 | (+)6.17% | C | 0.494 | 0.134 | 0.3 | - | - | - | 92.8% | *92.8% Very Satisfactory
MJMARI BUILDERS AND ENTERPRISES | 36434 | L | D | SB | GB | Renovation of Multi-Purpose Building (Repair of Gymnasium), Municipality of Labason, Zamboanga del Norte | Municipality of Labason, Zamboanga del Norte | 2015-06-03 | Final | Zamboanga del Norte 2nd DEO | LF | 2.95 | 135 | 2014-10-30 | 2015-03-13 | 1% | C | 0.468 | 0.133 | 0.3 | - | - | - | 90.1% | *90.1% Very Satisfactory
MJMARI BUILDERS AND ENTERPRISES | 36434 | L | D | SB | GB | Construction of Multi-Purpose Building (Phase II), Brgy. Pag-asa, Dumalinao, Zamboanga del Sur | Dumalinao, Zamboanga del Sur | 2015-11-12 | Final | Zamboanga Del Sur 2nd DEO | LF | 6.1776 | 90 | 2015-02-27 | 2015-05-27 | - | C | 0.483 | 0.133 | 0.3 | - | - | - | 91.6% | 91.6% Very Satisfactory
MJMARI BUILDERS AND ENTERPRISES/MINDANAO ROCK (Joint Venture) | - | L | D | SD | GE | Construction/Rehabilitation of Tukuran River Control Militar Bridge, Tukuran, Zamboanga del Sur | Tukuran, Zamboanga del Sur | 2015-06-06 | Final | Zamboanga del Sur 1st DEO | LF | 12.737 | 171 | 2014-03-18 | 2014-09-04 | 0% | C | 0.472 | 0.133 | 0.3 | - | - | - | 90.5% | *90.5% Very Satisfactory
MM Construction Corporation (Formerly: MM Construction) | 12012 | L | B | MA | GE1 | Widening of Daang Maharlika, K0270+755.40-K0271+736.40 | Solano, Nueva Vizcaya | 2013-03-20 | 1st | II | LF | 14.086 | 90 | 2013-01-28 | 2013-04-27 | 0.41 | O | 0.347 | 0.24 | 0.15 | 0.03 | 0.056 | 0.033 | 85.6 | -
MN Bayalas Construction | 34251 | L | D | SB | GB1 | Const. of 1-Storey, 2-CL at Kahayagan NHS | Tagbina, Surigao City | 2013-08-17 | Final | XIII | LF | 1.305 | 135 | 2012-11-14 | 2013-03-28 | 2.22 | C | 0.381 | 0.2 | 0.3 | - | - | - | 88.1 | 85.70% Satisfactory
MN Bayalas Construction | 34251 | L | B | SB | GE2 | Drainage along NRJ Barobo-Agusan del Sur Bdry. | Barobo, Surigao del Sur | 2013-03-17 | Final | XIII | LF | 4.55 | 165 | 2012-09-18 | 2013-03-01 | 0 | C | 0.449 | 0.2 | 0.3 | - | - | - | 94.9 | 89.20% V. Satisfactory
MN Bayalas Construction | 34251 | L | B | SB | GB1 | Const. of 1 Storey-2 CL at Kahayagan NHS, Tagbina, SDS Kahayagan | Tagbina, Surigao del Sur | 2013-03-17 | 1st | XIII | LF | 1.305 | 135 | 2012-11-14 | 2013-03-28 | 4.05 | O | 0.395 | 0.225 | 0.15 | 0.015 | 0.023 | 0.033 | 84.1 | -
MN Macato Builders | 33448 | L | D | SB | GE1 | Impv't. of Manlawaan Bridge II Approaches & Other Bridges along Nat'l Rds & Grouted Riprap, Districtwide | Tabango, Leyte | 2013-08-12 | Final | VIII | LF | 3.784 | 150 | 2012-11-14 | 2013-04-12 | 0 | C | 0.368 | 0.2 | 0.3 | - | - | - | 86.8 | 79.54% Unsatisfactory
MN Macato Builders | 33448 | L | D | SB | GE1 | Impv't. of Manlawaan Bridge II Approaches & Other Bridges along Nat'l. Rds. & Grouted Riprap, Districtwide | Tabango, Leyte | 2013-03-13 | 1st | VIII | LF | 3.784 | 150 | 2012-11-14 | 2013-04-12 | 1.52 | O | 0.269 | 0.225 | 0.15 | 0.03 | 0.04 | 0.033 | 74.7 | -
Molte Aries Construction & Industries | 3684 | L | B | MA | GE1 | Road Upgrading of San Fernando-Bagulin Road |  | 2009-09-02 | 2nd | I |  | 14.114 | 400 |  |  |  | O | 0.353 | 0.3 | 0.15 | 0.03 | 0.06 | 0.033 | 92.6 | -
Molte Aries Construction & Industries | 3684 | L | B | MA | GE1 | Road Upgrading of San Fernando-Bagulin Road |  | 2009-05-28 | 1st | I |  | 14.114 | 400 |  |  |  | O | 0.3 | 0.26 | 0.15 | 0.03 | 0.035 | 0.033 | 80.8 | -
MOM Enterprises | [5 empty] | Package X-M: Construction of lateral "N" (Sta. 14+500-Sta. 16+960) and sub-lat. "N-11" (Sta. 0+000-Sta. 1+380) including related structures and supply, delivery and installation of steel gates | Guimba, Nueva Ecija | 2015-02-07 | 1st | NIA | L | 25.621 | 180 | 2014-07-28 | 2015-03-31 | -3.5 | O | 0.3312 | 0.3 | 0.115 | 0.03 | 0.0187 | 0.05 | 84.49 | -
Monolithic Construction & Concrete Product, Inc. | 5733 | L | AAA | MB | GE3 | Const. of Water Impounding at Poblacion | General Nakar, Quezon | 2012-08-08 | 1st | IVA | LF | 30.07 | 300 | 2012-03-20 | 2013-01-13 | 5.48 | O | 0.34 | 0.24 | 0.15 | 0.03 | 0.05 | 0.033 | 84.3 | -
Monolithic Construction & Concrete Product, Inc. | 5733 | L | AA | LA | GE1 | Rehab./Conc. of Marinduque Circumferential Road (Intermittent Section) |  | 2009-08-25 | 3rd | IVB |  | 82.9515 | 360 |  |  |  | O | 0.37 | 0.282 | 0.15 | 0.03 | 0.051 | 0.033 | 91.6 | -
MONOLITHIC CONSTRUCTION & CONCRETE PRODUCTS INC. / BISLIG VENTURE CONSTRUCTION & DEV''T. INC. / LUMEL GLENN CONSTRUCTION JOINT VENTURE | JV-14-860 | L | AA | LA | GE | Rehabilitation/Reconstruction of Mindoro Oriental/Occidental East Coastal Road, KO183+000 to KO184+761; KO185+282 to KO186+153; KO186+420 to KO187+531.60; KO190+428 to KO190+530; KO195+00 to KO195+049.32, Roxas, Oriental Mindoro | Roxas, Oriental Mindoro | 2015-08-29 | 1st | Southern Mindoro DEO | LF | 80.837 | 272 | 2015-06-26 | 2016-03-23 | 2.12% | O | 0.363 | 0.24 | 0.15 | 0.03 | 0.054 | 0.05 | 88.7% | -
MONOLITHIC CONSTRUCTION & CONCRETE PRODUCTS INC./ BISLIG VENTURE CONSTRUCTION & DEV"T. INC / LUMEL GLENN CONSTRUCTION JOINT VENTURE | JV-14-466 | L | B | MA | GE | Repair/Improvement of San Rafael River Control, Sta. 0+000 - Sta. 0+703; Sta. 0+000-Sta. 0+189; Sta. 0+000-Sta. 0+780; Sta. 0+000 - Sta. 0+22.50, San Rafael, Roxas, Oriental Mindoro | San Rafael, Roxas, Oriental Mindoro | 2015-08-29 | 1st | Southern Mindoro DEO | LF | 88.765 | 282 | 2015-06-26 | 2016-04-03 | 1.03% | O | 0.348 | 0.28 | 0.15 | 0.03 | 0.049 | 0.05 | 90.7% | -
MONOLITHIC CONSTRUCTION & CONCRETE PRODUCTS INC./ GREEN ISLAND ENTERPRISES JOINT VENTURE | JV-14-841 | L | AA | LA | GE | Construction of New Permanent Bridge: Bagong Sikat Bridge along Calapan South Road, Bulalacao, Oriental Mindoro | Bulalacao, Oriental Mindoro | 2015-08-29 | 1st | Southern Mindoro DEO | LF | 23.754 | 222 | 2015-04-07 | 2015-11-14 | 4.15% | O | 0.373 | 0.24 | 0.15 | 0.023 | 0.054 | 0.05 | 89% | -
Monolithic Construction & Concrete Products, Inc. | 5733 | L | AA | LA | GE | Construction of Slope Protection along NCR-Bulacan Bdry.-Bigte-Ipo Dam Road, Ilog Bayad Bridge | San Jose Del Monte City, Bulacan | 2014-11-28 | 1st & Final | III | LF | 46.5342 | 170 | 2014-03-11 | 2014-08-27 | 0% | C | 0.466 | 0.133 | 0.3 | - | - | - | 89.9% | 89.9% Very Satisfactory
Monolithic Construction & Concrete Products, Inc. | 5733 | L | AA | MB | GE | Rehab./Reconst./Upgrading of Damaged Paved National Roads Mdo. Or./Occ. ECR Milagrosa Section (K0186+182-K0187+000 and K0201+527 | Bulalacao, Oriental Mindoro | 2014-11-27 | 1st & Final | IV | LF | 18.2392 | 189 | 2014-02-12 | 2014-08-19 | 0% | C | 0.463 | 0.133 | 0.3 | - | - | - | 89.6% | 89.6% Very Satisfactory
Monolithic Construction & Concrete Products, Inc. | 5733 | L | AA | MB | GE3 | Const. of Water Impounding at Poblacion | Gen. Nakar, Quezon | 2013-08-08 | Final | IVA | LF | 30.07 | 389 | 2012-03-20 | 2013-04-12 | 0 | C | 0.296 | 0.2 | 0.3 | - | - | - | 79.6 | 82.42% Satisfactory
Monolithic Construction & Concrete Products, Inc. | 5733 | L | AA | MB | GE1 | Rehab./Conc. of Marinduque Circumferential Road (Intermittent Section) |  | 2009-05-19 | 2nd | IV-B |  | 82.951 | 360 |  |  |  | O | 0.353 | 0.3 | 0.15 | 0.03 | 0.033 | 0.05 | 91.6 | -
Monolithic Construction & Concrete Products, Inc. | 5733 | L | AA | MB | GE1 | Rehab./Conc. of Marinduque Circ. Rd. (Intermittent Section) |  | 2009-03-11 | 1st | IV-B |  | 82.951 | 360 |  |  |  | O | 0.296 | 0.272 | 0.15 | 0.03 | 0.025 | 0.05 | #VALUE! | -
Monolithic Construction & Concrete Products, Inc. | 5733 | L | AA | MB | GE | Replacement/Rehabilitation of Tiguisan Munti Bridge along Calapan South Road | Bansud, Oriental Mindoro | 2014-08-12 | Final | IV-B | LF | 4.2729 | 207 | 2013-01-28 | 2013-08-22 | 0 | C | 0.406 | 0.133 | 0.3 |  |  |  | 83.9 | 83.18% Satisfactory
Monolithic Construction & Concrete Products, Inc. | 5733 | L | AA | MB | GE1 | Replacement/Rehab. of Tiguisan Munti Bridge along Calapan South Rd. | Bansud, Oriental Mindoro | 2013-07-31 | 1st | IVB | LF | 4.273 | 207 | 2013-01-28 | 2013-08-22 | 0.07 | O | 0.349 | 0.24 | 0.15 | 0.02 | 0.035 | 0.05 | 84.4
Monolithic Construction & Concrete Products, Inc. | 5733 | L | AA | LA | GE | Construction of Kasay Flood Control along Dr. Damian Reyes Road (Boac Side) | Boac, Marinduque | 2014-08-16 | Final | IV-B | LF | 15.3071 | 210 | 2013-05-30 | 2013-12-25 | 0 | C | 0.436 | 0.133 | 0.3 |  |  |  | 86.9 | 87.38% Satisfactory
Monolithic Construction & Concrete Products, Inc. | 5733 | L | AA | LA | GE2 | Const. of Kasay Flood Control along Dr. Damian Reyes Rd. (Boac Side) | Boac, Marinduque | 2013-08-07 | 1st | IVB | LF | 14.105 | 196 | 2013-05-30 | 2013-12-11 | 10.28 | O | 0.32 | 0.3 | 0.15 | 0.015 | 0.042 | 0.05 | 87.7
Monolithic Construction & Concrete Products, Inc. | 5733 | L | AA | MB | GE | Reconstruction of Road Slip along Mogpog - Balanacan Road (Mogpog - Balanacan Section) Km. 11+000 - Km. 16+937, with Exception | Balanacan, Mogpog, Marinduque | 41867 | Final | IV-B | LF | 15.9236 | 236 | 2013-01-25 | 2013-09-17 | 3.5 | C | 0.451 | 0.132 | 0.3 |  |  |  | 88.3 | 86.68% Satisfactory
Monolithic Construction & Concrete Products, Inc. | 5733 | L | AA | MB | GE1 | Reconst. of Rd. Slip along Mogpog-Balanacan Rd. (Mogpog-Balanacan Sect.) Km.11+000-Km.16+937 w/ exceptions | Balanacan, Mogpog, Marinduque | 2013-08-07 | 2nd | IVB | LF | 15.915 | 236 | 2013-01-25 | 2013-09-17 | 18.49 | O | 0.328 | 0.241 | 0.15 | 0.03 | 0.032 | 0.05 | 83.1
Monolithic Construction & Concrete Products, Inc. | 5733 | L | AA | MB | GE1 | Reconst. of Rd. Slip along Mogpog-Balanacan Rd. (Mogpog-Balanacan Sect.) Km.11+000-Km.16+937.00 w/ exception | Balanacan, Mogpog, Marinduque | 2013-03-23 | 1st | IVB | LF | 15.915 | 215 | 2013-01-25 | 2013-08-27 | 53.04 | O | 0.388 | 0.235 | 0.15 | 0.03 | 0.045 | 0.033 | 88.1 | -
Monolithic Construction & Concrete Products, Inc. | 5733 | L | AA | MB | GE1 | Impv't/Conc.Paving of Jct. Baliguian to Siocon Road, Jct. Baliguian-Nonoyan-Sta. Maria Section |  | 2009-03-07 | 1st | IX |  | 48.006 | 380 |  |  |  | O | 0.386 | 0.263 | 0.099 | 0.03 | 0.037 | 0.033 | #VALUE! | -
Monolithic Construction & Concrete Products, Inc. | 5733 | L | AA | MB | GE | Road leading to Mahangub-Lubilan & Talabaan Falls, Upgrading (Gravel to Concrete) | Naawan, Misamis Oriental | 2014-10-27 | 2nd | X | LF | 45.4342 | 239 | 2014-03-12 | 2014-11-05 | -12% | O | 0.267 | 0.294 | 0.03 | 0.023 | 0.037 | 0.033 | 68.4% | 68.4% Poor
Monolithic Construction & Concrete Products, Inc. | 5733 | L | AA | LA | GE | Improvement of Drainage Structure at Sapang Creek along Butuan City-Cagayan de Oro City Road Phase II | Brgy. Bulua, Cagayan de Oro City | 2014-08-16 | Final | X | LF | 40.8707 | 299 | 2013-02-22 | 2013-12-17 | 0 | C | 0.479 | 0.2 | 0.3 |  |  |  | 97.9 | 84.46% Satisfactory
Monolithic Construction & Concrete Products, Inc. | 5733 | L | AA | MB | GE1 | Impv't. of Drainage Structure at Sapang Creek along Butuan City-Cagayan de Oro City Rd. Phase II, Brgy. Bulua | Cagayan de Oro City | 2013-08-11 | 1st | X | LF | 40.871 | 239 | 2013-02-22 | 2013-10-18 | -10.59 | O | 0.368 | 0.24 | 0.044 | 0.03 | 0.04 | 0.033 | 75.5
Monolithic Construction & Concrete Products, Inc. | 5733 | L | A | LA | GE | Rehabilitation and Protection of Tuganay River | Tuganay, Carmen, Davao del Norte | 2014-10-23 | 1st | XI | LF | 39.5294 | 132 | 2014-09-23 | 2015-02-01 | 93.5% | O | 0.4 | 0.3 | 0.15 | 0.03 | 0.03 | 0.025 | 93.5% | 93.5% Very Satisfactory
Monolithic Construction & Concrete Products, Inc. | 5733 | L | AA | LA | GE | Concrete Revetment on Steel Sheet Piles along Talomo River, Kalye Apike Section, Calinan District, Davao City | Calinan District, Davao City | 2014-10-20 | 1st | XI | LF | 28.3408 | 201 | 2014-08-05 | 2015-02-21 | -4% | O | 0.389 | 0.243 | 0.11 | 0.015 | 0.055 | 0.033 | 84.5% | 84.5% Satisfactory
Monolithic Construction & Concrete Products, Inc. | 5733 | L | AA | MB | GE | Rehabilitation/Improvement/Widening of Mamay Road forn Jct. Diversion to Daang Maharlika | Davao City | 2014-08-15 | 1st | XI | LF | 44.6798 | 181 | 2014-04-28 | 2014-10-25 | 0.35 | O | 0.313 | 0.225 | 0.15 | 0.03 | 0.05 | 0.05 | 81.8
Monolithic Construction & Concrete Products, Inc. | 5733 | L | AA | MB | GE1 | Const./Widening/Upgrading/Rehab. of Jct. Island Garden City of Samal Circ. Road, Babak-Tambo Island Garden City of Samal | Davao del Norte | 2013-08-20 | 2nd | XI | LF | 41.594 | 222 | 2013-01-23 | 2013-09-01 | 0.6 | O | 0.279 | 0.3 | 0.15 | 0.03 | 0.045 | 0.033 | 83.7
Monolithic Construction & Concrete Products, Inc. | 5733 | L | AA | MB | GE1 | Const./Widening/Upgrading/Rehab. of Jct. Island Garden City of Samal Circ. Rd., Babak-Tambo | Davao del Norte | 2013-03-17 | 1st | XI | LF | 41.594 | 179 | 2013-01-23 | 2013-07-20 | 0.23 | O | 0.358 | 0.245 | 0.15 | 0.03 | 0.03 | 0.05 | 86.3 | -
Monolithic Construction & Concrete Products, Inc. | 5733 | L | AA | MB | GE1 | Rehabilitation of Odiongan Bridge along Cateel-Compostela Section |  | 2009-06-08 | 1st | XI |  | 52.91 | 240 |  |  |  | O | 0.37 | 0.237 | 0.15 | 0.03 | 0.042 | 0.05 | 87.9 | -
Monolithic Construction & Concrete Products, Inc. | 5733 | L | AA | MB | GE1 | Rehab. of Odiongan Bridge along Cateel-Compostela Sect. |  | 2009-09-11 | 2nd | XI |  | 52.91 | 240 |  |  |  | O | 0.376 | 0.24 | 0.15 | 0.03 | 0.038 | 0.033 | 86.7 | -
Monolithic Construction & Concrete Products, Inc. | 5733 | L | AA | MB | GE | Road Upgrading (Gravel to Concrete) along Surallah - Lake Sebu - Maitum Road, K01759+568 to K01765+260.50 (with Exceptions), South Cotabato; K01763+065 - K01763+085 (shadol I Bridge); K01763+701.40 - K01763+722 (Shadol II Bridge); K01764+138.20 - K01764+145.10 (RCBC) | South Cotabato | 2014-10-22 | 1st & Final | XII | LF | 169.0634 | 540 | 2013-03-27 | 2014-09-17 | 5.33% | C | 0.45 | 0.133 | 0.3 | - | - | - | 88.3% | 88.3% Satisfactory
Monolithic Construction & Concrete Products, Inc. | 5733 | L | AA | MB | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l. Rds. along Nueva Vizcaya-Ifugao-Mt. Province Rd., K0290+600-K0305+000 (IS), K0291+(-390)-K0305+000 (IS) as per RBIA | Ifugao, Mt. Province | 2013-03-17 | Final | CAR | LF | 48.126 | 205 | 2012-05-01 | 2012-11-21 | 0 | C | 0.47 | 0.2 | 0.3 | - | - | - | 97 | 93.76% V. Satisfactory
Monolithic Construction & Concrete Products, Inc. | 5733 |  | AA | LA |  | Quipot Irrigation Project | Tiaoag, Quezon | 2015-02-14 | 1st & Final | NIA | L | 117.463 | 360 | 2013-06-25 | 2014-10-31 | 0 | C | 0.375 | 0.2 | 0.3 | - | - | - | 87.5 | *87.50% Satisfactory
Monolithic Construction & Concrete Products, Inc. | 5733 | L | AA | MB | GE2 | Talibon Small Reservoir Irrigation Project |  | 9/29/08 10/3/08 | 1st | NIA |  | 49.099 | 390 |  |  |  | O | 0.367 | 0.175 | 0.1 | 0.03 | 0.042 | 0.2 | 91.4 | -
Monolithic Construction & Concrete Products, Inc. | 7533 | L | AAA |  |  | Quipot Irrigation Project | Brgy. Quipot, Tiaong, Quezon | 2015-11-21 | 1st | NIA | LF | 121.791 | 365 | 2014-12-10 | 2015-12-10 | -6.97 | O | 0.3583 | 0.2429 | 0.0803 | 0.03 | 0.07 | 0.05 | 83.15 | -
MONOLITHIC CONSTRUCTION & CONCRETE PRODUCTS, INC. / BISLIG VENTURE CONSTRUCTION & DEV'T INC. JOINT VENTURE | JV-14-383 | L | AA | LA | GE | Construction of Flood Control Structure/ Draingae along Surigao-Davao Coastal Road, K1459+516 - K1460+234 | Bislig City, Surigao Del Sur | 2015-06-02 | 1st | SURIGAO DEL SUR SECOND DEO | LF | 18.138 | 128 | 2015-02-25 | 2015-07-02 | (+) 0.91% | O | 0.333 | 0.3 | 0.15 | 0.03 | 0.05 | 0.05 | 91.3% | -
Monolithic Construction & Concrete Products, Inc./Colby Construction (JV) | JV-13-646 | L | AA | MB | GE | Road Upgrading (Gravel to Paved) of banaue-Mayoyao-A. Lista-Isabela Bdry. Road, Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standard (HDM-4 Project Analysis) Intermittent Sections, Section1: K0398+835 - K0399+118.91; Section2: K0401+641 - K0401+713.316; Section3: K0406+491 - K0406+572; Section4: K0406+648 - K0406+674.89; Section5: K0413+698 - K0413+787.74; Section6: K0416+130 - K0417+618.49; Section7: K0419+606 - K0421+048.35 | Aguinaldo, Ifugao | 2014-11-26 | 1st | CAR | LF | 102.9589 | 301 | 2014-06-11 | 2015-04-07 | 4.96% | O | 0.339 | 0.272 | 0.15 | 0.03 | 0.06 | 0.05 | 90.1% | 90.1% Very Satisfactory
Monolithic Construction & Concrete Products, Inc./Colby Construction (JV) | JV-13-560 | L | AA | MB | GE | Road Upgrading (Gravel to Paved) of Ubao-Taang, Based on Gravel Road Stategies, Traffic Benchmark for Upgrading to Paved Road Standard (HDM-4 Project Analysis) (Intermittent Sections), K0401+083-K0401+481, K401+481-K0401-571,K0401+571-K0402+499,K0402+635-K0402+690-K0402+775,K0402+775-K0404+267,K0404+267-K0404+387,K0404+387-K0404+513, K0404+513-K0404+609,K0404+609-K0404+656,K0404+656-K0404+736, K0404+736-K0404+888, & K0404+888-K0404+940 | Ifugao | 2014-11-26 | 1st | CAR | LF | 100.7 | 257 | 2014-06-11 | 2015-02-22 | -6.25% | O | 0.386 | 0.28 | 0.088 | 0.03 | 0.06 | 0.05 | 89.4% | 89.4% Very Satisfactory
MONOLITHIC CONSTRUCTION AND CONCRETE PRODUCTS | 5733 | L | AAA | LA | GE | Construction of Flood Control at Brgy. Lubogan | Toril District, Davao City | 2015-06-02 | Final | Davao City 2nd | LF | 18.766 | 220 | 2014-06-23 | 2015-01-28 | 0% | C | 0.393 | 0.133 | 0.3 | - | - | - | 82.6% | *82.6% Satisfactory
Monolithic Construction and Concrete Products, Inc. / Jagon Builders (JV) | JV-09-283 |  |  |  |  | Widening/Conc. Of Commonwealth Ave. Incl. RROW, Sta.5+400 - Sta.6+000 incl. Footbridge in front of COA Bldg. |  | 2010-09-03 |  | NCR |  | 40.826 | 108 |  |  |  | O | 0.254 | 0.3 | 0.15 | 0.03 | 0.045 | 0.033 | 81.2 | -
MONOLITHIC CONSTRUCTION AND CONCRETE PRODUCTS, INC. /BISLIG VENTURE CONSTRUCTION & DEV"T. INC. / ALBERTO UY CONSTRUCTION & DEVELOPMENT JOINT VENTURE | JV-14-441 | L | AA | LA | GE | Construction/Rehabilitation of Baroc River Protection, Sta. 0+000 to Sta. 1+566.80 San Mariano, Roxas, Mindoro Oriental | San Mariano, Roxas, Mindoro Oriental | 2015-08-29 | 1st | Southern Mindoro DEO | LF | 88.669 | 282 | 2015-06-26 | 2016-04-03 | 0.17% | O | 0.376 | 0.241 | 0.15 | 0.03 | 0.054 | 0.05 | 90.1% | -
Monolithic Construction and Concrete Products, Inc./Jagon Builders (JV) | JV-09-283 | L | AA | LA | GE1 | Widening/Conc. of Commonwealth Ave. inc. RROW Sta.5+400-Sta.6+000 inc. Footbridge infront of COA Building | Quezon City | 2011-04-08 | 2nd | NCR | LF | 40.826 | 153 | 2010-06-17 | 2010-11-16 | - | O | 0.333 | 0.259 | 0 | 0.03 | 0.05 | 0.033 | 70.5 | -
Monolithic Construction and Concrete Products, Inc./King's Builders & Development Corp. (JV) | JV-11-489 | L | AA | MB | GE1 | Rd. Upgrading (Gravel to Concrete) Calapan South Rd. (Km.183+124.50-Km.185+019.76; Km.186+733-Km.189+060; Km.190+439.57-Km.191+478) | Bulalacao, Oriental Mindoro | 2012-11-27 | 1st | IVB | LF | 111.476 | 390 | 2012-05-14 | 2013-06-07 | 0 | O | 0.365 | 0.269 | 0.15 | 0.03 | 0.051 | 0.05 | 91.5 | -
MONOLITHIC CONTRUCTION & CONCRETE PRODUCTS, INC./COLBY CONSTRUCTION (JV) | JV-13-560 | L | AA | MB | GE | Road Upgrading (Gravel to Paved) of Ubao-Taang, Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standard (HDM-4 Project Analysis)(Intermittent Sections) K0401+083 - K0401+481, K0401+481 - K0401+571, K0401+572 - K0402+499, K0402+635 - K0402+690, K0402+690 - K0402+775, K0402+775 - K0404+267, K0404+267 - K0404+387, K0404+387 - K0404+513, K0404+513 - K0404+609, K0404+609 - K0404+656, K0404+656 - K0404+736 - K0404+888 & K0404+888 - K0404+890 | Aguinaldo, Ifugao | 2015-06-08 | Final | CAR | LF | 105.519 | 364 | 2014-06-11 | 2015-06-09 | (+) 0.90% | C | 0.413 | 0.2 | 0.3 | - | - | - | 91.3% | *90.16% Very Satisfactory
MONOLITHIC CONTRUCTION & CONCRETE PRODUCTS, INC./COLBY CONSTRUCTION (JV) | JV-13-646 | L | AA | MB | GE | Road Upgrading (Gravel to Paved) of Banaue-Mayoyao-a. Lista-Isabela Bdry. Road, Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Strandard (HDM-4 Project Analyis) Intermittent Section, Section 1: K0398+835 - K0399+118.91, Section 2: K0401+641 - K0401+713.316, Section 3: K0406+491 - K0406+572, Section 4: k0406+648 - K0406+674.89, Section 5: K0413+698 - K0413+787.74, Section 6: K0416+130 - K0147+618.49, Section 7: K0419+606 - K0421+048.35 | Aguinaldo, Ifugao | 2015-06-08 | Final | CAR | LF | 102.959 | 362 | 2014-06-11 | 2015-06-07 | (+) 0.76% | C | 0.403 | 0.2 | 0.3 | - | - | - | 90.3% | *90.18% Very Satisfactory
MONTANO CONSTRUCTION & DEVELOPMENT CORP | 19473 | L | AA | LA | GE | Road Upgrading (Gravel to Concrete) Mabinay-Ayungon Road (K0095+718 to K0096+320 and K0096+684 to K0096+943), Mabinay, 2nd District, Negros Oriental | Mabinay-Ayungon, Negros Oriental | 2015-06-10 | Final | Negros Oriental Second DEO | LF | 34.949 | 329 | 2015-01-27 | 2015-12-22 | 0% | C | 0.482 | 0.15 | 0.3 | - | - | - | 93.2% | *93.2% Very Satisfactory
Montaño Construction & Development Corp | 9473 |  | AA | MB |  | Dipolog Airport Development Project | Brgy. Minaog, Dipolog City/ Region IX | 2016-01-28 | 3rd | DOTC | LF | 52.516 | 704 | 2014-04-06 | 2016-05-01 | -10.89 | O | 0.3741 | 0.3 | 0.0411 | 0.03 | 0.0382 | 0.0333 | 81.67 | -
Montaño Construction & Development Corp. | 2010-1185 | L |  |  |  | Dapitan Resettlement Project | Brgy. Sulangon, Dapitan City | 2013-11-12 | Final | NHA | LF | 22.695 | 215 | 2013-06-07 | 2013-09-02 | -16.55 | C | 0.494 | 0.2 | 0.3 |  |  |  | 99.4
Montaño Construction & Development Corp. | 2010-1185 | L | AA |  |  | Dapitan Resettlement Project | Brgy. Sulangon, Dapitan City | 2013-11-12 | Final | NHA | LF | 22.695 | 215 | 2013-06-07 | 2013-09-02 | 0 | C | 0.494 | 0.2 | 0.3 | - | - | - | - | 99.40% Outstanding
Montaño Construction & Development Corp. | 19473 |  |  |  |  | Const. of De Venta Perla Bridge & Approaches (Phase II) |  | 2010-06-12 |  | IX |  | 27.869 | 293 |  |  |  | O | 0.353 | 0.24 | 0 | 0.03 | 0.035 | 0.05 | 70.8 | -
Montaño Construction & Development Corp. | 2010-1185 | L | AA |  | GE1 | Dapitan City Resettlement Project | Brgy. Sulangon, Dapitan | 2013-01-23 | 1st | NHA | LF | 22.695 | 215 | 2012-06-07 | 2013-01-07 | 0.65 | O | 0.3983 | 0.3 | 0.15 | 0.03 | 0.056 | 0.05 | 98.43 | -
Montaño Construction & Development Corp. | 19473 | L | AA | SB | GE1 | Maasin Airport Development Project | Brgy. Panan-awan, Maasin, Leyte | 2013-03-21 | 1st | DOTC | LF | 29.295 | 150 | 2013-01-15 | 2013-06-14 | 3.03 | O | 0.4 | 0.3 | 0.15 | 0.03 | 0.056 | 0.025 | 96.1 | -
Montaño Construction & Development Corporation | 19473 | L | AA | MB |  | Maasin Airport Development Project | Brgy. Panan-awan, Maasin, Southern Leyte | 2014-06-24 | 1st | DOTC | LF | 57.589 | 360 | 2014-03-14 | 2015-03-08 | 1.19 | O | 0.3399 | 0.3 | 0.15 | 0.01 | 0.0445 | 0.05 | 89.44 | -
Montaño Construction & Development Corporation | 19473 | L | AA | LA | GE | Construction of Polanco PSCG Bridge and Approaches (PHASE I) Along Dipolog-Polanco-Piñan-Jct. Oroquieta Road | Polanco, Zamboanga del Norte | 2014-10-28 | 1st & Final | IX | LF | 14.95 | 245 | 2013-12-03 | 2014-08-04 | 0% | C | 0.443 | 0.143 | 0.3 | - | - | - | 88.6% | 88.6% Satisfactory
Montaño Construction & Development Corporation | 19473 | L | AA | MB | GE1 | Replacement of Licabang (Dipolog) Bridge Phase I, Jct. Mahayag-Dumingag-Siyam Rd. | Dumingag, Zamboanga del Sur | 2013-03-21 | Final | IX | LF | 28.082 | 240 | 2012-03-08 | 2012-11-03 | 0 | C | 0.465 | 0.133 | 0.3 | - | - | - | 89.8 | 87.28% Satisfactory
Montaño Construction & Development Corporation | 19473 | L | AA | MB | GE | Restoration of Sanito Bridge Sta. 1800+731 to Sta. 1800+764.40 | Ipil, Zamboanga Sibugay | 2014-08-08 | Final | IX | LF | 32.8989 | 554 | 2014-03-19 | 2015-09-23 | 0 | C | 0.457 | 0.2 | 0.3 |  |  |  | 95.7 | 88.38% Satisfactory
Montaño Construction & Development Corporation | 19473 | L | AA | MB | GE1 | Restoration of Sanito Bridge Sta.1800+731.60Sta.1800+764.40 | Ipil, Zamboanga Sibugay | 2013-08-09 | 3rd | IX | LF | 32.178 | 554 | 2012-03-19 | 2013-09-23 | 1.5 | O | 0.262 | 0.3 | 0.15 | 0.03 | 0.033 | 0.05 | 82.5
Montaño Construction & Development Corporation | 19473 | L | AA | MB | GE1 | Restoration of Sanito Bridge Sta.1800+731.60-Sta.1800+764.40 | Ipil, Zamboanga Sibugay | 2013-03-14 | 2nd | IX | LF | 32.178 | 404 | 2012-03-19 | 2013-04-26 | -3 | O | 0.364 | 0.24 | 0.12 | 0.03 | 0.047 | 0.033 | 83.4 | -
Montaño Construction & Development Corporation | 19473 | L | AA | MB | GE1 | Restoration of Sanito Bridge, Sta.1800+713.60-Sta.1800+764.40 | Ipil, Zaqmboanga Sibugay | 2012-11-26 | 1st | IX | LF | 31.039 | 374 | 2012-03-19 | 2013-03-27 | -3 | O | 0.379 | 0.225 | 0.12 | 0.03 | 0.059 | 0.033 | 84.6 | -
Montaño Construction & Development Corporation | 19473 | L | AA | MB | GE1 | Const. of Salug-Daku Bridge & Approaches along Sindangan-Siayan-Dumingag-Mahayag Rd. | Mahayag, Zamboanga del Sur | 2013-08-17 | 4th | IX | LF | 27.645 | 270 | 2012-07-19 | 2013-04-15 | - | O | 0.306 | 0.3 | 0 | 0.022 | 0.042 | 0.033 | 70.3
Montaño Construction & Development Corporation | 19473 | L | AA | MB | GE1 | Const. of Salug-Daku Bridge &Approaches along Sindangan-Siayan-Dumingag-Mahayag Rd. | Mahayag, Zamboanga del Sur | 2013-03-21 | 3rd | IX | LF | 27.645 | 270 | 2012-07-19 | 2013-04-15 | 0.3 | O | 0.361 | 0.24 | 0.15 | 0.03 | 0.033 | 0.033 | 84.7 | -
Montaño Construction & Development Corporation | 19473 | L | AA | MB | GE1 | Const. of Salug-Daku Bridge & Approaches along Sindangan-Siayan-Dumingag-Mahayag Rd. | Mahayag, Zamboanga del Sur | 2012-11-23 | 2nd | IX | LF | 27.645 | 210 | 2012-07-19 | 2013-02-14 | 0.21 | O | 0.367 | 0.225 | 0.15 | 0.03 | 0.045 | 0.05 | 86.7 | -
Montaño Construction & Development Corporation | 19473 | L | AA | MB | GE1 | Const. of Salug-Daku Bridge & Approaches along Sindangan-Siayan-Dumingag-Mahayag Rd. | Mahayag, Zamboanga del Sur | 2012-08-18 | 1st | IX | LF | 27.645 | 210 | 2012-07-19 | 2013-02-14 | 9.62 | O | 0.365 | 0.218 | 0.15 | 0.03 | 0.038 | 0.033 | 83.4 | -
MONTAÑO CONSTRUCTION & DEVELOPMENT CORPORATION | 19473 | L | AA | MA | GE | Construction/Rehabilitation of Dipolo Gamay Floo Control, Dipolo Gamay Bridge, Molave, Zamboanga del Sur | Molave, Zamboanga del Sur | 2015-06-06 | Final | Zamboanga del Sur 1st DEO | LF | 15.648 | 173 | 2014-03-31 | 2014-09-19 | 0% | C | 0.472 | 0.133 | 0.3 | - | - | - | 90.5% | *90.5% Very Satisfactory
MONTAÑO CONSTRUCTION & DEVELOPMENT CORPORATION | 19473 | L | AA | LA | GE | Rehab./Reconst./Upgrading of Bais-Kabankalan Road, Section 1 : K0065+211 - K0066+209; Section 2: K066+500 - K0067+021; Section 3: K0078+000 - K0078+138; Section 5: K0097+977 - K0098+000; Section 6: K0100+587 - K0100+666 | 2nd District, Negros Oriental | 2015-08-24 | 1st | Negros Oriental 2nd | LF | 37.589 | 239 | 2015-02-12 | 2015-10-08 | 15.38% | O | 0.356 | 0.297 | 0.15 | 0.03 | 0.05 | 0.05 | 93.3% | -
MONTAÑO CONSTRUCTION & DEVELOPMENT CORPORATION | 19473 | L | AAA | LA | GE | Upgrading (Gravel to Paved) of Road, Piñan-Mutia Road, KO 1818+275.00 - KO 1825+790.95 (Intermittent Section) with Exception, Zamboanga del Norte | Zamboanga del Norte | 2015-11-14 | Final | Regional Office | LF | 107.9033 | 570 | 2014-04-02 | 2015-10-23 | (+) 19.77 | C | 0.418 | 0.197 | 0.3 | - | - | - | 91.5% | 91.5% Very Satisfactory
Montano Construction & Development Corporation | 19473 | L | AA | MB | GE1 | Maasin Airport Development Project | Brgy. Panan-awan, Maasin, Leyte | 2013-09-26 | Final | DOTC | L | 29.295 | 150 | 2013-01-15 | 2013-06-14 | 0 | C | 0.4947 | 0.2 | 0.3 | - | - | - | 99.47 | 97.44% Outstanding
Montano Construction & Development Corporation | 19473 | L | AA | MB | GE1 | Maasin Airport Development Project | Brgy. Panan-awan, Maasin, Leyte | 2013-10-30 | 1st | DOTC | L | 12.926 | 120 | 2013-05-29 | 2013-09-25 | 23.33 | O | 0.3776 | 0.3 | 0.15 | 0.02 | 0.042 | 0.05 | 93.96 | -
Montaño Construction & Development Corporation / Westmin Enterprises and Construction Services (JV) | JV-12-346 | L | AA | MB | GE1 | Rd. Upgrading (Gravel to Conc.), Int. Sect., along Dipolog-Punta-Dansullan-Sergio Osmeña, ZDN/SIJR. From K1880+4915-K1880+5146; K1880+537 -K1885+120; K1888+096-K1889+000 to K1888+(-133)-K1889+373 | Zamboanga del Norte | 2013-08-20 | 2nd | IX | LF | 30.393 | 158 | 2013-02-18 | 2013-07-25 | - | O | 0.314 | 0.296 | 0 | 0.03 | 0.042 | 0.033 | 71.5
Montaño Construction & Development Corporation / Westmin Enterprises and Construction Services (JV) | JV-12-346 | L | AA | MB | GE1 | Rd. Upgrading (Gravel to Conc.) Int. Sect., along Dipolog-Punta-Dansullan-Sergio Osmeña, ZDN/SIJR. from K1880+4915-K1880+5146; K1880+5371-K1885+120; K1888+096-K1889+000 to K1888+(-133)-K1889+373 | Zamboanga del Norte | 2013-03-22 | 1st | IX | LF | 30.393 | 129 | 2013-02-18 | 2013-06-26 | 33 | O | 0.361 | 0.237 | 0.15 | 0.03 | 0.037 | 0.033 | 84.8 | -
Montaño Construction & Development Corporation /Rudhil Construction Enterprises, Inc. (JV) | JV-13-746 | L | AA | MB | GE | Widening of Taway Bridge along Ipil-Liloy-Sindangan Road Section Bridge Station: Km. 2012+391.08 - Km. 2012+417.13 | Zamboanga Sibugay | 2014-10-23 | 1st | IX | LF | 26.4538 | 315 | 2014-06-04 | 2015-04-14 | -2.07% | O | 0.355 | 0.24 | 0.129 | 0.03 | 0.04 | 0.033 | 82.7% | 82.7% Satisfactory
MONTAÑO CONSTRUCTION & DEVELOPMENT CORPORATION/WESTMIN ENTERPRISES AND CONSTRUCTION SERVICES (Joint Venture) | JV-14-446 | L | AA | LA | GE | Road Upgrading (Gravel to Concrete) Based on gravel Road Strategies/Traffic Benchmark for Upgrading to Paved Road Standard, HDM-4 (Project Analysis)(Intermittent Section) Ilaya - Isi - Polanco Road, K1814+(-892) to K1814+(-683) & K1814+(-206) to K1814+046, Zamboanga del Norte | Zamboanga del Norte | 2015-06-05 | Final | Zamboanga del Norte 3rd DEO | LF | 69.167 | 285 | 2014-04-03 | 2015-01-13 | 0% | C | 0.444 | 0.133 | 0.3 | - | - | - | 87.7% | *87.7% Satisfactory
Montaño Construction & Development Corporation/Westmin Enterprises and Construction Services (JV) | JV-12-346 | L | AA | MB | GE | Road Upgrading (Gravel to Paved) Based on Gravel/Strategies, Traffice Benchmark for Uograding to Paved Road Standard(HDM-4 Project Analysis) Intermittnet sections along Dipolog-Punta Dansullan-Sergio Osmeña, ZDN/Sur Boundary From K1880+4195 - K1880+5146; K1880+5371 - K1885+120; K1888+096 - K1889+000 - K1889+373 | Zamboanga Del Norte | 8/1/4/14 | Final | IX | LF | 30.3928 | 188 | 2013-02-18 | 2014-08-25 | 1.9 | C | 0.45 | 0.15 | 0.3 |  |  |  | 90 | 82.89% Satisfactory
Montaño Construction & Development Corporation/Westmin Enterprises and Construction Services (JV) | JV-13-272 | L | AA | MB | GE | Road Upgrading (Gravel to Paved) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standard (HDM-4 Project Analysis) (Intermittent sections) Ilaya-Isis-Polanco Road K1814+(-892) to K1814+(-683) - K181+(206) to K1814+046 | Zamboanga Del Norte | 2014-08-14 | 1st | IX | LF | 66.4864 | 176 | 2014-04-03 | 2014-09-26 | 1.72 | O | 0.33 | 0.3 | 0.15 | 0.03 | 0.04 | 0.05 | 90
Montano Construction and Development Corporation | 19473 | L | AA | MB |  | Maasin Airport Development Project | Maasin, Southern Leyte | 2014-03-12 | Final | DOTC | LF | 12.926 | 120 | 2013-05-29 | 2014-01-26 | 0 | C | 0.4364 | 0.2 | 0.3 | - | - | - | 93.64 | 93.84% Very Satisfactory
Montano Construction and Development Corporation | 19473 | L | AA | MB |  | Dipolog Airport Development Project | Dipolog City, Zamboanga del Norte | 2015-08-27 | 2nd | DOTC | LF | 52.516 | 588 | 2013-05-02 | 2016-01-06 | 0.85 | O | 0.399 | 0.3 | 0.15 | 0.02 | 0.05 | 0.05 | 96.9 | -
Montano Construction and Development Corporation | 19473 | L | AA | MB |  | Maasin Airport Development Project | Maasin, Southern Leyte | 2015-04-14 | 2nd | DOTC | LF | 57.589 | 426 | 2014-03-14 | 2015-05-14 | -26.53 | O | 0.4 | 0.3 | 0 | 0.03 | 0.061 | 0.05 | 84.1 | -
Montano Construction and Development Corporation | 19473 | L | AA | MB | GE-1 | Dipolog Airport Development Project | Dipolog City, Zamboanga del Norte/Region IX | 2015-06-11 | 1st | DOTC | LF | 52.516 | 420 | 2013-05-01 | 2016-01-05 | 9.5 | O | 0.3864 | 0.3 | 0.15 | 0.02 | 0.0323 | 0.05 | 93.87 | -
Montano Construction and Development Corporation | 19473 | L | AA | MB |  | Dipolog Airport Development Project | Dipolog City, Zamboanga del Norte/ Region IX | 2016-04-07 | 4th | DOTC | LF | 52.516 | 712 | 2013-03-02 | 2016-05-09 | 3.94 | O | 0.354 | 0.3 | 0.15 | 0.02 | 0.047 | 0.05 | 92.1 | -
Monte Construction & Supply | 19474 |  |  |  |  | Conc. of Bambang-Kasibu-Quezon-Solano Rd., Bumolos Camp Sect. |  | 2010-06-07 |  | II |  | 9.645 | 180 |  |  |  | O | 0.371 | 0.24 | 0.15 | 0.03 | 0.042 | 0.033 | 86.6 | -
MONTESCLAROS ENTERPRISES, INC. (Formerly M. Montesclaros Enterprises) | 6506 | L | AAA | LA | GE | Rehab/Reconst/Upgrading of Damaged Paved National Roads Including Drainage Based On Pavement Management System/Highway Development & Management-4 (HDM-4) (Intermittent Sections), Sayre Highway (Bukidnon-Davao Jct. to Cotabato Boundary), K1584+236 - K1585+713, K1541+266 - K1594+000, K1616+053 - K1616+315, Bukidnon | Bukidnon | 2015-11-11 | 2nd | Regional Office | LF | 135.197 | 268 | 2015-03-25 | 2015-12-18 | (+) 12.88% | OG | 0.371 | 0.235 | 0.15 | 0.03 | 0.06 | 0.05 | 89.6% | 89.6% Very Satisfactory
Montphil Construction Corporation | 24285 |  |  |  |  | Completion of MPB (Gym) |  | 2010-06-12 |  | IX |  | 1.905 | 110 |  |  |  | O | 0.397 | 0.24 | 0.15 | 0.03 | 0.029 | 0.05 | 89.6 | -
Morning Steel Construction | 30698 |  |  |  |  | Const./Repair/Rehab. of Quezon St. (12M Right-of-Way extension w/ Drainage Impvt.) |  | 2010-06-05 |  | III |  | 9.402 | 150 |  |  |  | O | 0.365 | 0.239 | 0.15 | 0.03 | 0.054 | 0.033 | 87.1 | -
Morning Steel Construction | 30698 | L | C | SB | GE1 | Rehab./Improvement of Debucao-Diome FTMR |  | 2009-09-08 | 1st | III |  | 4.717 | 150 |  |  |  | O | 0.359 | 0.228 | 0.15 | 0.03 | 0.05 | 0.033 | 85 | -
Morning Steel Construction | 30698 | L | C | SB | GE2 | Maint./Repair & Rehab. of Infra Facility/Flood Control & Drainage System, Suklayin Flood Control | Suklayin, Baler, Aurora | 2012-11-27 | 1st | III | LF | 2.768 | 124 | 2012-08-13 | 2012-12-14 | 4.08 | O | 0.327 | 0.24 | 0.15 | 0.03 | 0.047 | 0.05 | 84.4 | -
Morning Steel Construction | 30698 | L | C | SB | GE1 | Maint./Repair & Rehab. of Infra Facility/Flood Control & Drainage System, Buhangin Flood Control, Brgy. Buhangin | Baler, Aurora | 2012-11-27 | 1st | III | LF | 2.772 | 123 | 2012-08-13 | 2012-12-13 | 7.29 | O | 0.31 | 0.24 | 0.15 | 0.03 | 0.047 | 0.05 | 82.7 | -
Mountaineers Engineering & Const. Services | 6154 | L | B | MA | GE1 | Restoration of Roadslip/Rd. Cut along Tublay (K0264+200-K0268+900) | Tublay, Benguet | 2012-11-21 | 1st | CAR | LF | 2.909 | 155 | 2012-09-03 | 2013-02-04 | 10.32 | O | 0.307 | 0.3 | 0.15 | 0.02 | 0.033 | 0.033 | 84.3 | -
Mountaineers Engineering & Construction Services | 6154 | L | C | SB | GB1 | Const. of 2-Storey, 4-CL Benguet NHS-Beckel Annex |  | 2009-05-20 | 1st | CAR |  | 4.429 | 277 |  |  |  | O | 0.371 | 0.229 | 0.15 | 0.03 | 0.035 | 0.05 | 86.5 | -
Mountaineers Engineering & Construction Services | 6154 | L | B | MA | GE1 | Restoration of Roadslip/Rd. Cut along Tublay, Benguet (K0264+200-K0268+900) | Tublay, Benguet | 2013-03-14 | Final | CAR | LF | 2.909 | 155 | 2012-09-03 | 2013-02-05 | 0 | C | 0.426 | 0.133 | 0.3 | - | - | - | 85.9 | 84.94% Satisfactory
MPJR BUILDERS CO. | 20446 | L | B | SB | GE | Const/Repair/Rehab/Improvement of Various Infrastructure Including Local Projects - Road and Drainage Improvement New Panaderos Street and Vicinity to Pasig River via Brgy. 892, Sta. Ana, Manila | Sta. Ana, Manila | 2015-09-02 | 1st | SM DEO | LF | 6.243 | 150 | 2015-05-01 | 2015-09-27 | 1.6% | O | 0.373 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 89.8% | -
MQR Construction and Supplies | 33664 | L | C | SB | GE | Major Repair/Maintenance of Existing Permanent Bridge, Cabangan Bridge along Daang Maharlika | Oas, Albay | 2014-08-11 | 1st & Final | V | LF | 0.85098 | 60 | 2014-02-24 | 2014-04-24 | 0 | C | 0.325 | 0.2 | 0.3 |  |  |  | 82.5 | 82.50% Satisfactory
MRB Construction and Supply | 17701 | L | AA |  | GE5 | Const. of Rehabilitation of Rock Causeway at Port of Dingalan, Aurora Province (Ports & Harbor) | Port of Dingalan, Aurora Province | 02/21-25/11 | 1st | PPA | LF | 16.279 | 180 | 2010-10-14 | 2011-04-11 | -14 | O | 0.3644 | 0.2988 | 0.01 | 0.03 | 0.0653 | 0.033 | 80.15 | -
MRB Construction and Supply | 17701 | L |  | MB | GE1 | Repair of Damaged Facilities (Conc. Pavement, Fence, Drainage and Lighting System) | Pier 18, Vitas, north Harbor, Manila | 03/1-4/11 | 1st | PPA | LF | 12.883 | 136 | 2010-11-30 | 2011-04-07 | 40.21 | O | 0.39654 | 0.3 | 0.15 | 0.03 | 0.07 | 0.05 | 99.654 | -
MRB Construction Corp. | 17701 | L | AA |  | GE5 | Construction of RoRo Ramp at El Codo Canal, Pasig River | South Harbor, Intramuros, Port Area Manila | 2013-12-12 | 1st | PPA | LF | 19.666 | 180 | 2013-09-23 | 2014-03-21 | -14.37 | O | 0.4 | 0.3 | 0.0063 | 0.03 | 0.0653 | 0.0333 | 83.49 | -
MRB Construction Corporation | 17701 | L | AA |  | GE5 | Construction of Back-Up Area and Ext. of Pier | Basco, Port Batanes | 2014-05-23 | 1st | PPA | LF | 98.109 | 360 | 2013-12-19 | 2014-12-04 | 0.585 | O | 0.356 | 0.3 | 0.15 | 0.024 | 0.051 | 0.05 | 93.1 | -
MRB11 Construction Corporation | 17701 | L | AA |  |  | Construction of Back-Up Area and Extension of Pier | Basco Port, Batanes | 2015-05-22 | 2nd & Final | PPA | L | 98.109 | 409 | 2013-12-19 | 2015-01-22 | -1.042 | C | 0.473 | 0.2 | 0.269 | - | - | - | 94.2 | 93.50% V. Satisfactory
MRB11 Construction Corporation (Formerly: MRB Construction and Supply) | 17701 | L | AA | MA | GE | Asphalt Overlay with Concrete Blocking of Kamuning Road, Quezon City, K0011+(-245) - K0011+328 | Quezon City | 2014-08-15 | 1st & Final | NCR | LF | 11.9764 | 165 | 2014-01-30 | 2014-07-13 | 0 | C | 0.493 | 0.133 | 0.3 |  |  |  | 92.6 | 92.60% Very Satisfactory
MRB11 CONSTRUCTION CORPORATION (Formerly: MRB Construction and Supply) | 17701 | L | AA | MA | GE | Phase 1- Concreting/Widening and Drainage Improvement/Rehabilitation of Scout Castor St. Quezon City | Quezon City | 2015-06-03 | 1st | Quezon City 2nd DEO | LF | 11.831 | 202 | 2015-02-24 | 2015-09-13 | (+) 11.17 | O | 0.376 | 0.24 | 0.15 | 0.007 | 0.03 | 0.05 | 85.3% | -
MRBII CONSTRUCTION CORPORATION (Formerly: MRB Construction and Supply) | 17701 | L | AA | MA | GE | Netwok Development: Off-Carriage Improvement of (Paving of Shoulder) K0010+000 - K0010+260; K00150 - K0018+000, Batan Island, Batanes | Batan Island, Batanes | 2015-11-21 | 1st | BATANES DEO | LF | 47.8085 | 314 | 2015-03-03 | 2016-01-10 | (+) 17.10 | OG | 0.366 | 0.239 | 0.15 | 0.03 | 0.045 | 0.05 | 88% | 88% Satisfactory
MRRM Trading & Construction | 19657 | L | B | MA | GE | Construction/Rehabilitation/Raising of Grade of Alabang-Muntinlupa Road, S03264LZ, K0030+535-K0031+024 | Munitinlupa City, Metro Manila | 2014-11-17 | 1st | NCR | LF | 15.9325 | 174 | 2014-06-06 | 2014-11-26 | -10% | O | 0.348 | 0.3 | 0.05 | 0.03 | 0.039 | 0 | 76.7% | 76.7% Unsatisfactory
MRRM Trading & Construction | 19657 | L | B | MA | GB | Construciton of Two-Storey, Four-Classroom School Building with Comfort Room, Dr. Rodolfo V. Pamor MHS (Sagnay Western Annex High School) | Sagnay, Camarines Sur | 2014-08-09 | Final | V | LF | 4.4355 | 150 | 2013-06-13 | 2013-11-09 | 0 | C | 0.388 | 0.2 | 0.3 |  |  |  | 88.8 | 86.49% Satisfactory
MRRM Trading & Construction | 19657 | L | B | MA | GB1 | Const. of 2-Storey 4- Cl. Sch. Bldg. w/ CR, Dr. Rodolfo V. Pamor MHS (Sagnay Western Annex HS) | Sagnay, Camarines Sur | 2013-08-02 | 1st | V | LF | 4.435 | 120 | 2013-06-13 | 2013-10-10 | 2.33 | O | 0.334 | 0.256 | 0.15 | 0.03 | 0.052 | 0.033 | 85.5
MRRM TRADING & CONSTRUCTION | 19657 | L | B | MA | GE | Construction of Box Culvert and Slope Protection in the upstream portion of Bayanan Creek, Putatan, Muntinlupa City, Metro Manila | Muntinlupa City | 2015-06-10 | Final | Las Pinas-Muntinlupa | LF | 10.554 | 120 | 2015-03-02 | 2015-06-29 | (+) 15.87 | C | 0.426 | 0.133 | 0.3 | - | - | - | 85.9% | *85.9% Satisfactory
MRRM Trading and Construction |  | L |  |  | GB1 | Const. of 3-Storey 15 School Building | La Solidaridad Estate Homes 1 Timbao, Biñan, Laguna/Region IV-A | 2012-08-23 | 1st | NHA | LF | 22.103 | 180 | 2012-06-11 | 2012-12-07 | 4.05 | O | 0.3486 | 0.284 | 0.15 | 0.02 | 0.045 | 0.05 | 89.76 | -
MRRM Trading and Construction |  | L |  |  | GB1 | Const. of 3-Storey 15 School Building | La Solidaridad Estate Homes 1 Timbao, Biñan, Laguna/Region IV-A | 2012-10-10 | 2nd | NHA | LF | 22.103 | 180 | 2012-06-11 | 2012-12-07 | -0.46 | O | 0.2999 | 0.231 | 0.1454 | 0.03 | 0.042 | 0.03 | 77.83 | -
MSB Vitug Construction | 33019 | L |  |  |  | Rehabilitation and Development of Estero De San Miguel | Estero De San Miguel, City of Manila | 2014-07-08 | 3rd | PRRC | LF | 52.373 | 270 | 2011-10-31 | 2011-11-02 | 0 | O | 0.3563 | 0.2433 | 0.15 | 0.01 | 0.031 | 0.05 | 84.06 | -
MSB Vitug Construction | 33019 | L |  |  |  | Rehabilitation and Development of Estero de Concordia | Estero de Concordia, City Manila | 2014-03-25 | 1st | PRRC | LF | 9.733 | 180 | 2013-01-17 | 2013-06-16 | -9.91 | O | 0.363 | 0.3 | 0.051 | 0.024 | 0.035 | 0.05 | 82.3 | -
MSB Vitug Construction | 33019 | L |  |  |  | Rehabilitation and Development of Estero de Concordia | Estero de Concordia, Manila | 2014-05-06 | 2nd & Final | PRRC | LF | 9.733 | 180 | 2013-01-17 | 2013-06-16 | -10.4 | C | 0.431 | 0.2 | 0.196 | - | - | - | - | 82.46% Satisfactory
MSB Vitug Construction | 33019 | L |  |  |  | Rehabilitation and Development of Estero De Aviles | Estero De Aviles, City of Manila | 2014-03-28 | Final | PRRC | LF | 6.838 | 150 | 2012-08-09 |  | -12.33 | C | 0.426 | 0.2 | 0.177 | - | - | - | - | 74.96% Poor
MSB Vitug Construction | 33019 |  |  |  |  | Rehabilitation and Development of Estero De San Miguel | Estero De San Miguel, City of Manila | 2016-05-18 | Final | PRRC | LF | 40.922 | 969 | 2011-11-02 |  | 1.76 | C | 0.304 | 0.2 | 0.284 | - | - | - | 78.8 | 82.02% Satisfactory
MSDLR Construction |  | L |  |  | GB1 | Construction of Passenger Terminal Building | Port of Ozamis, Ozamis City, Region X | 2013-12-09 | Final | PPA | LF | 24.84 | 300 | 2012-11-19 | 2013-09-14 | 0 | C | 0.486 | 0.2 | 0.3 | - | - | - | 98.6 | 96.98% Outstanding
MSDLR Construction | 32266 | L |  | MA | GE5 | Construction of Passenger Terminal Building | Port of Ozamis, Ozamis, Ozamis City/Region - X | 2013-06-07 | 1st | PPA | L | 24.84 | 300 | 2012-11-07 | 2013-09-14 | 5.41 | C | 0.379 | 0.3 | 0.15 | 0.03 | 0.06 | 0.05 | 96.9 | -
MSF CONSTRUCTION | 25307 | L | C | SB | GE | Widening of National Road, MNR , K0483+493-K0484+000, San Nicolas, Ilocos Norte | K0483+493-K0484+000, San Nicolas, Ilocos Norte | 2015-08-26 | 1st | Ilocos Norte 2nd DEO | LF | 6.743 | 143 | 2015-04-29 | 2015-09-18 | (+)14.27 | O | 0.369 | 0.224 | 0.15 | 0.03 | 0.047 | 0.05 | 87% | -
MSF CONSTRUCTION | 25307 | L | C | SB | GE | Widening of National Roads, Manila North Road K0483+493 - K0484+000, San Nicolas, Ilocos Norte | San Nicolas, Ilocos Norte | 2015-11-13 | Final | ILOCOS NORTE 2ND DEO | LF | 7.0791 | 171 | 2015-04-29 | 2015-10-16 | - | C | 0.402 | 0.2 | 0.3 | - | - | - | 90.2% | 87.98% Satisfactory
MUANA CONSTRUCTION AND DEVELOPMENT CORP. | 9354 | L | B | MA | GB | Construction of Health Facilities and Mutli-Purpose Building and Rehabilitation of Public Market, Valencia, Bohol, Dimlao, Bohol | Valencia, Bohol, Dimlao, Bohol | 2015-11-15 | 1st | Bohol 3rd | LF | 3.8406 | 190 | 2015-05-11 | 2015-12-16 | 0.0137 | OG | 0.296 | 0.24 | 0.15 | 0.03 | 0.032 | 0.05 | 79.8% | 79.8% Unsatisfactory
MUAÑA CONSTRUCTION AND DEVELOPMENT CORP. (Formerly: Muaña Construction) | 9354 | L | B | SB | GE | Repair and Maintenance of River Control (Cluster I) a) Repair and Maintenance of Tangohay River Control | Dimiao, Bohol | 2015-08-27 | 1st & Final | Bohol 3rd | LF | 0.969 | 100 | ###### | 2015-03-27 | 5% | C | 0.375 | 0.2 | 0.3 | - | - | - | 87.5% | *87.5% Satisfactory
Mulana Construction | 30708 | L | D | SB | GB1 | Construction of School Building Cawag P/S |  | 2009-09-10 | 1st | VII |  | 0.58 | 165 |  |  |  | O | 0.4 | 0.155 | 0.15 | 0.03 | 0.037 | 0.033 | 80.5 | -
Multi-System Construction & Development Corp. |  | L |  |  |  | Repair of Conc. Pavement/Paving Blocks & Gaps of Conc. Piles & Blocks | Port of Capinpin, Orion Bataan | 2015-06-26 | 1st & Final | PPA | LF | 18.923 | 172 | 2015-12-19 | 2015-06-08 | 0.23 | C | 0.4529 | 0.1057 | 0.3 | - | - | - | 85.86 | *85.86% Satisfactory
Multi-System Construction & Development Corporation | 26920 | L |  | MA | GE5 | Various Repair at Port of Casiguran, Aurora Province | Port of Casiguran, Aurora Province | 2015-04-10 | 1st | PPA | L | 23.392 | 130 | 2014-12-19 | 2015-04-26 | 1.234 | O | 0.3996 | 0.3 | 0.15 | 0.03 | 0.063 | 0.05 | 99.26 | -
Multi-System Construction and Development Corporation | 26920 | L | A |  | GE1 | Repair of Sidewalk/Curb and Gutter at 25th St., A.C. Delgado | South Harbor, Port Area, Manila | 2013-12-12 | 1st | PPA | LF | 11.076 | 106 | 2013-08-29 | 2013-12-12 | -3.35 | O | 0.388 | 0.3 | 0.118 | 0.03 | 0.07 | 0.05 | 95.6 | -
Multi-System Construction and Development Corporation | 26920 | L |  | MB |  | Widening of Wharf Project | TMO-Pasig, Pasig River, South Harbor, Manila | 2016-12-14 | 1st | PPA | LF | 48.62 | 300 | 2016-03-24 | 2017-01-17 | -1.236 | O | 0.351 | 0.3 | 0.138 | 0.03 | 0.07 | 0.05 | 93.9 | -
Multi-System Construction and Devt. Corp | 26920 | L |  |  |  | Repair of Sidewalk/Curb and Gutter at 25th St., A.C. Delgado | South Harbor, Port Area, Manila | 2014-04-25 | 2nd & Final | PPA | LF | 11.076 | 121 | 2013-08-29 | 2013-12-27 | -3.31 | C | 0.4848 | 0.2 | 0.2669 | - | - | - | 95.17 | 95.43% V. Satisfactory
Must Enterprises | 13336 | L | B | MA | GE | Road Upgrading (Gravel to Concrete) along Kapinpilan - Lumpog Road, Sambolawan, Midsayap, Cotabato Km.1706+430 - Km. 1707+420 (104 Embankment), Km.1706+430 - Km. 1707+415 (311 PCCP) | Cotabato | 2014-08-11 | 1st & Final | XII | LF | 24.8009 | 139 | 2014-02-28 | 2014-07-17 | 0 | C | 0.442 | 0.189 | 0.3 |  |  |  | 93.1 | 93.10% Very Satisfactory
Must Enterprises | 13336 | L | B | MA | GE1 | Road Upgrading (Gravel to Concrete) Nat'l Secondary Rd., Km.1684+(-257) - Km.1684+779 along Paco-Roxas-Arakan Valley | Arakan, Cotabato | 2011-08-18 | 1st | XII | LF | 19.704 | 200 | 2011-06-15 | 2011-12-31 | -11.11 | O | 0.38 | 0.3 | 0.039 | 0.03 | 0.05 | 0.033 | 83.2 | -
Must Enterprises | 13336 |  |  |  |  | Const. of MPB at Don E. Sero E/S |  | 2010-06-01 |  | XII |  | 1.92 | 79 |  |  |  | O | 0.329 | 0.24 | 0.15 | 0.03 | 0.035 | 0.033 | 81.7 | -
Must Enterprises | 13336 | L | A | MA | GE1 | Const./Conc. of Cotabato Airport at Awang |  | 2009-05-26 | 1st | R-XII |  | 19.058 | 138 |  |  |  | O | 0.342 | 0.3 | 0.15 | 0.03 | 0.055 | 0.033 | 91 | -
MUST ENTERPRISES | 13336 | L | B | MA | GE | Road Concreting, Katalicanan-Bitoka | Aleosan, Cotabato | 2015-06-06 | Final | Cotabato 2nd DEO | LF | 1.878 | 36 | 2015-02-24 | 2015-04-01 | 0% | C | 0.443 | 0.133 | 0.3 | - | - | - | 87.6% | *87.6% Satisfactory
Must Enterprises / Rden Construction & Supply (JV) | JV-12-235 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Concrete) along Kapinpilan-Lumupog Rd., Km.1704+(-294)-Km.1706+430.20 Kapinpilan Sect. | Midsayap, Cotabato | 2013-08-12 | 1st | XII | LF | 43.234 | 203 | 2013-03-06 | 2013-09-24 | 3.53 | O | 0.338 | 0.3 | 0.15 | 0.03 | 0.058 | 0.033 | 90.9
Must Enterprises / Rden Construction & Supply (JV) | JV-12-235 | L | B | MA | GE | Road Upgrading (Gravel to Concrete) along Kapinpilan - Lumpog Road, Midsayap, Cotabato Km.1704+(-294) - Km. 1706+270.20 | Midsayap, Cotabato | 2014-08-11 | Final | XII | LF | 43.2338 | 203 | 2013-03-06 | 2013-09-24 | 0.49 | C | 0.424 | 0.2 | 0.3 |  |  |  | 92.4 | 91.50% Very Satisfactory
MWJ Construction | - | L | - | - | GE | Road Opening/Upgrading of Burauen-Albuera Road including Bridges, Leyte-Burauen Side, Leyte 2nd District | Burauen, Leyte | 2014-10-29 | 1st | VIII | LF | 45.1094 | 179 | 2014-09-05 | 2015-03-02 | 0.57% | O | 0.393 | 0.276 | 0.15 | 0.015 | 0.04 | 0.033 | 90.7% | 90.7% Very Satisfactory
MWJ Construction | 14882 | L | B | MB | GE2 | Repair/Impv't. of Flood Control Structures: A. Burauen-La Paz Rd., Km.981+108, Burauen-La Paz Rd. Sect., Tabon-Tabon | Leyte | 2013-03-11 | Final | VIII | LF | 2.371 | 150 | 2012-10-31 | 2013-03-29 | 51.67 | C | 0.372 | 0.18 | 0.3 | - | - | - | 85.2 | 84.60% Satisfactory
MWJ CONSTRUCTION | 14882 | L | B | MA | GE | Construction of Missing Gaps Connecting National Roads Including ROW Burauen-Albuera Road including Bridges, Burauen Side, Burauen, Leyte | Burauen Side, Burauen, Leyte | 2015-11-12 | 1st | Leyte Second DEO | LF | 45.1004 | 209 | 2015-06-15 | 2016-01-09 | (+)0.14% | OG | 0.35 | 0.24 | 0.15 | 0.03 | 0.035 | 0.05 | 85.5% | 85.5% Satisfactory
MY BUILDERS AND CONSTRUCTION | 22687 | L | B | MA | GB | Completion of Multi-Purpose Building, Brgy. Cabaroan, San Fernando City, La Union | San Fernando City, La Union | 2015-11-10 | 1st | LA UNION 1ST DEO | LF | 2.8511 | 199 | 2015-08-29 | 2016-03-15 | 0.397 | OG | 0.392 | 0.24 | 0.15 | 0.03 | 0.053 | 0.05 | 91.5% | 91.5% Very Satisfactory
MYMS Construction and Supply | 36258 | L | D | SB | GB | Rehabilitation of Multi-Purpose Building, Tubay | Tubay, Agusan del Norte | 2014-10-20 | 1st | XIII | LF | 1.9723 | 90 | 2014-09-06 | 2014-12-04 | 0.81% | O | 0.343 | 0.24 | 0.15 | 0.02 | 0.027 | 0.05 | 83% | 83% Satisfactory
MYMS CONSTRUCTION AND SUPPLY | 36258 | L | D | SB | GB | Construction of One (1) Storey, Two (2) Classroom at E.G. Montilla National High School (Mat-I NHS Annex), Las Nieves, Agussan del Norte | Las Nieves, Agussan del Norte | 2015-11-17 | 1st | Butuan City DEO | LF | 1.8008 | 90 | 2015-09-11 | 2015-12-09 | (+) 26.71 | OG | 0.325 | 0.3 | 0.15 | 0.03 | 0.047 | 0.05 | 90.2% | 90.2% Very Satisfactory
N & N Construction Corporation | 30716 | L | C | SB | GE | Repain/Construction/ Rehabilitation and Improvement (Road Slip) along Nasugbu-Ternate Road, Batangas, First Legislative District, K0121+700 to K0121+767.50 | Nasugbu, Batangas | 2014-08-06 | 1st & Final | IV-A | LF | 8.4023 | 210 | 2013-09-02 | 2014-03-30 | 0 | C | 0.402 | 0.2 | 0.3 |  |  |  | 90.2 | 90.20% Very Satisfactory
N & N Construction Corporation | 30716 | L | B | MA | GE2 | Package I - Repair/Maintenance 1. Sto. Niño River Control, Sto. Niño | Cabangan, Zambales | 2011-08-09 | 1st | III | LF | 1.956 | 100 | 2011-04-28 | 2011-08-05 | -20.18 | O | 0.34 | 0.18 | 0 | 0.022 | 0.035 | 0.033 | 61 | -
N. A. IBARRA CONSTRUCTION (Formerly: Diocletian's Construction) | 24742 | L | B | MA | GE | Rehabilitation/Improvement of Local Road, Gandara Diversion Road, Sta. 00+000-Sta. 01+000, Gandara, Samar 1st LD | Gandara, Samar 1st LD | 2015-11-18 | Final | Samar First DEO | LF | 8.8554 | 95 | 2015-01-30 | 2015-05-04 | - | C | 0.379 | 0.2 | 0.3 | - | - | - | 87.9% | 87.9% Satisfactory
N. B. Salbo Construction | 6091 | L |  |  |  | COMPLETION OF ACADEMIC BUILDING I PHASE II | Nangka Baloi, Lanao Del Norte | 2014-04-03 | Final | DOST | LF | 5.635 | 120 | 2012-04-16 | 2013-06-16 | -4 | C | 0.473 | 0.2 | 0.18 | - | - | - | - | 82.99% Satisfactory
N. B. SALBO CONSTRUCTION | 6091 | L | B | MA | GE | Local Infrastructure Program - Construction of Local Roads, Sapad to Poblacion Road, Municipality of Kapatagan, Lanao del Norte, Sta. 0+000-Sta. 0+114.79, Sta. 0+124.97-Sta. 1+007.59 and Sta. 1+206.47-Sta. 1+901.06 | Municipality of Kapatagan, Lanao del Norte, Sta. 0+000-Sta. 0+114.79, Sta. 0+124.97-Sta. 1+007.59 and Sta. 1+206.47-Sta. 1+901.06 | 2015-09-02 | 1st | Lanao del Norte 1st DEO | LF | 37.266 | 190 | 2015-03-11 | 2015-09-16 | 1.09% | O | 0.366 | 0.239 | 0.15 | 0.03 | 0.045 | 0.033 | 86.3% | -
N. Congson Construction & Supply | 25695 | L | B | MA | GE1 | Upgrading (Gravel to Concrete) Jct. Nat'l Highway (Sarangani-Davao del Sur Coastal Rd. to Gumasa White Beach Rd.), Gumasa | Glan, Sarangani Province | 2013-08-20 | Final | XII | LF | 17.772 | 150 | 2013-01-31 | 2013-06-29 | 0 | C | 0.411 | 0.197 | 0.3 | - | - | - | 90.8 | 88.70% Satisfactory
N. Congson Construction & Supply | 25695 | L | B | MA | GE1 | Upgrading (Gravel to Concrete) Jct. Nat'l Highway (Sarangani-Davao del Sur Coastal Rd. to Gumasa White Beach Rd.), Gumasa | Glan, Sarangani Province | 2013-03-22 | 1st | XII | LF | 17.772 | 137 | 2013-01-31 | 2013-06-16 | 4.4 | O | 0.367 | 0.234 | 0.15 | 0.03 | 0.042 | 0.05 | 87.3 | -
N. Congson Construction & Supply | 25695 | L | B | SB | GE2 | Rehab./Impv't. of Small Margus River Flood Control Structure along Sarangani-Davao del Sur Coastal Rd. | Glan, Sarangani Province | 2013-03-22 | Final | XII | LF | 7.544 | 178 | 2012-07-05 | 2012-12-29 | 2.52 | C | 0.417 | 0.133 | 0.3 | - | - | - | 85 | 85.30% Satisfactory
N. D. M. SANCHEZ BUILDERS & DEVELOPMENT CORPORATION | 35410 | L | AA | MB | GE | Widening of National Roads, Outside N1, Manila -Batangas Rd., K0061+(-51) - K0063+(-217), Sto. Tomas, Batangas | Sto. Tomas, Batangas | 2015-11-13 | 1st | BATANGAS 3RD DEO | LF | 45.5687 | 330 | 2015-02-03 | 2015-12-29 | 0.0018 | OG | 0.349 | 0.271 | 0.15 | 0.03 | 0.07 | 0.05 | 92% | 92% Very Satisfactory
N. D. M. SANCHEZ BUILDERS & DEVELOPMENT CORPORATION | 35410 | L | AA | MB | GE | Off-Carriageway Improvement - MSR Passing Poblacion Road, K0082+210 to K0082+610, San Pablo City, Laguna | San Pablo City, Laguna | 2015-11-19 | Final | LAGUNA 3RD DEO | LF | 9.212 | 177 | 2015-04-17 | 2015-11-09 | 0.0056 | C | 0.465 | 0.15 | 0.3 | - | - | - | 91.5% | 91.5% Very Satisfactory
N. Q Villapando Construction | 13338 | L | B | MB | GB-1 | Butuan Airport Development Project | Brgy. Bancasi, Butuan City/ CARAGA Region | 2015-04-20 | Final | DOTC | LF | 27.014 | 240 | 2015-04-06 | 2015-01-30 | 0 | C | 0.4781 | 0.2 | 0.3 | - | - | - | 97.81 | 93.53% V.Satisfactory
N. Q. Villapando Construction | 13338 | L | B | MA | GB-1 | Surigao Airport Development Project | Brgy. Luna, Surigao City/CARAGA Region | 2015-09-17 | 2nd & Final | DOTC | LF | 22.327 | 390 | 2014-04-06 | 2015-05-01 | 0 | C | 0.4703 | 0.2 | 0.3 | - | - | - | 97.03 | *97.05% Outstanding
N. Q. Villapando Construction | 13338 | L | B | MA | GB-1 | Surigao Airport Development Project | Surigao City, Surigao del Norte/ CARAGA Region | 2014-09-16 | 1st | DOTC | LF | 21.519 | 300 | 2014-04-06 | 2015-01-30 | 24.46 | O | 0.3823 | 0.3 | 0.15 | 0.03 | 0.0583 | 0.05 | 97.06 | -
N. Q. Villapando Construction | 13338 | L | B | MA | GB-1 | Butuan Airport Development Project | Butuan City/CARAGA Region | 2014-09-18 | 1st | DOTC | LF | 27.014 | 240 | 2014-04-06 | 2014-12-01 | 13.59 | O | 0.3871 | 0.24 | 0.15 | 0.03 | 0.06 | 0.05 | 91.71 | -
N.A. IBARRA CONSTRUCTION (Formerly: Diocletian's Construction) | 24742 | L | B | MA | GE | Construction of San Juan Bridge 2 along MNR | San Juan, Ilocos Sur | 2015-06-05 | Final | Ilocos Sur 1st DEO | LF | 9.901 | 162 | 2015-02-16 | 2015-07-27 | -22% | C | 0.4 | 0.24 | 0 | 0 | 0.045 | 0 | 68.5% | *68.5% Poor
N.A. IBARRA CONSTRUCTION (Formerly: Diocletion's Construction) | 24742 | L | B | MA | GE | Construction of Sinait Bridge 3 Along Manila North Road (MNR), Sinait, Ilocos Sur | Along Manila North Road (MNR), Sinait, Ilocos Sur | 2015-08-27 | 1st | Ilocos Sur 1st DEO | LF | 9.818 | 192 | 2015-02-23 | 2015-09-03 | - | O | 0.358 | 0.264 | 0.15 | 0.023 | 0.042 | 0.05 | 88.7% | -
N.B Avila Construction | 30983 |  |  |  |  | Road Upgrading (Gravel to Paved) of Jct. MWCR San Jose Airport - Jct. Bubog Rd., Brgy. Bubog |  | 2010-05-25 |  | IVB |  | 5.394 | 90 |  |  |  | O | 0.39 | 0.238 | 0.15 | 0.03 | 0.06 | 0.033 | 90.1 | -
N.B Avila Construction | 30983 |  |  |  |  | Rechanneling of Busuanga River, Pitogo |  | 2010-05-25 |  | IVB |  | 0.574 | 60 |  |  |  | O | 0.4 | - | 0.2 | 0.025 | 0.079 | 0.167 | 87.1 | -
N.B Garcia Construction/ F.A. Torres Construction (JV) | JV-08-288 | L | D | SB | GE1 | Road Upgrading (gravel to paved), MWCR, Rizal-Calintaan (San Pedro-Mangat Section) KO 256+028- KO 256+733 |  | 2009-08-31 | 2nd | IVB |  | 9.646 | 164 |  |  |  | O | 0.345 | 0.298 | 0.15 | 0.03 | 0.037 | 0.033 | 89.3 | -
N.B Garcia Construction/ F.A. Torres Construction (JV) | JV-08-288 | L | D | SB | GE1 | Road Upgrading (Gravel to Paved) MWCR, Rizal-Calintaan (San Pedro-Mangat Section) |  | 2009-05-29 | 1st | IV-B |  | 9.565 | 90 |  |  |  | O | 0.281 | 0.3 | 0.15 | 0.03 | 0.033 | 0.05 | 84.4 | -
N.B Salbo Construction | 6091 |  |  |  |  | Rehab./Reconst./Upgrading along Misamis Oriental-Ma.Cristina Bdry. Road, Dalipuga Centenial-Tag-ibo Section, Sta.1514+000 - Sta.1514+781 w/ exceptions |  | 2010-06-07 |  | X |  | 13.912 | 120 |  |  |  | O | 0.366 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 89.1 | -
N.B Salbo Construction | 6091 |  |  |  |  | Road Upgrading (Gravel to Paved) of Gingoog-Claveria-Villanueva Road Km.1362+580.794 - Km.1363+764.294 |  | 2010-06-10 |  | X |  | 19.297 | 105 |  |  |  | O | 0.374 | 0.235 | 0.15 | 0.023 | 0.05 | 0.033 | 86.5 | -
N.B Salbo Construction | 6091 | L | B | MA | GE1 | Rehab. / Reconst. of Damaged Road Sections along Linamon-Zamboanga Road (Taguitic Section) |  | 2008-11-28 | 1st | X |  | 19.212 | 455 |  |  |  | O | 0.251 | 0.3 | 0.1 | 0.024 | 0.045 | 0.1 | 82 | -
N.B Salbo Construction | 6091 | L | B | MA | GE1 | Road Upgrading (Gravel to Concrete) based on GTRSTB, Gingoog-Claveria-Villanueva Road |  | 2009-03-11 | 1st | X |  | 19.293 | 165 |  |  |  | O | 0.347 | 0.233 | 0.15 | 0.03 | 0.05 | 0.033 | #VALUE! | -
N.B. Avila Construction | 13751 | L | B | MA | GE | Construction/Rehabilitation of Flood Control Projects in Isabela 4th DEO/4th LD - Magabito Flood Control, K0000+000 - K0000+126 | Mabini, Santiago City | 2014-10-27 | 1st & Final | II | LF | 7.9537 | 114 | 2015-02-19 | 2015-06-12 |  | C | 0.4 | 0.16 | 0.3 | - | - | - | 86% | 86% Satisfactory
N.B. Avila Construction | 13751 | L | B | MA | GE | Construction of Flood Control along Tagaytay-Manila via Silang Road | K0054+612-K0056+100, 7th Legislative District | 2014-11-06 | 1st & Final | IV | LF | 10.4857 | 180 | 2014-02-14 | 2014-08-12 | - | C | 0.445 | 0.133 | 0.3 | - | - | - | 87.8% | 87.8% Satisfactory
N.B. Avila Construction | 13751 |  |  | SB |  | Rehabilitation of Diversion Works of Tres Cruzes River Irrigation System | Tanza, Cavite | 2015-02-14 | 1st & Final | NIA | L | 9.616 | 150 | 2014-02-14 | 2014-07-15 | 0 | C | 0.4333 | 0.16 | 0.3 | - | - | - | 89.33 | *89.33% V. Satisfactory
N.B. Salbo Construction | 6091 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Paved) (Int. Sect.) inc. Drainage & Rd. Facilities along LDNICR (Balo-i) to Pantao Ragat Rd., Km.1547+(-663)-Km.1548+000; Km.1548+000-Km.1548+250 | Balo-I, Lanao del Norte | 2013-08-13 | Final | X | LF | 40.357 | 152 | 2013-01-05 | 2013-06-15 | 5.26 | C | 0.414 | 0.133 | 0.3 | - | - | - | 84.7 | 83.26% Satisfactory
N.B. Salbo Construction | 6091 | L | B | MA | GE1 | Road Upgrading (Gravel to Paved) (Int. Sect.) inc. Drainage & Rd. Facilities along LDNICR (Balo-I) to Pantao Ragat Rd., Km.1547+(-663)-Km.1548+000; Km.1548+000-Km.1548+250 | Balo-i, Lanao del Norte | 2013-03-13 | 1st | X | LF | 38.894 | 132 | 2013-01-15 | 2013-05-26 | 11.39 | O | 0.305 | 0.3 | 0.15 | 0 | 0.035 | 0.033 | 82.3 | -
N.B. Salbo Construction | 6091 | L |  |  | GB1 | `Completion of Dormitory Bldg II Phase II | Langka Balol, Lanao del Norte | 2011-08-25 | 1st | DOST | LF | 20.564 |  | 2009-12-18 | 2011-08-31 | 0 | O | 0.395 | 0.3 | 0.15 | 0.033 | 0.0233 | 0.03 | 93.13 | -
N.B. SALBO CONSTUCTION | 6091 | L | B | MA | GE | Rehabilitation/Reconstruction of National Road with Slips, Slope Collapse and Landslide at Sta. Filomena-Bonbonon-Digkilaan-Rogongon Road, Km. 1530+260-Km. 1530+380, Brgy. Digkilaan, Iligan City, Lanao del Norte | Brgy. Digkilaan, Iligan City, Lanao del Norte | 2015-11-11 | Final | Lanao del Norte 2nd | LF | 23.1773 | 192 | 2015-02-18 | 2015-08-29 | 0.00% | C | 0.395 | 0.189 | 0.3 | - | - | - | 88.4% | 88.4% Satisfactory
N.C. Aguilar Const. & Supply Inc. | 36949 | L | D | SB | GE | Upgrading /Box Culvert along Villanueva Creek, Schillings Lane (Villanueva Village), Barangay San Dionisio | Parañaque City, M.M. | 2014-11-18 | 1st | NCR | LF | 6.4159 | 237 | 2014-06-30 | 2015-02-21 | -5% | O | 0.251 | 0.24 | 0.1 | 0.03 | 0.055 | 0.033 | 70.9% | 70.9% Poor
N.D.M. Sanchez Builders & Development Corporation | 35410 | L | A | MA | GE1 | Widening of Daang Maharlika inc. Drainage System, Sto. Tomas Sect., Sto. Tomas Sect., K062+570-K063+509.50 | Sto. Tomas, Batangas | 2013-08-01 | 1st | IVA | LF | 36.602 | 210 | 2013-03-13 | 2013-10-08 | 6.07 | O | 0.334 | 0.243 | 0.15 | 0.03 | 0.04 | 0.033 | 83
N.D.M. SANCHEZ BUILDERS & DEVELOPMENT CORPORATION | 35410 | L | AA | MB | GE | Off Carriageway Improvement of Lipa - Balete Road, K0077+(-165) to K0077+870 | Lipa City, Batangas | 2015-06-05 | 1st | Batangas 4th DEO | LF | 17.993 | 150 | 2015-02-12 | 2015-07-11 | 23% | O | 0.31 | 0.292 | 0.15 | 0.024 | 0.05 | 0.033 | 85.9% | -
N.D.M. SANCHEZ BUILDERS & DEVELOPMENT CORPORATION | 35410 | L | AA | MB | GE | Widening of National Roads, Outside N1, Manila - Batangas Rd., K0061+(-051) to K0063+(-217) | Sto. Tomas, Batangas | 2015-06-06 | 1st | Batangas 3rd DEO | LF | 45.57 | 290 | 2015-02-03 | 2015-11-19 | 0.07% | O | 0.333 | 0.282 | 0.15 | 0.03 | 0.03 | 0.033 | 85.8% | -
N.D.M. SANCHEZ BUILDERS & DEVELOPMENT CORPORATION | 35410 | L | AA | MB | GE | Repair/Rehabilitation and Improvement of Maspang Highway, K0070+(-910) to K0071+500 with exceptions | Calauan, Laguna | 2015-06-12 | Final | Laguna 3rd DEO | LF | 10.902 | 130 | 2014-09-04 | 2015-01-11 | 17% | C | 0.401 | 0.13 | 0.3 | - | - | - | 83.1% | *83.1% Satisfactory
N.D.M. Sanchez Builders & Development Corporation/IKM Builders & Construction Supply Joint Venture | JV-13-237 | L | A | MB | GE | Widening of Manila-Batangas, Aguila Section K0093+960-K0095+465.30 (Both Side) | San Jose, Batangas | 2014-12-05 | 1st & Final | IV | LF | 36.6673 | 210 | 2014-02-03 | 2014-08-31 | 0.55% | C | 0.483 | 0.133 | 0.3 | - | - | - | 91.6% | 91.6% Very Satisfactory
N.K Enterprise | 29292 |  |  |  |  | Rehab./Imprv't. of Various Brgy. Rds. At Villafont & Imparayan |  | 2010-02-25 |  | VI |  | 18.922 | 210 |  |  |  | O | 0.338 | 0.263 | 0.15 | 0.02 | 0.03 | 0.033 | 83.4 | -
N.K. Enterprise | 29292 | L | A | MA | GE | Replacement/Const. of Ipil Bridge Km. 160+947.97, Ipil , Barbaza, Antique | Barbaza, Antique | 2014-08-13 | Final | VI | LF | 16.3792 | 245 | 2013-02-12 | 2013-07-11 | -10.02 | C | 0.37 | 0.2 | 0 |  |  |  | 57 | 77.82% Unsatisfactory
N.K. Enterprise | 29292 | L | B | MA | GE1 | Replacement/Const. of Ipil Bridge, Km. 160+947.97, Brgy. Ipil | Barbaza, Antique | 2013-08-15 | 1st | VI | LF | 16.381 | 210 | 2013-02-12 | 2013-09-09 | 1.82 | O | 0.362 | 0.3 | 0.15 | 0.03 | 0.042 | 0.033 | 91.7 | -
N.K. Enterprise | 29292 | L | B | MA | GE2 | Const. of Drainage & Slope Protection Works along Bacolod South Rd., K0099+100-K0103+900 w/ exc. | Ilog, Negros Occidental | 2013-08-08 | Final | VI | LF | 9.603 | 188 | 2013-10-31 | 2013-05-06 | 0 | C | 0.43 | 0.133 | 0.3 | - | - | - | 86.3 | 86.48% Satisfactory
N.K. Enterprise | 29292 | L | B | MA | GE2 | Const. of Drainage & Slope Protection Works along Bacolod South Rd., K099+100-K0103+900, w/ exception | Ilog, Negros Occidental | 2013-03-13 | 1st | VI | LF | 9.603 | 170 | 2012-10-31 | 2013-04-18 | -1.85 | O | 0.322 | 0.295 | 0.132 | 0.024 | 0.06 | 0.033 | 86.6 | -
N.K. ENTERPRISE | 29292 | L | B | MA | GE | Replacement of Permanent Weak Bridge, Tomyong Bridge along Iloilo- Antique Road (Completion) | K0124+906.635 to K0125+100.135 (With Exception), Barangay La Rioja, Patnongon, Antique | 2015-06-04 | Final | Antique DEO | LF | 2.994 | 37 | 2015-03-04 | 2015-04-09 | 62.16% | C | 0.442 | 0.196 | 0.3 | - | - | - | 93.8% | *93.8% Very Satisfactory
N.S Gambito Construction Services | 31640 | L | D | SB | GE1 | Concreting of Aritao-Quirino Road, Bitnong Section |  | 2009-06-04 | 1st | II |  | 9.65 | 104 |  |  |  | O | 0.328 | 0.24 | 0.15 | 0.03 | 0.051 | 0.05 | 84.9 | -
N.V. Balbuena Construction | 12055 | L | C | SB | GB | Construction of Two (2) Storey Four (4) Classrooms, Mariveles National High School - Cabcaben Annex (Batangas II) | Mariveles, Bataan | 2014-08-13 | 1st & Final | III | LF | 4.7072 | 120 | 2014-02-01 | 2014-06-01 | 1.67 | C | 0.444 | 0.133 | 0.3 |  |  |  | 87.7 | 87.70% Satisfactory
N.V. BALBUENA CONSTRUCTION | 12055 | L | C | SB | GE | Construction/Upgrading/Rehab. of Drainage Canal along Gov. J. J. Linao Road at Balanga City, Bataan, Km. 139+600 to Km. 140+000, Balanga City, Bataan | Balanga City, Bataan | 2015-06-04 | Final | Bataan Second DEO | LF | 3.708 | 126 | 2015-02-24 | 2015-06-29 | 27.78% | C | 0.495 | 0.16 | 0.3 | - | - | - | 95.5% | *95.5% Very Satisfactory
Nascon Builders | 14786 | L | D | SB | GB1 | Const. of Multi-Purpose Building, Brgy. CP Garcia |  | 2009-06-02 | 1st | X |  | 1.06 | 75 |  |  |  | O | 0.374 | 0.276 | 0.11 | 0.03 | 0.019 | 0.033 | 84.2 | -
NBL CONSTRUCTION | 16722 | L | AAA | LB | GE | Preventive Maintenance of National Arterial Road based on PMS/HDM-4 (Intermittent Sections) along Palico-Balayan-Batangas Road at: 1. K0097+535-K0098+002; 2.K0098+736-K0099+066; 3. K0103+230; 4.K0113+000-K0113+800 and 5. K0128+000-K0128+230 | Palico-Balayan-Batangas Road, Calaca, Batangas | 2014-11-08 | 1st & Final | IV | LF | 7.1898 | 90 | 2014-02-03 | 2014-05-03 | - | C | 0.487 | 0.127 | 0.3 | - | - | - | 91.4% | 91.4% Very Satisfactory
NBL CONSTRUCTION | - | L | - | - | GE | National Road Network Services, Asset Preservation of National Roads, Construction/Upgrading/Rehabilitation of Drainage along National Roads, Talisay - Laurel - Agoncillo Road, K0084+280 to K0085+480 | Talisay, Batangas | 2015-06-06 | 1st | Batangas 3rd DEO | LF | 27.327 | 260 | 2015-02-03 | 2015-10-20 | 1.63% | O | 0.303 | 0.282 | 0.15 | 0.03 | 0.04 | 0.033 | 83.8% | -
NBL Construction / Vicmar Construction, Inc. Joint Venture | JV-09-090 |  |  |  |  | Conc./Widening/Impvt. of Bauan-Mabini Circumferential Rd. |  | 2010-06-04 |  | IVA |  | 57.895 | 90 |  |  |  | O | 0.365 | 0.24 | 0.15 | 0.023 | 0.048 | 0.05 | 87.6 | -
NBL CONSTRUCTION/ F. CASALME CONSTRUCTION & SUPPLY (JOINT VENTURE) | JV-14-1069 | L | AAA | MA | GE | Construction/Rehab. of Floodway | Brgy. Bagong Sikat, Lemery, Batangas | 2015-08-31 | 1st & Final | Batangas 1st | LF | 9.408 | 120 | 2015-06-22 | 2015-10-19 | 25% | C | 0.388 | 0.24 | 0.15 | - | - | - | 88.8% | *88.8% Satisfactory
NBL CONSTRUCTION/ GREAT SWISS METAL BUILDERS CORP. (JOINT VENTURE) | JV-15-031 | L | AAA | MA | GE | MFO 2 - Flood Management Services, Construction/Maintenance of Flood Mitigation Structures and Drainage Systems, Construction/Improvement of Revetment Wall along Calumpang River | Batangas City, Batangas 2nd LD | 2015-09-01 | 1st | Batangas 2nd | LF | 23.128 | 180 | 2015-07-15 | 2016-01-10 | 21.7% | O | 0.348 | 0.24 | 0.15 | 0.03 | 0.045 | 0.033 | 84.6% | -
NDM Equipment Rental and Construction |  | L |  |  |  | Land Development of Tacloban North Resettlement Project Phase 2 with Road Concreting of Phase I | Brgy. Kawayan, Tacloban City, Leyte | 2015-02-28 | 1st | NHA | L | 40.818 | 200 | 2014-05-31 | 2015-05-03 | 16.74 | O | 0.3767 | 0.242 | 0.15 | 0.024 | 0.0538 | 0.05 | 89.65 | -
NDM Equipment Rental and Construction | [5 empty] | Land Development of Tacloban North Resettlement Project Phase 2 with Road Concreting of Phase 1 | Brgy. Kawayan, Tacloban City, Leyte | 2016-01-29 | Final | NHA | LF | 40.79 | 200 | 2014-05-31 | 2015-09-13 | 0 | C | 0.4634 | 0.2 | 0.3 | - | - | - | 96.34 | 92.33% V. Satisfactory
NDM Sanchez Builders and Development Corporation | 35410 | L | AA | MB | GE | Widening of Daang Maharlika including Drainage System, Sto. Tomas Section, K0062+570 to K0063+509.50, Sto. Tomas, Batangas | Sto. Tomas, Batangas | 2014-08-09 | Final | IV-A | LF | 37.5792 | 240 | 2013-03-13 | 2013-11-07 | 0 | C | 0.434 | 0.2 | 0.3 |  |  |  | 93.4 | 87.16% Satisfactory
NES-SAN BUILDERS | 25142 | L | D | MA | GB | Construction of Three (3) Storey-Fifteen (15) Classroom School Building with Security Grilles and Soil Testing at Pandacaque NHS, Baliuag-Candaba Road, Baliuag, Bulacan | Baliuag-Candaba Road, Baliuag, Bulacan | 2015-08-27 | 1st & Final | Pampanga First DEO | LF | 18.712 | 326 | 2014-07-15 | 2015-06-05 | 15.33% | C | 0.435 | 0.129 | 0.3 | - | - | - | 86.4% | *86.4% Satisfactory
New Arcond Builders Incorporated (Formerly: Arcond Builders) | 9614 | L | A | MA | GE1 | Concrete Widening/Conc. Blocking w/ Drainage & Sidewalk Impv't. along Araneta Ave. K0009+646+(-033) Northbound | Quezon City | 2013-08-05 | 1st | NCR | LF | 31.295 | 249 | 2013-03-25 | 2013-11-28 | -4.48 | O | 0.303 | 0.224 | 0.105 | 0.03 | 0.045 | 0.033 | 74
NEW ARCOND BUILDERS INCORPORATED (Formerly: Arcond Builders) | 9614 | L | A | MA | GE | Drainage Improvement of Roosevelt Avenue, Brgy. Sta. Cruz, Quezon City | Brgy. Sta. Cruz, Quezon City | 2015-08-25 | 1st | QC 1st DEO | LF | PHP 17.758 | 180 | 2015-03-09 | 2015-09-04 | 0.56% | O | 0.375 | 0.24 | 0.15 | 0.03 | 0.07 | 0.05 | 91.5% | -
NEW ARCOND BUILDERS INCORPORATED (Formerly: Arcond Builders) | 9614 | L | A | MA | GE | Drainage Improvement of Visayas Avenue (Congressional Avenue to Bridge), Quezon City | Quezon City | 2015-12-09 | Final | QC 1st DEO | LF | 16.8486 | 240 | 2015-03-09 | 2015-12-03 | 0.00% | C | 0.485 | 0.133 | 0.3 | - | - | - | 91.8% | 91.8% Very Satisfactory
New Arcond Builders Incorporated/Alpiz Construction and Development Corporation Joint Venture | JV-13-445 | L | A | MA | GE | Improvement of Roosvelt Avenue (K0007+940 to K0010+811) | Quezon City | 2014-08-14 | 1st & Final | NCR | LF | 17.3701 | 180 | 2014-01-15 | 2014-07-13 | 7.22 | C | 0.474 | 0.133 | 0.3 |  |  |  | 90.7 | 90.70% Very Satisfactory
New Big Four J Construction, Inc. | 15104 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of Marikina-Victoria Valley-Antipolo Road |  | 2009-05-18 | 1st | IV-A |  | 19.209 | 180 |  |  |  | O | 0.389 | 0.24 | 0.15 | 0.02 | 0.03 | 0.05 | 87.9 | -
NEW BIG FOUR J CONSTRUCTION, INC. | 15104 | L | AAA | MA | GE | Const./Rehabilitation of Flood Control in Laguna 1st DEO/4th LD, Lumban River | Lumban, Laguna | 2015-08-27 | Final | Laguna 1st | LF | 45.57 | 312 | 2014-02-14 | 2014-12-22 | 0% | C | 0.479 | 0.2 | 0.3 | - | - | - | 97.9% | *82.54% Satisfactory
New Big Four J Construction, Inc. (Formerly: Four J Construction) | 15104 | L | AAA | MA | GB | Construction/Rehabilitation of Flood Control in Laguna 1st DEO/4th LD, Lumban River | Lumban, Laguna | 2014-11-26 | 1st | IV | LF | 45.5698 | 235 | 2014-02-14 | 2014-10-06 | - | O | 0.337 | 0.3 | 0 | 0.03 | 0.023 | 0.033 | 72.3% | 72.3% Poor
New Big Four J Construction, Inc. (Formerly: Four J Construction) | 15104 | L | AAA | MA | GB | Cluster II for the Preventive Maintenance (MFO-1) of Paete-Famy Poblacion Road, A. K0103+-1472 to K0103+-977; B. K0110+-088 to K0111+490; C. K0112+000 to K0112+810 | Laguna | 2014-11-26 | 1st & Final | IV | LF | 26.8959 | 60 | 2014-02-14 | 2014-04-14 | - | C | 0.355 | 0.2 | 0.3 | - | - | - | 85.5% | 85.5% Satisfactory
New Big Four J Construction, Inc. (Formerly: Four J Construction)/11 Diamond Eagle Construction (JV) | - | L | AAA | MA | GE | Construction/Rehabilitation of Flood Control in Laguna 2nd DEO/1st LD along Manila South Road at Brgy Tagapo, K000+000-K00+381, Sta. Rosa City, Laguna | Brgy. Tagapo, Sta. Rosa City, Laguna | 2014-11-28 | 1st & Final | IV | LF | 9.2019 | 165 | 2014-01-23 | 2014-07-06 | - | C | 0.386 | 0.2 | 0.3 | - | - | - | 88.6% | 88.6% Satisfactory
New C. C. Barcelona Construction Corporation | 14489 |  | AA |  |  | Infrastructure Development of Veterans Regional Hospital | Bayombong, Nueva Vizcaya | 2014-10-24 | 1st | DOH | L | 99.785 | 480 | 2014-07-08 | 2015-08-02 | 1.796 | O | 0.363 | 0.264 | 0.15 | 0.03 | 0.065 | 0.05 | 92.2 | -
New C.C. Barcelona Construction Corporation | 14489 |  | AA |  |  | Construction of Fire Protection System & Powerhouse Building | Bayombong, Nueva Vizcaya | 2016-06-24 | 1st | DOH | LF | 8.815 | 120 | 2016-01-11 | 2016-05-18 | 0 | O | 0.385 | 0.288 | 0.15 | 0.03 | 0.07 | 0.05 | 97.3 | -
New C.C. Barcelona Construction Corporation | 14489 |  | AA |  |  | Design and Build for the Construction of 4 Storey OPD Building | Bayombong, Nueva Vizcaya | 2016-06-24 | 2nd | DOH | LF | 101.787 | 675 | 2014-07-08 | 2015-12-29 | 0 | O | 0.385 | 0.295 | 0.15 | 0.03 | 0.065 | 0.05 | 97.5 | -
New C.C. Barcelona Construction Corporation | 14489 |  | AA |  |  | Construction of OPD Training Center Elevator Lobby Grid 21 to Grid 22 | Bayombong, Nueva Vizcaya | 2016-06-24 | 1st | DOH | LF | 10.455 | 150 | 2016-01-11 | 2016-06-08 | 0 | O | 0.366 | 0.272 | 0.15 | 0.03 | 0.065 | 0.05 | 93.3 | -
New C.C. Barcelona Construction Corporation | 14489 |  | AA |  |  | Completion of OPD Building - 4th Floor Phase-1 | Bayombong, Nueva Vizcaya | 2016-06-24 | 1st | DOH | LF | 11.118 | 135 | 2016-01-11 | 2016-05-24 | 0 | O | 0.355 | 0.299 | 0.15 | 0.03 | 0.07 | 0.05 | 95.4 | -
New Kanlaon Construction inc./ JE Manalo & CO., Inc. (JV) | 896 |  |  |  |  | Southern Philippines Irrigation Sector Project SPISP(Construction of Binalawan Concrete Buttress Dam & Appurtenant Facilities) |  | 2010-06-12 |  | NIA |  | 167.797 | 378 |  |  |  | O | 0.382 | 0.211 | 0 | 0.03 | 0.033 | 0.017 | 67.3 | -
New Kanlaon Construction Inc/ J E Manalo & Co., Inc (JV) | 896 | L | AAA |  | GE2 | Southern Philippines Irrigation Sector Project (SPISP) | Brgy. Balicotoc, Ilog, Negros Occidental | 06/07-12/10 | 1st | NIA | FA | 167.797 | 378 | 2009-06-18 | 2010-06-30 | -55.62 | O | 0.382 | 0.211 | - | 0.03 | 0.033 | 0.017 | 67.3 | -
New Kanlaon Construction Incorporated | 896 | L | AAA |  |  | Quipot Irrigation Project | Tiaong Candelaria, Sariaya, San Antonio & San Juan Batangas | 2015-11-21 | 1st | NIA | LF | 119.453 | 365 | 2015-01-27 | 2016-01-26 | -9.58 | O | 0.33 | 0.287 | 0.0542 | 0.03 | 0.07 | 0.05 | 82.12 | -
New Kanlaon Construction Incorporated | 896 | L | AAA |  |  | Quipot Irrigation Project | San Antoniozon, Quezon | 2015-11-21 | 1st | NIA | LF | 95.911 | 365 | 2015-01-27 | 2016-01-26 | -34.42 | O | 0.3473 | 0.3 | 0 | 0.03 | 0.07 | 0.05 | 79.73 | -
New Kanlaon Construction, Inc. | 896 | L | AAA | LB | GE1 | Concreting of Barotac Nuevo-Dumangas-Dacutan Wharf Road |  | 2009-06-11 | 1st | VI |  | 17.611 | 99 |  |  |  | O | 0.357 | 0.24 | 0.15 | 0.015 | 0.04 | 0.05 | 85.2 | -
New Kanlaon Construction, Inc./ GLS Const. & gen. Merch-JV | 896 |  | AAA |  |  | Maranding River Irrigation System | Maranding/ Lala, Lanao del Norte | 2015-11-25 | 1st | NIA | LF | 105.912 | 440 |  | 2015-08-15 | 1.81 | O | 0.3454 | 0.3 | 0.1319 | 0.025 | 0.061 | 0.0167 | 88 | -
NEW MINDOREÑOS HARDWARE AND GENERAL MERCHANDISE (Formerly: Mercedita Benasas General Merchandise) | 31745 | L | A | MA | GE | Construction of Banakan Bridge | Brgy. Tangkalan, Mamburao, Occidental Mindoro | 2015-11-17 | 1st | Mindoro Occidental DEO | LF | 18.8102 | 162 | 2015-08-04 | 2016-01-12 | 0.0364 | OG | 0.317 | 0.3 | 0.15 | 0.006 | 0.045 | 0.033 | 85.1% | 85.1% Satisfactory
New Mindoreños Lumber, Hardware and General Merchandise | 31745 | L | A | MA | GE1 | Road Upgrading (gravel to paved) MWCR, Sablayan-Sta. Cruz (Pag-asa-Amnay Section) KO 352+647-KO 354+004.5 |  | 2009-08-30 | 2nd | IVB |  | 19.1577 | 179 |  |  |  | O | 0.365 | 0.296 | 0.15 | 0.03 | 0.042 | 0.033 | 91.6 | -
New Mindoreños Lumber, Hardware and General Merchandise | 31745 | L | A | MA | GE1 | Road Upgrading (gravel to paved) MWCR, Sablayan-Sta. Cruz (San Vicente-Cabacungan Section) KO 329+363-KO 330+921 |  | 2009-08-30 | 2nd | IVB |  | 19.175 | 182 |  |  |  | O | 0.35 | 0.3 | 0.15 | 0.03 | 0.042 | 0.033 | 90.5 | -
New Mindoreños Lumber, Hardware and General Merchandise | 31745 | L | A | MA | GE1 | Road Upgrading (gravel to paved) MWCR, Sta. Cruz-Mamburao (Casoy-Balansay Section) KO 399+495-KO 400+872 |  | 2009-09-01 | 1st | IVB |  | 19.292 | 185 |  |  |  | O | 0.348 | 0.3 | 0.15 | 0.03 | 0.042 | 0.033 | 90.3 | -
New Mindoreños Lumber, Hardware and General Merchandise | 31745 | L | A | MA | GE1 | Road Upgrading (gravel to paved) MWCR, Sta. Cruz-Mamburao (Pagbahan-Talabaan Section) KO 389+704-KO 391+157 |  | 2009-08-30 | 1st | IVB |  | 14.471 | 191 |  |  |  | O | 0.368 | 0.3 | 0.101 | 0.022 | 0.042 | 0.033 | 86.6 | -
New Mindorenos Lumber, Hardware and General Merchandise | 31745 | L | A | MA | GE1 | Road Upgrading (Gravel to Paved) MWCR, Sablayan-Sta. Cruz (Pag-asa Amnay Section) |  | 2009-05-29 | 1st | IV-B |  | 19.158 | 140 |  |  |  | O | 0.354 | 0.3 | 0.115 | 0.03 | 0.035 | 0.033 | 86.7 | -
New Mindorenos Lumber, Hardware and General Merchandise | 31745 | L | A | MA | GE1 | Road Upgrading (Gravel to Paved) MWCR, Sablayan-Sta. Cruz (San Vicente-Cabacungan Section) |  | 2009-05-29 | 1st | IV-B |  | 19.176 | 140 |  |  |  | O | 0.351 | 0.3 | 0.15 | 0.03 | 0.037 | 0.033 | 90.1 | -
New Mindorenos Lumber, Hardware and General Merchandise | 31745 | L | A | MA | GE1 | Road Upgrading (Gravel to Paved) MWCR, Sta. Cruz-Mamburao (Casoy-Balansay Section) |  | 2009-05-30 | 1st | IV-B |  | 19.188 | 140 |  |  |  | O | 0.308 | 0.3 | 0.07 | 0.03 | 0.03 | 0.033 | 77.1 | -
New Mindoreños Lumber, Hardware and General Merchandise (Formerly: Mercedita Benasas General Merchandise) | 31745 | L | A | MA | GE1 | Replacement/Reconst. of Orobugan Bridge 1 along Crossing MWCR (Pola) - Casague-Jct. Alacaak Rd. | Sta. Cruz, Mindoro | 2013-07-29 | Final | IVB | LF | 7.454 | 201 | 2012-09-20 | 2013-04-08 | 20 | C | 0.428 | 0.165 | 0.3 | - | - | - | 89.3 | 86.24% Satisfactory
New Mindoreños Lumber, Hardware and General Merchandise (Formerly: Mercedita Benasas General Merchandise) | 31745 | L | A | MA | GE1 | Replacement/Reconst. of Siburan Bridge along Jct. MWCR (San Isidro)-Penal Colony-Jct. Yapang Rd. | Sablayan, Occidental Mindoro | 2013-07-30 | Final | IVB | LF | 9.443 | 219 | 2012-09-20 | 2013-04-26 | 0 | C | 0.396 | 0.196 | 0.3 | - | - | - | 89.2 | 85.96% Satisfactory
New Mindoreños Lumber, Hardware and General Merchandise (Formerly: Mercedita Benasas General Merchandise) | 31745 | L | A | MA | GE1 | Replacement/Reconst. of San Isidro Bridge 2 along Jct. MWCR (San Isidro)-Penal Colony-Jct. Yapang Rd., Brgy. Malisbong | Sablayan, Occidental Mindoro | 2013-07-30 | Final | IVB | LF | 7.475 | 215 | 2012-09-20 | 2013-04-22 | -4.65 | C | 0.376 | 0.2 | 0.16 | - | - | - | 73.6 | 79.84% Unsatisfactory
New Mindoreños Lumber, Hardware and General Merchandise (Formerly: Mercedita Benasas General Merchandise) | 31745 | L | A | MA | GE1 | Replacement/Reconst. of Orobugan Bridge 1 along Crossing MWCR (Pola)-Casague-Jct. Alacaak Rd., Brgy. Kurtinganan | Sta. Cruz, Occidental Mindoro | 2012-11-25 | 1st | IVB | LF | 7.454 | 201 | 2012-09-20 | 2013-04-08 | 20.37 | O | 0.337 | 0.22 | 0.15 | 0.03 | 0.055 | 0.05 | 84.2 | -
New Mindoreños Lumber, Hardware and General Merchandise (Formerly: Mercedita Benasas General Merchandise) | 31745 | L | A | MA | GE1 | Replacement/Reconst. of Siburan Bridge along Jct. MWCR-(San Isidro)-Penal Colony-Jct. Yapang Rd. | Sablayan, Occidental Mindoro | 2012-11-25 | 1st | IVB | LF | 9.443 | 2019 | 2012-09-20 | 2013-04-26 | 30.93 | O | 0.325 | 0.24 | 0.15 | 0.023 | 0.05 | 0.05 | 83.8 | -
New Mindoreños Lumber, Hardware and General Merchandise (Formerly: Mercedita Benasas General Merchandise) | 31745 | L | A | MA | GE1 | Replacement/Reconst. of San Isidro Bridge 2 along Jct. MWCR (San Isidro)-Penal Colony-Jct. Yapang Rd., Brgy. Malisbong | Sablayan, Occidental Mindoro | 2012-11-25 | 1st | IVB | LF | 7.476 | 185 | 2012-09-20 | 2013-03-23 | 16.4 | O | 0.327 | 0.24 | 0.15 | 0.023 | 0.05 | 0.05 | 84 | -
New Mindoreños Lumber, Hardware and General Merchandise (Formerly: Mercedita Benasas General Merchandise) | 31745 |  |  |  |  | Road Upgrading of Abra de Ilog-San Jose Rd.(Casoy Mimping Sect.) Brgy. Balansay |  | 2010-05-24 |  | IVB |  | 6.753 | 90 |  |  |  | O | 0.322 | 0.238 | 0.13 | 0.03 | 0.05 | 0.033 | 80.3 | -
New Mindoreños Lumber, Hardware and General Merchandise (Formerly: Mercedita Benasas General Merchandise) | 31745 | L | A | SB | GB1 | Const. of Casague MPB |  | 2008-11-21 | 1st | IV-B |  | 0.864 | 45 |  |  |  | O | 0.329 | 0.24 | 0.1 | 0.03 | 0.027 | 0.1 | 82.6 | -
NEW MINDOREÑOS LUMBER, HARDWARE AND GENERAL MERCHANDISE (Formerly: Mercedita Benasas General Merchandise) | 31745 | L | A | MA | GE | Construction of Farm-to-Market Road, Sitio Banakan, Barangay Tangkalan | Mamburao, Mindoro Occidental Lone District | 2015-06-08 | Final | Mindoro Occidental DEO | LF | 4.75 | 82 | 2015-02-15 | 2015-05-07 | 0% | C | 0.475 | 0.133 | 0.3 | - | - | - | 90.8% | *90.8% Very Satisfactory
NEW RICH GEN. CONT. SERVICES & TRADING CO., INC. | 27629 | L | B | SB | GB | Local Infrastructure Program - Const. of Classroom, San Cristobal NHS | Brgy. San Cristobal, San Pablo City 3rd LD | 2015-08-28 | 1st & Final | Laguna 3rd | LF | 1.481 | 90 | 2015-06-25 | 2015-09-22 | 27.78% | C | 0.47 | 0.133 | 0.3 | - | - | - | 90.3% | *90.3% Very Satisfactory
New Rich General Contractor Services & Trading Company, Inc. | 27629 | L | B | SB | GB | Construction of Slope Protection (Drainage) along Bacolod South Road, (Camansi Section, Phase II), K0021+770 - K0022+065 (Camansi Section) | Bago City, Negros Occidental | 2014-10-22 | 1st & Final | VI | LF | 5.7422 | 80 | 2014-05-14 | 2014-08-01 | -1.3% | C | 0.446 | 0.133 | 0.3 | - | - | - | 87.9% | 87.9% Satisfactory
New Rich General Contractor Services & Trading Company, Inc. | 27629 |  |  | SB |  | Construction of Canal Structures of Kay Mangga CIS Extension | Binangonan, Rizal | 2015-02-14 | 1st & Final | NIA | L | 1.163 | 120 | 2014-02-17 | 2014-06-17 | 0 | C | 0.333 | 0.2 | 0.3 | - | - | - | 83.3 | *83.30% Satisfactory
New TBP Construction & Development Corp. | 29155 | L | B | MA | GE2 | Const. of Cross Drainage Structures along MNR |  | 2008-11-25 | 1st | I |  | 4.417 | 120 |  |  |  | O | 0.344 | 0.12 | 0.1 | 0.02 | 0.042 | 0.133 | 75.9 | -
New TBP Construction & Development Corporation | 29155 | L | B | SB | GE2 | Construction of Cross Drainage Structures along MNR |  | 2009-08-25 | 2nd | I |  | 4.417 | 337 |  |  |  | O | 0.358 | 0.265 | 0.15 | 0.03 | 0.045 | 0.033 | 88.1 | -
New Vic Construction Corporation | 13779 |  | AAA |  |  | Construction of ER/Trauma Building Phase I | BRTTH, Legaspi, Region 5 | 2014-11-06 | 1st | DOH | L | 102.26 | 365 | 2014-02-14 | 2015-02-14 | 19.47 | O | 0.3965 | 0.2259 | 0.15 | 0.03 | 0.07 | 0.05 | 92.24 | -
Newadis Construction | 23806 | L | D | SB | GE1 | Road Upgrading (gravel to paved), MWCR, Calintaan-Sablayan (Bulangcog-Iriron Section) KO 276+468- KO 277+141 |  | 2009-08-31 | 2nd | IVB |  | 9.65 | 192 |  |  |  | O | 0.344 | 0.294 | 0.15 | 0.03 | 0.037 | 0.033 | 88.8 | -
Newadis Construction | 23806 | L | D | SB | GE1 | Road Upgrading (Gravel to Paved) MWCR, Calintaan-Sablayan (Bulangcog-Iriron Section) |  | 2009-05-30 | 1st | IV-B |  | 9.573 | 90 |  |  |  | O | 0.314 | 0.3 | 0.15 | 0.03 | 0.042 | 0.05 | 88.6 | -
Newadis Construction | 23806 |  |  |  |  | Const. of MPB Paluan NHS |  | 2010-05-24 |  | IVB |  | 1.44 | 100 |  |  |  | O | 0.356 | 0.24 | 0.15 | 0.03 | 0.029 | 0.033 | 83.8 | -
Newbig Four J Construction Inc. (Formerly: Four J Construction) | 15104 | L | AA | MA | GB1 | Completion of MPB at Philippine Drug Enforcement Agency (PDEA) Compound | Quezon City | 2011-04-07 | 1st | NCR | LF | 9.543 | 201 | 2010-09-20 | 2011-04-08 | 2.6 | O | 0.392 | 0.3 | 0.15 | 0.03 | 0.041 | 0.033 | 94.6 | -
Newbig Four J Construction Inc. (Formerly: Four J Construction) | 15104 |  |  |  |  | Const. of Municipal Hall |  | 2010-06-01 |  | IVA |  | 33.705 | 210 |  |  |  | O | 0.388 | 0.3 | 0.15 | 0.03 | 0.052 | 0.033 | 95.3 | -
Newbig Four J Construction Inc. (Formerly: Four J Construction) | 15104 | L | AA | MB | GE1 | Impvt./Widening of Gen. Emilio Aguinaldo Highway-Manila-Cavite Rd., IS inc. RROW, Km.17+512-Km.20+271 | Bacoor, Cavite | 2012-11-23 | 1st | IVA | LF | 43.649 | 381 | 2011-11-29 | 2012-12-13 | 2.08 | O | 0.345 | 0.3 | 0.15 | 0.03 | 0.044 | 0.033 | 90.2 | -
Newbig Four J Construction Inc. (Formerly: Four J Construction) | 15104 | L | AA | MB | GE1 | Asphalt Overlay of Mcdonald Jct.-Alido Bridge (Chainage 0000-Chainage 0375) inc. Drainage System (0+000-0+408) | Bacoor, Cavite | 2012-11-23 | 1st | IVA | LF | 5.259 | 364 | 2012-02-07 | 2013-02-04 | 16.96 | O | 0.344 | 0.3 | 0.15 | 0.023 | 0.051 | 0.033 | 90.1 | -
Newbig Four J Construction Inc. (Formerly: Four J Construction) | 15104 | L | AA | MB | GE1 | Widening of Molino-Bacoor Rd., K0014+800-K0016+986 | Bacoor, Cavite | 2012-11-24 | 1st | IVA | LF | 77.597 | 375 | 2012-03-07 | 2013-03-16 | 0.06 | O | 0.311 | 0.276 | 0.15 | 0.03 | 0.04 | 0.033 | 84 | -
NewBig Four J Construction, Inc. | 15104 |  |  |  |  | Const. of Municipal Hospital Building |  | 2010-03-01 |  | IVA |  | 33.705 | 210 |  |  |  | O | 0.337 | 0.3 | 0.15 | 0.03 | 0.05 | 0.033 | 90 | -
Newbig Four J Construction, Inc. (Formerly: Four J Construction) | 15104 | L | AAA | MB | GE1 | Impv't./Widening of Gen. Emilio Aguinaldo Highway-Manila-Cavite Road, Int. Sect. inc. RROW, Km.17+512-Km.20+271 | Bacoor, Cavite | 2013-08-14 | Final | IVA | LF | 47.395 | 381 | 2011-11-29 | 2012-12-13 | 0 | C | 0.344 | 0.2 | 0.3 | - | - | - | 84.4 | 84.88% Satisfactory
Newbig Four J Construction, Inc. (Formerly: Four J Construction) | 15104 | L | AAA | MB | GE1 | Asphalt Overlay of Mcdonald Jct.-Alido Bridge (Chainage 0000-Chainage 0375) inc. Drainage System (0+000-0+048) | Bacoor, Cavite | 2013-08-14 | Final | IVA | LF | 5.262 | 363 | 2012-02-07 | 2013-02-03 | 0 | C | 0.317 | 0.2 | 0.3 | - | - | - | 81.7 | 86.74% Satisfactory
Newbig Four J Construction, Inc. (Formerly: Four J Construction) | 15104 | L | AAA | MB | GE1 | Widening of Molino-Bacoor Rd., K0014+800-K0016+986 | Bacoor, Cavite | 2013-08-15 | Final | IVA | LF | 78.417 | 375 | 2012-03-07 | 2013-03-17 | 0 | C | 0.406 | 0.133 | 0.3 | - | - | - | 83.9 | 83.96% Satisfactory
Newbig Four J Construction, Inc. (Formerly: Four J Construction) | 15104 | L | AAA | MB | GE1 | Widening of Daang Maharlika, K0054+570-K0055+117 (w/ exception) | Calamba City | 2013-03-21 | Final | IVA | LF | 47.471 | 324 | 2012-02-10 | 2012-12-29 | 0 | C | 0.424 | 0.135 | 0.3 | - | - | - | 85.9 | 85.06% Satisfactory
Newington Builders, INC. | 17542 | L | AAA | LB | GE | Widening of Lipa-Rosario Road, Lipa City Section, Lipa City, Batangas, Km. 81+500 to Km. 82+700 (with exception) | Lipa City | 2014-08-08 | Final | IV-A | LF | 19.144 | 180 | 2013-01-21 | 2013-07-19 | 0 | C | 0.467 | 0.2 | 0.3 |  |  |  | 96.7 | 89.56% Very Satisfactory
Newington Builders, Inc. (Formerly: E. Gardiola Construction) | 17542 | L | AAA | LB | GE1 | Widening of Lipa-Rosario Rd., Lipa City Sect., (Km.81+500-Km.82+700 w/ exception) | Lipa City, Batangas | 2013-07-29 | 2nd | IVA | LF | 19.144 | 210 | 2013-01-21 | 2013-08-18 | -6.41 | O | 0.348 | 0.293 | 0.086 | 0.03 | 0.035 | 0.033 | 82.5
Newington Builders, Inc. (Formerly: E. Gardiola Construction) | 17542 | L | AAA | LB | GE1 | Const. of Lobo-Malabrigo-Laiya-San Juan Rd., Biga Sect. | Lobo, Batangas | 2013-08-03 | Final | IVA | LF | 43.649 | 278 | 2012-04-12 | 2013-01-14 | 0 | C | 0.467 | 0.188 | 0.3 | - | - | - | 95.5 | 95.08% V. Satisfactory
Newington Builders, Inc. (Formerly: E. Gardiola Construction) | 17542 | L | AAA | LB | GE1 | Const. of Lobo-Malabrigo-Laiya-San Juan Road, Biga Sect. | Lobo, Batangas | 2012-11-29 | 1st | IVA | LF | 43.65 | 248 | 2012-04-12 | 2012-12-16 | 0.03 | O | 0.393 | 0.3 | 0.15 | 0.03 | 0.042 | 0.033 | 94.8 | -
Newington Builders, Inc. (Formerly: E. Gardiola Construction) | 17542 | L | AAA | LB | GE1 | Widening of Lipa-Rosario Rd., Lipa City Sect., Km.81+500-Km.82+700 (w/ exception) | Lipa City, Batangas | 2013-03-11 | 1st | IVA | LF | 18.313 | 150 | 2013-01-21 | 2013-06-19 | 18.34 | O | 0.371 | 0.24 | 0.15 | 0.03 | 0.047 | 0.033 | 87.1 | -
NFH Construction & Supply |  |  |  |  | GE | Conctruction/Rehabilitation/Improvement of Ocampo Flood Control | Ocampo, Camarines Sur | 2014-08-08 | 1st | V | LF | 17.7693 | 191 | 2014-02-25 | 2014-09-03 | -10.43 | O | 0.342 | 0.3 | 0.046 | 0.02 | 0.047 | 0.033 | 78.8
NFH Construction & Supply | 16055 | L | AAA | LB | GE1 | Const. of Basag Bridge (Ligao-Sabloyon Road) |  | 2009-03-02 | 2nd | V |  | 23.78 | 487 |  |  |  | O | 0.335 | 0.239 | 0.15 | 0.03 | 0.061 | 0.05 | #VALUE! | -
NFH Construction & Supply | 16055 | L | AAA | LB | GE1 | Const. of Daguit 2 Bridge |  | 2009-03-13 | 3rd | V |  | 19.65 | 714 |  |  |  | O | 0.341 | 0.24 | 0 | 0.03 | 0.056 | 0.05 | #VALUE! | -
NFH Construction & Supply | 16055 | L | AAA | LB | GE1 | Const. of Daguit 2 Bridge |  | 2008-08-28 | 2nd | V |  | 19.65 | 330 |  |  |  | O | 0.342 | 0.3 | 0.07 | 0.03 | 0.028 | 0.067 | 83.7 | -
NFH Construction & Supply (Formerly: NFH Gravel & Sand) | 16055 | L | AAA | LB | GE1 | Mataoroc Bridge along Milaor-Minalabac-Pili Rd. Sect. | Minalabac, Camarines Sur | 2013-03-21 | Final | V | LF | 15.57 | 320 | 2013-01-23 | 2012-12-07 | 1 | C | 0.392 | 0.192 | 0.3 | - | - | - | 88.4 | 88.76% Satisfactory
NFH Construction & Supply (Formerly: NFH Gravel & Sand) | 16055 | L | AAA | LB | GE1 | Rehab. of Daang Maharlika, K0443+(-420)-K0446+724.36 Intermittent Sect. | Pili, Camarines Sur | 2013-03-22 | Final | V | LF | 23.449 | 139 | 2012-05-07 | 2012-09-23 | 0 | C | 0.394 | 0.186 | 0.3 | - | - | - | 88 | 86.92% Satisfactory
NFH Construction & Supply (Formerly: NFH Gravel & Sand) | 16055 | L | AAA | LB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads along Rolando Andaya Highway | K0327+000-K0328+917, Camarines Sur | 2014-11-09 | 1st & Final | V | LF | 26.5948 | 122 | 2014-03-18 | 2014-07-17 | 1.11% | C | 0.415 | 0.133 | 0.3 | - | - | - | 84.8% | 84.8% Satisfactory
NFH Construction & Supply (Formerly: NFH Gravel and Sand) | 16055 | L | AAA | LB | GE1 | Rehab./Reconst. of Damaged National Road, Lakandula Drive |  | 2009-05-27 | 1st | V |  | 32.61 | 120 |  |  |  | O | 0.343 | 0.24 | 0.15 | 0.023 | 0.035 | 0.05 | 84.1 | -
NFH Construction & Supply (Formerly: NFH Gravel and Sand) | 16055 | L | AAA | LB | GE1 | Widening/Impv't. of Rds. Cabrera-Kayticling-Antipolo Rd., Km.29+100-Km.30+400 (w/ exception) (Four Lanes) | Antipolo City | 2013-03-22 | Final | IVA | LF | 38.618 | 328 | 2012-02-06 | 2012-12-30 | 1 | C | 0.436 | 0.133 | 0.3 | - | - | - | 86.9 | 88.10% Satisfactory
NGP Construction | 11369 | L | B |  |  | Repainting of Building Facades and Various Re-waterproofing Works | BSP Cebu Regional Office | 2014-03-06 | 1st & Final | BPS | LF | 7.247 | 69 | 2013-09-23 | 2013-11-30 | 0 | C | 0.479 | 0.2 | 0.3 | - | - | - | 97.9 | *97.90% Outstanding
NGP Construction | 11369 |  | B |  |  | Re-Waterproofing of Roof Deck Area | BSP Tacloban Branch Office | 2014-10-23 | 1st & Final | BSP | LF | 1.191 | 30 | 2014-05-26 | 2014-06-25 | 0 | C | 0.459 | 0.2 | 0.3 | - | - | - | 95.9 | *95.90% V. Satisfactory
NGP Construction | 11369 | L | B | MA | GB | Initao-Libertad Landscape and Seascape Development | Initao-Libertad, Misamis Oriental | 2015-02-26 | Final | TIEZA | LF | 8 | 240 | 2011-02-18 | 2015-01-08 |  | C | 0.325 | 0.184 | 0.3 |  |  |  | 80.9 | 87.3 Satisfactory
NGP Construction | 11369 | L | B | MA | GB | Initao-Libertad Protected Landscape & Seascape Dev't. Project | Initao-Libertad, Misamis Oriental | 2014-06-19 | 1st | TIEZA | LF | 7.265 | 150 | 2011-02-18 | 7/19/201 | 0 | S | 0.337 | 0.263 | 0.15 | 0.03 | 0.07 | 0.05 | 90.02
NGP Construction | 11369 | L | B |  |  | Replacement of Damaged Roofing and Wall Cladding Systems at BSP Roxas Branch Office | Roxas City | 2014-10-20 | Final | BSP | L | 5.068 | 137 | 2014-06-05 | 2014-10-18 | 0 | C | 0.461 | 0.2 | 0.3 | - | - | - | 96.1 | 95.82% V. Satisfactory
NGP Construction | 11369 | L | B |  |  | Replacement of Damaged Roofing and Wall Cladding Systems at BSP Tacloban Branch Office | Tacloban City | 2014-10-23 | Final | BSP | L | 5.202 | 137 | 2014-06-04 | 2014-10-18 | 0 | C | 0.435 | 0.2 | 0.3 | - | - | - | 93.5 | 95.79% V. Satisfactory
Nirvana Construction and Supplies | 18691 | L | A | MA | GE | Rehabilitation/Reconstruction/Replacement of Existing Permanent Bridges, Molok Bridge along Makar-Marbel Road, Brgy. Labangal | General Santos City | 2014-08-16 | 1st & Final | XII | LF | 7.7697 | 68 | 2014-01-26 | 2014-04-04 | 3.44 | C | 0.488 | 0.133 | 0.3 |  |  |  | 92.1 | 92.10% Very Satisfactory
Nirvana Construction and Supplies | 18691 | L |  |  |  | Kidapawan City Resettlement Project/ LGU PABAHAY | Brgy. Magsaysay, Kidapawan City | 2015-03-29 | Final | NHA | L | 23.926 | 345 | 2014-11-05 | 2015-03-18 | 0 | C | 0.4333 | 0.2 | 0.3 | - | - | - | 93.33 | 89.09% V. Satisfactory
Nirvana Construction and Supplies | 18691 | L |  |  |  | Kidapawan City Resettlement Project/ LGU PABAHAY | Brgy. Magsaysay, Kidapawan City | 2015-01-09 | 2nd | NHA | L | 23.93 | 345 | 2013-11-10 | 2015-02-09 | 0.06 | O | 0.3401 | 0.3 | 0.15 | 0.03 | 0.033 | 0.05 | 90.31 | -
Nirvana Construction and Supplies | 18691 | L |  |  |  | Kidapawan City Resettlement Project/ LGU Pabahay | Brgy. Magsaysay, Kidapawan City | 2014-06-13 | 1st | NHA | LF | 23.93 | 345 | 2013-11-09 | 2014-11-07 | -6.37 | O | 0.3266 | 0.3 | 0.0863 | 0.03 | 0.042 | 0.033 | 81.79 | -
Nirvana Construction and Supplies | 18691 |  |  |  |  | Sarangani-Davao del Sur Coastal Road (Burias Section) |  | 2010-06-16 |  | XII |  | 9.394 | 150 |  |  |  | O | 0.316 | 0.237 | 0.15 | 0.03 | 0.047 | 0.05 | 83 | -
NIRVANA CONSTRUCTION AND SUPPLIES | 18691 | L | A | SB | GB | Construction of Multi-Purpose Building- Brgy. Baliton | Glan, Sarangani Province | 2015-06-11 | Final | Sarangani DEO | LF | 2.926 | 90 | 2014-10-28 | 2015-01-25 | 0% | C | 0.451 | 0.133 | 0.3 | - | - | - | 88.4% | *88.4% Satisfactory
NIRVANA CONSTRUCTION AND SUPPLIES | 18691 | L | A | SB | GE | Local Infrastructure Program: Construction of Multi-Purpose Building (Production Center) | Poblacion, T' Boli, South Cotabato | 2015-09-02 | 1st | South Cotabato | LF | 4.933 | 150 | 2015-05-20 | 2015-10-16 | (+)0.03% | O | 0.4 | 0.24 | 0.15 | 0.03 | 0.052 | 0.05 | 92.2% | -
Norielle Construction | 31300 | L | C | SB | GE | Construction of Junction National Highway Sta. Rita Road | Sta. Rita, Samar | 2014-10-25 | 1st & Final | VIII | LF | 4.6185 | 45 | 2014-06-13 | 2014-07-27 | 4.44% | C | 0.408 | 0.133 | 0.3 | - | - | - | 84.1% | 84.1% Satisfactory
Norm Construction | 13754 |  |  |  |  | Const. of MPB at DENR |  | 2010-06-07 |  | VII |  | 1.446 | 169 |  |  |  | O | 0.262 | 0.296 | 0.138 | 0.03 | 0.041 | 0.033 | 80 | -
Norsam Builders & Construction Supply | 21184 | L | B | MA | GE | Construction and Maintenace of Bridge along National Road, Rehabilitation/Reconstruction/Replacement/Retrofitting of Existing Permanent Bridges, Pambuian Bridge along Catarman-Laoang Road | Pambujan, Northern Samar | 2014-10-20 | 1st & Final | VIII | LF | 3.7901 | 82 | 2014-02-28 | 2014-05-20 | -13.42% | C | 0.491 | 0.132 | 0 | - | - | - | 62.3% | 62.3% Poor
Norsam Builders & Construction Supply | 21184 | L | B | MA | GE | Concreting/Upgrading of Gaps along Lapinig Arteche Road Lapinig - Imelda Section KO853+114.50 - KO854+210 | Lapinig, Northern Samar | 2014-08-12 | 1st & Final | VIII | LF | 25.556 | 232 | 2013-02-06 | 2013-06-02 | 0 | C | 0.41 | 0.133 | 0.3 |  |  |  | 84.3 | 84.30% Satisfactory
Norsam Builders & Construction Supply | 21184 | L | B | MA | GE1 | Conc./Upgrading of Gaps along Lapinig-Arteche Rd., Lapinig-Imelda Sect., K0853+114.50-K0854+210 | Lapinig, Northern Samar | 2013-08-06 | 1st | VIII | LF | 25.566 | 262 | 2013-02-06 | 2013-10-25 | 52.39 | O | 0.339 | 0.239 | 0.15 | 0.03 | 0.06 | 0.033 | 85.1
Norsam Builders & Construction Supply | 21184 |  |  |  |  | Rehab./Upgrading of Catarman Diversion Rd. II |  | 2010-06-14 |  | VIII |  | 7.518 | 100 |  |  |  | O | 0.363 | 0.24 | 0.15 | 0.03 | 0.037 | 0.033 | 85.3 | -
Norsam Builders & Construction Supply | 21184 | L | C | SB | GE2 | Macagtas IS |  | 7/6-10/09 | 1st | NIA |  | 4.559 | 240 |  |  |  | O | 0.3631 | 0.24 | 0.15 | 0.03 | 0.063 | 0.05 | 89.61 | -
Norsam Builders & Construction Supply | 21184 | L | C | SB | GE2 | San Miguel CIS |  | 7/6-10/09 | 1st | NIA |  | 4.005 | 150 |  |  |  | O | 0.3647 | 0.24 | 0.15 | 0.03 | 0.063 | 0.05 | 89.77 | -
Norsam Builders & Construction Supply | 21184 | L |  | SB | GE2 | Help for Catubig Agricultural Advancement Project HCAAP-LMC-C-4 | Catubig Service Area/Region 8 | 2014-03-15 | Final | NIA | LF | 9.889 | 403 | 2011-07-04 | 2012-08-10 | 0 | C | 0.44 | 0.104 | 0.3 | - | - | - | 84.4 | 84.40% Satisfactory
Norsam Builders & Construction Supply/ESD Cruz Construction & Supply ( JV) | JV-13-280 | L | B | SB | GE | Construction/Rehabilitation of Slope Protection, Bantayan River Control along Catarman-Laoang Road, K0767+878 - K0767+960 | Brgy. Bantayan, San Roque, Northern Samar | 2014-10-20 | 1st & Final | VIII | LF | 13.0736 | 120 | 2014-03-20 | 2014-07-17 | 28.22% | C | 0.457 | 0.133 | 0.3 | - | - | - | 89% | 89% Satisfactory
Northern / DMJ Construction (JV) | JV-08-115 | L | AAA | LB | GE1 | Construction of Baler-Casiguan Road CP3 |  | 2009-03-06 | 1st | III |  | 505.307 | 450 |  |  |  | O | 0.394 | 0.3 | 0.15 | 0.03 | 0.033 | 0.033 | #VALUE! | -
Northern / Z M Construction (JV) | JV-08-275 | L | AAA | LB | GE1 | Const. (Road Opening) of Lubao By-Pass Road of San Fernando-Olongapo Road inc. RROW |  | 2009-05-19 | 1st | III |  | 135.3958 | 180 |  |  |  | O | 0.318 | 0.272 | 0.15 | 0.03 | 0.051 | 0.05 | 87.1 | -
Northern / ZM Construction (JV) | JV-07-148 | L | AAA | LB | GE1 | Tarlac-Nueva Ecija-Dingalan Port Road, Sta. Rosa-Jct. Fort Magsaysay Road (Phase 2) & Gabaldon-Dingalan Road (Phase 3) |  | 2009-03-04 | 1st | III |  | 238.983 | 300 |  |  |  | O | 0.367 | 0.3 | 0.15 | 0.03 | 0.032 | 0.05 | #VALUE! | -
Northern Builders | 8789 | L | AAA | LB | GE1 | Widening/Conc. of R-10, (Bangkulasi Bridge inc. Approaches crossing Bangkulasi River) | Navotas City, Metro Manila | 2013-03-23 | Final | NCR | LF | 88.986 | 480 | 2011-09-03 | 2012-12-25 | 0 | C | 0.455 | 0.135 | 0.3 | - | - | - | 89 | 92.36% V. Satisfactory
Northern Builders | 8789 | L | AAA | LB | GE1 | Widening/Conc. of R-10 (Bangkulasi Bridge inc. approaches crossing Bangkulasi River) | Navotas City, Metro Manila | 2012-11-24 | 1st | NCR | LF | 89.051 | 480 | 2011-09-03 | 2012-12-25 | 2.53 | O | 0.352 | 0.299 | 0.15 | 0.03 | 0.065 | 0.05 | 94.6
Northern Builders | 8789 | L | AAA | LB | GE | Construction/Rehabilitation of Drainage System of Blumentritt Interceptor Catchment Area, Manila 4th | Manila 4th district | 2014-08-15 | 1st & Final | NCR | LF | 42.6459 | 300 | 2013-01-04 | 2014-07-30 | 0 | C | 0.497 | 0.133 | 0.3 |  |  |  | 93 | 93.00% Very Satisfactory
Northern Builders | 8789 |  |  |  |  | Urgent Rehab. Works due to the Passage of Typhoon "Pepeng" in the Province of Pangasinan under the Agno River Control Project |  | 2010-06-11 |  | AFCS |  | 5.79 | 45 |  |  |  | O | 0.353 | 0.24 | 0.15 | 0.03 | 0.047 | 0.05 | 87 | -
Northern Builders | 8789 | L | AAA | LA | GE1 | Widening/Conc. of Bontoc-Banaue Road, Talubin-Samoki Section Bontoc, Km. 376+911-Km.385+000 (intermittent Section) |  | 2009-08-30 | 1st | CAR |  | 120.619 | 450 |  |  |  | O | 0.365 | 0.24 | 0.087 | 0.03 | 0.056 | 0.017 | 79.5 | -
Northern Builders | 8789 | L | AAA | LB | GE | Preventive Maintenance Based on Pavement Management System/Highway Development & Management (HDM-4) Intermittent Section National Arterial Roads, Daang Maharlika, Alicia & Cauayan | Isabela | 2014-08-10 | 1st | II | LF | 87.8793 | 130 | 2014-04-28 | 2014-09-04 | -3.82 | O | 0.374 | 0.3 | 0.112 | 0.03 | 0.045 | 0.033 | 89.4
Northern Builders | 8789 | L | AAA | LB | GE | Widening/Improvement of Nambang-Kasibu-Solano Road including Drainage (Bambang-Kasibu Section) | Bambang, Nueva Vizcaya | 2014-08-14 | Final | II | LF | 42.3756 | 216 | 2013-02-04 | 2013-09-07 | 0 | C | 0.452 | 0.133 | 0.3 |  |  |  | 88.5 | 88.05% Satisfactory
Northern Builders | 8789 | L | AAA | LB | GE1 | Widening/Impv't. of Bambang-Kasibu-Solano Rd. inc. Drainage (Bambang-Kasibu Sect.) | Bambang, Nueva Vizcaya | 2013-08-14 | 2nd | II | LF | 41.677 | 209 | 2013-02-04 | 2013-08-31 | 0.97 | O | 0.353 | 0.24 | 0.15 | 0.03 | 0.055 | 0.033 | 86.1
Northern Builders | 8789 | L | AAA | LB | GE1 | Widening/Impv't. of Bambang-Kasibu Rd. inc. Drainage (Bambang-Kasibu Sect.) | Bambang, Nueva Vizcaya | 2013-03-20 | 1st | II | LF | 41.677 | 180 | 2013-02-04 | 2013-08-02 | 3.57 | O | 0.39 | 0.24 | 0.15 | 0.03 | 0.051 | 0.033 | 89.4 | -
Northern Builders | 8789 | L | AAA | LB | GE1 | Road Upgrading (Gravel to Paved) Aritao-Quirino Road, a)K0272+358.6-K0272+580.696; b)0273+188.85-K0274+(-445.5); c)K0274+247.52-K0276+(-491.08); d)K0276+126.31-K0278+817.04 | Kasibu, Nueva Vizcaya | 2013-03-20 | 1st | II | LF | 98.68 | 269 | 2013-02-18 | 2013-11-13 | 7.88 | O | 0.383 | 0.246 | 0.15 | 0.03 | 0.047 | 0.033 | 88.9 | -
Northern Builders | 8789 | L | AAA | LB | GE1 | Concrete Paving/Impvt. of Jct. National Road, Bitnong-Belance, Nueva Vizcaya Boundary Road |  | 2009-06-01 | 2nd | II |  | 125.42 | 540 |  |  |  | O | 0.347 | 0.3 | 0.15 | 0.03 | 0.051 | 0.05 | 92.8 | -
Northern Builders | 8789 | L | AAA | LB | GE1 | Concrete Paving/Impv't of Jct. National Road, Bitnong-Belance, Nueva Vizcaya Bdry. Road |  | 2009-03-10 | 1st | II |  | 125.412 | 540 |  |  |  | O | 0.354 | 0.3 | 0.15 | 0.03 | 0.045 | 0.05 | #VALUE! | -
Northern Builders | 8789 | L | AAA | LB | GE | Completion of Moncada-Paniqui Road | Paniqui, Tarlac | 2014-11-20 | 1st & Final | III | LF | 18.6137 | 160 | 2014-02-12 | 2014-07-21 | 0% | C | 0.362 | 0.17 | 0.3 | - | - | - | 83.2% | 83.2% Satisfactory
Northern Builders | 8789 | L | AAA | LB | GE | Rehabilitation/Reconstruction of Damaged Paved National Roads including Drainage at Capas - San Jose - Mayantoc - Malacampa Road, KO118+874 to KO120+498 with exception | Capas, Tarlac | 2014-11-20 | 1st & Final | III | LF | 19.4105 | 80 | 2014-03-20 | 2014-06-07 | 0% | C | 0.444 | 0.133 | 0.3 | - | - | - | 87.7% | 87.7% Satisfactory
Northern Builders | 8789 | L | AAA | LB | GE | Rehab./Reconst. Of Damaged Paved National Roads including Drainage at Capas - San Jose Mayantoc - Malacampa Road, K0118+874 to K0120+498 with exception | Capas, Tarlac | 2014-08-05 | 1st & Final | III | LF | 19.4105 | 8789 | 2014-03-27 | 2014-06-14 | 0 | C | 0.419 | 0.133 | 0.3 |  |  |  | 85.2 | 85.20% Satisfactory
Northern Builders | 8789 | L | AAA | LB | GE | Const./Rehab./ of various Projects in Tarlac 1st LD (Const./Rehab. Of Anao - Ramos Road with Bridge Component, Anao Section, Anao, Tarlac) | Anao, Tarlac | 2014-08-06 | 1st | III | LF | 46.5442 | 265 | 2014-04-04 | 2014-12-23 | 4.08 | O | 0.391 | 0.231 | 0.15 | 0.024 | 0.06 | 0.033 | 88.9
Northern Builders | 8789 | L | AAA | LB | GE1 | Conc. of Baras-Baras-Mapalad Road | Tarlac City | 2013-08-07 | Final | III | LF | 21.341 | 187 | 2012-12-06 | 2013-06-10 | 1.61 | C | 0.437 | 0.133 | 0.3 | - | - | - | 87 | 86.64% Satisfactory
Northern Builders | 8789 |  |  |  |  | Widening/Conc. of Manila North Road (MNR), Tarlac province Phase VI (Package II), Tarlac 2nd Congressional District, Tarlac City & Gerona Sect. |  | 2010-06-03 |  | III |  | 123.01 | 210 |  |  |  | O | 0.384 | 0.268 | 0.15 | 0.03 | 0.048 | 0.033 | 91.3 | -
Northern Builders | 8789 | L | AAA | LB | GE1 | Const. of Tarlac-Nueva Ecija-Dingalan Port Road (Jct. Fort Magsaysay-Laur Section) Contract Package 3 |  | 2009-05-30 | 1st | III |  | 299.894 | 360 |  |  |  | O | 0.337 | 0.3 | 0.15 | 0.03 | 0.042 | 0.05 | 90.9 | -
Northern Builders | 8789 | L | AAA | LB | GE1 | Const. of Tarlac-Nueva Ecija-Dingalan Port Road (Jct. Fort Magsaysay-Laur Section) CP 3 |  | 2009-09-07 | 2nd | III |  | 299.894 | 360 |  |  |  | O | 0.379 | 0.3 | 0.15 | 0.03 | 0.05 | 0.033 | 94.2 | -
Northern Builders | 8789 | L | AAA | LB | GE1 | Asphalt Overlay of City of San Fernando-GSO Rd., Const. of Pedestrian Overpass & Installation of 3 Traffic Lights | Pampanga | 2012-11-21 | 2nd | III | LF | 62.518 | 240 | 2012-01-04 | 2012-09-29 | 0.67 | O | 0.35 | 0.3 | 0.15 | 0.03 | 0.031 | 0.05 | 91.1 | -
Northern Builders | 8789 | L | AAA | LB | GE1 | Asphalt Overlay of City of San Fernando-GSO Rd., Const. of Pedestrian Overpass & Installation of 3 Traffic Lights | Pampanga | 2012-08-16 | 1st | III | LF | 62.518 | 240 | 2012-01-04 | 2012-08-30 | 1.03 | O | 0.34 | 0.215 | 0.15 | 0.03 | 0.047 | 0.05 | 83.2 | -
Northern Builders | 8789 | L | AAA | LB | GE1 | Conc. of Rd. @ Quezon to New Salem Rd. | Gerona, Tarlac | 2012-11-24 | 1st | III | LF | 7.891 | 97 | 2012-09-17 | 2012-12-22 | 1.8 | O | 0.352 | 0.282 | 0.15 | 0.03 | 0.05 | 0.033 | 89.7 | -
Northern Builders | 8789 | L | AAA | LB | GE1 | Reconst. of New Ibajay Bridge | El Nido, Palawan | 2012-08-04 | 2nd | IVB | LF | 12.819 | 325 | 2011-11-03 | 2012-09-22 | -0.09 | O | 0.332 | 0.263 | 0.149 | 0.03 | 0.035 | 0.05 | 85.9 | -
Northern Builders | 8789 | L | AAA | LB | GE2 | Construction of Togbongon River Control |  | 2009-03-10 | 1st | XIII |  | 9.585 | 149 |  |  |  | O | 0.3 | 0.3 | 0.15 | 0.03 | 0.033 | 0.05 | #VALUE! | -
NORTHERN BUILDERS | 8789 | L | AAA | LB | GE | Construction of Flood Control Drainage Structure (Drainage Canal) Pennsylvania Avenue-Mabini St., Catbanagan | San Fernando, La Union | 2015-06-06 | 1st | La Union 1st DEO | LF | 18.581 | 195 | 2015-02-07 | 2015-08-20 | 3.82% | O | 0.353 | 0.24 | 0.15 | 0.03 | 0.045 | 0.033 | 85.1% | -
NORTHERN BUILDERS | 8789 | L | AAA | LB | GE | Construction of Slope Protection and Desilting of Creek along C-6, Brgy. New Lower Bicutan, Taguig City | Brgy. New Lower Bicutan, Taguig City | 2015-06-04 | Final | Metro Manila 1st DEO | LF | 17.369 | 180 | 2015-02-18 | 2015-08-16 | (+) 47.22 | C | 0.443 | 0.133 | 0.3 | - | - | - | 87.6% | *87.6% Satisfactory
NORTHERN BUILDERS | 8789 | L | AAA | LB | GE | Construction of Slope Protection with Gabions as Foundation along Labasan River, Brgy. Napindan, Taguig City | Brgy. Napindan, Taguig City | 2015-06-04 | Final | Metro Manila 1st DEO | LF | 17.367 | 180 | 2015-02-18 | 2015-08-16 | (+) 47.22 | C | 0.431 | 0.133 | 0.3 | - | - | - | 86.4% | *86.4% Satisfactory
NORTHERN BUILDERS | 8789 | L | AAA | LB | GE | Construction of Slope Protection and Desilting of Creek at Barangay Hagonoy, Taguig City | Barangay Hagonoy, Taguig City | 2015-08-27 | 1st & Final | MM 1st DEO | LF | 17.368 | 210 | 2015-02-18 | 2015-09-15 | 31.11% | C | 0.436 | 0.133 | 0.3 | - | - | - | 86.9% | *86.9% Satisfactory
NORTHERN BUILDERS | 8789 | L | AAA | LB | GE | Construction of Camiling River Control (Phase II), Brgy. Libueg Section, Camiling, Tarlac | Camiling, Tarlac | 2015-09-03 | 1st | Tarlac First DEO | LF | 42.116 | 215 | 2015-06-23 | 2016-01-23 | 17.8% | O | 0.306 | 0.24 | 0.15 | 0.03 | 0.07 | 0.05 | 84.6% | -
NORTHERN BUILDERS | 8789 | L | AAA | LB | GE | Network Development-Widening of National Roads-Arterial Roads, Roman Expressway, 1st Legislative District, 101+(-749.00) - 104+275.00, Hermosa, Bataan | Hermosa, Bataan | 2015-11-12 | 1st | Regional Office | LF | 71.531 | 240 | 2015-07-16 | 2016-03-11 | 2.04% | OG | 0.394 | 0.24 | 0.15 | 0.024 | 0.061 | 0.05 | 91.9% | 91.9% Very Satisfactory
Northern Builders / Ferdstar Builders Contractors (JV) | JV-07-118 | L | AAA | LB | GE1 | Rehab/Reconst. of Tulaoc-Sto. Domingo Road, Mexico Section |  | 2009-02-24 | 1st | III |  | 96.425 | 300 |  |  |  | O | 0.337 | 0.281 | 0.15 | 0.03 | 0.047 | 0.05 | #VALUE! | -
Northern Builders / New Big Four J Construction (JV) | JV-08-207 |  |  |  |  | Impvt./Conc. & Widening of Panglao Island Central Spur Rd. |  | 2010-06-03 |  | VII |  | 111.09 | 300 |  |  |  | O | 0.258 | 0.3 | 0 | 0.03 | 0.06 | 0.05 | 69.8 | -
Northern Builders / R.A. Pahati Gravel & Sand (JV) | JV-08-008 | L | AAA | LB | GE1 | Rehab/Impvt./Widening of Tarlac-Nueva Ecija-Dingalan Port Road, Phase I, Fort Magsaysay-Laur Road Section |  | 2009-03-04 | 1st | III |  | 223.075 | 300 |  |  |  | O | 0.388 | 0.3 | 0.15 | 0.022 | 0.032 | 0.05 | #VALUE! | -
Northern Builders/Ferdstar Builders Contractor Joint Venture | JV-07-143 | L | AAA | LB | GE1 | Completion/Continuation of Unfinished On-going Bridge: Anao Bridge along San Jose Malino-Anao Road |  | 2009-05-18 | 1st | III |  | 18.988 | 60 |  |  |  | O | 0.307 | 0.3 | 0.15 | 0.03 | 0.042 | 0.05 | 87.9 | -
Northern Builders/Ferdstar Builders Contractor Joint Venture | JV-07-118 | L | AAA | LB | GE1 | Rehab./Reconst. of Tulaoc Sto. Domingo Road, Mexico Sect. |  | 2009-05-18 | 2nd | III |  | 96.425 | 300 |  |  |  | O | 0.298 | 0.3 | 0.15 | 0.03 | 0.037 | 0.05 | 86.5 | -
Northern Builders/New Big Four J Const. Inc. (Joint Venture) | JV-08-207 | L | AAA | LB | GE1 | Imprv't/Conc./widening of Panglao center Spur Rd. Sta. 3+120-to Sta.3=500; Sta.3+700-Sta.5+200;Sta.5+540-Sta.6+200 |  | 2009-09-03 | 2nd | VII |  | 110.999 | 300 |  |  |  | O | 0.383 | 0.24 | 0.15 | 0.03 | 0.037 | 0.05 | 89 | -
Northern Builders/New Big Four J Const. Inc. (Joint Venture) | JV-08-207 | L | AAA | LB | GE1 | Imprv't./Conc. of Jct.(TER),Jagna-Sierra Bullones Rd. Km.86.283-Km86.800;Km.87.020-Km.87.380;Km87.540-Km.89.64550;Km.94.380-Km.95.680 |  | 2009-09-04 | 1st | VII |  | 87.718 | 270 |  |  |  | O | 0.329 | 0.24 | 0.15 | 0.03 | 0.037 | 0.05 | 83.6 | -
Northern Builders/New Big Four J Construction Inc. Joint Venture | JV-08-207 | L | AAA | LB | GE1 | Impvt./Conc./Widening of Panglao Center Spur Road, Sta. 3+120-Sta.3+500, Sta. 3+700-Sta. 5+200, Sta. 5+540-Sta. 6+200 |  | 2009-06-10 | 1st | VII |  | 110.999 | 300 |  |  |  | O | 0.358 | 0.3 | 0.15 | 0.03 | 0.047 | 0.05 | 93.5 | -
Northern/DMJ Construction Joint Venture | JV-08-115 | L | AAA | LB | GE1 | Construction of Baler-Casiguran Road (Contract Package 3) |  | 2009-05-28 | 2nd | III |  | 505.307 | 450 |  |  |  | O | 0.337 | 0.3 | 0.15 | 0.03 | 0.037 | 0.033 | 88.7 | -
Northern/ZM Construction Joint Venture | JV-08-275 | L | AAA | LB | GE1 | Const. of (Road Opening) of Lubao-By Pass Road of San Fernando-Olongapo Road inc. RROW |  | 2009-08-25 | 2nd | III |  | 135.396 | 180 |  |  |  | O | 0.336 | 0.3 | 0.15 | 0.03 | 0.051 | 0.033 | 90 | -
Novanne Ventures Construction Corporation (Formerly: Novanne Ventures Construction) | 22107 | L | D | SB | GE | Const. of Slope Protection along Bacolod South Road Km. 0182+618 (Bacuyangan Bridge Approaches), Brgy. Talacagay | Hinoba-an, Negros Occidental | 2014-08-08 | Final | VI | LF | 2.831 | 60 | 2013-06-13 | 2013-08-11 | 0 | C | 0.383 | 0.2 | 0.3 |  |  |  | 88.3 | 83.56% Satisfactory
Novanne Ventures Construction Corporation (Formerly: Novanne Ventures Construction) | 22107 | L | D | SB | GE2 | Const. of Slope Protection along Bacolod South Rd. Km.0182+618 (Bacuyangan Bridge Approaches), Brgy. Talacagay | Hinoba-an, Negros Occidental | 2013-08-09 | 1st | VI | LF | 2.831 | 60 | 2013-06-13 | 2013-08-11 | -1.38 | O | 0.342 | 0.225 | 0.136 | 0.03 | 0.038 | 0.033 | 80.4
NTL Builders & Developer | 33450 | L |  | SB |  | Completion of AcademicBLDG 2-III | Brgy. Masoc, Bayombong, Nueva Vizcaya | 2014-09-10 | Final | DOST | L | 12.106 | 303 | 2012-11-21 | 2013-09-20 | 0 | C | 0.47 | 0.2 | 0.3 | - | - | - | 97 | 97.14% Outstanding
NTL Builders & Developers | 33450 | L |  |  | GE2 | Dibuluan River Irrigation Project | San Agustin, Isabela / Region 2 | 2013-04-27 | Final | NIA | LF | 4.699 | 208 | 2012-04-20 | 2012-11-13 | 0 | C | 0.384 | 0.184 | 0.3 | - | - | - | 86.8 | 86.86% Satisfactory
NTL Builders & Developers | 33450 | L | B | SB | GB | Construction of Two Classroom School Building, Gamis E/S | Saguday, Quirino | 2014-10-28 | 1st & Final | II | LF | 1.9704 | 75 | 2014-07-23 | 2014-10-05 |  | C | 0.438 | 0.133 | 0.3 | - | - | - | 87.1% | 87.1% Satisfactory
NTL Builders and Developer | 33450 | L | B | SB | GB | Construction of Multi Purpose Building, Capitol Complex | Cabarroguis, Quirino | 2014-08-13 | Final | II | LF | 9.163 | 165 | 2013-04-10 | 2013-09-21 | 0 | C | 0.392 | 0.191 | 0.3 |  |  |  | 88.3 | 88.37% Satisfactory
NTL Builders and Developer | 33450 | L | B | SB | GB1 | Const. of MPB, Capitol Complex | Cabarroguis, Quirino | 2013-08-11 | 1st | II | LF | 8.783 | 150 | 2013-04-10 | 2013-09-06 | 3.66 | O | 0.384 | 0.24 | 0.15 | 0.03 | 0.047 | 0.033 | 88.4
NTL BUILDERS AND DEVELOPERS | 33450 | L | B | MA | GB | Construction/Completion of Multi-Purpose Building, Bannawag, Diffun, Quirino | Bannawag, Diffun, Quirino | 2015-08-30 | 1st & Final | Quirino DEO | LF | 2.383 | 60 | 2015-02-13 | 2015-04-13 | 2.45% | C | 0.468 | 0.133 | 0.3 | - | - | - | 90.1% | *90.1% Very Satisfactory
Nukaza Trading and Construction Services | 32067 |  |  |  |  | Const./Rehab./Completion of Flood Control Project at Brgy. Cupang |  | 2010-02-18 |  | NCR |  | 2.381 | 101 |  |  |  | O | 0.342 | 0.24 | 0.15 | 0.03 | 0.029 | 0.033 | 82.4 | -
Nurben Engineering and Building Contractor | 32432 | L | B | MA | GE | Development of Tourist Spots in Misamis Oriental | Jasaan, Misamis Oriental | 2015-06-30 | 1st | TIEZA | LF | 2.95 | 120 | 2015-03-31 | 2015-07-31 |  | O | 0.3505 | 0.2774 | 0.15 | 0.015 | 0.014 | 0.05 | 85.69
NURBEN ENGINEERING AND BUILDING CONTRACTOR | 32432 | L | B | MA | GE | Development of Tourist Spots in Misamis Oriental | Jasaan, Misamis Oriental | 2015-09-03 | Final | TIEZA | LF | 3 | 120 | 2015-03-31 | 2015-07-31 | 0 | C | 0.458 | 0.185 | 0.3 |  |  |  | 94.3 | 88.27% Satisfactory
NY Construction | 30388 | L |  | MA |  | Emergency Repair of Damaged Open Storage/Back-up Area, RoRo Ramps, Retaining Wall and Rock Bulkhead Caused by 7.2 Magnitude Earthquake on October 15, 2013 | Tubigon, Bohol/ Region VII | 2015-04-10 | 1st | PPA | L | 26.154 | 250 | 2014-10-01 | 2015-06-08 | 1.05 | O | 0.3505 | 0.2824 | 0.15 | 0.024 | 0.0642 | 0.05 | 92.11 | -
NY Construction and Supply | 30388 | L | B | MA |  | Repair of Damaged Slope Protection Structure | Port of Virac, Catanduanes.Region V | 2015-09-30 | 1st & Final | PPA | LF | 12.519 | 270 | 2014-12-24 | 2015-06-22 | 37.11 | C | 0.342 | 0.2 | 0.3 | - | - | - | 84.2 | *84.20% Satisfactory
NY Construction and Supply | 30388 |  |  |  |  | Construction and Supply for the Catbalogan Port Rehabilitation Project |  | 04/20-23/10 |  | PPA |  | 35.835 | 150 |  |  |  | O | 0.396 | 0.3 | 0.15 | 0.03 | 0.07 | 0.05 | 99.6 | -
NY Construction and Supply | 30388 | L |  | MA | GE5 | Concrete Paving of Reclaimed Area (open storage area) | Port of Tagbilaran, Tagbilaran City, Bohol | 2013-05-09 | 1st | PPA | LF | 19.002 | 315 | 2013-02-14 | 2013-12-25 | 20.605 | O | 0.3998 | 0.3 | 0.15 | 0.03 | 0.065 | 0.05 | 99.48 | -
O. G. SANTODS | 2050 | L | A | MA | GE | Road Upgrading (Unpaved to Paved) based on Gravel Road Strategies Traffic Benchmark for Upgrading to Paved Road Standards (HDM-4) (Project Analysis) Intermittent Section, Lanao-Pagadian-Zamboanga City Road, Zamboanga Del Sur, K1634+494.50-K1635+020; K1640+400-K1641+500 | Zamboanga Del Sur, | 2015-08-29 | 1st | Zamboanga del Sur 1st | LF | 43.618 | 165 | 2015-04-13 | 2015-09-24 | (+)10.00% | O | 0.319 | 0.2794 | 0.15 | 0.03 | 0.057 | 0.05 | 88.54% | -
O. G. Santos Construction |  | L |  |  |  | NHA-Pantukan Resettlement Project | Brgy. King-king, Pantukan, Compostela Valley | 2014-05-16 | Final | NHA | LF | 29.904 | 365 | 2012-06-14 | 2014-01-17 | 0 | C | 0.4941 | 0.2 | 0.3 | - | - | - | - | 99.41% Outstanding
O. G. Santos Construction and GP & H Construction & Supply (Joint Venture) | - | L |  |  |  | Road Upgrading of Cateel-Compostela Road (Davao Oriental Side) Cateel | Davao Oriental | 2014-10-29 | 1st & Final | XI | LF | 43.2575 | 135 | 2014-02-16 | 2014-06-30 |  | C | 0.218 | 0.197 | 0.3 | - | - | - | 71.5% | 71.5% Poor
O.G. Santos Construction | 2050 | L | A | MA | GE | Rehab/Reconst/Upgrading of Damaged National Road Including Drainage based on (PMS/HDM-4)(Intermittent Section) Lanao-Pagadian-Zamboanga City Road K1655+000 - K1657+000 | Pagadian City | 2014-10-27 | 1st & Final | IX | LF | 25.6747 | 165 | 2014-02-24 | 2014-08-07 | 0% | C | 0.34 | 0.2 | 0.3 | - | - | - | 84% | 84% Satisfactory
O.G. Santos Construction | 2050 | L | A | MA | GE1 | Road Upgrading (Gravel to Conc.) Int. Sect., Lanao-Pagadian-Zamboanga City Rd., K1638+500-K1640+000, Lantungan | Aurora, Zamboanga del Sur | 2013-03-20 | Final | IX | LF | 32.527 | 240 | 2012-02-28 | 2012-10-25 | 0 | C | 0.445 | 0.174 | 0.3 | - | - | - | 91.9 | 83.44% Satisfactory
O.G. Santos Construction | 2050 | L | A | MA | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Road Digos-Makar Road: Km. 1586+600 - Km. 1588+472 | Davao del Sur | 2014-10-22 | 1st | XI | LF | 31.3847 | 180 | 2014-02-24 | 2014-08-22 |  | O | 0.026 | 0.202 | 0.104 | 0.018 | 0.035 | 0.017 | 40.2% | 40.2% Poor
O.G. Santos Construction | 2050 | L | A | SB | GE | Construction of River Protection | Manay, Davao Oriental | 2014-10-28 | 1st & Final | XI | LF | 4.6059 | 88 | 2014-02-16 | 2014-05-14 | 2.49% | C | 0.4 | 0.15 | 0.3 | - | - | - | 85% | 85% Satisfactory
O.G. Santos Construction | 2050 | L | A | SB | GE | GAA Widening of Tagum-Panabo Circumferencial Road, Davao del Norte 2nd LD Panabo City to St. Tomas Section K1496+714 – K1497+666, Menzi Section (Widening of Tagum-Panabo Circumferencial Road, K1496+714 – K1497+685 Menzi Section, Sto. Tomas | Davao del Norte | 2014-08-09 | 1st & Final | XI | LF | 18.2954 | 102 | 2014-02-03 | 2014-05-15 | 0 | C | 0.342 | 0.2 | 0.3 |  |  |  | 84.2 | 84.20% Satisfactory
O.G. Santos Construction | 2050 | L | A | SB | GE | Construction of Mahan-Ub River Protection along Surigao-Davao, Manay, Davao Oriental | Davao Oriental | 2014-08-16 | Final | XI | LF | 6.8245 | 153 | 2013-06-11 | 2013-11-10 | 0 | C | 0.339 | 0.2 | 0.3 |  |  |  | 83.9 | 83.6% Satisfactory
O.G. Santos Construction | 2050 | L | A | SB | GE2 | Const. of Mahan-ub River Protection along Surigao-Davao Coastal Rd., Brgy. Central | Manay, Davao Oriental | 2013-08-17 | 1st | XI | LF | 6.824 | 153 | 2013-06-11 | 2013-11-10 | 17.91 | O | 0.296 | 0.3 | 0.15 | 0.03 | 0.025 | 0.033 | 83.4
O.G. Santos Construction | 2050 | L | A | MA | GE1 | Road Upgrading (Gravel to Paved) Int. Sect., Fatima-Malabog Rd.: a)Km.1503+400-Km.1503+961 b)Km.1506+541-Km.1507+470.98 | Davao City | 2013-08-20 | 1st | XI | LF | 34.731 | 140 | 2013-03-18 | 2013-08-04 | 0.69 | O | 0.377 | 0.271 | 0.15 | 0.03 | 0.035 | 0.05 | 91.3
O.G. Santos Construction | 2050 | L | A | MA | GB1 | Const. of two (2) Storey Sixteen (16) Cl & one (1) Storey Eight (8) Cl Sch. Bldg. @ New Corella NHS | New Corella, Davao del Norte | 2013-08-12 | 1st | XI | LF | 28.497 | 225 | 2013-03-27 | 2013-11-06 | 0.1 | O | 0.363 | 0.225 | 0.15 | 0.03 | 0.03 | 0.05 | 84.8
O.G. Santos Construction | 2050 | L | A | MA | GE1 | Rd. Slip along Malalag-Malita-JAS-Glan Rd., Malalag | Sta. Maria, Davao del Sur | 2013-03-13 | 1st | XI | LF | 29.091 | 212 | 2012-11-06 | 2013-06-05 | 9.43 | O | 0.32 | 0.186 | 0.15 | 0.03 | 0.03 | 0.033 | 74.9 | -
O.G. Santos Construction | 2050 | L | A | SB | GE2 | Const. of Buhangin Flood Control, Malalag-Malita JAS, Brgy. Buhangin | Malita, Davao del Sur | 2013-03-15 | 1st | XI | LF | 4.994 | 98 | 2012-12-26 | 2013-04-03 | 3.8 | O | 0.2 | 0.148 | 0.15 | 0.01 | 0.03 | 0.05 | 58.8 | -
O.G. Santos Construction | 2050 | L | A | MA | GE1 | Road Upgrading (Gravel to Paved) Demoloc-Little Baguio-Alabel Rd., Bolila-Sanghay, Malita Km.1646+620-Km.1647+680 | Davao del Sur | 2012-03-21 | 1st | XI | LF | 33.238 | 140 | 2012-02-07 | 2012-06-25 | 2.99 | O | 0.399 | 0.275 | 0.15 | 0.02 | 0.037 | 0.05 | 93.1 | -
O.G. Santos Construction | 2050 | L | A | MA | GE1 | (Rd. Slip) Surigao-Davao Coastal Rd., Bislig-Lingig Rd. Sect., Mangagoy & Lingig, Km.1467+680-Km.1467+780, (Km.1467+430-Km.1467+765) | Surigao del Sur | 2013-03-17 | 1st | XIII | LF | 25.968 | 285 | 2012-08-17 | 2013-05-28 | -10.8 | O | 0.342 | 0.3 | 0.042 | 0.03 | 0.028 | 0.017 | 75.9 | -
O.G. Santos Construction |  | L |  |  |  | NHA-Pantukan Resettlement Project | Brgy. King-king, Pantukan, Compostela Valley | 2014-05-16 | Final | NHA | LF | 29.904 | 365 | 2012-06-14 | 2014-01-17 |  | C | 0.4941 | 0.2 | 0.3 |  |  |  | 99.41
O.G. SANTOS CONSTRUCTION | 2050 | L | A | MA | GE | Ising Bridge (B00018MN) along Daang Maharlika (MN) (Widening of Permanent Bridge, Ising Bridge (B00018MN) along Daang Maharlika (MN) | Carmen, Davao del Norte | 2015-06-10 | 1st | Davao del Norte | LF | 32.287 | 166 | 2015-02-05 | 2015-07-20 | (+)4.05% | O | 0.331 | 0.24 | 0.15 | 0.03 | 0.042 | 0.033 | 82.6% | -
O.G. SANTOS CONSTRUCTION | 2050 | L | A | MA | GE | Road Upgrading (Unpaved to Paved) Based on Gravel Road Strategies, Traffic Project Analysis Benchmark for Upgrading to Paved Road Standards (HDM-4), Intermittent Sections, Lanao-Pagadian-Zamboanga City Road, K1634+494.50-K1635+020;K1640+400-K1641+500, Tukuran, Zamboanga del Sur | Tukuran, Zamboanga del Sur | 2015-11-13 | 2nd | Zamboanga Del Sur 1st DEO | LF | 43.6177 | 135 | 2015-04-13 | 2015-08-25 | 0.13% | OG | 0.332 | 0.298 | 0.15 | 0.02 | 0.037 | 0.05 | 88.7% | 88.7% Satisfactory
O.G. SANTOS CONSTRUCTION | 2050 | L | A | SA | GE | Ising Bridge along Daang Maharlika (MN), Widening of Permanent Bridge, Ising Bridge along Daang Maharlika, Carmen, Davao del Norte | Carmen, Davao del Norte | 2015-11-13 | Final | Davao del Norte DEO | LF | 3.2287e-05 | 184 | 2015-02-05 | 2015-08-07 | 0 | C | 0.441 | 0.187 | 0.3 | - | - | - | 92.8% | 92.8% Very Satisfactory
O.G. SANTOS CONSTRUCTION | 2050 | L | AAA | MA | GB | Construction of One Storey Two Classroom School Building, Hinatuan NCHS-Roxas NHS Annex | Hinatuan, Surigao del Sur | 2015-11-13 | 1st | Surigao del Sur 2nd DEO | LF | 1.7891 | 116 | 2015-08-03 | 2015-11-26 | (+) 10.37 | OG | 0.358 | 0.3 | 0.15 | 0.03 | 0.058 | 0.05 | 94.6% | 94.6% Very Satisfactory
O.G. Santos Construction |  | L |  |  | GB1 | NHA - Pantukan Resettlement Project | Brgy. King-king, Pantukan , Compostela Valley | 2013-06-14 | 1st | NHA | L | 29.926 | 365 | 2012-06-14 | 2013-08-22 | -0.92 | O | 0.3984 | 0.3 | 0.1408 | 0.03 | 0.0653 | 0.05 | 98.45 | -
O.L. De Leon Construction | 16194 | L | B | MA | GE1 | Upgrading (Gravel to Concrete) of Bagong Silang-Capalonga Rd., K0321+000-K0321+458 | Capalonga, Camarines Norte | 2011-08-18 | 1st | V | LF | 9.229 | 230 | 2011-05-05 | 2011-12-20 | 48.91 | O | 0.301 | 0.283 | 0.15 | 0.02 | 0.042 | 0.05 | 84.6 | -
O.L. De Leon Construction | 16194 | L | B | SB | GE2 | Const. of Drainage System at Pob. 1, 2 & 3 | Vinzons, Camarines Norte | 2011-04-03 | 1st | V | LF | 5.725 | 150 | 2010-12-15 | 2011-05-13 | 15.34 | O | 0.356 | 0.225 | 0.15 | 0.03 | 0.035 | 0.033 | 82.9 | -
O.R Sarmiento Construction | 1411 | L | AA | LA | GE1 | Conc. of Junction (TER), Jagna-Sierra-Bullones Road |  | 2008-08-29 | 2nd | VII |  | 81.102 | 300 |  |  |  | O | 0.337 | 0.223 | 0 | 0.03 | 0.059 | 0.1 | 74.9 | -
O.R Sarmiento Construction | 1411 |  |  |  |  | Repair/Impvt./Asphalt Paving of Bugko-Nenita-San Jose Rd., Km.760+000 - Km.779+000 (Mondragon-Silvino Rd.) |  | 2010-06-16 |  | VIII |  | 192.823 | 385 |  |  |  | O | 0.387 | 0.3 | 0.15 | 0.03 | 0.042 | 0.05 | 95.9 | -
O.R Sarmiento Construction | 1411 | L | AA | LA | GE2 | Talibon Small Reservoir Irrigation Project |  | 9/29/08 10/3/08 | 1st | NIA |  | 11.574 | 343 |  |  |  | O | 0.35 | 0.157 | 0.1 | 0.03 | 0.047 | 0.2 | 88.4 | -
O.R. Sarmiento Construction | 1411 | L | AAA | LB | GE1 | Road Upgrading of Jct. Taft-Oras-San Policarpio-Arteche Road | San Policarpio, Eastern Samar | 2012-03-29 | 1st | VIII | LF | 61.048 | 230 | 2011-08-19 | 2012-04-04 | -12.39 | O | 0.373 | 0.3 | 0.026 | 0.03 | 0.055 | 0.033 | 81.7 | -
O.R. Sarmiento Construction | 1411 | L | AAA | LB | GE1 | Rd. Upgrading (Gravel to Concrete) along Balbalan-Pinukpuk Rd., Km.505+000-Km.523+399 (I.S.) | Pinukpuk, Kalinga | 2013-03-20 | 1st | CAR | LF | 165.98 | 480 | 2011-11-14 | 2013-03-07 | -11.7 | O | 0.319 | 0.24 | 0.15 | 0.03 | 0.051 | 0.05 | 84 | -
O.R. Sarmiento Construction / Plerm Construction & Development Corp. JV | JV-11-277 | L | AAA | LB | GE1 | Reconst. of Longos Bridge, Calapan North Rd. | Calapan City, Mindoro | 2012-08-07 | 1st | IVB | LF | 104.412 | 386 | 2011-12-29 | 2013-01-17 | -6.77 | O | 0.34 | 0.3 | 0.082 | 0.03 | 0.04 | 0.033 | 82.5 | -
O.R. Sarmiento Construction / Plerm Construction & Development Corporation (JV) | JV-11-031 | L | AAA | LB | GE1 | CP 2.1 Const. of Tangcul Bridge & Approaches & CP 2.2 Const. of Sicalaco Bridge & Approaches | Lasam, Cagayan | 2013-08-15 | Final | PMO-SBP | LF | 67.616 | 375 | 2011-11-11 | 2012-11-19 | 0 | C | 0.459 | 0.2 | 0.3 | - | - | - | 95.9 | 96.50% Outstanding
O.R. Sarmiento Construction / Plerm Construction & Development Corporation (JV) | JV-11-031 | L | AAA | LB | GE1 | CP 2.1, Const. of Tangcul Bridge & Approaches and CP 2.2, Const. of Sicalao Bridge & Approaches | Lasam, Cagayan | 2012-08-01 | 1st | PMO-SBP | FA | 67.616 | 375 | 2011-11-11 | 2012-11-21 | 5.25 | O | 0.374 | 0.3 | 0.15 | 0.03 | 0.065 | 0.05 | 96.9 | -
O.R. Sarmiento Construction / Plerm Construction & Development Corporation (JV) | JV-11-487 | L | AAA | LB | GE1 | Replacement of Baroc Bridge to Const. of Pre-Stressed Bridge at Calapan Rd. | Mansalay, Oriental Mindoro | 2013-03-21 | Final | IVB | LF | 46.732 | 380 | 2012-03-22 | 2013-04-05 | 6.51 | C | 0.471 | 0.133 | 0.3 | - | - | - | 90.4 | 90.37% V. Satisfactory
O.R. Sarmiento Construction / Plerm Construction & Development Corporation (JV) | JV-11-277 | L | AAA | LB | GE1 | Reconst. of Longos Bridge, Calapan North Rd. | Calapan City, Oriental Mindoro | 2013-03-18 | 2nd | IVB | LF | 103.455 | 416 | 2011-12-29 | 2013-02-16 | 2.96 | O | 0.387 | 0.24 | 0.15 | 0.03 | 0.051 | 0.033 | 89.1 | -
O.R. Sarmiento Construction / Plerm Construction and Development Corporation (JV) | JV-11-277 | L | AAA | LB | GE1 | Reconst. of Longos Bridge, Calapan North Rd. | Calapan City, Oriental Mindoro | 2013-11-26 | Final | IVB | LF | 103.454 | 615 | 2012-01-02 | 2013-09-07 | 0.81 | C | 0.467 | 0.134 | 0.3 | - | - | - | 90.1 | 87.52% Satisfactory
O.R. Sarmiento Construction Inc./ Aualine Const. (JV) | [5 empty] | SRIPD-C-21 | Sta. Rita, Western Samar | 2015-11-21 | 1st | NIA | LF | 313.65 | 1157 | 2014-02-24 | 2017-05-04 | 13.99 | O | 0.358 | 0.271 | 0.15 | 0.03 | 0.065 | 0.05 | 92.4 | -
O.R. Sarmiento Construction Inc./ Newington Builders Inc. (JV) | JV-13-521 | L | AAA |  |  | Barotac Viejo SRIP | Brgy. Nueva Invencion, Barotac Viejo, Iloilo | 2015-11-13 | 1st | NIA | LF | 720.607 | 1154 | 2014-05-09 | 2017-07-05 | 11.81 | O | 0.3487 | 0.2889 | 0.15 | 0.024 | 0.0467 | 0.0333 | 89.16 | -
O.R. Sarmiento Construction Inc./ Newington Builders Inc. (JV) | JV-13-521 |  | AAA |  |  | Barotac Viejo SRIP | Brgy. Nueva Invencion, Barotac Viejo, Iloilo | 2016-10-07 | 2nd | NIA | LF | 720.607 | 1154 | 2014-05-09 | 2017-07-05 | -10.02 | O | 0.373 | 0.2817 | 0.0498 | 0.03 | 0.0607 | 0.0333 | 82.85 | -
Ocean Construction Services | 32220 | L | D | SB | GB1 | Const. of 27.75m x 27.20m Public Market Bldg. | Diadi, Nueva Vizcaya | 2013-03-20 | Final | II | LF | 3.8 | 136 | 2012-09-05 | 2013-01-18 | 1.71 | C | 0.498 | 0.133 | 0.3 | - | - | - | 93.1 | 88.24% Satisfactory
OCM Steel Corporation | 32421 |  |  |  |  | Construction and Fit-out of DBP Pototan Branch | Milagros Bldg., R.Y. Ladrido Street, Pototan, Iloilo | 2016-09-05 | Final | DBP | LF | 11.342 | 150 | 2016-04-07 | 2016-08-31 | 0 | C | 0.441 | 0.2 | 0.3 | - | - | - | 94.1 | *94.11% Very Satisfactory
OCTAGON CONCRETE SOLUTION | 34475 | L | A | MB | GE | Construction of Drainage System along Naval-Caibiran Cross Country Road to include payment of RROW damages, Km. 1026+800-Km. 1027+236 (Right Side.)-Km. 1027+400-Km. 1027+648 (Right SIde)Naval, Biliran | Km. 1026+800-Km. 1027+236 (Right Side.)-Km. 1027+400-Km. 1027+648 (Right SIde)Naval, Biliran | 2015-08-27 | 2nd | Biliran DEO | LF | 8.365 | 234 | 2015-02-06 | 2015-09-27 | (-)13.39 | O | 0.352 | 0.3 | 0.016 | 0.01 | 0.04 | 0.033 | 75.1% | -
OCTAGON CONCRETE SOLUTION | 34475 | L | A | MB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads including Drainage based on Pavement Management System/Highway Development and Management-4 (HDM-4) (intermitent Sections) Bagahupi-Babatngon-Sta. Cruz-Barugo-Carigara Road, K0942+353 to K0943+209, Carigara, Leyte | K0942+353 to K0943+209, Carigara, Leyte | 2015-08-25 | 1st & Final | Leyte 2nd DEO | LF | 12.815 | 120 | 2015-02-20 | 2015-06-19 | - | C | 0.364 | 0.2 | 0.3 | - | - | - | 86.4% | *86.4% Satisfactory
Octagon Concrete Solutions | 34475 | L | A |  |  | MANGUINO-O PORT IMPROVEMENT PROJECT | Port of Manguino-o, Brgy. Manguino-o, Calbayog City, Samar | 2015-06-25 | 1st | PPA | LF | 39.905 | 300 | 2014-12-08 | 2015-10-03 | 1.83 | O | 0.4 | 0.3 | 0.15 | 0.03 | 0.05 | 0.05 | 98 | -
Octagon Concrete Solutions | 34475 | L | A |  |  | Repair of R.C. Deck at Conventional Pier & Mooring and Fendering System | Port of Ormoc, Leyte | 2014-03-21 | 1st | PPA | LF | 21.871 | 75 | 2013-04-12 | 2014-03-02 | -41.99 | O | 0.4 | 0.3 | 0 | 0.02 | 0.064 | 0.033 | 81.7 | -
Octagon Concrete Solutions | 34475 | L | A | MB | GE | Asphalt Overlay along Biliran Circumferential Road, Bagongbong-Almeria Road Section, Km. 1033+000 - Km. 1034+000 | Biliran Province | 2014-10-27 | 1st & Final | VIII | LF | 10.226 | 94 | 2014-02-06 | 2014-05-10 | -10% | C | 0.452 | 0.201 | 0 | - | - | - | 65.3% | 65.3% Poor
Octagon Concrete Solutions | 34475 | L | A | MB | GE | Road Upgrading (gravel to Paved) Merida - Lundag - Putting Bato - Consolacion - Isabel Road A. K1109+059 - K1110+000 B. 1110+057 - K1111+(-389) | Leyte | 2014-08-07 | Final | VIII | LF | 34.7448 | 260 | 2013-01-28 | 2013-10-14 | 0 | C | 0.382 | 0.189 | 0.3 |  |  |  | 87.1 | 88.72% Satisfactory
Octagon Concrete Solutions | 34475 | L | A | MB | GE1 | Rd. Upgrading (Gravel to Pave) Merida-Lundag-Puting Bato-Consolacion-Isabel Rd., a.K1109+059-K1110+000, b.K1110+057-K1111+(-389) | Leyte | 2013-08-10 | 1st | VIII | LF | 34.745 | 260 | 2013-01-28 | 2013-10-14 | 0.86 | O | 0.393 | 0.24 | 0.15 | 0.015 | 0.05 | 0.05 | 89.8
Octagon Concrete Solutions | 34475 | L | A | MB | GE1 | Rehab./Reconst. of Damaged Paved Nat'l Rd. (Intermittent Sect.), Ormoc-Baybay Southern Leyte Bdry. Rd., A.K1032+000-K1033+000 B.K1026+000-K1027+000 | Ormoc City | 2013-03-14 | 1st | VIII | LF | 13.815 | 150 | 2013-01-28 | 2013-06-26 | 13.29 | O | 0.39 | 0.29 | 0.15 | 0.023 | 0.04 | 0.033 | 92.6 | -
Octagon Concrete Solutions | 34475 | L | A | MB | GE1 | Prev. Maint. of Palo-Carigara-Ormoc Rd., K0939+(-935)-K0940+000 | Jaro, Leyte | 2013-03-11 | 1st | VIII | LF | 13.963 | 95 | 2013-01-15 | 2013-04-19 | 0 | O | 0.36 | 0.24 | 0.15 | 0.023 | 0.04 | 0.05 | 86.3 | -
Octagon Concrete Solutions | 34475 | L | A | MB | GE1 | Rd. Upgrading (Gravel to Paved) of Sambulawan Jct.-Calaguise-Calubian Rd., Km.995+407-Km.997+417 | Leyte | 2013-03-13 | Final | VIII | LF | 41.353 | 281 | 2012-01-09 | 2012-10-15 | 0 | C | 0.39 | 0.153 | 0.3 | - | - | - | 84.3 | 84.78% Satisfactory
Octagon Concrete Solutions | 34475 | L | A | MB | GE1 | Concrete Paving of Biliran Circ. Rd., Asug-Talibong Rd. Section, Km.1091+826-Km.1095+153 w/ exceptions | Cabucgayan, Biliran Province | 2013-03-12 | Final | VIII | LF | 47.954 | 300 | 2012-02-01 | 2012-11-27 | 0 | C | 0.273 | 0.186 | 0.3 | - | - | - | 75.9 | 82.08% Satisfactory
Octagon Concrete Solutions | 34475 | L | A | MB | GE1 | Rd. Upgrading (Gravel to Paved) of Sambulawan Jct.-Calaguise-Calubian Rd., Km.1000+230-Km.1001+390 | Leyte | 2013-03-13 | Final | VIII | LF | 26.941 | 221 | 2012-01-09 | 2012-08-16 | 0 | C | 0.334 | 0.154 | 0.3 | - | - | - | 78.8 | 82.04% Satisfactory
Octagon Concrete Solutions | 34475 | L | A | MB | GE1 | Repair/Rehab./Impvt. of Carigara-Barugo Rd. (S00069LT), K0944+835-K0945+349 w/ exceptions | Leyte | 2012-11-25 | 1st | VIII | LF | 9.895 | 90 | 2012-10-18 | 2013-01-15 | 0 | O | 0.359 | 0.24 | 0.15 | 0.03 | 0.043 | 0.033 | 85.5 | -
Octagon Concrete Solutions | 34475 | L | A | MB | GE1 | Road Upgrading (Gravel to Paved) Based on Gravel Rd. along Libungao-Matag-ob-Palompon Rd., Km.1005+567-Km.1006+567 | Leyte | 2012-08-13 | 1st | VIII | LF | 19.75 | 220 | 2012-01-16 | 2012-08-22 | 3.79 | O | 0.309 | 0.3 | 0.15 | 0.03 | 0.045 | 0.033 | 86.7 | -
Octagon Concrete Solutions | 34475 | L | A | MB | GE1 | Rd. Upgrading (Gravel to Paved) of Calubian Jct.-San Isidro-Tabango-Villaba - Palompon Rd., Km.1011+248.55-Km.1013+133; Km.1019+882-Km.1019+962 | San Isidro, Leyte | 2012-08-09 | 1st | VIII | LF | 43.469 | 281 | 2012-01-06 | 2012-10-11 | 2.83 | O | 0.298 | 0.286 | 0.15 | 0.03 | 0.045 | 0.033 | 84.2 | -
OCTAGON CONCRETE SOLUTIONS | 34475 | L | A | SB | GE | Const. of Drainage System along Naval-Caibiran Cross Country Road to include Payment RROW Damages, K1026+800 to K1027+236 (Right Side)- K1027+400 to K1027+648 (Left Side) Naval, Biliran Provice | K1026+800 to K1027+236 (Right Side)- K1027+400 to K1027+648 (Left Side) Naval, Biliran Provice | 2015-06-03 | 1st | Biliran DEO | LF | 8.365 | 174 | 2015-02-06 | 2015-07-29 | - | O | 0.298 | 0.121 | 0.15 | 0.03 | 0 | 0.05 | 64.9% | -
Octagon Concrete Solutions | 34475 | L |  |  |  | Manguino-o Port Improvement Project | Port of Manguino-o, Brgy. Manguino-o, Calabayog City, Samar | 2016-06-15 | 2nd & Final | PPA | LF | 39.905 | 418 | 2014-12-08 | 2016-01-29 | -11.43 | C | 0.4994 | 0.2 | 0 | - | - | - | 69.94 | 86.78% Satisfactory
O'hara Construction & Aggregates | 33173 | L | D | SB | GB1 | Proposed One Storey Two Class room 7x7 (modified) Mamuyod E/S |  | 2009-08-26 | 1st | CAR |  | 1.025 | 82 |  |  |  | O | 0.344 | 0.24 | 0.118 | 0.03 | 0.043 | 0.033 | 80.8 | -
OIC Construction & Supply (Formerly: OIC Construction) | 23727 |  |  |  |  | Rehab./Reconst. of Talisay-Laurel-Agoncillo Rd., Laurel-Agoncillo Sect. |  | 2010-06-10 |  | IVA |  | 21.225 | 120 |  |  |  | O | 0.384 | 0.225 | 0.15 | 0.023 | 0.054 | 0.033 | 86.9 | -
Olin Development Engineering & Construction | 26271 | L | D | SB | GB | Construction of Multi-Purpose Building at Brgy. Poblacion | Carmen, Agusan del Norte | 2014-10-21 | 1st & Final | XIII | LF | 1.9747 | 60 | 2014-07-29 | 2014-09-26 | 0% | C | 0.41 | 0.176 | 0.3 | - | - | - | 88.6% | 88.6% Satisfactory
OLIN Development Engineering & Construction | 26271 | L |  | SB |  | Completion of Perimeter Fence/ Gate | Brgy. Ampayon, Tiniwisan, Butuan City | 2016-09-21 | Final | DOST | LF | 4.987 |  |  | 2016-08-15 | 0 | C | 0.499 | 0.2 | 0.3 | - | - | - | 99.9 | 98.64% Outstanding
OLIN Development Engineering & Construction | 26271 | L |  | SB |  | Site Development Phase I | Brgy. Ampayon, Tiniwisan, Butuan City | 2016-09-21 | Final | DOST | LF | 4.606 | 237 |  | 2016-08-15 | 0 | C | 0.5 | 0.2 | 0.3 | - | - | - | 100 | 96.57% Outstanding
OLIN DEVELOPMENT ENGINEERING AND CONSTRUCTION | 26271 | L | C | SB | GB | Construction of One Storey Two Classroom School Building Quezon Integrated Secondary School, Tagbina, Surigao del Sur | Tagbina, Surigao del Sur | 2015-11-12 | 1st | Surigao del Sur 2nd DEO | LF | 1.7786 | 120 | 2015-08-03 | 2015-11-30 | (+)2.16 | OG | 0.36 | 0.3 | 0.15 | 0.03 | 0.052 | 0.05 | 94.2% | 94.2% Very Satisfactory
OLSIM CONSTRUCTION | 36105 | L | C | SB | GE | Road Upgrading (Unpaved to Paved) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standards (HDM-4 Project Analysis)(Intermittent Sections) Dantay-Sagada Road K0390+840 - K0390+941 | Sagada, Mt. Province | 2015-06-05 | Final | Mountain Province DEO | LF | 2.82 | 97 | 2015-02-11 | 2015-05-18 | (+) 14.43% | C | 0.358 | 0.2 | 0.3 | - | - | - | 85.8% | *85.8% Satisfactory
Omengan Construction and Development Corporation | 5119 | L | AAA | LB | GE | Road Upgrading (Gravel to Concrete) of Conner - Kabugao Road KO585+834 - KO588+691 & KO590+340 - KO594+774 | Apayao | 2014-11-28 | 1st | CAR | LF | 193.5485 | 448 | 2014-06-11 | 2015-09-01 | 11.48% | O | 0.328 | 0.28 | 0.15 | 0.03 | 0.06 | 0.05 | 89.8% | 89.8% Very Satisfactory
Omengan Construction and Development Corporation | 5119 | L | AAA | LB | GE | Road Upgrading (Gravel to Paved) of Mt. Province Bdry.-Calanan-Pinukpuk-Abbut Road (Pinukpuk) K0523+850 - K0527+214, KO527+615 - K0529+041, KO529+474 - KO530-268, KO532+019-KO534+852 | Pinukpuk, Kalinga | 2014-11-27 | 1st | CAR | LF | 127.8951 | 285 | 2014-06-11 | 2015-03-22 | 19.62% | O | 0.354 | 0.279 | 0.15 | 0.03 | 0.06 | 0.05 | 92.3% | 92.3% Very Satisfactory
Omengan Construction and Development Corporation | 5119 | L | AA | LA | GE | Road Upgading (Gravel to Concrete) along Claveria - Calanasan - Kalagao Road, K0649+629 to K0651+469 (I.S.), Apayao | Apayao | 2014-08-09 | 1st | CAR | LF | 46.9085 | 179 | 2014-04-22 | 2014-10-17 | 1.02 | O | 0.374 | 0.24 | 0.15 | 0.024 | 0.04 | 0.033 | 86.1
Omengan Construction and Development Corporation | 5119 | L | AA | LA | GE | Road Upgrading (Gravel to Concrete) along Conner-Kabugao, Apayao-Solsona-Ilocos Norte Road, Apayao Side, K0606+(-370) to K0607+376, Apayao | Kabugao, Apayao, Solsona Road | 2014-08-08 | Final | CAR | LF | 42.116 | 241 | 2013-02-11 | 2013-10-09 | 1.05 | C | 0.405 | 0.133 | 0.3 |  |  |  | 83.8 | 89.62% Very Satisfactory
Omengan Construction and Development Corporation | 5119 | L | AA | LA | GE1 | Rd. Upgrading (Gravel to Conc.) along Kabugao, Apayao-Solsona-Ilocos Norte Rd., Apayao Side, K0606+(-370)-K0607+376 | Apayao | 2013-08-10 | 2nd | CAR | LF | 42.116 | 230 | 2013-02-11 | 2013-09-28 | 3.26 | O | 0.36 | 0.3 | 0.15 | 0.03 | 0.05 | 0.033 | 92.3
Omengan Construction and Development Corporation | 5119 | L | AA | LA | GE1 | Road Upgrading (Gravel to Concrete) along Kabugao, Apayao-Solsona-Ilocos Norte Rd., Apayao Side, K0606+(-370)-K0607+376 | Apayao | 2013-03-21 | 1st | CAR | LF | 42.116 | 170 | 2013-02-11 | 2013-07-30 | 1.16 | O | 0.398 | 0.297 | 0.15 | 0.024 | 0.045 | 0.033 | 94.7 | -
Omengan Construction and Development Corporation | 5119 | L | AA | LA | GE1 | Conc. along Kabugao-Pudtol-Luna Road, Matuguise Section |  | 2009-09-05 | 2nd | CAR |  | 18.868 | 277 |  |  |  | O | 0.365 | 0.24 | 0.15 | 0.03 | 0.056 | 0.033 | 87.4 | -
Omengan Construction and Development Corporation | 5119 | L | AA | LA | GE1 | Conc. along Kabugao-Pudtol-Luna Road, Mataguisi Section |  | 2009-06-01 | 1st | CAR |  | 18.868 | 277 |  |  |  | O | 0.322 | 0.3 | 0.15 | 0.03 | 0.05 | 0.033 | 88.5 | -
Omengan Construction and Development Corporation | 5119 | L | AA | LA | GE1 | Improvement/Widening/Concreting of Bontoc-Tabuk-Tuguegarao Road, Phase III, Dao Bridge-Cobaet Bridge |  | 2009-03-03 | 1st | CAR |  | 47.241 | 300 |  |  |  | O | 0.362 | 0.288 | 0.15 | 0.03 | 0.045 | 0.033 | #VALUE! | -
Omengan Construction and Development Corporation | 5119 | L | AA | LA | GE1 | Impvt./Widening/Conc. Of Bontoc-Tabuk-Tuguegarao Road, Phase VI, Mamaga Bridge-Basao Bridge, Km. 420+970-Km.429+940 |  | 2009-03-04 | 2nd | CAR |  | 83.149 | 365 |  |  |  | O | 0.376 | 0.3 | 0.15 | 0.03 | 0.045 | 0.033 | #VALUE! | -
Omengan Construction and Development Corporation | 5119 | L | AA | LA | GE1 | Impvt./Widening/Conc. of Bontoc-Tabuk-Tuguegarao Road, Phase VI, Mamaga Bridge-Basao Bridge, Km. 420+970-Km.429+940 |  | 2008-11-20 | 1st | CAR |  | 83.149 | 365 |  |  |  | O | 0.331 | 0.24 | 0.1 | 0.03 | 0.045 | 0.067 | 81.3 | -
Omengan Construction and Development Corporation | 5119 | L | AA | LA | GE1 | Widening / Conc. of Mt. Data-Bontoc Road Sabangan Bridge, Poblacion to Malitep Bridge Section Balili Section, Km. 374+233-Km 380+227 |  | 2009-08-28 | 1st | CAR |  | 91.443 | 430 |  |  |  | O | 0.361 | 0.24 | 0.053 | 0.023 | 0.042 | 0.017 | 73.6 | -
Omengan Construction and Development Corporation | 5119 | L | AA | LA | GE1 | Rehab. of Nat'l Rd. along Conner-Kabugao Rd., Landslide, K0570+200-K0571+800 w/ exception, Matalag Sect. | Conner, Apayao | 2012-11-27 | 2nd | CAR | LF | 24.219 | 342 | 2011-11-23 | 2012-10-30 | -5.06 | O | 0.354 | 0.3 | 0.068 | 0.02 | 0.042 | 0.033 | 81.7 | -
Omengan Construction and Development Corporation | 5119 | L | AA | LA | GE1 | Rehab./Reconst./Upgrading of Paved Nat'l Rds. along Baguio-Bontoc Rd., K0317+415-K0318+500, Sinipsip | Bugias, Benguet | 2012-08-02 | 1st | CAR | LF | 20.272 | 252 | 2012-01-22 | 2012-09-30 | -1.73 | O | 0.291 | 0.24 | 0.133 | 0.01 | 0.051 | 0.033 | 75.8 | -
Omengan Construction and Development Corporation | 5119 | L | AA | LA | GE1 | Rehab. of Nat'l Rd. along Conner-Kabugao Rd., Landslide, K0570+200-K0571+800 w/ exception, Matalag Sect. | Conner, Apayao | 2012-08-10 | 1st | CAR | LF | 24.219 | 300 | 2011-11-23 | 2012-09-18 | -10.41 | O | 0.31 | 0.3 | 0.046 | 0.015 | 0.045 | 0.033 | 74.9 | -
Omengan Construction and Development Corporation | 5119 | L | AA | LA | GE1 | Rd. Upgrading (Gravel to Concrete) of Mt. Province-Ilocos Sur Rd. K0388+000-K0412+425 (I.S.) Tadian-Bauko-Sabangan | Mt. Province | 2012-08-04 | 1st | CAR | LF | 137.509 | 425 | 2011-08-16 | 2012-10-14 | -12.79 | O | 0.302 | 0.3 | 0.022 | 0.03 | 0.047 | 0.033 | 73.4 | -
OMENGAN CONSTRUCTION AND DEVELOPMENT CORPORATION | 5119 | L | AAA | LB | GE | Road Upgrading (Gravel to Paved) of Mt. Province Bdry. - Calanan - Pinukpuk - Abbut Road (Pinukpuk), K0523+850 - K0527+214, K0527+615 - K0529+041, K0529+474 - K0530+268, K0532+019 - K0534+852 | Pinukpuk, Kalinga | 2015-06-09 | Final | CAR | LF | 127.895 | 315 | 2014-06-11 | 2015-04-21 | (+) 0.32 | C | 0.373 | 0.2 | 0.3 | - | - | - | 87.3% | *90.3% Very Satisfactory
OMENGAN CONSTRUCTION AND DEVELOPMENT CORPORATION | 5119 | L | AAA | LB | GE | Road Upgrading (Unpaved to Paved) Malalao National Road (Agbanawag - Malalao - Bulo Section), K0512+480 to K0514+026 and K0514+23+6 to K0514+690, Tabuk City, Kalinga | Tabuk City, Kalinga | 2015-08-28 | 1st | Kalinga DEO | LF | 43.97 | 209 | 2015-03-14 | 2015-10-08 | 7.12% | O | 0.385 | 0.3 | 0.15 | 0.03 | 0.065 | 0.05 | 98% | -
OMENGAN CONSTRUCTION AND DEVELOPMENT CORPORATION | 5119 | L | AAA | LB | GE | Road Upgrading (Unpaved to Paved) Malalao National Road Agbannawag-Malalao-Bulo Section, K0512+480 - K0514+026 and K0514+236 - K0514+690, Tabuk City, Kalinga | Tabuk City, Kalinga | 2015-11-13 | Final | Kalinga | LF | 43.9708 | 209 | 2015-03-14 | 2015-10-08 | 0.00% | C | 0.443 | 0.2 | 0.3 | - | - | - | 94.3% | 94.3% Very Satisfactory
OMICRON CONSTRUCTION | - | L | - | - | - | Restoration of Caulaman River Slope Protection, Floridablanca, a.) Sto. Rosario; b.) Dampe; c.) Bodega, Floridablanca, Pampanga | Floridablanca, Pampanga | 2015-06-03 | Final | Pampanga 2nd DEO | LF | 24.018 | 180 | 2014-09-29 | 2015-03-21 | 0% | C | 0.484 | 0.2 | 0.3 | - | - | - | 98.4% | *98.4% Outstanding
Omnicon Builders | 22816 | L | B | MA | GB1 | Const. of MPB at Patindig Araw | Imus, Cavite | 2013-08-14 | Final | IVA | LF | 0.679 | 135 | 2012-07-18 | 2012-11-29 | 0 | C | 0.475 | 0.133 | 0.3 | - | - | - | 90.8 | 86.46% Satisfactory
OMNICON BUILDERS | 22816 | L | B | MA | GB | Construction of Multi Purpose Building at Buhay na Tubig | Imus City, Cavite | 2015-06-13 | Final | Cavite 1st DEO | LF | 9.308 | 120 | 2014-08-16 | 2014-12-13 | 0% | C | 0.324 | 0.2 | 0.3 | - | - | - | 82.4% | *82.4% Satisfactory
OQC Construction | 22690 | L | B | SB | GE2 | Addalam River Irrigation Project |  | 04/27/09 05/01/09 | 1st | NIA |  | 2.827 | 178 |  |  |  | O | 0.3583 | 0.24 | 0.15 | 0.0225 | 0.0382 | 0.0333 | 84.23 | -
Orani Builders Supply | 5349 | L | B | MA | GE | Replacement/Rehab.Strengthening of Limay Bridge along Jct. Layac - Balanga - Mariveles Port Road | Limay, Bataan | 2014-08-13 | 1st & Final | III | LF | 24.2557 | 148 | 2013-03-27 | 2013-08-21 | 1.35 | C | 0.499 | 0.133 | 0.3 |  |  |  | 93.2 | 93.20% Very Satisfactory
Orani Builders Supply | 5349 | L | B | MA | GE | Improvement ofConcrete Revetment of Colo River, Magsaysay Section | Dinalupihan, Bataan | 2014-08-12 | 1st & Final | III | LF | 12.8253 | 158 | 2014-02-10 | 2014-08-03 | 1.56 | C | 0.401 | 0.191 | 0.3 |  |  |  | 89.2 | 89.20% Very Satisfactory
Orani Builders Supply | 5349 | L | B | MA | GE1 | Replacement/Rehab./Strengthening of Limay Bridge along Jct. Layac-Balanga-Mariveles Port Rd. | Limay, Bataan | 2013-08-03 | 1st | III | LF | 24.03 | 148 | 2013-03-27 | 2013-08-21 | 4.58 | O | 0.4 | 0.24 | 0.15 | 0.03 | 0.05 | 0.033 | 90.3
Orani Builders Supply | 5349 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of Jct. Layac-Balanga-Mariveles Port Rd. (Mariveles Zigzag Rd.) K0158+398-K0160+120 | Mariveles, Bataan | 2013-08-02 | 1st | III | LF | 46.523 | 148 | 2013-04-01 | 2013-08-26 | 2 | O | 0.379 | 0.24 | 0.15 | 0.03 | 0.045 | 0.033 | 87.7
Orani Builders Supply | 5349 | L | B | MA | GE1 | Asphalt Overlay of Tabacan-Poblacion Road |  | 2009-05-20 | 1st | III |  | 16.2679 | 120 |  |  |  | O | 0.4 | 0.2 | 0.15 | 0.023 | 0.025 | 0.05 | 84.8 | -
Orani Builders Supply | 5349 | L | B | MA | GE1 | Widening of Gapan-San Fernando-Olongapo Road |  | 2009-05-20 | 1st | III |  | 28.5159 | 120 |  |  |  | O | 0.35 | 0.209 | 0.15 | 0.03 | 0.04 | 0.05 | 82.9 | -
Orani Builders Supply | 5349 | L | B | MA | GE1 | Concreting of Mabatang-Vicinal Road |  | 2009-05-20 | 1st | III |  | 7.6428 | 120 |  |  |  | O | 0.314 | 0.233 | 0.15 | 0.03 | 0.037 | 0.05 | 81.4 | -
Orani Builders Supply | 5349 | L | B | MA | GE1 | Replacement of Castañeda Bridge along TLLR, (Km.37+340-Km.37+466) Lubang Island | Occidental Mindoro | 2012-03-24 | 1st | IVB | LF | 7.386 | 150 | 2012-02-06 | 2012-07-05 | 2 | O | 0.388 | 0.24 | 0.15 | 0.022 | 0.018 | 0.05 | 86.8 | -
Orani Builders Supply | 5349 | L | B | MA | GE1 | Replacement & Const. of Palasingsingan Bridge, Km.24+900-Km.25+057.50, Lubang Island | Occidental Mindoro | 2012-03-24 | 1st | IVB | LF | 9.821 | 240 | 2012-02-06 | 2012-10-02 | 38 | O | 0.389 | 0.24 | 0.15 | 0.02 | 0.029 | 0.033 | 86.1 | -
ORANI BUILDERS SUPPLY | 5349 | L | B | MA | GE | Dredging/Improvement of Muzon River, Malabon City | Malabon City | 2015-09-04 | 1st | Mal-Nav DEO | LF | 34.369 | 214 | 2015-05-21 | 2015-12-20 | 11.49% | O | 0.328 | 0.24 | 0.15 | 0.03 | 0.045 | 0.05 | 84.3% | -
ORANI BUILDERS SUPPLY | 5349 | L | B | MA | GE | Road Upgrading (Unpaved to Paved) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Road Standards (HDM-4 Project Analysis) (Intermittent Sections) - Secondary Roads Mariveles By-Pass Road, K0158+(-031) to K0158+1690 , Mariveles, Bataan | Mariveles, Bataan | 2015-08-28 | 1st | Bataan Second DEO | LF | 36.594 | 198 | 2015-05-28 | 2015-12-11 | 11.15% | O | 0.295 | 0.3 | 0.15 | 0.015 | 0.045 | 0.05 | 85.5% | -
ORANI BUILDERS SUPPLY | 5349 | L | B | MA | GE | Local Infrastructure Program-Construction of Barangay Road, Leona, Barangay Balut, Orani, Bataan | Barangay Balut, Orani, Bataan | 2015-11-12 | Final | Bataan First DEO | LF | 1.902 | 75 | 2016-03-03 | 2016-05-16 | - | C | 0.474 | 0.133 | 0.3 | - | - | - | 90.7% | 90.7% Very Satisfactory
ORANI BUILDERS SUPPLY | 5349 | L | B | MA | GE | Flood Control Project in Central Luzon: Dike Slope Protection Downstream of Neilsen Bridge, Project "A" Sta.0+975 to Sta.1+296.40 & Sta.1+319.70 to Sta.1+375 and Project "B" Sta.1+915 to Sta.2+083.40, Bamban, Tarlac | Bamban, Tarlac | 2015-11-18 | 1st | Tarlac Second DEO | LF | 46.645 | 185 | 2015-08-27 | 2016-02-27 | 27.00% | OG | 0.391 | 0.24 | 0.15 | 0.024 | 0.056 | 0.05 | 91.1% | 91.1% Very Satisfactory
ORANI BUILDERS SUPPLY | 5349 | L | B | MA | GE | Repair/Rehabilitation/Improvement (Drainage System), Olongapo-Bugallon Road K0144+950 to K0145+352 with exceptions, Del Pilar, Castillejos, Zambales | Del Pilar, Castillejos, Zambales | 2015-11-10 | 1st | Zambales Second DEO | LF | 7.113 | 120 | 2015-07-20 | 2015-11-16 | 2.00% | OG | 0.377 | 0.24 | 0.15 | 0.018 | 0.037 | 0.033 | 85.5% | 85.5% Satisfactory
ORANI BUILDERS SUPPLY / G. UY CONSTRUCTION (JOINT VENTURE) | JV-14-996 | L | B | MA | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Road along Tapaz-Jamindan-Altavas, Tapaz and Jamindan, Capiz, K0078+(-489)-K0082+080 (Crossing Switch): K0102+428-K0103+604 (Jamindan proper) and K0104+(-968)-K0104+351, with exception | Tapaz - Jamindan, Capiz | 2015-09-03 | 1st | Capiz 2nd | LF | 41.017 | 224 | 2015-07-09 | 2016-02-17 | 0.97% | O | 0.367 | 0.226 | 0.15 | 0.03 | 0.05 | 0.05 | 87.3% | -
Orient Star Const./Lumel Glenn Const. (JV) | JV-09-001 | LF | A | MA | GE1 | Completion of Mindoro Oriental/Occidental East Coastal Road, Nasucob-Campasaan Sect. |  | 2009-09-04 | 1st | IVB |  | 14.281 | 200 |  |  |  | O | 0.336 | 0.3 | 0.15 | 0.022 | 0.02 | 0.033 | 86.1 | -
Orient Star Construction / BCT Trading & Construction, JV | JV-09-067 | L | AAA | MA | GE5 | Const. of Bulalacao Port Development Project -Phase 2 (Ports & Harbor) | Port of Bulalacao, Oriental Mindoro | 02/7-10/11 | 1st | PPA | LF | 70.838 | 403 | 2010-03-25 | 2011-05-01 | -1.34 | O | 0.386 | 0.3 | 0.137 | 0.03 | 0.065 | 0.033 | 95.1 | -
Orient Star Construction Inc. (Formerly: Orient Star Construction) | 7183 | L | A | MA | GE | Construction of Alcate River Control, Victoria, Oriental Mindoro | Victoria, Oriental Mindoro | 2014-08-11 | 1st & Final | IV-B | LF | 9.0149 | 102 | 2014-02-24 | 2014-06-05 | 2 | C | 0.42 | 0.133 | 0.3 |  |  |  | 85.3 | 85.30% Satisfactory
Orient Star Construction Inc./Lumel Glenn Construction - Joint Venture |  | L |  |  | GE | Construction of Bongabong Flood Control (Minscat Section), Brgy. Labasan, Bongabong, Oriental Mindoro | Bongabong, Oriental Mindoro | 2014-08-13 | 1st & Final | IV-B | LF | 9.1042 | 135 | 2013-01-28 | 2013-06-11 | 2.27 | C | 0.4 | 0.133 | 0.3 |  |  |  | 83.3 | 83.30% Satisfactory
ORIENT STAR CONSTRUCTION, INC. (Formerly: Orient Star Construction) | 7183 | L | A | MA | GE | Construction of Gabions Revetment Maujao River Control | Bulalacao, Oriental Mindoro | 2015-06-10 | 1st | Southern Mindoro DEO | LF | 9.382 | 118 | 2015-02-20 | 2015-06-17 | 0% | O | 0.364 | 0.24 | 0.15 | 0.03 | 0.037 | 0.05 | 87.1% | -
ORIENT STAR CONSTRUCTION, INC. (Formerly: Orient Star Construction) | 7183 | L | A | MA | GE | Construction of Gabions Revetment Cagancan River Control (Upstream) | Mansalay, Oriental Mindoro | 2015-06-10 | Final | Southern Mindoro DEO | LF | 7.051 | 71 | 2015-03-17 | 2015-05-26 | 0% | C | 0.469 | 0.133 | 0.3 | - | - | - | 90.2% | *90.2% Very Satisfactory
ORIENT STAR CONSTRUCTION, INC. (Formerly: Orient Star Construction) | 7183 | L | A | MA | GE | Rehab./Reconst./Replacement of Zaragoza Bridge along CSR | Calapan City, Oriental Mindoro | 2015-11-20 | Final | Mindoro Oriental DEO | LF | 5.5855 | 199 | 2015-03-18 | 2015-10-02 | 0 | C | 0.483 | 0.133 | 0.3 | - | - | - | 91.6% | 91.6% Very Satisfactory
Orient Star Construction, Inc. / Lumel Glenn Construction (JV) | JV-12-203 | L | A | MA | GE2 | Const. of Bongabong Flood Control (Minscat Sect.) Brgy. Labasan | Bongabong, Oriental Mindoro | 2013-07-31 | Final | IVB | LF | 9.104 | 135 | 2013-01-28 | 2013-06-11 | 2.27 | C | 0.45 | 0.143 | 0.3 | - | - | - | 89.3 | 87.62% Satisfactory
Orient Star Construction, Inc. / Lumel Glenn Construction (JV) | JV-12-203 | L | A | MA | GE2 | Const. of Bongabong Flood Control (Minscat Sect.), Brgy. Labasan | Bongabong, Oriental Mindoro | 2013-03-20 | 1st | IVB | LF | 9.104 | 135 | 2013-01-28 | 2013-06-11 | 2.91 | O | 0.365 | 0.242 | 0.15 | 0.03 | 0.045 | 0.033 | 86.5 | -
Orientech Construction & Development Corporation | 8874 | L | A | MB | GB1 | Construction of Multi-Purpose Bldg.(Phase II) |  | 2009-09-04 | 1st | XIII |  | 14.47 | 210 |  |  |  | O | 0.386 | 0.24 | 0.15 | 0.03 | 0.043 | 0.033 | 88.2 | -
Oscar R. Sarmiento Construction, Inc. | 1411 |  | AAA |  |  | Ibato-Iraan SRIP | 3rd District, Aborlan, Palawan/ Region IV-B | 2016-08-01 | 1st | NIA | LF | 454.831 | 1157 | 2014-04-02 | 2017-06-01 | -29.08 | O | 0.3898 | 0.2817 | 0 | 0.03 | 0.0513 | 0.0333 | 78.61 | -
Oscar R. Sarmiento Construction, Inc. (Formerly: O.R. Sarmiento Construction) | 1411 | L | AAA | LB | GE1 | Conc. of Panglao Island Circ. Rd. (Songculan Sect.) Sec.1)K0004+002.98-K0005+774; Sec.2)K0006+637-K00012+000 | Bohol Province | 2013-08-15 | 1st | VII | LF | 140.475 | 405 | 2012-07-05 | 2013-09-02 | 2.58 | O | 0.288 | 0.3 | 0.15 | 0.03 | 0.06 | 0.05 | 87.8
OSCAR R. SARMIENTO CONSTRUCTION, INC. (FORMERLY: O.R. SARMIENTO CONSTRUCTION) | 1411 | L | AAA | LB | GE | Road Upgrading (Unpaved to Paved) of Jct. Osmena-Pilar Road | K0019+898.5 to K0020+500, Pilar, Dapa, Surigao Del Norte | 2015-06-09 | 1st | SURIGAO DEL NORTE SECOND DEO | LF | 9.395 | 120 | 2015-03-04 | 2015-07-01 | (+) 16.93% | O | 0.385 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 90.5% | -
P. C. Panopio Construction and Trading | 32824 | L | D | SB | GE1 | Upgrading/Conc. of FMR at Sta. Rita | Minalin, Pampanga | 2013-07-29 | Final | III | LF | 1.866 | 30 | 2013-02-19 | 2013-03-20 | 0 | C | 0.396 | 0.133 | 0.3 | - | - | - | 82.9 | 86.26% Satisfactory
P. L Sebastian Construction | 1076 | L | AAA | LB | GE1 | Rehab./Reconst./Upgrading of Tagum-Panabo Circumferential Road |  | 2009-09-07 | 2nd | XI |  | 96.181 | 200 |  |  |  | O | 0.389 | 0.241 | 0.15 | 0.03 | 0.051 | 0.05 | 91.1 | -
P. T. DIAMOND MERCHANDISE AND CONSTRUCTION | 15451 | L | B | MA | GE | Construction of New Pavement Bridge, Sulvec Bridge 2 along Manila North Road, Narvacan, Ilocos Sur | Nirvacan, Ilocos Sur | 2015-11-15 | Final | ILOCOS SUR 2ND DEO | LF | 13.2736 | 233 | 2015-02-04 | 2015-09-24 | - | C | 0.471 | 0.133 | 0.3 | - | - | - | 90.4% | 88.9% Satisfactory
P.B Obial Construction | 16784 |  |  |  |  | Conc. along Liloy, ZN-Ipil, ZS (Phase IV) Sta. 2000+260 - Sta. 2001+010 |  | 2010-02-25 |  | IX |  | 14.335 | 130 |  |  |  | O | 0.306 | 0.287 | 0.15 | 0.02 | 0.028 | 0.033 | 82.4 | -
P.B Obial Construction | 16784 |  |  |  |  | Const. of MPB at Palomoc, Titay |  | 2010-06-06 |  | IX |  | 3.344 | 100 |  |  |  | O | 0.346 | 0.24 | 0.15 | 0.03 | 0.029 | 0.05 | 84.5 | -
P.B Obial Construction | 16784 | L | B | MA | GE1 | Rehab./Const. of Dipolog-Sindangan-Liloy Road Magsaysay Section |  | 2009-06-01 | 1st | IX |  | 3.292 | 90 |  |  |  | O | 0.394 | 0.24 | 0.085 | 0.03 | 0.047 | 0.033 | 82.9 | -
P.B Obial Construction | 16784 | L | A | SB | GE | Construction/Rehabilitation of Flood Control Project in Naghalin Bridge/River Brgy. Naghalin | Catmon, Cebu | 2014-10-21 | 1st | VII | LF | 13.4332 | 140 | 2014-06-30 | 2014-11-16 | 28.26% | O | 0.328 | 0.24 | 0.15 | 0.03 | 0.045 | 0.033 | 82.6% | 82.6% Satisfactory
P.B. OBIAL CONSTRUCTION | 16784 | L | A | MA | GE | Construction/Rehabilitation of Flood Control project in Naghalin Bridge/River | Catmon, Cebu | 2015-06-05 | Final | Cebu Fifth DEO | LF | 13.433 | 140 | 2015-06-30 | 2015-11-16 | 4.29% | C | 0.349 | 0.2 | 0.3 | - | - | - | 84.9% | *84.9% Satisfactory
P.B. OBIAL CONSTRUCTION | 16784 | L | A | MB | GE | Rehabilitation/Improvement of A. S. Fortune St., Mandaue City, K0007+(-384) to K0008+046 | A.S. Fortuna Street, Mandaue City | 2015-06-01 | Final | Cebu Sixth DEO | LF | 44.521 | 360 | 2014-02-17 | 2015-02-11 | 13.33% | C | 0.468 | 0.135 | 0.3 | - | - | - | 90.3% | *90.3% Very Satisfactory
P.B. OBIAL CONSTRUCTION | 16784 | L | A | MB | GE | Rehabilitation/ Reconstruction/ Upgrading of Damage Paved National Roads including Drainage Based on PMS/HDM-4, National Secondary Road at A.S. Fortuna St., Chainage 864-1421, Mandaue City (Modified to: Chainage 000-2798), Mandaue City, Cebu | Mandaue City, Cebu | 2015-11-14 | 1st | Cebu 6th | LF | 21.0389 | 180 | 2015-07-13 | 2016-01-08 | 0.3389 | OG | 0.387 | 0.24 | 0.15 | 0.03 | 0.025 | 0.05 | 88.2% | 88.2% Satisfactory
P.B. OBIAL CONSTRUCTION/ARMANDO U KHONG HUN GENERAL CONTRACTOR, INC. (JV) | - | L | - | - | GE | Construction/Rehabilitation of Flood Control A.S. Fortuna Street | Mandaue City, Section 1: K0007+(-384)-K0009+034; Section 2: K0000+0000- K0000+568.80, Cebu Province | 2015-06-07 | 1st | Regional Office No. VII | LF | 91.983 | 420 | 2014-05-02 | 2015-06-25 | 20.75% | O | 0.386 | 0.254 | 0 | 0.03 | 0.056 | 0.033 | 75.9% | -
P.E.R.R.C Construction and Development Corpporation |  | L |  |  | GB1 | Const. of 1 Unit 3-Storey School Building | Valley Breeze Residences, mbrgy. Kay-anlog, Calamba, Laguna | 2012-10-19 | 1st | NHA | LF | 22.123 | 180 | 2012-06-11 | 2012-12-07 | -10.022 | O | 0.331 | 0.263 | 0.049 | 0.03 | 0.05 | 0.033 | 75.6 | -
P.E.R.R.C. Construction and Development Corporation | 23869 |  | AA |  |  | Malabon Homes 1 | Longos, Malabon City | 2016-02-05 | 1st | NHA | LF | 111.032 | 390 | 2014-10-15 | 2016-05-19 | -13.73 | O | 0.3904 | 0.2709 | 0.0127 | 0.03 | 0.045 | 0.017 | 76.6 | -
P.E.R.R.C. Construction and Development Corporation | 23869 | L | AAA | LA | GE | Widening of Naic Diversion including Major Junction with Indang and Governor's Drive leading to Ternate-Nasugbu Road | K0046+053-K0047+517; 7th Legislative District | 2014-11-06 | 1st | IV | LF | 30.555 | 231 | 2014-05-02 | 2014-12-18 | 0.07% | O | 0.318 | 0.299 | 0.15 | 0.023 | 0.04 | 0.017 | 84.7% | 84.7% Satisfactory
P.E.R.R.C. Construction and Development Corporation |  | L |  |  | GB1 | Const. of 1 Unit 3-Storey School Building | Valley Breeze Residences, Brgy. Kay-anlog, Calamba, Laguna | 2013-04-23 | 2nd & Final | NHA | L | 22.123 | 180 | 2012-06-11 | 2012-12-07 | 0 | C | 0.439 | 0.2 | 0.3 | - | - | - | 93.9 | 81.09% Unsatisfactory
P.J Cruz Construction and Trading (Formerly: P.J. Cruz Const.) | 14223 | L | A | MA | GB1 | Completion of School Bldg. at Rosa Susano-Novaliches E/S |  | 2009-09-14 | 1st | NCR |  | 11.463 | 152 |  |  |  | O | 0.343 | 0.227 | 0.15 | 0.02 | 0.047 | 0.033 | 82 | -
P.J San Pedro Construction and Supply | 14994 | L | B | SB | GB1 | Completion of Multi Purpose Gymnasium |  | 2009-07-08 | 1st | DOST |  | 10.426 | 226 |  |  |  | O | 0.383 | 0.3 | 0.05 | 0.03 | 0.047 | 0.067 | 87.7 | -
P.J San Pedro Construction and Supply | 14996 | L | C | SB | GB1 | Construction of Multi-Purpose Building, Brgy. Bato |  | 2009-03-02 | 1st | XI |  | 2.265 | 180 |  |  |  | O | 0.334 | 0.3 | 0.15 | 0.03 | 0.038 | 0.033 | #VALUE! | -
P.J San Pedro Construction and Supply | 14994 |  |  |  |  | Rehab./Reconst. of Damaged Paved National Roads at Davao-Cotabato Old Rd. |  | 2010-06-16 |  | XI |  | 12.257 | 113 |  |  |  | O | 0.377 | 0.24 | 0.15 | 0.03 | 0.047 | 0.033 | 87.7 | -
P.J. San Pedro Construction and Supply | 14994 | L | B | SB | GE2 | Impv't. of Drainage along Davao City Diversion Rd., Countryside Village | Davao City | 2013-03-23 | Final | XI | LF | 8.995 | 210 | 2012-06-28 | 2013-01-23 | 2.38 | C | 0.434 | 0.133 | 0.3 | - | - | - | 86.7 | 87.90% Satisfactory
P.J. San Pedro Construction and Supply | 14994 | L | B | MA | GE1 | Road Upgrading along Bayabas-Eden Road, Toril District | Davao City | 2011-03-29 | 1st | XI | LF | 8.504 | 180 | 2010-12-30 | 2011-06-27 | 17.49 | O | 0.314 | 0.3 | 0.15 | 0.03 | 0.033 | 0.05 | 87.7 | -
P.L Sebastian Construction | 1076 | L | AAA | LB | GE2 | Baobo River Irrigation Project |  | 10/21-24/08 | 2nd | NIA |  | 224.599 | 631 |  |  |  | O | 0.3677 | 0.162 | 0.07 | 0.03 | 0.042 | 0.2 | 87.17 | -
P.L Sebastian Construction | 1076 |  |  |  |  | Impvt./Widening of Agusan-Davao Rd. (Daang Maharlika) Poblacion Carmen and Poblacion Panabo Sect. |  | 2010-06-02 |  | XI |  | 30.24 | 180 |  |  |  | O | 0.366 | 0.24 | 0.15 | 0.03 | 0.051 | 0.033 | 87 | -
P.L Sebastian Construction | 1076 | L | AAA | LB | GE1 | CP-9: Imprvt./ Concreting of Surigao-Davao Oriental Coastal Road, (Manay-Boston) Cateel-Boston Section |  | 2009-09-11 | 3rd | XI |  | 197.331 | 615 |  |  |  | O | 0.374 | 0.3 | 0.15 | 0.03 | 0.054 | 0.05 | 95.8 | -
P.L Sebastian Construction | 1076 | L | AAA | LB | GE1 | Impvt./Conc. of Surigao Sur-Davao Oriental Coastal Road (Manay Boston) Cateel-Boston Section |  | 2009-06-09 | 2nd | XI |  | 197.331 | 615 |  |  |  | O | 0.378 | 0.279 | 0.15 | 0.03 | 0.06 | 0.05 | 94.7 | -
P.L Sebastian Construction | 1076 | L | AAA | LB | GE1 | CP9: Impvt./Conc. of Surigao del Sur-Davao Oriental Coastal Road, (Manay-Boston) Cateel-Boston Section) |  | 2008-11-25 | 1st | XI |  | 197.331 | 615 |  |  |  | O | 0.393 | 0.271 | 0.1 | 0.03 | 0.065 | 0.1 | 95.9 | -
P.L Sebastian Construction | 1076 | L | AAA | LB | GE1 | Impvt./Conc. of Kapalong-Talaingod-Valencia, Bukidnon Road, Brgy. Tiburcia -Brgy. Sto. Nino Section |  | 2009-06-03 | 2nd | XI |  | 226.942 | 600 |  |  |  | O | 0.373 | 0.3 | 0.15 | 0.03 | 0.047 | 0.05 | 95 | -
P.L Sebastian Construction | 1076 | L | AAA | LB | GE1 | Impv't/Conc. of Kapalong-Talaingod-Valencia Bukidnon Road, Brgy. Tiburcia to Brgy. Sto. Nino Sect. |  | 2009-03-14 | 1st | XI |  | 226.943 | 600 |  |  |  | O | 0.375 | 0.3 | 0.15 | 0.03 | 0.06 | 0.05 | #VALUE! | -
P.L Sebastian Construction | 1076 | L | AAA | LB | GE1 | Rehab./Reconst./Upgrading of Carmen-Dapecol Compound Road |  | 2009-09-07 | 2nd | XI |  | 67.347 | 180 |  |  |  | O | 0.347 | 0.3 | 0.15 | 0.03 | 0.047 | 0.05 | 92.4 | -
P.L Sebastian Construction | 1076 | L | AAA | LB | GE1 | Rehab./Recons/Upgrading of Carmen-Dapecol Compound Road |  | 2009-06-01 | 1st | XI |  | 67.346 | 180 |  |  |  | O | 0.356 | 0.278 | 0.15 | 0.03 | 0.047 | 0.05 | 91.1 | -
P.L Sebastian Construction | 1076 | L | AAA | LB | GE1 | Rehab./Recons/Upgrading of Tagum-Panabo Circumferential Road |  | 2009-06-01 | 1st | XI |  | 96.181 | 200 |  |  |  | O | 0.4 | 0.197 | 0.12 | 0.03 | 0.042 | 0.033 | 82.2 | -
P.L. Sebastian Construction | 35840 | L | AAA | LB | GE2 | Dummun River Irrigation System, Cagayan - Batanes IMO, Region 2 PIDP2-C-DRISN-1 | Gattaran, Cagayan, Region 2 | 2014-04-26 | 1st & Final | NIA | LF | 67.006 | 911 | 2012-09-24 | 2014-03-24 | 45.29 | C | 0.432 | 0.2 | 0.3 | - | - | - | 93.2 | *93.21% V. Satisfactory
P.L. Sebastian Construction | 35840 | L | AAA | LB | GE | Replacement of Tiblawan Bridge and approaches along Tibanban-Lavigan Road | Davao Oriental | 2014-08-14 | Final | XI | LF | 61.263 | 375 | 2013-04-01 | 2014-04-10 | 0 | C | 0.482 | 0.2 | 0.3 |  |  |  | 98.2 | 82.48% Satisfactory
P.L. Sebastian Construction | 35840 | L | AAA | LB | GE1 | Replacement of Tiblawan Bridge & Approaches along Tibanban-Lavigan Rd. | Governor Generoso, Davao Oriental | 2013-08-15 | 1st | XI | LF | 61.263 | 210 | 2013-04-01 | 2013-10-27 | -8.44 | O | 0.333 | 0.225 | 0.066 | 0.03 | 0.033 | 0.033 | 72
P.L. Sebastian Construction | 35840 | L | AAA | LB | GE | Road Upgrading (Gravel to Paved) along Compostela - Cateel Road, Bango Section | Compostela, Comval Province | 2014-10-26 | 1st & Final | XI | LF | 46.9929 | 250 | 2014-01-20 | 2014-09-26 |  | C | 0.366 | 0.189 | 0.3 | - | - | - | 85.5% | 85.5% Satisfactory
P.L. Sebastian Construction / R.D. Interior Junior Construction / Wee Eng Construction Inc. (JV) | JV-10-040 | L | AAA | LB | GE1 | Impvt. of Digos-Cotabato Rd., Contract Package-R1 - 2.7B, Kidapawan-Pagalungan Sect. under NRIMP II | Mindanao | 2012-08-13 | 1st | NRIM-PMO | FA | 379.1 | 639 | 2011-08-17 | 2013-05-16 | 3.347 | O | 0.39 | 0.245 | 0.15 | 0.03 | 0.056 | 0.05 | 92.1 | -
P.L. Sebastian Construction/ R.D. Interior Junior Construction / Wee Eng Construction Inc. (JV) | JV-10-040 | L | AAA | LB | GE1 | Impv't. of Digos-Cotabato Rd., Contract Package-R1-2.7B, Kidapawan-Pagalungan Sect. under the Nat'l Rds. Impv't. & Mgt. Program Phase II (NRIMP II) | Mindanao | 2013-03-17 | 2nd | XII | FA | 379.1 | 639 | 2011-08-17 | 2013-05-16 | -4.98 | O | 0.317 | 0.3 | 0.1 | 0.03 | 0.055 | 0.033 | 83.5 | -
P.S. Sepian Construction and Trucking | 20519 | L | A | MB | GE | Upgrading of Balili-Suyo-Sagada Road leading to Sagada Cave, Rice Terraces and Water Falls, Bontoc, Mountain Province | Sgada, Mt. Province | 2014-08-12 | 1st | CAR | LF | 92.1882 | 237 | 2014-04-28 | 2014-12-20 | 5.31 | O | 0.373 | 0.24 | 0.15 | 0.024 | 0.05 | 0.05 | 88.7
P.T. Diamond Merchandise and Construction | 15451 | L | B | MA | GE | Rehabilitation of Local Roads, Barangay Poblacion, Bangued, Abra | Bangued, Abra | 2014-08-11 | 1st & Final | CAR | LF | 9.772 | 38 | 2014-05-19 | 2014-06-25 | 0 | C | 0.445 | 0.133 | 0.3 |  |  |  | 87.8 | 87.80% Satisfactory
P.T. Diamond Merchandise and Construction | 15451 | L | B | SB | GE | Rehabilitation of Revetment/Protection Works along Parsua River | Magsingal, Ilocos Sur | 2014-10-23 | 1st & Final | I | LF | 7.1291 | 71 | 2014-02-26 | 2014-05-07 | 0% | C | 0.438 | 0.133 | 0.3 | - | - | - | 87.1% | 87.1% Satisfactory
P.T. Diamond Merchandise and Construction | 15451 | L | B | MA | GE | Rehabilitation of Road Along Manila North Road (MNR) | Poblacion, Sto. Domingo, Ilocos Sur | 2015-10-23 | 1st & Final | I | LF | 9.2649 | 121 | 2014-06-03 | 2014-10-01 | 0% | C | 0.441 | 0.2 | 0.3 | - | - | - | 94.1% | 94.1% Very Satisfactory
P.T. Diamond Merchandise and Construction | 15451 | L | B | MA | GE | Rehabilitation of Roads along Manila North Road Km. 423+500 to Km. 429+700 w/ Exception | Poblacion, San Juan, Ilocos Sur | 2014-10-23 | 1st & Final | I | LF | 9.184 | 150 | 2014-04-25 | 2014-09-21 | 54% | C | 0.453 | 0.168 | 0.3 | - | - | - | 92.1% | 92.1% Very Satisfactory
P.T. DIAMOND MERCHANDISE AND CONSTRUCTION | 15451 | L | B | MA | GE | Replacement of Magsingal Bridge Along Manila North Road (MNR), Magsingal, Ilocos Sur | Along Manila North Road (MNR), Magsingal, Ilocos Sur | 2015-08-27 | 1st | Ilocos Sur 1st DEO | LF | 21.076 | 192 | 2015-04-13 | 2015-10-22 | (-)4.85 | O | 0.366 | 0.279 | 0.102 | 0.023 | 0.042 | 0.033 | 84.5% | -
P.T. DIAMOND MERCHANDISE AND CONSTRUCTION | 15451 | L | B | MA | GE | Construction of New Permanent Bridge, Sulvec Bridge 2, along MNR, Narvacan, Ilocos Sur | Narvacan, Ilocos Sur | 2015-08-28 | 1st | Ilocos Sur 2nd DEO | LF | 13.274 | 251 | 2015-02-04 | 2015-10-13 | - | O | 0.375 | 0.212 | 0.15 | 0.03 | 0.047 | 0.05 | 86.4% | -
Pablo S. Labasbas Construction | 6302 | L | B | MA | GE1 | Repair of Damaged Rd. Sect. along Looc-Odionagan-San Andres Rd., Km.3+334.30-Km.17+500 (IS) / (Km.3+400-Km.17+500 (IS) | Tablas Island, Romblon | 2012-11-29 | 1st | IVB | LF | 10.102 | 150 | 2012-07-13 | 2012-12-09 | 2.5 | O | 0.353 | 0.24 | 0.15 | 0.023 | 0.04 | 0.033 | 83.9 | -
Pablo S. Labasbas Construction | 6302 | L | B | MA | GE | Repair/Rehab./Imprv't. of Malayog Flood Control | Calbayog City, Samar | 2014-08-13 | Final | VIII | LF | 17.8171 | 150 | 2013-04-17 | 2013-09-13 | 14.67 | C | 0.48 | 0.133 | 0.3 |  |  |  | 91.3 | 90.46% Very Satisfactory
Pablo S. Labasbas Construction | 6302 | L | B | MA | GE | Raising of Grade & Drainage (Flooded Section) Jct. Buenavista - Lawaan - Marabut Road KO997+448.80 - KO998+292 | Quinapondan, Eastern Samar | 2014-08-14 | Final | VIII | LF | 21.3608 | 138 | 2013-01-30 | 2013-06-16 | 0 | C | 0.341 | 0.2 | 0.3 |  |  |  | 84.1 | 73.78% Poor
Pablo S. Labasbas Construction | 6302 | L | B | MA | GB1 | Const. of 1 unit-2 Storey 8 CL Sch. Bldg. & 1 unit-1 Storey 3 CL Sch. Bldg,. Carigara School of Fisheries | Carigara, Leyte | 2013-08-17 | 1st | VIII | LF | 11.222 | 200 | 2013-03-22 | 2013-10-07 | 0.36 | O | 0.347 | 0.24 | 0.15 | 0.023 | 0.045 | 0.05 | 85.5
Pablo S. Labasbas Construction | 6302 | L | B | MA | GE2 | Repair/Rehab./Impv't. of Malayog Flood Control, Brgy. Malayog | Calbayog City, Samar | 2013-08-13 | 1st | VIII | LF | 17.817 | 150 | 2013-02-17 | 2013-09-13 | 16.93 | O | 0.391 | 0.24 | 0.15 | 0.03 | 0.055 | 0.033 | 89.9
Pablo S. Labasbas Construction | 6302 | L | B | MA | GE2 | Const. of Retaining Wall and Line Ditch Canal along Calbayog-Allen Rd., K0699+200-K0713+000 w/ exceptions | Calbayog City, Samar | 2013-08-13 | 1st | VIII | LF | 19.3 | 150 | 2013-04-17 | 2013-09-13 | 6.77 | O | 0.335 | 0.24 | 0.15 | 0.03 | 0.055 | 0.033 | 84.3
Pablo S. Labasbas Construction | 6302 | L | B | MA | GE1 | Raising of Grade & Drainage (Flooded Sect.) Jct. Buenavista-Lawaan-Marabut Rd., K0997+448.80-K0998+292 | Quinapondan, Eastern Samar | 2013-08-19 | 1st | VIII | LF | 21.361 | 148 | 2013-01-30 | 2013-06-26 | -39.95 | O | 0.272 | 0.3 | 0 | 0.03 | 0.05 | 0.017 | 66.9
Pablo S. Labasbas Construction | 6302 | L | B | MA | GE1 | Const. of Gandara-Matuguinao Road |  | 2009-03-10 | 1st | VIII |  | 24.121 | 240 |  |  |  | O | 0.351 | 0.24 | 0.15 | 0.03 | 0.047 | 0.033 | #VALUE! | -
Pablo S. Labasbas Construction | 6302 | L | B | MA | GE | Concreting of Jct. Bolod-Bolod - Albor Road, Libjo, Dinagat Island | Libjo, Dinagat Islands | 2014-10-27 | 1st | XIII | LF | 23.6997 | 225 | 2014-03-21 | 2014-10-31 | -21.57% | O | 0.272 | 0.239 | 0 | 0.024 | 0.042 | 0.033 | 61% | 61% Poor
Pablo S. Labasbas Construction |  | L |  |  |  | Help for Catubig Agricultural Advancement Project HCAAP-LCB-C3-2012 | Catubig, Northern Samar/Region 8 | 2014-03-15 | 1st | NIA | LF | 17.663 | 577 | 2012-08-16 | 2014-04-13 | -9.38 | O | 0.3862 | 0.2608 | 0.0517 | 0.03 | 0.07 | 0.05 | 84.87 | -
Pablo S. Labasbas Construction | [5 empty] | WSIIMO Contract No. 10-2014 | Gandara, Western Samar | 2015-11-21 | 1st | NIA | LF | 14.215 | 300 | 2014-08-29 | 2015-11-30 | -4 | O | 0.38 | 0.222 | 0.11 | 0.018 | 0.051 | 0.05 | 83.1 | -
Pacific Concrete Products, Inc. | 17150 | L | AAA | LB |  | Virac Airport Development Project | Virac, Cantanduanes/ Region V | 2016-06-01 | 2nd | DOTC | LF | 101.151 | 231 | 2015-04-13 | 2016-06-19 | -15.47 | O | 0.4 | 0.3 | 0 | 0.03 | 0.0467 | 0.05 | 82.67 | -
Pacific Concrete Products, Inc. | 17150 | L | AAA | LB |  | Virac Airport Development Project | Virac, Cantanduanes/ Region V | 2016-09-07 | 2nd & Final | DOTC | LF | 101.1511 | 231 | 2015-04-13 | 2016-06-19 | 0 | C | 0.5 | 0.2 | 0.3 | - | - | - | 100 | 89.60% Very Satisfactory
Pacific Star Erectors | 14224 | L | B | MA | GE1 | Const. of Bunot Bridge along Apayao (Calanasan)-Ilocos Norte Rd. | Calanasan, Apayao | 2013-03-22 | 1st | CAR | LF | 10.398 | 165 | 2013-01-25 | 2013-07-08 | -5.95 | O | 0.363 | 0.3 | 0.09 | 0.022 | 0.025 | 0.033 | 83.3 | -
Pacific Star Erectors | 14224 | L | B | MA | GB1 | Const. of Apayao State College MPB (Phase IV) |  | 2009-05-30 | 1st | CAR |  | 4.717 | 180 |  |  |  | O | 0.343 | 0.292 | 0.15 | 0.03 | 0.029 | 0.033 | 87.7 | -
Pacific Star Erectors | 14224 | L | B | MA | GB1 | Construction of Apayao State College Multi-Purpose Building |  | 2009-02-28 | 2nd | CAR |  | 2.324 | 150 |  |  |  | O | 0.391 | 0.3 | 0.15 | 0.03 | 0.045 | 0.033 | #VALUE! | -
Pacific Star Erectors | 14224 | L | B | MA | GB1 | Construction of Pudtol MPB (Gymnasium) Phase IV |  | 2009-02-27 | 1st | CAR |  | 6.613 | 210 |  |  |  | O | 0.327 | 0.3 | 0.15 | 0.022 | 0.041 | 0.033 | #VALUE! | -
Pacific Stars Erectors | 14224 | L | B | MA | GB1 | Const. of DPWH Regional Office Building (Phase VII) Region II | Tuguegarao City, Cagayan | 2011-04-03 | 1st | II | LF | 10.605 | 300 | 2010-06-28 | 2011-04-23 | 2.92 | O | 0.386 | 0.3 | 0.15 | 0.023 | 0.037 | 0.033 | 92.9 | -
Pacific Stars Erectors | 14225 | L | B | MA | GB1 | Construction of Apayao State College MPB (Phase IV) |  | 2009-09-04 | 2nd | CAR |  | 4.712 | 199 |  |  |  | O | 0.393 | 0.24 | 0.15 | 0.03 | 0.056 | 0.033 | 90.2 | -
Pacific Stars Erectors | 14224 | L | B | MA | GB1 | Construction of Pudtol MPB (Gymnasium) |  | 2009-09-04 | 2nd | CAR |  | 6.613 | 266 |  |  |  | O | 0.396 | 0.24 | 0.15 | 0.03 | 0.056 | 0.033 | 90.5 | -
Pader Construction and Supply | 20213 | L | B | SB | GE | Road Upgrading (Gravel to Concrete) along Bukidnon - Cotabato Road,Tambad, Carmen, Cotabato (Km. 1608+572 - Km. 1608+634.41) | Carmen, Cotabato | 2014-08-11 | 1st & Final | XII | LF | 1.5121 | 49 | 2014-02-21 | 2014-04-11 | 7.55 | C | 0.457 | 0.149 | 0.3 |  |  |  | 90.6 | 90.60% Very Satisfactory
Pader Construction and Supply | 20213 | L | B | SB | GB1 | Construction of 2 CL SB at Eliseo E/S |  | 2009-03-04 | 1st | XII |  | 1.047 | 70 |  |  |  | O | 0.353 | 0.3 | 0.15 | 0.03 | 0.035 | 0.033 | #VALUE! | -
Palmares General Merchandise | 24657 | L | B | SB | GE | Repair/Rehab. Of Banga River Flood Control and Drainage along Cotabato - Marbel Road, Kibid - Dumaguil Section | Norala, South Cotabato | 2014-08-05 | Final | XII | LF | 7.8499 | 120 | 2013-05-24 | 2013-09-20 | 1.7 | C | 0.418 | 0.2 | 0.3 |  |  |  | 91.8 | 85.98% Satisfactory
Palmares General Merchandise | 24657 | L | B | SB | GE2 | Repair/Rehab. of Banga River Flood Control & Drainage along Cotabato-Marbel Rd., Kibid-Dumaguil Sect. | Norala, South Cotabato | 2013-08-06 | 1st | XII | LF | 7.85 | 120 | 2013-05-24 | 2013-09-20 | 8.3 | O | 0.24 | 0.3 | 0.15 | 0.03 | 0.051 | 0.05 | 82.1
PALMARES GENERAL MERCHANDISE | 24657 | L | B | SB | GB | Cluster MP-5 c) Const of MPB at Brgy. Mangilala | Tacurong City & Pres. Quirino, Sultan Kudarat | 2015-08-31 | 1st & Final | Sultan Kudarat 1st | LF | 2.455 | 130 | 2015-03-04 | 2015-07-11 | (-) 4.98% | C | 0.5 | 0.2 | 0.151 | - | - | - | 85.1% | *85.1% Satisfactory
Palmea Construction & Development | 8200 | L |  | MA | GE2 | Construction of Lateral "A" at Sta. 5+299.75 - Sta 5+510.80 of Laris | Rosales, Pangasinan Region I | 02/27-03/03/12 | 1st | NIA | FA | 3.904 | 60 | 2011-11-21 | 2012-01-19 | -4.41 | O | 0.3741 | 0.287 | 0.1059 | 0.03 | 0.0382 | 0.05 | 88.52 | -
PANAAD CONSTRUCTION | 186 | L | D | SB | GB | Construction of Multi-Purpose Building, Brgy. Apoc-Apoc | Aborlan, Palawan | 2015-11-12 | Final | Palawan 3rd DEO | LF | 3.7972 | 186 | 2015-03-21 | 2015-09-23 | 0.0468 | C | 0.404 | 0.133 | 0.3 | - | - | - | 83.7% | 83.7% Satisfactory
Panay East Coast Construction & Supply | 26469 |  |  |  |  | Jalaur-Suage River Irrigation System |  | 01/10-15/11 |  | NIA |  | 3.307 | 224 |  |  |  | O | 0.389 | 0.2407 | 0.0792 | 0.03 | 0.0573 | 0.05 | 84.62 | -
Panay East Coast Construction & Supply | 26469 |  |  |  |  | Impvt. of Drainage System, Brgy. Poblacion (along Plaza) |  | 2010-03-05 |  | VI |  | 0.481 | 60 |  |  |  | O | 0.347 | 0.3 | 0.044 | 0.01 | 0.023 | 0.033 | 75.7 | -
Panay East Coast Construction & Supply | 26469 | L | D | SB | GE1 | Rd. Upgrading (Gravel to Paved) of Nat'l Secondary Rd., Guimbal-Igbaras-Tubungan-Leon Rd., K0067+591-K0067+992.6 Brgy. Tina-an Sur Sect. | Leon, Iloilo | 2013-08-22 | Final | VI | LF | 6.129 | 90 | 2013-01-21 | 2013-04-20 | 0 | C | 0.463 | 0.133 | 0.3 | - | - | - | 89.6 | 91.94% V. Satisfactory
Panay East Coast Construction & Supply | 26469 | L | D | SB | GE1 | Road Upgrading (Gravel to Paved) of Nat'l. Secondary Rd., Guimbal-Igbaras-Tubungan-Leon Rd., K0067+591-K0067+992.6, Brgy. Tina-an Sur Sect. | Leon, Iloilo | 2013-03-22 | 1st | VI | LF | 6.129 | 90 | 2013-01-21 | 2013-04-20 | 1.06 | O | 0.36 | 0.3 | 0.15 | 0.03 | 0.045 | 0.05 | 93.5 | -
PANAY EAST COAST CONSTRUCTION AND SUPPLY | 26469 | L | D | SB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads Including Drainage Based on Pavement Management System/Highway Development Management-4 (HDM-4) (Intermittent Section), Concreting of Pototan-Tabugon Road | K0031+(-429) to K0031+366, Pototan, Iloilo | 2015-06-10 | 1st | Iloilo Second DEO | LF | 13.45 | 115 | 2015-03-18 | 2015-07-10 | 0.96% | O | 0.371 | 0.284 | 0.15 | 0.022 | 0.03 | 0.05 | 90.7% | -
PANAY EAST COAST CONSTRUCTION AND SUPPLY | 26469 | L | D | SB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Secondary Roads (Intermittent Sections), Delgado Streets | Chainage 1288-1582, Iloilo City | 2015-06-02 | 1st | Iloilo City DEO | LF | 11.125 | 102 | 2015-03-10 | 2015-06-19 | 3% | O | 0.348 | 0.21 | 0.15 | 0.03 | 0.035 | 0.05 | 82.3% | -
PANAY EAST COAST CONSTRUCTION AND SUPPLY | 26469 | L | D | SB | GE | Side Slope Protection along Mambusao-Imbug Road | K096+000-K097+000 (with Exception) (Intermittent Section), Capiz | 2015-06-08 | Final | Capiz Second DEO | LF | 1.418 | 60 | 2015-01-19 | 2015-03-19 | 1.67% | C | 0.355 | 0.171 | 0.3 | - | - | - | 82.6% | *82.6% Satisfactory
PANAY EAST COAST CONSTRUCTION AND SUPPLY | 26469 | L | D | SB | GE | Rehabilitation/Reconstruction/Ugrading of Damaged Paved National Secondary Roads (Intermittent Sections), Delgado Streets-Chainage 1288-1582 | Iloilo City | 2015-08-24 | 1st & Final | Iloilo City | LF | 11.125 | 102 | 2015-03-10 | 2015-06-19 | 3.15% | C | 0.44 | 0.133 | 0.3 | - | - | - | 87.3% | *87.3% Satisfactory
PANAY EAST COAST CONSTRUCTION AND SUPPLY | 26469 | L | D | SB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads including Drainage Based on PMS/HDM-4 (Intermittent Section), Concreting of Pototan-Tabugon Road, Pototan, Iloilo, KO031+(-429)-KO031+366 | Pototan, Iloilo | 2015-11-17 | Final | Iloilo 2nd | LF | 13.4495 | 115 | 2015-03-18 | 2015-07-11 | 0.00% | C | 0.369 | 0.2 | 0.3 | - | - | - | 86.9% | 86.9% Satisfactory
Pangasinan New Wilson Lumber & Construction | 8313 | L | B | MA | GE | Widening of Camiling-Wawa-Bayambang-Malasiqui-Sta. Barbara Road (Malasiqui Section) Km. 193+490 to Km. 194+120 | Malasiqui, Pangasinan | 2014-08-12 | Final | I | LF | 20.1651 | 193 | 2013-02-04 | 2013-08-15 | 0 | C | 0.418 | 0.133 | 0.3 |  |  |  | 85.1 | 84.77% Satisfactory
Pangasinan New Wilson Lumber & Construction | 8313 | L | B | MA | GE1 | Widening of Camiling-Wawa-Bayambang-Malasiqui-Sta. Barbara Rd. (Malasiqui Sect.) Km.193+490-Km.194+120 | Malasiqui, Pangasinan | 2013-03-14 | 1st | I | LF | 20.166 | 170 | 2013-02-04 | 2013-07-23 | -12.48 | O | 0.397 | 0.3 | 0.025 | 0.015 | 0.029 | 0.033 | 79.9 | -
Pangasinan New Wilson Lumber & Construction | 8313 | L | B | MA | GE | Widening of Camiling-Wawa-Bayambang-Malasiqui-Sta. Barbara Road (Bayambang Section) Km. 180+440 to Km. 181+247.85, Pangasinan (Phase II) | Bayambang, Pangasinan | 2014-08-12 | Final | I | LF | 21.7134 | 200 | 2013-02-04 | 2013-08-23 | 2.61 | C | 0.38 | 0.2 | 0.3 |  |  |  | 88 | 83.74% Satisfactory
Pangasinan New Wilson Lumber & Construction | 8313 | L | B | MA | GE1 | Widening of Camiling-Wawa-Bayambang-Malasiqui-Sta. Barbara Rd. (Bayambang Sect.) Km.180+500-Km. 181+120, (Phase II) | Bayambang, Pangasinan | 2013-08-03 | 1st | I | LF | 21.713 | 200 | 2013-01-16 | 2013-08-03 | -10.61 | O | 0.343 | 0.3 | 0.044 | 0.03 | 0.042 | 0.05 | 80.9
Pangasinan New Wilson Lumber & Construction | 8313 | L | B | MA | GE1 | Widening of Camiling-Wawa-Bayambang-Malasiqui-Sta. Barbara Rd. (Malasiqui Sect.) Km. 193+490-Km. 194+120 | Malasiqui, Pangasinan | 2013-08-02 | 2nd | I | LF | 20.166 | 200 | 2013-02-04 | 2013-08-22 | 2.65 | O | 0.332 | 0.3 | 0.15 | 0.03 | 0.047 | 0.033 | 89.2
Pangasinan New Wilson Lumber & Construction / Pas Construction & Supplies (JV) | JV-12-463 | L | B | MA | GE1 | Repair/Rehab./Impv't. of Lingayen-Binmaley Rd. K0363+(-762)-K0364+061 w/ exception | Pangasinan | 2013-08-06 | Final | I | LF | 9.404 | 76 | 2013-01-15 | 2013-03-31 | 7.9 | C | 0.471 | 0.133 | 0.3 | - | - | - | 90.4 | 89.68% V. Satisfactory
PANGASINAN NEW WILSON LUMBER & CONSTRUCTION SUPPLY/JASA BUILDER (JV) | JJV-14-689 | L | A | MA | GE | Construction/Upgrading/Rehabilitation of Drainage along Pangasinan-Zambales Road | KO354+000 - KO356+000, Bugallon, Pangasinan | 2015-06-11 | 1st | Pangasinan 2nd DEO | LF | 18.62 | 150 | 2015-03-02 | 2015-07-29 | 6% | O | 0.337 | 0.24 | 0.15 | 0.03 | 0.055 | 0.033 | 84.5% | -
Pangasinan New Wilson Lumber / Pas Construction & Supplies (JV) | JV-12-463 | L | B | MA | GE1 | Repair/Rehab./Impv't. of Lingayen-Binmaley Rd., K0363+(-762)-K0364+061 w/ exception | Pangasinan | 2013-03-16 | 1st | I | LF | 9.405 | 76 | 2013-01-15 | 2013-03-31 | 33.41 | O | 0.339 | 0.3 | 0.15 | 0.03 | 0.04 | 0.033 | 89.2 | -
Partido Construction & Supply | 20631 | L | B | MA | GE1 | Impvt. of Jct. Digdigon (GOA)-Tinambac Road, (Balaynan-Tierra Nevada Section) |  | 2009-09-09 | 2nd | V |  | 21.358 | 175 |  |  |  | O | 0.318 | 0.3 | 0.15 | 0.03 | 0.051 | 0.05 | 89.9 | -
Partido Construction & Supply | 20631 | L | B | MA | GE1 | Impvt. of Junction Digdigon (GOA)-Tinambac Road, (Balaynan-Tierra Nevada Sect.) |  | 2009-05-31 | 1st | V |  | 21.358 | 150 |  |  |  | O | 0.303 | 0.3 | 0.15 | 0.03 | 0.055 | 0.05 | 88.8 | -
Partido Construction & Supply | 20631 | L | B | MA | GE1 | Conc. of Bagong Silang Capalonga Road, Katabangan Sect. |  | 2009-06-04 | 1st | V |  | 6.021 | 180 |  |  |  | O | 0.366 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 88.6 | -
Partido Construction & Supply | 20631 | L | B | MA | GE1 | Conc.of Goa-Tinambac Road, Payatan-Tupi-Tierra Nevaion |  | 2009-03-10 | 1st | V |  | 4.704 | 165 |  |  |  | O | 0.388 | 0.24 | 0.15 | 0.03 | 0.056 | 0.05 | #VALUE! | -
Partido Construction & Supply | 20631 | L | B | MA | GE | Road Upgrading (Gravel to Paved) of Digdigon (Goa)-Tinambac Road, Goa, Camarines Sur K0496+072 - K0496+343 | Digdigon (Goa)-Tinambac, Goa, Camarines Sur | 2014-11-13 | 1st & Final | V | LF | 7.1242 | 105 | 2014-03-03 | 2014-06-15 | 4.76% | C | 0.451 | 0.155 | 0.3 | - | - | - | 90.6% | 90.6% Very Satisfactory
Partido Construction & Supply | 20631 | L | B | MA | GE | Road Upgrading (Gravel to Paved) of Jct. Digdigon (Goa) - Tinambac Road, K0496+072 - K0496+388 with exceptions | Goa, Camarines Sur | 2014-08-09 | 1st & Final | V | LF | 7.1242 | 105 | 2014-03-03 | 2014-06-15 | 4.76 | C | 0.401 | 0.164 | 0.3 |  |  |  | 86.5 | 86.50% Satisfactory
PARTIDO CONSTRUCTION AND SUPPLY | 20631 | L | B | MA | GE | Concreting of Roads at Baliuag Viejo to San Jose Road, Minalabac, Camarines Sur | Minalabac, Camarines Sur | 2015-11-12 | Final | Camarines Sur First DEO | LF | 4.5639 | 118 | 2015-03-04 | 2015-06-29 | 2.41% | C | 0.397 | 0.13 | 0.3 | - | - | - | 82.7% | 82.7% Satisfactory
PAS Construction & Supplies | 32890 | L | D | SB | GE | Preventive Maintenance along Pangasinan- Zambales Road K0353+860 to K0354+500 | Bugallon, Pangasinan | 2014-10-28 | 1st & Final | I | LF | 6.6732 | 10 | 2014-02-14 | 2014-02-23 | 0% | C | 0.468 | 0.136 | 0.3 | - | - | - | 90.4% | 90.4% Very Satisfactory
Pascal Construction | 34168 | L | A | SB | GE | Rehabilitation and/or Improvement of Tourism Activity Center | Baler, Aurora | 2014-05-14 | Final | TIEZA | LF | 2.497 | 120 | 2013-11-21 | 2014-05-05 | 0 | C | 0.48 | 0.2 | 0.3 |  |  |  | 98 | 98.00% Outstanding
PASTRANA CONSTRUCTION & SUPPLIES | 17340 | L | B | SB | GE | Local Infrastructure Program- Concreting of Barangay Road | Brgy. Joyao-Joyao, Numancia, Aklan | 2015-06-05 | Final | Aklan DEO | LF | 1.924 | 52 | 2015-02-20 | 2015-04-12 | 7.52% | C | 0.401 | 0.185 | 0.3 | - | - | - | 88.6% | *88.6% Satisfactory
Patrick Construction | 27780 | L | D | SB | GE | Rehabilitation of Bridge Approach along Dugo-San Vicente Road (DSVR), Palagao Bridge No. 2, KO591+1097, Simpatuyo | Sta. Teresita, Cagayan | 2014-10-20 | 1st & Final | II | LF | 1.3864 | 52 | 2014-03-13 | 2014-05-03 | 5% | C | 0.404 | 0.2 | 0.15 | - | - | - | 75.4% | 75.4% Unsatisfactory
Patrila Builders, Inc. | 26628 | L | A | MA | GE | Widening of Iloilo East Coast-Estancia Wharf Road K0178+(-817) - K0179+040 | Estancia, Iloilo | 2014-10-29 | 1st | VI | LF | 42.6986 | 323 | 2014-04-24 | 2015-03-12 | 30.86% | O | 0.366 | 0.21 | 0.15 | 0.03 | 0.054 | 0.05 | 86% | 86% Satisfactory
Patrila Builders, Inc. | 26658 | L | A | MA | GE1 | Upgrading/Conc. of Ajuy-Concepcion Road |  | 2009-09-08 | 3rd | VI |  | 9.233 | 240 |  |  |  | O | 0.322 | 0.286 | 0 | 0.03 | 0.05 | 0.05 | 73.8 | -
Patrila Builders, Inc. | 26628 | L | A | MA | GE1 | Upgrading/Concreting of Ajuy-Concepcion Road |  | 2009-06-09 | 2nd | VI |  | 9.233 | 240 |  |  |  | O | 0.373 | 0.3 | 0.15 | 0.03 | 0.05 | 0.05 | 95.3 | -
Patrila Builders, Inc. | 26628 | L | A | MA | GE1 | Upgrading/Conc. of Ajuy-Concepcion Road |  | 2009-03-17 | 1st | VI |  | 8.394 | 180 |  |  |  | O | 0.362 | 0.3 | 0.15 | 0.03 | 0.055 | 0.05 | #VALUE! | -
Patrila Builders, Inc. | 26628 | L |  |  | GE1 | Rehabilitation of San Miguel-Sebaste, Sibunag/Region VI | Maabay, Bubog & sebaste, Sibunag/region VI | 2011-06-10 | 1st | Guimaras | LF | 25.649 | 30 weeks | 2012-03-21 | 2011-09-16 | 25.509 | O | 0.4 | 0.3 | 0.15 | 0.03 | 0.07 | 0.05 | 100 | -
Patrila Builders, Inc. | 26628 | L |  |  | GE1 | Rehabilitation of San Miguel-Sebaste, Sibunag/Region VI | Maabay, Bubog & sebaste, Sibunag/region VI | 2011-08-15 | 2nd | Guimaras | LF | 28.022 | 34 weeks | 2012-03-21 | 2011-10-16 | 11.195 | O | 0.399 | 0.3 | 0.15 | 0.024 | 0.07 | 0.05 | 99.3 | -
PATRILA BUILDERS, INC. | 26628 | L | A | MA | GB | Construction of 2-Storey Municipal Hall Annex Building, Municipality of Leon, Iloilo 2nd LD | Municipality of Leon, Iloilo 2nd LD | 2015-11-16 | 1st | Iloilo 4th | LF | 4.798 | 150 | 2015-08-14 | 2016-01-11 | (+) 0.1% | OG | 0.34 | 0.3 | 0.15 | 0.03 | 0.053 | 0.05 | 92.3% | 92.3% Very Satisfactory
Patrila Builders, Inc. | 26628 | L |  |  | GE1 | Rehabilitation of San Miguel-Sebaste Road | San Miguel, Jordan & Sebaste Road | 2011-08-15 | 2nd | PPA | LF | 25.649 | 30 | 2011-03-21 | 2011-09-16 | 11.195 | O | 0.399 | 0.3 | 0.15 | 0.024 | 0.07 | 0.05 | 99.3 | -
Patrilla Builders Inc. | 26628 | L | A |  |  | Construction of Gaban CIP | San Lorenzo, Guimaras | 2014-04-05 | 1st & Final | NIA | LF | 3.339 | 120 | 2014-02-02 | 2014-06-01 | 56.65 | C | 0.427 | 0.191 | 0.3 | - | - | - | 91.8 | *91.80% V. Satisfactory
Paula Mae Buhong Construction | 26128 | L | B | MA | GE | Road Upgrading (Gravel to Paved) Along Banaue-Hungduan-Benguet Bdry Road, K0368+000 to K0370+300, Hungduan, Ifugao | Hunguduan,Ifugao | 2014-08-05 | Final | CAR | LF | 48.461 | 328 | 2013-01-31 | 2013-12-24 | 0 | C | 0.418 | 0.133 | 0.3 |  |  |  | 85.1 | 87.08% Satisfactory
Paula Mae Buhong Construction | 26128 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Conc.) of Banaue-Hungduan-Benguet Bdry. Rd., K0368+000-K0370+300 | Hungduan, Ifugao | 2013-08-04 | 1st | CAR | LF | 44.934 | 296 | 2013-01-31 | 2013-11-22 | 1.57 | O | 0.371 | 0.24 | 0.15 | 0.023 | 0.05 | 0.05 | 88.4
Paula Mae Buhong Construction | 26128 |  |  |  |  | Widening/Concreting of Banaue-Hungduan-Tinoc-Benguet Bdry. Rd., Hwang Section |  | 2010-02-25 |  | CAR |  | 4.739 | 349 |  |  |  | O | 0.356 | 0.24 | 0.15 | 0.03 | 0.03 | 0.033 | 83.9 | -
PBO Construction | 18403 | L | AA | MB | GE1 | Impvt./Widening/Conc. of Bontoc-Tabuk-Tuguegarao Road, Phase IV, Km. 461+000-Km. 467+000, Lubuagan-Cagaluan Section |  | 2009-03-04 | 2nd | CAR |  | 47.185 | 300 |  |  |  | O | 0.255 | 0.285 | 0.15 | 0.03 | 0.041 | 0.05 | #VALUE! | -
PBO Construction | 18403 | L | AA | LA | GE1 | Impvt./Widening/Conc. of Bontoc-Tabuk-Tuguegarao Road, Phase IV, Km. 461+000-Km. 467+000, Lubuagan-Cagaluan Section |  | 2008-11-19 | 1st | CAR |  | 47.185 | 300 |  |  |  | O | 0.305 | 0.24 | 0.1 | 0.03 | 0.04 | 0.1 | 81.5 | -
PBO Construction | 18403 | L | AA | MB | GE1 | Widening/Concreting of Mayoyao-Aguinaldo Road, Km. 399+000 - Km. 419+000 (w/ exception) |  | 2009-03-06 | 1st | CAR |  | 68.468 | 420 |  |  |  | O | 0.296 | 0.136 | 0.15 | 0.022 | 0.032 | 0.017 | #VALUE! | -
PBO Construction | 18403 |  |  |  |  | Widening/Concreting of Mayoyao-Aguinaldo Road, Km. 399+000 - Km. 419+000 (w/ exception) |  | 2010-02-24 |  | CAR |  | 68.441 | 473 |  |  |  | O | 0.348 | 0.24 | 0.144 | 0.03 | 0.045 | 0.033 | 84 | -
PBO Construction | 18403 | L | AA | MB | GE1 | Rd. Upgrading (Gravel to Concrete) along Kalinga-Abra Rd. K0470+000-K0472+100, Ableg-Balenciagao Sur, Pasil Sect. | Kalinga | 2012-11-26 | 1st | CAR | LF | 48.989 | 263 | 2012-04-23 | 2013-02-09 | -3.34 | O | 0.374 | 0.24 | 0.117 | 0.023 | 0.05 | 0.033 | 83.7 | -
Pearl Construction and Supply | 34806 | L | D | SB | GE1 | Conc. of Road, Brgy. Esperanza | Norala, South Cotabato | 2013-08-06 | Final | XII | LF | 2.29 | 120 | 2012-11-26 | 2013-03-25 | 0 | C | 0.468 | 0.2 | 0.15 | - | - | - | 81.8 | 85.88% Satisfactory
Pearl Construction and Supply | 34806 | L | D | SB | GE1 | Conc. of Road, Brgy. Esperenza | Norala, South Cotabato | 2013-03-20 | 1st | XII | LF | 2.29 | 120 | 2012-11-26 | 2013-03-25 | -1.63 | O | 0.36 | 0.279 | 0.134 | 0.03 | 0.05 | 0.033 | 88.6 | -
PEARL CONSTRUCTION AND SUPPLY | 34806 | L | D | SB | GE | Construction of Bukay Pait Box Culvert, K1780+282 including Inlet and Outlet Protection Works along Midsayap-Marbel Road | Tantangan, South Cotabato 2nd LD | 2015-06-02 | 1st | South Cotabato DEO | LF | 3.928 | 150 | 2015-04-01 | 2015-08-29 | 12.69% | O | 0.4 | 0.2 | 0.15 | 0.03 | 0.025 | 0.033 | 83.8% | -
PEARL CONSTRUCTION AND SUPPLY | 34806 | L | D | SB | GE | Construction of Bukay Pait Box Culvert. K1780+282 Including Inlet and Outlet Protection Works along Midsayap-Marbel Road | Tantangan, South Cotabato | 2015-09-01 | 1st | South Cotabato | LF | 3.928 | 160 | 2015-04-01 | 2015-09-07 | (+)0.76% | O | 0.387 | 0.24 | 0.15 | 0.03 | 0.045 | 0.033 | 88.5% | -
PEARL CONSTRUCTION AND SUPPLY | 34806 | L | D | SB | GE | Construction of Bukay Bait Box Culvert K1780+282 incl. inlet and outlet protection works along Midsayap-Marbel Road | Tantangan, South Cotabato, 2nd LD | 2015-11-09 | Final | South Cotabato First DEO | LF | 3.9284 | 160 | 2015-04-01 | 2015-09-07 | (-) 2.95% | C | 0.415 | 0.174 | 0.212 | - | - | - | 80.1% | 80.1% Unsatisfactory
Pentagon Industrial Development & Construction Company, Incorporated | 12796 | L | AA | LA | GE1 | Impvt./Widening of McArthur Highway (MNR)-Phase V, Meycauayan (Bulacan) to Mabalacat (Pampanga)-(Meycauayan-Marilao Section)-CP III |  | 2009-09-09 | 1st | III |  | 47.235 | 150 |  |  |  | O | 0.376 | 0.3 | 0.15 | 0.03 | 0.042 | 0.033 | 93.1 | -
Persan Construction Inc. | 2852 |  |  |  |  | Const./Conc. of Sect. Of the Third Bulacan Circum. Rd. Network Daang Maharlika-DRT Via San Ildefonso Rd. (San Ildefonso Sect.) |  | 2010-03-04 |  | III |  | 47.642 | 210 |  |  |  | O | 0.367 | 0.3 | 0.15 | 0.03 | 0.047 | 0.05 | 94.4 | -
Persan Construction Inc. | 2852 |  |  |  |  | Const./Conc. Of Sects. Of the Third Bulacan Circum. Rd. Network CVR-San Miguel-DRT-Angat Gen. Alejo Santos Highway (Akle to DRT Sect.) |  | 2010-03-04 |  | III |  | 47.642 | 210 |  |  |  | O | 0.338 | 0.296 | 0.15 | 0.03 | 0.042 | 0.05 | 90.6 | -
Persan Construction Inc. | 2852 |  |  |  |  | Conc. and Const. of Slope Protection of Pintong Bukawe FMR |  | 2010-02-18 |  | IVA |  | 19.23 | 120 |  |  |  | O | 0.333 | 0.3 | 0.15 | 0.03 | 0.05 | 0.033 | 89.6 | -
Persan Construction, Inc. | 2852 | L | AAA | LB | GE1 | Impvt./Rehab. of Daang Maharlika Road, Bulacan 3rd Congressional District |  | 2009-06-04 | 1st | III |  | 77.0941 | 150 |  |  |  | O | 0.364 | 0.3 | 0.15 | 0.03 | 0.05 | 0.05 | 94.4 | -
Persan Construction, Inc. | 2852 | L | AAA | LB | GE1 | Rehabilitation of Sibul-Biak Na Bato Road |  | 2009-06-01 | 1st | III |  | 14.2988 | 110 |  |  |  | O | 0.372 | 0.239 | 0.15 | 0.03 | 0.051 | 0.05 | 89.2 | -
Persan Construction, Inc. | 2852 | L | AAA | LB | GE1 | Impvt. And Rehab. of Daang Maharlika Road, San Rafael-San Ildefonso Section |  | 2008-11-21 | 1st | III |  | 95.473 | 120 |  |  |  | O | 0.37 | 0.3 | 0.1 | 0.018 | 0.037 | 0.1 | 92.5 | -
Persan Construction, Inc. | 2852 | L | AAA | LB | GE1 | Improvement of Pintong-Bukawe Road |  | 2009-08-24 | 1st | IVA |  | 19.232 | 180 |  |  |  | O | 0.341 | 0.285 | 0.15 | 0.03 | 0.043 | 0.05 | 89.9 | -
Persan Construction, Inc. | 2852 |  |  |  |  | Widening of Carmona Bridge (Phase I) inc. approaches |  | 2010-03-03 |  | IVA |  | 60.454 | 529 |  |  |  | O | 0.393 | 0.3 | 0.15 | 0.03 | 0.05 | 0.033 | 95.6 | -
Persan Construction, Inc. | 2852 | L | AAA | LB | GE1 | Rehab. of FMR, Brgy. Pintong Bukawe |  | 2009-03-14 | 1st | IV-A |  | 18.711 | 150 |  |  |  | O | 0.375 | 0.276 | 0.15 | 0.03 | 0.033 | 0.05 | #VALUE! | -
Persan Construction, Inc. | 2852 | L | AAA | LB | GE1 | Impvt./Rehab. of Daang Maharlika Road |  | 2009-09-08 | 2nd | III |  | 77.099 | 150 |  |  |  | O | 0.362 | 0.3 | 0.15 | 0.03 | 0.051 | 0.033 | 92.6 | -
Persan Construction, Inc. (Formerly: Persan Construction) | 2852 |  |  |  |  | Repair/Rehab./Reconst./Upgrading of Gen. Luna St. |  | 2010-06-28 |  | NCR |  | 15.36 | 145 |  |  |  | O | 0.385 | 0.3 | 0.15 | 0.03 | 0.055 | 0.05 | 97 | -
Persan Construction, Inc. / Ulticon Builders, Inc. (JV) | JV-07-108 | L | AAA | LB | GE1 | Impv't/Conc. of Kapalong-Talaingod Bdry. Valencia Bukidnon Road, Sitio Napisulan to Highway Bdry. |  | 2009-03-14 | 1st | XI |  | 738.154 | 780 |  |  |  | O | 0.399 | 0.3 | 0.15 | 0.022 | 0.055 | 0.05 | #VALUE! | -
Persan Construction, Incorporated / HG III Construction and Development Corporation (JV) | JV-08-038 | L | AAA | LB | GE1 | Implementation of Civil Works for Const. of CP 2, Pantabangan-Canili Road Sect. | Nueva Ecija & Nueva Vizcaya | 2011-04-11 | 1st | PJHL | LF | 579 | 499 | 2009-12-18 | 2011-04-30 | 3.42 | O | 0.339 | 0.3 | 0.15 | 0.03 | 0.042 | 0.05 | 91.1 | -
Persan Construction/Ulticon Builders, Inc. (JV) | JV-07-108 | L | AAA | LB | GE1 | Impvt./Conc. of Kapalong-Talaingod-Valencia, Bukidnon Road (Sitio Napisulan to Highway Boundary, Valencia Section) |  | 2009-06-03 | 2nd | XI |  | 738.153 | 780 |  |  |  | O | 0.394 | 0.3 | 0.15 | 0.03 | 0.042 | 0.05 | 96.6 | -
PETER G. CHUA BUILDERS | 25367 | L | B | SB | GB | Completion of Southville 3, Multi-Purpose Building, Brgy. Poblacion, Muntinlupa City, Metro Manila | Metro Manila | 2015-06-10 | 1st | Las Pinas-Muntinlupa | LF | 4.608 | 150 | 2015-02-27 | 2015-07-26 | (+) 1.28 | O | 0.394 | 0.24 | 0.15 | 0.02 | 0.048 | 0.05 | 90.2% | -
Petrina Construction & General Merchandise (Formerly: Petrina Grocers Marketing) | 29695 | L | D | SB | GB1 | Const. of Classroom at Bangcud NHS | Malaybalay City, Bukidnon | 2013-08-10 | 1st | X | LF | 6.509 | 180 | 2013-03-22 | 2013-09-17 | 0.58 | O | 0.36 | 0.205 | 0.15 | 0.03 | 0.029 | 0.033 | 80.7
Petrina Construction & General Merchandise (Formerly: Petrina Grocers Marketing) | 29695 | L | D | SB | GB | Construction of Classroom at Bangcud National High School | Malaybalay City, Bukidnon | 2014-08-05 | Final | X | LF | 6.5093 | 210 | 2013-03-22 | 2013-10-17 | 0 | C | 0.494 | 0.168 | 0 |  |  |  | 66.2 | 76.35% Unsatisfactory
PETRONAL BUILDERS | 31510 | L | D | SB | GE | Construction of Level III Water System, Municipality of Leon, Iloilo 2nd LD | Municipality of Leon, Iloilo 2nd LD | 2015-11-16 | 1st | Iloilo 4th | LF | 1.3959 | 107 | 2015-09-04 | 2015-12-20 | (+)0.81% | OG | 0.339 | 0.278 | 0.15 | 0.03 | 0.053 | 0.05 | 90% | 90% Very Satisfactory
PGM Construction & Plumbing Services | 9997 | L | C | SB | GE1 | Supply of Labor and Materials for Proposed Arch Gateway | Padre Faura Street, College of Arts & Sciences, UP Manila | 2011-11-23 | 1st | UP | LF | 0.737 | 60 | 2011-06-06 | 2011-11-25 | 0 | O | 0.372 | 0.3 | 0.15 | 0 | 0.028 | 0.05 | 90 | -
PGM Construction & Plumbing Services |  | L |  |  | GB1 | Renovation of Ten Laboratory | PGH Central Block | 2011-02-17 | 1st | UP | LF | 14.019 | 150 | 2011-07-21 | 2011-03-18 | 0 | O | 0.305 | 0.3 | 0.15 | 0.03 | 0.051 | 0.05 | 88.6 | -
PGO Construction | 15153 | L | B | MA | GE | Road Upgrading (Gravel to Paved) / Concreting of Stop Aguinaldo - Bug-Ang Road, K0111+543 - K0112+153 and K0112+648 - K0113+595 | Toboso, Negros Occidental | 2014-10-22 | 1st & Final | VI | LF | 42.4003 | 207 | 2014-02-24 | 2014-09-18 |  | C | 0.439 | 0.133 | 0.3 | - | - | - | 87.2% | 87.2% Satisfactory
PGO Construction | 15153 | L | C | SB | GE1 | Rehab./Reblocking of Deteriorated Conc. Pavement along Bacolod North Road |  | 2009-03-10 | 2nd | VI |  | 9.231 | 220 |  |  |  | O | 0.331 | 0.3 | 0.15 | 0.03 | 0.06 | 0.033 | #VALUE! | -
PGO Construction | 15153 | L | C | SB | GE1 | Rehab./Reblocking of Deteriorated Conc. Pavement along Bacolod North Road |  | 2008-11-24 | 1st | VI |  | 9.231 | 220 |  |  |  | O | 0.343 | 0.225 | 0.1 | 0.022 | 0.048 | 0.067 | 80.5 | -
PGO CONSTRUCTION | 15153 | L | B | MA | GE | Upgrading/ Concreting (Gravel to Paved) of Stop Aguinaldo - Bug-ang Road, K0119+081 - K0120+650 | Toboso, Negros Occidental | 2015-08-22 | 1st & Final | 1st Negros Occidental | LF | 42.477 | 182 | 2015-02-13 | 2015-08-13 | 0.11% | C | 0.426 | 0.138 | 0.3 | - | - | - | 86.4% | *86.4% Satisfactory
Pheames Community Construction Corporation | 31773 | L | B | MA | GE | Widening of Daang Maharlika (with exception), Quezon LD, MSR Diversion Road Section | K0126+000-K0127+621, Quezon | 2014-11-28 | 1st | IV | LF | 21.5598 | 300 | 2014-03-28 | 2015-01-21 | 0.48% | O | 0.372 | 0.241 | 0.15 | 0.03 | 0.045 | 0.033 | 87.1% | 87.1% Satisfactory
PHIL MANNA CONSTRUCTION & SUPPLY | 10320 | L | D | SB | GB | Construction of Multi-Purpose Building | Brgy. San Agustin, Canaman, Camarines Sur | 2015-06-06 | 1st | Camarines Sur 2nd | LF | 2.848 | 135 | 2015-03-15 | 2015-07-27 | 0.56% | O | 0.371 | 0.277 | 0.15 | 0.03 | 0.047 | 0.033 | 90.8% | -
PHIL MANNA CONSTRUCTION & SUPPLY | 10320 | L | D | SB | GE | Construction/Rehabilitation of Camaligan Flood Control and Improvement of Attached Facilities, Camaligan, Camarines Sur | Camaligan, Camarines Sur | 2015-11-14 | Final | Camarines Sur Second DEO | LF | 2.6925 | 65 | 2015-02-12 | 2015-04-17 | -22.76% | C | 0.343 | 0.2 | 0 | - | - | - | 54.3% | 54.3% Poor
PHILIPPINE CHEMICAL STEEL INDUSTRIES, INC. | 16965 | L | AA | SB | GE | Development of Boho Rock Beach Resort | Western Poblacion, Poro, Cebu | 2015-07-03 | Final | TIEZA | LF | 6.5 | 270 | 2012-11-29 | 2015-02-28 | -18.78 | C | 0.4198 | 0.189 | 0 |  |  |  | 60.88 | 60.88% Poor
PHILIPPINE CHEMSTEEL INDUSTRIES, INC. | 16965 | L | AA | MA | GE | Repair/Rehabilitation/Improvement (Asphalt Overlay) of Lucban-Majayjay Road, K0125+800 - K0127+130, with exception | Lucban, Quezon | 2015-09-04 | 1st & Final | Quezon 1st | LF | 9.967 | 45 | 2015-07-08 | 2015-08-21 | 24.44% | C | 0.471 | 0.133 | 0.3 | - | - | - | 90.4% | *90.4% Very Satisfactory
Philsouth Builders | 21962 | L | A | MB | GB-1 | Northern Mindanao PCG Search and Rescue Base Project | Laguindingan, Misamis Oriental | 2015-07-08 | Final | DOTC | LF | 72.13 | 464 | 2014-04-17 | 7/24/15 | 4.74 | O | 0.374 | 0.3 | 0.103 | 0.03 | 0.063 | 0.05 | 92 | -
Philsouth Builders | 21962 | L | A | MB |  | Northern Mindanao PCG Search and Rescue Project | Brgy. Mauswagon, Laguindingan, Misamis Oriental | 2015-02-05 | 1st | DOTC | L | 72.13 | 390 | 2014-04-17 | 2015-05-11 | -4.58 | O | 0.3953 | 0.3 | 0.1042 | 0.03 | 0.055 | 0.05 | 93.45 | -
Philsouth Builders | 21962 | L | A | MB | GE | Upgrading (Gravel to Concrete) Concreting of Dumaguete - Valencia Road Leading to Casaroro Falls & Japanese Shrine | Candau-ay, Dumaguete City, Negros Oriental | 2014-08-14 | 1st & Final | VII | LF | 9.626 | 110 | 2013-03-18 | 2013-07-05 | 0 | C | 0.391 | 0.188 | 0.3 |  |  |  | 87.9 | 87.90% Satisfactory
Philsouth Builders | 21962 |  | B | MB |  | Northern Mindanao Philippine Coastguard Search and Rescue Base Development Project | Brgy. Mauswagon, Laguindingan, Misamis Oriental/ Region X | 2016-02-10 | 3rd & Final | DOTC | LF | 77.479 | 555 | 2014-04-17 | 2016-04-05 | 6.91 | C | 0.4835 | 0.2 | 0.3 | - | - | - | 98.35 | 94.98% V. Satisfactory
PHILSOUTH BUILDERS (Formerly: Lotiff Construction) | 21962 | L | AA | MB | GE | Concreting of Dumaguete City-Valencia-Bacong Road, Dumaguete City, K0004+532 - K0004+867.82, 2nd District, Negros Oriental | 2nd District, Negros Oriental | 2015-11-12 | Final | Negros Oriental 2nd DEO | LF | 6.8321 | 151 | 2015-02-05 | 2015-07-05 | - | C | 0.469 | 0.132 | 0.3 | - | - | - | 90.1% | 90.1% Very Satisfactory
PHILSOUTH BUILDERS (Formerly: Lotiff Construction) | 21962 | L | AA | MB | GE | Construction/Improvement of Access Roads Leading to Airports, Seaports and Declared Tourism Destinations - To Declared Toursim Destinations: Improvement of Road Leading to Mt. Talinis (Lipayo-Magsaysay Section) | Dauin, Negros Oriental | 2015-11-13 | Final | Negros Oriental 3rd DEO | LF | 46.143 | 173 | 2015-03-26 | 2015-09-14 | - | C | 0.47 | 0.123 | 0.3 | - | - | - | 89.3% | 89.3% Very Satisfactory
Philsouth Builders (Formerly: Lotiff Construction) | 21962 | L | A | MB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads (Concrete Pavement) Dumaguete City - Valencia - Bacong Road, K0008+(-495) to K0009+000 | Valencia, Negros Oriental | 2014-10-28 | 1st & Final | VII | LF | 21.0433 | 142 | 2014-02-05 | 2014-06-26 | 0% | C | 0.363 | 0.2 | 0.258 | - | - | - | 82.1% | 82.1% Satisfactory
Philsouth Builders (Formerly: Lotiff Construction) | 21962 | L | A | MB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads Including Drainage Based on Pavement Management System/Highway Development and Management-4 (HDM-4) (I.S.) Dumaguete City - Valencia - Bacong Road, 2nd District | Dumaguete City, Negros Oriental | 2014-10-27 | 1st | VII | LF | 33.8411 | 268 | 2014-01-27 | 2014-10-21 | -5% | O | 0.314 | 0.3 | 0.1 | 0.03 | 0.055 | 0 | 79.9% | 79.9% Unsatisfactory
Philsouth Builders (Formerly: Lotiff Construction) | 21962 | L | A | MA | GE1 | Rd. Upgrading (Gravel to Paved), Metro Dumaguete Diversion Rd. | Negros Oriental | 2013-08-21 | 1st | VII | LF | 45.57 | 179 | 2013-03-26 | 2013-09-21 | 2.12 | O | 0.375 | 0.238 | 0.15 | 0.03 | 0.05 | 0.033 | 87.6
PHILSOUTH BUILDERS (Formerly: Lotiff Construction) | 21962 | L | AA | MA | GE | Construction/Improvement of Access Roads Leading to Airports, Seaports and Declared Tourism Destinations - To Declared Toursim Destinations: Concreting of Road Leading to Casaroro Falls (Poblacion-Calayugan Section) | Valencia, Negros Oriental | 2015-08-25 | 1st & Final | Negros Oriental 3rd | LF | 18.501 | 156 | 2015-03-26 | 2015-08-28 | 1.56% | C | 0.32 | 0.293 | 0.15 | - | - | - | 89.5% | *89.5% Very Satisfactory
PHILSOUTH CONSTRUCTION (Formerly: Lotiff Construction) | 21962 | L | AA | MB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads including Drainage Based on Pavement Management System/Highway Development and Management-4 (HDM-4) (I.S.) Dumaguete City-Valencia-Bacong Road, Dumaguete City, 2nd District, Negros Oriental | Dumaguete City-Valencia-Bacong Road, Dumaguete City, Negros Oriental | 2015-06-10 | Final | Negros Oriental Second DEO | LF | 33.841 | 268 | 2015-01-27 | 2015-10-21 | 0% | C | 0.492 | 0.139 | 0.3 | - | - | - | 93.1% | *93.1% Very Satisfactory
PHILWORKS CONSTRUCTION & SUPPLY | 32103 | L | AAA | LB | GE | Construction/Improvement of Access Road Leading to Declared Tourism Destinations, Bagac - Mariveles Road leading to Anvaya Cove and Bataan Technology Park, Bagac, Bataan | Bagac, Bataan | 2015-06-02 | 1st | Regional Office No. III | LF | 91.262 | 346 | 2015-08-01 | 2016-07-12 | -14.83% | O | 0.392 | 0.3 | 0.002 | 0.03 | 0.03 | 0.033 | 78.7% | -
Philworks Construction and Supply | 32103 | L | AAA | LB | GE | Rehab./Reconst./Upgrading of Damaged Paved National Roads including Drainage Based on HDM-4 (Intermittent Section), Rolando A. Andaya Highway, K0295+542-K0303+000, with exceptions | Camarines Sur | 2014-08-06 | 1st | V | LF | 91.8045 | 180 | 2014-04-16 | 2014-10-12 | -9.38 | O | 0.335 | 0.3 | 0.056 | 0.03 | 0.05 | 0.05 | 82.1
Philworks Construction and Supply | 32103 | L | AAA | MB | GE | Repair and Improvement of Slope Protection & Drainage System along Rolando Andaya Highway, A) KO 330+180 to KO330+245, B) KO327+750 to KO327+776 | Lupi, Camarines Sur | 2014-08-06 | Final | V | LF | 5.7147 | 154 | 2012-12-12 | 2013-05-14 | 2.5 | C | 0.364 | 0.2 | 0.3 |  |  |  | 86.4 | 85.20% Satisfactory
Philworks Construction and Supply | 32103 | L | AAA | LB | GE | Rehab/Reconst. Of Damaged Paved National Road along Daang Maharlika Hghway, K0397+354 - K0433+964, with exceptions | Camarines Sur | 2014-08-07 | Final | V | LF | 122.6775 | 249 | 2012-12-20 | 2013-08-25 | 0 | C | 0.379 | 0.2 | 0.3 |  |  |  | 87.9 | 87.00% Satisfactory
Philworks Construction and Supply | 32103 | L | AAA | LB | GE1 | Rehab./Reconst. of Damaged Paved Nat'l Rd. along Daang Maharlika Highway, K0397+354-K0433+964 w/exceptions | Camarines Sur | 2013-08-07 | 1st | V | LF | 122.677 | 249 | 2012-12-20 | 2013-08-25 | 0.01 | O | 0.269 | 0.3 | 0.15 | 0.03 | 0.065 | 0.05 | 86.4
Philworks Construction and Supply | 32103 | L | AAA | LB | GE1 | Rehab./Restoration/Impv't. of Damaged Sect. along Libon-Marocmoc-Pantao Rd. (Mararag Sect.) | Libon, Albay | 2013-08-09 | Final | V | LF | 19.402 | 240 | 2012-06-29 | 2013-02-23 | 0 | C | 0.47 | 0.133 | 0.3 | - | - | - | 90.3 | 88.98% Satisfactory
Philworks Construction and Supply | 32103 | L | AAA | LB | GE1 | Restoration/Impv't. of Damaged Sect. along Libon-Marocmoc-Pantao Rd. | Libon, Albay | 2013-08-09 | Final | V | LF | 19.402 | 240 | 2012-06-29 | 2013-02-23 | 0 | C | 0.416 | 0.133 | 0.3 | - | - | - | 84.9 | 86.76% Satisfactory
Philworks Construction and Supply | 32103 | L | AAA | LB | GE1 | Const. of Martirez Bridge & Approaches | Libon, Albay | 2013-08-07 | Final | V | LF | 72.409 | 541 | 2011-11-21 | 2013-05-14 | 0 | C | 0.435 | 0.133 | 0.3 | - | - | - | 86.8 | 85.27% Satisfactory
Philworks Construction and Supply | 32103 | L | AAA | MB | GE2 | Repair and Impv't. of Slope Protection & Drainage System along Rolando Andaya Highway, a) K0330+180-K0330+245; b) K0327+750-K0327+776, Brgy. Bulawan | Camarines Sur | 2013-08-03 | 1st | V | LF | 7.81 | 120 | 2013-05-07 | 2013-09-03 | 0.5 | O | 0.315 | 0.251 | 0.15 | 0.03 | 0.065 | 0.033 | 84.4
Philworks Construction and Supply | 32103 | L | AAA | LB | GE1 | Rehab. of Damaged Paved Nat'l. Rd. along Daang Maharlika | Camarines Sur | 2013-03-22 | Final | V | LF | 163.033 | 376 | 2011-12-05 | 2012-12-14 | 0 | C | 0.377 | 0.2 | 0.3 | - | - | - | 87.7 | 88.84% Satisfactory
Philworks Construction and Supply | 32103 | L | AAA | LB | GE1 | Const. of Martinez Bridge & Approaches | Libon, Albay | 2013-03-20 | 2nd | V | LF | 72.409 | 541 | 2011-11-21 | 2013-05-14 | -9.63 | O | 0.354 | 0.3 | 0.054 | 0.03 | 0.05 | 0.033 | 82.1 | -
Philworks Construction and Supply | 32103 |  |  |  |  | Const./Completion of San Vicente-Gutan-Lubac-Nangaramuan-Pozo Robo Rd. |  | 2010-08-17 |  | II |  | 109.8 | 365 |  |  |  | O | 0.33 | 0.275 | 0.15 | 0.015 | 0.03 | 0.033 | 83.3 | -
Philworks Construction and Supply | 32103 | L | AAA | LB | GE1 | Rehab./Restoration/Impvt. of Damaged Sect. along Libon-Marocmoc-Pantao Rd. (Mararag Sect.) | Libon, Albay | 2012-11-26 | 1st | V | LF | 19.402 | 210 | 2012-06-29 | 2013-01-24 | 0.19 | O | 0.366 | 0.25 | 0.15 | 0.03 | 0.052 | 0.033 | 88.1 | -
Philworks Construction and Supply | 32103 | L | AAA | LB | GE1 | Restoration/Impvt. of Damaged Sect. along Libon-Marocmoc-Pantao Rd. | Libon, Albay | 2012-11-26 | 1st | V | LF | 19.402 | 210 | 2012-06-29 | 2013-01-24 | 0.74 | O | 0.375 | 0.24 | 0.15 | 0.03 | 0.052 | 0.033 | 88 | -
Philworks Construction and Supply / MWJ Construction (JV) | JV-09-087 |  |  |  |  | Road Opening/Const. of Burauen Rd. including Bridges (Sta.987+169 - Sta.990+269.40 |  | 2010-05-31 |  | VIII |  | 94.97 | 300 |  |  |  | O | 0.386 | 0.24 | 0.15 | 0.03 | 0.047 | 0.033 | 88.6 | -
PHINMA Property Holdings Corp. | 34902 |  | AAA |  |  | Construction of Ten (10) 5-Storey Residential Buildings with Land Development, Pleasant Hills Package 1 | SJDM, Bulacan | 2016-03-13 | Final | NHA | LF | 274.955 | 788 | 2016-10-01 | 2015-11-22 | -1.1 | C | 0.4935 | 0.1545 | 0.3 | - | - | - | 94.8 | 92.46% V. Satisfactory
Phintecstar Construction, Inc. | [5 empty] | Land Development and Construction of 409 Housing Units (Villa Diana) | Brgy. 101 New Kawayan, Tacloban City, Leyte | 2016-01-29 | 2nd & Final | NHA | LF | 116.999 | 295 | 2015-02-04 | 2015-11-26 | 0 | C | 0.4877 | 0.2 | 0.3 | - | - | - | 98.77 | 93.39% V. Satisfactory
Phintecstar Constructionn, Inc. |  | L |  |  |  | Land Development and Construction of 409 Housing Units (Villa Diana) | Brgy. 101 New Kawayan, Tacloban City, Leyte | 2015-06-12 | 1st | NHA | LF | 116.999 | 295 | 2015-02-04 | 11/26/15 | 32.57 | O | 0.3711 | 0.2584 | 0.15 | 0.03 | 0.0513 | 0.05 | 91.08 | -
Phranaret Construction | 16878 | L | B | MA | GE | Road Upgrading (Gravel to Paved) of Banaue-Mayoyao-A. Lista-Isabela Bdry. Road K0343+652 - K0343+748, K0344+143 - K0344+171, K0347+880 - K0348+135, K0349+000 - K0349+190, K0349+375 - K0349+384, K0351+829 - K0351+891 & K0352+122 - K0352+503 | Banaue, Ifugao | 2014-11-26 | 1st | CAR | LF | 32.4064 | 266 | 2014-06-11 | 2015-03-03 | 11% | O | 0.35 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 87.5% | 87.5% Satisfactory
Phranaret Construction | 16878 | L | B | MA | GE | Road Upgrading (Gravel to Paved) along Banaue - Hungdun - Benguet Bdry. Road, K0348+380 - K0353+205, with exception | Banaue, Ifugao | 2014-08-10 | Final | CAR | LF | 42.6865 | 321 | 2013-02-21 | 2014-01-07 | 0 | C | 0.441 | 0.133 | 0.3 |  |  |  | 87.4 | 84.58% Satisfactory
Phranaret Construction | 16878 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Conc.) along Banaue-Hungduan-Benguet, K0348+380-K0353+205 | Banaue, Ifugao | 2013-08-06 | 1st | CAR | LF | 40.013 | 232 | 2013-02-21 | 2013-10-10 | -8.3 | O | 0.347 | 0.3 | 0.067 | 0.03 | 0.05 | 0.033 | 82.7
PHRANARET CONSTRUCTION | 16878 | L | B | MA | GE | Road Upgrading (Gravel to Paved) of Banaue-Mayoyao-a. Lista-Isabela Bdry. Road, K0343+652 - K0343+748, K0344+1443 - K0344+171, K0347+880 - K0348+135, K0349+000 - K0349+190 | Banaue, Ifugao | 2015-06-08 | Final | CAR | LF | 32.406 | 266 | 2014-06-11 | 2015-03-03 | 0% | C | 0.41 | 0.2 | 0.3 | - | - | - | 91% | *88.9% Satisfactory
Pibs Trading and Construction | 14734 |  |  |  |  | Rehab./Reconst./Upgrading of Camague-Ceanuri-Tominobo Section-Sta.1527+950 - Sta.1529+342 w/ exception |  | 2010-06-09 |  | X |  | 9.257 | 105 |  |  |  | O | 0.349 | 0.24 | 0.15 | 0.03 | 0.045 | 0.05 | 86.4 | -
Pibs Trading and Construction | 14734 | L | A | MA | GB1 | Rehab./Impvt. of DPWH Bldg. Lanao del Norte 1st District Engineering Office and Employees Quarter |  | 2009-06-05 | 1st | X |  | 3.733 | 180 |  |  |  | O | 0.376 | 0.273 | 0.15 | 0.03 | 0.005 | 0.033 | 86.7 | -
PILIPINAS REALTY MANAGEMENT CORPORATION | 37749 | L | D | SB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads including Drainage Based on Pavement Management System/Highway Development and Management-4 (HDM-4) (Intermittent Sections), Leonard Wood Road, K0252+929 to K0253+325, Baguio City | Baguio City | 2015-09-04 | 1st & Final | Baguio City DEO | LF | 6.578 | 120 | 2015-04-07 | 2015-08-04 | 0% | C | 0.423 | 0.133 | 0.3 | - | - | - | 85.6% | *85.6% Satisfactory
Ping-Ann's Construction and Trading | 34188 | L | B | SB | GE | Development of Camp Manuel T. Yan Eco-Tourism and Tribal Park | Brgy. Tuburan, Mawab, compostela Valley | 2015-03-07 | 1st | TIEZA | LF | 10 | 120 | 2015-03-08 | 2015-08-04 |  | O | 0.311 | 0.2344 | 0.15 | 0.03 | 0.0583 | 0.05 | 83.37
PING-ANN'S CONSTRUCTION AND TRADING | 34188 | L | B | SB | GE | Development of Camp Manuel T. Yan Eco-Tourism and Tribal Park | Mawab, Compostela Valley | 2015-09-23 | Final | TIEZA | LF | 10 | 120 | 2015-03-08 | 2015-08-04 | 0 | C | 0.473 | 0.2 | 0.3 |  |  |  | 97.3 | 87.60% Satisfactory
PING-ANN'S CONSTRUCTION AND TRADING | 34188 | L | B | SB | GE | Lake Mainit Development (Cost to Complete) | Jabonga, Agusan del Norte | 2015-10-01 | 1st | TIEZA | LF | 15 | 150 | 2015-07-07 | 2015-11-03 | -2.05 | O | 0.384 | 0.3 | 0.13 | 0.03 | 0.039 | 0.05 | 93.3 | -
PING-ANN'S CONSTRUCTION AND TRADING | 34188 | L | B | SB | GE | Lake Mainit Development (Cost to Complete) | Jabonga, Agusan del Norte | 2015-12-03 | Final | TIEZA | LF | 15 | 150 | 2015-06-07 | 2015-11-03 | 0 | C | 0.482 | 0.2 | 0.3 |  |  |  | 98.2 | 94.8% Very Satisfactory
Pins Construction | 13630 | L | D | SB | GE | Concrerting of Brgy. Road along Upper Dumalinao to Brgy. Kalingayan Road, Dumalinao (Phase IV) | Dumalinao, Zamboanga del Sur | 2014-08-13 | Final | IX | LF | 6.4497 | 155 | 2013-04-08 | 2013-09-09 | 0 | C | 0.284 | 0.2 | 0.3 |  |  |  | 78.4 | 80.80% Unsatisfactory
Pins Construction | 13630 | L | D | SB | GE1 | Conc. of Brgy. Rd. along Upper Dumalinao to Brgy.Kalingayan Rd., Brgy. Upper Dumalinao & Brgy. Kalingayan, Dumalinao (Phase IV) | Dumalinao, Zamboanga del Sur | 2013-08-16 | 1st | IX | LF | 6.45 | 155 | 2013-04-08 | 2013-09-09 | 0.2 | O | 0.305 | 0.278 | 0.15 | 0.03 | 0.028 | 0.033 | 82.4
Pins Construction | 13630 | L | D | SB | GE1 | Conc. of R.T. LIM Street & M. Roxas Ave. | Lakewood, Zamboanga del Sur | 2012-11-21 | 1st | IX | LF | 9.305 | 118 | 2012-07-23 | 2012-11-17 | -49.95 | O | 0.315 | 0.225 | 0 | 0.023 | 0.043 | 0.033 | 63.9 | -
Pins Construction | 13630 | L | D | SB | GE1 | Repair/Rehab./Impvt. of Lakewood-Bayog-Sindangan Nat'l Secondary Rd., K1717++340-K1717+860, Pob. Lakewood | Zamboanga del Sur | 2012-08-16 | 1st | IX | LF | 9.49 | 135 | 2012-05-30 | 2012-10-11 | 0.14 | O | 0.318 | 0.219 | 0.15 | 0.03 | 0.038 | 0.033 | 78.8 | -
PINS CONSTRUCTION | 13630 | L | D | SB | GE | Rehabilitation/Reconstruction/Upgrading of Damage Pavement National Road, Lanao-Pagadian-Zamboanga City Road (K1651+401-K1652+000), Tukuran, Zamboanga del Sur | Tukuran, Zamboanga del Sur | 2015-08-28 | 1st & Final | Zamboanga del Sur 1st | LF | 9.532 | 102 | 2015-04-13 | 2015-07-23 | - | C | 0.39 | 0.1712 | 0.3 | - | - | - | 86.12% | *86.12% Satisfactory
PINS CONSTRUCTION | 13630 | L | D | SB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Pavement National Road, Lanao-Pagadian-Zamboanga City Road, K1651+401-K1652+000, Tukuran, Zamboanga del Sur | Tukuran, Zamboanga del Sur | 2015-11-13 | Final | Zamboanga Del Sur 1st DEO | LF | 9.5318 | 72 | 2015-04-13 | 2015-06-23 | - | C | 0.389 | 0.2 | 0.3 | - | - | - | 88.9% | 88.9% Satisfactory
Pirra Construction Enterprises | 10545 | L | C | SB | GB1 | Const. of ACA Bldg. I & Dormitory Bldg. |  | 2009-04-16 | 1st | DOST |  | 24.29 | 180 |  |  |  | O | 0.356 | 0.271 | 0.15 | 0.03 | 0.044 | 0.05 | 90.1 | -
PJ Construction and Supply | 32305 | L | B | MA | GE-2 | UMAYAM RIVER IRRIGATION PROJECT | LA PAZ-LORETO, AGUSAN DEL SUR, REGION XIII | 2015-09-12 | 1st | NIA | LF | 15.219 | 242 | 2014-07-23 | 2015-03-21 | -46.92 | O | 0.3671 | 0.24 | 0 | 0.015 | 0.06 | 0.05 | 73.21 | -
PJ SAN PEDRO CONSTRUCTION AND SUPPLY | 14994 | L | B | MA | GE | Package 27-2: Concreting of Roads Barangay Megkawayan, Calinan District, Davao City | Calinan District, Davao City | 2015-11-18 | Final | Davao City 2nd DEO | LF | 4.801e-06 | 163 | 2015-04-17 | 2015-09-26 | 0 | C | 0.407 | 0.14 | 0.3 | - | - | - | 84.7% | 84.7% Satisfactory
PJ San Pedro Construction andSupply | 14994 | L | C | SB | GE1 | Completion of Multi-Purpose Gymnasium |  | 2008-07-08 | 1st | DOST |  | 10.426 | 226 |  |  |  | O | 0.383 | 0.3 | 0.05 | 0.03 | 0.047 | 0.067 | 87.7 | -
PJ San Pedro Construction andSupply | 14994 | L | B | MA | GB1 | Tiling Works and Exterior & Interior Painting of Central Administration Building |  | 2009-07-08 | 1st | U.P. |  | 5.768 | 195 |  |  |  | O | 0.366 | 0.165 | 0.1 | 0.03 | 0.044 | 0.1 | 80.5 | -
PLD Construction | 1859 | L | A | MA | GE | Repair/Imprv't of Mandaue City, Causeway Ouano Avenue) Chainage 2001 to Chainage 2727, Mandaue City, Cebu | Mandaue City, Cebu | 2014-08-08 | 1st | VII | LF | 44.2823 | 210 | 2014-02-05 | 2014-09-01 | 1.67 | O | 0.371 | 0.2 | 0.15 | 0.03 | 0.056 | 0.05 | 85.7
PLD Construction | 1859 | L | AAA | MA | GE | Preventive Maintenance Based on Pavement Management System Highway Development Management-4 (HDM-4), National Secondary Road, J. Luna Avenue, C0000 | Cebu City | 2014-08-09 | 1st & Final | VII | LF | 18.7804 | 50 | 2014-02-14 | 2014-04-04 | 0 | C | 0.45 | 0.133 | 0.3 |  |  |  | 88.3 | 88.30% Satisfactory
PLD Construction | 1859 | L | A | MB | GE1 | Opening/Conc. of Cebu-Toledo Wharf Road, Linao-Talisay-Minglanilla |  | 2008-08-20 | 1st | VII |  | 18.693 | 160 |  |  |  | O | 0.281 | 0.217 | 0.1 | 0.023 | 0.022 | 0.1 | 74.3 | -
PLD Construction | 1859 | L | A | MB | GB1 | Const. of Main Building, Cebu State College of Science & Tecnology (CSCST) Bitoon Campus |  | 2009-03-13 | 1st | VII |  | 19.084 | 160 |  |  |  | O | 0.366 | 0.3 | 0.15 | 0.03 | 0.057 | 0.05 | #VALUE! | -
PLD Construction | 1859 | L | A | MA | GE1 | Asset Preservation of Nat'l Rd., (Int. Sect.) Prev. Maint., Overton-Buru-un Bdry. Rd., Km.1532+(-831)-Km.1532+(-420)-Km.1532+124.50 | Iligan City | 2013-08-17 | Final | X | LF | 23.342 | 60 | 2013-01-31 | 2013-03-31 | 1 | C | 0.408 | 0.133 | 0.3 | - | - | - | 84.1 | 82.60% Satisfactory
PLD Construction | 1859 | L | A | MA | GE1 | Prev. Maint. (Int. Sect.) Overton-Buru-un Bdry. Rd., K1532+(-831)-K1532+(-420); K1532+(-420)- K1532+124.50 | Iligan City | 2013-03-15 | 1st | X | LF | 23.342 | 60 | 2013-01-31 | 2013-03-31 | 5.58 | O | 0.379 | 0.187 | 0.15 | 0.01 | 0.04 | 0.05 | 81.6 | -
PLD CONSTRUCTION | 1859 | L | AAA | MA | GE | Reconstruction of V. Rama-Tres de Abril Street, Chainage 0+795.00- Chainage 1+795.00, Cebu City | V. Rama-Tres de Abril Street, Cebu City | 2015-06-09 | Final | Regional Office No. VII | LF | 47.184 | 240 | 2015-05-30 | 2016-01-24 | 0% | C | 0.395 | 0.133 | 0.3 | - | - | - | 82.8% | *82.8% Satisfactory
PLD CONSTRUCTION | 1859 | L | AAA | MA | GE | Repair/Rehabilitation of Road Besides Jollibee from Quano Avenue to End of the Road | Mandaue City, Cebu | 2015-06-01 | Final | Cebu Sixth DEO | LF | 7.923 | 66 | 2015-02-26 | 2015-05-02 | 0% | C | 0.477 | 0.133 | 0.3 | - | - | - | 91% | *91% Very Satisfactory
PLD CONSTRUCTION | 1859 | L | AAA | MA | GE | Rehabilitation/Major Repair of Permanent Bridges at Cansaga Bay Bridge (B00613CB), Chainage 0000 - 0641 | Consolacion, Cebu | 2015-09-04 | 1st | Cebu 6th | LF | 44.939 | 180 | 2015-04-08 | 2015-10-04 | 0% | O | 0.381 | 0.119 | 0.15 | 0.03 | 0.03 | 0.033 | 74.3% | -
PLD CONSTRUCTION | 1859 | L | AAA | MA | GE | Replacement of Rubber Expansion Joints at Marcelo B. Fernan Bridge (Phase III), Mandaue City, Cebu | Mandaue City, Cebu | 2015-11-15 | Final | Cebu 6th | LF | 27.0885 | 180 | 2015-03-03 | 2015-10-25 | 0.95 | C | 0.5 | 0.133 | 0.3 | - | - | - | 93.3% | 93.3% Very Satisfactory
Plerm Construction & Development Corporation | 33288 | L | AA | LA | GE | Construction and Maintenance of Bridges along National Roads - Replacement of Papandayan Bridge along Calapan South Road | Pinamalayan, Oriental Mindoro | 2014-08-12 | 1st | IV-B | LF | 10.9476 | 200 | 2014-05-12 | 2014-11-27 | 6.67 | O | 0.367 | 0.236 | 0.15 | 0.03 | 0.04 | 0.033 | 85.6
PLERM CONSTRUCTION AND DEVELOPMENT CORPORATION | 33288 | L | AA | LB | GE | Replacement of Orconuma Bridge Bongabong-Sagana-San Aquilino Road Sta. 113+610 - Sta. 114+000 | Bongabong, Oriental Mindoro | 2015-06-09 | 1st | Regional Office IV-B | LF | 84.595 | 325 | 2014-10-14 | 2015-09-03 | -0.72% | O | 0.392 | 0.29 | 0.143 | 0.03 | 0.051 | 0.033 | 93.9% | -
PLERM CONSTRUCTION AND DEVELOPMENT CORPORATION | 33288 | L | AA | LA | GE | Rehabilitation/Major Repair of Permanent Bridges, Cavillian Br. (B00072MR) Along Calapan South Road | Bulalacao, Oriental Mindoro | 2015-06-10 | 1st | Southern Mindoro DEO | LF | 9.212 | 240 | 2015-04-07 | 2015-12-02 | 0% | O | 0.357 | 0.293 | 0.15 | 0.03 | 0.06 | 0.05 | 94% | -
PM Pacia Construction | 1913 | L | C | SB | GB1 | Completion of Sch. Bldg. at Baclaran Elem. Sch. Central | Parañaque City, Metro Manila | 2013-08-08 | Final | NCR | LF | 3.447 | 120 | 2013-01-16 | 2013-05-15 | 21.67 | C | 0.391 | 0.133 | 0.3 | - | - | - | 82.4 | 83.80% Satisfactory
PM Pacia Construction | 1913 | L | C | SB | GB1 | Completion of Sch. Bldg. at Baclaran Elem. Sch. Central | Parañaque City, M.M. | 2013-03-21 | 1st | NCR | LF | 3.366 | 120 | 2013-01-16 | 2013-05-15 | 23.8 | O | 0.391 | 0.211 | 0.15 | 0.03 | 0.029 | 0.033 | 84.4 | -
POLO ENGINEERING & CONSTRUCTION | 34966 | L | D | SB | GB | Construction/Repair of Various School Building and Other Educational Facilities/Public Markets/MPB/Pavements within Benguet 2nd DEO (Package IV-2015) | Kibungan, Benguet | 2015-06-03 | Final | Benguet 2nd DEO | LF | 0.483 | 105 | 2015-02-16 | 2015-05-31 | 0% | C | 0.427 | 0.133 | 0.3 | - | - | - | 86% | *86% Satisfactory
Polymer-Vic Construction | 6157 | L | B | MA | GE1 | Asphalt Overlay of Bataan Technological Park Inc. Road |  | 2009-05-20 | 1st | III |  | 19.0298 | 90 |  |  |  | O | 0.396 | 0.2 | 0.15 | 0.03 | 0.025 | 0.05 | 85.1 | -
POLYMER-VIC CONSTRUCTION | 6157 | L | B | MA | GE | Widening of Gov. JJ Linao Road, K0129+300 to K0129+900, Pilar, Bataan | Pilar, Bataan | 2015-06-06 | 1st | Bataan 2nd DEO | LF | 12.738 | 119 | 2015-02-24 | 2015-06-22 | 0.02% | O | 0.371 | 0.259 | 0.15 | 0.008 | 0.023 | 0.05 | 86.1% | -
Pon Construction and Trading | 33667 |  |  |  |  | Impvt. of Pentor-Balsik River Control (Daang Bago Section) |  | 2010-02-18 |  | III |  | 4.728 | 120 |  |  |  | O | 0.367 | 0.22 | 0.15 | 0.02 | 0.038 | 0.05 | 84.5 | -
PONARBUILT CONSTRUCTION & GENERAL MERCHANDISE | 32682 | L | B | SB | GE | Widening of National Road along MNR, KO502+300 - KO503+380 | Pasuquin, Ilocos Norte | 2015-06-03 | 1st | Ilocos Norte 1st DEO | LF | 4.58 | 118 | 2015-02-12 | 2015-06-09 | 0.25% | O | 0.259 | 0.3 | 0.15 | 0.03 | 0.055 | 0.033 | 82.7% | -
PONARBUILT CONSTRUCTION & GENERAL MERCHANDISE | 32682 | L | B | SB | GE | Widening of Road along Laoag-Sarrat-Piddig-Solsona Road, K0503+845 to K0505+147, Loing, Piddig, Ilocos Norte | K0503+845 to K0505+147, Loing, Piddig, Ilocos Norte | 2015-08-25 | 1st | Ilocos Norte 1st DEO | LF | 14.045 | 123 | 2015-05-15 | 2015-09-14 | - | O | 0.317 | 0.277 | 0.15 | 0.022 | 0.028 | 0.05 | 84.4% | -
PONARBUILT CONSTRUCTION & GENERAL MERCHANDISE | 32682 | L | B | SB | GE | Widening of national Road along Manila North Road (MNR), K0502+300 to K0503+380, Pasuquin, Ilocos Norte | K0502+300 to K0503+380, Pasuquin, Ilocos Norte | 2015-08-25 | Final | Ilocos Norte 1st DEO | LF | 4.58 | 118 | 2015-02-12 | 2015-06-10 | - | C | 0.411 | 0.157 | 0.3 | - | - | - | 86.8% | *84.34% Satisfactory
POWER K CONSTRUCTION SUPPLY & SERVICES | 31574 | L | B | MA | GB | Construction of Two (2) Storey (4) CL School Building Bungkol, Brgy. Bungkol, Magdalena Laguna | Magdalena, Laguna | 2015-11-18 | 1st | LAGUNA 1ST DEO | LF | 5.9834 | 120 | 2015-10-26 | 2016-02-22 | 0.1915 | OG | 0.382 | 0.251 | 0.15 | 0.022 | 0.048 | 0.05 | 90.3% | 90.3% Very Satisfactory
Pragmatic Development & Construction Corporation | 4846 | L | AA | MB | GE | Construction/Rehabilitation of Flood Control Project in Catmon Daan Bridge/River Brgy. Catmon Daan | Catmon, Cebu | 2014-10-21 | 1st | VII | LF | 9.8322 | 154 | 2014-06-30 | 2014-11-30 | 1.2% | O | 0.275 | 0.3 | 0.15 | 0.03 | 0.045 | 0.033 | 83.3% | 83.30% Satisfactory
Pragmatic Development & Construction Corporation | 4846 | L | AA | MB | GE | Preventive Maintenance based on Pavement Management System/Highway Development and Management-4 (HDM-4), National Secondary Road, Salinas Drive, Chainage 0012 - Chainage 0569 | Cebu City | 2014-10-20 | 1st & Final | VII | LF | 16.3757 | 150 | 2014-02-14 | 2014-07-13 | 1.33% | C | 0.445 | 0.147 | 0.3 | - | - | - | 89.2 | 89.20% Very Satisfactory
Pragmatic Development & Construction Corporation |  | L | AAA | LB |  | Construction of the BCDA Remaining Works Inside Bonifacio Global, Package 2 | Bocifacio Global City | 2015-09-24 | Final | BCDA | LF | 115.105 | 365 | 2014-01-21 | 2015-07-24 | 0 | C | 0.4323 | 0.1906 | 0.3 | - | - | - | 92.29 | 84.77% Satisfactory
Pragmatic Development & Construction Corporation | 4846 | L |  |  |  | Construction of BCDA Remaining Infrastructure Works inside Bonifacio Global City, package 2 | Bonifacio Global City | 2015-02-24 | 2nd | BCDA | L | 115.618 | 420 | 2014-01-23 | 2015-03-24 | 17.21 | O | 0.38 | 0.23 | 0.032 | 0.03 | 0.043 | 0.033 | 74.8 | -
PRAGMATIC DEVELOPMENT & CONSTRUCTION CORPORATION | 4846 | L | AA | MB | GE | Construction/Rehabilitation of Flood Control Project in Catmon Daan Bridge/River | Brgy. Catmon Daan Catmon, Cebu | 2015-06-05 | Final | Cebu Fifth DEO | LF | 10.463 | 169 | 2015-06-30 | 2015-12-15 | 0.59% | C | 0.433 | 0.137 | 0.3 | - | - | - | 87% | *84.78% Satisfactory
Precious Construction | 32995 | L | B | SB | GE1 | Improvement of Farm-to-Market Road, Quinfermin-Bugbuga-San Jose Road |  | 2009-02-26 | 1st | I |  | 9.6304 | 133 |  |  |  | O | 0.315 | 0.3 | 0.15 | 0.02 | 0.025 | 0.05 | #VALUE! | -
Precious Construction | 32995 | L | A | MA | GE | Desilting/Channel Improvement/Revetment at Waras River, Sta. Elena Section | Nabua, Camarines Sur | 2014-08-10 | 1st | V | LF | 17.8986 | 231 | 2014-02-17 | 2014-10-04 | 1.58 | O | 0.32 | 0.3 | 0.15 | 0.024 | 0.028 | 0.05 | 87.2
Precious Construction | 32995 | L | B | MA | GE3 | Const. of Water Impounding at Anoling | Gen. Nakar, Quezon | 2013-08-08 | Final | IVA | LF | 28.18 | 365 | 2012-03-20 | 2013-03-19 | 0 | C | 0.345 | 0.2 | 0.3 | - | - | - | 84.5 | 85.28% Satisfactory
Precious Construction | 32995 | L | B | MA | GE2 | Const. of Flood Control System along Palico-Balayan-Batangas Road, Brgy. Tuyon-Tuyon & Brgy. Luntal | Tuy, Batangas | 2012-03-23 | 1st | IVA | LF | 17.149 | 90 | 2012-01-01 | 2012-03-30 | 5 | O | 0.303 | 0.3 | 0.15 | 0.03 | 0.048 | 0.033 | 86.4 | -
Precious Construction | 32095 | L | B | MA | GE3 | Const. of Water Impounding at Anoling | Gen. Nakar, Quezon | 2012-08-08 | 1st | IVA | LF | 26.814 | 300 | 2012-03-20 | 2013-01-13 | 26.64 | O | 0.351 | 0.24 | 0.15 | 0.022 | 0.045 | 0.05 | 85.8 | -
PRECIOUS CONSTRUCTION | 32995 | L | A | MB | GB | Construction of 4 Storey 8 Classroom Building at Ismael Mathay Sr. H/S, Quezon City | Quezon City | 2015-06-02 | 1st | Quezon City 1st DEO | LF | 18.793 | 270 | 2015-03-05 | 2015-11-29 | (+) 1.00 | O | 0.382 | 0.252 | 0.15 | 0.015 | 0.035 | 0.05 | 88.4% | -
PRECIOUS CONSTRUCTION | 32995 | L | A | MA | GE | Drainage Improvement along EDSA NB (Brgy. Bago Bantay and Veterans Village), Quezon City | Quezon City | 2015-08-25 | 1st | QC 1st DEO | LF | 17.755 | 270 | 2015-03-09 | 2015-12-03 | 1.2% | O | 0.378 | 0.243 | 0.15 | 0.023 | 0.055 | 0.05 | 89.9% | -
PRECIOUS CONSTRUCTION | 32995 | L | A | MB | GE | Conc./Rehab. of Cumadcad-Macalaya Port, Castilla, Sorsogon | Castilla, Sorsogon | 2015-09-01 | 1st | Sorsogon First DEO | LF | 37.162 | 240 | 2015-03-26 | 2015-11-20 | 0.19% | O | 0.38 | 0.246 | 0.15 | 0.03 | 0.06 | 0.05 | 91.6% | -
PRECIOUS CONSTRUCTION | 32995 | L | A | MA | GE | Drainage Improvement of EDSA NB, Brgy. Bago Bantay and Veterans Village, Quezon City | Brgy. Bago Bantay and Veterans Village, Quezon City | 2015-12-09 | Final | QC 1st DEO | LF | 17.7559 | 240 | 2015-03-09 | 2015-12-17 | (+)3.75% | C | 0.458 | 0.133 | 0.3 | - | - | - | 89.1% | 89.1% Very Satisfactory
PRECIOUS CONSTRUCTION | 32995 | L | A | MB | GE | Conc./Rehab. of Cumadcad-Macalaya Port | Castilla, Sorsogon | 2015-11-19 | Final | Sorsogon First DEO | LF | 37.1616 | 240 | 2015-03-26 | 2015-11-20 | 0.83% | C | 0.404 | 0.145 | 0.3 | - | - | - | 84.9% | 88.92% Satisfactory
PREMIUM MEGASTRUCTURE INC. | 36079 | L | AAA | MA | GE | Construction of Palanas Flood Control, Brgy. Balugo, Albuera, Leyte | Brgy. Balugo, Albuera, Leyte | 2015-08-28 | Final | Leyte 4th DEO | LF | 15.602 | 155 | 2015-02-02 | 2015-07-06 | (+)3.87 | C | 0.322 | 0.2 | 0.3 | - | - | - | 82.2% | *83.22% Satisfactory
PREMIUM MEGASTRUCTURE, INC. | 36079 | L | - | - | - | Construction of Palanas Flood Control, Brgy. Damulaan, Albuerto, Leyte | Brgy. Damulaan, Albuerto, Leyte | 2015-06-06 | 1st | Leyte Fourth DEO | LF | 15.602 | 155 | 2015-02-02 | 2015-07-06 | - | O | 0.359 | 0.24 | 0.15 | 0.02 | 0.037 | 0.033 | 83.9% | -
Premium Megastructures Inc. | 36079 | L | AAA | LB | GE | Road Upgrading (Gravel to Paved) of Cabungaan - Tabunok - Consuegra Road K1014+(-403)……... | Villaba & San Isidro Leyte | 2014-08-08 | 1st | VIII | LF | 97.6669 | 305 | 2014-02-17 | 2014-10-19 | 13.6 | O | 0.376 | 0.24 | 0.15 | 0.022 | 0.045 | 0.033 | 86.6
Premium Megastructures Inc. | 36079 | L | B | SB | GE1 | Rehab./Resurfacing of Cabungaan-Tabunok-Consuegra Rd., K1017+797-K1019+862.30 w/ exceptions | Villaba, Leyte | 2013-08-12 | 1st | VIII | LF | 4.758 | 90 | 2013-06-19 | 2013-09-16 | 32.23 | O | 0.387 | 0.225 | 0.15 | 0.012 | 0.05 | 0.05 | 87.4
Premium Megastructures Inc. | 36079 | L | AAA | MA | GE | Construction/Rehabilitation of Flood Control Projects, Baybay City Flood Control Structures | Baybay City, Leyte | 2014-10-28 | 1st & Final | VIII | LF | 12.964 | 160 | 2014-03-07 | 2014-08-13 | 0% | C | 0.433 | 0.133 | 0.3 | - | - | - | 86.6% | 86.6% Satisfactory
PREMIUM MEGASTRUCTURES, INC. | 36879 | L | AAA | LB | GE | Widening of National Road, Palo-Carigara-Ormoc Road, K0990+(-836.16)-K0990+212, K1005(-296)-K1005+001.84, Ormoc, Leyte | Ormoc, Leyte | 2015-11-14 | Final | Leyte Fourth DEO | LF | 33.2549 | 190 | 2015-02-05 | 2015-08-13 | - | C | 0.42 | 0.2 | 0.3 | - | - | - | 92% | 92% Very Satisfactory
PRESLI DELES CONSTRUCTION | 22694 | L | D | SB | GB | Construction of Multi-Purpose Building at Brgy. San Vicente, Tambulig, Zamboanga del Sur | Tambulig, Zamboanga del Sur | 2015-06-06 | 1st | Zamboanga del Sur 1st DEO | LF | 1.955 | 75 | 2015-05-11 | 2015-07-24 | 30.93% | O | 0.372 | 0.24 | 0.15 | 0.03 | 0.057 | 0.033 | 88.2% | -
PRESLI DELES CONSTRUCTION | 22694 | L | D | SB | GB | Construction of Multi-Purpose, Brgy. San Vicente, Tambulig, Zamboanga del Sur | Tambulig, Zamboanga del Sur | 2015-08-29 | Final | Zamboanga del Sur 1st | LF | 1.995 | 75 | 2015-05-11 | 2015-07-24 | (+)12.25% | C | 0.4328 | 0.2 | 0.3 | - | - | - | 93.28% | *89.72% Very Satisfactory
Prime Mate Builders | 32687 | L | D | SB | GB1 | Const. of 2-Storey, 4-CL Balili E/S (Phase I) |  | 2009-05-20 | 1st | CAR |  | 4.163 | 268 |  |  |  | O | 0.348 | 0.275 | 0.15 | 0.03 | 0.029 | 0.05 | 88.2 | -
PRIME PACIFIC MARINE & INDUSTRIAL SERVICES CORP. | 36171 | L | A | SB | GE | Rehabilitaion/Improvement of Drainage along C-4 Road and P. Aquino Letre Creek, Malabon City | Malabon City | 2015-06-05 | 1st | Malabon-Navotas DEO | LF | 4.559 | 121 | 2015-03-10 | 2015-07-08 | (+) 12.65 | O | 0.37 | 0.24 | 0.15 | 0.022 | 0.037 | 0.05 | 86.9% | -
PRIME PACIFIC MARINE & INDUSTRIAL SERVICES CORP. | 36171 | L | A | SB | GE | Rehabilitation/Improvemnet of Drainage along C-4 Road and P. Aquino, Letre Creek, Malabon City | Malabon City | 2015-12-11 | Final | Malabon-Navotas DEO | LF | 4.5592 | 141 | 2015-03-10 | 2015-07-28 | 0.00% | C | 0.424 | 0.133 | 0.3 | - | - | - | 85.7% | 85.7% Satisfactory
Prime Pave Construction and Asphalt Corporation | 36597 | L | B | MA | GE | Preventive Maintenance Based on Pavement Management System/Highway Development and Management-4 (Intermittent Section) of Gapan-San Fernando-Olongapo Road, Km.0069+(-554) - Km.0069+(-437) | San Fernando, Pampanga | 2014-11-17 | 1st & Final | III | LF | 1.5759 | 12 | 2014-07-08 | 2014-07-19 | 16.67% | C | 0.472 | 0.133 | 0.3 | - | - | - | 90.5% | 90.5% Very Satisfactory
Prismodial Const. Corp/Izumo Contractors Inc. (JV) | 28345/27742 | L |  |  |  | Contruction of Eight (8) Five Storey Residential Buildings with Land Development and Survey Works | #4 Republic Avenue, Brgy. Holy Spirit, Quezon City | 2014-06-24 | 1st | NHA | LF | 253.3 | 360 | 2013-11-17 | 2014-11-11 | 1.02 | O | 0.329 | 0.246 | 0.15 | 0.03 | 0.051 | 0.05 | 85.6 | -
Prismodial Construction Corporation | 28345 | L | AAA | LA | GB32107 | Construction/ Improvement of Tourism Facilities at Grand Apo Reef Nature Park | Grand Apo Reef Island, Sablayan, Occidental Mindoro | 2014-03-21 | 1st | TIEZA | LF | 9.988 | 240 | 2010-02-14 | 2012-05-29 | -24.91 | S | 0.31 | 0.212 | 0 | 0 | 0.07 | 0 | 59.2
Prismodial Construction Corporation | 28345 |  |  |  |  | Construction of 3-Storey, 15-Classroom School Building pkg.1B |  | 2009-12-08 |  | NHA |  | 18.111 | 150 |  |  |  | O | 0.308 | 0.3 | 0 | 0.03 | 0.045 | 0 | 68.3 | 68.30% Poor
Prismodial Construction Corporation | 28345 | L | AA | LB | GB1 | Construction of 3-Storey, 15-Classroom School Building |  | 2009-09-03 | 1st | NHA |  | 18.107 | 150 |  |  |  | O | 0.36 | 0.276 | 0 | 0.03 | 0.055 | 0 | 63.6 | -
Prismodial Construction Corporation | 28345 | L | AA | MB |  | Dipolog Airport Development Project | Dipolog City, Zamboanga del Norte | 2015-02-11 | 2nd & Final | DOTC | L | 49.42 | 479 | 2013-03-07 | 2014-07-09 | -4.5 | C | 0.462 | 0.2 | 0.165 | - | - | - | - | 88.70% Satisfactory
Prismodial Construction Corporation | 28345 | L | AA | MB | GE1 | Dipolog Airport Development Project | Dipolog City, Zamboanga del Norte | 2013-10-09 | 1st | DOTC | L | 46.483 | 300 | 2013-03-07 | 2013-12-31 | 10.22 | O | 0.349 | 0.3 | 0.15 | 0.02 | 0.044 | 0.05 | 91.3 | -
Prismodial Construction Corporation | 28345 | L | AA |  | GE1 | Timberland Village | Brgy. Bulatoc, Pagadian City | 2012-11-15 | 1st | NHA | LF | 33.168 | 300 | 2012-05-20 | 2013-03-15 | 1.24 | O | 0.3189 | 0.1993 | 0.15 | 0.0225 | 0.045 | 0.05 | 78.57 | -
Prismodial Construction/ RCDG Construction Corporation (JV) | JV-09-082 |  |  |  |  | Rehab. of Manlipac-Mayaposi Section |  | 2010-09-01 |  | VII |  | 57.85 | 240 |  |  |  | O | 0.338 | 0.3 | 0.15 | 0.03 | 0.042 | 0.033 | 89.3 | -
Prismodial Cosntruction Corporation/ E.M. Cuerpo, Inc. (J.V.) | JV-14-139 |  |  |  |  | Construction of Seven (7) Five Storey LRBs with Land Development and Survey Works | Manggahan Residences 3, Brgy. Sta. Lucia, Pasig City | 2016-02-04 | 1st | NHA | LF | 202.334 | 360 | 2015-05-15 | 2016-05-08 | -11.85 | O | 0.2218 | 0.173 | 0.0315 | 0.03 | 0.0175 | 0.017 | 49.08 | -
Proline Construction | 33548 | L | D |  | GE2 | Dabubu River Irrigation Project | San Agustin, Isabela / Region 2 | 2013-04-27 | 1st | NIA | LF | 3.917 | 150 | 2013-02-18 | 2013-07-19 | 22.1 | O | 0.374 | 0.213 | 0.15 | 0.023 | 0.028 | 0.05 | 83.8 | -
PROTECH CONSTRUCTION & DEVELOPMENT CORP. (Formerly: Sards Construction) | 15408 | L | B | SB | GE | Repair/Maintenance of River Control along Sta. Cruz River, Brgy. V, Sta. Cruz, Laguna | Sta. Cruz, Laguna | 2015-11-18 | 1st | LAGUNA 1ST DEO | LF | 2.8893 | 88 | 2015-09-18 | 2015-12-14 | 0.0073 | OG | 0.345 | 0.241 | 0.15 | 0.018 | 0.053 | 0.05 | 85.7% | 85.7% Satisfactory
PST CONSTRUCTION | 32741 | L | B | MA | GE | Widening of Cainta-Kaytikling-Antipolo-Teresa-Morong Road, K0 031+011 - K0 031+648 (Intermittent Section) | Antipolo City, 2nd LD | 2015-08-26 | 1st & Final | Rizal 1st | LF | 8.995 | 90 | 2014-02-12 | 2014-05-12 | 3.33% | C | 0.414 | 0.133 | 0.3 | - | - | - | 84.7% | *84.7% Satisfactory
PTK Group Inc./IPM Construction & Development Corporation - Joint Venture | JV-13-656 | L | AAA | LB | GE | Road Upgrading (Gravel to Paved) Aramaywan-Berong-Puerto Princesa Road, K0179+516 to K0181+905.50, Quezon, Palawan | Quezon, Palawan | 2015-02-23 | 1st & Final | IV | LF | 37.5319 | 224 | 2014-05-28 | 2015-01-06 | 7.12% | C | 0.419 | 0.2 | 0.3 | - | - | - | 91.9% | 83.08% Satisfactory
PTK Group Inc./IPM Construction & Development Corporation - Joint Venture | JV-13-656 | L | AAA | LB | GE | Upgrading of Access Road from National Highway to Panacan Port, Narra, Palawan | Narra, Palawan | 2014-08-04 | 1st & Final | IV-B | LF | 19.4275 | 136 | 2014-02-19 | 2014-07-04 | 0 | C | 0.416 | 0.139 | 0.3 |  |  |  | 85.5 | 85.50% Satisfactory
PTK Group Inc./IPM Construction & Development Corporation - Joint Venture | JV-13-656 | L | AAA | LB | GE | Road Upgrading (Gravel to Paved) Aramaywan - Berong - Puerto Princesa Road) K0179+516 - K0181+905.50 | Quezon, Palawan | 2014-08-05 | 1st | IV-B | LF | 35.0445 | 179 | 2014-05-28 | 2014-11-22 | -7 | O | 0.364 | 0.233 | 0.08 | 0.022 | 0.04 | 0.033 | 77.2
Pulsar Construction | 24422 | L | AA | LA | GE | Road Upgrading (Gravel to Paved) along Cadcadir-Kabugao Road, KO602+420 to KO603+160 | Sta. Praxedes, Cagayan | 2014-10-22 | 1st & Final | II | LF | 14.9428 | 180 | 2014-01-20 | 2014-08-17 | 0.01% | C | 0.456 | 0.168 | 0.3 | - | - | - | 92.4% | 92.4% Very Satisfactory
Pulsar Construction | 24422 | L | AA | LA | GE | Preventive Maintenance along Manila North Road, KO590+(-955) to KO593+560 | San Juan, Sta. Praxedes, Cagayan | 2014-10-22 | 1st & Final | II | LF | 38.3516 | 165 | 2014-03-05 | 2014-08-16 | 1.09% | C | 0.455 | 0.133 | 0.3 | - | - | - | 88.8% | 88.8% Satisfactory
Pulsar Construction | 24422 | L | AA | LA | GE | Network Development-Widening of National Roads-Arterial Roads: Widening of Cagayan-Apayao Road with exceptions, Cagayan-Apayao Road with exceptions, Tuguegarao Cathedral to Buntun Bridge Section, KO482+776 - KO486+276 | Tuguegarao City, Cagayan | 2014-10-22 | 2nd | II | LF | 30.6295 | 224 | 2014-03-21 | 2014-11-02 | -11% | O | 0.273 | 0.3 | 0.149 | 0.03 | 0.051 | 0.05 | 85.3% | 85.3% Satisfactory
Pulsar Construction | 24422 | L | AA | LA | GE | Network Development-Widening of National Roads-Arterial Roads: Widening of Cagaan-Apayao Road with exceptions, Cagayan-Apayao Road with exceptions, Tuguegarao Cathedral to Buntun Bridge Section, K0482+776 to K0486+276 | Tuguegarao City, Cagayan | 2014-08-08 | 1st | II | LF | 30.6295 | 224 | 2014-03-24 | 2014-11-02 | 10.76 | O | 0.353 | 0.238 | 0.15 | 0.033 | 0.04 | 0.033 | 84.7
Pulsar Construction | 24422 | L | AAA | MA | GE | Restoration of Claveria Bridge Protection Work, KO611+680 along Manila North Road | Cagayan | 2014-10-23 | 1st & Final | II | LF | 17.7943 | 240 | 2013-10-07 | 2014-06-02 | 0.03% | C | 0.333 | 0.2 | 0.3 | - | - | - | 83.3% | 83.3% Satisfactory
Pulsar Construction | 24422 | L | AA | LA | GE | Rehabilitation of Tucalan Bridge | Lasam, Cagayan | 2014-08-06 | 1st & Final | II | LF | 10.7247 | 180 | 2014-01-20 | 2014-07-18 | 0 | C | 0.46 | 0.133 | 0.3 |  |  |  | 89.3 | 89.30% Very Satisfactory
Pulsar Construction | 24422 | L | A | MB | GE1 | Const. of Gagabutan Bridge No.4 inc. PCCP along CAR | Rizal, Cagayan | 2013-08-03 | Final | II | LF | 30.444 | 300 | 2012-07-10 | 2013-05-06 | 0.02 | C | 0.448 | 0.133 | 0.3 | - | - | - | 88.1 | 90.50% V. Satisfactory
Pulsar Construction | 24422 | L | A | MB | GE1 | Const. of Gagabutan Bridge No. 4 inc PCCP | Rizal, Cagayan | 2013-03-12 | 2nd | II | LF | 30.444 | 270 | 2012-07-10 | 2013-04-06 | 1.34 | O | 0.385 | 0.24 | 0.15 | 0.03 | 0.061 | 0.05 | 91.6 | -
Pulsar Construction | 24422 | L | A | MB | GE1 | Const. of Gagabutan Bridge No. 4 inc PCCP along CAR | Rizal, Cagayan | 2012-11-25 | 1st | II | LF | 30.444 | 270 | 2012-07-10 | 2013-04-06 | 13.64 | O | 0.381 | 0.256 | 0.15 | 0.03 | 0.059 | 0.05 | 92.6 | -
Pulsar Construction | 24422 | L | A | MB | GE1 | Const. of Gagabutan Bridge No.1 inc. PCCP along CAR | Rizal, Cagayan | 2013-08-03 | Final | II | LF | 12.62 | 180 | 2012-07-10 | 2013-03-29 | 0.76 | C | 0.442 | 0.133 | 0.3 | - | - | - | 87.5 | 86.60% Satisfactory
Pulsar Construction | 24422 | L | A | MB | GE1 | Const. of Gagabutan Bridge No. 1 inc. PCCP | Rizal, Cagayan | 2013-03-12 | 2nd | II | LF | 12.62 | 210 | 2012-07-09 | 2013-02-03 | - | O | 0.377 | 0.3 | 0 | 0.03 | 0.061 | 0.033 | 80.1 | -
Pulsar Construction | 24422 |  |  |  |  | Cagayan River Flood Control |  | 2010-05-28 |  | II |  | 22.193 | 210 |  |  |  | O | 0.373 | 0.24 | 0.15 | 0.03 | 0.061 | 0.05 | 90.4 | -
Pulsar Construction | 24422 |  |  |  |  | Cagayan River Flood Control Project (Enrile Section) |  | 2010-02-21 |  | II |  | 22.193 | 210 |  |  |  | O | 0.35 | 0.3 | 0.15 | 0.03 | 0.057 | 0.05 | 93.7 | -
Pulsar Construction | 24422 |  |  |  |  | Construction of River Control Project |  | 2010-02-15 |  | II |  | 4.822 | 75 |  |  |  | O | 0.338 | 0.3 | 0.15 | 0.03 | 0.056 | 0.05 | 92.4 | -
Pulsar Construction | 24422 |  |  |  |  | Repair/Rehab. of Revetment Flood Control at Enrile Sect. along Cagayan River |  | 2010-05-28 |  | II |  | 14.998 | 180 |  |  |  | O | 0.366 | 0.3 | 0.15 | 0.03 | 0.061 | 0.033 | 94 | -
Pulsar Construction | 24422 | L | A | MB | GE1 | Rehab./Reconst./Upgrading of Damaged Paved National Roads Cagayan-Apayao Road, Sampaguita-Solano Section, |  | 2009-05-18 | 1st | II |  | 19.289 | 120 |  |  |  | O | 0.379 | 0.24 | 0.15 | 0.03 | 0.056 | 0.05 | 90.5 | -
Pulsar Construction | 24422 | L | A | MB | GE1 | Concrete Paving along JLLGR, San Pedro Section |  | 2009-02-23 | 2nd | II |  | 19.291 | 240 |  |  |  | O | 0.328 | 0.3 | 0.15 | 0.023 | 0.04 | 0.05 | #VALUE! | -
Pulsar Construction | 24422 | L | A | MA | GE2 | Const. of Sanchez Mira Flood Control Project | Sanchez Mira, Cagayan | 2012-03-14 | 1st | II | LF | 16.561 | 195 | 2011-12-19 | 2012-06-30 | 3.16 | O | 0.325 | 0.24 | 0.15 | 0.03 | 0.045 | 0.05 | 84 | -
Pulsar Construction | 24422 | L | A | MB | GE1 | Const. of Gagabutan Bridge No. 1 inc. PCCP along CAR | Rizal, Cagayan | 2012-11-25 | 1st | II | LF | 12.089 | 180 | 2012-07-09 | 2013-01-04 | 4.94 | O | 0.387 | 0.243 | 0.15 | 0.03 | 0.059 | 0.05 | 91.9 | -
Pulsar Construction | 24422 | L | A | MB | GE1 | Upgrading of Abbut-Conner-Kabugao Road |  | 2009-05-30 | 2nd | CAR |  | 13.99 | 330 |  |  |  | O | 0.388 | 0.242 | 0.11 | 0.03 | 0.04 | 0.05 | 86 | -
Pulsar Construction | 24422 | L | A | MB | GE1 | Upgrading of Abbut-Corner-Kabungao Road |  | 2009-02-28 | 1st | CAR |  | 13.991 | 428 |  |  |  | O | 0.4 | 0.3 | 0.15 | 0.03 | 0.037 | 0.033 | #VALUE! | -
Pulsar Construction | 24422 | L | A | MB | GE1 | Upgrading of Abbut-Conner-Kabugao Road |  | 2009-09-05 | 3rd | CAR |  | 13.991 | 428 |  |  |  | O | 0.382 | 0.24 | 0.046 | 0.03 | 0.056 | 0.017 | 77.1 | -
Pulsar Construction | 24422 |  |  |  |  | Road Upgrading (Gravel to Concrete) of Abbut-Conner-Kabugao Road, Mayogyog Section |  | 2010-02-21 |  | CAR |  | 17.997 | 377 |  |  |  | O | 0.357 | 0.24 | 0.15 | 0.03 | 0.05 | 0.033 | 86 | -
Pulsar Construction | 24422 | L | A | MA | GE2 | Addalam River Irrigation Project |  | 04/27/09 05/01/09 | 1st | NIA |  | 7.952 | 227 |  |  |  | O | 0.3297 | 0.2593 | 0.15 | 0.0225 | 0.0382 | 0.0333 | 83.3 | -
Pulsar Construction | 24422 | L | A | MB | GE1 | Rd. Upgrading (Gravel to Concrete) along Conner-Kabugao Rd., K0567+765.50-K0568+393.36 w/ exemption; K0568+393.36-K0569+208.36 | Conner, Apayao | 2012-11-28 | 1st | CAR | LF | 17.537 | 175 | 2012-01-27 | 2012-07-19 | - | O | 0.326 | 0.3 | 0 | 0.02 | 0.042 | 0.033 | 72.1 | -
PULSAR CONSTRUCTION | 24422 | L | AA | MA | GE | Construction of Sipa Flood Control Structures, Sta. Marcela, Apayao | Sta. Marcela, Apayao | 2015-08-26 | 1st | Apayao 2nd DEO | LF | 41.288 | 290 | 2015-04-13 | 2016-01-27 | 0.7% | O | 0.364 | 0.278 | 0.15 | 0.03 | 0.06 | 0.05 | 93.2% | -
PULSAR CONSTRUCTION | 24422 | L | AA | LA | GE | Road Upgrading (Unpaved to Paved) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standards (HDM-4 Project Analysis) along Sampaguita - Warat - La Suerte - Piat Road, Piat, Cagayan | Piat, Cagayan | 2015-08-25 | 1st | Cagayan 2nd DEO | LF | 46.122 | 224 | 2015-02-19 | 2015-09-30 | 0.07% | O | 0.368 | 0.256 | 0.15 | 0.03 | 0.06 | 0.05 | 91.4% | -
PULSAR CONSTRUCTION | 24422 | L | AAA | LA | GE | Rehabilitation/Reconstruction/Upgrading of Peñablanca Callao Cave Road, K0475+619 - K0475+212, Chainage 0-Chainage 110, Chainage 0-Chainage 138, Peñablanca, Cagayan | Peñablanca, Cagayan | 2015-11-10 | Final | CAGAYAN 3RD DEO | LF | 13.2531 | 90 | 2015-04-28 | 2015-07-27 | (+) 0.12 | C | 0.351 | 0.134 | 0.3 | - | - | - | 78.5% | 78.5% Unsatisfactory
Pulsar Construction / Deoj Construction (JV) | JV-11-684 | L | A | MB | GE1 | Const. of Illuru Bridge No.3 inc. PCCP along Cagayan-Apayao Rd. | Rizal, Cagayan | 2013-08-03 | Final | II | LF | 19.879 | 270 | 2012-07-09 | 2013-04-04 | 0 | C | 0.474 | 0.133 | 0.3 | - | - | - | 90.7 | 90.28% V. Satisfactory
Pulsar Construction / Deoj Construction (JV) | JV-11-684 | L | A | MB | GE1 | Const. of Illuru No.3 inc. PCCP | Rizal, Cagayan | 2013-03-12 | 2nd | II | LF | 19.879 | 270 | 2012-07-09 | 2013-04-04 | 0.67 | O | 0.377 | 0.3 | 0 | 0.03 | 0.061 | 0.033 | 80.1 | -
Pulsar Construction / Deoj Construction Joint Venture | JV-11-684 | L | A | MB | GE1 | Const. of Illuru Bridge No. 3 inc PCCP | Rizal, Cagayan | 2012-11-25 | 1st | II | LF | 19.042 | 210 | 2012-07-09 | 2013-02-03 | 2.81 | O | 0.392 | 0.242 | 0.15 | 0.03 | 0.059 | 0.033 | 90.6 | -
PUREGOLD CONSTRUCTION & DEVELOPMENT CORP | 34258 | L | C | SB | GE | Road Upgrading (Unpaved to Paved) Based on Gravel Road Strategies Traffic Benchmark for Upgrading to Paved Road Standards (HDM-4) (Project Analysis) Dologon, Maramag, Bukidnon, K1546+136-K1546+518.50 | Dologon, Maramag, Bukidnon, K1546+136-K1546+518.50 | 2015-08-27 | 1st & Final | Bukidnon 2nd DEO | LF | 10.477 | 94 | 2015-02-27 | 2015-05-31 | - | C | 0.489 | 0.133 | 0.3 | - | - | - | 92.2% | *92.20% Very Satisfactory
Puregold Construction & Development Corp. | 34258 | L | C | SB | GE | Construction of Flood Control at Sibulan River, Sta. Cruz, Davao del Sur | Sta. Cruz, Davao delSur | 2014-08-06 | 1st & Final | XI | LF | 4.7744 | 75 | 2014-02-17 | 2014-04-11 | 45.65 | C | 0.431 | 0.133 | 0.3 |  |  |  | 86.4 | 86.40% Satisfactory
Puregold Construction & Development Corp. | 34258 | L | C | SB | GB | Construction of Multi-Purpose Building at Zone IV | Sta. Cruz, Davao del Sur | 2014-10-24 | 1st & Final | XI | LF | 1.8444 | 60 | 2014-04-29 | 2014-06-27 |  | C | 0.442 | 0.133 | 0.3 | - | - | - | 87.5% | 87.5% Satisfactory
PUREGOLD CONSTRUCTION & DEVELOPMENT CORP. | 34258 | L | A | SB | GB | Rehabilitation of Multi-Purpose Building (Supergym), Brgy. Poblacion, Matanao, Davao del Sur | Brgy. Poblacion, Matanao, Davao del Sur | 2015-09-02 | 1st & Final | Davao del Sur First DEO | LF | 7.636 | 120 | 2015-04-30 | 2015-08-27 | - | C | 0.476 | 0.133 | 0.3 | - | - | - | 90.9% | *90.9% Very Satisfactory
PUREGOLD CONSTRUCTION AND DEVELOPMENT CORP. | 34258 | L | A | SB | GE | Improvement of Roads with Drainage System at Brgy. 177, Caloocan City | Caloocan City | 2015-06-06 | 1st | Metro Manila 3rd DEO | LF | 7.612 | 150 | 2015-03-20 | 2015-08-16 | (+) 0.23 | O | 0.392 | 0.24 | 0.15 | 0.022 | 0.042 | 0.05 | 89.6% | -
PUREGOLD CONSTRUCTION AND DEVELOPMENT CORP. | 34258 | L | A | SB | GE | Rehabilitation of Road, Yangco St. Brgy. Navotas East, Navotas City | Brgy. Navotas East, Navotas City | 2015-06-05 | 1st | Malabon-Navotas DEO | LF | 6.504 | 121 | 2015-03-10 | 2015-07-28 | (+) 0.10 | O | 0.38 | 0.24 | 0.15 | 0.015 | 0.046 | 0.05 | 88.1% | -
Pyramid Consolidated Builders & Gen. Merchandise | 15599 | L | B | SB | GB | Const. of 1 Storey - 2 CL School Building, Sil-ipon E/S | Libona, Bukidnon | 2014-10-21 | 1st | X | LF | 1.8608 | 120 | 2014-07-10 | 2014-11-06 | 5.46% | O | 0.305 | 0.278 | 0.15 | 0.01 | 0.038 | 0.05 | 83.1% | 83.1% Satisfactory
Pyramid Consolidated Builders & Gen. Merchandise | 15599 | L | C | SB | GE1 | Rehab./Upgrading (Asphalt to Concrete) along S.H. Alae-Kisolon Rd., Maluko-Kisolon Rd. Sect., K1472+355.95-K1472+895.95, Manolo Fortich | Sumilao, Bukidnon | 2013-08-06 | Final | X | LF | 10.909 | 127 | 2012-12-21 | 2013-04-26 | 45.33 | C | 0.406 | 0.133 | 0.3 | - | - | - | 83.9 | 85.04% Satisfactory
Pyramid Consolidated Builders & Gen. Merchandise | 15599 | L | D | SB | GB1 | Const. of 2-Cl Modified Standard School Buildin Mahayag NHS |  | 2009-03-12 | 1st | IX |  | 0.949 | 90 |  |  |  | O | 0.349 | 0.247 | 0.15 | 0.03 | 0.03 | 0.05 | #VALUE! | -
Pyramid Consolidated Builders & Gen. Merchandise | 15599 |  |  |  |  | Const. of Seawall, San Alonzo, Balingoan |  | 2010-03-03 |  | X |  | 0.447 | 119 |  |  |  | O | 0.329 | 0.24 | 0.15 | 0.03 | 0.047 | 0.05 | 84.6 | -
PYRAMID CONSOLIDATED BUILDERS & GEN. MERCHANDISE | 15599 | L | B | MA | GE | Cluster "21" Rehabilitation/Major Repair of Bridges (Mangima Bridge & Dicklum Bridge), along Sayre Highway (Alae-Kisolon Road), Manolo Fortich, Bukidnon | Manolo Fortich, Bukidnon | 2015-11-13 | Final | Bukidnon 3rd | LF | 2.9743 | 140 | 2015-02-10 | 2015-06-30 | (+) 11.42% | C | 0.48 | 0.133 | 0.3 | - | - | - | 91.3% | 91.3% Very Satisfactory
Pyramid Consolidated Builders & General Merchandise | 15599 | L | C | SB | GE1 | Rehab./Upgrading (Asphalt to Concrete) along S.H. Alae-Kisolon Road, Maluka-Kisolon Rd. Sect., K1462+300-K1472+895.95, Manolo Fortich-Sumilao | Bukidnon | 2013-03-21 | 1st | X | LF | 10.909 | 127 | 2012-12-21 | 2013-04-26 | 35.69 | O | 0.283 | 0.3 | 0.15 | 0.03 | 0.045 | 0.05 | 85.8 | -
Q.C.D. Construction & Supply | 37537 | L | C | SB | GB | Construction of Classroom in Areas Experiencing Acute Classroom Shortage, Macalong E/S, One (1) Classroom School Building | Macalong, Kasibu, Nueva Vizcaya | 2014-10-30 | 1st & Final | II | LF | 1.1197 | 90 | 2014-07-15 | 2014-10-12 |  | C | 0.478 | 0.133 | 0.3 | - | - | - | 91.1% | 91.1% Very Satisfactory
Q.C.D. Construction & Supply | 37537 | L | C | SB | GB | Construction of Classroom, Bonfal West ES | Bayombong, Nueva Vizcaya | 2014-10-29 | 1st & Final | II | LF | 1.068 | 58 | 2014-09-04 | 2014-10-28 |  | C | 0.448 | 0.133 | 0.3 | - | - | - | 88.1% | 88.1% Satisfactory
Q.C.D. CONSTRUCTION & SUPPLY | 37537 | L | C | SB | GB | Const./Repair/Rehab./Impvt. of VILP - Const. of the Office of the Vice President, Office of the Senior Citizen's Affairs (MPB Center), Sta. Fe, Nueva Vizcaya | Sta. Fe, Nueva Vizcaya | 2015-09-03 | 1st & Final | NV 2nd DEO | LF | 1.91 | 150 | 2015-06-09 | 2015-11-05 | 89.83% | C | 0.424 | 0.164 | 0.3 | - | - | - | 88.8% | *88.8% Satisfactory
Qingjian Group Co., Ltd. Philippine Branch | FC-10-005 | F | AAA | LB | GE1 | Impv't. of Digos-Cotabato Rd., CP-RI-2.7A: Digos-Kidapawan Sect. under the Nat'l Rds. Impv't. & Mgt. Program-Phase II (NRIMP-2) | Mindanao | 2013-08-22 | 1st | NRIM-PMO | FA | 623.61 | 731 | 2011-08-17 | 2013-08-16 | -1.79 | O | 0.378 | 0.3 | 0.132 | 0.03 | 0.051 | 0.033 | 92.4
Qingjian Group Co., Ltd. Philippine Branch | FC-11-011 | L | AAA | LB | GE1 | CP-R1-2.4: Impv't. of Bacolod-Kabankalan Rd., Bacolod-Bago Sect., under Nat'l Rds. Impv't. Mgt. Program, Phase II (NRIMP-2), Bacolod-Bago City Sect. | Negros Occidental | 2013-08-07 | 1st | NRIM-PMO | FA | 340.6 | 540 | 2012-06-09 | 2013-11-30 | -9.94 | O | 0.394 | 0.3 | 0.051 | 0.03 | 0.051 | 0.05 | 87.6
QM Builders | 30743 | L | A | MB | GE | Road Upgrading (Concreting) of Tapal - (Carcar) Zaragosa - Olango - Aloguinsan Road, K0081+600 to K0083+020 | Aloguinsan, Cebu | 2014-10-23 | 1st & Final | VII | LF | 39.547 | 166 | 2014-02-13 | 2014-07-28 | 0% | C | 0.391 | 0.138 | 0.3 | - | - | - | 82.9% | 82.9% Satisfactory
QM Builders | 30743-B | L | A | MB | GE | Widening of Cebu-Toledo Wharf Road Km.20+560 to Km. 21+120, Talisay City Section | Talisay City, Cebu | 2014-08-04 | 1st | VII | LF | 45.7681 | 224 | 2014-01-24 | 2014-09-05 | #VALUE! | O | 0.397 | 0.281 | 0.15 | 0.018 | 0.037 | 0.033 | 91.6
QM Builders | 30743 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Paved) along Dalaguete-Mantalongon-Badian Rd., K0091+580-K0092+019 (Phase 1) & K0091+580-K0091+145 (Phase 2 & 3) | Dalaguete, Cebu | 2013-08-08 | 1st | VII | LF | 59.05 | 351 | 2013-02-22 | 2014-02-07 | 25.21 | O | 0.396 | 0.288 | 0.15 | 0.03 | 0.056 | 0.033 | 95.3
QM Builders | 30743 | L | B | MA | GE1 | Rd. Upgrading (Conc.) of Toledo-Pinamungajan-Aloguinsan-Mantalongon Rd., K0081+160-K0083+094 | Aloguinsan, Cebu | 2013-08-07 | Final | VII | LF | 10.787 | 103 | 2013-01-24 | 2013-05-06 | 8.11 | C | 0.439 | 0.178 | 0.3 | - | - | - | 91.7 | 90.86% V. Satisfactory
QM Builders | 30743 | L | B | MA | GE1 | Rd. Upgrading (Conc.) of Toledo-Pinamungajan-Aloguinsan-Mantalongon Rd. K0081+160-K0083+094 | Aloguinsan, Cebu | 2013-03-15 | 1st | VII | LF | 10.787 | 74 | 2013-01-24 | 2013-04-07 | 20.55 | O | 0.335 | 0.3 | 0.15 | 0.03 | 0.055 | 0.033 | 90.3 | -
QM Builders | 30743 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rds., Cebu-Toledo Wharf Rd., Km.11+216-Km.12+000 | Cebu | 2013-08-06 | Final | VII | LF | 16.266 | 210 | 2012-07-02 | 2013-01-27 | 0.96 | C | 0.436 | 0.155 | 0.3 | - | - | - | 89.1 | 87.30% Satisfactory
QM Builders | 30743 | L | B | MA | GE1 | Rehab. of Cebu-Toledo Wharf Road | Cebu | 2013-03-15 | 2nd | VII | LF | 52.337 | 238 | 2012-07-27 | 2013-03-21 | 0.51 | O | 0.378 | 0 | 0.2 | 0.05 | 0.073 | 0.125 | 82.6 | -
QM Builders | 30743 | L | B | MA | GE1 | Road Rehab./Reconst./Upgrading along Sibonga-Dumanjug Road, Balagytiki Section |  | 2009-05-29 | 1st | VII |  | 14.037 | 75 |  |  |  | O | 0.392 | 0.3 | 0.15 | 0.03 | 0.05 | 0.05 | 97.2 | -
QM Builders | 30743 | L | B | MA | GE1 | Const. of Roadway Realignment /Widening of Cebu-Balamban-Transcentral Road Km. 37+910-Km. 37+960, Sitio Kurus-Kurus |  | 2009-05-26 | 1st | VII |  | 9.524 | 120 |  |  |  | O | 0.4 | - | 0.2 | 0.05 | 0.071 | 0.25 | 97.1 | -
QM Builders | 30743 | L | B | MA | GE1 | Road Upgrading (Gravel to Paved) along Sibonga-Dumanjug Road |  | 2009-05-29 | 1st | VII |  | 18.718 | 75 |  |  |  | O | 0.377 | 0.3 | 0.15 | 0.03 | 0.05 | 0.05 | 95.7 | -
QM Builders | 30743 | L | B | MA | GE1 | Imprv't.(Conc.) of Access Rd., Bais Port Access Rd. |  | 2009-09-12 | 1st | VII |  | 19.168 | 200 |  |  |  | O | 0.252 | 0.3 | 0.15 | 0.03 | 0.047 | 0.05 | 82.9 | -
QM Builders | 30743 |  |  |  |  | Road Widening of Toledo-Pinamungajan-Mantalongon Rd. Km.77+320 - Km.78+400, Aloguinsan Sect. |  | 2010-06-12 |  | VII |  | 16.338 | 120 |  |  |  | O | 0.4 | 0.3 | 0.15 | 0.03 | 0.037 | 0.033 | 95 | -
QM Builders | 30743 |  |  |  |  | Road Widening of Toledo-Pinamungajan-Mantalongon Rd. Km.86+987.10 - Km.87+721.24 |  | 2010-06-12 |  | VII |  | 13.554 | 120 |  |  |  | O | 0.348 | 0.297 | 0.15 | 0.03 | 0.035 | 0.033 | 89.3 | -
QM Builders | 30743 | L | B | MA | GE1 | Rehab./Reconstruction of Cebu-Toledo Wharf Road |  | 2009-03-16 | 1st | VII |  | 21.217 | 150 |  |  |  | O | 0.372 | 0.3 | 0 | 0.022 | 0.027 | 0.05 | #VALUE! | -
QM Builders | 30743 | L | B | MA | GE1 | Repair/Rehab. of Brgy. Upper Tunghaan to Sitio Maria Respondo FMR |  | 2009-09-10 | 1st | VII |  | 14.41 | 120 |  |  |  | O | 0.341 | 0.24 | 0.15 | 0.03 | 0.04 | 0.05 | 85.1 | -
QM BUILDERS | 30743 | L | B | MA | GE | Construction/Upgrading of Cebu Toledo Wharf Road, Cebu Province, Section 1: Sta. 17+843- Sta. 18+483; Section 2: sta. 18+483-Sta. 18+694.03; Section 3: Sta. 18+771-Sta. 21+926; Section 4: Sta. 21+926- Sta. 21+968.24; Section 5: Sta. 23+110-Sta. 23+894; Section 6: Sta. 27+888 -Sta.28+000 | Cebu Toledo Wharf, Cebu | 2015-06-03 | Final | Regional Office No. VII | LF | 45.438 | 300 | 2014-06-02 | 2015-03-28 | 0% | C | 0.425 | 0.192 | 0.3 | - | - | - | 91.7% | *91.7% Very Satisfactory
QM BUILDERS | 30743 | L | A | MB | GE | Widening of Cebu South Coastal Road ( CSCR) | K0011+184 to K0011+857, Cebu Province | 2015-06-03 | 1st | Cebu Second DEO | LF | 15.166 | 219 | 2015-02-24 | 2015-09-30 | 20% | O | 0.376 | 0.245 | 0.15 | 0.03 | 0.05 | 0.033 | 88.4% | -
QM BUILDERS | 30743 | L | A | MB | GE | Off Carriageway Improvement, Palo-Carigara-Ormoc Road, K1009+904-K1010+933 Ormoc City | K1009+904-K1010+933 Ormoc City | 2015-08-28 | 1st | Leyte 4th DEO | LF | 16.766 | 255 | 2015-02-05 | 2015-10-17 | (+)0.92 | O | 0.346 | 0.266 | 0.15 | 0.01 | 0.03 | 0.05 | 85.2% | -
QM BUILDERS | 30743 | L | AA | MB | GE | Rehab./Reconst./Upgrading of Bayawan - Mabinay Road, Mabinay, K0139+340 - K0139+675 | 2nd District, Negros Oriental | 2015-08-24 | 1st & Final | Negros Oriental 2nd | LF | 8.247 | 172 | 2015-02-12 | 2015-08-02 | 0% | C | 0.434 | 0.171 | 0.3 | - | - | - | 90.5% | *90.5% Very Satisfactory
QM BUILDERS | 30743 | L | AA | MB | GE | Widening of Cebu South Coastal Road (CSCR), K0011+184 - K0011+857 | Cebu Province | 2015-08-31 | Final | Cebu 2nd | LF | 15.168 | 166 | 2015-02-24 | 2015-08-08 | 0.6% | C | 0.447 | 0.149 | 0.3 | - | - | - | 89.6% | *88.88% Satisfactory
QM BUILDERS | 30743 | L | A | MB | GE | Construction/Improvement of Access Road Leading to Declared Tourism Destination, Mabinay Road Leading to Crystal Cave, Mabinay, Negros Occidental | Mabinay, Negros Occidental | 2015-11-13 | 1st | Negros Oriental 2nd DEO | LF | 27.783 | 239 | 2015-03-25 | 2015-11-18 | (+)0.08% | OG | 0.378 | 0.247 | 0.15 | 0.03 | 0.055 | 0.05 | 91% | 91% Very Satisfactory
QM BUILDERS | 30743 | L | A | MB | GE | Rehab./Reconst./Upgrading of Bayawan-Mabinay Road, Mabinay, K0139+340-K0139+675, 2nd District, Negros Occidental | Mabinay, 2nd District, Negros Occidental | 2015-11-12 | Final | Negros Oriental 2nd DEO | LF | 8.2467 | 172 | 2015-02-12 | 2015-08-02 | - | C | 0.427 | 0.133 | 0.3 | - | - | - | 86% | 88.7% Satisfactory
QM BUILDERS | 30743 | L | A | MB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Road including Drainage along Antoni Y. De Pio Highway (Intermittent Sections): K0114+548 - K0114+824; K0119+000 - K0119+826; K0119+852 - K0120+282, San Remigio, Cebu | San Remigio, Cebu | 2015-11-13 | Final | Cebu 1st | LF | 28.9094 | 208 | 2015-03-03 | 2015-09-26 | 0 | C | 0.423 | 0.133 | 0.3 | - | - | - | 85.6% | 85.6% Satisfactory
QM BUILDERS | 30743 | L | A | MB | GE | Asset Preservation of National Roads - Rehabilitation/ Reconstruction/ Upgrading of National Roads with Slips, Collapse and Landslide Secondary Roads at Cebu - Toledo Wharf Road (Jct. Naga Uling) - K0016+500-K0016+800, K0017+520-K0017+620, K0020+560-K0020+720, K0020+940; K0020+000-K0021+160, Cebu Province | Cebu Province | 2015-11-09 | 1st | Cebu 2nd | LF | 34.8797 | 239 | 2015-04-22 | 2015-12-16 | 0.06 | OG | 0.35 | 0.24 | 0.15 | 0.03 | 0.04 | 0.05 | 86% | 86% Satisfactory
QM Builders | 30743 | L | B | MA | GE1 | Rehab. of Cebu-Toledo Wharf Rd. | Cebu | 2012-11-19 | 1st | VII | LF | 52.337 | 210 | 2012-07-27 | 2013-02-21 | 46.91 | O | 0.398 | 0.291 | 0.15 | 0.03 | 0.035 | 0.033 | 93.7 | -
QM Builders / Ven Ray Construction (JV) | JV-11-488 | L | B | MA | GE1 | Rehab. of Toledo-Pinamungahan-Mantalongon Rd. | Cebu | 2013-03-15 | Final | VII | LF | 62.992 | 270 | 2012-05-22 | 2013-02-15 | 1.71 | C | 0.444 | 0.2 | 0.3 | - | - | - | 94.4 | 88.79% Satisfactory
QM BUILDERS/RJIR ENTERPRISES JOINT VENTURE | JV-14-520 | L | A | MB | GE | Off-Carriageway Improvement, Palo-Carigara-Ormoc Road, K999+000-K1000+000, Ormoc, Leyte | Ormoc, Leyte | 2015-11-14 | Final | Leyte Fourth DEO | LF | 16.8045 | 136 | 2015-02-05 | 2015-06-20 | - | C | 0.395 | 0.2 | 0.3 | - | - | - | 89.5% | 89.5% Very Satisfactory
Quadcore Construction and Development Corporation | 34815 |  | A |  |  | Construction of Fourteen (14) 3-Storey LRB and Land Development, Disiplina Village Site 1 Package 2 | Brgy. Bignay, Valenzuela City | 2016-01-15 | 1st | NHA | LF | 187.558 | 445 | 2015-01-15 | 2016-04-03 | -9.98 | O | 0.3915 | 0.255 | 0.0502 | 0.03 | 0.051 | 0.017 | 79.47 | -
Quezon Victory General Contractor | 6631 |  |  |  |  | Road Upgrading (Gravel to Paved) MSR Jct.-Lopez-Hondagua Port Road |  | 2010-05-31 |  | IVA |  | 21.515 | 90 |  |  |  | O | 0.384 | 0.225 | 0.15 | 0.03 | 0.05 | 0.05 | 88.9 | -
Quezon Victory General Contractor | 6631 | L | B | MA | GE1 | Rehab./Reconst. of Tiaong-San Antonio Road |  | 2009-05-25 | 1st | IVA |  | 9.59 | 139 |  |  |  | O | 0.384 | 0.24 | 0.15 | 0.03 | 0.025 | 0.05 | 87.9 | -
Quezon Victory General Contractor | 6631 | L | B | MA | GE1 | Concreting of Gumaca-Pitogo-Mulanay-San Narciso Road |  | 2009-05-26 | 1st | IVA |  | 14.473 | 146 |  |  |  | O | 0.393 | 0.24 | 0.15 | 0.02 | 0.025 | 0.05 | 87.8 | -
Quezon Victory General Contractor | 6631 | L | B | MA | GE1 | Const./Conc. of Candelaria-By-Pass Road inc. RROW at Brgy. Mangilag Sur |  | 2009-05-25 | 1st | IVA |  | 17.658 | 99 |  |  |  | O | 0.358 | 0.24 | 0.15 | 0.03 | 0.025 | 0.05 | 85.3 | -
Quezon Victory Lumber and General Contractor (Formerly: Quezon Victory General Contractor) | 6631 | L | B | MA | GE | Road Upgrading along MSR Jct. lopez-Cabanatuan Road, K0237+005-K0257+835, K0238+009-K0238+899, Net Length=1.63kms., 230mm thick | General Luna, Quezon | 2014-11-29 | 1st & Final | IV | LF | 37.2713 | 280 | 2014-01-27 | 2014-11-02 | - | C | 0.444 | 0.133 | 0.3 | - | - | - | 87.7% | 87.7% Satisfactory
Quezon Victory Lumber and General Contractor (Formerly: Quezon Victory General Contractor) | 6631 | L | B | MA | GE1 | Rehab./Impvt. of MSR Diversion Rd., Km.125+(-241)-Km.125+680 w/ exception | Quezon | 2011-08-08 | 1st | IVA | LF | 16.928 | 170 | 2011-06-02 | 2011-11-18 | 10.49 | O | 0.309 | 0.3 | 0.15 | 0.03 | 0.04 | 0.05 | 87.9 | -
QUIRANTE CONSTRUCTION | 32827 | L | B | MA | GE | Road Upgrading (Unpaved to Paved) Based on Gravel Strategies Traffic Benchmmark for Upgrading to Paved Road Standards (HDM-4 Project Analysis) (I.S.) Nat'l Scdry Rds Tapal ( Carcar) Zaragosa-Olango-Aloguinsan Rd | K0088+737-K0089+795, Cebu Province | 2015-06-02 | 1st | Cebu Second | LF | 23.456 | 209 | 2015-01-26 | 2015-08-22 | 0% | O | 0.337 | 0.246 | 0.15 | 0.03 | 0.045 | 0.05 | 85.8% | -
QUIRANTE CONSTRUCTION | 32827 | L | B | MA | GE | Local Infrastructure Program/Rehabilitation of Road, City of Carcar, Cebu 1st LD at Valladolid-Poblacion III | Carcar City, Cebu | 2015-06-02 | 1st | Cebu Second DEO | LF | 4.778 | 151 | 2015-02-24 | 2015-07-24 | 0.63% | O | 0.334 | 0.254 | 0.15 | 0.03 | 0.045 | 0.033 | 84.6% | -
QUIRANTE CONSTRUCTION | 32827 | L | B | MA | GE | Asset Preservation of National Road - Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads including drainage based on Pavement Management System/ Highway Development and Management -4 (HDM-4) (Intermittent Secions) National Arterial Roads Carcar-Barili-Mantayupan Road, K0044+000 - K0044+462, K0045+640 - K0046+088, Cebu Province | Cebu Province | 2015-11-10 | 1st | Cebu 2nd | LF | 13.3912 | 224 | 2015-04-22 | 2015-12-01 | 0.0991 | OG | 0.315 | 0.24 | 0.15 | 0.03 | 0.06 | 0.05 | 84.5% | 84.5% Satisfactory
QUIRANTE CONSTRUCTION | 32827 | L | B | MA | GE | Local Infrastruture Program/Rehabilitation of Road, City of Carcar, Cebu 1st LD at Valladolid - Poblacion III Road | Carcar City, Cebu | 2015-08-31 | Final | Cebu 2nd | LF | 4.779 | 151 | 2015-02-24 | 2015-07-24 | 0% | C | 0.322 | 0.197 | 0.3 | - | - | - | 81.9% | *83.52% Satisfactory
R C S Construction | 12458 | L | C | SB | GB1 | Repair/Rehab. of One (1) Classroom School Building @ M.P. Cuaderno Sr., ES, Brgy. Sibacan |  | 2009-08-28 | 1st | III |  | 0.49 | 53 |  |  |  | O | 0.384 | 0.24 | 0.15 | 0.02 | 0.037 | 0.033 | 86.4 | -
R N V CONSTRUCTION | 12570 | L | D | SB | GB | Construction/Completion of Multi-Purpose Building Budiong | Odiongan, Romblon | 2015-06-12 | 1st | Romblon DEO | LF | 3.932 | 120 | 2015-04-08 | 2015-08-05 | 0% | O | 0.336 | 0.243 | 0.15 | 0.02 | 0.053 | 0.05 | 85.2% | -
R N V Construction | 12570 | L | D | SB | GE2 | Const. of Bachawan River Control along Tablas Circ. Rd. | San Agustin, Romblon | 2013-08-05 | Final | IVB | LF | 1.616 | 85 | 2012-09-19 | 2012-12-13 | 0 | C | 0.373 | 0.2 | 0.3 | - | - | - | 87.3 | 86.58% Satisfactory
R N V Construction | 12570 | L | D | SB | GE2 | Const. of Line Canal along Tablas Circ. Rd., K039+550-K040+250 | Tablas Island, Romblon | 2013-08-05 | Final | IVB | LF | 3.08 | 65 | 2012-10-19 | 2012-12-22 | 4 | C | 0 | 0.2 | 0.3 | - | - | - | 50 | 72.32% Poor
R N V Construction | 12570 |  |  |  |  | Const./Imprv't of Brgy. Poblacion Line Canal-San Andres |  | 2010-02-22 |  | IVB |  | 1.466 | 100 |  |  |  | O | 0.274 | 0.3 | 0.15 | 0.03 | 0.048 | 0.033 | 83.5 | -
R N V Construction | 12570 | L | D | SB | GE1 | Rehab./Impvt. of Romblon DEO |  | 2008-11-24 | 1st | IVB |  | 4.693 | 146 |  |  |  | O | 0.355 | 0.24 | 0.1 | 0.03 | 0.032 | 0.1 | 85.7 | -
R N V CONSTRUCTION | 12570 | L | D | SB | GE | Construction of Road, Libertad-Tuburan Road | Odiongan, Romblon | 2015-06-14 | Final | Romblon DEO | LF | 4.849 | 60 | 2015-03-11 | 2015-05-09 | 0% | C | 0.423 | 0.133 | 0.3 | - | - | - | 85.6% | *85.6% Satisfactory
R N V Construction | 12570 | L | D | SB | GE2 | Const. of Bachawan River Control along Tablas Circ. Rd. | San Agustin, Romblon | 2012-11-29 | 1st | IVB | LF | 1.616 | 80 | 2012-09-19 | 2012-12-07 | 1.25 | O | 0.346 | 0.24 | 0.15 | 0.03 | 0.045 | 0.05 | 86.1 | -
R N V Construction | 12570 | L | D | SB | GE2 | Const. of Line Canal, Km.39+550-K0040+250 | Tablas Island, Romblon | 2012-11-29 | 1st | IVB | LF | 3.08 | 60 | 2012-10-19 | 2012-12-17 | 24 | O | 0.364 | 0.24 | 0.15 | 0.023 | 0.045 | 0.05 | 87.2 | -
R R C Construction | 24369 | L | A | MA | GE | Construction of Flood Control at Brgy. Bulihin with Drainage Outfall Connecting to National Road 5th Legislative District | Silang, Cavite | 2014-11-06 | 1st & Final | IV | LF | 22.4845 | 171 | 2014-02-17 | 2014-08-06 | - | C | 0.438 | 0.133 | 0.3 | - | - | - | 87.1% | 87.1% Satisfactory
R R C Construction | 24369 | L | A | MA | GE | Repair/Rehab along Santiago-Tuguegarao Road, K0419+259.21 to K0421+000, K0425+695.50 to K0426+200 & K0426+200 | Sta. Maria, Isabela | 2014-08-08 | Final | II | LF | 36.3636 | 289 | 2013-01-28 | 2013-11-12 | 0.02 | C | 0.407 | 0.131 | 0.3 |  |  |  | 83.8 | 87.40% Satisfactory
R R C Construction | 24369 | L | A | MA | GE1 | Repair/Rehab. Along Santiago-Tuguegarao Rd., K0419+259.21-K0421+000, K0425+695.50-K0426+200 & K0426+200-K0427+000 | Sta. Maria, Isabela | 2013-08-05 | 2nd | II | LF | 34.673 | 209 | 2013-01-28 | 2013-08-24 | 0.65 | O | 0.357 | 0.3 | 0.15 | 0.03 | 0.055 | 0.033 | 92.5
R R C Construction | 24369 | L | A | MA | GE1 | Repair/Rehab. of Santiago-Tuguegarao Rd., K0419+259.21-K0421+000, K0425+695.50-K0426+200 & K0426+200-K0427+000 | Sta. Maria, Isabela | 2013-03-13 | 1st | II | LF | 34.673 | 179 | 2013-01-28 | 2013-07-25 | 1.09 | O | 0.371 | 0.24 | 0.15 | 0.03 | 0.047 | 0.033 | 87.1 | -
R R C Construction | 24369 | L | A | MA | GE1 | Const. of Babanuang Bridge along Santiago-Tuguegarao Rd. (inclusive of Approaches & Detour Bridge) @ Brgy. Babanuang | San Manuel, Isabela | 2013-03-18 | 1st | II | LF | 10.906 | 240 | 2012-10-08 | 2013-06-03 | 6.89 | O | 0.399 | 0.225 | 0.15 | 0.03 | 0.039 | 0.033 | 87.6 | -
R R C Construction | 24369 | L | A | MA | GE1 | Repair/Maint. of Nat'l Rds. along Naguilian-San Mariano Rd. @ a)K0391+540-K0396+878 (Int. Sect.) Benito Soliven, Isabela & b)K0398+120-K0403+518 (Int. Sect.) San Mariano,Benito Soliven & San Mariano | Isabela | 2013-03-18 | Final | II | LF | 10.672 | 240 | 2012-06-25 | 2013-02-20 | 0.35 | C | 0.432 | 0.133 | 0.3 | - | - | - | 86.5 | 85.78% Satisfactory
R R C Construction | 24369 | L | A | MA | GE1 | Rehab./Strengthening of Paza Bridge, Manaring | Ilagan, Isabela | 2013-03-13 | 1st | II | LF | 4.726 | 89 | 2013-01-28 | 2013-04-26 | 1.15 | O | 0.337 | 0.126 | 0.15 | 0.03 | 0.04 | 0.033 | 71.6 | -
R R C CONSTRUCTION | 24369 | L | A | MA | GE | Assets Preservation of National Roads: Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads, Including Drainage Based on Pavement Management System/Highway Development and Management-4 (PMS/HDM-4) (I.S.) Gamu Roxas Road | Gamu & Roxas, Isabela | 2015-06-05 | 1st | Regional Office No. I | LF | 58.385 | 237 | 2015-02-28 | 2015-10-22 | 1.1% | O | 0.317 | 0.3 | 0.15 | 0.03 | 0.05 | 0.033 | 88% | -
R R C CONSTRUCTION | 24369 | L | A | MA | GE | Construction of River Bank Protection, Stiffu River Flood Control Project, San Placido Section, Roxas, Isabela | Roxas, Isabela | 2015-11-14 | Final | REGIONAL | LF | 18.3929 | 249 | 2015-02-24 | 2015-10-30 | (+) 0.01 | C | 0.4 | 0.133 | 0.3 | - | - | - | 83.3% | 83.3% Satisfactory
R TWO S BUILDERS AND ENTERPRISE | 36883 | L | D | SB | GE | Construction of Road at Santo Niño | Angadanan, Isabela | 2015-06-06 | Final | Isabela 3rd DEO | LF | 3.465 | 82 | 2014-06-24 | 2014-09-13 | 0% | C | 0.29 | 0.2 | 0.3 | - | - | - | 79% | *82.24% Satisfactory
R Two S Builders and Enterprises | 36883 | L | D | SB | GB | Construction of 1 Storey 2 CL 7.00mx18.00m School Building at Don Faustino N. Dy E/S | Cauayan City, Isabela | 2014-10-25 | 1st & Final | II | LF | 1.9021 | 92 | 2014-08-04 | 2014-11-03 | 9.03% | C | 0.483 | 0.132 | 0.3 | - | - | - | 91.5% | 91.5% Very Satisfactory
R Two S Builders and Enterprises | 36883 | L | D | SB | GE | Construction of Brgy. Road at Santo Niño | Angandanan, Isabela | 2014-08-11 | 1st | II | LF | 3.3958 | 82 | 2014-06-24 | 2014-09-13 | 3.54 | O | 0.306 | 0.29 | 0.15 | 0.03 | 0.035 | 0.033 | 84.4
R V Laborte Builders |  | L |  |  | GE2 | Castanas Centro Communal Irrigation System | Sariaya, Quezon | 2013-09-07 | 1st | NIA | L | 2.702 |  |  |  | 0 | O | 0.35 | 0.2437 | 0.15 | 0.02 | 0.023 | 0.05 | 83.67 | -
R. A. M. BUILDERS | 10549 | L | B | MA | GE | Widening of National Roads along National Road (NI) Daang Maharlika/Asian Highway-26, Daang Maharlika (LZ) K0102+694 - K0103+608, Candelaria Section, Candelaria, Quezon | Candelaria, Quezon | 2015-11-16 | 1st | QUEZON 2ND DEO | LF | 43.855 | 300 | 2015-01-23 | 2015-11-18 | 0.0629 | OG | 0.385 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 90.5% | 90.5% Very Satisfactory
R. A. PAHATI CONST. & SUPPLY INC. | 35843 | L | A | MB | GE | Network Development-Widening of National Roads-Arterial Roads along National Road 1 (N1)/Daang Maharlika/Asian Highway-26, Daang Maharlika (LZ), Nueva Ecija 4th Legislative District, Nueva Ecija | Daang Maharlika (LZ), Nueva Ecija 4th Legislative District, Nueva Ecija | 2015-09-02 | 1st | Regional Office No. III | LF | 49.225 | 240 | 2015-06-05 | 2016-01-30 | 23.85% | O | 0.341 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 86.6% | -
R. A. PAHATI CONST. & SUPPLY, INC. | 35843 | L | A | MA | GE | Flood Management Service-Construction/Maintenance of Flood Mitigation Structures and Drainage Systems, Construction of Retaining Wall of Nangka River, Sta. 2+870 - Sta. 3+150 & Sta. 3+650 - Sta. 3+850, Brgy. Sto. Niño, San Mateo, Rizal 2nd LD | San Mateo, Rizal, 2nd LD | 2015-11-02 | Final | RIZAL 2ND DEO | LF | 35.2459 | 190 | 2015-03-10 | 2015-09-15 | 0.3263 | C | 0.438 | 0.133 | 0.3 | - | - | - | 87.1% | 88.9% Satisfactory
R. Allosa Construction & Trucking Service (Formerly: R. Allosa Construction) | 12964 | L | B | SB | GE1 | Rd. Upgrading (Gravel to Paved) of Calubian Jct. San Isidro-Tabango-Villaba-Palompon Rd., Km.1034+479-Km.1034+708; & Km.1035+184-Km.1035+624 | Tabango, Leyte | 2013-03-13 | 1st | VIII | LF | 13.286 | 210 | 2013-01-07 | 2013-08-04 | 35.07 | O | 0.328 | 0.237 | 0.15 | 0.03 | 0.045 | 0.033 | 82.3 | -
R. ALLOSA CONSTRUCTION & TRUCKING SERVICES | 12964 | L | B | MA | GE | Road Upgrading (Unpaved to Paved) of Tabango- Catmon, La Fortuna- Manlawaan- Gimarco Road, K1039+287.50 to K039+642, K1045+032 to K1045+047, Tabango, Leyte | K1039+287.50 to K039+642, K1045+032 to K1045+047, Tabango, Leyte | 2015-06-10 | 1st | Leyte Third DEO | LF | 10.053 | 179 | 2015-02-06 | 2015-08-03 | - | O | 0.344 | 0.236 | 0.15 | 0.012 | 0.01 | 0.05 | 80.2% | -
R. ALLOSA CONSTRUCTION & TRUCKING SERVICES | 12964 | L | B | MA | GE | Road Upgrading (Unpaved to Paved) of Tabango-Catmon La Fortuna-Manlawaan-Gimarco Road, K1039+287.56-K1039+642; K1045+032-K1045+047, Tabango, Leyte | K1039+287.56-K1039+642; K1045+032-K1045+047, Tabango, Leyte | 2015-08-26 | Final | Leyte 3rd DEO | LF | 10.053 | 179 | 2015-02-06 | 2015-08-03 | (+)11.17 | C | 0.333 | 0.2 | 0.3 | - | - | - | 83.3% | *81.44% Unsatisfactory
R. C. Tagala Construction | 11597 | L | A | MB | GE1 | Rehab. of Tabla-Sta. Cruz Section, Tanjay, Dumaguete North Rd., Km.35.183-Km.36.183 | Tanjay City, Negros Oriental | 2011-08-08 | 2nd | VII | LF | 19.2 | 250 | 2010-12-17 | 2011-09-13 | 0.39 | O | 0.344 | 0.3 | 0.15 | 0.03 | 0.025 | 0.033 | 88.2 | -
R. C. Tagala Construction | 11597 |  | A | MB |  | Culasi Port Development Project | Poblacion, Culasi, Antique/ Region VI | 2015-12-02 | 2nd & Final | DOTC | LF | 21.002 | 210 | 2014-03-17 | 2015-01-02 | 0 | C | 0.4836 | 0.2 | 0 | - | - | - | 68.36 | 77.70% Unsatisfactory
R. C. TAGALA CONSTRUCTION | 11597 | L | A | MB | GE | Concrete Paving/Widening along Manila North Road, K0290+000 to K0292+000, With Exceptions, Bacnotan, La Union | K0290+000 to K0292+000, With Exceptions, Bacnotan, La Union | 2015-08-29 | 1st | La Union 1st DEO | LF | 18.453 | 214 | 2015-02-11 | 2015-09-13 | (+)0.47 | O | 0.323 | 0.3 | 0.15 | 0.023 | 0.051 | 0.05 | 89.7% | -
R. C. TAGALA CONSTRUCTION | 11597 | L | A | MA | GE | Concrete Paving/Widening along Manila North Road, K0290+000 to K0292+000 with exceptions, Bacnotan, La Union | Bacnotan, La Union | 2015-11-10 | Final | REGIONAL OFFICE | LF | 1.846 | 214 | 2015-02-11 | 2015-09-12 | 0.003 | C | 0.455 | 0.133 | 0.3 | - | - | - | 88.8% | 89.04% Very Satisfactory
R. D Interior Jr. Const./Brostan Const. Dev't (JV) | JV-08-002 | L | AA | LB | GE1 | Pagadian Airport Development Project |  | 2009-03-23 | 1st | DOTC |  | 174.361 | 360 |  |  |  | O | 0.377 | 0.3 | 0.15 | 0.03 | 0.056 | 0.05 | 96.3 | -
R. D Policarpio Co., Inc. | 4414 | L | AAA | LB | GE1 | Tacloban Airport Development Project |  | 2009-10-08 | 1st | DOTC |  | 0.126 | 180 |  |  |  | O | 0.365 | 0.3 | 0.04 | 0.03 | 0.042 | 0.05 | 82.7 | -
R. D. Interior Junior Construction | 6483 | L | AAA | LB |  | Pinamalayan Airport Development Project | Pinamalayan, Oriental Mindoro/ Region IV-B | 2015-03-25 | Final | DOTC | L | 62.125 | 266 | 2014-06-07 | 2015-03-28 | 0 | C | 0.48 | 0.2 | 0.3 | - | - | - | - | 90.78% V. Satisfactory
R. D. Interior Junior Construction | 6483 | L | AAA | LB | GE-1 | Pinamalayan Airport Development Project | Pinamalayan, Oriental Mindoro | 2014-12-04 | 1st | DOTC | LF | 62.125 | 180 | 2014-05-27 | 2015-01-02 | -13.14 | O | 0.397 | 0.2 | 0.0186 | 0.03 | 0.0642 | 0.05 | 75.98 | -
R. D. INTERIOR JUNIOR CONSTRUCTION | 6483 | L | AAA | LB | GE | Construction & Maintenance of Bridges along National Roads: Rehabilitation/Reconstruction/Replacement/Retrofitting of Existing Permanent Bridges, Pantar Bridge along Iligan City-Marawi City National Road, Pantar, Lanao del Norte | Pantar, Lanao del Norte | 2015-05-08 | Final | Lanao del Norte First DEO | LF | 24.394 | 330 | 2014-02-12 | 2015-01-07 | - | C | 0.495 | 0.2 | 0.3 | - | - | - | 99.5% | *92.48% Very Satisfactory
R. D. Policarpio & Co. Inc./ TGV Builders, Inc. (JV) | 2011-0361 |  | AAA |  |  | PIDP5-C-THIRISN-1R | Calabanga, Camarines Sur/ Region 5 | 2015-09-11 | 1st | NIA | LF | 87.524 | 700 | 2013-07-25 | 2015-06-25 | -66.18 | O | 0.3409 | 0 | 0 | 0 | 0 | 0.05 | 39.09 | -
R. De Mesa Construction | 18770 | L | C | SB | GE | Const./ Concreting of Roads, Brgy. Camaman-an | Cagayan de Oro City | 2014-10-25 | 1st & Final | X | LF | 4.7002 | 127 | 2014-05-30 | 2014-10-03 | 0% | C | 0.451 | 0.133 | 0.3 | - | - | - | 88.4% | 88.4% Satisfactory
R. DE MESA CONSTRUCTION | 18770 | L | C | SB | GB | Construction of Multi-Purpose Building (Covered Court) at Barangay Poblacion, Maigo, Lanao del Norte | Barangay Poblacion, Maigo, Lanao del Norte | 2015-11-18 | Final | Lanao del Norte 1st | LF | 4.7364 | 95 | 2015-04-28 | 2015-08-01 | 0.00% | C | 0.409 | 0.133 | 0.3 | - | - | - | 84.2% | 84.2% Satisfactory
R. G. Tabin Construction & Supply | [5 empty] | Development of Municipal Plaza as a Tourist Destination | Tayug, Pangasinan | 2016-02-25 | 1st | TIEZA (TOF) | LF | 5 | 161 | 2015-11-10 | 2016-04-18 |  | O | 0.393 | 0.3 | 0.15 | 0.03 | 0.056 | 0.05 | 97.94
R. M. Vitug Construction | 9227 | L | B | MA |  | San Fernando LTO Regional Office Building Project | San Fernando, Pampanga | 2014-05-15 | 3rd & Final | DOTC | LF | 45.279 | 450 | 2013-04-14 | 2014-08-06 | 18 | C | 0.469 | 0.2 | 0.3 | - | - | - | - | 97.40% Outstanding
R. M. Vitug Construction | 9227 | L | B | MA | GB1 | San Fernando LTO Regional Office Building Project | San Fernando, Pampanga | 2013-11-20 | 1st | DOTC | L | 24.864 | 300 | 2013-04-14 | 2014-07-07 | 22.88 | O | 0.366 | 0.3 | 0.15 | 0.03 | 0.07 | 0.05 | 96.6 | -
R. R. Encabo Construction, Inc. |  | L | AAA |  |  | Infrastructure Development of the Jose B. Lingad Memorial Regional Hospital | San Fernando, Pampanga | 2015-02-18 | 1st | DOH | L | 224.815 | 540 | 2014-04-08 | 2015-06-08 | 0 | O | 0.362 | 0.295 | 0.15 | 0.03 | 0.065 | 0.05 | 95.2 | -
R. R. Encabo Construction, Inc. |  |  | AAA |  |  | Infrastructure Development of the Jose B. Lingad Memorial Regional Hospital | San Fernando, Pampanga | 2014-10-15 | 1st | DOH | L | 224.815 | 540 | 2014-04-08 | 2015-10-08 | 0 | O | 0.382 | 0.254 | 0.15 | 0.03 | 0.05 | 0.05 | 91.6 | -
R. R. Encabo Construction, Inc. | 14716 | L | AAA | LA |  | LTFRB Central Office Building and NCR LTFRB Regional Office Building Project | East Avenue, Quezon City | 2015-01-06 | 1st | DOTC | L | 61.269 | 540 | 2013-07-16 | 2015-03-05 | 0.19 | O | 0.393 | 0.3 | 0.15 | 0.015 | 0.056 | 0.017 | 93.1 | -
R. R. Encabo Construction, Inc. |  | L | AAA |  |  | Design and Build of MRH | Margosatubig Zamboanga del Sur, Region IX | 2014-11-21 | 2nd | DOH | L | 149.784 | 520 | 2013-06-20 | 2014-11-14 | -0.934 | O | 0.388 | 0.25 | 0.141 | 0.03 | 0.056 | 0.016 | 88.1 | -
R. R. Encabo Constructors, Inc. | 14716 |  | AAA | LA |  | LTO Administration Building, East Avenue Project | East Avenue, Quezon City | 2016-03-15 | 1st & Final | DOTC | LF | 25.745 | 360 | 2013-03-25 | 2016-02-27 | 0.07 | C | 0.403 | 0.2 | 0.3 | - | - | - | 90.3 | *90.30% V. Satisfactory
R. R. Encabo Constructors, Incorporated | [5 empty] | Procurement of Fully Developed Lots and Complete Housing Units (750 units) | Guadalupe Heights 3, Brgy. San Isidro/ Suhi, Tacloban City | 2016-06-25 | 1st | NHA | LF | 217.389 | 210 | 2015-09-30 | 2016-06-30 | -29.885 | O | 0.3225 | 0.2946 | 0 | 0.03 | 0.0653 | 0.0332 | 74.56 | -
R. R. Encabo Constructors, Incorporated |  |  | AAA |  |  | Design and Build of Infrastructure Project for the Cotabato Regional and Medical Center Modernization | Sinsuat, Cotabato City | 2016-07-22 | 1st | DOH | LF | 348.724 | 807 | 2014-05-19 | 2015-12-21 | 32.3 | O | 0.392 | 0.3 | 0 | 0.01 | 0.06 | 0 | 76.2 | -
R. R. Encabo Contractors, Inc./Espina-Perez-Espina and Associates | 14-02373 |  | AAA |  |  | Design-Built for Infra Proj. for CVMC Hospital Modernization | Carig, Tuguegarao City Cagayan | 2014-10-24 | 1st | DOH | L | 281.638 | 540 | 2014-02-24 | 2015-09-30 | 5.52 | O | 0.392 | 0.278 | 0.15 | 0.03 | 0.064 | 0.033 | 94.7 | -
R. R. RICAFORT CONSTRUCTION & SUPPLY | 14402 | L | A | MA | GE | Construction/Extension of Dike with Protection Works, Ambayaoan River Control Project, Brgy. San Rafael, San Nicolas, Pangasinan | San Nicolas, Pangasinan | 2015-09-04 | 1st | Pangasinan 3rd DEO | LF | 39.323 | 180 | 2015-03-31 | 2015-09-27 | (+)13.44 | C | 0.48 | 0.133 | 0.3 | - | - | - | 91.3% | -
R. R. Ricafort Construction and Supplies | 14402 | L | A |  |  | PIDP/Camiling River Irrigation System | Anoling 3rd, Camiling, Tarlac/ Region 3 | 2014-05-31 | 1st | NIA | LF | 13.882 | 160 | 2013-03-01 | 2014-06-21 | -1.6 | O | 0.3791 | 0.24 | 0.134 | 0.015 | 0.042 | 0.0333 | 84.34 | -
R. R. Ricafort Construction and Supplies | 14402 |  | A |  |  | PIDP/ Camiling River Irrigation System | Poblacion 1, Gerona, Tarlac | 2015-03-31 | Final | NIA | L | 13.882 | 558 | 2013-02-22 | 2015-01-10 | 0 | C | 0.3811 | 0.2 | 0.3 | - | - | - | 88.11 | 85.85% Satisfactory
R. R. Seismundo Construction & Supply | 10961 |  | A |  |  | Design & Build for Construction of new OPD Bldg (1st 7 2nd Floor) Medical Records Slope Protection | Tandag, Surigao del Sur | 2016-07-21 | 2nd | DOH | LF | 59.98 | 420 | 2013-02-08 | 2016-08-26 | -2.81 | O | 0.468 | 0.195 | 0.3 | - | - | - | 96.3 | -
R. SEMILLA CONSTRUCTION & MARKETING | 9263 | L | AAA | MA | GE | Rehabilitation of Permanent Bridges Batang Bridge along SDCR | Tago, Surigao del Sur | 2015-08-27 | 1st & Final | Surigao del Sur 1st | LF | 5.516 | 123 | 2015-03-11 | 2015-07-11 | 0% | C | 0.454 | 0.171 | 0.3 | - | - | - | 92.5% | *92.5% Very Satisfactory
R. Semilla Construction and Marketing | 9263 | L | A | SB | GE | Construction of Nasipit River Protection | Tarragona, Davao Oriental | 2014-10-28 | 1st & Final | XI | LF | 4.7293 | 88 | 2014-02-16 | 2014-05-14 |  | C | 0.357 | 0.2 | 0.3 | - | - | - | 85.7% | 85.7% Satisfactory
R. Semilla Construction and Marketing | 9263 | L | A | SB | GE | Construction of Nasipit River Protection, Tarragona, Davao Oriental | Davao Oriental | 2014-08-13 | 1st & Final | XI | LF | 4.7293 | 88 | 2014-02-16 | 2014-05-14 | 11.32 | C | 0.409 | 0.133 | 0.3 |  |  |  | 84.2 | 84.20% Satisfactory
R. SEMILLA CONSTRUCTION AND MARKETING | 9263 | L | AAA | MA | GE | Construction of Revetment Masao Flood Control | Baganga, Davao Oriental | 2015-06-06 | 1st | Davao Oriental 1st | LF | 8.25 | 115 | 2015-02-16 | 2015-06-10 | -4.56% | O | 0.351 | 0.3 | 0.104 | 0.03 | 0.056 | 0.017 | 85.8% | -
R. SEMILLA CONSTRUCTION AND MARKETING | 9263 | L | A | MA | GE | Completion of Multi-Purpose Building (Gym) | Poblacion, Montevista, Comval Province | 2015-06-09 | Final | Compostela Valley | LF | 2.93 | 30 | 2015-04-24 | 2015-05-23 | 0% | C | 0.463 | 0.086 | 0.3 | - | - | - | 84.9% | *84.9% Satisfactory
R. SEMILLA CONSTRUCTION AND MARKETING | 9263 | L | A | SB | GE | Rehabilitation/Major Repair of Permanent Bridge, Manuangan Bridge along Davao-Cotabato Road | Manuangan, Pigcawayan, Cotabato | 2015-06-06 | Final | Cotabato 2nd DEO | LF | 2.088 | 64 | 2014-03-04 | 2014-05-07 | 0% | C | 0.499 | 0.133 | 0.3 | - | - | - | 93.2% | *93.2% Very Satisfactory
R. SEMILLA CONSTRUCTION AND MARKETING | 9263 | L | AAA | MA | GB | Construction of One Storey Two Classroom School Building Tarusan Integrated Sceondary School, Hinatuan, Surigao del Sur | Hinatuan, Surigao del Sur | 2015-11-13 | 1st | Surigao del Sur 2nd DEO | LF | 1.7931 | 115 | 2015-08-03 | 2015-11-25 | (+) 0.75 | OG | 0.205 | 0.271 | 0.15 | 0.03 | 0.058 | 0.05 | 76.4% | 76.4% Unsatisfactory
R. T. Y. CONSTRUCTION | 10341 | L | B | MA | GE | Widening of National Roads, Daang Maharlika (S05868LZ) K0134+660 - K0135+860, K0135+880 - K0137+000, Pagbilao Quezon | Pagbilao, Quezon | 2015-11-17 | 1st | QUEZON 4TH DEO | LF | 44.433 | 240 | 2015-07-07 | 2016-03-02 | 0.0472 | OG | 0.38 | 0.207 | 0.15 | 0.023 | 0.043 | 0.05 | 85.3% | 85.3% Satisfactory
R. V. LABORTE BUILDERS | 20459 | L | A | MB | GE | Widening of National Roads, Arterial Roads along National Road (NI) Daang Maharlika/Asian Highway - 26, Daang Maharlika (LZ), K0109+636 - K0110+626, Candelaria Section, Candelaria, Quezon | Candelaria, Quezon | 2015-11-16 | 1st | QUEZON 2ND DEO | LF | 43.3665 | 300 | 2015-01-23 | 2015-11-18 | 0.0633 | OG | 0.319 | 0.24 | 0.15 | 0.03 | 0.06 | 0.05 | 84.9% | 84.9% Satisfactory
R.A Del Rosario Construction | 4636 | L | A | MB | GB1 | Const. of MPB, Brgy. San Agustin III |  | 2008-11-10 | 1st | IV-A |  | 4.778 | 90 |  |  |  | O | 0.322 | 0.231 | 0.1 | 0.015 | 0.029 | 0.1 | 79.7 | -
R.A Del Rosario Construction | 4636 | L | A | MA | GE1 | Rehab./Reconst. (Concreting) of Indang-Alfonso via Luksuhin Rd. |  | 2008-11-13 | 1st | IV-A |  | 39.525 | 210 |  |  |  | O | 0.325 | 0.3 | 0.1 | 0.02 | 0.028 | 0.1 | 87.3 | -
R.A. Construction & General Merchandise | 33060 | L | B | SB | GB | Const. of DepEd Standard Type School Building on Gil Montilla NHS, Main Sipalay City, Negros Occidental | Main Sipalay City, Negros Occidental | 2014-08-09 | Final | VI | LF | 3.3379 | 85 | 2013-05-24 | 2013-08-16 | 0 | C | 0.42 | 0.2 | 0.3 |  |  |  | 92 | 86.05% Satisfactory
R.A. Construction & General Merchandise | 33060 | L | B | SB | GB1 | Const. of DepEd Standard Type Sch. Bldg. @ Gil Montilla NHS Main, Sipalay City | Sipalay City, Negros Occidental | 2013-08-09 | 1st | VI | LF | 3.338 | 90 | 2013-05-24 | 2013-08-21 | 12.93 | O | 0.339 | 0.24 | 0.15 | 0.03 | 0.043 | 0.033 | 83.5
R.A. Construction & General Merchandise | 33060 | L | B | MA | GE1 | Rd. Upgrading of Isabela-Libas Negros Occidental Bdry. Rd., a) K0086+250-K0087+000 | Isabela, Negros Occidental | 2013-08-10 | 2nd | VI | LF | 18.023 | 157 | 2013-01-28 | 2013-07-03 | - | O | 0.38 | 0.202 | 0 | 0.03 | 0.037 | 0.033 | 68.2
R.A. Construction & General Merchandise | 33060 | L | B | MA | GE1 | Rd. Upgrading of Isabela-Libas-Negros Occidental Bdry. Rd., a)K0086+250-K0087+000 | Isabela, Negros Occidental | 2013-03-12 | 1st | VI | LF | 18.023 | 157 | 2013-01-28 | 2013-07-03 | 31.24 | O | 0.322 | 0.3 | 0.15 | 0.015 | 0.03 | 0.05 | 86.7 | -
R.A. Lacanlale Construction | 32661 | L | D | SB | GB | Abatan River Eco-Tourism Development Project | Abatan River, Bohol | 2014-04-29 | 1st | TIEZA | LF | 4.29 | 160 | 2013-11-15 | 2014-04-23 | 0 | S | 0.36 | 0.289 | 0.15 | 0.015 | 0.018 | 0.05 | 88.2
R.A. Lacanlale Construction |  | L |  |  |  | Abatan River Eco-Tourism Development Project | Abatan River (Cortes, Balilihan and Maribojoc) Bohol | 2014-04-30 | 1st | TIEZA | LF | 4.29 | 160 | 2013-11-15 | 2014-04-23 | 0 | O | 0.36 | 0.289 | 0.15 | 0.015 | 0.018 | 0.05 | 88.2 | -
R.A. MATIAS CONSTRUCTION AND DEVELOPERS | 26346 | L | B | MA | GE | Construction/Extension of Bank Protection Works Agno River Basin Flood Constrol Project (Phase III) Brgy. Sta. Rosa-Callitang, Sta. Maria, Pangasinan | Sta. Maria, Pangasinan | 2015-11-16 | 1st | PANGASINAN 3RD DEO | LF | 9.1688 | 120 | 2015-08-28 | 2015-12-25 | 0.0344 | OG | 0.385 | 0.239 | 0.15 | 0.03 | 0.05 | 0.05 | 90.4% | 90.4% Very Satisfactory
R.A. Moya Construction Corporation | 10097 | L | A | MA | GB1 | Const. of 3-Storey MPB, C.P. Garcia Ave., Brgy. U.P. Campus, District 4 | Quezon City | 2013-03-19 | 1st | NCR | LF | 9.483 | 210 | 2013-01-14 | 2013-08-11 | 0.02 | O | 0.364 | 0.3 | 0.15 | 0.022 | 0.041 | 0.033 | 91 | -
R.A. Pahati Const. & Supply, Inc. | 35843 | L | A | MA | GE | Rehabilitation/ Reconstruction/Upgrading of Damaged Paved National along San Juan-San Gabriel Road, K0282+000 to K0282+980 | La Union | 2014-10-25 | 1st & Final | I | LF | 15.2828 | 150 | 2014-02-12 | 2014-07-11 | 0% | C | 0.35 | 0.2 | 0.3 | - | - | - | 85% | 85% Satisfactory
R.A. Pahati Const. & Supply, Inc. | 35843 | L | A | MA | GE | Construction of Retaining Wall (Slope Protection) at Nangka River (San Mateo Side), Barangay Sto. Niño, Sta. 3+150 to Sta. 3+650, San Mateo, Rizal | San Mateo, Rizal | 2014-11-27 | 2nd | IV | LF | 3.0642 | 180 | 2014-05-19 | 2014-11-14 | 0% | C | 0.449 | 0.2 | 0.3 | - | - | - | 94.9% | 94.54% Very Satisfactory
R.A. Pahati Const. & Supply, Inc. | 35843 | L | A | MB | GE1 | Widening/Impv't. of Sumulong Highway | Antipolo City | 2013-08-15 | Final | IVA | LF | 17.14 | 210 | 2013-01-29 | 2013-08-26 | 7.79 | C | 0.437 | 0.133 | 0.3 | - | - | - | 87 | 87.12% Satisfactory
R.A. Pahati Const. & Supply, Inc. | 35843 | L | A | MB | GE1 | Widening/Impv't. of Sumulong Highway | Antipolo City | 2013-03-22 | 1st | IVA | LF | 17.14 | 180 | 2013-01-29 | 2013-07-27 | 7.04 | O | 0.346 | 0.24 | 0.15 | 0.03 | 0.056 | 0.05 | 87.2 | -
R.A. PAHATI CONST. & SUPPLY, INC. | 35843 | L | A | MA | GE | MF02- Flood Management Services - Construction/Maintenance of Flood Control Structures and Drainage Systems, Construction of Retaining Wall of Nangka River, Sta. 2+870 to Sta. 3+150 and Sta. 3+650 to Sta. 3+850, Brgy. Sto. Niño | San Mateo, Rizal | 2015-06-01 | 1st | Rizal 2nd DEO | LF | 35.246 | 190 | 2015-03-10 | 2015-09-15 | 45.71% | O | 0.343 | 0.3 | 0.15 | 0.03 | 0.045 | 0.033 | 90.1% | -
R.A. PAHATI CONST. & SUPPLY, INC. | 35843 | L | A | MA | GE | MFO 2 - Flood Management Services, Construction/Maintenance of Flood Mitigation Structures and Drainage Systems, Construction of Retaining Wall of Nangka River, Sta. 2+870 - Sta. 3+150 & Sta. 3+650 - Sta. 3+850, Brgy. Sto. Niňo | San Mateo, Rizal 2nd LD | 2015-08-25 | 1st & Final | Rizal 2nd | LF | 35.246 | 190 | 2015-03-10 | 2015-09-15 | 32.64% | C | 0.426 | 0.133 | 0.3 | - | - | - | 85.9% | *85.9% Satisfactory
R.A. PAHATI CONST. & SUPPLY, INC. | 35843 | L | A | MB | GE | Construction/Improvement of Bacaca Circumferential Road including Davao Medical Foundation Road Leading to Davao City International Airport, Davao City | Davao City | 2015-08-30 | 1st | Regional Office No. XI | LF | 55.534 | 200 | 2015-03-31 | 2015-10-16 | 1% | O | 0.378 | 0.2 | 0.15 | 0.03 | 0.059 | 0.05 | 86.7% | -
R.A. PAHATI CONST. & SUPPLY, INC./811 TRADING & CONSTRUCTION JOINT VENTURE | JV-14-557 | L | A | MA | GE | Construction of Madugo River Control | Brgy. San Mariano, Roxas, Oriental Mindoro | 2015-06-11 | 1st | Southern Mindoro DEO | LF | 14.112 | 160 | 2015-02-18 | 2015-07-27 | 0% | O | 0.388 | 0.237 | 0.15 | 0.03 | 0.042 | 0.05 | 89.7% | -
R.A. Pahati Construction and Supply Inc. | 35843 | L |  |  |  | Rehabilitation and Development of Estero De Valencia | Estero De Valencia, City of Manila | 2014-03-04 | Final | PRRC | LF | 23.255 | 433 | 11/16/11 | 01/22/14 | 1.31 | C | 0.411 | 0.2 | 0.3 | - | - | - | 91.1 | 89.80% Very Satisfactory
R.A. Pahati Construction and Supply Inc. | 35843 | L |  |  |  | Rehabilitation and Development of Estero De Valencia | Estero De Valencia, City of Manila | 01/24/14 | 1st | PRRC | LF | 23.255 | 433 | 11/16/11 | 01/22/14 | 1.31 | O | 0.362 | 0.3 | 0.101 | 0.02 | 0.057 | 0.05 | 89 | -
R.A. PAHATI CONSTRUCTION AND SUPPLY INC. | 35843 | L | A | MB | GE | Road Improvement Brgy. Cristo, Quezon City | Quezon City | 2015-06-02 | 1st | Quezon City 1st DEO | LF | 4.752 | 120 | 2015-03-05 | 2015-07-02 | (+) 15.72 | O | 0.395 | 0.24 | 0.15 | 0.015 | 0.042 | 0.033 | 87.5% | -
R.A. PAHATI CONSTRUCTION AND SUPPLY INC. | 35843 | L | A | SB | GB | Construction of Multi-Purpose Building at NIA Village, Brgy. Sauyo, Quezon City | Brgy. Sauyo, Quezon City | 2015-08-25 | 1st & Final | QC 1st DEO | LF | 2.85 | 90 | 2015-03-02 | 2015-05-30 | 4.44% | C | 0.499 | 0.133 | 0.3 | - | - | - | 93.2% | *93.2% Very Satisfactory
R.A. Pahati Construction and Supply, INC. | 35843 | L | A | MB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads along San Juan-San Gabriel Road @ K0282+000 - K0282+980 | Bambanay-Nadsaag, San Juan, La Union | 2014-08-04 | 1st | I | LF | 15.2828 | 150 | 2014-02-12 | 2014-07-11 | 0 | O | 0.313 | 0.291 | 0.15 | 0.022 | 0.031 | 0.05 | 85.7
R.A. Pahati Construction and Supply, Inc. | 35843 | L | A | MA | GE | Construction of Retaining Wall (Slope Protection) at Nangka River (San Mateo Side), Brgy. Sto. Niño, Sta. 3+150 to Sta. 3+650, San Mateo Rizal | San Mateo, Rizal | 2014-08-04 | 1st | IV-A | LF | 43.2756 | 180 | 2014-05-19 | 2014-11-14 | 26.83 | O | 0.383 | 0.3 | 0.15 | 0.03 | 0.047 | 0.033 | 94.3
R.A. Pahati Construction and Supply, INC. | 35843 | L | A | MB | GE | Widening of National Roads, Daang Maharlika Road, KO85+000 - KO85+500 and KO089+094 - KO090+557.86 | Gapan City, Nueva Ecija | 2014-09-26 | 1st & Final | Special 3 | LF | 25.4568 | 120 | 2014-04-01 | 2014-07-29 | 2.21 | C | 0.332 | 0.2 | 0.3 |  |  |  | 83.2 | 83.20% Satisfactory
R.A. Pahati Gravel and Sand | 22495 | L | A | MA | GE1 | Rehab./Restoration of Road & Bridges along Various Road Sect. in Aurora under POPSTIRP, Roads and Bridges Component, Cluster No. RB17 | Aurora | 2012-03-23 | 1st | BOM / III | FA | 52.799 | 360 | 2011-05-09 | 2012-04-12 | 0.31 | O | 0.351 | 0.3 | 0.15 | 0.03 | 0.035 | 0.033 | 89.9 | -
R.A.M Builders | 10549 | L | B | MA | GE1 | Rehab./Reconst. of MSR-Diversion Road |  | 2009-05-26 | 1st | IV-A |  | 27.964 | 114 |  |  |  | O | 0.352 | 0.24 | 0.15 | 0.03 | 0.025 | 0.05 | 84.7 | -
R.A.M Builders | 10549 | L | B | MA | GE1 | Const. (Road Opening) of Quezon Eco-Tourism Road (LUCBATCR) inc. RROW, Phase II, Brgy. Bignay II, Maggalang Kiling |  | 2009-05-25 | 1st | IV-A |  | 17.689 | 114 |  |  |  | O | 0.343 | 0.24 | 0.15 | 0.03 | 0.025 | 0.05 | 83.8 | -
R.A.M Builders | 10549 | L | B | MA | GE1 | Const. of Quezon Eco-Tourism Road (LUC-BAT CR) incl. RROW: Phase I, Guisguis-Talaan Sect., Conc. Of Guisguis Section |  | 2008-11-18 | 1st | IV-A |  | 17.78 | 206 |  |  |  | O | 0.337 | 0.3 | 0.1 | 0.03 | 0.037 | 0.1 | 90.4 | -
R.A.M Builders | 10549 | L | B | MA | GE | Construction of Lucena-Diversion Talao-Talao Port Road, including RROW, Concreting of Silangang Mayao Road Section including Slope Protection | Lucena City, Quezon | 2014-11-28 | 1st | IV | LF | 43.9899 | 299 | 2014-05-05 | 2015-02-27 | 0.13% | O | 0.383 | 0.246 | 0.15 | 0.03 | 0.04 | 0.033 | 88.2% | 88.2% Satisfactory
R.A.M Builders | 10549 | L | B | MA | GE | Asset Preservation of National Roads-Preventive Maintenance based on Pavement Management System-4 (HDM-4), (Intermittent Sections), National Arterial Roads 3. Gumaca-Pitogo-Mulanay-San Narciso Rd., K0202+200-K0206+537 | Gumaca, Quezon | 2014-11-28 | 1st | IV | LF | 18.2069 | 120 | 2014-09-01 | 2014-12-29 | 15.84% | O | 0.365 | 0.203 | 0.15 | 0.03 | 0.045 | 0.033 | 82.6% | 82.6% Satisfactory
R.A.M Builders | 10549 | L | B | MA | GE1 | Const. of Slope Protection incl. RROW along Quezon Eco-Tourism Rd. (LUC-BATCR) at Bantilan-Guis-Guis Sect. | Sariaya, Quezon | 2013-03-16 | Final | IVA | LF | 29.775 | 294 | 2012-04-11 | 2013-01-29 | 1.51 | C | 0.434 | 0.133 | 0.3 | - | - | - | 86.7 | 87.18% Satisfactory
R.A.M. BUILDERS | 10549 | L | B | MA | GE | Widening of National Roads, Arterial Roads along National Road 1 (N1), Daang Maharlika/Asia Highway-26, K0102+694 to K0103+608, Candelaria Section | Candelaria, Quezon | 2015-06-09 | 1st | Quezon 2nd DEO | LF | 43.855 | 300 | 2015-01-28 | 2015-11-23 | 0.37% | O | 0.371 | 0.24 | 0.15 | 0.03 | 0.04 | 0.033 | 86.4% | -
R.A.M. BUILDERS | 10549 | L | B | MA | GE | MFO 2- Flood Management Services Construction/Maintenance of Flood Mitigation Structures and Drainage Systems Construction/Rehabilitation of Flood Control Stuctures, Daang Maharlika (LZ), Pagbilao, Quezon Section | Pagbilao, Quezon | 2015-06-11 | 1st | Quezon 4th DEO | LF | 18.235 | 150 | 2015-03-16 | 2015-08-12 | 1% | O | 0.334 | 0.242 | 0.15 | 0.03 | 0.05 | 0.05 | 85.6% | -
R.A.M. BUILDERS | 10549 | L | B | MA | GE | Widening of National Roads, Arterial Roads along National Road I (NI) Daang Maharlika/Asian Highway-26 Daang Maharlika (LZ), K0 102+694 - K0 103+608, Candelaria Section | Candelaria, Quezon | 2015-09-02 | 1st | Quezon 2nd | LF | 43.855 | 300 | 2015-01-28 | 2015-11-23 | 4.69% | O | 0.382 | 0.24 | 0.15 | 0.03 | 0.03 | 0.05 | 88.2% | -
R.A.M. Builders / BC Villaseñor Construction (JV) | JV-11-206 | L | B | MA | GE1 | Road Upgrading (Gravel to Concrete) Nat'l Secondary Rd., MSR JCT. Lopez-Buenavista Road, K0221+636-K0222+138 | Lopez, Quezon | 2012-03-15 | 1st | IVA | LF | 5.197 | 120 | 2012-02-13 | 2012-06-11 | 4.17 | O | 0.372 | 0.24 | 0.15 | 0.03 | 0.041 | 0.05 | 88.3 | -
R.A.M. Builders/L.S. Abelar Construction JV | JV-08-229 | L | B | MA | GE1 | Impvt. of Quirino-Andaya Highway, Quezon Side, Brgy. Silang II-Sto. Niño-San Diego |  | 2009-05-28 | 1st | IV-A |  | 33.765 | 90 |  |  |  | O | 0.333 | 0.24 | 0.15 | 0.03 | 0.035 | 0.05 | 83.8 | -
R.B. CANDARE CONSTRUCTION | 8819 | L | B | SB |  | LMC-2013-ANDANAN-WAWA-RIS | Bayugan City, Agusan del Sur | 2014-06-07 | 1st | NIA | LF | 11.95 | 150 | 2013-06-11 | Suspended | 0 | O | 0.37 | 0.19 | 0.15 | 0.018 | 0.051 | 0.017 | 79.6 | -
R.C Tagala Construction | 11597 | L | A | MB | GE1 | Road Upgrading (gravel to paved) Conc. of MOOECR (Calawag-Caguray Br. And Talaba Section) KO 219+141- KO 221+141 to KO 224+456 - KO 224+740 |  | 2009-09-01 | 1st | IVB |  | 19.3 | 176 |  |  |  | O | 0.341 | 0.3 | 0.129 | 0.03 | 0.051 | 0.033 | 88.4 | -
R.C Tagala Construction | 11597 | L | A | MB | GE1 | Road Upgrading (gravel to paved) Conc. of MOOECR KO 210+760 - KO 212+248 |  | 2009-08-30 | 1st | IVB |  | 33.688 | 219 |  |  |  | O | 0.341 | 0.3 | 0.129 | 0.03 | 0.051 | 0.033 | 88.4 | -
R.C Tagala Construction | 11597 | L | A | MB | GE1 | Road Upgrading (gravel to paved) MWCR, Sta. Cruz-Mamburao (Mulawin-San Vicente Section) KO 383+519-KO 385+002.5 |  | 2009-08-31 | 2nd | IVB |  | 19.26 | 186 |  |  |  | O | 0.357 | 0.298 | 0.15 | 0.022 | 0.023 | 0.033 | 88.3 | -
R.C Tagala Construction | 11597 | L | A | MB | GE1 | Road Upgrading (Gravel to Paved) MWCR, Sta. Cruz-Mamburao (Mulawin-San Vicente Section) |  | 2009-05-30 | 1st | IV-B |  | 19.205 | 140 |  |  |  | O | 0.331 | 0.239 | 0.123 | 0.03 | 0.03 | 0.05 | 80.3 | -
R.C Tagala Construction | 11597 | L | A | MB | GE1 | Const./Completion of Macagua Bridge along Brookes Point-Rio Tuba Road |  | 2009-09-09 | 2nd | IVB |  | 17.95 | 180 |  |  |  | O | 0.355 | 0.283 | 0.15 | 0.03 | 0.028 | 0.033 | 87.9 | -
R.C Tagala Construction | 11597 | L | A | MB | GE1 | Const./Completion of Macagua Bridge aling Brooke's Point-Rio Tuba Road |  | 2009-06-02 | 1st | IV-B |  | 17.95 | 180 |  |  |  | O | 0.337 | 0.222 | 0.15 | 0.023 | 0.02 | 0.05 | 80.2 | -
R.C Tagala Construction | 11597 | L | A | MB | GE1 | Rehab./Reconst./Upgrading of Dumaguete North Rd., Tapon Norte-Tandayag Rd. Sect. |  | 2009-09-12 | 1st | VII |  | 28.787 | 200 |  |  |  | O | 0.377 | 0.24 | 0.15 | 0.03 | 0.037 | 0.033 | 86.7 | -
R.C Tagala Construction | 11597 | L | A | MB | GE1 | Rehab./Reconst./Upgrading of Dumaguete North Rd.,CAB-Sta. Cruz Sec. |  | 2009-09-12 | 1st | VII |  | 28.796 | 200 |  |  |  | O | 0.35 | 0.24 | 0.15 | 0.03 | 0.037 | 0.033 | 84 | -
R.C Tagala Construction | 11597 | L | A | MB | GE1 | Repair/Rehab. of Dumaguete North Road, Km. 15.090-Km. 17.0775 |  | 2009-05-26 | 1st | VII |  | 20.194 | 105 |  |  |  | O | 0.361 | 0.24 | 0 | 0.03 | 0.051 | 0.033 | 71.5 | -
R.C. TAGALA CONSTRUCTION | 11597 | L | A | MB | GE | Widening of Permanent Bridges from 1 Lane to 2 Lanes Malinao Bridge, Narra, Palawan | Narra, Palawan | 2015-08-27 | 1st | Palawan II DEO | LF | 14.591 | 160 | 2015-06-15 | 2015-11-21 | 1% | O | 0.384 | 0.252 | 0.15 | 0.015 | 0.028 | 0.05 | 87.9% | -
R.C. TAGALA CONSTRUCTION | 11597 | L | A | MB | GE | Rehabilitation/Major Repair of Sta. Cruz Br. (B00005MQ) along Marinduque Circumferential Road, Sta. Cruz, Marinduque | Sta. Cruz, Marinduque | 2015-09-01 | 1st & Final | Marinduque DEO | LF | 11.8 | 124 | 2015-02-23 | 2015-06-26 | - | C | 0.491 | 0.133 | 0.3 | - | - | - | 92.4% | *92.4% Very Satisfactory
R.C. Tagala Const./ITP Const. Inc. (JV) | JV-11-333 | L | AAA | LA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rd., Puerto Princesa South Rd. (Caramay-Aplian-Calasageun Sect.) (K0164+024-K0168+587.25 w/ exceptions) | Española, Palawan | 2012-11-20 | 2nd | IVB | LF | 93.914 | 347 | 2012-03-20 | 2013-03-01 | -4.36 | O | 0.357 | 0.272 | 0.106 | 0.03 | 0.056 | 0.033 | 85.4 | -
R.C. Tagala Const./ITP Const. Inc. (JV) | JV-11-333 | L | AAA | LA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rd. Puerto Princesa South Rd. (Caramay-Apilan-Calasaguen Sect.) K0+165+024-K0168+587.25 w/ exceptions) | Española, Palawan | 2012-08-01 | 1st | IVB | LF | 92.156 | 330 | 2012-03-20 | 2013-02-12 | -9.45 | O | 0.392 | 0.284 | 0.056 | 0.03 | 0.045 | 0.017 | 82.4 | -
R.C. Tagala Construction | 11597 | L | A | MA | GE | Rehabilitation/Strengthening of Babuyan Bridge PPNR | Puerto Princesa City | 2014-08-08 | Final | IV-B | LF | 12.0156 | 255 | 2013-02-06 | 2013-10-18 | 0 | C | 0.397 | 0.133 | 0.3 |  |  |  | 83 | 84.74% Satisfactory
R.C. Tagala Construction | 11597 | L | A | MA | GE1 | Rehab./Strengthening of Babuyan Bridge PPNR | Puerto Princesa City | 2013-08-15 | 1st | IVB | LF | 11.72 | 225 | 2013-02-06 | 2013-09-19 | -2.3 | O | 0.376 | 0.248 | 0.127 | 0.03 | 0.045 | 0.033 | 85.9
R.C. Tagala Construction | 11597 | L | A | MA | GE | Upgrading (Gravel to Concrete) Concreting of Luka Road Leading to Tanjay Boardwalk. Tanjay City, Negros Oriental | Tanjay City, Negros Oriental | 2014-08-14 | Final | VII | LF | 14.4643 | 175 | 2013-03-18 | 2013-09-09 | 0 | C | 0.426 | 0.148 | 0.3 |  |  |  | 87.4 | 86.74% Satisfactory
R.C. Tagala Construction | 11597 | L | A | MA | GE1 | Upgrading (Gravel to Concrete) Conc. of Luka Rd. leading to Tanjay Boardwalk | Tanjay City, Negros Oriental | 2013-08-21 | 1st | VII | LF | 13.717 | 175 | 2013-03-18 | 2013-09-08 | 0.57 | O | 0.288 | 0.3 | 0.15 | 0.03 | 0.045 | 0.05 | 86.3
R.C. TAGALA CONSTRUCTION | 11597 | L | A | MA | GE | Construction of Flood Control Structure Tigaplan Flood Control | Brooke's Point, Palawan | 2015-06-04 | 1st | Palawan 2nd DEO | LF | 9.211 | 134 | 2015-03-13 | 2015-07-24 | 0% | O | 0.385 | 0.24 | 0.15 | 0.023 | 0.047 | 0.05 | 89.5% | -
R.C. TAGALA CONSTRUCTION | 11597 | L | A | MB | GE | Concreting Paving/Widening along Manila North Road | KO290+000 - KO292+000, Bacnotan, La Union | 2015-06-06 | 1st | La Union 1st DEO | LF | 18.454 | 214 | 2015-02-11 | 2015-09-12 | -3.88% | O | 0.245 | 0.297 | 0.111 | 0.03 | 0.045 | 0.033 | 76.1% | -
R.C. TAGALA CONSTRUCTION | 11597 | L | A | MB | GE | Rehabilitation/Reconstruction of Damaged Paved National Road including Drainage Based on Pavement Management System/Highway Development and Management-4 (HDM-4) of Kalinga -Cagayan Road (Calanan - Enrile Section), K0522+000 to K0523+015, K0523+655 to K0523+725, K0524+000 to K0524+131, K0524+582 to K0524+810, K0524+893 to K0524+953, K0524+980 to K0525+043, K0525+052 to K0525+087, Rizal, Kalinga | Rizal, Kalinga | 2015-08-28 | 1st | Kalinga DEO | LF | 21.864 | 157 | 2015-05-23 | 2015-10-26 | 1.65% | O | 0.378 | 0.3 | 0.15 | 0.03 | 0.065 | 0.05 | 97.3% | -
R.C. TAGALA CONSTRUCTION | 11597 | L | A | MB | GE | MFO 1 - National Road Network Services - Asset Preservation of National Roads, Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads including Drainage based on Pavement Management System/Highway Development and Management-4 (HDM-4) (Intermittent Sections), Arterial Roads-Gumaca-Pitogo-Mulanay-San Narciso Road (S04238LZ) | K0 203+257 - K0 206+366, Gumaca, Quezon | 2015-09-03 | 1st | Quezon 4th | LF | 36.066 | 120 | 2015-06-29 | 2015-10-26 | 35.24% | O | 0.342 | 0.24 | 0.15 | 0.03 | 0.042 | 0.05 | 85.4% | -
R.C. TAGALA CONSTRUCTION | 11597 | L | A | MB | GE | Construction/Improvement of Declared Tourism Destination, Bais City Road leading to Dolphin Watching & White Sand Bar | 2nd District, Negros Oriental | 2015-08-24 | 1st | Negros Oriental 2nd | LF | 16.6 | 121 | 2015-04-22 | 2015-08-20 | ##### | O | 0.334 | 0.227 | 0 | 0.022 | 0.025 | 0 | 60.8% | -
R.C. TAGALA CONSTRUCTION | 11597 | L | A | MB | GE | Widening of Permanent Bridge from 1 lane to 2 lanes Malinao Bridge along Puerto Princesa City Road | Narra, Palawan | 2015-11-11 | 2nd | Palawan 2nd Deo | LF | 14.5911 | 215 | 2015-06-15 | 2016-01-15 | 0.0299 | OG | 0.326 | 0.3 | 0.15 | 0.008 | 0.045 | 0.05 | 87.9% | 87.9% Satisfactory
R.C. TAGALA CONSTRUCTION | 11597 | L | A | MB | GE | Rehab./Reconst./Upgrading of Damaged Paved Secondary N/R including Drainage based on PMS/HDM-4 (Intermittent Section) along San Jose-Caminawit Port Road, K0237+(-438) to K0239+709, Road Section ID: S00149MR | San Jose, Occidental Mindoro | 2015-11-17 | 1st | Mindoro Occidental DEO | LF | 45.1707 | 299 | 2015-04-30 | 2016-02-22 | 0.0378 | OG | 0.36 | 0.24 | 0.15 | 0.015 | 0.04 | 0.033 | 83.8% | 83.8% Satisfactory
R.D Interior Junior Construction | 6483 | L | AAA | LB | GE1 | Upgrading/Improvement of Magapit-Mission Road |  | 2009-09-09 | 2nd | II |  | 96.491 | 330 |  |  |  | O | 0.36 | 0.3 | 0.15 | 0.03 | 0.042 | 0.05 | 93.2 | -
R.D Interior Junior Construction | 6483 | L | AAA | LB | GE1 | Upgrading/Improvement of Magapit-Mission Road, Lal-lo and Sta. Teresita |  | 2009-05-19 | 1st | II |  | 96.491 | 330 |  |  |  | O | 0.385 | 0.24 | 0.15 | 0.03 | 0.056 | 0.05 | 91.1 | -
R.D Interior Junior Construction | 6483 | L | AAA | LB | GE1 | Improvement of Access Road, Bagabag Airport |  | 2009-06-01 | 1st | II |  | 35.416 | 74 |  |  |  | O | 0.375 | 0.24 | 0.15 | 0.03 | 0.056 | 0.05 | 90.1 | -
R.D Interior Junior Construction | 6483 |  |  |  |  | Road Upgrading (Gravel to Paved) of Lala-Salvador-Tubod Road |  | 2010-06-03 |  | X |  | 19.138 | 121 |  |  |  | O | 0.363 | 0.24 | 0.15 | 0.03 | 0.045 | 0.033 | 86.1 | -
R.D Interior Junior Construction | 6483 | L | AAA | LB | GE1 | Conc. of SDCR, Marihatag-Hinatuan-Bislig Section, (Tagbina-Hinatuan Subsection) |  | 2008-11-27 | 1st | XIII |  | 282.908 | 345 |  |  |  | O | 0.331 | 0.3 | 0.1 | 0.03 | 0.05 | 0.1 | 91.1 | -
R.D Interior Junior Construction | 6483 | L | AAA | LB | GE1 | Impvt./Conc. of Bislig-Manay Road (Boston-Bislig Sect. with Monkag & San Vicente Bridge) |  | 2008-11-27 | 5th | XIII |  | 289.168 | 570 |  |  |  | O | 0.342 | 0.3 | 0.1 | 0.03 | 0.055 | 0.1 | 92.7 | -
R.D Interior Junior Construction | 6483 | L | AAA | LB | GE1 | Impvt./Conc. of Bislig-Manay Road (Boston-Bislig Section with Monkag & San Vicente Bridge) |  | 2009-06-06 | 7th | XIII |  | 289.168 | 570 |  |  |  | O | 0.374 | 0.3 | 0.106 | 0.03 | 0.056 | 0.05 | 91.6 | -
R.D Interior Junior Construction | 6483 | L | AAA | LB | GE1 | Impvt./Conc. of Bislig-Manay Road (Boston-Bislig Sect. with Monkag & San Vicente Bridge) |  | 2009-03-14 | 6th | XIII |  | 289.168 | 570 |  |  |  | O | 0.37 | 0.3 | 0.106 | 0.03 | 0.061 | 0.033 | #VALUE! | -
R.D Interior Junior Construction | 6483 | L | AAA | LB | GE1 | Conc. of Surigao-Davao Coastal Rd./ Hinatuan-Bislig-Lingig Subsection, w/ 2 Bridges & 1 RCBC |  | 2009-09-10 | 1st | XIII |  | 259.76 | 420 |  |  |  | O | 0.388 | 0.3 | 0.083 | 0.03 | 0.06 | 0.033 | 89.4 | -
R.D Interior Junior Construction | 6483 | L | AAA | LB | GE1 | Conc. of Surigao-Davao Coastal Rd., Marihatag-Hinatuan-Bislig Sect.,(Tagbina-Hinatuan Subsection) |  | 2009-09-18 | 3rd | XIII |  | 232.908 | 375 |  |  |  | O | 0.371 | 0.3 | 0.027 | 0.03 | 0.06 | 0.033 | 82.1 | -
R.D Interior Junior Construction | 6483 | L | AAA | LB | GE1 | Concreting of Surigao-Davao Coastal Road, Marihatag-Hinatuan Bislig Section (Tagbina-Hinatuan Subsection) |  | 2009-06-06 | 2nd | XIII |  | 232.908 | 345 |  |  |  | O | 0.381 | 0.3 | 0.055 | 0.03 | 0.061 | 0.05 | 87.7 | -
R.D Policarpio Inc. | 4414 | L | AAA | LB | GE1 | Impvt./Widening of McArthur Highway (Manila North Road) Phase V Meycauayan Bulacan) to Mabalacat (Pampanga), (City of San Fernando Section Contract Package II) |  | 2009-08-28 | 1st | III |  | 48.066 | 160 |  |  |  | O | 0.354 | 0.3 | 0.15 | 0.03 | 0.05 | 0.05 | 93.4 | -
R.D Policarpio Inc. | 4414 | L | AAA | LB | GE1 | Impv./Widening/Conc. of MNR-Phase V-Meycuayan, Bulacan to Mabalacat, Pampanga-Replacement of Del Pilar Bridge and Approaches |  | 2009-08-28 | 1st | III |  | 68.686 | 210 |  |  |  | O | 0.362 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 88.2 | -
R.D Policarpio Inc. | 4414 | L | AAA | LB | GE1 | Impvt. (Widening/Conc. of McArthur Highway (MNR) Meycauayan (Bulacan) to Mabalacat (Pampanga) Ph-IV Package VII, Replacement of Tinajero Bridge & App. |  | 2008-11-11 | 1st | III |  | 45.805 | 180 |  |  |  | O | 0.373 | 0.24 | 0.1 | 0.03 | 0.061 | 0.1 | 90.4 | -
R.D Policarpio Inc. | 4414 | L | AAA | LB | GE1 | CP 6: Impvt./Conc. of Surigao Sur-Davao Oriental Coastal Road (Manay-Boston) Baganga Section Phase I |  | 2008-11-25 | 1st | XI |  | 157.077 | 492 |  |  |  | O | 0.339 | 0.24 | 0.1 | 0.03 | 0.055 | 0.1 | 86.4 | -
R.D Policarpio Inc. | 4414 | L | AAA | LB | GE1 | Impvt./Conc. of Surigao Sur-Davao Oriental Coastal Road (Manay-Boston) Baganga Section, Phase I |  | 2009-06-09 | 2nd | XI |  | 157.077 | 492 |  |  |  | O | 0.371 | 0.254 | 0.15 | 0.03 | 0.056 | 0.033 | 89.4 | -
R.D Policarpio Inc. | 4414 | L | AAA | LB | GE1 | Impvt./Conc. of Surigao Sur-Davao Oriental Coastal Road, (Manay-Boston) Baganga Section Phase I, CP No. 6 |  | 2009-09-11 | 3rd | XI |  | 157.076 | 522 |  |  |  | O | 0.365 | 0.3 | 0.15 | 0.03 | 0.056 | 0.033 | 93.4 | -
R.D. Interior Junior Construction | 6483 | L | AAA | LB | GE | Preventive Maintenance Based on Pavement System/Highway Development and Management-4 (HDM-4) (Intermittent Section), Cordon Aurora Boundary Road (Isabela Boundary Jct. Dumabato), KO322+(-360) - KO322+000; KO322+200 - KO323+000; KO341+100 - KO342+000; KO343+680 - KO345+040; KO345+481 - KO346+000; KO346+511 - KO348+326; KO349+038 - KO349+948; KO350+000 - KO531+1013 | Cabarroguis-Aglipay, Quirino | 2014-10-25 | 1st & Final | II | LF | 68.0707 | 150 | 2014-02-14 | 2014-07-13 | 5.29% | C | 0.466 | 0.133 | 0.3 | - | - | - | 89.9% | 89.9% Very Satisfactory
R.D. Interior Junior Construction | 6483 | L | AAA | LB | GE2 | Washed Out Flood Control Proj. (Restoration), San Vicente | Iguig, Cagayan | 2013-03-17 | Final | II | LF | 44.676 | 360 | 2012-01-30 | 2013-01-23 | 0 | C | 0.374 | 0.133 | 0.3 | - | - | - | 80.7 | 88.56% Satisfactory
R.D. Interior Junior Construction | 6483 | L | AAA | LB | GE1 | Const. of Maguiling Bridge along the Chico River | Tuao, Cagayan | 2012-03-15 | 2nd | II | LF | 132.907 | 360 | 2011-04-14 | 2012-04-07 | -7.44 | O | 0.388 | 0.3 | 0.076 | 0.03 | 0.06 | 0.05 | 90.4 | -
R.D. Interior Junior Construction | 6483 | L | AAA | LB | GE1 | Const. of Naguiling Bridge along The Chico River | Tuao, Cagayan | 2011-08-06 | 1st | II | LF | 132.907 | 360 | 2011-04-14 | 2012-04-08 | 19.13 | O | 0.396 | 0.285 | 0.15 | 0.03 | 0.061 | 0.05 | 97.2 | -
R.D. Interior Junior Construction | 6483 | L | AAA | LB | GE1 | Preventive Maint. of Nat'l Rd. (Asphalt Overlay=80mm Thk) Cagayan Valley Rd. K0499+041-K0493+463 w/ exception | Iguig, Cagayan | 2011-08-04 | 1st | II | LF | 18.391 | 90 | 2011-05-27 | 2011-08-24 | 0.2 | O | 0.356 | 0.3 | 0.15 | 0.03 | 0.061 | 0.05 | 94.7 | -
R.D. Interior Junior Construction | 6483 | L | AAA | LB | GE1 | Rehab./Replacement of Lucban Bridge along Manila North Road | Abulug, Cagayan | 2012-03-15 | 2nd | II | LF | 76.195 | 385 | 2011-04-08 | 2012-04-26 | -5.71 | O | 0.381 | 0.286 | 0.093 | 0.03 | 0.05 | 0.033 | 87.3 | -
R.D. Interior Junior Construction | 6483 | L | AAA | LB | GE1 | Rehab./Replacement of Lucban Bridge along Manila North Road | Abulug, Cagayn | 2011-08-03 | 1st | II | LF | 69.268 | 240 | 2011-04-08 | 2011-12-03 | -10.5 | O | 0.374 | 0.281 | 0.045 | 0.03 | 0.061 | 0.033 | 82.4 | -
R.D. Interior Junior Construction | 6483 | L | AAA | LB | GE | Const. of Pantar Bridge along Iligan City-Marawi City Road | Lanao del Norte (1st LD) | 2014-10-29 | 1st | X | LF | 84.6021 | 390 | 2013-04-19 | 2014-05-13 | -3.009% | O | 0.39 | 0.248 | 0.12 | 0.03 | 0.061 | 0.033 | 88.2% | 88.2% Satisfactory
R.D. Interior Junior Construction | 6483 | L | AAA | LB | GE | Repair/ Reconst./ Replacement/ Retrofitting of Existing Permanent Bridge, Pantar Bridge along Iligan City-Marawi City National Road | Pantar, Lanao del Norte | 2014-10-29 | 1st | X | LF | 24.3941 | 225 | 2014-02-12 | 2014-09-24 | 5.84% | O | 0.391 | 0.232 | 0.15 | 0.03 | 0.042 | 0.033 | 87.8% | 87.8% Satisfactory
R.D. Interior Junior Construction | 6483 | L | AAA | LB | GE | Strengthening of Pantar Bridge along Iligan-Marawi City Road | Pantar, Lanao del Norte | 2014-10-29 | 1st | X | LF | 14.1558 | 204 | 2013-12-23 | 2014-07-14 | -3.5% | O | 0.395 | 0.24 | 0.115 | 0.03 | 0.042 | 0.033 | 85.5% | 85.5% Satisfactory
R.D. INTERIOR JUNIOR CONSTRUCTION | 6483 | L | AAA | LB | GE | Replacement of Lisap Bridge along Calapan South Road: Sta. 122+020- Sta. 122+560.00 | Bongabong, Oriental Mindoro | 2015-06-09 | 1st | Regional Office IV-B | LF | 273.822 | 730 | 2014-10-14 | 2016-10-13 | 0% | O | 0.367 | 0.267 | 0.15 | 0.03 | 0.042 | 0.05 | 90.6% | -
R.D. Mandanas Construction | 32114 | L | D | SB | GE | Construction/Rehabilitation of Flood Control in Laguna 2nd DEO/1st LD along Manila South Road at Salang Bago Bridge, Sta. Rosa City | Sta. Rosa City, Laguna | 2014-11-28 | 1st & Final | IV | LF | 13.5992 | 210 | 2014-01-23 | 2014-08-20 | 17.78% | C | 0.367 | 0.2 | 0.3 | - | - | - | 86.7% | 86.7% Satisfactory
R.D. Policarpio & Company, Inc. | 4414 | L | AAA | LB | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rds. (Int. Sect.) Roman Expressway, Km.137+246.10-Km.152+120 | Bataan | 2013-03-23 | 1st | III | LF | 39.768 | 376 | 2012-08-03 | 2013-08-13 | -3.4 | O | 0.38 | 0.3 | 0.116 | 0.03 | 0.06 | 0.033 | 91.9 | -
R.D. POLICARPIO & COMPANY, INC. | 4414 | L | AAA | B | GE | Road Upgrading (Gravel to Paved) of Tigbao-Sta. Fe-San Miguel Road, K0911+224-K0913+000 and K0913+828-K0913+876, Tacloban City | Tacloban City | 2015-11-11 | Final | Regional Office No. VIII | LF | 55.7231 | 290 | 2015-02-05 | 2015-11-21 | (+)4.37 | C | 0.437 | 0.2 | 0.3 | - | - | - | 93.7% | 93.7% Very Satisfactory
R.D. Sadsad Construction and Trading | 19240 | L | A | MA | GB1 | Const. of Multi-Purpose Building at Calulut |  | 2009-08-24 | 1st | III |  | 5.239 | 98 |  |  |  | O | 0.393 | 0.24 | 0.15 | 0.03 | 0.051 | 0.05 | 91.4 | -
R.D. Sadsad Construction and Trading | 19240 | L | A | MA | GE1 | Repair/Rehab., Gapan-San Fernando-Olongapo (GSO) |  | 2008-08-18 | 1st | III |  | 9.653 | 90 |  |  |  | O | 0.348 | 0.2 | 0.1 | 0.03 | 0.058 | 0.1 | 83.6 | -
R.D. Sadsad Construction and Trading | 19240 | L | A | MA | GE | Construction/Rehabilitation of Flood Control in Laguna 2nd DEO/1st LD along Macabling River | Brgy. Aplaya, Sta. Rosa City, Laguna | 2014-11-28 | 1st & Final | IV | LF | 16.4488 | 195 | 2014-01-23 | 2014-08-05 | - | C | 0.459 | 0.2 | 0.3 | - | - | - | 95.9% | 95.9% Very Satisfactory
R.E. Orlina Construction Corporation | 17176 | L | B | MA | GE | Rehabilitation/Drainage Improvement and Concrete Reblocking along C.P. Garcia Avenue | Quezon City | 2014-11-27 | 1st | NCR | LF | 15.5991 | 271 | 2014-08-01 | 2015-04-28 | 0.12% | O | 0.328 | 0.24 | 0.15 | 0.03 | 0.03 | 0.033 | 81.1% | 81.1% Unsatisfactory
R.E. ORLINA CONSTRUCTION CORPORATION | 17176 | L | B | MA | GE | Rehabilitation/Improvement of Amburayan River Control Project, Mindoro | Bangar, La Union | 2015-06-07 | 1st | La Union 1st DEO | LF | 18.618 | 257 | 2015-02-07 | 2015-10-21 | 28% | O | 0.334 | 0.253 | 0.15 | 0.03 | 0.045 | 0.033 | 84.5% | -
R.E.ORLINA CONSTRUCTION CORPORATION | 17176 | L | B | MA | GE | Rehabilitaion/Drainage Improvement and Concrete Reblocking along c.p. Garcia Avenue, Quezon City | Quezon City | 2015-06-03 | Final | Quezon City 2nd DEO | LF | 15.599 | 271 | 2014-08-01 | 2015-04-28 | (+) 2.88 | C | 0.469 | 0.133 | 0.3 | - | - | - | 90.2% | *84.74% Satisfactory
R.F. Varquez Construction | 24307 | L | B | SB | GE1 | Replacement of Mabini Bridge along Dinagat-Loreto Rd. | Tubajon, Dinagat Islands | 2012-08-09 | 1st | XIII | LF | 5.265 | 165 | 30/20/12 | 2012-08-31 | -4.38 | O | 0.342 | 0.279 | 0.106 | 0.03 | 0.055 | 0.033 | 84.5 | -
R.F. Varquez Construction | 24307 | L | B | SB | GE1 | Replacement of Allan Bridge along Dinagat-Loreto Rd. | Tubajon, Dinagat Islands | 2012-08-09 | 1st | XIII | LF | 5.267 | 165 | 2012-03-20 | 2012-08-16 | 0.26 | O | 0.34 | 0.24 | 0.15 | 0.023 | 0.035 | 0.033 | 82.1 | -
R.F. Varquez Construction | 24302 | L | B | MA | GE | Road Upgrading (Gravel to Paved) Jct. Gamut - San Miguel - Bayugan Road (K1321+415.88 to K1321+770.68) | Tago, Surigao del Sur | 2014-10-25 | 1st & Final | XIII | LF | 12.1144 | 159 | 2014-03-18 | 2014-08-23 | 1% | C | 0.417 | 0.154 | 0.3 | - | - | - | 87.1% | 87.1% Satisfactory
R.F. Varquez Construction | 24302 | L | B | MA | GE | Road Upgrading (Gravel to Paved) Jct. Gamut - San Miguel - Bayugan Road, K1321+415.88 - K1321+770.68 | Tago, Surigao del Sur | 2014-08-11 | 1st | XIII | LF | 12.1144 | 159 | 2014-03-18 | 2014-08-23 | 26.84 | O | 0.381 | 0.225 | 0.15 | 0.022 | 0.033 | 0.05 | 86.1
R.G Erillo Construction Incorporated (Formerly: R.G. Erillo Construction & Supply) | 932 |  | A | MB | GE1 | Rehab./Reconst./Upgrading of Bacolod Circumferential Road Km. 11+552 (South) to Km. 4+567 (North) w/ exceptions |  | 2009-09-12 | 1st | VI |  | 14.466 | 250 |  |  |  | O | 0.298 | 0.3 | 0.15 | 0.03 | 0.04 | 0.05 | 86.8 | -
R.G. Dela Cruz Construction | 35498 | L | B | MA | GE | Construction of Road, Brgy. Poblacion Sur | Licab, Nueva Ecija | 2014-09-24 | 1st & Final | Special 3 | LF | 4.9857 | 98 | 2014-06-03 | 2014-09-08 | -0.12 | C | 0.336 | 0.192 | 0.3 |  |  |  | 82.8 | 82.80% Satisfactory
R.G. Diaz Builders & Trading | 23814 | L | B | SB | GE | Widening/Improvement of Camp Dau Road including Drainage System along Camp Dau Road, K0088+(-212) to K0088+(-142) | Brgy. Dau, Mabalacat City, Pampanga | 2014-11-19 | 1st & Final | III | LF | 2.6246 | 83 | 2014-04-28 | 2014-07-19 | 0% | C | 0.448 | 0.133 | 0.3 | - | - | - | 88.1% | 88.1% Satisfactory
R.G. Diaz Builders & Trading | 23814 | L | B | SB | GB | Construction/Completion of One (1) Storey Three (3) CL San Pedro Elem. School @ Brgy. San Pedro 2 | Magalang, Pampanga | 2014-11-19 | 1st & Final | III | LF | 1.8527 | 75 | 2014-04-21 | 2014-07-04 | 0% | C | 0.454 | 0.133 | 0.3 | - | - | - | 88.7% | 88.7% Satisfactory
R.G. DIAZ BUILDERS & TRADING | 23814 | L | B | SB | GE | Concreting of Mining Barangay Road (With Drainage), Barangay Mining, Angeles City, 1st LD | Barangay Mining, Angeles City, 1st LD | 2015-11-13 | Final | Pampanga Third DEO | LF | 4.645 | 60 | 2015-05-18 | 2015-07-16 | - | C | 0.491 | 0.133 | 0.3 | - | - | - | 92.4% | 92.4% Very Satisfactory
R.G. Florentino Construction & Trading-San Andres, Romblon Branch (Formerly: R.G. Florentino Construction) | 18301 | L | B | SB | GE2 | Const. of Parpagoha River Control along Tablas Circ. Rd. | San Andres, Romblon | 2012-11-29 | 1st | IVB | LF | 4.574 | 90 | 2012-09-19 | 2012-12-17 | 1.5 | O | 0.35 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 87 | -
R.G. Florentino Construction & Trading-Sand Andres Romblon Branch (Formerly: R.G. Florentino Construction) | 18301 | L | B | SB | GE2 | Const. of Parpagoha River Control along Tablas Circ. Rd. | San Andes, Romblon | 2013-08-05 | Final | IVB | LF | 4.574 | 90 | 2012-09-19 | 2012-12-17 | 2.22 | C | 0.336 | 0.2 | 0.3 | - | - | - | 83.6 | 85.64% Satisfactory
R.G. Macaspac Construction and Engineering Consultant | 23402 | L | B | SB | GE1 | Rehab./Impv't. of Rds. in Panghulo, Brgy. Panghulo | Malabon City | 2013-03-15 | Final | NCR | LF | 1.927 | 150 | 2012-08-08 | 2013-01-04 | 29.17 | C | 0.446 | 0.133 | 0.3 | - | - | - | 87.9 | 83.46% Satisfactory
R.J. Ibarra Construction | 23538 | L | B | MA | GB1 | Construction of DPWH-Zambales 2nd District Engineering Office Building |  | 2009-05-23 | 1st | III |  | 18.9014 | 180 |  |  |  | O | 0.368 | 0.239 | 0.15 | 0.03 | 0.029 | 0.05 | 86.6 | -
R.J. Ibarra Construction | 23538 | L | B | MA | GB1 | Partial Completion of Gordon Heights National High School |  | 2009-09-01 | 1st | III |  | 1.958 | 90 |  |  |  | O | 0.32 | 0.24 | 0.15 | 0.03 | 0.048 | 0.033 | 82.1 | -
R.J. Ibarra Construction | 23538 | L | B | MA | GB1 | Const. of 2 CL Sch. Bldg. Secondary |  | 2008-11-12 | 1st | III |  | 2.062 | 90 |  |  |  | O | 0.26 | 0.266 | 0.1 | 0.03 | 0.023 | 0.1 | 77.9 | -
R.J. Ibarra Construction | 23538 | L | B | MA | GE | Construction of Drainage Structure along San Marcelino - San Antonio Road, K0155+104 - K0156+512 | San Marcelino, Zambales | 2014-11-27 | 1st & Final | III | LF | 19.2461 | 150 | 2014-01-14 | 2014-06-12 | 0% | C | 0.365 | 0.133 | 0.3 | - | - | - | 79.8% | 79.8% Unsatisfactory
R.J. Ibarra Construction | 23538 | L | B | MA | GE2 | Impv't. of Pamatawan River, Brgy. Del Pilar Side | Castillejos, Zambales | 2013-08-05 | Final | III | LF | 26.924 | 210 | 2013-01-29 | 2013-08-26 | 18.48 | C | 0.446 | 0.133 | 0.3 | - | - | - | 87.9 | 83.82% Satisfactory
R.J. Ibarra Construction | 23538 | L | B | MA | GE2 | Impv't. of Pamatawan River, Brgy. Del Pilar Side, Phase II | Castillejos, Zambales | 2013-03-15 | 1st | III | LF | 26.924 | 210 | 2013-01-29 | 2013-08-26 | 19.04 | O | 0.339 | 0.2 | 0.15 | 0.03 | 0.042 | 0.05 | 81.1 | -
R.J. Ibarra Construction | 23538 | L | B | MA | GE2 | Impv't. of Sacatihan River, Brgy. Sacatihan | Subic, Zambales | 2013-08-05 | Final | III | LF | 11.853 | 120 | 2013-01-29 | 2013-05-28 | 3.33 | C | 0.408 | 0.133 | 0.3 | - | - | - | 84.1 | 82.30% Satisfactory
R.J. Ibarra Construction | 23538 | L | B | MA | GE2 | Impv't. of Sacatihan River, Brgy. Sacatihan | Subic, Zambales | 2013-03-16 | 1st | III | LF | 11.853 | 120 | 2013-01-29 | 2013-05-28 | 30.17 | O | 0.373 | 0.18 | 0.15 | 0.03 | 0.045 | 0.033 | 81.1 | -
R.K.X. Odiamar Construction | 16107 | L | A | MA | GE | Rehab./Reconst./Upgrading of Damaged Paved National Roads including Drainage along Daang Maharlika Road, Package 5: K0459+005-K0459+802, Baao, Camarines Sur | Nabua and Balatan, Camarines Sur, K0459+005-K0459+802, Baao, Camarines Sur | 2014-11-12 | 1st & Final | V | LF | 1.2861 | 165 | 2014-02-21 | 2014-08-04 | 1.48% | C | 0.487 | 0.133 | 0.3 | - | - | - | 92% | 92% Very Satisfactory
R.K.X. Odiamar Construction | 16107 | L | A | MA | GE1 | Restoration of Slip/Embankment along Maguiring-Sibobo-Cagsao Road, Km.460+571 | Calabanga, Camarines Sur | 2012-03-21 | 1st | V | LF | 2.388 | 150 | 2012-01-23 | 2012-06-20 | 59.92 | O | 0.347 | 0.225 | 0.15 | 0.03 | 0.043 | 0.033 | 82.8 | -
R.K.X. ODIAMAR CONSTRUCTION | 16107 | L | A | SB | GE | Construction/Rehabilitation/Improvement of Canaman Flood Control | Canaman, Camarines Sur | 2015-11-14 | Final | Camarines Sur Second DEO | LF | 13.5782 | 125 | 2015-02-10 | 2015-06-15 | - | C | 0.45 | 0.133 | 0.3 | - | - | - | 88.3% | 88.3% Satisfactory
R.M Padillo Builders | 31206 | L | D | SB | GB1 | Const./Repair/Rehab of MPB (San Isidro Parish MPC), Poblacion |  | 2009-03-05 | 1st | VIII |  | 0.7095 | 90 |  |  |  | O | 0.336 | 0.272 | 0.15 | 0.015 | 0.025 | 0.05 | #VALUE! | -
R.M Vitug Construction | 9227 | L | B | MA | GE1 | Upgrading of Lubao Diversion Road |  | 2009-05-18 | 1st | III |  | 28.663 | 100 |  |  |  | O | 0.315 | 0.24 | 0.15 | 0.03 | 0.04 | 0.05 | 82.5 | -
R.M. Mondares Construction | 23173 |  |  |  |  | Supply & Installation of 6-person 3 stops-Elevator | Echem Street, Cagayan de Oro City, Region X | 2014-08-18 | 1st | PICE-Misamis Oriental-CDO | L | 3.872 | 240 | 2013-12-27 | 2014-08-26 | 6.99 | O | 0.397 | 0.3 | 0.08 | 0.03 | 0.07 | 0.05 | 92.7 | -
R.M. Mondares Construction | 23173 |  |  |  |  | Supply & Installation of 6-person 3 stops-Elevator | Echem Street, Cagayan de Oro City, Region X |  | Final | PICE-Misamis Oriental-CDO | L | 3.872 | 240 | 2013-12-27 | 2014-09-25 | 0 | C | 0.5 | 0.2 | 0 | - | - | - | 70 | 85.89% Satisfactory
R.M. Vitug Construction | 9227 | L | B | MA | GB1 | San Fernando LTO Regional Office Building Project | San Fernando, Pampanga / Region III | 2014-02-06 | 2nd | DOTC | LF | 45.279 | 450 | 2013-04-14 | 2014-07-07 | 29.56 | O | 0.3874 | 0.3 | 0.15 | 0.03 | 0.07 | 0.05 | 98.74 | -
R.M. Vitug Construction | 9227 | L | B | MA | GE2 | Impv't. of Camachile River, Brgy. Nagbunga | San Marcelino, Zambales | 2013-08-05 | Final | III | LF | 16.223 | 120 | 2013-01-28 | 2013-05-27 | 10 | C | 0.39 | 0.133 | 0.3 | - | - | - | 82.3 | 86.68% Satisfactory
R.M. Vitug Construction | 9227 | L | B | MA | GE2 | Impv't. of Camachile River, Brgy. Nagbunga | San Marcelino, Zambales | 2013-03-16 | 1st | III | LF | 15.42 | 120 | 2013-01-28 | 2013-05-27 | 46.15 | O | 0.376 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 89.6 | -
R.M. VITUG CONSTRUCTION/E.M. DANAN TRADING & CONSTRUCTION (JOINT VENTURE) | JV-14-712 | L | B | MA | GE | Network Development, Widening of National Roads, (Arterial Roads), Outside N1, DAU/NLEX-MNR Road, K0088+(-342) to K0089+323, 1st LD, Mabalacat City, Pampanga | K0088+(-342) to K0089+323, 1st LD, Mabalacat City, Pampanga | 2015-08-29 | 1st | Pampanga Third DEO | LF | 36.713 | 210 | 2015-04-23 | 2015-11-18 | 31% | O | 0.342 | 0.24 | 0.15 | 0.03 | 0.07 | 0.05 | 88.2% | -
R.M.A.J. CONSTRUCTION | 18623 | L | B | MA | GE | Network Development-Widening of Secondary N/R along Mamburao Airport Rd., K0407+(-364)- K0407+257.70 Road Section ID: S00097MR | Mamburao, Occidental Mindoro | 2015-06-09 | 1st | Mindoro Occidental DEO | LF | 17.275 | 144 | 2015-03-12 | 2015-08-03 | 0% | O | 0.391 | 0.24 | 0.15 | 0.03 | 0.04 | 0.033 | 88.4% | -
R.N.G.M. CONSTRUCTION/B.M.K. CONSTRUCTION (JV) | JV-13-187 | L | AAA | LA | GE | Construction/Improvement of Access Road Leading to Declared Tourism Destinations, Sabang - Baler Road Leading to Sabang Garden Malls and Garden Plaza | Aurora | 2015-06-10 | Final | Aurora DEO | LF | 48.25 | 300 | 2014-03-25 | 2015-01-18 | 0% | C | 0.422 | 0.2 | 0.3 | - | - | - | 92.2% | *92.2% Very Satisfactory
R.O Builders & Dev. Corp. | 22393 |  |  |  |  | Rehab./Reconst./Upgrading of Damaged Paved National Rd. along Daang Maharlika Namamparan-Diadi Poblacion Sect. |  | 2010-06-10 |  | II |  | 19.28 | 105 |  |  |  | O | 0.334 | 0.3 | 0.15 | 0.03 | 0.047 | 0.033 | 89.4 | -
R.O Builders & Dev. Corp. | 22393 | L | A | MA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved National Road along Maharlika (Nagsabaran-Balete Section) |  | 2009-06-01 | 1st | II |  | 18.904 | 90 |  |  |  | O | 0.358 | 0.3 | 0.15 | 0.03 | 0.051 | 0.033 | 92.2 | -
R.O Builders & Dev. Corp. | 22393 | L | A | MA | GE1 | Conc. of Aritao-Dupax-Kasibu-Quirino Road, Mangayang Section |  | 2009-03-11 | 2nd | II |  | 16.182 | 150 |  |  |  | O | 0.345 | 0.3 | 0.15 | 0.03 | 0.05 | 0.05 | #VALUE! | -
R.O Builders & Dev. Corp. | 22393 | L | A | MA | GE1 | Conc. of Aritao-Dupax-Kasibu-Quirino Road, Mangayang Section |  | 2008-11-28 | 1st | II |  | 16.182 | 150 |  |  |  | O | 0.351 | 0.279 | 0.1 | 0.02 | 0.033 | 0.067 | 85 | -
R.O. BUILDERS & DEV. CORP | 22393 | L | A | SB | GE | Construction of Slope Protection along Daang Maharlika, K0246+800 | Bambang, Nueva Vizcaya | 2015-06-09 | 1st | Nueva Vizcaya 1st DEO | LF | 9.309 | 180 | 2015-02-17 | 2015-08-15 | 0.12% | O | 0.244 | 0.3 | 0.15 | 0.03 | 0.05 | 0.05 | 82.4% | -
R.O. BUILDERS & DEV. CORP. | 22392 | L | A | MA | GE | Construction of Bridges (New) Tinabla Box Culvert along Papaya - Malabing - Wangal -Binogawan - Tadji - Runruno, Kasibu, Nueva Vizcaya | Kasibu, Nueva Vizcaya | 2015-09-03 | 1st & Final | NV 2nd DEO | LF | 12.701 | 180 | 2014-08-27 | 2015-02-23 | 0% | C | 0.409 | 0.2 | 0.3 | - | - | - | 90.9% | *90.9% Very Satisfactory
R.O. BUILDERS & DEV. CORP. | 22393 | L | A | SB | GE | Construction of Slope Protection along Daang Maharlika, K0246+800, Bambang, Nueva Vizcaya | Bambang, Nueva Vizcaya | 2015-09-02 | 1st & Final | NV 1st DEO | LF | 9.309 | 180 | 2015-02-18 | 2015-08-16 | 0.28% | C | 0.422 | 0.133 | 0.3 | - | - | - | 85.5% | *85.5% Satisfactory
R.R Encabo Constructors and Traders | 14716 |  |  |  |  | Alaminos Airport Dev't Project (Construction of Runway Strip - Phase I) |  | 2011-04-01 |  | DOTC |  | 96.342 | 210 |  |  |  | O | 0.363 | 0.3 | 0.15 | 0.03 | 0.062 | 0.017 | 92.2 | -
R.R Seismundo Construction & Supply | 10961 | L | A | MB | GE1 | Conc. of Compostela Cateel Road-Osmeña Sect., Sitio Nursery Sec. & Spur II-Pansansalan Sec. |  | 2009-03-16 | 1st | XI |  | 46.27 | 330 |  |  |  | O | 0.283 | 0.288 | 0.15 | 0.03 | 0.038 | 0.033 | #VALUE! | -
R.R. Encabo Constructor's Inc. |  | L | AAA |  |  | Rehabilitation and Development of Estero de San Sebastian (Sta. 0+000 to Sta. 0+316) | Estero De San Sebastian, Manila | 02/27/14 | 1st | PRRC | LF | 6.849 | 150 | 11/16/12 |  |  | O | 0.4 | 0.3 | 0.15 | 0.03 | 0.032 | 0.05 | 96.2 | -
R.R. Encabo Constructors Incorporated / R.C. Tagala Construction (Joint Venture) | JV-12-366 | L | AAA | MB | GE1 | Rehab./Reconst./Strengthening of Bridges along Catanduanes Circ. Rd., Kanparel Bridge, (Km.0056+470) | Panganiban, Catanduanes | 2013-07-30 | 1st | V | LF | 31.52 | 211 | 2013-02-15 | 2013-09-13 | -1.91 | O | 0.342 | 0.272 | 0.131 | 0.03 | 0.04 | 0.033 | 84.8
R.R. Encabo Constructors Incorporated/R.C. Tagala Construction (JV) | JV-12-366 | L | AAA | MB | GE | Rehabilitation/Reconstruciton/Strengthening of Bridges along Catanduanes Circumferential Road, Kanparel Bridge | Panganiban, Catanduanes | 2014-08-14 | Final | V | LF | 32.1258 | 241 | 2013-02-15 | 2013-10-13 | 0 | C | 0.365 | 0.2 | 0 |  |  |  | 56.5 | 73.48% Poor
R.R. Ricafort Construction and Supplies (Formerly: R.R. Ricafort Construction) | 14402 | L | A | MB | GE | Preventive Maintenance along La Paz - Victoria Road (Lapaz Section), KO138+863 to KO139+000 | La Paz, Tarlac | 2014-08-05 | 1st & Final | III | LF | 1.3519 | 15 | 2014-02-06 | 2014-02-20 | 0 | C | 0.457 | 0.133 | 0.3 |  |  |  | 89 | 89.00% Satisfactory
R.R. Ricafort Construction and Supplies (Formerly: R.R. Ricafort Construction) | 14402 | L | A | MB | GE | Completion/Concreting of Brgy. Bacsay - Maasin Road | Camiling, Tarlac | 2014-08-06 | 1st & Final | III | LF | 6.796 | 60 | 2014-02-12 | 2014-04-12 | 12.27 | C | 0.482 | 0.126 | 0.3 |  |  |  | 90.8 | 90.80% Very Satisfactory
R.R. Ricafort Construction and Supplies (Formerly: R.R. Ricafort Construction) | 14402 | L | B | MA | GB1 | Const. of MPB, Brgy. Burgos |  | 2008-11-14 | 1st | III |  | 3.004 | 90 |  |  |  | O | 0.302 | 0.24 | 0.1 | 0 | 0.018 | 0.1 | 76 | -
R.R. Ricafort Construction and Supplies (Formerly: R.R. Ricafort Construction) | 14402 | L | A | MB | GE1 | Conc. of Brgy. Road @ Brgy. San Agustin-Bantog Rd. | Victoria, Tarlac | 2012-11-24 | 1st | III | LF | 7.904 | 80 | 2012-09-17 | 2012-12-05 | 1.93 | O | 0.315 | 0.288 | 0.15 | 0.03 | 0.035 | 0.033 | 85.1 | -
R.R. Ricafort Construction and Supplies (Formerly: R.R. Ricafort Construction) | 14402 | L | A | MB | GE | Preventive Maintenance along Victoria-Pura Road KO151+000 to KO152+000 Modified to Preventive Maintenance along Victoria-Pura Road KO151+000 to KO152+000 w/ exceptions | Victoria, Tarlac | 2014-11-20 | 1st & Final | III | LF | 8.4751 | 30 | 2014-05-08 | 2014-06-06 | 6.67% | C | 0.492 | 0.133 | 0.3 | - | - | - | 92.5% | 92.5% Very Satisfactory
R.R. Ricafort Construction and Supplies (Formerly: R.R. Ricafort Construction) | 14402 | L | A | MB | GE | Construction of Road at Brgy. Patling, Sta. 0+000 to Sta. 0+477 | Capas, Tarlac | 2014-11-20 | 1st & Final | III | LF | 3.6111 | 23 | 2014-05-13 | 2014-06-04 | 0% | C | 0.492 | 0.133 | 0.3 | - | - | - | 92.5% | 92.5% Very Satisfactory
R.R. Ricafort Construction and Supplies (Formerly: R.R. Ricafort Construction) | 14402 | L | A | MA | GE2 | Mogpog River Control along Marinduque Circ. Rd. (Banto-Mogpog Sect.) | Mogpog, Marinduque | 2013-08-07 | Final | IVB | LF | 12.701 | 200 | 2012-10-22 | 2013-05-09 | 0 | C | 0.386 | 0.2 | 0.3 | - | - | - | 88.6 | 85.18% Satisfactory
R.R. Ricafort Construction and Supplies (Formerly: R.R. Ricafort Construction) | 14402 | L | A | MA | GE2 | Mogpog River Control along Marinduque Circ. Rd. (Banto-Mogpog Sect.) | Mogpog, Marinduque | 2013-03-23 | 1st | IVB | LF | 12.701 | 190 | 2012-10-22 | 2013-04-29 | 0 | O | 0.344 | 0.232 | 0.15 | 0.03 | 0.04 | 0.033 | 82.9 | -
R.R. Ricafort Construction and Supplies (Formerly: R.R. Ricafort Construction) | 14402 | L | A | MB | GE1 | Conc. of Polangui-Gebulwangan-Quezon-Trangue-Mabini Rd. (Sta.762+140-Sta.765+420) w/ exceptions | Catarman, Northern Samar | 2013-03-21 | Final | VIII | LF | 72.749 | 370 | 2012-03-22 | 2013-03-26 | 1.8 | C | 0.435 | 0.136 | 0.3 | - | - | - | 87.1 | 88.78% Satisfactory
R.R. SEISMUNDO CONSTRUCTION & SUPPLY / GP & H CONSTRUCTION AND SUPPLY JOINT VENTURE | JV-14-503 | L | A | MA | GE | Construction of Bank Protection Matiao River | Pantukan, Comval Province | 2015-06-09 | 1st | Compostela Valley | LF | 18.617 | 183 | 2015-02-18 | 2015-08-19 | (+)5.72% | O | 0.33 | 0.239 | 0.15 | 0.03 | 0.051 | 0.05 | 85% | -
R.S Reyna Construction | 9648 | L | D | SB | GE1 | Repair of Brgy. Roads, Brgy. Balocawehay-Katipunan-Ulhay-Tambis |  | 2009-05-28 | 1st | VIII |  | 1.915 | 25 |  |  |  | O | 0.32 | 0.2 | 0.15 | 0.03 | 0.047 | 0.033 | 78 | -
R.S. REYNA CONSTRUCTION | 9648 | L | D | SB | GE | Network Development-Off-Carriageway Improvement along National Road, Abuyog-Silago Road, K0969+000 to K0970+060, Baybay City, Leyte | Baybay City, Leyte | 2015-11-15 | Final | Leyte Fifth DEO | LF | 4.59 | 60 | 2015-03-03 | 2015-05-01 | - | C | 0.275 | 0.2 | 0.3 | - | - | - | 77.5% | 77.5% Unsatisfactory
R.S. Sepian Construction and Trucking | 20519 | L | A | MB | GE | Upgrading (Gravel to Paved) Balili-Suyo-Sagada Road Leading to Sagada Caves, Rice Terraces and Water Falls | Bontoc & Sagada, Mt. Province | 2014-11-21 | 1st | CAR | LF | 92.1882 | 297 | 2014-04-28 | 2015-02-18 | 11.99% | O | 0.312 | 0.281 | 0.15 | 0.03 | 0.055 | 0.05 | 87.8% | 87.8% Satisfactory
R.S. Sepian Construction and Trucking | 20519 | L | A | MB | GE | Road Upgrading (Gravel to Concrete) based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standard (HDM-4 Project Analysis) (Intermittent Sections) along Acop-Kapangan-Kibungan-Bakun Road, K0334+690 - K0335+000, K0335+000 - K0335+124, K0335+205 - K0336+000 | Bakun, Benguet | 2014-11-21 | 1st | CAR | LF | 44.5355 | 209 | 2014-06-25 | 2015-01-19 | 4.62% | O | 0.334 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 85.9% | 85.9% Satisfactory
R.S. Sepian Construction and Trucking | 20519 | L | A | MB | GE | Construction / Improvement of Poblacion - Chumang - Liwo Road Leading to O'phaw - Mechancha Waterfalls | Mayoyao, Ifugao (DSTD) | 2014-11-25 | 1st | CAR | LF | 57.9 | 300 | 2014-04-28 | 2015-02-21 | 0.97% | O | 0.362 | 0.238 | 0.15 | 0.03 | 0.055 | 0.05 | 88.5% | 88.5% Satisfactory
R.S. Sepian Construction and Trucking | 20519 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Concrete), Abra-Ilocos Norte Rd., K0436+000-K0436+700 | Abra | 2013-03-23 | Final | CAR | LF | 14.954 | 220 | 2012-01-16 | 2012-08-24 | 0.91 | C | 0.25 | 0.133 | 0.3 | - | - | - | 68.3 | 64.34% Poor
R.S. Sepian Construction and Trucking | 20519 | L | B | MA | GE1 | Repair/Restoration along Baguio-Bua-Itogon Rd. K0260+480-K0260+530 | Itogon, Benguet | 2012-07-30 | 1st | CAR | LF | 17.825 | 180 | 2012-02-10 | 2012-08-07 | -3.51 | O | 0.324 | 0.217 | 0.115 | 0.01 | 0.033 | 0.033 | 73.2 | -
R.S. SEPIAN CONSTRUCTION AND TRUCKING | 20519 | L | A | MB | GE | Construction/Improvement of Poblacion-Chumang-Liwo Road Leading to O'phaw-Mechancha Waterfalls | Mayoyao, Ifugao | 2015-06-08 | Final | CAR | LF | 57.9 | 324 | 2014-04-28 | 2015-03-17 | (+) 2.16% | C | 0.405 | 0.2 | 0.3 | - | - | - | 90.5% | *89.3% Very Satisfactory
R.S. SEPIAN CONSTRUCTION AND TRUCKING | 20519 | L | A | MB | GE | Upgrading (Gravel to Paved) of Balili-Suyo-Sagada Road Leading to Sagada Caves, Rice Terraces and Water Falls | Bontoc & Sagada, Mt. Province | 2015-06-04 | Final | CAR | LF | 96.211 | 398 | 2014-04-28 | 2015-05-30 | 0% | C | 0.399 | 0.2 | 0.3 | - | - | - | 89.9% | *88.64% Satisfactory
R.T Morabe Construction | 11377 | L | B | MA | GE1 | Concreting of Laoang-Lapinig-Arteche Road Km. 965+515.00-Km.966+645.00 |  | 2009-06-08 | 1st | VIII |  | 19.138 | 150 |  |  |  | O | 0.331 | 0.235 | 0.15 | 0.03 | 0.045 | 0.05 | 84.1 | -
R.T Morabe Construction | 13377 |  |  |  |  | Const. of La Paz-Javier-Bito Road, La Paz-Javier-Bito Rd. Section |  | 2010-08-24 |  | VIII |  | 14.167 | 120 |  |  |  | O | 0.473 | 0.133 | 0.3 | - | - | - | 90.6 | 88.44% Satisfactory
R.T Morabe Construction | 13377 |  |  |  |  | Const. of La Paz-Javier-Bito Rd., La Paz-Javier-Bito Rd. Sect. |  | 2010-05-31 |  | VIII |  | 14.167 | 120 |  |  |  | O | 0.377 | 0.3 | 0.104 | 0.03 | 0.042 | 0.017 | 87 | -
R.T Morabe Construction | 11377 | L | C | SB | GE1 | Concreting of Tabango-Catmon- (La Fortuna) Manlawaan-Gimarco Road |  | 2009-06-02 | 2nd | VIII |  | 9.353 | 336 |  |  |  | O | 0.343 | 0.3 | 0.15 | 0.03 | 0.037 | 0.05 | 91 | -
R.T Morabe Construction | 11377 | L | C | SB | GE1 | Concreting of Tabango-Catmon (La Fortuna) Manlawaan-Gimarco Road Km 1039+540-Km 1040+000 |  | 2009-03-12 | 1st | VIII |  | 9.3533 | 180 |  |  |  | O | 0.341 | 0.026 | 0.15 | 0.03 | 0.037 | 0.033 | #VALUE! | -
R.T. Builders | 33773 | L | D | SB | GE2 | Drainage System at Abucay Daang Maharlika, Brgy. Abucay | Tacloban City | 2013-08-22 | Final | VIII | LF | 4.009 | 107 | 2012-10-12 | 2013-01-26 | 40 | C | 0.459 | 0.133 | 0.3 | - | - | - | 89.2 | 86.20% Satisfactory
R.T. Diwa Construction | 14263 | L | B | SB | GE | Concreting of Provincial Road Brgy. Casingsingan-San Juan Section, Amulung West | Cagayan | 2014-10-23 | 1st & Final | II | LF | 2.97 | 75 | 2014-04-23 | 2014-07-06 |  | C | 0.342 | 0.2 | 0.3 | - | - | - | 84.2% | 84.2% Satisfactory
R.T. Morabe Construction | 11377 | L | B | MA | GE | Rehab./Reconst. Along Jct Taft-Oras, San Policarpio-Arteche, KO 890+400-KO895+177 | Eastern Samar | 2014-08-14 | 1st & Final | VIII | LF | 22.5471 | 155 | 2013-01-30 | 2013-07-03 | 0 | C | 0.458 | 0.2 | 0 |  |  |  | 65.8 | 65.80% Poor
R.T. Morabe Construction | 11377 | L | B | MA | GE1 | Rehab./Reconst. along Taft-Oras-San-San Policarpio-Arteche Rd., K0890+400-K0895+177 | Eastern Samar | 2013-08-19 | 1st | VIII | LF | 22.547 | 155 | 2013-01-30 | 2013-07-03 | -5 | O | 0.361 | 0.3 | 0 | 0.03 | 0.055 | 0.017 | 76.3
R.T. Morabe Construction | 11377 | L | B | MA | GE1 | Repair/Rehab./Conc. of Jct. Taft-Oras-San Policarpio-Arteche Nat'l Rd., Km.954.540-Km.956+020, Brgy. Carapdapan | Arteche, Eastern Samar | 2013-08-19 | Final | VIII | LF | 28.95 | 357 | 2011-10-27 | 2012-10-18 | 5.2 | C | 0.447 | 0.186 | 0.3 | - | - | - | 93.3 | 87.42% Satisfactory
R.T. Morabe Construction | 11377 | L | B | MA | GE1 | Repair/Rehab./Conc. Of Jct. Taft-Oras-San Policarpio-Arteche Nat'l Rd., Km.954+540-Km.956+020 | Arteche, Eastern Samar | 2012-08-19 | 1st | VIII | LF | 28.95 | 327 | 2011-10-27 | 2012-09-18 | 25.47 | O | 0.294 | 0.3 | 0.15 | 0.03 | 0.028 | 0.033 | 83.5 | -
R.T. MORABE CONSTRUCTION/JULITA BUILDERS JOINT VENTURE | JV-14-417 | L | B | MA | GB | Construction of Municipal Hall, Tabontabon, Leyte | Tabontabon, Leyte | 2015-06-09 | 1st | Leyte Second DEO | LF | 19.248 | 240 | 2015-03-30 | 2015-11-24 | - | O | 0.363 | 0.284 | 0.15 | 0.03 | 0.041 | 0.05 | 91.8% | -
R.T.Y Construction | 10341 | L | B | MA | GE1 | Rehab./Reconst. of San Juan-Candelaria Jct.-Candelaria-Bolboc Road, inc. Bantilan Bridge |  | 2009-05-25 | 1st | IV-A |  | 19.195 | 114 |  |  |  | O | 0.394 | 0.24 | 0.15 | 0.03 | 0.025 | 0.05 | 88.9 | -
R.T.Y Construction | 10341 | L | B | MA | GE1 | Road Upgrading of Dr. Damian Reyes Memorial Road (Torrijos Side) |  | 2009-08-25 | 1st | IVB |  | 47.275 | 210 |  |  |  | O | 0.344 | 0.25 | 0.15 | 0.03 | 0.051 | 0.05 | 87.5 | -
R.T.Y Construction | 10341 | L | B | MA | GB1 | Construction of TESDA Training Center |  | 2009-05-18 | 2nd | IV-B |  | 14.395 | 213 |  |  |  | O | 0.343 | 0.289 | 0.15 | 0.03 | 0.012 | 0.05 | 87.4 | -
R.T.Y Construction | 10341 | L | B | MA | GB1 | Construction of TESDA Training Center |  | 2009-03-11 | 1st | IV-B |  | 14.395 | 180 |  |  |  | O | 0.39 | 0.204 | 0.15 | 0.03 | 0.018 | 0.05 | #VALUE! | -
R.T.Y Construction | 10341 | L | B | MA | GE1 | Rehab./Conc. of Dr. Damian Reyes Road (Torrijos Side) |  | 2009-05-18 | 2nd | IV-B |  | 48.247 | 254 |  |  |  | O | 0.351 | 0.259 | 0.15 | 0.03 | 0.023 | 0.05 | 86.3 | -
R.T.Y Construction | 10341 | L | B | MA | GE1 | Rehab./Conc. of Dr. Damian Reyes Road (Torrijos Side) |  | 2009-03-11 | 1st | IV-B |  | 48.245 | 240 |  |  |  | O | 0.362 | 0.179 | 0.15 | 0.03 | 0.025 | 0.05 | #VALUE! | -
R.T.Y. CONSTRUCTION | L | L | B | MA | GE | Repair/Rehabilitation/Improvement of Mogpog-Balanacan Port Road, Balanacan-Mogpog, Marinduque | Marinduque | 2015-09-01 | 1st & Final | Marinduque DEO | LF | 12.555 | 75 | 2015-01-12 | 2015-03-27 | - | C | 0.48 | 0.133 | 0.3 | - | - | - | 91.3% | *91.3% Very Satisfactory
R.T.Y. Construction | 10341 | L | B | MA | GE | Road Upgrading (Concrete Paving) along Talaba - Summit - Panaon Road, K0195+533 to K0197+045, Quezon Third | Unisan, Quezon | 2014-08-12 | Final | IV-A | LF | 36.0328 | 310 | 2013-03-11 | 2014-01-14 | 0 | C | 0.351 | 0.2 | 0.3 |  |  |  | 85.1 | 83.30% Satisfactory
R.T.Y. Construction | 10341 | L | B | MA | GE1 | Rd. Upgrading (Concrete Paving) along Talaba-Summit-Panaon Rd., K0195+533-K0197+045 | Quezon | 2013-08-06 | 1st | IVA | LF | 34.582 | 165 | 2013-03-11 | 2013-08-22 | 0.24 | O | 0.328 | 0.245 | 0.15 | 0.03 | 0.035 | 0.033 | 82.1
R.T.Y. Construction | 10341 | L | B | MA | GE | Preventive Maintenance Daang Maharlika, K0163+291 to K164+100; K0164+100 to K0164+1050; K0164+1050 to K0166+171 | Quezon | 2014-08-11 | Final | IV-A | LF | 42.4824 | 221 | 2013-02-12 | 2013-09-20 | 0 | C | 0.436 | 0.2 | 0.3 |  |  |  | 93.6 | 82.98% Satisfactory
R.T.Y. Construction | 10341 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of Lucena-Tayabas-Mauban Port Rd. Jct. Km.128+282-Km.132+070 w/ exception | Lucena City | 2013-08-03 | Final | IVA | LF | 42.817 | 245 | 2012-03-09 | 2012-11-08 | 1.22 | C | 0.301 | 0.2 | 0.3 | - | - | - | 80.1 | 84.54% Satisfactory
R.T.Y. Construction | 10341 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of Lucena-Tayabas-Mauban Port Rd. Jct. Km.128+282-Km.132+070 w/ exception | Lucena City | 2012-07-30 | 1st | IVA | LF | 39.824 | 230 | 2012-03-09 | 2012-10-24 | 0.88 | O | 0.346 | 0.239 | 0.15 | 0.03 | 0.06 | 0.05 | 87.5 | -
R.T.Y. Construction | 10341 | L | B | MA | GE1 | Assets Preservation of Nat'l Roads Gen. from Pvmt. Mgt. System/Highway Dev't. Mgt.-4 (HDM-4) Int. Sect.; A. Prev. Maint.; 1. Nat'l Arterial (Prev. Maint.); 1. Daang Maharlika; a.K0163+291 - K0164+100; b.K0164+100-K0164+1050; c.K0164+1050-K0166+171 | Quezon | 2013-08-05 | 2nd | IVA | LF | 40.482 | 171 | 2013-02-12 | 2013-08-01 | -32 | O | 0.395 | 0.225 | 0 | 0.03 | 0.028 | 0.017 | 69.5
R.T.Y. Construction | 10341 | L | B | MA | GE1 | Assets Preservation of Nat'l Rds. Int. Sect.; A. Prev. Maint.; 1. Nat'l Arterial (Prev. Maint.); 1. Daang Maharlika; A.K0163+291-K0164+100; B.K0164+100-K0164+1050; C.K0164+1050-K0166+171 | Quezon | 2013-03-19 | 1st | IVA | LF | 40.482 | 171 | 2013-02-12 | 2013-08-01 | -7.62 | O | 0.39 | 0.24 | 0.074 | 0.03 | 0.056 | 0.033 | 82.3 | -
R.T.Y. Construction | 10341 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of MCR (Tawiran-Taytay-Bonliw Sect.) Km.36+87 -Km.33+000 / Km.42+331-Km.42+518 / Km.48+936-Km.497+224.80, Sta. Cruz-Torrijos | Marinduque | 2013-03-23 | Final | IVB | LF | 23.634 | 205 | 2012-01-26 | 2012-08-17 | 0 | C | 0.427 | 0.133 | 0.3 | - | - | - | 86 | 86.96% Satisfactory
R.T.Y. Construction | 10341 | L | B | MA | GE | Repair/Improvement of Sabang Bridge Approaches along Tigwi - Dampulan - Lipata - Yook - Buenavista Road (K0096+612.5 - K0096+700) | Buenavista, Marinduque | 2014-08-16 | 1st & Final | IV-B | LF | 4.9213 | 85 | 2014-04-21 | 2014-07-14 | 0 | C | 0.412 | 0.133 | 0.3 |  |  |  | 84.5 | 84.50% Satisfactory
R.T.Y. CONSTRUCTION | 10341 | L | B | MA | GE | Road Upgrading (Unpaved to Paved) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standard (HDM-4) Project Analysis, (Intermittent Sections) Secondary Road MSR Jct. Lopez - Buenavista Rd., K0220+531 to K220+943, K0221+849 to K0221+889, K0222+944 to K0224+000 | Lopez, Quezon | 2015-06-11 | 1st | Quezon 4th DEO | LF | 40.005 | 210 | 2015-03-06 | 2015-10-01 | 20.85% | O | 0.347 | 0.281 | 0.15 | 0.024 | 0.04 | 0.033 | 87.5% | -
R.T.Y. CONSTRUCTION | 10341 | L | B | MA | GE | Road Upgrading (Concrete Paving) MSR Jct. Lopez - Buenavista Road, K0241+651 to K0243+927, Net Length= 2276 l.m. (SO4254LZ) | Quezon | 2015-06-08 | Final | Quezon 3rd DEO | LF | 53.19 | 240 | 2014-06-23 | 2015-02-17 | 0% | C | 0.466 | 0.101 | 0.3 | - | - | - | 86.7% | *86.7% Satisfactory
R.T.Y. CONSTRUCTION | 10341 | L | B | MA | GE | Road Upgrading (Unpaved to Road) Based on Gavel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standards (HDM-4 Project Analysis) (Intermittent Sections) - Secondary Roads - MSR Jct - Lopez - Buenavista Road | K0 220+531 - K0 220+943, K0 221+849 - K0 221+889, K0 222+944 - K0 224+000, Lopez, Quezon | 2015-08-26 | 1st & Final | Quezon 4th | LF | 40.005 | 210 | 2015-03-06 | 2015-10-01 | 0% | C | 0.453 | 0.133 | 0.3 | - | - | - | 88.6% | *87.94% Satisfactory
R.U Aquino Construction and Development Corporation / RCDG Construction Corporation Joint Venture | JV-08-130 | L | AA | LA | GE1 | Widening/Concreting of Mt. Data-Bontoc Road, Malitep Bridge, Balili to Amsolong Bridge Alab Section |  | 2009-05-23 | 1st | CAR |  | 114.942 | 450 |  |  |  | O | 0.38 | 0.24 | 0.15 | 0.03 | 0.06 | 0.033 | 89.3 | -
R.U Aquino Construction and Development Corporation / RCDG Construction Corporation Joint Venture | JV-08-131 | L | AA | LA | GE1 | Widening/Conc. of Mount Data-Bontoc Road Amsolong Alab Poblacion Sectiopn. Km. 385+350-Km. 391+457 |  | 2009-08-28 | 2nd | CAR |  | 99.305 | 450 |  |  |  | O | 0.369 | 0.24 | 0.087 | 0.023 | 0.047 | 0.017 | 78.3 | -
R.U Aquino Construction and Development Corporation / RCDG Construction Corporation Joint Venture | JV-08-157 | L | AA | LA | GE1 | Conc. of Bontoc-Tabuk-Tuguegarao Road (Package BLT-16), Tinglayan Boundary Section I Tocucan to Betwagan Sect., Km. 401+300-Km. 406+200 with exception |  | 2009-08-29 | 1st | CAR |  | 128.685 | 425 |  |  |  | O | 0.351 | 0.24 | 0.004 | 0.023 | 0.056 | 0.017 | 69.1 | -
R.U. AGUINO CONSTRUCTION & DEVELOPMENT CORPORATION/NORTH TECH BUILDERS AND SUPPLY JOINT VENTURE | 0 | L | AA | MB | GE | Construction/Improvement of Access Roads leading to Airport, Seaports and declared Tourism Destinations-Concreting/Improvement of Luga Barangay Road leading to Tabaco, Banggalao and Ngiwatan Caves, Sta. Teresita, Cagayan | Sta. Teresita, Cagayan | 2015-11-10 | Final | CAGAYAN 1ST DEO | LF | 41.2273 | 187 | 2015-03-18 | 2015-09-20 | (-) 2.00 | C | 0.44 | 0.166 | 0.24 | - | - | - | 84.6% | 84.6% Satisfactory
R.U. Aquino Construction and Development Corporation ESR Construction & Supply | 23507 |  | AAA |  |  | Centralization of Power Supply | Baguio General Hospital, Baguio | 2016-06-17 | 1st | DOH | LF | 25.722 |  | 2016-02-11 | 2016-08-08 | 32.85 | O | 0.4 | 0 | 0 | 0.03 | 0.035 | 0.0167 | 48.17 | -
R.U. AQUINO CONSTRUCTION AND DEVELOPMENT CORPORATION/NORTH TECH BUILDERS AND CONSTRUCTION SUPPLY (JV) | JV-14-447 | L | AA | MB | GE | Construction/Improvement of Access Rpads at Claveria Bay View Blvd., Leading to Beach Resorts & Taggat Lagoon & Cave | Claveria, Cagayan | 2015-06-02 | 1st | Cagayan 2nd DEO | LF | 45.509 | 179 | 2015-03-02 | 2015-08-27 | 21.85% | O | 0.291 | 0.3 | 0.15 | 0.015 | 0.035 | 0.033 | 82.4% | -
R.U. AQUINO CONSTRUCTION AND DEV'T CORP./NORTH TECH BUILDERS AND CONSTRUCTION SUPPLY (Joint Venture) | JV-14-447 | L | AA | MB | GE | Construction/Improvement of Access Roads, Claveria Bay View Boulevard Leading to Beach Resorts and Taggat Lagoon and Cave, Sta. 0+000 to Sta. 2+300, Claveria, Cagayan | Claveria, Cagayan | 2015-08-26 | Final | Cagayan 2nd DEO | LF | 45.508 | 179 | 2015-03-02 | 2015-08-27 | 0.07% | C | 0.485 | 0.133 | 0.3 | - | - | - | 91.8% | *86.16% Satisfactory
R.V Construction | 6110 | L | C | SB | GB1 | Const. of MPB @ Brgy. Obrero |  | 2009-03-10 | 1st | VIII |  | 1.929 | 120 |  |  |  | O | 0.4 | 0.263 | 0.15 | 0.03 | 0.033 | 0.05 | #VALUE! | -
R.V Laborte Builders | 20459 |  |  |  |  | Const./Conc. of Candelaria-By-Pass Road, Brgy. Malabanban Sur, incl. RROW |  | 2010-02-17 |  | IVA |  | 17.68 | 240 |  |  |  | O | 0.355 | 0.3 | 0.15 | 0.03 | 0.042 | 0.05 | 92.7 | -
R.V Laborte Builders | 20459 |  |  |  |  | Const./Conc. of Candelaria-By-Pass Road, Brgy. Masin Sur, incl. RROW |  | 2010-02-17 |  | IVA |  | 17.676 | 180 |  |  |  | O | 0.353 | 0.3 | 0.15 | 0.02 | 0.042 | 0.033 | 89.8 | -
R.V Laborte Builders | 20459 | L | A | MB | GB1 | Completio of Olongtao MPB |  | 2008-11-11 | 1st | IV-A |  | 3.37 | 90 |  |  |  | O | 0.325 | 0.3 | 0.1 | 0.02 | 0.023 | 0.1 | 86.8 | -
R.V Rieta Trading & Gen. Construction | 28671 | L | C | SB | GB1 | Const. of 2 Storey MPB |  | 2008-08-26 | 1st | IV-A |  | 0.575 | 120 |  |  |  | O | 0.295 | 0.263 | 0.1 | 0.03 | 0.018 | 0.1 | 80.6 | -
R.V. Construction | 6110 | L | D | SB | GE | Paving of Shoulders (Seal Widening) along Sta. Margarita Old Route | Sta. Margarita, Samar | 2014-10-23 | 1st & Final | VIII | LF | 9.5583 | 160 | 2014-02-24 | 2014-08-02 | 2% | C | 0.384 | 0.173 | 0.3 | - | - | - | 85.7% | 85.7% Satisfactory
R.V. CONSTRUCTION | 6110 | L | D | SB | GE | Repair/Rehabilitation of Existing Permanent Bridge Diit Bridge, Tacloban City | Tacloban City | 2015-11-11 | Final | Tacloban City DEO | LF | 2.4177 | 60 | 2015-03-03 | 2015-05-01 | (+)30% | C | 0.477 | 0.133 | 0.3 | - | - | - | 91% | 91% Very Satisfactory
R.V. Laborte Builders | 20459 |  | B | MA |  | Quipot Irrigation Project | Tiaoag, Quezon | 2015-02-14 | 1st & Final | NIA | L | 31.282 | 356 | 2013-07-10 | 2014-06-30 | 0 | C | 0.35 | 0.2 | 0.3 | - | - | - | 85 | *85.00% Satisfactory
R.V. Laborte Builders | 20459 | L | A | MB | GE1 | Const. of Lucena Diversion Rd. Talao-Talao Port Rd. inc.RROW, Mayao Crossing Sect. | Lucena City | 2013-08-03 | 1st | IVA | LF | 40.807 | 160 | 2013-06-07 | 2013-11-13 | 2.88 | O | 0.282 | 0.3 | 0.15 | 0.03 | 0.028 | 0.033 | 82.3
R.V. Laborte Builders | 20459 | L | A | MB | GE1 | Rehab./Reconst./Strengthening of Maligaya Bridge along Daang Maharlika (LZ) | Atimonan, Quezon | 2013-03-19 | Final | IVA | LF | 47.574 | 360 | 2012-02-05 | 2013-01-29 | 0 | C | 0.45 | 0.133 | 0.3 | - | - | - | 88.3 | 90.88% V. Satisfactory
R.V. Laborte Builders | 20459 | L | A | MB | GE1 | Rehab./Widening of Lucena Diversion Rd. inc. Const. of Lined Canal | Lucena City | 2013-03-16 | Final | IVA | LF | 44.346 | 258 | 2012-04-11 | 2012-12-25 | 0.87 | C | 0.452 | 0.133 | 0.3 | - | - | - | 88.5 | 87.00% Satisfactory
R.V. LABORTE BUILDERS | 20459 | L | A | MB | GE | Widening of National Roads, Arterial Roads along National Road 1 (N1), Daang Maharlika/Asia Highway-26, K0109+636 to K0110+626, Candelaria Section | Candelaria, Quezon | 2015-06-09 | 1st | Quezon 2nd DEO | LF | 43.366 | 300 | 2015-01-28 | 2015-11-23 | 10.62% | O | 0.281 | 0.3 | 0.15 | 0.03 | 0.03 | 0.033 | 82.4% | -
R.V. LABORTE BUILDERS | 20459 | L | A | MB | GE | Widening of National Roads, Arterial Roads along National Road I (NI) Daang Maharlika/Asian Highway-26 Daang Maharlika (LZ), K0 109+636 - K0 110+626, Candelaria Section | Candelaria, Quezon | 2015-09-02 | 1st | Quezon 2nd | LF | 43.366 | 270 | 2015-01-28 | 2015-10-24 | 5.15% | O | 0.36 | 0.207 | 0.15 | 0.03 | 0.03 | 0.05 | 82.7% | -
R.Z. Roncal Const. and Trading/GVDPM Const. Corp. (JV) | JV-13-559 | L | A | MA | GE | West Circumferencial Road (Friendship Highway) leading to DMIA (Angeles City Section) Angeles City, Pampanga | Angeles City | 2014-08-23 | 1st | III | LF | 101.677 | 360 | 2014-04-07 | 2015-04-01 | 0 | O | 0.388 | 0.24 | 0.102 | 0.024 | 0.056 | 0.016 | 82.6
R.Z. Roncal Construction and Trading | 22219 | L | A | MB | GE | Rehab./Reconst./Replacement/Retrofitting of Existing Permanent Bridge, Maharlika Road | Cabanatuan City, Nueva Ecija | 2014-09-26 | 1st & Final | Special 3 | LF | 44.0933 | 160 | 2014-03-23 | 2014-08-29 | 14.4 | C | 0.45 | 0.133 | 0.3 |  |  |  | 88.3 | 88.30% Satisfactory
RA Construction & General Merchandise | 33060 |  |  | SB |  | Rehabilitation of Hacienda Mimi-Ilian Communal Irrigation System | Victorias City, Negros Occidental, Region 6 | 2015-02-17 | 1st | NIA | L | 4.719 | 150 | 2014-06-04 | 2015-03-10 | 0.49 | O | 0.345 | 0.241 | 0.15 | 0.03 | 0.023 | 0.05 | 83.9 | -
Rabbit Construction & Development Corporation | 8545 | L | A | MB | GE1 | Conc. of Zamboanga City-Labuan-Limpapa Road (Upper Labuan Section) |  | 2009-09-01 | 2nd | IX |  | 18.874 | 185 |  |  |  | O | 0.366 | 0.3 | 0.15 | 0.03 | 0.06 | 0.033 | 93.9 | -
Rabbit Construction & Development Corporation | 8545 | L | A | MB | GE1 | Concreting of Zamboanga City-Labuan-Limpapa Road (Upper Labuan Section) |  | 2009-05-25 | 1st | IX |  | 18.874 | 185 |  |  |  | O | 0.343 | 0.24 | 0.15 | 0.03 | 0.056 | 0.05 | 86.9 | -
Rabbit Construction & Development Corporation | 8545 | L | A | MB | GE1 | Reconst. of Zamboanga City-Labuan-Limpapa Road |  | 2009-03-03 | 2nd | IX |  | 46.6 | 365 |  |  |  | O | 0.346 | 0.243 | 0.15 | 0.03 | 0.06 | 0.05 | #VALUE! | -
Rabbit Construction & Development Corporation | 8545 | L | A | MB | GE1 | Reconst. of Zamboanga City-Labuan-Limpapa Road |  | 2008-11-18 | 1st | IX |  | 46.6 | 365 |  |  |  | O | 0.32 | 0.3 | 0.1 | 0.03 | 0.045 | 0.1 | 89.5 | -
Rachki Enterprises | 17689 | L | D | SB | GB | Construction of 2 Storey 4 Classroom School Building at Miranda Elementary School | Talisay, Batangas | 2014-08-09 | Final | IV-A | LF | 4.7191 | 120 | 2013-03-27 | 2013-08-23 | 0 | C | 0.484 | 0.2 | 0.3 |  |  |  | 98.4 | 88.11% Satisfactory
Rachki Enterprises (Formerly: Geto Construction) | 17689 | L | D | SB | GB1 | Const. of Two (2) Storey, Four (4) Cl. Sch. Bldg. at Miranda Elem. Sch. | Talisay, Batangas | 2013-08-02 | 1st | IVA | LF | 4.719 | 150 | 2013-03-27 | 2013-08-23 | 7.02 | O | 0.333 | 0.268 | 0.15 | 0.03 | 0.023 | 0.033 | 83.7
Rachki Enterprises (Formerly: Geto Construction) | 17689 | L | D | SB | GE1 | Improvement of FMR in Sto. Niño, Pagrai, Brgy. Mayamot |  | 2009-05-18 | 1st | IV-A |  | 4.804 | 169 |  |  |  | O | 0.383 | 0.24 | 0.15 | 0.02 | 0.025 | 0.033 | 85.1 | -
Radiance Traders & Builders | 32891 | L | D | SB | GE1 | Const. of Alcala-Cabituculan East FTMR |  | 2009-09-08 | 1st | III |  | 0.936 | 118 |  |  |  | O | 0.3 | 0.3 | 0.15 | 0.03 | 0.05 | 0.033 | 86.3 | -
Radiance Traders & Builders | 32891 | L | B | SB | GE2 | Rehab. Of San Luis-Ma. Aurora-Castañeda Rd., San Luis-Ma. Aurora-Castañeda | Aurora | 2012-11-27 | 1st | III | LF | 10.459 | 150 | 2012-07-12 | 2012-12-08 | 0.8 | O | 0.234 | 0.3 | 0.15 | 0.03 | 0.058 | 0.05 | 82.2 | -
RADIANCE TRADERS & BUILDERS | 32891 | L | B | SB | GB | Construction of Multi-Purpose Building, Sitio Curva, Brgy. Suklayin, Baler, Aurora | Baler, Aurora | 2015-06-10 | Final | Aurora DEO | LF | 7.029 | 225 | 2014-08-18 | 2015-03-28 | 0% | C | 0.466 | 0.2 | 0.3 | - | - | - | 96.6% | *96.6% Outstanding
Raf General Construction | 6699 | L | B | MA | GE | Preventive Maintenance of National Road, Abra - Kalinga Road, K046+369 - K0427+730, Poblacion and Laang, Lagangilang, Abra | Poblacion and Laang, Lagangilang, Abra | 2014-08-11 | 1st & Final | CAR | LF | 19.0698 | 76 | 2014-02-07 | 2014-04-03 | 0 | C | 0.444 | 0.133 | 0.3 |  |  |  | 87.7 | 87.70% Satisfactory
Raf General Construction | 6699 | L | B | MA | GE1 | Replacement of Bontoc-Cadre Bridge along Bontoc-Cadre Rd. | Bontoc, Mt. Province | 2013-08-03 | Final | CAR | LF | 8.598 | 177 | 2012-03-09 | 2012-09-01 | 0 | C | 0.472 | 0.133 | 0 | - | - | - | 60.5 | 65.30% Poor
Raf General Construction | 6699 | L | B | MA | GE1 | Replacement of Bontoc-Cadre Bridge along Bontoc-Cadre Rd. | Bontoc, Mountain Province | 2012-11-23 | 1st | CAR | LF | 8.271 | 120 | 2012-03-09 | 2012-07-06 | - | O | 0.299 | 0.3 | 0 | 0.02 | 0.033 | 0.033 | 68.5 | -
RAF GENERAL CONSTRUCTION | 6699 | L | B | SB | GE | Rehabilitation of Water System | Poblacion North, Lagawa, Ifugao | 2015-06-07 | 1st | Ifugao 1st DEO | LF | 1.857 | 120 | 2015-04-15 | 2015-08-12 | (+) 0.24% | O | 0.245 | 0.24 | 0.15 | 0.03 | 0.047 | 0.05 | 76.2% | -
RAF General Construction/Jaben General Contracting & Eng'g. Services (JV) | JV-13-263 | L | B | MA | GE | Road Upgrading of Mt. Province-Cagayan via Tabuk-Enrile Road, KO396+812 - KO396+889, KO397+655 - KO397+704, KO397+806 - KO397+818, KO398+571 - KO397+576, KO398+693 - KO398+744, KO 399+136 - KO399+225, KO410+646 - KO410+736, KO411+324 - KO411+430 | Mt. Province | 2014-11-22 | 1st | CAR | LF | 14.7245 | 265 | 2014-05-19 | 2015-02-07 | -20.66% | O | 0.362 | 0.265 | 0 | 0.03 | 0.055 | 0.033 | 74.5% | 74.5% Poor
RAF GENERAL CONSTRUCTION/JABEN GENERAL CONTRACTING & ENGINERING SERVICES (JV) | - | - | - | - | GE | Road Upgrading of Mt. Province-Cagayan via Tabuk-Enrile Road, K0396+812 - K0396+889, K0397+655 - k0397+704, K0397+806 - K0397+818, K0398+571 -K0398+576, K0398+744, K0399+136 - K0399+225, K0410+736, K0411+324 - K0411+430 | Bontoc & Sagada, Mt. Province | 2015-06-05 | 2nd | CAR | LF | 14.724 | 422 | 2014-05-19 | 2015-07-14 | (-) 0.50% | O | 0.361 | 0.3 | 0.145 | 0.015 | 0.028 | 0.033 | 88.2% | -
RAMARPLUS INCORPORATED | 8092 | L | B | MA | GE | Construction/ Upgrading/ Rehabilitation of Drainage along National Roads, Polangui Poblacion Road, K0491+(-419) - K0491+1150 | Polangui, Albay | 2015-06-03 | 1st | Albay 3rd | LF | 18.252 | 210 | 2015-02-09 | 2015-09-06 | 0% | O | 0.399 | 0.231 | 0.15 | 0.023 | 0.051 | 0.033 | 88.7% | -
Ramarplus Incorporated (Formerly: Ramar Enterprises) | 8092 | L | B | MA | GE | Construction of Dike at Left Quintal River | Libon, Albay | 2014-08-16 | 1st | V | LF | 46.0654 | 248 | 2014-01-17 | 2014-09-21 | 5.14 | O | 0.337 | 0.3 | 0.15 | 0.02 | 0.03 | 0.05 | 88.7
Ramises Construction | 17351 | L | C | SB | GE | Rehabilitation/Reconstruction/Replacement/Retrofitting of Doongan Bridge along Butuan City - Masao Port Road Jct. Doongan Bridge | Butuan City | 2014-10-29 | 1st & Final | XIII | LF | 4.4581 | 78 | 2014-02-14 | 2014-05-02 | 15% | C | 0.483 | 0.133 | 0.3 | - | - | - | 91.6% | 91.6% Very Satisfactory
Ramona Construction & Enterprises | 14661 | L | B | MA | GE1 | Road Upgrading (Gravel to Paved) Int. Sect. Jct. Blancia-Molave-Josefina Rd., Km.1682+460-K1683+000 | Zamboanga del Sur | 2013-03-21 | 1st | IX | LF | 18.042 | 100 | 2013-02-18 | 2013-05-02 | 2.66 | O | 0.367 | 0.225 | 0.15 | 0.03 | 0.032 | 0.05 | 85.4 | -
RAMONA CONSTRUCTION & ENTERPRISES | 14661 | L | B | MA | GE | Construction of Local Roads at the Municipality of Diplahan; Sungcuya - Paradise, Diplahan, Zamboanga Sibugay | Diplahan, Zamboanga Sibugay | 2015-06-08 | Final | Zamboanga Sibugay 1st DEO | LF | 1.968 | 75 | 2014-05-30 | 2014-08-12 | 0.2% | C | 0.467 | 0.135 | 0.3 | - | - | - | 90.2% | *90.2% Very Satisfactory
RAMONA CONSTRUCTION & ENTERPRISES | 14661 | L | B | MA | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads Including Drainage Based on Pavement Management System/Highway Development & Management-4 (HDM-4), Ozamiz-Oroquieta Rd, K1703+000-K1703+680; K1705+011-K1706+217; K1708+614-K1709+002 | Ozamiz-Oroquieta Rd, K1703+000-K1703+680; K1705+011-K1706+217; K1708+614-K1709+002 | 2015-06-05 | 1st | Misamis Occidental Second DEO | LF | 36.369 | 160 | 2015-02-27 | 2015-08-05 | - | O | 0.344 | 0.292 | 0.15 | 0.024 | 0.05 | 0.05 | 91% | -
RAMONA CONSTRUCTION & ENTERPRISES | 14661 | L | B | SB | GE | Construction/Maintenance of Flood Mitigation Structures and Drainage System, Usugan, Tambulig, Zamboanga del Sur | Usugan, Tambulig, Zamboanga del Sur | 2015-08-29 | 1st & Final | Zamboanga del Sur 1st | LF | 9.106 | 138 | 2015-04-13 | 2015-08-28 | - | C | 0.36 | 0.2 | 0.3 | - | - | - | 86% | *86% Satisfactory
RAMONA CONSTRUCTION & ENTERPRISES | 14661 | L | B | SB | GB | Construction of Senior High School Classroom, Tabid NHS, Tabid, Ozamis City | Tabid, Ozamis City | 2015-11-19 | 1st | Misamis Occidental 2nd | LF | 8.0183 | 150 | 2015-08-31 | 2016-01-28 | (+) 4.34% | OG | 0.368 | 0.24 | 0.15 | 0.03 | 0.058 | 0.033 | 87.9% | 87.9% Satisfactory
Ramsa Construction | 25580 | L | B | SB | GE1 | Repair/Rehab./Impvt. of MNR Km. 426+800-Km. 429+058 w/ exceptions | Ilocos Sur | 2013-07-13 | Final | I | LF | 4.937 | 90 | 2013-01-28 | 2013-04-27 | 2.22 | C | 0.452 | 0.133 | 0.3 | - | - | - | 88.5 | 86.94% Satisfactory
Ramsa Construction | 25580 | L | B | SB | GE1 | Repair/Rehab./Impv't. of MNR, Km.426+800-Km.429+058 w/ exceptions | Ilocos Sur | 2013-03-20 | 1st | I | LF | 4.938 | 90 | 2013-01-28 | 2013-04-27 | 0.09 | O | 0.396 | 0.225 | 0.15 | 0.015 | 0.04 | 0.033 | 85.9 | -
Ramsa Construction | 25580 |  |  |  |  | Impvt. of DPWH Ilocos Sur 1st DEO Building |  | 2010-05-29 |  | I |  | 4.756 | 250 |  |  |  | O | 0.364 | 0.24 | 0.15 | 0.022 | 0.029 | 0.033 | 83.8 | -
Rania Construction & Supplies | 34064 | L |  | MA | GE2 | Construction of Lateral "A" at Sta. 5+510.80 Sta 5+729.24 of Laris (Class A Rectangular Canal Lining) | Rosales, Pangasinan Region I | 02/27-03/03/12 | 1st | NIA | FA | 3.604 | 60 | 2011-11-21 | 2012-01-19 | 2.32 | O | 0.334 | 0.3 | 0.15 | 0.03 | 0.047 | 0.05 | 91.1 | -
Rania Construction & Supplies |  |  |  | MA |  | Soriano Communal Irrigation System | Mangatarem, Pangasinan, Region 1 | 2015-01-27 | 1st | NIA | L | 9.507 | 120 | 2014-02-13 | 2014-06-22 | 8.67 | O | 0.25 | 0.3 | 0.15 | 0.03 | 0.06 | 0.05 | 84 | -
Rania Construction & Supplies |  |  |  | MA |  | Soriano Communal Irrigation System | Mangatarem, Pangasinan, Region 1 | 2015-01-27 | 1st | NIA | L | 9.65 | 120 | 2014-02-13 | 2015-02-26 | 6.06 | O | 0.26 | 0.3 | 0.15 | 0.03 | 0.06 | 0.05 | 85 | -
Rapid Foremost Const. Co. | 32618 | L | C | SB | GE1 | Replacement/Rehab./Strengthening of Permanent Bridges: 2. Binahaan Bridge along Daang Maharlika | Quezon | 2013-03-18 | 1st | IVA | LF | 4.585 | 79 | 2013-02-22 | 2013-05-11 | 26.98 | O | 0.338 | 0.24 | 0.15 | 0.03 | 0.042 | 0.033 | 83.3 | -
Rapid Foremost Const., Co. | 32618 | L | C | SB | GE1 | Replacement/Rehab./Strengthening of Permanent Bridges Gen. from Bridge Mgt. System (BMS) 2. Binahaan Bridge along Daang Maharlika | Quezon | 2013-08-05 | Final | IVA | LF | 4.585 | 170 | 2013-02-22 | 2013-08-10 | 3 | C | 0.456 | 0.133 | 0.3 | - | - | - | 88.9 | 85.54% Satisfactory
RAQI Builders Construction & Supply | 27032 | L | D | SB | GE | Construction/ Rehabilitation of Drainage/Protection Works along National Roads and Bridges, Flood Control along Isulan Highway Junction Dukay-Bagumbayan Section-Sen. Ninoy Aquino Road | Bagumbayan, Sultan Kudarat | 2014-10-27 | 1st & Final | XII | LF | 2.2726 | 150 | 2014-02-17 | 2014-07-16 | 0% | C | 0.478 | 0.133 | 0.3 | - | - | - | 91.1% | 91.1% Very Satisfactory
RAQI Builders Construction & Supply | 27082 | L | D | SB | GB | Construction of Water Sanitation Facilities, Koronadal NCHS | Koronadal City | 2014-08-05 | 1st & Final | XII | LF | 3.9839 | 155 | 2013-10-07 | 2014-03-10 | 0 | C | 0.494 | 0.133 | 0.3 |  |  |  | 92.7 | 92.70% Very Satisfactory
RB Soriano Construction | 22635 |  |  |  |  | Thermal Moisture Protection (Re-roofing & Waterproofing) |  | 2010-08-26 |  | U.P Manila |  | 2.011 | 90 |  |  |  | O | 0.35 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 87 | -
RC Tagala Construction | 11597 | L | A | MB | GE-5 | Alcantara Port Development Project | Alcantara, Aromblon/ Region IV-B | 2014-10-22 | 1st & Final | DOTC | LF | 4.482 | 120 | 2014-03-03 | 2014-06-30 | 0 | C | 0.4149 | 0.2 | 0.3 | - | - | - | 91.49 | *91.49% V. Satisfactory
RC Tagala Construction | 11597 | L | A | MB | GE-5 | Culasi Port Development Project | Poblacion, Culasi, Antique/ Region VI | 2014-09-25 | 1st | DOTC | LF | 21.002 | 210 | 2014-03-17 | 2014-11-26 | -1.55 | O | 0.333 | 0.3 | 0.1345 | 0.02 | 0.035 | 0.0166 | 83.91 | -
RC Tagala Construction | 11597 | L | A | MB |  | Azagra Port Development Project | Brgy. Azagra, San Fernando, romblon/ Region IV-B | 2016-04-07 | 1st & Final | DOTC | LF | 13.217 | 247 | 2014-03-03 | 2014-11-04 | -193.52 | C | 0.5 | 0.2 | 0 | - | - | - | 70 | *70.00% Poor
RCDG CONSTRUCTION CORP/ KENT MARKETING GROUP OF COMPANIES INC. JOINT VENTURE | JV-14-448 | L | AAA | MB | GE | Construction of Surigao del Norte Provincial Hospital, A. Medical Arts Building | Placer, Surigao del Norte | 2015-09-01 | 1st | Regional Office No. XIII | LF | 19.795 | 345 | 2015-02-06 | 2016-01-16 | (+) 0.85% | O | 0.36 | 0.24 | 0.15 | 0.03 | 0.047 | 0.05 | 87.7% | -
RCDG Construction Corporation | 5063 | L | AA | MB | GE | Road Rehabilitation (Asphalt Overlay with Pavement Markings) at Barangay Sta. Catalina | Zamboanga City | 2014-10-21 | 1st & Final | IX | LF | 3.8866 | 103 | 2014-04-23 | 2014-08-03 | 0% | C | 0.448 | 0.127 | 0.3 | - | - | - | 87.5% | 87.5% Satisfactory
RCDG Construction Corporation | 5063 | L | AA | MB | GE | Road Rehabilitation | Sta. Catalina, Zamboanga City | 2014-08-05 | 1st & Final | IX | LF | 3.8866 | 103 | 2014-04-23 | 2014-08-03 | 0 | C | 0.471 | 0.2 | 0.3 |  |  |  | 97.1 | 97.10% Outstanding
RCDG CONSTRUCTION CORPORATION | 5063 | L | AA | MB | GE | Road Rehabilitation, Brgy. Talon - Talon, Zamboanga City | Zamboanga City | 2015-06-11 | Final | Zamboanga City DEO | LF | 4.132 | 98 | 2014-04-23 | 2014-07-29 | 0% | C | 0.451 | 0.133 | 0.3 | - | - | - | 88.4% | *88.4% Satisfactory
RCDG CONSTRUCTION CORPORATION | 5063 | L | AA | MA | GE | Construction/Rehabilitation of Drainage System along B. Serrano Avenue Extension (Katipunan Ave, Marikina Bdry), Quezon City 3rd LD | Quezon City 3rd LD | 2015-08-26 | 1st | QC 2nd DEO | LF | 3.604 | 120 | 2015-03-27 | 2015-07-24 | -8.25% | O | 0.343 | 0.3 | 0.068 | 0.03 | 0.055 | 0.05 | 84.6% | -
RCDG CONSTRUCTION CORPORATION | 5063 | L | AA | MB | GE | Road Upgrading (Gravel to Paved) of Crossing Sta. Clara-Sandayong Road, K1789+117.19-K1789+237, K1789+237-K1810+517.70(Intermittent Sections), Zamboanga Sibugay | Zamboanga Sibugay | 2015-08-24 | 1st | Regional Office No. IX | LF | 92.445 | 267 | 2015-03-18 | 2015-12-10 | - | O | 0.318 | 0.24 | 0.15 | 0.022 | 0.06 | 0.05 | 84% | -
RCDG Construction Corporation / Badsbro Construction and General Merchandise (Joint Venture) | JV-12-029 | L | AA | MA | GE2 | Const./Impv't. of Lower Sibuguey Flood Protection along Lanao-Pagadian-Zamboanga City Rd., Kimus-Balucanan Sect., Phase I, Km.0+000-Km.2+240 | Zamboanga, Sibugay | 2013-03-15 | 2nd | IX | LF | 36.813 | 260 | 2012-07-23 | 2013-04-08 | 7 | O | 0.381 | 0.24 | 0.15 | 0.03 | 0.033 | 0.05 | 88.4 | -
RCDG Construction Corporation / Badsbro Construction and General Merchandise (JV) | JV-12-029 | L | AA | MA | GE1 | Const./Imprv't. of Lower Sibuguey Flood Protection along Lanao-Pagadian-Zamboanga City Rd., Kimus-Balucanan Sect., Phase I, Km.0+000-Km.2+240 | Zamboanga Sibugay | 2013-08-08 | Final | IX | LF | 37.564 | 275 | 2012-07-23 | 2013-04-23 | 0 | C | 0.312 | 0.2 | 0.3 | - | - | - | 81.2 | 85.61% Satisfactory
RCDG Construction Corporation / Badsbro Construction and General Merchandise (JV) | JV-12-029 | L | AA | MA | GE2 | Const./Impvt. of Lower Sibuguey Flood Protection along Lanao-Pagadian-Zamboanga City Rd., Kimus-Balucanan Sect., Phase 1, Km.0+000-Km.2+240 | Zamboanga Sibugay | 2012-11-26 | 1st | IX | LF | 36.813 | 230 | 2012-07-23 | 2013-03-09 | 0 | O | 0.349 | 0.254 | 0.15 | 0.03 | 0.054 | 0.05 | 88.7 | -
RCDG Construction Corporation and DSB Construction & Supply Inc. | [5 empty] | Rehabilitation and Development of Pasong Tamo Creek Package 1 (Sta. 3+346 to 4+529= 1,183LM) | Pasong Tamo Creek, City of Quezon | 2016-03-18 | 1st & Final | PRRC | LF | 12.844 | 120 | 2013-06-03 | 2015-01-12 | 0 | C | 0.342 | 0.182 | 0.3 | - | - | - | 82.4 | *82.40% Satisfactory
RCDS CONSTRUCTION & SUPPLY, INC. (Formerly RCDS Construction & Supply) | 32331 | L | B | MA | GE | Improvements of Road Leading to Kawa-Kawa Natural Park, Ligao City, Sta. 0+000-Sta. 0+960/Sta. 0+000-Sta. 0+866, Ligao City | Ligao City | 2015-08-26 | 1st | Albay Third DEO | LF | 12.492 | 210 | 2015-04-03 | 2015-10-29 | 0.09% | O | 0.382 | 0.24 | 0.15 | 0.03 | 0.06 | 0.05 | 91.2% | -
RCDS Construction & Supply, Inc. (Formerly: RCDS Construction and Supply) | 32331 | L | B | MA | GE | Preventive Maintenance along Danao-Pasacao Road | Pamplona, Camarines Sur | 2014-08-07 | 1st & Final | V | LF | 9.3807 | 50 | 2014-02-20 | 2014-04-10 | 2.09 | C | 0.432 | 0.133 | 0.3 |  |  |  | 86.5 | 86.50% Satisfactory
RCDS Construction & Supply, Inc. (Formerly: RCDS Construction and Supply) | 32331 | L | B | MA | GE | Widening of DM Jct.-Legazpi-Sto. Domingo-Tabaco-Tiwi-Cam Sur Bdry. Road, Tabaco Section, K0553+660 - K0554+600 | Tabaco City, Albay | 2014-08-04 | 1st | V | LF | 20.6945 | 189 | 2014-03-03 | 2014-09-07 | -10.73 | O | 0.352 | 0.3 | 0.043 | 0.022 | 0.051 | 0.033 | 80.1
RCDS CONSTRUCTION & SUPPLY, INC. (Formerly: RCDS Construction and Supply) | 32331 | L | B | MA | GE | Widening of DM Jct. - Legazpi - Sto. Domingo - Tabaco - Tiwi - Cam Sur Boundary Road , Tabaco Sectio, K0553+660 to K0554+600 | Tabaco City | 2015-06-01 | Final | Albay 1st | LF | 20.695 | 219 | 2014-03-03 | 2014-10-07 | 0% | C | 0.465 | 0.144 | 0.3 | - | - | - | 90.9% | *84.5% Satisfactory
R'Cel Gen. Contractor & Gen. Merchandise | 13385 | L | B | MA | GE1 | Replacement/Rehab./Strengthening of Permanent Bridges Gen. from Bridge Mgt. System (BMS) 3. Gumihan Bridge along Quirino Highway | Quezon | 2013-08-06 | 2nd | IVA | LF | 14.38 | 220 | 2013-02-12 | 2013-09-19 | 0.43 | O | 0.26 | 0.292 | 0.15 | 0.03 | 0.04 | 0.033 | 80.5
R'Cel Gen. Contractor & Gen. Merchandise | 13385 | L | B | MA | GE1 | Replacement/Rehab./Strengthening of Permanent Bridges; 3. Gumihan Bridge along Quirino H-way | Quezon | 2013-03-19 | 1st | IVA | LF | 14.38 | 80 | 2013-02-12 | 2013-05-02 | -0.42 | O | 0.278 | 0.245 | 0.146 | 0.03 | 0.065 | 0.033 | 79.7 | -
R'Cel Gen. Contractor & Gen. Merchandise | 13385 | L | B | MA | GE1 | Widening of Bridges along Nat'l. Rds., Liliw Bridge along San Pablo-Nagcarian-Liliw Rd., Km.100+420 | Laguna | 2013-03-15 | Final | IVA | LF | 12.652 | 215 | 2012-02-23 | 2012-09-24 | 0 | C | 0.445 | 0.133 | 0 | - | - | - | 57.8 | 75.44% Unsatisfactory
R'cel Gen. Contractor & Gen. Merchandise | 13385 | L | B | MA | GE1 | Widening of Bridges along Nat'l Rds., Liliw Bridge along San Pablo-Rizal-Nagcarlan-Liliw Rd., Km.100+420 | Liliw, Laguna | 2012-11-28 | 1st | IVA | LF | 12.652 | 215 | 2012-02-23 | 2012-09-24 | -14.72 | O | 0.319 | 0.285 | 0.15 | 0.03 | 0.055 | 0.033 | 87.2 | -
R'Cel Gen. Contractor & Gen. Merchandise | 13385 | L | B | MA | GE1 | Widening of Bridges along Nat'l. Rds., Oples Bridge along San Pablo-Rizal-Nagcarlan-Liliw Rd., Km.99+620 | Laguna | 2013-03-15 | Final | IVA | LF | 12.641 | 215 | 2012-02-23 | 2012-09-24 | - | C | 0.448 | 0.133 | 0 | - | - | - | 58.1 | 74.90% Poor
R'cel Gen. Contractor & Gen. Merchandise | 13385 | L | B | MA | GE1 | Widening of Bridges along Nat'l Rds., Oples Bridge along San Pablo-Rizal-Nagcarlan-Liliw Rd., Km.99+620 | Liliw, Laguna | 2012-11-28 | 1st | IVA | LF | 12.641 | 215 | 2012-02-23 | 2012-09-24 | -22.17 | O | 0.314 | 0.284 | 0.15 | 0.03 | 0.05 | 0.033 | 86.1 | -
R'Cel Gen. Contractor & Gen. Merchandise | 13385 | L | B | MA | GE1 | Rehab./Reconst./Strengthening of Bridges along Nat'l. Rd.s Inalakan Bridge along Daang Maharlika (L2) | Lopez, Quezon | 2013-03-19 | Final | IVA | LF | 7.642 | 180 | 2012-01-27 | 2012-07-24 | 0 | C | 0.475 | 0.133 | 0.3 | - | - | - | 90.8 | 87.02% Satisfactory
R'Cel Gen. Contractor & Gen. Merchandise | 13385 | L | B | MA | GE1 | Widening of Daang Maharlika K0085+304.43-K0091+518 (Intermittent Sect.) | San Pablo, Laguna | 2013-03-15 | Final | IVA | LF | 45.23 | 274 | 2012-02-21 | 2012-11-20 | - | C | 0.426 | 0.133 | 0 | - | - | - | 55.9 | 70.21% Poor
R'cel Gen. Contractor & Gen. Merchandise | 13385 | L | B | MA | GE1 | Widening of Daang Maharlika, K0085+304.43-K0091+518 (IS) | San Pablo City, Laguna | 2012-11-29 | 2nd | IVA | LF | 45.23 | 274 | 2012-02-21 | 2012-11-20 | - | O | 0.331 | 0.3 | 0 | 0.03 | 0.05 | 0.033 | 74.4 | -
R'cel Gen. Contractor & Gen. Merchandise | 13385 | L | B | MA | GE1 | Widening of Daang Maharlika Highway K0085+304.43-K0091+518 (IS) | Laguna | 2012-08-08 | 1st | IVA | LF | 45.23 | 250 | 2012-02-21 | 2012-10-27 | -3.86 | O | 0.332 | 0.3 | 0.111 | 0.03 | 0.045 | 0.033 | 85.1 | -
R'cel Gen. Contractor & Gen. Merchandise | 13385 | L | B | MA | GE | Paving of Shoulders (Seal Widening) along Calamba-Sta. Cruz-Famy Jct. Road, Lumban Section | Lumban, Laguna | 2014-11-26 | 1st & Final | IV | LF | 5.297 | 70 | 2014-01-23 | 2014-04-02 | - | C | 0.459 | 0.2 | 0.3 | - | - | - | 95.9% | 95.9% Very Satisfactory
R'CEL GEN. CONTRACTOR & GEN. MERCHANDISE | 13385 | L | B | MA | GB | Construction/Repair/Rehabilitation of Multi Purpose Building | Brgy. Malinao, Sta. Cruz, Laguna | 2015-06-07 | Final | Laguna 1st DEO | LF | 1.802 | 90 | 2015-02-12 | 2015-05-12 | 0% | C | 0.49 | 0.122 | 0.3 | - | - | - | 91.2% | *91.2% Very Satisfactory
R'CEL GEN. CONTRACTOR & GEN. MERCHANDISE | 13385 | L | B | MA | GE | Construction and Maintenance of Bridges along National Roads - Rehabilitation/Major Repair of Permanent Bridges, Cavinti Bridge 1 (B02495LZ) along Cavinti - Caliraya Road | Laguna Province | 2015-06-07 | 1st | Laguna 1st DEO | LF | 14.179 | 192 | 2015-03-18 | 2015-09-25 | 8.34% | O | 0.4 | 0.205 | 0.15 | 0.03 | 0.035 | 0.033 | 85.3% | -
RCM CONSTRUCTION & SUPPLIES | 32623 | L | D | SB | GE | Construction of Flood Control, San Jose Gusu Creek, Baliwasan Side, Baliwasan Zamboanga City | Baliwasan Zamboanga City | 2015-11-19 | Final | Zamboanga City DEO | LF | 1.4176 | 75 | 2015-08-17 | 2015-10-30 | 6.67% | C | 0.4 | 0.133 | 0.3 | - | - | - | 83.3% | 83.3% Satisfactory
RCM CONSTRUCTION & SUPPLIES | 32623 | L | D | SB | GB | Construction of One(1) Unit, Two (2) Storey, Six (6) Classroom School Building (7mx9m) at Tampilisan NHS, Tampilisan, Zamboanga del Norte | Tampilisan, Zamboanga del Norte | 2015-11-17 | 1st | Zamboanga Del Norte 2nd DEO | LF | 7.9087 | 150 | 2015-09-21 | 2016-02-17 | 3.16% | OG | 0.346 | 0.24 | 0.15 | 0.015 | 0.032 | 0.05 | 83.3% | 83.3% Satisfactory
RCPS CONSTRUCTION & GENERAL TRADING | 17792 | L | B | SB | GE | Local Infrastructure Program - Concreting of Barangay Road, Barangay Burgos, Alicia, Isabela | Alicia, Isabela | 2015-08-29 | 1st & Final | Isabela 3rd DEO | LF | 4.801 | 65 | 2015-02-17 | 2015-04-22 | 0% | C | 0.434 | 0.135 | 0.3 | - | - | - | 86.9% | *86.9% Satisfactory
RCPS Construction & General Trading | 17792 | L |  | SB | GE2 | Improvement of Minante Checkgate, Supply Canal Protection | MARIIS Division IV | 2012-07-27 | 1st | NIA | LF | 1.766 | 60 | 2012-03-20 | 2012-05-24 | -5 | O | 0.3851 | 0.2274 | 0.1 | 0.03 | 0.07 | 0.05 | 86.25 | -
RDen Construction & Supply | 33707 | L | D | SB | GE | Concreting of Roads, Poblacion to Buluan, Pob. 1 - Front of Brgy. Hall and Concreting of Manuangan - Malu - oa Road, Pigcawayan, Cotabato | Pigcawayan, Cotabato | 2014-10-25 | 1st & Final | XII | LF | 5.64 | 42 | 2014-05-27 | 2014-07-07 | 0% | C | 0.475 | 0.133 | 0.3 | - | - | - | 90.8% | 90.8% Very Satisfactory
RDen Construction & Supply | 33707 | L | D | SB | GE1 | Const. of FMR, Lower Baguer, Impv't. of FMR, Libungan, Cotabato, K1705+176-K1706+340 end of Proj. K1705+176.50-K1706.50 (PCCP) (1.1635kms.) | Libungan, Cotabato | 2013-08-13 | Final | XII | LF | 7.374 | 57 | 2013-02-06 | 2013-04-03 | 0 | C | 0.395 | 0.2 | 0.3 | - | - | - | 89.5 | 87.10% Satisfactory
RDEN CONSTRUCTION & SUPPLY | 33707 | L | D | SB | GE | Road Concreting | Datu Piang-Poblacion 4, Poblacion 7 Street, Poblacion, Midsayap, Cotabato | 2015-06-06 | Final | Cotabato 2nd DEO | LF | 5.527 | 46 | 2015-02-20 | 2015-04-07 | 0% | C | 0.463 | 0.133 | 0.3 | - | - | - | 89.6% | *89.6% Very Satisfactory
RDen Construction & Supply | 33707 | L | D | SB | GE1 | Const. of FMR, Lower Baguer, Impv't. of FMR, K1705+176-K1706+340 end of proj. K1705+176.50-K1706.50 (PCCP) (1,163.5 kms.) | Libungan, Cotabato | 2013-03-16 | 1st | XII | LF | 7.374 | 57 | 2013-02-06 | 2013-04-03 | 3.78 | O | 0.34 | 0.235 | 0.15 | 0.03 | 0.05 | 0.05 | 85.5 | -
RDen Construction & Supply / ACJ Construction Resources (JV) | JV-11-291 | L | B | MA | GE1 | Conc. of Rd. along Banisilan-Guiling-Alamada-Libungan Rd., Tuasi-Barangiran Sect., Barangiran | Alamada, Cotabato | 2013-03-16 | Final | XII | LF | 40.065 | 260 | 2012-02-07 | 2012-10-24 | 2.69 | C | 0.391 | 0.133 | 0.3 | - | - | - | 82.4 | 85.58% Satisfactory
RDF CONSTRUCTION AND SUPPLY | 12843 | L | D | SB | GB | Completion of Multi-Purpose Building | Brgy. Naboc, Monkayo, Comval Province | 2015-06-09 | Final | Compostela Valley | LF | 0.737 | 60 | 2015-03-09 | 2015-05-07 | 0% | C | 0.434 | 0.092 | 0.3 | - | - | - | 82.6% | *82.6% Satisfactory
RDG CONSTRUCTION & SUPPLY (Formerly: RDG Construction) | 19488 | L | B | MA | GE | Improvement/Rehabilitation of Elpidio Quirino, Camus St., Legaspi St. Drainage, Davao City | Davao City | 2015-11-19 | 1st | Davao City 1st DEO | LF | 2.8444e-05 | 204 | 2015-06-30 | 2016-01-19 | 0.0005 | OG | 0.367 | 0.24 | 0.15 | 0.03 | 0.07 | 0.033 | 89% | 89% Satisfactory
RDG Construction and Supply | 19388 | L |  | SB | GE-5 | Rehabilitation and Minor Improvement Works of Km.15 Kipalili-New Loon Road | Asuncion and San Isidro, Davao del Norte | 2015-06-10 | 3rd & Final | Davao Del Norte | LF | 12.862 | 155 | 2014-12-12 | 2015-05-15 | 0 | C | 0.4539 | 0.0872 | 0.3 | - | - | - | 84.11 | 84.16% Satisfactory
RDG Construction and Supply | 19388 | L |  | SB | GE-5 | RMI of Km.15 Kipalili-New Loon road | Asuncion, Davao del Norte | 2015-05-06 | 2nd | Davao Del Norte | LF | 12.909 | 155 CD | 2014-12-12 | 2015-05-15 | -4.8 | O | 0.364 | 0.283 | 0.136 | 0.03 | 0.044 | 0.033 | 89 | -
RDG Construction and Supply | 19388 | L |  | SB | GE-5 | RMI of Km.15 Kipalili-New Loon road | Asuncion and San Isidro, Davao del Norte | 2015-04-21 | 1st | Davao Del Norte | LF | 12.909 | 155 | 2014-12-12 | 2015-05-15 | -6.42 | O | 0.3691 | 0.2213 | 0.0848 | 0.03 | 0.04 | 0.05 | 79.52 | -
RDG Construction and Supply | 19488 | L | B | SB | GE2 | Sirawan (CARFA) SIP | Poblacion Calinan, Davao City/Region XI | 2013-06-01 | 1st | NIA | L | 13.131 | 120 | 2013-02-05 | 2013-06-03 | 5.7 | O | 0.3891 | 0.24 | 0.15 | 0.03 | 0.0513 | 0.05 | 91.04 | -
Readycon Trading & Construction Corporation | 15452 | L | AAA | LB | GE1 | Asphalt Overlay of Batangas-Quezon Rd. a)San Ignacio, Rosario Sect. (K0126+249-K0127+000) b)Ibaan Sect. (K0127+963-K0131+163) | Batangas | 2013-03-11 | 1st | IVA | LF | 23.883 | 75 | 2013-01-14 | 2013-03-29 | 35.86 | O | 0.385 | 0.3 | 0.15 | 0.03 | 0.05 | 0.033 | 94.8 | -
Regg's Builders / Mar-deb Construction & Development (Joint Venture) | JV-12-035 | L | A | MA | GE2 | Repair/Restoration of Rang-ay Flood Control, Sta.000+000-Sta.000+220 | San Agustin, Isabela | 2013-03-15 | Final | II | LF | 15.52 | 165 | 2012-08-10 | 2013-01-22 | 0 | C | 0.436 | 0.149 | 0.3 | - | - | - | 88.5 | 87.36% Satisfactory
Regional Infrastructure Development Corporation | 26373 |  |  |  |  | Rehab./Gravelling of NRJ Karaos-Lapag-Sumogbong Rd. |  | 2010-03-07 |  | XIII |  | 2.354 | 105 |  |  |  | O | 0.384 | 0.228 | 0.15 | 0.03 | 0.042 | 0.033 | 86.7 | -
Regional Infrastructure Development Corporation | 26373 | L | A | MA | GE1 | Const. of Earth Canal at Talacogon-La Paz Road, along Circumferential Road |  | 2009-03-17 | 1st | XIII |  | 3.733 | 120 |  |  |  | O | 0.333 | - | 0.2 | 0.05 | 0.04 | 0.25 | #VALUE! | -
Regional Infrastructure Development Corporation | 26373 | L | A | MA | GE1 | Concreting of Sta. Josefa Bdry.-Veruela Sect. along National Secondary Rd. |  | 2009-09-14 | 1st | XIII |  | 4.764 | 145 |  |  |  | O | 0.376 | 0.225 | 0.139 | 0.03 | 0.065 | 0.033 | 86.8 | -
Regional Infrastructure Development Corporation | 26373 | L | A | MA | GE1 | Conc. of NRJ-Calaitan-Tandag Rd. (Calaitan Sect.) |  | 2009-09-14 | 1st | XIII |  | 9.621 | 195 |  |  |  | O | 0.346 | 0.248 | 0.15 | 0.03 | 0.055 | 0.033 | 86.2 | -
Rely Construction & Supply | 10433 | L | AA | MA | GE | Upgrading of Road Surfaces along Asuncion - San Isidro - Laak - Veruel Road, Sagayen Section, Km. 1481+380 - Km. 1483+500 with exception | Davao del Norte | 2014-10-24 | 1st | XI | LF | 21.3385 | 135 | 2013-09-23 | 2014-02-04 | 19.44% | O | 0.366 | 0.162 | 0.3 |  |  |  | 82.8% | 82.8% Satisfactory
Rely Construction & Supply | 10433 | L | AA | MA | GE1 | Conc. of Juction Lingig-Trento Road |  | 2009-03-14 | 2nd | XIII |  | 28.878 | 230 |  |  |  | O | 0.329 | 0.3 | 0.15 | 0.03 | 0.037 | 0.05 | #VALUE! | -
Rely Construction & Supply | 10433 | L | AA | MA | GE1 | Conc. of Juction Lingig-Trento Road |  | 2008-11-27 | 1st | XIII |  | 28.878 | 230 |  |  |  | O | 0.342 | 0.212 | 0.1 | 0.03 | 0.043 | 0.1 | 82.7 | -
Rely Construction & Supply | 10433 | L | AA | MA | GE1 | Impv't/Widening of Agusan-Davao Road, Daang Maharlika, Pob. Carmen and Pob. Panabo |  | 2009-03-13 | 1st | XI |  | 38.575 | 270 |  |  |  | O | 0.337 | 0.252 | 0.15 | 0.03 | 0.043 | 0.05 | #VALUE! | -
Rely Construction and Supply | 10433 | L | AAA | MA | GE | Road Upgrading (Gravel to Paved) based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standard (HDM-4 Project Analysis) Intermittent Section, Improvement/Widening of Daang Maharlika Road K1501+561 - K1501+400 | Davao City | 2014-08-15 | 1st | XI | LF | 33.622 | 155 | 2014-02-10 | 2014-07-14 | 0.04 | O | 0.463 | 0.2 | 0.15 | 0.03 | 0.035 | 0.033 | 91.1
Rely Construction and Supply | 10433 | L | AA | MA | GE1 | Impv't./Widening of Agusan-Davao Rd. (Daang Maharlika), Pob. Nabunturan-Mawab Sect. | Comval Province | 2013-08-14 | Final | XI | LF | 17.1 | 157 | 2012-07-18 | 2012-12-12 | 0 | C | 0.374 | 0.152 | 0.3 | - | - | - | 82.6 | 83.44% Satisfactory
Rely Construction and Supply | 10433 | L | AA | MA | GE1 | Impvt./Widening of Agusan-Davao Rd. (Daang Maharlika) Pob. Nabunturan-Mawa Sect. | COMVAL Province | 2012-11-27 | 1st | XI | LF | 17.1 | 157 | 2012-07-18 | 2012-12-21 | 3.59 | O | 0.364 | 0.23 | 0.15 | 0.03 | 0.033 | 0.033 | 84 | -
Rely Construction and Supply | 10433 | L | AA | MA | GE1 | Rd. Upgrading along Asuncion-San Isidro-Laak-Veruela Rd. | Davao del Norte | 2013-03-17 | Final | XI | LF | 81.658 | 283 | 2012-03-28 | 2013-01-04 | 0 | C | 0.339 | 0.133 | 0.3 | - | - | - | 77.2 | 83.80% Satisfactory
Rely Construction and Supply | 10433 | L | AA | MA | GE1 | Rd. Upgrading along Asuncion-San Isidro-Laak Veruela Rd. | Compostela Valley | 2013-03-17 | 2nd | XI | LF | 91.565 | 344 | 2012-04-18 | 2013-03-17 | 0.15 | O | 0.147 | 0.24 | 0.15 | 0.03 | 0.05 | 0.033 | 65 | -
Rely Construction and Supply | 10433 | L | AA | MA | GE1 | Rd. Upgrading along Asuncion-San Isidro-Laak-Veruela Rd. | Compostela Valley | 2012-11-24 | 1st | XI | LF | 88.29 | 269 | 2012-04-18 | 2013-01-11 | 0.12 | O | 0.373 | 0.24 | 0.15 | 0.03 | 0.051 | 0.033 | 87.7 | -
Rely Construction and Supply | 10433 | L | AAA | MA | GE1 | Const./Widening of Libasan Bridge along Nabunturan-Mainit Park Rd. | Nabunturan, Comval Province | 2011-08-17 | 1st | XI | LF | 15.473 | 280 | 2011-03-25 | 2011-12-29 | 26.13 | O | 0.362 | 0.274 | 0.15 | 0.03 | 0.06 | 0.05 | 92.6 | -
Rely Construction and Supply | 10433 |  |  |  |  | Compostela-Cateel Rd. Dispatching-Mahilaya Sect. |  | 2010-06-06 |  | XI |  | 18.042 | 180 |  |  |  | O | 0.373 | 0.225 | 0.15 | 0.03 | 0.045 | 0.033 | 85.6 | -
Rely Construction and Supply | 10433 |  |  |  |  | Rehab./Reconst./Upgrading of Damaged Paved National Rd. Sect., Lipata (Surigao Del Norte) Davao City Highway through Daang Maharlika Rd. (Agusan to Davao Rd.) |  | 2010-06-02 |  | XI |  | 47.219 | 180 |  |  |  | O | 0.332 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 85.2 | -
Rely Construction and Supply | 10433 | L | AA | MA | GE1 | Impvt./Const. of Baganga-New Bataan Road Section, Baganga-Tigabauan-Binondo Section |  | 2009-09-12 | 1st | XI |  | 27.199 | 280 |  |  |  | O | 0.311 | 0.3 | 0.15 | 0.03 | 0.038 | 0.033 | 86.2 | -
Rely Construction and Supply | 10433 | L | AA | MA | GE1 | Road Upgrading at Cateel-Compostela Rd. (Davao Oriental Side) Km.1580+000-Km.1581+580 | Cateel, Davao Oriental | 2012-08-17 | 1st | XI | LF | 38.241 | 203 | 2012-03-15 | 2012-10-03 | 3.39 | O | 0.297 | 0.24 | 0.15 | 0.03 | 0.056 | 0.05 | 82.3 | -
RELY CONSTRUCTION AND SUPPLY | 10433 | L | AA | MA | GE | Construction of Cabasagan River Control | Boston, Davao Oriental | 2015-06-06 | Final | Davao Oriental 1st | LF | 10.075 | 99 | 2015-02-16 | 2015-05-25 | 0% | C | 0.469 | 0.084 | 0.3 | - | - | - | 85.3% | *85.3% Satisfactory
RELY CONSTRUCTION AND SUPPLY | 10433 | L | AA | MA | GE | Construction of Ibobotoc River Control, Boston, Davao Oriental | Boston, Davao Oriental | 2015-11-10 | Final | Davao Oriental 1st DEO | LF | 9.16e-06 | 139 | 2015-02-16 | 2015-07-04 | 0 | C | 0.423 | 0.152 | 0.3 | - | - | - | 87.5% | 87.5% Satisfactory
RELY CONSTRUCTION AND SUPPLY | 10433 | L | AA | MA | GE | Slope Protection of Surigao del Sur Boundary-Davao Oriental Coastal Road, Boston, Davao Oriental | Boston, Davao Oriental | 2015-11-10 | Final | Davao Oriental 1st DEO | LF | 4.573e-06 | 70 | 2015-02-16 | 2015-04-26 | -0.0488 | C | 0.478 | 0.2 | 0.154 | - | - | - | 83.2% | 83.2% Satisfactory
REMIGIO GENERAL CONSTRUCTION | 2298 | L | B | MA | GE | Widening of Permanent Bridges, Binasay Bridge (B2759LZ), along Laoag-Balacad Road Brgy. Balatong, Laoag City, Ilocos Norte | Laoag City, Ilocos Norte | 2015-11-11 | Final | ILOCOS NORTE 1ST DEO | LF | 12.0083 | 235 | 2015-04-16 | 2015-12-06 | -0.0311 | C | 0.357 | 0.293 | 0.119 | 0.03 | 0.055 | 0.033 | 88.7% | 88.7% Satisfactory
Remigio General Construction / Werr Corp. (International) (JV) | JV-11-345 | L | AA | LA | GE1 | Rehab. of Dakkel a Dannum Bridge along MNR | Pagudpud, Ilocos Norte | 2013-03-22 | Final | I | LF | 12.955 | 222 | 2012-03-06 | 2012-09-24 | 0 | C | 0.358 | 0.133 | 0.3 | - | - | - | 79.1 | 79.82% Unsatisfactory
REND ENTERPRISES & GENERAL CONTRACTOR | 32382 | L | B | MA | GE | Rehabilitation/Reconstruction of Damageed Paved National Roads including Drainage (Intermittent Sections) along Mac Arthur Highway, Valenzuela City | Valenzuela City | 2015-06-06 | Final | NCR | LF | 30.533 | 281 | 2014-04-14 | 2015-01-19 | (-) 2.05 | C | 0.459 | 0.133 | 0.238 | - | - | - | 83% | *83% Satisfactory
REND ENTERPRISES & GENERAL CONTRACTOR | 32382 | L | B | MA | GE | Preventive Maintenance (Intermittent Section) of Canumay - Bignay Road, Valenzuela City | Valenzuela City | 2015-08-28 | 1st | MM 3rd DEO | LF | 9.489 | 180 | 2015-03-31 | 2015-09-26 | 1.09% | O | 0.331 | 0.24 | 0.15 | 0.03 | 0.04 | 0.05 | 84.1% | -
REPOLMAN CONSTRUCTION | 32842 | L | B | MA | GE | Package 1: Construction of Multi-Purpose Building (Covered Court) at J.F. Khonghun Special Education School, Subic, Zambales | Subic, Zambales | 2015-11-10 | Final | Zambales Second DEO | LF | 3.254 | 75 | 2015-01-16 | 2015-03-31 | - | C | 0.489 | 0.133 | 0.3 | - | - | - | 92.2% | 92.2% Very Satisfactory
REVERE CONSTRUCTION & SUPPLY CORPORATION (Formerly: Revere Construction & Supply) | 17426 | L | AAA | LB | GE | Widening of Permanent Bridges to more than 2 lanes, Quiling Bridge 2 (B00031LZ) along Tanauan - Talisay - Tagaytay Road | Talisay, Batangas | 2015-06-06 | 1st | Batangas 3rd DEO | LF | 17.317 | 180 | 2015-02-03 | 2015-08-01 | 2.69% | O | 0.359 | 0.23 | 0.15 | 0.03 | 0.05 | 0.033 | 85.2% | -
REVERE CONSTRUCTION & SUPPLY CORPORATION (Formerly: Revere Construction & Supply) | 17426 | L | AAA | LB | GE | Widening of National Roads, Arterials Road, Outside N1, Manila - Batangas Road (Calansayan Section), K0092+900 to K0093+960 | San Jose, Batangas | 2015-06-05 | 1st | Batangas 4th DEO | LF | 44.872 | 240 | 2015-04-06 | 2015-12-01 | 28.01% | O | 0.286 | 0.3 | 0.15 | 0.024 | 0.05 | 0.033 | 84.3% | -
REVERE CONSTRUCTION & SUPPLY CORPORATION (Formerly: Revere Construction and Supply) | 17426 | L | AAA | LB | GE | Widening of National Roads, Arterial Roads, Outside NI, Manila-Batangas Road (Calansayan Section), K0 092+900 - K0 093+960 | San Jose, Batangas | 2015-08-29 | 1st | Batangas 4th | LF | 45.569 | 240 | 2015-04-06 | 2015-12-01 | 1.26% | O | 0.366 | 0.24 | 0.15 | 0.03 | 0.04 | 0.05 | 87.6% | -
REVERE CONSTRUCTION & SUPPLY CORPORATION (Formerly: Revere Construction and Supply) | 17426 | L | AAA | LB | GE | Widening of National Roads, Arterial Roads, Outside NI, Manila -Batangas Road (Calansayan Section) K0092+900 - K0093+960, San Jose Batangas | San Jose, Batangas | 2015-11-14 | 1st | BATANGAS 4TH DEO | LF | 45.5687 | 270 | 2015-04-06 | 2015-12-31 | 0.0008 | OG | 0.384 | 0.24 | 0.15 | 0.03 | 0.07 | 0.05 | 92.4% | 92.4% Very Satisfactory
Revere Construction and Supply | 17426 | L | AAA | LB | GE1 | Asphalt Overlay of Manila-Batangas Rd., Lipa City Sect. (K0079+091-K0080+249 w/ exception) | Batangas | 2013-07-29 | Final | IVA | LF | 17.854 | 95 | 2013-01-21 | 2013-04-25 | 0 | C | 0.447 | 0.133 | 0.3 | - | - | - | 88 | 90.70% V. Satisfactory
Revere Construction and Supply | 17426 | L | AAA | LB | GE1 | Asphalt Overlay of Manila-Batangas Rd., Lipa City Sect. (K0079+091-K0080+249 w/ exemption) | Batangas | 2013-03-11 | 1st | IVA | LF | 17.349 | 60 | 2013-01-21 | 2013-03-21 | 0.17 | O | 0.371 | 0.3 | 0.15 | 0.023 | 0.048 | 0.033 | 92.5 | -
Revere Construction and Supply | 17426 | L | AAA | LB | GE1 | Asphalt Overlay of Rosario-San Juan Rd., Pinagsibaan-Puting Kahoy Sect., (K0106+174-K0107+184) | Batangas | 2013-07-29 | Final | IVA | LF | 6.49 | 100 | 2013-01-21 | 2013-04-30 | 5 | C | 0.406 | 0.2 | 0.3 | - | - | - | 90.6 | 90.48% V. Satisfactory
Revere Construction and Supply | 17426 | L | AAA | LB | GE1 | Asphalt Overlay of Rosario-San Juan Rd., Pinagsibaan-Puting Kahoy Sect. (K0106+174-K0107+184) | Batangas | 2013-03-11 | 1st | IVA | LF | 6.335 | 90 | 2013-01-21 | 2013-04-20 | 61.83 | O | 0.35 | 0.3 | 0.15 | 0.023 | 0.048 | 0.033 | 90.4 | -
Revere Construction and Supply | 17426 | L | AAA | LB | GE1 | Replacement/Rehab./Strengthening of Permanent Bridges Gen. from Bridge Mgt. System (BMS) Bignay Bridge along Tanauan-Talisay-Tagaytay Rd. | Talisay, Batangas | 2013-08-02 | Final | IVA | LF | 7.94 | 75 | 2013-03-13 | 2013-05-26 | 0 | C | 0.421 | 0.133 | 0.3 | - | - | - | 85.4 | 89.54% V. Satisfactory
Revere Construction and Supply | 17426 | L | AAA | LB | GE1 | Replacement/Rehab./Strengthening of Permanent Bridges, Bignay Bridge along Talisay-Laurel-Agoncillo Rd. | Talisay, Batangas | 2013-03-14 | 1st | IVA | LF | 7.94 | 75 | 2013-03-13 | 2013-05-26 | 0.23 | O | 0.4 | 0.3 | 0.15 | 0.015 | 0.025 | 0.033 | 92.3 | -
Revere Construction and Supply | 17426 | L | AAA | LB | GE1 | Widening of Daang Maharlika Rd. K0070+(-)611-K0073+760.00, Net Length = 4,371.00 L.M. | Laguna | 2013-03-15 | Final | IVA | LF | 150.858 | 240 | 2012-03-29 | 2013-01-01 | 0 | C | 0.47 | 0.133 | 0.3 | - | - | - | 90.3 | 91.32% V. Satisfactory
Revere Construction and Supply | 17426 |  |  |  |  | Impvt. of Drainage and other Related Structures of Manila-Batangas City Road, Sto. Tomas-Malvar Sect. |  | 2010-06-10 |  | IVA |  | 11.574 | 90 |  |  |  | O | 0.374 | 0.225 | 0.15 | 0.015 | 0.05 | 0.033 | 84.7 | -
Revere Construction and Supply | 17426 |  |  |  |  | Widening of Manila-Batangas Rd., Brgy. Maraouy, Lipa City Sect. (Phase I) |  | 2010-06-07 |  | IVA |  | 24.625 | 120 |  |  |  | O | 0.345 | 0.225 | 0.15 | 0.023 | 0.045 | 0.05 | 83.8 | -
Revere Construction and Supply | 17426 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of Damaged National Roads at San Juan-Laiya Road |  | 2009-05-28 | 1st | IV-A |  | 48.238 | 180 |  |  |  | O | 0.373 | 0.24 | 0.15 | 0.03 | 0.03 | 0.05 | 87.3 | -
Revere Construction and Supply | 17426 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of Damaged of Talisay-Laurel-Agoncillo Road (Laurel-Agoncillo Section) |  | 2009-05-22 | 1st | IV-A |  | 48.242 | 120 |  |  |  | O | 0.366 | 0.24 | 0.15 | 0.03 | 0.03 | 0.05 | 86.6 | -
REX E. MORALES CONSTRUCTION | 17427 | L | A | MB | GE | Road Upgrading (Upgrading to Paved) of Sambulawan Jct. Calaguise- Calubian Road, K0993+493 - K0994+283, K0997+603, Leyte | K0993+493 - K0994+283, K0997+603, Leyte | 2015-06-10 | 1st | Leyte Third DEO | LF | 37.59 | 179 | 2015-02-11 | 2015-08-08 | - | O | 0.363 | 0.138 | 0.15 | 0.015 | 0.035 | 0.05 | 75.1% | -
REX E. MORALES CONSTRUCTION | 17427 | L | A | MB | GE | Road Upgrading (Unpaved to Paved) of Sambulawan Jct.-Calaguise-Calubian Road, K0993+493-KO994+283; KO997+603-KO998+311 Leyte, Leyte | K0993+493-KO994+283; KO997+603-KO998+311 Leyte, Leyte | 2015-08-26 | 1st | Leyte 3rd DEO | LF | 37.59 | 209 | 2015-02-11 | 2015-09-07 | (+)2.90 | O | 0.256 | 0.298 | 0.15 | 0.01 | 0.025 | 0.05 | 78.9% | -
REX E. MORALES CONSTRUCTION | 17427 | L | A | MB | GE | Road Upgrading (Unpaved to Paved) of Sambulawan Jct-Calaguise-Calubian Road, K0993+493-K0994+283; K0997+603-K0998+311, Leyte, Leyte | Leyte, Leyte | 2015-11-13 | Final | Leyte Third DEO | LF | 37.5902 | 209 | 2015-02-11 | 2015-09-07 | (+)1.68% | C | 0.397 | 0.2 | 0.3 | 0 | 0 | 0 | 89.7% | 82.08% Satisfactory
Rey Rose Construction & Supply | 22934 | L | B | SB | GE | Rehabilitation/Reconstruction of Critical Section, Road Slip along Agusan-Bukidnon Road, K1259+898 - K1259+940 | Buenavista, Agusan del Norte | 2014-10-21 | 1st & Final | XIII | LF | 2.9243 | 88 | 2014-02-04 | 2014-05-02 | 2.28% | C | 0.422 | 0.163 | 0.3 | - | - | - | 88.5% | 88.5% Satisfactory
REY ROSE CONSTRUCTION & SUPPLY | 22934 | L | B | SB | GE | Construction/Rehabilitation of Drainage Along Butuan City-Malaybalay Road (S00431MN), Chainage 2285 - Chainage 2432 (Line 1) & Chainage 1227 - Chainage 2285 (with Exception), Butuan City | Butuan City | 2015-09-01 | 1st & Final | Butuan City | LF | 14.658 | 231 | 2015-03-05 | 2015-10-21 | (+) 50.39% | C | 0.482 | 0.143 | 0.3 | - | - | - | 92.5% | *92.5% Very Satisfactory
REY ROSE CONSTRUCTION & SUPPLY | 22934 | L | B | MA | GE | Rehabilitation/ Reconstruction of National Road Along Agusan Malaybalay Road (New Gingoog Section), K1277+147.00-K1277+216, K1277+592-K1277+615 | Esperanza, Agusan Del Sur | 2015-08-24 | 1st & Final | Agusan del Sur 1st | LF | 9.442 | 128 | 2015-03-03 | 2015-07-08 | 0% | C | 0.487 | 0.142 | 0.3 | - | - | - | 92.9% | *91.52% Very Satisfactory
REY ROSE CONSTRUCTION & SUPPLY | 22934 | L | B | MA | GE | Widening of National Roads, Nasipit Port Road, K1265+000 - K1266+(-478), Nasipit, Agusan del Norte | Nasipit Agusan del Norte | 2015-11-19 | Final | Agusan del Norte DEO | LF | 13.0218 | 132 | 2015-03-27 | 2015-08-05 | - | C | 0.347 | 0.2 | 0.3 | - | - | - | 84.7% | 84.7% Satisfactory
Rey Rose Construction & Supply/ROIM Builders & Construction Supply -Joint Venture | SL1-SN-00811 | L | B | MA | GE | Rehab./Reconst./Upgrading of Damaged Paved National Roads along NRJ - Bahbah - Talacogon Road, K1294+(-499) - K1295+000; K1301+000 - K1302+000; K1306+000 - K1306+280 | Prosperidad, Agusan del Sur | 2014-08-06 | 1st | XIII | LF | 40.0352 | 233 | 2014-02-11 | 2014-10-03 | 3.16 | O | 0.369 | 0.226 | 0.15 | 0.03 | 0.033 | 0.05 | 85.8
Rey Rose Construction & Supply/ROIM Builders & Construction Supply (JV) | JV-13-262 | L | B | MA | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads along NRJ-Bahbah-Talacogon Road | Prosperidad, Agusan del Sur | 2014-10-22 | 1st | XIII | LF | 40.0352 | 297 | 2014-02-11 | 2014-12-04 | 3.74% | O | 0.339 | 0.234 | 0.15 | 0.03 | 0.042 | 0.05 | 84.5% | 84.5% Satisfactory
REYDAN BUILDERS | 13059 | L | A | MA | GB | Completion of DPWH-South Cotabato II District Engineering Office | Brgy. Lagao, General Santos City | 2015-06-12 | 1st | South Cotabato 2nd DEO | LF | 18.1 | 240 | 2014-12-07 | 2015-08-03 | 0.5% | O | 0.389 | 0.24 | 0.15 | 0.031 | 0.041 | 0.05 | 90.1% | -
REYDAN BUILDERS | 13059 | L | A | MA | GE | San Felipe Br. (B01038MN) along Midsayap-Marbel Road (including Protection Works), San Felipe Section | Tantangan, South Cotabato | 2015-06-03 | 1st | South Cotabato DEO | LF | 4.78 | 165 | 2015-03-02 | 2015-08-13 | 12.26% | O | 0.35 | 0.225 | 0.15 | 0.03 | 0.051 | 0.033 | 83.9% | -
Reydan Builders | 13059 | L |  |  | GE | Construction of Box Culvert and Slope Protection along Surallah - Lake Sebu - Maitum Road, K1745+300 | Lake Sebu, South Cotabato | 2014-10-21 | 1st & Final | XII | LF | 4.8706 | 117 | 2014-05-07 | 2014-08-31 | 0% | C | 0.356 | 0.133 | 0.3 | - | - | - | 78.9% | 78.9% Unsatisfactory
Reydan Builders | 13059 | L | A | MA | GE | Widening of Makar - Kiamba Road, K1667+243 - K1668+236, General Santos City | General Santos City | 2014-08-16 | 1st & Final | XII | LF | 19.2884 | 117 | 2014-01-26 | 2014-05-23 | 0.86 | C | 0.453 | 0.192 | 0.3 |  |  |  | 94.5 | 94.50% Very Satisfactory
Reydan Builders | 13059 | L | A | MA | GE | Const. of San Felipe Bridge Bank Protection along Midsayap - Marbel Road, KO1789+249, San Felipe Section | Tantangan, South Cotabato | 2014-08-05 | 1st & Final | XII | LF | 4.9708 | 135 | 2014-05-07 | 2014-09-18 | 25 | C | 0.437 | 0.2 | 0.3 |  |  |  | 93.7 | 93.70% Very Satisfactory
Reydan Builders | 13059 | L | A | MA | GE | Concreting/Widening of Marbel - Makar Road, South Cotabato, K1675+661.8 - K1677+761, Polomok Section | Polomok, South Cotabato | 2014-08-16 | 1st & Final | XII | LF | 18.5531 | 116 | 2014-01-26 | 2014-05-22 | 0.86 | C | 0.474 | 0.133 | 0.3 |  |  |  | 90.7 | 90.70% Very Satisfactory
Reydan Builders | 13059 | L | A | MA | GE | Road to Address Critical Bottlenecks National Road Traffic Decongestion, Widening of Marbel-Midsayap Road | South Cotabato | 2014-08-05 | Final | XII | LF | 32.6997 | 204 | 2013-03-12 | 2013-06-24 | 0.62 | C | 0.409 | 0.2 | 0.3 |  |  |  | 90.9 | 90.51% Very Satisfactory
Reydan Builders | 13059 | L | A | MA | GE1 | Rds. to Address Critical Bottlenecks Nat'l Rd. Traffic Decongestion, Widening of Marbel-Midsayap Rd. | South Cotabato | 2013-08-06 | 2nd | XII | LF | 32.7 | 150 | 2013-03-12 | 2013-09-01 | 0.004 | O | 0.367 | 0.236 | 0.15 | 0.015 | 0.056 | 0.033 | 85.7
Reydan Builders | 13059 | L | A | MA | GE1 | Rds. To address Critical Bottlenecks Nat'l. Rd. Traffic Decongestion, Widening of Marbel-Midsayap Rd. | South Cotabato | 2012-03-20 | 1st | XII | LF | 31.7 | 105 | 2013-03-12 | 2013-06-24 | 15.45 | O | 0.353 | 0.3 | 0.15 | 0.03 | 0.065 | 0.05 | 94.8 | -
REYROSE CONSTRUCTION & SUPPLY | 22934 | L | B | MA | GE | Widening of National Roads, Nasipit Port Road | K1265+000 yo K1266+(-478), Nasipit Port Road, Agusan Del Norte | 2015-06-02 | 1st | AGUSAN DEL NORTE DEO | LF | 13.022 | 97 | 2015-03-27 | 2015-07-01 | (+) 13.43% | O | 0.394 | 0.237 | 0.15 | 0.03 | 0.05 | 0.05 | 91.1% | -
REYROSE CONSTRUCTION & SUPPLY | 22934 | L | B | MA | GE | Rehabilitation/ Reconstruction of National Road along Agusan-Malaybalay Road (New Gingoog Section) | K1277+197.00 - K1277+216, K1277+592 - K1277+615, Esperanza, Agusan Del Sur | 2015-06-04 | 1st | AGUSAN DEL SUR FIRST DEO | LF | 9.442 | 98 | 2015-03-03 | 2015-06-08 | (+) 20.35% | O | 0.381 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 90.6% | -
RFN Construction & Development Corp. | 8722 |  |  |  |  | Const. of Livelihood, Production & Training Center |  | 2010-02-18 |  | NHA |  | 4.992 | 90 |  |  |  | O | 0.3966 | 0.255 | 0.15 | 0.03 | 0.05 | 0.05 | 93.16 | -
RFN Construction & Development Corp. | 8722 | L | AA | MB | GB1 | Construction of One (1) unit Three-Storey School Building |  | 2009-09-18 | 1st | NHA |  | 18.108 | 150 |  |  |  | O | 0.375 | 0.3 | 0.15 | 0.03 | 0.0583 | 0.05 | 96.33 | -
RFN Construction & Development Corporation | 2272 | L | B |  | GB1 | Construction of One (1) Unit 3-Storey, 15 Classroom School Bldg. | South Summer Ridge, Brgy. Aguado, Trece Martirez, Cavite | 2013-05-07 | 2nd & Final | NHA | L | 17.527 | 250 | 2012-06-08 | 2013-06-30 | 7.88 | C | 0.4703 | 0.2 | 0.3 | - | - | - | 97.03 | 88.73% Satisfactory
RFN Construction & Development Corporation | 2272 | L |  |  | GB1 | Construction of One (1) Unit 3-Storey, 15 Classroom School Bldg. | South Summer Ridge, Brgy. Aguado, Trece Martirez, Cavite | 2013-01-31 | 1st | NHA | LF | 22.122 | 180 | 2012-04-20 | 2013-01-29 | -9.06 | O | 0.385 | 0.3 | 0.0594 | 0.03 | 0.054 | 0.017 | 84.54 | -
RFN Construction Dev't Corp./Versontal Builders JV |  | L |  |  | GE1 | Sr. San Roque Resettlement Project, Phase 1 | Brgy. Budlaan, Cebu City / Region VII | 2012-09-21 | 1st | NHA | LF | 33.785 | 345 | 2012-03-11 | 2012-04-21 | 6.69 | O | 0.3879 | 0.2538 | 0.0831 | 0.03 | 0.0296 | 0.05 | 83.44 | -
RFN Construction Dev't. Corp./Versontal Builders JV |  | L |  |  | GE1 | Sr. San Roque Resettlement Project, Phase 1 | Brgy. Budlaan, Cebu City/Region VII | 2012-11-23 | 2nd | NHA | LF | 33.785 | 345 | 2012-03-11 | 2013-04-25 | 1.21 | O | 0.3252 | 0.3 | 0.15 | 0.03 | 0.0525 | 0.05 | 90.77 | -
RG & K Construction and General Merchandise | 33021 | L | B | SB | GE2 | Const. of Slope Protection along Butuan City-Cagayan de Oro City-Iligan City, Downstream of Iponan Bridge I and II, Misamis Oriental Side, Barra | Opol, Misamis Oriental | 2013-08-19 | 2nd | X | LF | 17.118 | 240 | 2012-10-18 | 2013-06-14 | 6.27 | O | 0.366 | 0.208 | 0.15 | 0.02 | 0.041 | 0.05 | 83.5
RG & K Construction and General Merchandise | 33021 | L | B | SB | GE2 | Const. of Slope Protection along Butuan City-Cagayan de Oro City-Iligan City, Downstream of Iponan Bridge I and II, Misamis Oriental Side | Opol, Misamis Oriental | 2013-03-13 | 1st | X | LF | 17.118 | 240 | 2012-10-18 | 2013-06-14 | 2.46 | O | 0.352 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 87.2 | -
RG & K Construction and General Merchandise | 33021 | L | B | MA | GE1 | Const. of Misamis Oriental-Bukidnon By-Pass Rd. PHIVDEC-Alae Sect. | Misamis Oriental | 2013-08-19 | 1st | X | LF | 45.294 | 179 | 2013-03-05 | 2013-08-30 | 2.28 | O | 0.329 | 0.24 | 0.15 | 0.03 | 0.04 | 0.033 | 82.2
RG & K Construction and General Merchandise | 33021 | L | D | SB | GE1 | Assets Preservation of Nat'l Rds., Butuan City-Cagayan de Oro City-Iligan City Rd. (Km.1488+000-Km.1489+000) | Misamis Oriental | 2012-08-16 | Final | X | LF | 10.611 | 120 | 2012-01-19 | 2012-05-17 | 69.5 | C | 0.421 | 0.2 | 0.3 | - | - | - | 92.1 | 86.22% Satisfactory
RGP Builders | 20680 | L | B | MA | GE1 | Const. of Rds. from Marine Hatchery Proj. to Nat'l. Highway, Brgy. Punta | Unisan, Quezon | 2013-08-06 | Final | IVA | LF | 23.275 | 161 | 2012-10-26 | 2013-04-04 | 2 | C | 0.252 | 0.2 | 0.3 | - | - | - | 75.2 | 82.52% Satisfactory
RGP Builders | 20680 | L | B | MA | GE1 | Const. of Rd. from Marine Hatchery Proj. to Nat'l. Highway, Brgy. Punta | Unisan, Quezon | 2013-03-17 | 1st | IVA | LF | 23.275 | 157 | 2012-10-26 | 2013-03-31 | 0.97 | O | 0.358 | 0.251 | 0.15 | 0.03 | 0.035 | 0.05 | 87.4 | -
RGP BUILDERS | 20680 | L | B | MA | GE | Road Upgrading (Unpaved to Paved) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standard (HDM-4 Project Analysis), (Intermittent Sections) Secondary Road Talaba - Summit - Panaon Rd., K0179+426 to K0179+867, K0179+897 to K0180+072 | Atimonan, Quezon | 2015-06-11 | 1st | Quezon 4th DEO | LF | 11.429 | 120 | 2015-02-26 | 2015-06-25 | 2.68% | O | 0.358 | 0.226 | 0.15 | 0.03 | 0.05 | 0.05 | 86.4% | -
RGP BUILDERS | 20680 | L | B | MA | GE | Road Upgrading, Talaba-Summit-Panaon Road, K0179+426 - K0179+867, K0179+897 - K0180+072, Atimonan, Quezon | Atimonan, Quezon | 2015-11-17 | Final | QUEZON 4TH DEO | LF | 11.4287 | 120 | 2015-02-26 | 2015-06-25 | 0 | C | 0.453 | 0.133 | 0.3 | - | - | - | 88.6% | 88.6% Satisfactory
Rhodwill Parts and Hardware | 18871 | L | B | MA | GE1 | Widening of Pres. Diosdado P. Macapagal Highway (Maputi Sect.) Km.1766+980-Km.1767+633.40 w/ exception | Banaybanay, Davao Oriental | 2013-08-16 | Final | XI | LF | 10.29 | 69 | 2013-01-25 | 2013-04-03 | 0 | C | 0.441 | 0.133 | 0.3 | - | - | - | 87.4 | 86.44% Satisfactory
Rhodwill Parts and Hardware | 18871 | L | B | MA | GE1 | Widening of Pres. Diosdado P. Macapagal Highway (Maputi Sect.) Km.1766+980-Km.1767+633.40 w/ exception | Banaybanay, Davao Oriental | 2013-03-19 | 1st | XI | LF | 10.291 | 69 | 2013-01-25 | 2013-04-03 | 8.14 | O | 0.343 | 0.24 | 0.15 | 0.03 | 0.045 | 0.05 | 85.8 | -
Rhodwill Parts and Hardware | 18871 |  |  |  |  | San Jose River Control |  | 2010-03-03 |  | XI |  | 4.714 | 120 |  |  |  | O | 0.4 | 0.24 | 0.15 | 0.023 | 0.049 | 0.05 | 91.2 | -
RHODWILL PARTS AND HARDWARE & CONSTRUCTION SERVICES (Formerly: Rhodwill Parts and Hardware) | 18871 | L | B | MA | GE | Construction of Roads and Bridges, c) Construction of Footbridge at Brgy. Central, City of Mati, Davao Oriental | Mati, Davao Oriental | 2015-11-11 | Final | Davao Oriental 2nd DEO | LF | 1.434e-06 | 114 | 2015-05-08 | 2015-08-29 | 0 | C | 0.395 | 0.2 | 0.3 | - | - | - | 89.5% | 89.5% Very Satisfactory
Rhyes Builders & Supply | 22115 | L | A | MA | GE | Repair/Reconst. Of Roadslip along Catarman-Calbayog Road K0770+911 - K0771+150, Nabaloog, Catarman | Catarman, Northern Samar | 2014-10-21 | 1st | VIII | LF | 8.6614 | 120 | 2014-09-16 | 2015-01-13 | 26.3% | O | 0.367 | 0.239 | 0.15 | 0.023 | 0.045 | 0.033 | 85.7% | 85.7% Satisfactory
Rhyes Builders & Supply | 22115 | L | A | MA | GE | Concreting of Bangkerohan-Gulutan-Imelda-Hinatad-McKinley-Cabangahan Road | Catarman, Northern Samar | 2014-10-21 | 1st | VIII | LF | 9.117 | 71 | 2014-09-16 | 2014-11-25 | 25.05% | O | 0.341 | 0.24 | 0.15 | 0.03 | 0.04 | 0.05 | 85.1% | 85.1% Satisfactory
Rhyes Builders & Supply | 22115 | L | A | MA | GE1 | Conc. of Bangkerohan-Galutan-Imelda-Hinatad-Mckinley Rd. | Catarman, Northern Samar | 2013-03-21 | Final | VIII | LF | 46.462 | 180 | 2012-02-06 | 2012-08-03 | 0 | C | 0.391 | 0.133 | 0.3 | - | - | - | 82.4 | 82.22% Satisfactory
Rhyes Builders & Supply | 22115 | L | A | MA | GE1 | Conc. of Bangkerohan-Galutan-Imelda-Hinatad-Mckinley Rd. | Catarman, Northern Samar | 2012-08-13 | 1st | VIII | LF | 46.462 | 180 | 2012-02-06 | 2012-08-04 | 10 | O | 0.324 | 0.239 | 0.15 | 0.03 | 0.033 | 0.033 | 80.9 | -
RHYES BUILDERS & SUPPLY | 22115 | L | A | MA | GE | Concreting of Bangkerohan-Galutan-Imelda-Hinatad-Mckinley-Cabangahan Road, Catarman, Northern Samar | Catarman, Northern Samar | 2015-06-25 | Final | Northern Samar First DEO | LF | 9.117 | 87 | 2014-09-16 | 2014-12-11 | - | C | 0.403 | 0.128 | 0.3 | - | - | - | 83.1% | *84.3% Satisfactory
RHYES BUILDERS & SUPPLY | 22115 | L | A | MA | GE | Repair/Reconst. of Roadslip along Catarman-Calbayog Road K0770+911 - K0771+150, Nabaloog, Catarman, Northern Samar | Catarman, Northern Samar | 2015-06-25 | Final | Northern Samar First DEO | LF | 8.661 | 120 | 2014-09-16 | 2015-01-13 | - | C | 0.348 | 0.2 | 0.3 | - | - | - | 84.8% | *85.34% Satisfactory
Rhyes Builders & Supply / ESD Cruz Construction & Supply (JV) | JV-11-066 | L | B | MA | GE1 | Conc. of Pangpang-Palapag-Mapanas-Gamay-lapinig Rd, Cabatuan-Magtaun Sect., Km.820+000.00-Km.824+000.00 w/ exception | Palapag, Northern Samar | 2012-08-17 | 1st | VIII | LF | 33.889 | 305 | 2011-12-14 | 2012-10-14 | 15.9 | O | 0.335 | 0.24 | 0.15 | 0.03 | 0.033 | 0.033 | 82.1 | -
Rhyes Builders & Supply / Norsam Builders & Construction Supply (JV) | JV-11-271 | L | B | MA | GE1 | Upgrading of Colab-og-Lungib-Buenasuerte-Pasabuena-Maxvilla Rd. | Northern Samar | 2013-08-10 | Final | VIII | LF | 46.345 | 270 | 2012-02-06 | 2012-11-02 | 0.37 | C | 0.369 | 0.188 | 0.3 | - | - | - | 85.7 | 85.52% Satisfactory
Rhyes Builders & Supply / Norsam Builders & Construction Supply (JV) | JV-11-271 | L | B | MA | GE1 | Upgrading of Colab-og-Lungib-Buenasuerte-Pasabuena-Maxvilla Rd. | Victoria, Northern Samar | 2012-08-11 | 1st | VIII | LF | 46.345 | 180 | 2012-02-06 | 2012-08-04 | 0.28 | O | 0.289 | 0.3 | 0.15 | 0.03 | 0.035 | 0.05 | 85.4 | -
Rhyes Builders / ESD Cruz Construction (JV) | JV-11-066 | L | B | MA | GE1 | Conc. of Pangpang-Palapag-Mapanas-Gamay-Lapinig Rd., Cabatuan-Magtaon Sect., Km.820+000-Km.824+000 w/ exception | Palapag, Northern Samar | 2013-08-06 | Final | VIII | LF | 33.889 | 407 | 2011-12-14 | 2013-01-24 | 0.25 | C | 0.391 | 0.182 | 0.3 | - | - | - | 87.3 | 84.18% Satisfactory
Rhyes Builders and Supply |  | L |  |  |  | Help for Catubig Agricultural Advancement Project HCAAP-LMC-C-2 | Catubig, Northern Samar/Region 8 | 2014-03-15 | Final | NIA | LF | 9.26 | 540 | 2011-02-07 | 2012-08-02 | 0 | C | 0.4732 | 0.0712 | 0.3 | - | - | - | 84.44 | 84.44% Satisfactory
Richfield Builders | 24525 | L | D | SB | GB | Construction of Two (2) Storey Six (6) Classrooms Bais City Pilot School, Bais City | Bais City | 2014-08-14 | Final | VII | LF | 6.6768 | 163 | 2013-03-27 | 2013-09-05 | 0 | C | 0.465 | 0.155 | 0.3 |  |  |  | 92 | 88.15% Satisfactory
Richfield Builders | 24525 | L | D | SB | GB1 | Const. of 2 Storey 6-CL SB at Bais City Pilot Sch. | Bais City, Negros Oriental | 2013-08-21 | 1st | VII | LF | 6.555 | 153 | 2013-03-27 | 2013-08-27 | -0.78 | O | 0.393 | 0.22 | 0.142 | 0.03 | 0.047 | 0.033 | 86.5
Richfield Builders | 24525 | L | D | SB | GE1 | Rehab./Reconst. of Damaged Paved Nat'l Rd., Dumaguete North Rd., K0044+78-K0044+328 | Negros Oriental | 2011-08-09 | 1st | VII | LF | 3.843 | 91 | 2011-05-20 | 2011-08-19 | -6.52 | O | 0.339 | 0.3 | 0.085 | 0.03 | 0.04 | 0.033 | 82.7 | -
RICHFIELD BUILDERS | 24525 | L | D | SB | GE | Construction/Improvement of Access Road Leading to Declared Tourism Destination, Abante Road Leading to Palaypay Falls, Pamplona 2nd District, Negros Oriental | Pamplona 2nd District, Negros Oriental | 2015-11-12 | Final | Negros Oriental 2nd DEO | LF | 9.3004 | 151 | 2015-04-22 | 2015-09-19 | (+)1.32% | C | 0.431 | 0.173 | 0.3 | - | - | - | 90.4% | 90.4% Very Satisfactory
Richmark Construction | 14227 |  |  |  |  | Calbiga Irrigation Project | Calbiga, Samar | 2014-11-22 | 1st & Final | NIA | L | 8.777 | 290 | 2013-04-10 | 2014-01-24 | 0 | C | 0.4571 | 0.2 | 0.3 | - | - | - | 95.71 | *95.71 V. Satisfactory
Richmark Construction | 14227 |  |  |  |  | Calbiga Irrigation Project | Calbiga, Samar Region 8 | 2014-11-22 | 1st & Final | NIA | L | 9.92 | 180 | 2013-05-07 | 2014-06-01 | 0 | C | 0.4565 | 0.2 | 0.3 | - | - | - | 95.65 | *95.65% V. Satisfactory
Richmark Construction | 14227 |  | B | SB |  | Construction of Brgy. Lumalantang Wharf | Brgy. Lumalantang, Zumarraga, Western Samar/ Region VIII | 2015-10-15 | 1st | DOTC | LF | 8.974 | 120 | 2015-08-21 | 2015-12-19 | 10.64 | O | 0.3047 | 0.3 | 0.15 | 0.02 | 0.0175 | 0.05 | 84.22 | -
Richmark Construction | 14227 |  | B | SB |  | Cawarak Port Development Project | Brgy. Canwarak, Zumarraga, Samar/ Region VIII | 2016-03-30 | 1st & Final | DOTC | LF | 7.635 | 90 | 2015-08-21 | 2016-01-29 | 0 | C | 0.445 | 0.2 | 0.3 | - | - | - | 94.5 | *94.50% V. Satisfactory
Richphil Builders, Inc. / Armando U. Khong Hun General Contractor, Inc. (Joint Venture) | JV-11-042 | L | A | MA | GE1 | Rehab./Widening of Rd.s & Impv't. of Drainage System along Manila East Rd. (Rosario-Cainta Rd.) Km.15+654-Km.17+131 | Pasig City | 2013-03-16 | Final | NCR | LF | 43.261 | 395 | 2011-10-18 | 2012-11-15 | - | C | 0.418 | 0.2 | 0.254 | - | - | - | 87.2 | 82.55% Satisfactory
RIEZL LANDCARE AND CONSTRUCTION |  |  | AA |  |  | Construction of Maternal and Child Care Facility Building | Davao City | 2016-06-23 | 1st | DOH | LF | 128.389 | 720 | 2015-03-23 | 2017-03-12 | 0 | O | 0.3908 | 0.2547 | 0.15 | 0.03 | 0.0592 | 0.05 | 93.47 | -
RIEZL LANDCARE AND CONSTRUCTION | 9460 |  | AA |  |  | Construction of Oncology Building | Davao City | 2016-06-22 | 1st | DOH | LF | 86.881 | 550 | 2014-10-03 | 2016-04-03 | 0 | O | 0.3937 | 0.254 | 0.15 | 0.03 | 0.0592 | 0.05 | 93.69 | -
Rikda Construction & Dev't Corp. | 32758 | L |  | SB |  | Completion of Academic Building I | Talaytay Argao, Cebu | 2014-10-16 | Final | DOST | L | 4.104 | 119 | 2013-11-27 | 2014-04-26 | 0 | C | 0.437 | 0.2 | 0.3 | - | - | - | 93.7 | 95.68% V. Satisfactory
Rikki Construction | 33492 | L | D | SB | GE | Replacement/Rehabilitation/Strengthening of Kapayawan Bridge along Mt. Province-Ilocos Sur via Tue Road | Mt. Province-Ilocos Sur Road via Tue Road, Otucan, Bauko, Mt. Province | 2014-08-12 | Final | CAR | LF | 4.4757 | 140 | 2013-04-03 | 2013-08-20 | 0 | C | 0.449 | 0.133 | 0.3 |  |  |  | 88.2 | 83.40% Satisfactory
Rim Construction | 15938 | L | B | MA | GE1 | Rehab./Impvt. of Mountain Province-Ilocos Sur Road via Tue |  | 2009-03-09 | 1st | CAR |  | 19.012 | 369 |  |  |  | O | 0.351 | 0.3 | 0.15 | 0.03 | 0.05 | 0.05 | #VALUE! | -
Rim Construction | 15938 | L | B | MA | GE1 | Rehab./Impvt. of Mountain Province-Ilocos Sur Road via Tue |  | 2009-08-28 | 1st | CAR |  | 19.011 | 460 |  |  |  | O | 0.367 | 0.24 | 0.061 | 0.015 | 0.042 | 0.017 | 74.2 | -
Rising Sun Builders Phils., Inc. | 30703 | L | B | SB | GB | Improvement & Beautification of Bulusukan River | Pila, Laguna | 2015-05-19 | 2nd | TIEZA | LF | 8.6 | 210 | 2014-10-19 | 2015-05-17 |  | O | 0.3502 | 0.2326 | 0.15 | 0.03 | 0.07 | 0.05 | 88.28
Rising Sun Builders Phils., Inc. | 30703 | L | B | SB | GB | Improvement & Beautification of Bulusukan River | Pila, Laguna | 2015-01-23 | 1st | TIEZA | LF | 8.6 | 180 | 2014-10-19 | 2015-04-17 |  | O | 0.3509 | 0.3 | 0.15 | 0.03 | 0.0583 | 0.0333 | 92.26
Rising Sun Builders Phils., Inc. | 30703 | L | B | SB | GB | Hundred Islands Development | Alaminos City, Pangasinan | 2014-08-15 | Final | TIEZA | LF | 9.987 | 150 | 2012-09-06 | 2014-06-07 | 0 | C | 0.466 | 0.198 | 0.3 |  |  |  | 96.4 | 88.90% Satisfactory
Rising Sun Builders Phils., Inc. | 30703 | L | B | SB | GB | Hundred Islands Development | Alaminos City, Pangasinan | 2014-05-21 | 1st | TIEZA | LF | 9.99 | 150 | 2012-09-06 | 2014-06-07 | 0 | O | 0.301 | 0.3 | 0.15 | 0.015 | 0.023 | 0.05 | 83.91
RISING SUN BUILDERS PHILS., INC. | 30703 | L | B | SB | GB | Improvement and Beautification of Bulusukan River | Pila, Laguna | 2015-07-02 | Final | TIEZA | LF | 9 | 210 | 2015-10-19 | 2015-05-17 |  | C | 0.4971 | 0.2 | 0.3 |  |  |  | 99.71 | 94.04% Very Satisfactory
Rism Designer's and General Merchandise & Engineering Services | 32830 | L | D | SB | GB | Const. of DepED Standard Type School Building at Carol-an ES Kabankalan City | Kabankalan City, Negros Occidental | 2014-08-08 | Final | VI | LF | 2.4294 | 85 | 2013-05-24 | 2013-07-22 | 0 | C | 0.448 | 0.2 | 0.3 |  |  |  | 94.8 | 85.84% Satisfactory
Rism Designer's and General Merchandise & Engineering Services | 32830 | L | D | SB | GB1 | Const. of DepEd Standard Type Sch. Bldg. @ Carol-an ES | Kabankalan City, Negros Occidental | 2013-08-08 | 1st | VI | LF | 2.429 | 85 | 2013-05-24 | 2013-08-16 | 3.44 | O | 0.369 | 0.2 | 0.15 | 0.03 | 0.038 | 0.033 | 82
Ritche-Nathalie Builders and General Merchandise | 27501 | L | C | SB | GE1 | Completion of Opol Building |  | 2009-06-09 | 1st | X |  | 0.952 | 180 |  |  |  | O | 0.4 | 0.225 | 0.15 | 0.01 | 0.011 | 0.033 | 82.9 | -
RITVIT Construction & Development Corp. |  | L |  |  | GB1 | Renov. Of Acct., Budget, HRD, Legal, UPMDFI, Provident Offices & Social Hall (Building) | 8F PGH, Central Block Bldg. | 2011-02-17 | 1st | UP | LF | 14.019 | 150 | 2010-07-20 |  | 0 | O | 0.342 | 0.3 | 0.15 | 0.02 | 0.057 | 0.05 | 91.9 | -
RITVIT Construction & Development Corp. |  | L |  |  | GB1 | Proposed Renovation of Accounting, Budget, HRD, Legal, UPMDFI, Provident Offices & Social Hall | 8F PGH, Central Block Bldg., UP Manila | 2011-11-24 | 2nd | UP | LF | 14.829 | 150 | 2010-07-21 | 2011-12-08 | - | O | 0.339 | 0.3 | 0.15 | 0.03 | 0.07 | 0.05 | 93.9 | -
Ritvit Construction & Development Corporation | 9426 |  |  |  |  | Renovation of Budget, Accounting, HRDO, Legal, UPMDFI Provident Offices & Social Hall |  | 2010-08-26 |  | U.P Manila |  | 14.091 | 150 |  |  |  | O | 0.4 | 0.3 | 0.08 | 0.03 | 0.07 | 0.05 | 91 | -
RITZTOK CONSTRUCTION AND SUPPLY | 36070 | L | D | SB | GE | Concreting of Road, Barangay Manga to Tamlangon Farm to Market Road | Matanao, Davao del Sur | 2015-06-04 | 1st | Davao del Sur 1st | LF | 1.912 | 60 | 2015-04-17 | 2015-06-15 | (+)20.06% | O | 0.358 | 0.225 | 0.15 | 0.023 | 0.05 | 0.05 | 85.6% | -
RIVBROS Construction Factors and Development | [5 empty] | Calitlitan Communal Irrigation System | Umingan, Pangasinan, Region 1 | 2015-01-26 | 1st | NIA | L | 26.984 | 240 | 2014-03-28 | 2015-03-13 | 0 | O | 0.25 | 0.3 | 0.15 | 0.03 | 0.06 | 0.05 | 84 | -
RJ IBARRA CONSTRUCTION | 23538 | L | B | MA | GE | Off-Carriageway Improvement Olongapo - Bugallon Road, K0139+000 to K0139+810, Subic, Zambales | Subic, Zambales | 2015-06-07 | 1st | Zambales 2nd DEO | LF | 17.758 | 150 | 2015-01-12 | 2015-06-10 | 0.78% | O | 0.376 | 0.3 | 0.15 | 0.02 | 0.051 | 0.033 | 93% | -
RJIR Enterprises | 34843 | L | B | SB | GE | Widening of Road along Palo-Carigara-Ormoc Road Chainage 0+131 Leyte along Palo-Carigara-Ormoc Road, K1010+512 - K1010+562 | Ormoc City | 2014-08-07 | 1st & Final | VIII | LF | 4.33 | 120 | 2014-02-07 | 2014-04-07 | 20 | C | 0.403 | 0.133 | 0.3 |  |  |  | 83.6 | 83.60% Satisfactory
RJIR Enterprises | [5 empty] | BHHDRIS Contract No. 14-2015 | Hindang-Hilongos RIS, Hindang, Leyte | 2015-11-21 | 1st | NIA | LF | 6.373 | 240 | 2015-07-02 | 2015-03-02 | 11.43 | O | 0.343 | 0.237 | 0.15 | 0.023 | 0.045 | 0.05 | 84.8 | -
RJIR ENTERPRISES | 34843 | L | A | MA | GE | Construction of Access Road to Hilongos Port, Hilongos Leyte | Hilongos Leyte | 2015-06-03 | 1st | Leyte Fifth DEO | LF | 8.928 | 90 | 2015-04-01 | 2015-06-29 | - | O | 0.315 | 0.239 | 0.15 | 0.03 | 0.055 | 0.033 | 82.2% | -
RJIR ENTERPRISES | 34843 | L | B | SB | GE | Local Infrastructure Program- Construction of Leyte Water System Level II Spring System, Brgy. Poblacion, Leyte, Leyte | Brgy. Poblacion, Leyte, Leyte | 2015-05-18 | Final | Leyte Third DEO | LF | 4.777 | 90 | 2015-07-01 | 2015-09-28 | - | C | 0.454 | 0.163 | 0.3 | - | - | - | 91.7% | *91.7% Very Satisfactory
RJIR ENTERPRISES | 34843 | L | B | SB | GE | Rehabilitation/Major Repair of Permanent Bridges, Canaya Bridge (B00547LT) along Daang Maharlika, Mahaplag, Leyte | Mahaplag, Leyte | 2015-08-29 | 1st & Final | Leyte 5th DEO | LF | 7.205 | 162 | 2015-03-02 | 2015-08-10 | - | C | 0.432 | 0.133 | 0.3 | - | - | - | 86.5% | *86.5% Satisfactory
RJIR ENTERPRISES | 34843 | L | B | SB | GE | Construction of Calubian-Jubay Road-1115IE-0013, Sta. 4+080-Sta. 6+080, Calubian, Leyte | Calubian, Leyte | 2015-11-13 | Final | Leyte Third DEO | LF | 9.2515 | 120 | 2015-01-23 | 2015-05-22 | - | C | 0.285 | 0.133 | 0.3 | - | - | - | 71.8% | 71.8% Poor
RJIR ENTERPRISES/ARCA BUILDERS JOINT VENTURE | JV-14-350 | L | B | SB | GE | Repair/Rehabilitation/Improvement (Additional Pavement Width) along Ormoc-Baybay So. Leyte Boundary Road, K1019+429.30 - K1020+649.39 w/ exceptions | K1019+429.30 - K1020+649.39 w/ exceptions | 2015-05-18 | Final | Leyte Fourth DEO | LF | 10.582 | 90 | 2014-12-11 | 2015-03-10 | - | C | 0.396 | 0.2 | 0.3 | - | - | - | 89.6% | *89.6% Very Satisfactory
RJIR ENTERPRISES/ROLANDO M. VILLASENCIO CONSTRUCTION & GENERAL SERVICES JOINT VENTURE | JV-14-373 | L | B | MA | GE | Construction of Drainage Lines along Palo-Carigara-Ormoc Road, K999+000 to K1000+680; K1005+441.80 to K1006+000; K1006+000 to K1006+544.3, Ormoc City | K999+000 to K1000+680; K1005+441.80 to K1006+000; K1006+000 to K1006+544.3, Ormoc City | 2015-06-06 | 1st | Leyte Fourth DEO | LF | 31.658 | 214 | 2015-02-05 | 2015-09-06 | - | O | 0.336 | 0.24 | 0.15 | 0.03 | 0.045 | 0.05 | 85.1% | -
RKKI Construction | 33492 | L | D | SB | GE1 | Replacement/Rehab./Strengthening of Kapayawan Bridge along Mt. Province-Ilocos Sur via Tue Rd. | Bauko, Mt. Province | 2013-08-02 | 1st | CAR | LF | 4.171 | 140 | 2013-04-02 | 2013-08-19 | -5.15 | O | 0.367 | 0.24 | 0.099 | 0.015 | 0.048 | 0.033 | 80.2
RKKI Construction | 33492 | L | D | SB | GE1 | Replacement of Losong Bridge along Mt. Province-Ilocos Sur via Kayan Rd. | Tadian, Mt. Province | 2013-03-16 | Final | CAR | LF | 8.456 | 150 | 2012-03-09 | 2012-08-05 | - | C | 0.444 | 0.2 | 0 | - | - | - | 64.4 | 68.42% Poor
RLK Construction & Builders | 32194 | L |  | SB | GE2 | Construction of Lateral "A" at Sta. 4+876 - Sta 5+299.75 of Laris | Rosales, Pangasinan Region I | 02/27-03/03/12 | 1st | NIA | FA | 6.856 | 90 | 2011-11-21 | 2012-02-17 | 0.19 | O | 0.3763 | 0.24 | 0.15 | 0.03 | 0.0525 | 0.05 | 89.88 | -
RMS Builder and Supply | 19490 | L | D | SB | GE1 | Prev. Maint. RT Lim Blvd. (Dual) Chainage 0063-Chainage 0823 | Zamboanga City | 2013-08-05 | 1st | IX | LF | 4.621 | 121 | 2013-02-25 | 2013-06-26 | - | O | 0.363 | 0.294 | 0 | 0.03 | 0.047 | 0.033 | 76.7
RMS Builders and Supply | 19490 | L | D | SB | GE | Rehabilitation of Local Road at Sta. Maria - Gov. Ramos Intersection | Sta. Maria, Zamboanga City | 2014-08-05 | 1st | IX | LF | 6.9906 | 102 | 2014-05-02 | 2014-08-11 | -4.95 | O | 0.35 | 0.3 | 0.105 | 0.03 | 0.041 | 0.033 | 85.9
RMS Builders and Supply | 19490 | L | D | SB | GE | Preventive Maintenance of R.T. Lim Boulevard (Dual Chainage 0063 - Chainage 0823 | Zamboanga City | 2014-08-05 | Final | IX | LF | 4.5199 | 166 | 2013-02-25 | 2013-08-09 | 0 | C | 0.425 | 0.139 | 0.3 |  |  |  | 86.4 | 80.58% Unsatisfactory
RND Construction | 7035 | L | D | SB | GE4 | Agno River Integrated Irrigation Project |  | 7/13-18/09 | 1st | NIA |  | 3.806 | 90 |  |  |  | O | 0.3446 | 0.3 | 0.15 | 0.015 | 0.0382 | 0.0333 | 88.11 | -
RNMK Construction and Development | 35680 | L | A | SB | GE | Kalanggaman Island Development Project (Jetty Port) | Kalanggaman Island, Palompon, Leyte | 2016-04-28 | Final | TIEZA | LF | 7.5 | 90 | 2016-01-27 | 2016-04-25 |  | C | 0.5 | 0.2 | 0.3 |  |  |  | 100 | 100% Outstanding
RNMK Construction and Development | 35680 | L | A | SB | GE | Rehabilitation and Expansion of DOT Regional Office | Tacloban City | 2016-06-09 | 1st | TIEZA | LF | 7 | 150 | 2016-01-28 | 2016-06-25 | -25.90 | O | 0.395 | 0.3 | 0 | 0.03 | 0.07 | 0.033 | 82.8
RNV CONSTRUCTION | 12570 | L | D | SB | GB | Const./Rehab. of MPB @ Odiongan National High School Dapawan | Odiongan, Romblon | 2015-11-21 | Final | Romblon DEO | LF | 3.757 | 90 | 2015-07-08 | 2015-10-05 | 0 | C | 0.466 | 0.133 | 0.3 | - | - | - | 89.9% | 89.9% Very Satisfactory
RNV CONSTRUCTION | 12570 | L | D | SB | GB | Const. of Road, Libertad-Tuburan Road | Odiongan, Romblon | 2015-11-21 | Final | Romblon DEO | LF | 4.8349 | 60 | 2015-03-11 | 2015-05-09 | 0 | C | 0.444 | 0.133 | 0.3 | - | - | - | 87.7% | 87.7% Satisfactory
Road Edge Trading & Development Services | 33140 | L | A | MA | GE | Preventive Maintenance Based on PMS/HDM-4 (Intermittent Section), along Surigao City - San Juan Coastal Road | Surigao City | 2014-08-13 | 1st & Final | XIII | LF | 15.3499 | 71 | 2014-02-26 | 2014-05-07 | 0 | C | 0.371 | 0.133 | 0.3 |  |  |  | 80.4 | 80.40% Unsatisfactory
Road Edge Trading & Development Services | 33140 | L | A | MA | GE | Repair/Rehab./Improvement along Surigao - Agusan Road, Sta. 1150+375 - Sta. 1146+800 with Exceptions, Timamana | Timamana, Tubod, Surigao del Norte | 2014-08-13 | Final | XIII | LF | 4.743 | 78 | 2013-05-27 | 2013-08-13 | 7.52 | C | 0.296 | 0.136 | 0.3 |  |  |  | 73.2 | 81.18% Unsatisfactory
Road Edge Trading & Development Services | 33140 | L | A | MB | GE1 | Repair/Rehab./Impv't. along Surigao-Agusan Rd,. Sta.1150+37 -Sta.1146+800 w/ exceptions | Timamana, Tubod, Surigao del Norte | 2013-08-07 | 1st | XIII | LF | 4.743 | 78 | 2013-05-27 | 2013-08-13 | 1.24 | O | 0.362 | 0.223 | 0.15 | 0.03 | 0.05 | 0.05 | 86.5
Road Edge Trading & Development Services | 33140 | L | A | MA | GE | Protection Works along Dinagat - Loreto Road (Paragua Section) | Tubajon, Dinagat Island | 2014-08-14 | 1st | XIII | LF | 9.1829 | 100 | 2014-03-10 | 2014-06-17 | -14.88 | O | 0.202 | 0.24 | 0.001 | 0.03 | 0.023 | 0.033 | 52.9
Road Edge Trading & Development Services | 33140 | L | A | MA | GE | Major Repair/Maintenance of Existing Permanent Bridges, Lagonglong Bridge Along BCIR | Lagonglong Bridge Along Butuan City-Cagayan de Oro City-Iligan City | 2014-08-11 | 1st | X | LF | 4.576 | 180 | 2014-01-20 | 2014-06-09 | 0.3 | O | 0.388 | 0.265 | 0.15 | 0.023 | 0.048 | 0.033 | 90.7
Road Edge Trading & Development Services | 33140 | L | A | MA | GE | Construction of Drainage Canal along Butuan City-Cagayan de Oro City-Iligan City Road | K1313+000 - K1314+000, Misamis Oriental | 2014-08-11 | 1st | X | LF | 13.8089 | 210 | 2014-01-20 | 2014-10-29 | 6.77 | O | 0.4 | 0.3 | 0.15 | 0.008 | 0.029 | 0.033 | 92
ROAD EDGE TRADING & DEVELOPMENT SERVICES | 33140 | L | A | MB | GE | Rehabilitation/ Reconstruction of National Roads w/ Slips, Slope Collapse and Landslide, Nasipit Road | K1264+311 - K1264+455, Nasipit Port Road, Agusan Del Norte | 2015-06-02 | 1st | AGUSAN DEL NORTE DEO | LF | 9.301 | 116 | 2015-03-27 | 2015-07-20 | (+) 29.82% | O | 0.394 | 0.227 | 0.15 | 0.03 | 0.05 | 0.05 | 90.1% | -
ROAD EDGE TRADING & DEVELOPMENT SERVICES | 33140 | L | A | SB | GE | Construction of Binalbagan River Bank Slope Protection (Upstream) along Bacolod South Road, Negros Occidental 5th Legislative District | Binalbagan, Negros Occidental | 2015-08-27 | 1st | Negros Occidental 2nd | LF | 15.287 | 200 | 2015-02-25 | 2015-09-12 | 0.07% | O | 0.398 | 0.24 | 0.15 | 0.03 | 0.047 | 0.05 | 91.5% | -
ROAD EDGE TRADING & DEVELOPMENT SERVICES | 33140 | L | A | SB | GE | Construction of Binalbagan River Bank Slope Protection (Upstream) along Bacolod South Road, Negros Occidental 5th Legislative District, Binalbagan, Negos Occidental | Negros Occidental 5th Legislative District, Binalbagan, Negos Occidental | 2015-11-16 | Final | Negros Occidental 2nd DEO | LF | 15.2873 | 230 | 2015-02-25 | 2015-10-12 | - | C | 0.45 | 0.133 | 0.3 | - | - | - | 88.3% | 90.22% Very Satisfactory
Roadtech Construction | 17580 | L | B | MA | GE | Preventive Maintenance along Lingayen-Labrador Diversion Road K0364+690- K0366+000 | Lingayen, Pangasinan | 2014-10-28 | 1st & Final | I | LF | 13.5839 | 16 | 2014-03-03 | 2014-03-18 | 0% | C | 0.361 | 0.2 | 0.3 | - | - | - | 86.1% | 86.1% Satisfactory
Roadtech Construction | 17580 | L | B | MB | GE1 | Replacement of Udiao Bridge | Rosales, Pangasinan | 2013-03-13 | 1st | I | LF | 32.104 | 210 | 2012-07-20 | 2013-02-14 | -42 | O | 0.374 | 0.285 | 0 | 0.023 | 0.04 | 0.017 | 73.9 | -
Roadtech Construction | 17580 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rds. along Urdaneta Jct.-Dagupan Rd. Km.203+459-Km.206+777 w/ exception | Calasiao, Pangasinan | 2011-08-16 | 2nd | I | LF | 15.589 | 190 | 2011-02-21 | 2011-08-29 | 3.16 | O | 0.383 | 0.3 | 0.15 | 0.03 | 0.045 | 0.05 | 95.8 | -
Roadtech Construction | 17580 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved National Roads along Urdaneta Jct.-Dagupan Road, Km.203+459 - Km. 206+777 w/ exception | Calasiao, Pangasinan | 2011-04-07 | 1st | I | LF | 15.589 | 150 | 2011-02-21 | 2011-07-20 | 14.89 | O | 0.39 | 0.24 | 0.15 | 0.018 | 0.037 | 0.033 | 86.8 | -
ROADTECH CONSTRUCTION | 17580 | L | B | MA | GE | Rehabilitation/Reconstruction/Upgrading of Pangasinan-Zambales Road K0233+000 - K0300+000, K0306+096 - K0307+197, K0308+000 - K0308+543, Burgos & Mabini, Pangasinan | Burgos & Mabini, Pangasinan | 2015-11-20 | Final | PANGASINAN 1ST DEO | LF | 37.0861 | 240 | 2015-06-09 | 2016-02-03 | 0.0049 | C | 0.369 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 89.4% | 89.4% Very Satisfactory
ROBETH GEN. DSE. CONST. & SUPPLY (Formerly: Robeth Gen. Mdse. & Supplies - Isulan Branch) | 23175 | L | B | SB | GB | Construction of MPB at Brgy. D'Lotilla | Isulan, Sultan Kudarat | 2015-08-31 | 1st & Final | Sultan Kudarat 1st | LF | 2.463 | 138 | 2015-03-04 | 2015-07-19 | 0% | C | 0.496 | 0.133 | 0.3 | - | - | - | 92.9% | *92.9% Very Satisfactory
Robeth Gen. Mdse. Const. & Supply (Formerly: Robeth Gen. Mdse & Supplies-Isulan Branch) | 23175 | L | B | MA | GE1 | Strengthening/Reconst./Replacement of Pamintuan Bridge (24 L.M. Flatslab) along Makilala-Ala Valley Rd. C006+152-C006+224 (24 LM Flatslab) | Makilala, Cotabato | 2012-08-11 | 1st | XII | LF | 10.336 | 226 | 2012-02-06 | 2012-09-18 | 0 | O | 0.381 | 0.278 | 0.15 | 0.03 | 0.051 | 0.05 | 94 | -
Robeth Gen. Mdse. Const. & Supply (Formerly: Robeth Gen. Mdse. & Supplies - Isulan Branch) | 23175 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Paved) along Awang-Upi-Lebak-Kalamansig-Palimbang-Sarangani Road (Km.1963+471-Km.1977+121) Realign to Rd. Upgrading (Gravel to Paved) along Awang-Upi-Lebak - Kalamasig-Palimbang-Sarangani Rd. (Km.1954+708-Km.1957+000 w/ exception), Kalamansig-Palimbang | Sultan Kudarat | 2013-08-15 | Final | XII | LF | 33.43 | 309 | 2012-07-06 | 2013-05-10 | 0 | C | 0.41 | 0.2 | 0.3 | - | - | - | 91 | 89.02% V. Satisfactory
Robeth Gen. Mdse. Const. & Supply (Formerly: Robeth Gen. Mdse. & Supplies - Isulan Branch) | 23175 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Paved) Int. Sect. along Isulan Jct. Ninoy Rd., Km.1777+474-Km.1778+125, Km.1779+077-Km.1778+806, Km.1780+175, Km.1780+965-Km.1781+589 | Isulan, Sultan Kudarat | 2013-08-17 | 1st | XII | LF | 34.932 | 215 | 2013-01-30 | 2013-09-01 | 0.66 | O | 0.308 | 0.3 | 0.15 | 0.03 | 0.048 | 0.033 | 86.9
Robeth Gen. Mdse. Const. & Supply (Formerly: Robeth Gen. Mdse. & Supplies-Isulan Branch) | 23175 | L | B | MA | GE | Road Upgrading along Isulan Jct. Ninoy Aquino Road K1777+1474 - K1781+594 | Isulan, Sultan Kudarat | 2014-08-08 | Final | XII | LF | 34.9324 | 207 | 2013-01-30 | 2013-08-02 | 0 | C | 0.418 | 0.133 | 0.3 |  |  |  | 85.1 | 86.20% Satisfactory
Robeth Gen. Mdse. Const. & Supply (Formerly: Robeth Gen. Mdse. & Supplies-Isulan Branch) | 23175 | L | B | MA | GE | Construction of Road-Jose Abad Santos St. Purok 5, Poblacion Tulunan, Under Local Infrastructure Program, Poblacion Tulunan, Cotabato, Km. 0+000 to Km. 0+328 with 15.9 meters Exemption | Tulunan, Cotabato | 2014-10-24 | 1st & Final | XII | LF | 4.0007 | 49 | 2014-04-22 | 2014-06-09 | 0% | C | 0.41 | 0.133 | 0.3 | - | - | - | 84.3% | 84.3% Satisfactory
Robeth Gen. Mdse. Const. & Supply (Formerly: Robeth Gen. Mdse. & Supplies-Isulan Branch) | 23175 | L | B | MA | GE | Road Upgrading (Gravel to Concrete) along Isulan Hwy. Jct. Dukay-Bagumbayan-Sen. Aquino-Kalamansig Road (Km. 1859+046 - Km. 1850+218), Buenaflores | Sen. Ninoy Aquino, Sultan Kudarat | 2014-10-27 | 1st & Final | XII | LF | 26.8051 | 127 | 2014-02-22 | 2014-06-28 | 0% | C | 0.398 | 0.127 | 0.3 | - | - | - | 82.5% | 82.5% Satisfactory
Robeth Gen. Mdse. Const. & Supply (Formerly: Robeth Gen. Mdse. & Supplies-Isulan Branch) | 23175 | L | B | MA | GE1 | Strengthening/Reconst./Replacement of Pamintuan Bridge (24 Lm Flatslab) along Makilala-Ala Valley Rd. C006+152-C006+224 (24 lm Flatslab) | Makilala, Cotabato | 2012-11-20 | Final | XII | LF | 11.361 | 236 | 2012-02-06 | 2012-09-28 | 0 | C | 0.456 | 0.133 | 0.3 | - | - | - | 88.9 | 91.96% V. Satisfactory
Robeth Gen. Mdse. Const. & Supply (Formerly: Robeth Gen. Mdse. & Supplies-Isulan Branch) | 23175 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Paved) along Awang-Upi-Lebak-Kalamansig-Palimbang-Sarangani Rd. (Km.1963+471-Km.1977+121) realigned to Rd Upgrading (Gravel to Paved) along Awang-Upi-Lebak-Kalamansig-Palimbang-Sarangani Rd. (Km.1954+708-Km.1957+000 w/ exception) | Palimbang, Sultan Kudarat | 2013-03-14 | 1st | XII | LF | 33.43 | 309 | 2012-07-06 | 2013-05-10 | 26.58 | O | 0.337 | 0.255 | 0.15 | 0.03 | 0.055 | 0.05 | 87.7 | -
ROBETH GEN. MDSE. CONST. & SUPPLY (Formerly: Robeth Gen. Mdse. & Supplies-Isulan Branch) | 23175 | L | B | MA | GE | Repair/Rehabilitation/Improvement (Additional Pavement Width) along Marbel-Ala Valley-Cotabato Road, K1769+270.25 - K1769+931 (both sides) with exceptions | Isulan, Sultan Kudarat | 2015-11-10 | 1st | Sultan Kudarat First DEO | LF | 10.2643 | 121 | 2015-08-26 | 2015-12-24 | (+) 0.06% | OG | 0.378 | 0.254 | 0.15 | 0.015 | 0.04 | 0.05 | 88.7% | 88.7% Satisfactory
Robeth Gen. Mdse., Const. & Supplies-Isulan Branch | 23175 | L | B | MA | GE1 | Road Upgrading, Gamasil Section |  | 2009-03-13 | 2nd | XII |  | 14.048 | 225 |  |  |  | O | 0.39 | 0.3 | 0.15 | 0.03 | 0.06 | 0.05 | 98 | -
Robeth Gen. Mdse., Const. & Supplies-Isulan Branch | 23175 | L | B | MA | GE1 | Road Upgarding, Gamasil Section |  | 2008-11-26 | 1st | XII |  | 14.048 | 225 |  |  |  | O | 0.161 | 0.3 | 0.1 | 0.03 | 0.043 | 0.1 | 73.4 | -
ROBETH GEN.MDSE. CONST. & SUPPLY ( Formerly : Robeth Gen. Mdse. & Supplies-Isulan Branch | 23175 | L | B | MA | GE | Rehabilitation/Major Repair of Permanent Bridge at Sadsalan Bridge along Dulawan-Marbel Road | Lambayong, Sultan Kudarat | 2015-06-03 | 1st | Sultan Kudarat 1st DEO | LF | 5.402 | 114 | 2015-03-04 | 2015-06-25 | 1.86% | O | 0.368 | 0.24 | 0.15 | 0.03 | 0.032 | 0.05 | 87% | -
ROBIG Builders and Development Corporation | 35327 | L |  |  |  | Safety Signages Works along SCTEX | Subic-Pampanga-Tarlac | 2015-03-12 | 1st & Final | BCDA | L | 12.379 | 60 | 2014-11-30 | 2015-01-28 | 0 | C | 0.45609 | 0.2 | 0.3 | - | - | - | 95.609 | *95.61% V. Satisfactory
ROCKSTONE CONSTRUCTION SERVICES AND SUPPLY | 22702 | L | A | SB | GE | Rehabilitation/Repair of Kansan Bridge along Sarangani-Sultan, kudarat Coastal Orad | Kiamba, Sarangani Province | 2014-11-26 | Final | Sarangani DEO | LF | 0.99 | 60 | 2015-02-23 | 2015-04-23 | 0% | C | 0.442 | 0.133 | 0.3 | - | - | - | 87.5% | *87.5% Satisfactory
Rockworld Industries | 7852 | L | B | MB | GE | Off Carriage-way Improvement Paving of Shoulders (Seal Widening) Dulag - Julita - Buraen Road KO944+000 - KO944+214, Brgy. San Vicente - Brgy. Del Pilar | Dulag, Leyte | 2014-08-09 | 1st | VIII | LF | 22.5021 | 150 | 2014-03-27 | 2014-08-23 | 0.32 | O | 0.37 | 0.228 | 0.15 | 0.03 | 0.045 | 0.033 | 85.6
Rockworld Industries | 7582 | L | B | MA | GE1 | Rehab./Reconst. of Damaged Paved Nat'l. Rd. along Dulag-Julita-Burauen Rd., K0941+000-K0945+600; K0947+000-K0948+300 | Dulag, Leyte | 2013-03-11 | 1st | VIII | LF | 18.268 | 135 | 2013-01-15 | 2013-05-30 | 10.26 | O | 0.353 | 0.225 | 0.15 | 0.023 | 0.05 | 0.05 | 85.1 | -
Rockworld Industries | 7582 |  |  |  |  | Const. of Burauen-Mahagnao Rd. |  | 2010-05-31 |  | VIII |  | 10.713 | 120 |  |  |  | O | 0.371 | 0.3 | 0.104 | 0.03 | 0.042 | 0.033 | 88 | -
ROCKWORLD INDUSTRIES | 7582 | L | B | MA | GE | Construction/Improvement of Access Road Leading to Tourisim Destination-Road Concreting of Poblacion, La Paz to Colabato Hot Spring, La Paz, Leyte | La Paz, Leyte | 2015-11-12 | 1st | Leyte Second DEO | LF | 45.0777 | 148 | 2015-06-11 | 2015-11-05 | (-)3.99% | OG | 0.333 | 0.3 | 0.11 | 0.03 | 0.035 | 0.017 | 82.5% | 82.5% Satisfactory
Roda Construction and General Supply | 19674 |  |  |  |  | Conc. of Ariman-Bulusan Lake Road |  | 2010-05-26 |  | V |  | 19.2 | 82 |  |  |  | O | 0.352 | 0.237 | 0.15 | 0.03 | 0.035 | 0.033 | 83.7 | -
Roda Construction and General Supply | 19674 | L | B | MA | GE1 | Rehab./Impvt. of Sitio Wawa-Brgy. Lajong Road |  | 2009-08-26 | 1st | V |  | 1.92 | 60 |  |  |  | O | 0.314 | 0.269 | 0.15 | 0.03 | 0.047 | 0.05 | 86 | -
RODOLFO R. SANTIAGO CONSTRUCTION | 32580 | L | B | SB | GB | Construction of Multi-Purpose Building, Barangay Sta. Cruz I, San Jose del Monte City, Bulacan | Barangay Sta. Cruz I, San Jose del Monte City, Bulacan | 2015-08-30 | 1st & Final | Bulacan Second DEO | LF | 0.948 | 60 | 2015-02-16 | 2015-04-16 | - | C | 0.479 | 0.133 | 0.3 | - | - | - | 91.2% | *91.2% Very Satisfactory
ROGENOX CONSTRUCTION AND SUPPLY CORP. | 32475 | L | A | SB | GE | Construction/Extension of Dike with Protection Works, Viray-Depalo River Control Project, Brgy. San Miguel, Natividad, Pangasinan | Natividad, Pangasinan | 2015-11-16 | 1st | PANGASINAN 3RD DEO | LF | 14.7 | 120 | 2015-07-31 | 2015-11-27 | 0.0394 | OG | 0.383 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 90.8% | 90.8% Very Satisfactory
Roim Builders & Construction Supply | 20226 | L | B | MA | GE | Road Upgrading (Gravel to Paved) along Butuan City-Talacogon-Loreto-Veruela-Sta. Josefa Road (K1331+180 - K1332+490.10) | Talacogon, Agusan del Sur | 2014-10-22 | 1st & Final | XIII | LF | 27.9367 | 257 | 2014-02-11 | 2014-10-25 | 9.82% | C | 0.407 | 0.132 | 0.3 | - | - | - | 83.9% | 83.9% Satisfactory
Roim Builders & Construction Supply | 20226 | L | B | MA | GE | Road Upgrading (Gravel to Paved) along Butuan City - Talacogon - Loreto - Veruela - Sta. Josefa Road, K1325+992 - K1328+427 | San Luis, Agusan del Sur | 2014-08-06 | Final | XIII | LF | 48.9999 | 287 | 2013-03-16 | 2013-12-27 | 3.55 | C | 0.341 | 0.2 | 0.3 |  |  |  | 84.1 | 82.96% Satisfactory
Roim Builders & Construction Supply | 20226 | L | B | MA | GE1 | Const./Rehab. of Rd. Slip along NRJ-Bahbah-Talacogon Rd. (Sta.1305+350.00-Sta.1310.40 L/S (Slip 3); Sta.1305+803.60-Sta.1305+870.20 R/S (Slip 4) Prosperidad & Talacogon | Agusan del Sur | 2013-08-21 | Final | XIII | LF | 14.146 | 350 | 2012-05-04 | 2013-04-18 | 0.3 | C | 0.411 | 0.133 | 0.3 | - | - | - | 84.4 | 85.38% Satisfactory
Roim Builders & Construction Supply | 20226 | L | B | MA | GE1 | Road Upgrading from Gravel to Paved along Butuan City-Talacogon-Loreto-Veruela-Sta. Josefa Rd. K1325+992-K1328+427 | San Luis, Agusan del Sur | 2013-08-21 | 1st | XIII | LF | 45.086 | 209 | 2013-03-16 | 2013-10-10 | 2.46 | O | 0.267 | 0.3 | 0.15 | 0.015 | 0.04 | 0.05 | 82.2
Roim Builders & Construction Supply | 20226 | L | B | MA | GE1 | Const./Rehab. of Slip along NRJ-Bahbah-Talacogon Rd. (Sta. 1305+350.00-Sta. 1310.40 L/S (Slip 3); Sta.1305+803.60-Sta.1305+870.20 R/S (Slip 4) | Prosperidad, Agusan del Sur | 2013-03-20 | 3rd | XIII | LF | 14.146 | 350 | 2012-05-04 | 2013-04-18 | 2.06 | O | 0.325 | 0.3 | 0.15 | 0.03 | 0.032 | 0.033 | 87 | -
Roim Builders & Construction Supply | 20226 | L | B | MA | GE1 | Const./Rehab. of Rd. Slip along NRJ Bahbah-Talacogon Rd., Sta. K1305+350-Sta. K1310.40L/S (Slip 3); Sta. 1305+803.60-Sta. 1305+870.2 R/S (Slip 4) | Prosperidad, Agusan del Sur | 2012-11-28 | 2nd | XIII | LF | 14.146 | 300 | 2012-05-04 | 2013-02-27 | 0.49 | O | 0.252 | 0.278 | 0.15 | 0.03 | 0.065 | 0.05 | 82.5 | -
Roim Builders & Construction Supply | 20226 | L | B | MA | GE1 | Const./Rehab. of Rd. Slip along NRJ-Bahbah-Talacogon Rd. (Sta. 1305+350.00-Sta. 1310.40 L/S (Slip 3); Sta.1305+803.60-Sta.1305+870.20 R/S (Slip 4) | Prosperidad, Agusan del Sur | 2012-08-18 | 1st | XIII | LF | 14.146 | 270 | 2012-05-04 | 2013-01-28 | 0.95 | O | 0.311 | 0.3 | 0.15 | 0.03 | 0.045 | 0.05 | 88.6 | -
ROIM BUILDERS & CONSTRUCTION SUPPLY/JIMBERNS BUILDERS & CONSTRUCTIONN SUPPLY JOINT VENTURE | 0 | L | B | MA | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Road along Daang Maharlika (Agusan-Davao Section), Sibagat, Agusan del Sur | Sibagat, Agusan del Sur | 2015-11-09 | Final | Agusan del Sur 1st DEO | LF | 10.7149 | 194 | 2015-03-03 | 2015-09-12 | - | C | 0.426 | 0.2 | 0.3 | - | - | - | 92.6% | 92.6% Very Satisfactory
Rojuned Construction | 13483 | L | D | SB | GE | Road Upgrading (Gravel to Concrete) Along Alfonso Lista-Aurora Bdry Road, K0440+(-158) - K00441+347 (K0442+100) Intermittent Section | Alfonso, Lista, Ifugao | 2014-08-06 | 1st & Final | CAR | LF | 1.2462 | 60 | 2014-01-16 | 2014-03-16 | 0 | C | 0.43 | 0.133 | 0.3 |  |  |  | 86.3 | 86.30% Satisfactory
Rola Construction | 6813 | L | B | MA | GE | Concreting of Pugay-Bongliw-Yade-Tambangan Road | San Jose, Camarines Sur | 2014-08-09 | Final | V | LF | 2.779 | 60 | 2013-06-10 | 2013-08-08 | 0 | C | 0.329 | 0.2 | 0.3 |  |  |  | 82.9 | 84.82% Satisfactory
Rola Construction | 6813 | L | B | MA | GE1 | Conc. of Pugay-Bongliw-Yade-Tambangan Rd. | San Jose , Camarines Sur | 2013-08-02 | 1st | V | LF | 2.779 | 60 | 2013-06-10 | 2013-08-08 | 0.47 | O | 0.363 | 0.24 | 0.15 | 0.03 | 0.045 | 0.033 | 86.1
Rola Construction | 6813 | L | B | SB | GB1 | Indv. Project-Const. of Two Storey 8-Cl Sch. Bldg. Nonito Paz Arroyo Memorial Nat'l High Sch., Sagrada Familia | Baao, Camarines Sur | 2012-08-09 | 1st | V | LF | 9.555 | 180 | 2012-04-13 | 2012-10-10 | 22.9 | O | 0.37 | 0.24 | 0.15 | 0.03 | 0.05 | 0.033 | 87.3 | -
Rola Construction | 6813 | L | B | MA | GE | Cluster : Concreting of Local Roads at Lupi, Del Gallego and Sipocot, Camarines Sur | Lupi, Del Gallego and Sipocot, Camarines Sur | 2014-11-09 | 1st & Final | V | LF | 1.8775 | 90 | 2014-06-13 | 2014-09-10 | 1.11% | C | 0.453 | 0.133 | 0.3 | - | - | - | 88.6% | 88.6% Satisfactory
Rola Construction | 6813 | L | B | SB | GB | Capiz National High School, Roxas City (capital), Capiz (b) Const. of Two (2) Storey, 4 Classrooms School Building | Roxas City, Capiz | 2014-08-14 | Final | VI | LF | 4.6753 | 245 | 2013-04-18 | 2013-11-13 | 0 | C | 0.402 | 0.2 | 0.3 |  |  |  | 90.2 | 85.93% Satisfactory
Rola Construction | 6813 | L | B | SB | GB1 | Capiz NHS, Roxas City (Capital), Capiz, (b) Const. of 2-Storey, 4 Cl Sch. Bldg. | Roxas City, Capiz | 2013-08-18 | 1st | VI | LF | 4.493 | 210 | 2013-04-18 | 2013-11-13 | 1.75 | O | 0.317 | 0.24 | 0.15 | 0.03 | 0.054 | 0.05 | 84.1
Rola Construction | 6813 |  |  |  |  | Road Upgrading, Roxas City Boundary, Panitan-Bailan Rd. |  | 2010-03-01 |  | VI |  | 19.099 | 238 |  |  |  | O | 0.332 | 0.3 | 0.15 | 0.01 | 0.028 | 0.033 | 85.3 | -
ROLA CONSTRUCTION | 6813 | L | B | SB | GE | FY 2015 Local Infrastructure Program-Construction of Seawall Sabang, San Jose, Camarines Sur | San Jose, Camarines Sur | 2015-11-15 | Final | Camarines Sur Third DEO | LF | 4.7186 | 79 | 2015-05-19 | 2015-08-05 | - | C | 0.479 | 0.067 | 0.3 | - | - | - | 84.6% | 84.6% Satisfactory
Roland Construction | 19201 | L | C | SB | GE | Road Upgrading (Gravel to Paved) Jct. Gamut-San Miguel-Bayugan Road (K1318+565 - K1318+756.85) | Tago, Surigao City | 2014-10-25 | 1st & Final | XIII | LF | 4.1226 | 56 | 2014-03-18 | 2014-05-12 | 2.52% | C | 0.415 | 0.175 | 0.3 | - | - | - | 89% | 89% Satisfactory
ROLANDO M. VILLASENCIO CONST & GENERAL SERVICES | 24797 | L | B | SB | GE | Construction of Tugbong Flood Control, Kananga, Leyte | Kananga, Leyte | 2015-11-14 | Final | Leyte Fourth DEO | LF | 12.4462 | 120 | 2015-01-05 | 2015-05-04 | - | C | 0.424 | 0.2 | 0.3 | - | - | - | 92.4% | 92.4% Very Satisfactory
Rolco Construction & Development Corporation (Formerly: Rolco Construction & General Merchandise) | 29686 | L | B | MA | GE | Local Infrastructure Program - Construction of Road Brgy. Nagotgot | Manito, Albay | 2014-11-15 | 1st & Final | V | LF | 4.7811 | 52 | 2014-05-23 | 2014-07-13 | 0% | C | 0.462 | 0.2 | 0.069 | - | - | - | 73.1% | 73.1% Poor
Rolco Construction & Development Corporation (Formerly: Rolco Construction & General Merchandise) | 29686 | L | B | MA | GE | Contract Package No. 01 (Installation of Road Safety Devices and Pavement Markings) g. Goa-Digdigon-San Isidro Road (Pinaglabanan Section) | Goa, Camarines Sur | 2014-11-13 | 1st & Final | V | LF | 0.75027 | 45 | 2014-07-01 | 2014-08-14 | 0% | C | 0.469 | 0.133 | 0.3 | - | - | - | 90.2% | 90.2% Very Satisfactory
ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION (Formerly: Rolco Construction & General Merchandise) | 29686 | L | B | MA | GE | Local Infrastructure Program - Construction/Repair/Rehabilitation of Puro Taysan Road (Improvement of Road Shoulders), Legazpi City, Albay 2nd LD | Legazpi City, Albay 2nd LD | 2015-08-25 | 1st & Final | Albay Second DEO | LF | 9.212 | 74 | 2015-06-03 | 2015-08-15 | - | C | 0.493 | 0.133 | 0.3 | - | - | - | 92.6% | *92.6% Very Satisfactory
ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION (Formerly: Rolco Construction & General Merchandise) | 29686 | L | B | MA | GE | Cluster 2 - Off-Carriageway Improvement along Daang Maharlika, Daraga, Albay | Daraga, Albay | 2015-11-10 | Final | Albay Second DEO | LF | 6.715 | 70 | 2015-02-09 | 2015-04-19 | - | C | 0.39 | 0.133 | 0.3 | - | - | - | 82.3% | 82.3% Satisfactory
Roma Construction and Development Corporation | 6514 | L | AA | LA | GE1 | Completion of Agbalo Bridge along Iloilo East Coast Capiz Road | Poneteverdra, Capiz | 2012-03-26 | 1st | VI | LF | 85.106 | 360 | 2011-10-07 | 2012-09-30 | 3.63 | O | 0.4 | 0.181 | 0.15 | 0.03 | 0.035 | 0.05 | 84.6 | -
ROMA CONSTRUCTION AND DEVELOPMENT CORPORATION | 6514 | L | AAA | MA | GE | Construction of Maayon River Control System Maayon River Control 9 (Downstream) | Maayon, Capiz | 2015-06-06 | 1st | Capiz First DEO | LF | 16.72 | 155 | 2015-01-25 | 2015-06-28 | 0% | O | 0.338 | 0.256 | 0.15 | 0.015 | 0.035 | 0.05 | 84.4% | -
ROMA CONSTRUCTION AND DEVELOPMENT CORPORATION | 6514 | L | AAA | MA | GE | Construction of Maayon River Control System, Maayon River Control (Downstream) | Maayon, Capiz 1st | 2015-09-02 | 1st & Final | Capiz 1st | LF | 16.72 | 185 | 2015-01-25 | 2015-07-28 | 0% | C | 0.45 | 0.133 | 0.3 | - | - | - | 88.3% | *88.3% Satisfactory
ROMA CONSTRUCTION AND DEVELOPMENT CORPORATION / DPJ ENGINEERS & CONSULTANTS JOINT VENTURE | JV-14-638 | L | AAA | LA | GE | Road Upgrading (Unpaved to Paved) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standards (HDM-4 Project Analysis) Intermittent Sectionsalong Mt. Province - Isabela Road, Chainage 0 - Chainage 798, Chainage 1220 - Chainage 1315, Chainage 1420 - Chainage 3890, Chainage 3930 - Chainage 6941, Chainage 7524 - Chainage 9300, | Mt. Province | 2015-11-18 | 1st | Regional Office | LF | 163.36 | 419 | 2015-06-29 | 2016-08-20 | 49.49% | OG | 0.338 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 86.3% | 86.3% Satisfactory
ROMA CONSTRUCTION AND DEVELOPMENT/JMT CONSTRUCTION JOINT VENTURE | 0 | L | AAA | LA | GE | Upgrading (Unpaved to Paved) of Dinagat-Loreto Road, K4+710 - K4+882, K4+882.18 - K5+647.89, K5+651.49 + K5+651.49 - K6+441.81, K6+505.54 - K6+735.36, K6+887.58 - K8+662.58, K8+689.66 - K9+965, Dinagat Island | Diangat Island | 2015-11-16 | 1st | Regional Office | LF | 196.5267 | 380 | 2015-06-20 | 2016-07-09 | (+) 31.15 | OG | 0.353 | 0.23 | 0.15 | 0.03 | 0.061 | 0.05 | 87.4% | 87.4% Satisfactory
ROMANA CONSTRUCTION & ENTERPRISES | 14661 | L | B | MA | GE | Rehab/Reconst/Upgrading of Damaged Paved National Roads Including Drainage Based on Pavement Management System/Highway Development and Management-4 (HDM-4) (Intermittent Section), Ozamis-Oroquieta Road, K1703+000-K1703+680; K1705+011-K1706+217; K1708+614-K1709+002 | Ozamis-Oroquieta Road, K1703+000-K1703+680; K1705+011-K1706+217; K1708+614-K1709+002 | 2015-08-31 | 1st | Misamis Occidental 2nd DEO | LF | 36.368 | 220 | 2015-02-27 | 2015-10-04 | 12.27% | O | 0.362 | 0.239 | 0.15 | 0.03 | 0.045 | 0.033 | 85.9% | -
ROMARPLUS INCORPORATED (Formerly: Ramar Enterprises) | 8092 | L | B | MA | GE | Widening of National Roads along Guinobatan Poblacion Road, KO511+(-1007) - KO511+(-723.08), Polangui, Albay | Polangui, Albay | 2015-11-20 | Final | Albay Third DEO | LF | 6.5876 | 150 | 2015-06-15 | 2015-11-11 | 4.65% | C | 0.402 | 0.133 | 0.3 | - | - | - | 83.5% | 83.5% Satisfactory
Ronwood Construction & Supply | 25311 | L | AA | MA | GE1 | Impvt./ (Conc.) of Access Road Jct. BCIR to Balingoan Port Road |  | 2009-06-01 | 1st | X |  | 2.603 | 120 |  |  |  | O | 0.333 | 0.24 | 0.133 | 0.02 | 0.065 | 0.033 | 82.4 | -
Ronwood Construction & Supply | 25311 | L | AA | MA | GE | Widening of Butuan - Cagayan de Oro - Iligan Road (Agusan - Misamis Oriental Section) Nasipit Section, Sta. 1259+480 - Sta. 1261+253 | Nasipit, Agusan del Norte | 2014-08-04 | Final | XIII | LF | 34.5474 | 221 | 2013-02-08 | 2013-09-16 | 0 | C | 0.391 | 0.143 | 0.3 |  |  |  | 83.4 | 84.60% Satisfactory
Ronwood Construction & Supply | 25311 | L | AA | MA | GE1 | Widening of Butuan-Cagayan de Oro-Iligan Rd. (Agusan-Misamis Oriental Sect.) Nasipit Sect., Sta.1259+480-Sta.1261+253 | Nasipit, Agusan del Norte | 2013-03-12 | 1st | XIII | LF | 34.547 | 157 | 2013-02-08 | 2013-07-14 | 12.43 | O | 0.358 | 0.233 | 0.15 | 0.03 | 0.05 | 0.033 | 85.4 | -
Ronwood Construction & Supply | 25311 | L | AA | MA | GE1 | Jct. Cancohoy-Pilar Road, (Caridad-Pilar Section) | Surigao Del Norte | 2011-08-12 | 1st | XIII | LF | 21.116 | 260 | 2011-01-11 | 2011-09-27 | 24.28 | O | 0.361 | 0.225 | 0.15 | 0.023 | 0.032 | 0.033 | 82.4 | -
Ronwood Construction & Supply | 25311 |  |  |  |  | Jct. Del Carmen-San Benito-Burgos Rd., Del Carmen-San Benito Rd. Section |  | 2010-02-26 |  | XIII |  | 17.126 | 261 |  |  |  | O | 0.371 | 0.24 | 0.104 | 0.03 | 0.047 | 0.033 | 82.5 | -
Ronwood Construction & Supply | 25311 | L | AA | MA | GE1 | Jct. del Carmen-San Benito-Burgos Rd., Del Carmen-San Benito Rd. Sect. |  | 2009-09-03 | 1st | XIII |  | 17.126 | 240 |  |  |  | O | 0.355 | 0.263 | 0.15 | 0.03 | 0.06 | 0.033 | 89.1 | -
Ronwood Construction & Supply | 25311 |  |  |  |  | Completion of the Channel of Osmeña-Dapa Flood Control |  | 2010-06-05 |  | XIII |  | 9.645 | 180 |  |  |  | O | 0.304 | 0.3 | 0.15 | 0.03 | 0.04 | 0.033 | 85.7 | -
Ronwood Construction & Supply | 25311 |  |  |  |  | Completion of the Channel of Osmeña-Dapa Flood Control |  | 2010-08-28 |  | XIII |  | 9.645 | 240 |  |  |  | O | 0.345 | 0.266 | 0.15 | 0.008 | 0.045 | 0.05 | 86.4 | -
Ronwood Construction & Supply | 25311 | L | AA | MA | GE1 | Const. of Catangan-Cabitoonan-Libertad Road & Bridges |  | 2009-03-07 | 2nd | XIII |  | 9.644 | 194 |  |  |  | O | 0.353 | 0.237 | 0.15 | 0.03 | 0.032 | 0.05 | #VALUE! | -
Ronwood Construction & Supply | 25311 | L | AA | MA | GE1 | Const. of Catangan-Cabitoonan-Libertad Road & Bridges |  | 2008-11-21 | 1st | XIII |  | 9.644 | 180 |  |  |  | O | 0.284 | 0.213 | 0.1 | 0.03 | 0.032 | 0.1 | 75.9 | -
Ronwood Construction & Supply | 25311 | L | AA | MA | GE1 | Cancohoy-San Isidro-Pilar Road, San Isidro-Pilar Section |  | 2009-05-29 | 1st | XIII |  | 6.752 | 150 |  |  |  | O | 0.39 | 0.201 | 0.15 | 0.03 | 0.051 | 0.05 | 87.2 | -
Ronwood Construction & Supply | 25311 | L | AA | MA | GE1 | Conc. of SAFRAGEMC Subdivision Road, San Isidro |  | 2009-06-08 | Final | XIII |  | 2.825 | 150 |  |  |  | O | 0.427 | 0.133 | 0.3 | - | - | - | 86 | 84.98% Satisfactory
Ronwood Construction & Supply | 25311 | L | AA | MA | GE1 | Concreting of SAFRAGEMC Subdivision Road |  | 2009-03-17 | 1st | XIII |  | 2.825 | 150 |  |  |  | O | 0.324 | 0.252 | 0.15 | 0.03 | 0.037 | 0.05 | #VALUE! | -
Ronwood Construction & Supply | 25311 | L | AA | MA | GE1 | Del Carmen-Sta. Monica-San Isidro Rd., Sta Monica-San Isidro Sect. |  | 2009-09-03 | 1st | XIII |  | 7.715 | 150 |  |  |  | O | 0.364 | 0.289 | 0.15 | 0.03 | 0.06 | 0.033 | 92.6 | -
Ronwood Construction & Supply | 25311 | L | AA | MA | GE1 | Jct. Osmeña-Pilar Rd. |  | 2009-09-03 | 1st | XIII |  | 13.239 | 210 |  |  |  | O | 0.326 | 0.225 | 0.15 | 0.03 | 0.06 | 0.033 | 82.4 | -
Ronwood Construction & Supply | 25311 | L | AA | MA | GE1 | Impvt./Conc. of Jct. Del Carmen-Sta. Monica (Km.0076+297.20-Km.0028+080) | Del Carmen, Surigao del Norte | 2012-08-13 | 1st | XIII | LF | 29.498 | 180 | 2012-02-28 | 2012-08-25 | 3.67 | O | 0.283 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 80.3 | -
Ronwood Construction & Supply | 25311 | L | AA | MA | GE1 | Widening of Butuan-Cagayan de Oro-Iligan Rd. (Agusan-Misamis Oriental Sect.) Nasipit Sect., Sta.1259+480-Sta.1261+253 | Nasipit, Agusan del Norte | 2013-08-06 | 2nd | XIII | LF | 34.547 | 251 | 2013-02-08 | 2013-09-16 | 2.01 | O | 0.363 | 0.234 | 0.15 | 0.03 | 0.027 | 0.05 | 85.4
Ronwood Construction & Supply / Regional Infrastructure Development Corporation (J.V.) | JV-12-129 | L | A | MA | GE1 | Const. of Jct. Osmeña-Pilar Rd. (San Roque-Pilar Sect.), K18+000-K19+000 & K20+500-K22+620, Pilar, Siargao Island | Surigao del Norte | 2013-08-09 | 1st | XIII | LF | 79.634 | 225 | 2013-03-12 | 2013-10-22 | 15.3 | O | 0.372 | 0.23 | 0.15 | 0.023 | 0.045 | 0.05 | 87
Ronwood Construction & Supply/Regional Infrastructure Development Corporation (JV) | JV-13-384 | L | AA | MA | GE | Improvement/Upgrading (Gravel to Concrete) of NRJ Blanca-Bunawan Eco Park Road leading to Bunawan Eco Park, K1344+300 - K1347+036 | Bunawan, Agusan del Sur | 2014-10-23 | 1st | XIII | LF | 72.4764 | 225 | 2014-04-03 | 2014-11-13 | 0.16% | O | 0.31 | 0.3 | 0.15 | 0.023 | 0.042 | 0.05 | 87.5% | 87.5% Satisfactory
Ronwood Construction & Supply/Regional Infrastructure Development Corporation (JV) | JV-13-384 | L | AA | MA | GE | Improvement/Upgrading (Gravel to Concrete) of NRJ Blanca - Bunawan Eco Park Road Leading to Bunawan Eco Park, K1344+300 - K1347+036 | Bunawan, Agusan del Sur | 2014-08-08 | 1st | XIII | LF | 72.4764 | 225 | 2014-04-03 | 2014-11-13 | 0.58 | O | 0.381 | 0.242 | 0.15 | 0.03 | 0.047 | 0.05 | 90
Ronwood Construction and Supply | 25311 | L | AA |  |  | Rehab of Pisaan - Del Monte Road (Tagapua Section) | Tagapua, San Francisco, Agusan del Sur | 2012-11-28 | 1st | Agusan del Sur | LF | 37.445 | 229 | 2012-05-21 | 2013-01-04 | -4.76 | O | 0.386 | 0.299 | 0.15 | 0.03 | 0.06 | 0.05 | 97.5 | -
Ronwood Construction and Supply | 25311 | L | AA |  |  | Rehab of Pisaan - Del Monte Road (Tagapua Section) | Tagapua, San Francisco, Agusan del Sur | 2013-02-26 | Final | Agusan del Sur | LF | 37.445 | 229 | 2012-05-21 | 2013-01-04 | -4.76 | C | 0.466 | 0.199 | 0 | - | - | - | 66.5 | 85.10% Satisfactory
RONWOOD CORPORATION (FORMERLY RONWOOD CONSTRUCTION SUPPLY) | 253111 | L | AAA | MA | GE | Construction of Agusan-Bukidnon Road | Agusan-Bukidnon, Buenavista Section, Agusan Del Norte | 2015-06-02 | 1st | AGUSAN DEL NORTE DEO | LF | 44.667 | 180 | 2015-02-12 | 2015-08-10 | (+) 0.32% | O | 0.394 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 91.4% | -
RONWOOD CORPORATION (FORMERLY RONWOOD CONSTRUCTION SUPPLY) | 25311 | L | AA | MA | GE | Concreting/ Improvement of Nasipit - Buenavista - Masao Port Coastal Road | Agusan Del Norte | 2015-06-02 | 1st | AGUSAN DEL NORTE DEO | LF | 46.528 | 180 | 2015-03-16 | 2015-09-11 | (+) 17.36% | O | 0.392 | 0.236 | 0.15 | 0.03 | 0.05 | 0.05 | 90.8% | -
RONWOOD CORPORATION / REGIONAL INFRASTRUCTURE DEVELOPMENT CORPORATION JOINT VENTURE | JV-14-418 | L | AA | MA | GE | Upgrading (Gravel to Paved) of Dapa Port - Consuelo - Corazon - Sta.Cruz - Sta.Fe - Libertad - Cabitoonan - Catangnan - General Luna | Surigao Del Norte | 2015-06-09 | 1st | Regional Office No. XIII | LF | 90.146 | 210 | 2015-03-31 | 2015-10-26 | (+) 1.70% | O | 0.395 | 0.235 | 0.15 | 0.03 | 0.05 | 0.05 | 91% | -
Roprim Construction | 8546 | L | A | MA | GB | Construction of Multi-Purpose Building at Oton Central School | Oton, Iloilo City | 2014-08-04 | Final | VI | LF | 3.7987 | 327 | 2013-07-15 | 2013-11-11 | 0 | C | 0.443 | 0.2 | 0.3 |  |  |  | 94.3 | 87.16% Satisfactory
Roprim Construction | 8516 | L | A | MA | GB1 | Const. of MPB at Trapiche Elem. Sch. | Oton, Iloilo | 2013-08-14 | Final | VI | LF | 3.799 | 150 | 2013-01-19 | 2013-05-18 | 0 | C | 0.451 | 0.133 | 0.3 | - | - | - | 88.4 | 90.71% V. Satisfactory
Roprim Construction | 8516 | L | A | MA | GB1 | Const. of MPB at Oton Central Sch. | Oton, Iloilo | 2013-08-14 | 1st | VI | LF | 3.799 | 327 | 2013-07-15 | 2013-11-11 | 0.55 | O | 0.361 | 0.24 | 0.15 | 0.03 | 0.027 | 0.033 | 84.1
Roprim Construction | 8516 | L | A | MA | GB1 | Const. of MPB at Trapiche Elem. School | Oton, Iloilo | 2013-03-17 | 1st | VI | LF | 3.799 | 150 | 2012-12-20 | 2013-05-18 | 6.02 | O | 0.365 | 0.27 | 0.15 | 0.03 | 0.052 | 0.05 | 91.7 | -
Roprim Construction | 8546 |  |  |  |  | Conc. of Pototan-Dingle-Tabugon Rd. |  | 2010-02-24 |  | VI |  | 43.38 | 240 |  |  |  | O | 0.334 | 0.284 | 0.15 | 0.03 | 0.033 | 0.05 | 88.1 | -
Roprim Construction | 8546 |  |  |  |  | Rehab. of Capiz-Aklan Rd. Km.324+000 - Km.328+905.50 w/ exception |  | 2010-06-14 |  | VI |  | 27.802 | 250 |  |  |  | O | 0.325 | 0.24 | 0.15 | 0.03 | 0.042 | 0.05 | 83.7 | -
Roprim Construction | 8546 | L | A | MA | GE1 | Reblocking of Pototan-Mina Janiuay Road |  | 2009-03-18 | 2nd | VI |  | 9.545 | 232 |  |  |  | O | 0.348 | 0.3 | 0.15 | 0.03 | 0.06 | 0.05 | #VALUE! | -
Roprim Construction | 8546 | L | A | MA | GE1 | Reblocking of Pototan-Mina Janiuay Road |  | 2008-12-04 | 1st | VI |  | 9.546 | 120 |  |  |  | O | 0.293 | 0.225 | 0.1 | 0.015 | 0.032 | 0.1 | 76.5 | -
ROPRIM CONSTRUCTION | 8546 | L | A | MA | GB | Const. of CY 2014 BEFF Batch 1 (Const. of Senior High School Classrooms in area experiencing acute classroom shortage) Roxas City Cluster-2.1 Const. of 2-Bldg., Dumulog NHS, Storey, 6-Classroom School Bldg., Dumulog NHS, Dumulog, Roxas City | Dumulog, Roxas City | 2015-11-12 | 1st | Capiz 1st | LF | 16.0127 | 150 | 2015-08-17 | 2016-01-14 | (+) 3.73% | OG | 0.386 | 0.2 | 0.15 | 0.03 | 0.059 | 0.05 | 87.5% | 87.5% Satisfactory
ROPRIM CONSTRUCTION | 8546 | L | A | MB | GE | Construction/ Rehabilitation of Flood Mitigation Facilities along Major & Principal River Basins, Panay/Mabusao River Basins, Construction of Panitan River Control, Panitan, Capiz | Panitan, Capiz | 2015-11-12 | Final | Capiz 1st | LF | 12.7857 | 157 | 2015-02-14 | 2015-07-21 | 0.00% | C | 0.423 | 0.133 | 0.3 | - | - | - | 85.6% | 85.6% Satisfactory
ROPRIM CONSTRUCTION | 8546 | L | A | MA | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads along Iloilo-Capiz Road (New Route), KO064+(-865)-KO064+(-240), KO064+443.70-KO065+316.40, KO065+563-KO065+801.50, KO067+658.50-KO067+848.50, KO070+748-KO071+160, KO071+487.20-KO071+6 | Capiz | 2015-11-13 | 1st | Capiz 2nd | LF | 46.519 | 232 | 2015-06-23 | 2016-02-10 | (+) 0.22% | OG | 0.355 | 0.219 | 0.15 | 0.03 | 0.051 | 0.05 | 85.5% | 85.5% Satisfactory
Roprim Construction / Jet Construction Supply (JV) | JV-11-266 | L | A | MA | GE1 | Replacement/Const. of Linaban Bridge, (Km. 83+017.60) | Hamtic, Antique | 2013-08-15 | 1st | VI | LF | 23.959 | 410 | 2012-05-30 | 2013-07-13 | -4.54 | O | 0.356 | 0.3 | 0.024 | 0.03 | 0.033 | 0.033 | 77.6
Rosand Builders | 15781 | L | B | MA | GE | Imprv't./Asphalt Overlay of Hemady St. Quezon City, K0008+534 - K0009+618 | Quezon City | 2014-08-15 | 1st & Final | NCR | LF | 8.2422 | 45 | 2014-02-11 | 2014-03-27 | 0 | C | 0.489 | 0.133 | 0.3 |  |  |  | 92.2 | 92.20% Very Satisfactory
Rosand Builders | 15781 | L | B | MA | GE1 | Impv't./Asphalt Overlay of Hemady St., (K0008+53 -K0009+618) | Quezon City | 2013-03-19 | 1st | NCR | LF | 7.67 | 38 | 2013-02-08 | 2013-03-17 | -15 | O | 0.378 | 0.3 | 0 | 0.023 | 0.025 | 0.033 | 75.9 | -
Rosand Builders | 15781 |  |  |  |  | Rehab./Reconst. of Damaged Paved National Roads at Davao City Diversion Rd. Ma-a-Shrine Rd. Sect. |  | 2010-06-16 |  | XI |  | 14.474 | 90 |  |  |  | O | 0.384 | 0.237 | 0.15 | 0.03 | 0.047 | 0.033 | 88.1 | -
Rosand Builders | 15781 |  |  |  |  | Construction of 3-Storey, 15 Classroom School Buildings |  | 2010-01-20 |  | NHA |  | 21.615 | 150 |  |  |  | O | 0.391 | 0.3 | 0.006 | 0.03 | 0.055 | 0.05 | 83.2 | -
Rosand Builders | 15781 |  |  |  |  | Construction of Two-Storey Multi-Purpose Center |  | 2010-02-25 |  | NHA |  | 3.492 | 90 |  |  |  | O | 0.388 | 0.3 | 0.15 | 0.03 | 0.07 | 0.05 | 98.8 | -
Rosand Builders | 15781 |  |  |  |  | Construction of 3-Storey, 15 Classroom School Building |  | 2010-04-14 |  | NHA |  | 21.605 | 350 |  |  |  | O | 0.397 | 0.3 | 0.15 | 0.03 | 0.05 | 0.05 | 99.7 | -
ROSAND BUILDERS | 15781 | L | B | MA | GE | Construction of Concrete Revetment on Steel Sheet Piles along Talomo River, Calinan Section, Calinan District, Davao City | Calinan District, Davao City | 2015-11-18 | Final | Davao City 2nd DEO | LF | 1.863e-05 | 160 | 2015-02-10 | 2015-07-19 | 0.3462 | C | 0.465 | 0.141 | 0.3 | - | - | - | 90.6% | 90.6% Very Satisfactory
Rostel Construction & Supply | 26934 | L | B | MA | GE | Impvt./Upgrading (Gravel to Paved) of Buenavista - Bunaguit Road, Sta. 1272+000 - Sta. 1273+500 | Buenavista, Agusan del Norte | 2014-08-05 | Final | XIII | LF | 38.0173 | 206 | 2013-02-08 | 2013-09-01 | 0 | C | 0.387 | 0.133 | 0.3 |  |  |  | 82 | 79.15% Unsatisfactory
Rostel Construction & Supply | 26934 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Paved) of Buenavista-Bunaguit Rd., Sta.1272+000-Sta.1273+500 | Buenavista, Agusan del Norte | 2013-08-06 | 2nd | XIII | LF | 38.017 | 169 | 2013-02-08 | 2013-07-26 | -12.86 | O | 0.341 | 0.252 | 0.021 | 0.03 | 0.035 | 0.017 | 69.6
Rostel Construction & Supply | 26934 | L | B | MA | GE1 | Road Upgrading (Gravel to Paved) of Buenavista-Bunaguit Road, Sta.1272+000 - Sta.1273+500 | Buenavista, Agusan del Norte | 2013-03-12 | 1st | XIII | LF | 38.017 | 131 | 2013-02-08 | 2013-06-18 | 0.07 | O | 0.313 | 0.3 | 0.15 | 0.03 | 0.023 | 0.033 | 84.9 | -
Rostel Construction & Supply | 26934 |  |  |  |  | Upgrading of Buenavista-Bunaguit Road (Malpoc-Rizal Section) |  | 2010-05-31 |  | XIII |  | 10.663 | 135 |  |  |  | O | 0.374 | 0.249 | 0.15 | 0.023 | 0.035 | 0.033 | 86.4 | -
Rostel Construction & Supply | 26934 |  |  |  |  | Upgrading of Buenavista-Bunaguit Road (Malpoc-Rizal Section) |  | 2010-08-23 |  | XIII |  | 10.563 | 180 |  |  |  | O | 0.344 | 0.245 | 0.15 | 0.03 | 0.045 | 0.033 | 84.7 | -
Rovilla Construction | 19514 | L | B | MA | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Road along Antonio Y de Pio Highway: 1) K0112+135 - K0112+326, Tabuelan and 2) K0139+979 - K0140+213 | Tabuelan and San Remegio, Cebu | 2014-10-22 | 1st & Final | VII | LF | 10.4338 | 151 | 2014-01-21 | 2014-06-20 | 0.66% | C | 0.35 | 0.2 | 0.3 | - | - | - | 85% | 85% Satisfactory
Rowie's Construction | 23595 | L | B | MA | GE | Road Upgrading (Gravel to Paved) Based on Gravel Road Strategies Traffic Benchmark for Upgrading to Paved Road Standard (HDM-4 Project Analysis)(Intermittent Sections) Surigao - Davao Coastal Road, K1480+155 - K1480+191 | Mahayhay, Lingig, Surigao del Sur | 2014-10-24 | 1st & Final | XIII | LF | 1.1757 | 64 | 2014-02-11 | 2014-04-15 | -1.56% | C | 0.407 | 0.2 | 0.253 | - | - | - | 86% | 86% Satisfactory
Rowie's Construction | 23595 | L | B | A | GE1 | Conc. of Farm-To-Market Road | Tandag City, Surigao del Sur | 2013-03-15 | 1st | XIII | LF | 1.902 | 49 | 2013-01-09 | 2013-02-26 | 2.14 | O | 0.376 | 0.271 | 0.15 | 0.03 | 0.02 | 0.03 | 87.7 | -
Rowie's Construction | 23595 | L | D | SB | GB1 | Rehab./Improvement of DPWH Surigao del Sur 1st DEO Bldg. |  | 2009-06-03 | 1st | XIII |  | 1.923 | 90 |  |  |  | O | 0.357 | 0.3 | 0.15 | 0.03 | 0.03 | 0.05 | 91.7 | -
ROWIE'S CONSTRUCTION | 23595 | L | B | MA | GE | Concreting of Roads, Municipality of Cantilan, Cantilan, Surigao del Sur | Cantilan, Surigao del Sur | 2015-11-14 | Final | Surigao del Norte 1st DEO | LF | 5.6941 | 109 | 2015-07-23 | 2015-11-08 | - | C | 0.336 | 0.2 | 0.3 | - | - | - | 83.6% | 83.6% Satisfactory
Royal Crown Monarch Const. & Supplies Corp./REND | SL2-SN-001516 |  | AA | MA |  | PIDP/Angat-Maasim River Irrigation System | Bulacan & Pampanga | 2015-03-31 | Final | NIA | L | 34.579 | 427 | 2013-09-26 | 2014-11-25 | 0 | C | 0.4218 | 0.2 | 0.3 | - | - | - | 92.18 | 87.28% Satisfactory
Royal Crown Monarch Const. & Supplies Corp./REND | SL2-SN-001516 | L | AA | MA |  | PIDP/Angat-Maasim River Irrigation System | Bulacan & Pampanga | 2014-05-31 | 1st | NIA | LF | 34.577 | 305 | 2013-09-26 | 2014-09-09 | -2.32 | O | 0.3318 | 0.2625 | 0.1268 | 0.0225 | 0.0467 | 0.05 | 84.03 | -
Royal Crown Monarch Construction & Supplies Corporation | 9036 | L | A | MB | GE1 | Concreting of Capas-Botolan Road, Km. 122+528-Km. 124+628, Capas Section |  | 2009-05-20 | 1st | III |  | 28.686 | 150 |  |  |  | O | 0.375 | 0.214 | 0.15 | 0.02 | 0.03 | 0.05 | 83.9 | -
Royal Crown Monarch Construction & Supplies Corporation | 9036 | L | A | MB | GB1 | Const. of Multi-Purpose Building at Tarlac College of Agriculture |  | 2009-09-02 | 1st | III |  | 9.355 | 150 |  |  |  | O | 0.358 | 0.3 | 0.15 | 0.03 | 0.056 | 0.05 | 94.4 | -
Royal Crown Monarch Construction & Supplies Corporation (Formerly: R.C. Miranda Construction & Supplies) | 9036 | L | AA | MB | GE1 | Prev. Maint. of NE-Pangasinan Rd., K0151+503-K0154+000; K0155+262-K0155+637; K0155+637-K0156+075 | Nueva Ecija | 2013-08-13 | Final | III | LF | 26.657 | 60 | 2013-02-07 | 2013-04-07 | 5 | C | 0.393 | 0.133 | 0.3 | - | - | - | 82.6 | 84.28% Satisfactory
Royal Crown Monarch Construction & Supplies Corporation (Formerly: R.C. Miranda Construction & Supplies) | 9036 | L | AA | MB | GE1 | Prev. Maint. of Tarlac-Sta. Rosa Rd. | Tarlac City | 2012-11-24 | 2nd | III | LF | 54.013 | 265 | 2012-04-10 | 2012-12-30 | 14 | O | 0.367 | 0.262 | 0.15 | 0.03 | 0.061 | 0.05 | 92 | -
Royal Crown Monarch Construction & Supplies Corporation (Formerly: R.C. Miranda Construction & Supplies) | 9036 | L | AA | MB | GE1 | Prev. Maint. of Tarlac-Sta. Rosa Rd. | Tarlac City | 2012-08-08 | 1st | III | LF | 54.013 | 180 | 2012-04-10 | 2012-10-06 | 1.4 | O | 0.315 | 0.3 | 0.15 | 0.03 | 0.039 | 0.05 | 88.4 | -
Royal Crown Monarch Construction & Supplies Corporation (Formerly: R.C. Miranda Construction & Supplies) | 9036 | L | AAA | LA | GE | Construction of Susuba Bridge along Manila North Road, KO104+712.60 to KO104+737.40 | Capas, Tarlac | 2014-08-05 | 1st | III | LF | 21.3188 | 210 | 2014-06-11 | 2015-06-06 | 31.12 | O | 0.4 | 0.258 | 0.15 | 0.023 | 0.051 | 0.05 | 93.2
Royal Crown Monarch Construction & Supplies Corporation (Formerly: R.C. Miranda Construction & Supplies) | 9036 | L | AAA | MA | GE | Rehab./Impv't. of Flood Control Structures in Tarlac 1st LD along Camiling River, Sawat - Bilad Section | Camiling, Tarlac | 2014-08-07 | 1st & Final | III | LF | 21.3209 | 118 | 2014-05-05 | 2014-08-30 | 33.9 | C | 0.48 | 0.133 | 0.3 |  |  |  | 91.3 | 91.30% Very Satisfactory
Royal Crown Monarch Construction & Supplies Corporation (Formerly: R.C. Miranda Construction & Supplies) | 9036 | L | AAA | LA | GE | Road Upgrading (Gravel to Concrete) based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standard (HDM-4 Project Analysis) (Intermittent Section) Secondary Road: NJR Villa Sur-San Pedro-Cabua-an-Ysmael Disimungal | Maddela, Quirino | 2014-08-13 | 1st & Final | II | LF | 45.9863 | 240 | 2014-02-06 | 2014-10-03 | 0.56 | C | 0.334 | 0.266 | 0.15 | 0.03 | 0.055 | 0.05 | 88.5 | 88.50% Satisfactory
Royal Sea Bees Construction | 30099 | L | B | SB | GE4 | Implementation of Various Projects under Package 15 |  | 2008-11-17 | 1st | CAR |  | 0.933 | 120 |  |  |  | O | 0.241 | 0.214 | 0.1 | 0.03 | 0.03 | 0.067 | 68.2 | -
RR & B Finest Construction & Development Corp. | 14849 | L |  | MA | GE-5 | Repair of R. C. Platform and Roro Ramp | Port of Broke's Point, Palawan | 2015-05-29 | 1st & Final | PPA | L | 22.757 | 150 | 2014-11-05 | 2015-04-03 | 0 | C | 0.4895 | 0.2 | 0.3 | - | - | - | - | *98.95% Outstanding
RR Encabo Construction Inc./Brostan Construction and Development |  | L |  |  |  | Construction of Four(4) Five Storey Low Rise Building and Land Development | Vitas, Tondo Manila | 2015-08-11 | 1st | NHA | LF | 151.207 | 300 | 11/13/2013 | 2015-09-03 | -45.92 | O | 0.3738 | 0.2646 | 0 | 0.03 | 0.051 | 0 | 71.94 | -
RR Ricafort Construction & Supply | 14402 | L |  | MA | GE2 | Construction of Lateral "A" at Sta. 3+262 Sta 4+256 of Laris | Rosales, Pangasinan Region I | 02/27-03/03/12 | 1st | NIA | FA | 17.949 | 150 | 2011-11-21 | 2012-04-18 | 7 | O | 0.3526 | 0.2653 | 0.15 | 0.03 | 0.0467 | 0.05 | 89.46 | -
RRC Construction | 24369 | L | A | MA | GE | Construction of Drainage along Daang Maharlika KO426+800 - KO429+100 with exception | Tumauini, Isabela | 2014-10-24 | 1st & Final | II | LF | 9.7087 | 234 | 2014-02-11 | 2014-10-02 |  | C | 0.339 | 0.2 | 0.3 | - | - | - | 83.9% | 83.9% Satisfactory
RRC CONSTRUCTION | 24369 | L | A | MA | GE | National Road Network Services: Asset Preservation of National Road: Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads Including Drainage Based on Pavement Management System/Highway Development and Management-4 (Intermittent Sections), Gamu - Roxas Road, K0393+000 to K0393+708, K0395+912 to K0396+995, K0399+665 to K400+000, K0400+539 to K0401+000, K0404+000 to K0404+501, K0408+084 to K0408+141, Gamu and Roxas, Isabela | Gamu and Roxas, Isabela | 2015-08-27 | 1st | Regional Office No. II | LF | 58.385 | 237 | 2015-02-28 | 2015-10-22 | 4.29% | O | 0.369 | 0.239 | 0.15 | 0.03 | 0.055 | 0.05 | 89.3% | -
RRC CONSTRUCTION | 24369 | L | A | MA | GE | MFO-1 National Road Network Services - Asset Preservation of National Roads: Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads including Drainage based on Pacement Management System/Highway Development and Management-4 (HDM-4) (Inter | Gamu and Roxas, Isabela | 2015-11-13 | 1st | REGIONAL | LF | 61.4577 | 316 | 2015-02-28 | 2016-01-09 | (+) 4.53 | OG | 0.367 | 0.208 | 0.15 | 0.03 | 0.05 | 0.033 | 83.8% | 83.8% Satisfactory
RRL Builders | 23454 | L | B | MA | GB1 | Iloilo City LTFRB Regional Office Development Project | Tabuk Suba, Jaro, Iloilo City | 2014-03-19 | Final | DOTC | LF | 4.979 | 150 | 2013-03-15 | 2013-08-11 | 0 | C | 0.4872 | 0.2 | 0.3 | - | - | - | 98.72 | 93.85% Outstanding
RRL Builders | 23454 | L | B | MA | GB1 | Iloilo City LTFRB Regional Office Development Project | Tabuk Suba, Jaro, Iloilo City | 2013-07-25 | 1st | DOTC | L | 4.979 | 150 | 2013-03-15 | 2013-08-12 | 5.08 | O | 0.354 | 0.3 | 0.15 | 0.015 | 0.049 | 0.05 | 91.8 | -
RRL Builders Corp. / WTG Construction & Dev't Corp. (JV) | JV-12-091 | L | AAA | LA | GE5 | Construction of Back-up Area with RoRo Ramp on Fill & Upgrading of Existing Back-up Area | Port of Dumangas, Iloilo City / Region VI | 2013-04-12 | 1st | PPA | LF | 62.38 | 360 | 2012-10-17 | 2013-10-11 | 2.241 | O | 0.394 | 0.267 | 0.15 | 0.03 | 0.051 | 0.05 | 94.2 | -
RRL Builders Corp./WTG Construction & Development Corp. (JV) | JV-12-091 | L | AAA | LA | GE-5 | Construction of Back-Up Area w/ RoRo Ramp on Fill and Upgrading of Existing Back-Up Area | Port of Dumangas, Dumangas, Iloilo | 2014-02-21 | 2nd & Final | PPA | LF | 62.38 | 421 | 2012-10-17 | 2013-12-11 | 0 | C | 0.479 | 0.2 | 0.3 | - | - | - | 97.9 | 95.66% Very Satisfactory
RRL Builders Corporation | 23454 | L | A | MA | GB1 | Iloilo City PCG District Station Development Project | Parola, Iloilo City | 2013-02-14 | 1st | DOTC | LF | 10.544 | 180 | 2012-10-19 | 2013-04-16 | 0.75 | O | 0.393 | 0.3 | 0.15 | 0.02 | 0.039 | 0.033 | 93.5 | -
RRL Builders Incorporated | 23454 | L | B | MA | GB1 | Iloilo City PCG Station Building Project | Parola, Iloilo City | 2014-02-20 | Final | DOTC | LF | 10.544 | 180 | 2012-10-19 | 2014-02-03 | 0 | C | 0.42 | 0.2 | 0.3 | - | - | - | 92 | 93.10% Very Satisfactory
RRMD Construction and Supply (Formerly: RRMD Construction) | 23615 |  |  |  |  | Rehab./Reconst./Upgrading along Misamis Oriental-Ma. Cristina Bdry. Road Mandulog-Tambo-IIT Section, Sta.1520+962 - Sta.1524+094 |  | 2010-06-07 |  | X |  | 13.935 | 120 |  |  |  | O | 0.378 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 90.3 | -
RRMD Construction and Supply (Formerly: RRMD Construction) | 23615 |  |  |  |  | Rehab./Reconst./Upgrading along Overton Buru-un Road at Buru-un - Poblacion Section, Sta.1535+067 - Sta.1535+803.50 w/ exception |  | 2010-06-10 |  | X |  | 9.284 | 105 |  |  |  | O | 0.373 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 89.8 | -
RRN CONSTRUCTION | 20228 | L | B | MA | GE | Rehab/Reconst/Upgrading of Damaged Paved National Roads Including Drainage Based on Pavement Management System/Highway Development and Management-4 (HDM-4) (Intermittent Section) | Sayre Highway, K1541+279-K1541+789, Musuan, Maramag, Bukidnon, K1541+279-K1541+729 | 2015-08-27 | 1st & Final | Bukidnon 2nd DEO | LF | 8.831 | 75 | 2015-02-27 | 2015-05-12 | 12.5% | C | 0.473 | 0.133 | 0.3 | - | - | - | 90.6% | *90.60% Very Satisfactory
RRN CONSTRUCTION | 20228 | L | B | MA | GE | Road Upgrading (Unpaved to Paved) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standards (HDM-4 Project Analysis) Intermittent Section) along Dologon-Kisanday-Guinoyoran Road, K1546+(-356)-K1546+(-040), K1549+875-K1550+559, Bukidnon | Bukidnon | 2015-11-12 | Final | Bukidnon 2nd | LF | 23.9588 | 150 | 2015-02-27 | 2015-07-27 | 0.00% | C | 0.478 | 0.134 | 0.3 | - | - | - | 91.2% | 91.2% Very Satisfactory
RRN Construction Corporation (Formerly: RNN Construction) | 24880 | L | C | SB | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Roads (IS) (K0028+572.50-K0028+996.50) at PPTA Road | Muntinlupa City | 2011-08-17 | 1st | NCR | LF | 3.566 | 98 | 2011-06-06 | 2011-09-11 | 1.42 | O | 0.367 | 0.3 | 0.15 | 0.03 | 0.05 | 0.05 | 94.7 | -
RSKC CONSTRUCTION | 38292 | L | B | SB | GB | Construction of Multi-Purpose Building, Poblacion, Tumauini, Isabela | Tumauini, Isabela | 2015-08-27 | 1st | Isabela 1st DEO | LF | 4.699 | 162 | 2015-03-26 | 2015-09-03 | 0.04% | O | 0.35 | 0.234 | 0.15 | 0.03 | 0.058 | 0.05 | 87.2% | -
RT Builders | 33773 | L | D | SB | GE2 | Drainage System at Abucay, Daang Maharlika, Barangay Abucay | Tacloban City | 2012-11-29 | 1st | VIII | LF | 4.009 | 107 | 2012-10-12 | 2013-01-26 | 32 | O | 0.354 | 0.24 | 0.15 | 0.03 | 0.035 | 0.033 | 84.2 | -
RT Morabe Construction | 11377 | L |  |  | GE2 | BIP No. 11-2011 Construction of Open canal and Canal Structures | Basey, Western Samar | 2011-09-06 | 1st | NIA | LF | 7.0711 | 105 | 2011-04-18 | 2011-09-22 | -0.25 | O | 0.3594 | 0.2582 | 0.15 | 0.0225 | 0.0573 | 0.05 | 89.74 | -
RTY CONSTRUCTION | 10341 | L | B | MA | GB | Constrution of Multi-Purpose Building | Boac, Marinduque | 2015-11-16 | Final | Marinduque DEO | LF | 1.8326 | 60 | 2015-02-19 | 2015-04-19 | 0 | C | 0.477 | 0.181 | 0.3 | - | - | - | 95.8% | 95.8% Very Satisfactory
Ruby-Jade Construction | 19202 |  |  |  |  | Rehab. of Lobbot Street |  | 2010-06-06 |  | III |  | 4.688 | 120 |  |  |  | O | 0.394 | 0.241 | 0.15 | 0.03 | 0.032 | 0.033 | 88 | -
Ruby-Jade Construction | 19202 | L | B | MA | GE1 | Construction of Brgy. Lobbot Road |  | 2009-03-03 | 1st | III |  | 4.703 | 150 |  |  |  | O | 0.329 | 0.3 | 0.124 | 0.023 | 0.018 | 0.033 | #VALUE! | -
Rubylim Construction & Supplies, Inc. | 11685 |  |  |  |  | Impvt. of San Fernando South Road, San Fernando Section |  | 2010-02-17 |  | V |  | 11.34 | 240 |  |  |  | O | 0.346 | 0.232 | 0.15 | 0.03 | 0.04 | 0.033 | 83.1 | -
Rubylim Construction & Supplies, Inc. (Formerly: Ruby Lim Construction & Supplies) | 11685 | L | A | MA | GE1 | Const. of/Repair of Scoured Shoulder/Embankment/Lined Canal & Riprap along San Fernando North Rd., Km.21+400-Km.28+070 with exception | Monreal, Masbate | 2013-03-14 | 1st | V | LF | 9.506 | 150 | 2012-11-05 | 2013-04-03 | -10.83 | O | 0.304 | 0.22 | 0.042 | 0.018 | 0.01 | 0.017 | 61.1 | -
Rubylim Construction & Supplies, Inc. (Formerly: Ruby Lim Construction & Supplies) | 11685 | L | A | MA | GE1 | Rehab./Reconst./Upgrading of P. Florentino St. | Sampaloc, Manila | 2013-03-20 | Final | NCR | LF | 14.406 | 223 | 2011-10-10 | 2012-05-20 | - | C | 0.468 | 0.097 | 0 | - | - | - | 56.5 | 69.16% Poor
Rubylim Construction & Supplies, Inc. (Formerly: Ruby Lim Construction & Supplies) | 11685 |  |  |  |  | Road Upgrading of San Fernando South Rd. (Pinamoghaan Sect.) |  | 2010-08-24 |  | V |  | 19.1 | 170 |  |  |  | O | 0.292 | 0.3 | 0.15 | 0.02 | 0.035 | 0.033 | 83 | -
RUDHIL CONSTRUCTION & ENTERPRISES (Formerly: RUDHIL CONSTRUCTION) | 22901 | L | A | MA | GE | Widening of National Roads, Oroqieta City-Calamba Mt. Road K1746+250-K1746+390 & 2.Oroquieta City-Langcangan Road Chainage 0 - Chainage 203 | Oroqieta City-Calamba Mt. Road K1746+250-K1746+390 & 2.Oroquieta City-Langcangan Road Chainage 0 - Chainage 203 | 2015-06-04 | 1st | Misamis Occidental First DEO | LF | 3.316 | 120 | 2015-03-02 | 2015-06-29 | 0.56% | O | 0.37 | 0.2 | 0.144 | 0.03 | 0.058 | 0.033 | 83.5% | -
Rudhil Construction & Enterprises Inc. (Formerly: Rudhil Const.) | 22901 | L | A | MA | GE1 | Rd. Upgrading (Gravel to Paved) Imelda-Bayog Kumalarang-Lapuyan-Margosatubig Rd., Minsulao Sect., Km.1762+730-Km.1764+000 | Diplahan, Zamboanga Sibugay | 2013-08-14 | 1st | IX | LF | 32.914 | 225 | 2013-02-22 | 2013-10-04 | -2.55 | O | 0.31 | 0.248 | 0.124 | 0.03 | 0.028 | 0.033 | 77.3
Rudhil Construction & Enterprises Inc. (Formerly: Rudhil Const.) | 22901 | L | A | MA | GE1 | Const. of Slope Protection along Dipolog-Punta-Dansullan-Sergio Osmeña Rd., Km.1875+490-Km.1875+560 (due to Rd. Slip) | Polanco, Zamboanga del Norte | 2013-08-20 | 1st | IX | LF | 8.324 | 90 | 2013-03-21 | 2013-06-18 | - | O | 0.319 | 0.3 | 0 | 0.02 | 0.033 | 0.033 | 70.5
Rudhil Construction & Enterprises, Inc. | 22901 | L | A | MA | GE | Road Upgrading (Gravel to Paved) based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Rd Standard (HDM-4 Project Analysis) Intermittent Sect., ZNAC Acccess Road, K1989+(-773) - K1989+(-260)(FY 2014), Z.N. | Zamboanga del Norte | 2014-10-24 | 1st & Final | IX | LF | 12.5604 | 169 | 2014-02-20 | 2014-08-07 | 0% | C | 0.428 | 0.123 | 0.3 | - | - | - | 85.1% | 85.1% Satisfactory
Rudhil Construction & Enterprises, Inc. | 22901 | L | A | MA | GE | Const./Improvement of Access Roads Leading to Declared Tourism Destinations Juction Manukan Town Site Leading to Libutan Cave | Manukan, Zamboanga del Norte | 2014-10-30 | 1st | IX | LF | 27.9293 | 195 | 2014-03-27 | 2014-10-07 | -2% | O | 0.256 | 0.297 | 0.13 | 0.03 | 0.045 | 0.017 | 77.5% | 77.5% Unsatisfactory
Rudhil Construction & Enterprises, Inc. | 22901 | L | A | MA | GB | Construction of Multi-Purpose Building at Brgy. Candiis, Malangas | Malangas, Zamboanga Sibugay | 2014-10-25 | 1st | IX | LF | 5.9108 | 158 | 2014-05-30 | 2014-11-03 | -1.44% | O | 0.296 | 0.198 | 0.134 | 0.03 | 0.041 | 0.033 | 73.2% | 73.2% Poor
Rudhil Construction & Enterprises, Inc. (Formerly: Rudhil Construction) | 22901 | L | A | MA | GE | Road Upgrading of (Gravel to Paved) Imelda-Bayog-Kumalarag-Lapuyan-Margosatubig Road, Minsulao Section, K1762+730 to K1764+000 | Diplahan, Zamboanga Sibugay | 2014-08-09 | Final | IX | LF | 32.9122 | 270 | 2013-02-22 | 2013-11-18 | 1.5 | C | 0.326 | 0.2 | 0.3 |  |  |  | 82.6 | 79.42% Unsatisfactory
Rudhil Construction & Enterprises, Inc. (Formerly: Rudhil Construction) | 22901 | L | A | MA | GE | Road Upgrading of (Gravel to Paved) based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standard (HDM-4 Project Analysis) intermittent Section, ZNAC Access Road K1989+(-773) - K1989+(-260)(FY 2014) | Zamboanga Del Norte | 2014-08-09 | 1st | IX | LF | 12.2073 | 181 | 2014-02-20 | 2014-08-19 | 0 | O | 0.334 | 0.3 | 0.15 | 0.03 | 0.05 | 0.033 | 89.7
Rudhil Construction & Enterprises, Inc. (Formerly: Rudhil Construction) | 22901 | L | A | MA | GE | Rehab./Reconst./Upgrading of Damaged National Road including Drainage based on (PMS/HDM-4)(Intermittent Section) Pagadian City-Zamboanga City Road K1662+500 - K1663+500 | Pagadian City, Zamboanga del Sur | 2014-08-13 | 1st & Final | IX | LF | 13.9892 | 100 | 2014-02-24 | 2014-06-03 | 0 | C | 0.337 | 0.2 | 0.3 |  |  |  | 83.7 | 83.70% Satisfactory
Rudhil Construction & Enterprises, Inc. (Formerly: Rudhil Construction) | 222901 | L | A | MA | GE | Rehabilitation of Road (Rotunda) along Pagadian-Zamboanga City Road Sta. 1801+252.90 | Ipil, Zamboanga Sibugay | 2014-08-07 | 1st | IX | LF | 11.8306 | 195 | 2014-04-04 | 2014-10-15 | -1 | O | 0.295 | 0.3 | 0.14 | 0.03 | 0.051 | 0.017 | 83.3
Rudhil Construction & Enterprises, Inc. (Formerly: Rudhil Construction) | 22901 | L | A | MA | GE1 | Rd. Upgrading (Gravel to Conc.) Int. Sect. along Piñan-Mutia Rd., K1816+192-K1818+(-083) | Zamboanga del Norte | 2013-03-22 | 1st | IX | LF | 38.898 | 144 | 2013-02-05 | 2013-06-28 | 1.4 | O | 0.36 | 0.225 | 0.15 | 0.03 | 0.037 | 0.033 | 83.5 | -
RUDHIL CONSTRUCTION & ENTERPRISES, INC. (Formerly: Rudhil Construction) | 22901 | L | A | MA | GE | Widening of National Roads Oroquieta City - Calamba Mt. Road, Km. 1746+250 to Km. 1746+390, Oroquieta City - Calamba Mt. Road | Oroquieta City - Calamba Mt. Road | 2015-09-01 | Final | Misamis Occidental 1st DEO | LF | 3.316 | 120 | 2015-03-02 | 2015-06-29 | -5.65% | C | 0.495 | 0.2 | 0.13 | - | - | - | 82.5% | *82.50% Satisfactory
RUDHIL CONSTRUCTION & ENTERPRISES, INC. (Formerly: Rudhil Construction) | 22901 | L | A | MA | GE | Widening of National Roads 1) Oroquieta City-Calamba Mt. Road (S01015MN), K1746+250-K1746+390, Oroquieta City, Misamis Occidental | Oroquieta City, Misamis Occidental | 2015-11-19 | Final | Misamis Occidental 1st | LF | 3.3163 | 120 | 2015-03-02 | 2015-06-30 | 0.00% | C | 0.47 | 0.133 | 0.3 | - | - | - | 90.3% | 90.3% Very Satisfactory
RUDHIL CONSTRUCTION & ENTERPRISES, INC. (Formerly:Rudhil Construction) | 22901 | L | A | MA | GE | Construction/Improvement of Access Roads Leading to Airports, Seaports and Declared Tourism Destination, Road Upgrading (Gravel to Concrete) from Junct. National Highway Leading to Eriberta Spring Resort, Mahayag, Zamboanga del Sur | Mahayag, Zamboanga del Sur | 2015-11-13 | Final | Zamboanga Del Sur 1st DEO | LF | 46.7952 | 126 | 2015-03-30 | 2015-08-02 | - | C | 0.396 | 0.197 | 0.3 | - | - | - | 89.3% | 89.3% Very Satisfactory
RUDHIL CONSTRUCTION & ENTERPRISES, INC. (Formerly:Rudhil Construction) | 22901 | L | A | MA | GB | Completion of Multi-Purpose Building, Brgy. Venus, Sergio Osmeña, Zamboanga Del Norte | Sergio Osmeña, Zamboanga Del Norte | 2015-11-14 | Final | Zamboanga Del Norte 3rd DEO | LF | 1.8806 | 60 | 2015-02-26 | 2015-04-26 | - | C | 0.386 | 0.2 | 0.3 | - | - | - | 88.6% | 88.6% Satisfactory
RUDHIL CONSTRUCTION & ENTERPRISES, INC. (Formerly:Rudhil Construction) | 22901 | L | A | MA | GE | Construction /Rehabilitation of Flood Control (Slope Protection), Tupilac, R.T. Lim, Zamboanga Sibugay | Tupilac, R.T. Lim, Zamboanga Sibugay | 2015-11-10 | Final | Zamboanga Sibugay 2nd DEO | LF | 28.1367 | 264 | 2015-01-27 | 2015-10-19 | 15.38% | C | 0.448 | 0.133 | 0.3 | - | - | - | 88.1% | 87.08% Satisfactory
RUDHIL CONSTRUCTION & ENTERPRISES, INC. (Formerly:Rudhil Construction) | 22901 | L | A | MA | GB | Construction of Two (2) Unit, One (1) Storey, Three (3) Classroom School Building (Toilet Attached) at Baybay ES | Liloy, Zamboanga Del Norte | 2015-11-17 | 1st | Zamboanga Del Norte 2nd DEO | LF | 5.6987 | 160 | 2015-09-21 | 2016-02-27 | 28.02% | OG | 0.364 | 0.237 | 0.15 | 0.02 | 0.032 | 0.05 | 85.3% | 85.3% Satisfactory
RUDHIL CONSTRUCTION &ENTERPRISES, INC. (Formerly Rudhil Construction) | 3771 | L | A | MA | GB | Construction of Multi-Purpose Building, NMSCST, Brgy. Labuyo, Tangub City | Brgy. Labuyo, Tangub City | 2015-08-31 | 1st & Final | Misamis Occidental 2nd DEO | LF | 9.36 | 240 | 2014-08-08 | 2015-04-04 | 0.84% | C | 0.493 | 0.133 | 0.3 | - | - | - | 92.6% | *92.60% Very Satisfactory
RUDHILL CONSTRUCTION & ENTERPRISES, INC. (Formerly: Rudhil Construction) | 22901 | L | A | MA | GE | Construction/Rehabilitation of Flood Control (Slope Protection) Tupilac, R.T. Lim, Zamboanga Sibugay | Tupilac, R.T. Lim, Zamboanga Sibugay | 2015-08-25 | 1st | Zamboanga Sibugay 2nd | LF | 28.137 | 279 | 2015-01-27 | 2015-11-01 | (+)10 | O | 0.352 | 0.239 | 0.15 | 0.022 | 0.051 | 0.05 | 86.4% | -
Rusmen Builders & Development Corporation | 10674 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of Damaged National Road at Batangas-Lobo Road |  | 2009-05-22 | 1st | IV-A |  | 48.24 | 180 |  |  |  | O | 0.384 | 0.24 | 0.15 | 0.03 | 0.04 | 0.05 | 89.4 | -
Rusmen Builders & Development Corporation | 10674 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of Damaged National Roads of Banay-banay-Cuenca-Mojon Road |  | 2009-05-20 | 1st | IV-A |  | 42.456 | 120 |  |  |  | O | 0.392 | 0.24 | 0.15 | 0.03 | 0.03 | 0.05 | 89.2 | -
Rusmen Builders & Development Corporation (Formerly: Rusmen Builders) | 10674 | L | A | MA | GE1 | Prev. Maint. (MFO-1) (Intermittent Sect.) Banay-Banay-Mojon-Cuenca Rd., K0090+849-K0091+370 | Cuenca, Batangas | 2013-03-14 | 1st | IVA | LF | 5.79 | 30 | 2013-03-15 | 2013-04-13 | 0.22 | O | 0.371 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 89.6 | -
RUSMEN BUILDERS & DEVELOPMENT CORPORATION (Formerly: Rusmen Builders) | 10674 | L | A | MB | GE | Retrofitting/Strengthening of Permanent Bridge, Matala Bridge (B03179LZ) along Nasugbu - Lian - Calatagan Road | Lian, Batangas | 2015-06-03 | Final | Batangas 1st DEO | LF | 3.97 | 75 | 2015-02-05 | 2015-04-20 | 0% | C | 0.384 | 0.139 | 0.3 | - | - | - | 82.3% | *82.3% Satisfactory
RUSMEN BUILDERS & DEVELOPMENT CORPORATION (Formerly: Rusmen Builders) | 10674 | L | A | MA | GE | Const./Upgrading/Rehab. of Drainage along National Roads, Palico-Balayan-Batangas Road, K0 096+326.00 - K0 097+437.00 | Batangas | 2015-08-31 | 1st & Final | Batangas 1st | LF | 18.224 | 194 | 2015-02-05 | 2015-08-17 | 1.11% | C | 0.479 | 0.133 | 0.3 | - | - | - | 91.2% | *91.2% Very Satisfactory
Rusmen Builders & Development Corpration (Formerly: Rusmen Builders) | 10674 | L | A | MA | GE1 | Prev. Maint. (MFO-1) (Int. Sect.) Banay-Banay-Mojon-Cuenca Rd., K0090+849-K0091+370 | Cuenca, Batangas | 2013-08-02 | Final | IVA | LF | 5.79 | 30 | 2013-03-15 | 2013-04-13 | 6.67 | C | 0.429 | 0.139 | 0.3 | - | - | - | 86.8 | 88.48% Satisfactory
S & CU Construction | 13128 | L | B | MA | GE-5 | Panay Ports Cluster Development Project | Panay, Capiz | 2014-11-18 | 1st & Final | DOTC | LF | 16.374 | 180 | 2013-03-15 | 2014-04-15 | 0 | C | 0.397 | 0.2 | 0.3 | - | - | - | 89.7 | *89.70% V. Satisfactory
S & CU Construction | 13128 | L | B | MA | GE-5 | Pontevedra Ports Cluster Development Project | Pontevedra, Capiz | 2014-11-19 | 1st & Final | DOTC | LF | 12.361 | 150 | 2013-03-15 | 2014-05-16 | 0 | C | 0.417 | 0.2 | 0.3 | - | - | - | 91.7 | *91.70% V. Satisfactory
S & CU Construction | 13128 | L | B | MA | GE5 | Pilar Port Cluster Project | Brgy. Casanayan and Brgy. Dayhagan, Pilar, Capiz | 2014-05-08 | 1st & Final | DOTC | LF | 4.69 | 90 | 2013-03-15 | 2013-06-12 | 0 | C | 0.4084 | 0.2 | 0.3 | - | - | - | 90.84 | *90.84% V. Satisfactory
S & CU Construction | 13128 | L | B | MA | GE | Rehab./Reconst. Of Damaged National Roads, Antequera - San Isidro - Libertad (Tubigon Road) | San Isidro, Bohol | 2014-08-11 | Final | VII | LF | 16.7933 | 202 | 2013-01-30 | 2013-08-29 | 0 | C | 0.403 | 0.194 | 0.3 |  |  |  | 89.7 | 88.14% Satisfactory
S & CU Construction | 13128 | L | B | MA | GE1 | Rehab./Reconst. of Damaged Nat'l Rds., Antequera-San Isidro-Libertad (Tubigon) Rd., K0031+000-K0032+000 | San Isidro, Bohol | 2013-08-19 | 1st | VII | LF | 16.793 | 212 | 2013-01-30 | 2013-08-29 | 0 | O | 0.352 | 0.251 | 0.15 | 0.03 | 0.055 | 0.033 | 87.1
S & CU Construction | 13128 | L | B | MA | GE1 | Repair of Rd. Slip Cortes-Balilihan-Catigbian-Macaas Rd., Km.43+800-Km.44+134 | Tubigon, Bohol | 2013-03-12 | Final | VII | LF | 16.979 | 225 | 2011-12-29 | 2012-08-09 | 0 | C | 0.467 | 0.046 | 0.3 | - | - | - | 81.3 | 86.64% Satisfactory
S & CU Construction | 13128 | L | B | MA | GB1 | Const. of School Building, San Jose National High School |  | 2009-09-10 | 1st | VII |  | 1.042 | 175 |  |  |  | O | 0.4 | 0.257 | 0.15 | 0.03 | 0.042 | 0.033 | 91.2 | -
S.A. TAMAYO CONSTRUCTION | - | L | - | - | GB | Construction of Multi-Purpose Covered Court | Brgy. Gaid, Dimasalang, Masbate | 2015-06-14 | Final | Masbate 2nd | LF | 1.905 | 120 | 2015-03-02 | 2015-06-29 | 29.17% | C | 0.5 | 0.138 | 0.3 | - | - | - | 93.8% | *93.8% Very Satisfactory
S.T Hidalgo Construction | 22498 | L | C | SB | GE2 | Construction of Flood Control, Brgy. Linao |  | 2009-05-28 | 2nd | VIII |  | 4.745 | 90 |  |  |  | O | 0.31 | 0.24 | 0.15 | 0.022 | 0.03 | 0.033 | 78.5 | -
S.T Hidalgo Construction | 22498 | L | C | SB | GE2 | Construction of Flood Control |  | 2009-03-04 | 1st | VIII |  | 4.7447 | 90 |  |  |  | O | 0.312 | 0.3 | 0.15 | 0.02 | 0.019 | 0.033 | #VALUE! | -
Safeway Construction | 5842 | L | D | SB | GE1 | Const./Impv't./Rehab. Of FMR, Brgy. Baritao | Manaoag, Pangasinan | 2013-08-05 | Final | I | LF | 1.963 | 60 | 2013-02-07 | 2013-04-07 | 22.23 | C | 0.479 | 0.133 | 0.3 | - | - | - | 91.2 | 86.76% Satisfactory
Safeway Construction & Supply | 5842 | L | D | SB | GE1 | Const./Impv't./Rehab. of FMR, Brgy. Baritao | Manaoag, Pangasinan | 2013-03-16 | 1st | I | LF | 1.963 | 60 | 2013-02-07 | 2013-04-07 | 12.67 | O | 0.357 | 0.223 | 0.15 | 0.03 | 0.045 | 0.033 | 83.8 | -
Saga Engineering | 35019 | L | D | SB | GE | Const./ Concreting of Roads, Brgy. Agusan | Cagayan de Oro City | 2014-10-25 | 2nd | X | LF | 4.383 | 97 | 2014-05-30 | 2014-09-03 | 0% | C | 0.412 | 0.133 | 0.3 | - | - | - | 84.5% | 90.72% Very Satisfactory
Saga Engineering | 35019 | L | D | SB | GE | Const./Conc. Of Road Brgy. Agusan, Cagayan de Oro City | Cagayan de Oro City | 8/4//14 | 1st | X | LF | 4.383 | 97 | 2014-05-30 | 2014-09-03 | 8.28 | O | 0.389 | 0.3 | 0.15 | 0.03 | 0.05 | 0.033 | 95.2
SAGA ENGINEERING | 35019 | L | D | SB | GE | Construction/Concreting of Road, Barangay Agusan, Cagayan de Oro City | Barangay Agusan, Cagayan de Oro City | 2015-06-12 | Final | Cagayan de Oro City Second DEO | LF | 4.383 | 97 | 2014-05-30 | 2014-09-03 | - | C | 0.453 | 0.2 | 0.3 | - | - | - | 95.3% | *95.24% Very Satisfactory
Saint Bernard Construction | 28368 | L | C | SB | GE | Road Upgrading (Gravel to Paved) of Goa-Digdigon Isidro Road (Tagongtong Section) Original Sta.: K0488+477.37 - K0489+000.00 with exception, Revised Sta.: K0488+477.32 - K0489+060.00 with exception | Goa, Camarines Sur | 2014-08-09 | 1st & Final | V | LF | 10.6024 | 119 | 2014-03-04 | 2014-06-30 | 0 | C | 0.38 | 0.153 | 0.3 |  |  |  | 83.3 | 83.30% Satisfactory
SAL Construction |  | L |  |  |  | Help for Catubig Agricultural Advancement Project HCAAP-LMC-C-3 | Las Navas, Northern Samar/Region 8 | 2014-03-15 | Final | NIA | LF | 5.382 | 405 | 2011-07-04 | 2012-08-12 | 0 | C | 0.4642 | 0.0854 | 0.3 | - | - | - | 84.96 | 84.96% Satisfactory
SAL CONSTRUCTION | 34646 | L | D | SB | GE | Rehabilitation/Major Repair of Permanent Bridges Dakong Bato Bridge Along Lilo-an-San Ricardo Road (B00353LT), San Francisco, Southern, Leyte | San Francisco, Southern, Leyte | 2015-11-16 | Final | Southern Leyte DEO | LF | 4.7199 | 150 | 2015-02-02 | 2015-07-01 | - | C | 0.474 | 0.129 | 0.3 | - | - | - | 90.3% | 90.3% Very Satisfactory
SAL Construction | 34646 | L |  |  | GE2 | BIP No. 11-2011 Construction of Open canal and Canal Structures | Basey, Samar | 2011-09-06 | 1st | NIA | LF | 6.977 | 105 | 2011-05-11 | 2011-08-22 | 0.95 | O | 0.3599 | 0.2603 | 0.15 | 0.0225 | 0.0573 | 0.05 | 90 | -
SAMANTHA ENTERPRISES | 35697 | L | D | SB | GE | Widening of Fernandez Bridge along Alaminos-Lucap Road | Alaminos Pangasinan | 2015-06-12 | Final | Pangasinan 1st DEO | LF | 3.757 | 105 | 2015-01-23 | 2015-05-07 | 0% | C | 0.397 | 0.2 | 0.3 | - | - | - | 89.7% | *89.7% Very Satisfactory
Sammi Construction Company Ltd. | FC-05-008 | L | AAA | LB | GE1 | CP IV, Const./Impvt of Looc-Odiongan-San Andres Road Rural Road Network Development Project |  | 2009-05-21 | 3rd | RRNDP |  | 646.871 | 890 |  |  |  | O | 0.347 | 0.3 | 0.074 | 0.03 | 0.037 | 0.05 | 83.8 | -
Sammi Construction Company Ltd. | FC-05-008 | F | AAA | LB | GE1 | CP IV, Const./Impvt. of Looc-Odiongan-San Andres Road |  | 2009-08-30 | 4th | RRNDP |  | 698.808 | 980 |  |  |  | O | 0.348 | 0.24 | 0.149 | 0.03 | 0.051 | 0.033 | 85.1 | -
Sammi Construction Company Ltd. | FC-05-008 |  |  |  |  | Contract Package IV, Const./Impvt. of Looc-Odiongan-San Andres Road, Km 101+965.00 - Km. 143+560.68 |  | 2010-02-22 |  | RRNDP |  | 646.871 | 750 |  |  |  | O | 0.359 | 0.3 | 0.15 | 0.03 | 0.061 | 0.05 | 95 | -
Sammi Construction Company Ltd. | FC-05008 | F | AAA | LB | GE1 | CP IV, Const./Impvt. of Looc-Odiongan-San Andres Road |  | 2008-08-29 | 1st | IV-B |  | 649.871 | 750 |  |  |  | O | 0.4 | 0.3 | 0.05 | 0.03 | 0.07 | 0.067 | 91.7 | -
Sammi Construction Company Ltd. | FC-05-008 | F | AAA | LB | GE1 | CP IV, Const./Impvt. of Looc-Odiongan-San Andres Road |  | 2008-11-25 | 2nd | IV-B |  | 649.871 | 750 |  |  |  | O | 0.365 | 0.3 | 0.03 | 0.03 | 0.07 | 0.067 | 86.2 | -
Samurai Construction | 32214 | L | D | SB | GE | Construction of Multi-Purpose Building | Brgy. Magsaysay, Aborlan, Palawan | 2014-11-24 | 1st & Final | IV | LF | 1.8736 | 120 | 2014-05-26 | 2014-09-22 | 0% | C | 0.481 | 0.133 | 0.3 | - | - | - | 91.4% | 91.4% Very Satisfactory
Samurai Construction | 32214 | L | D | SB | GB1 | Const. of MPB,Palawan State University | Narra, Palawan | 2013-03-15 | 1st | IVB | LF | 2.789 | 90 | 2013-01-31 | 2013-04-30 | -12 | O | 0.342 | 0.3 | 0.03 | 0.03 | 0.035 | 0.017 | 75.4 | -
San Narciso Builders Corporation | 24527 | L |  | SB |  | CONSTRUCTION OF DRAINAGE SYSTEM | PSHS-CVISC, Talaytay, Argao, Cebu | 2014-02-27 | 1st & Final | DOST | LF | 9.049 | 217 | 2012-11-16 | 2013-06-20 | 0 | C | 0.439 | 0.2 | 0.3 | - | - | - | 93.9 | *93.9% V.Satisfactory
San Narciso Builders Corporation | 24527 |  |  |  |  | Design and Construction of the University of the Philippines Cebu Undergraduate (U.G.) Expansion Building | UP Cebu Campus | 2016-10-10 | 1st | UP | LF | 2.989 | 160 | 2016-04-19 | 2016-05-05 | 0 | O | 0.3958 | 0 | 0 | 0 | 0 | 0 | 39.58 | -
San Narciso Builders Corporation | 24527 |  |  |  |  | Design and Construction of the UP Cebu 2 Storey Business Management Cluster | UP Cebu Campus | 2016-10-10 | 1st | UP | LF | 10.408 | 246 | 2016-04-19 | 2016-05-24 | 0 | O | 0.3191 | 0 | 0 | 0 | 0 | 0 | 31.91 | -
SANDSTORM CONSTRUCTION | 23411 | L | D | SB | GB | Construction of Alangilan Multi-Purpose Building | Batangas City, Batangas | 2014-12-06 | 1st & Final | IV | LF | 2.495 | 120 | 2014-05-29 | 2014-09-25 | 22.5% | C | 0.485 | 0.133 | 0.3 | - | - | - | 91.8% | 91.8% Very Satisfactory
SANDSTORM CONSTRUCTION | 23411 | L | D | SB | GE | Repair/Rehabilitation and Construction of Barangay Padre Castillo - Banaba Farm to Market Road | San Pascual, Batangas | 2015-06-04 | Final | Batangas 2nd DEO | LF | 4.677 | 40 | 2015-01-07 | 2015-02-15 | 0% | C | 0.385 | 0.154 | 0.3 | - | - | - | 83.9% | *83.9% Satisfactory
Sanlahi Group of Builders Inc. | 11874 | L | A | MB | GE1 | Conc. of Calapan North Road (Calapan-Puerto Galera Section) |  | 2009-09-03 | 3rd | IVB |  | 48.162 | 370 |  |  |  | O | 0.332 | 0.292 | 0.15 | 0.03 | 0.047 | 0.033 | 88.4 | -
Sanlahi Group of Builders Inc. | 11874 | L | A | MA | GE1 | Rehabilitation/Reconstruction of Calapan South Road Section |  | 2009-05-25 | 1st | IV-B |  | 12.544 | 90 |  |  |  | O | 0.338 | 0.286 | 0.15 | 0.03 | 0.055 | 0.05 | 90.9 | -
Sanlahi Group of Builders Inc. | 11874 | L | A | MB | GE1 | Conc. of Calapan North Road (Calapan-Puerto Galera Section) |  | 2009-05-24 | 2nd | IV-B |  | 48.152 | 295 |  |  |  | O | 0.327 | 0.297 | 0.15 | 0.03 | 0.045 | 0.033 | 88.2 | -
Sanlahi Group of Builders Inc. | 11874 | L | A | MB | GE1 | Conc. of Calapan North Road (Calapan-puerto Galera Sec.) |  | 2009-02-25 | 1st | IV-B |  | 48.152 | 270 |  |  |  | O | 0.251 | 0.223 | 0.15 | 0.03 | 0.042 | 0.05 | #VALUE! | -
Sanlahi Group of Builders, Inc./811 Trading & Construction Joint Venture | JV-09-253 |  |  |  |  | Road Upgrading (Gravel to Paved) of Jct. MWCR Labangan-Murtha-Jct., Iriron Road |  | 2010-08-27 |  | IVB |  | 38.6 | 250 |  |  |  | O | 0.349 | 0.046 | 0.15 | 0.03 | 0.03 | 0.033 | 63.8 | -
SANRHO BUILDERS INC./ 3RB CONSTRUCTION & SUPPLY (JV) | JV-13366 | L | A | MA | GE | Widening/ Improvement of Ligao - Tabaco Road, K0526+000 to K0527+1012 (S03651LZ) | Tabaco City, Albay | 2015-06-01 | Final | Albay 1st | LF | 40.06 | 247 | 2014-05-07 | 2015-01-08 | 0% | C | 0.485 | 0.154 | 0.3 | - | - | - | 93.9% | *93.9% Very Satisfactory
Sanrho Builders, Inc./3RB Construction & Supply (JV) | JV-13-366 | L | A | MA | GE | Widening/Improvement of Ligao-Tabaco Road, K0526+000 to K0527+1012 | Tabaco City, Albay | 2014-08-04 | 1st | V | LF | 36.4238 | 179 | 2014-05-07 | 2014-11-01 | 0.37 | O | 0.354 | 0.221 | 0.15 | 0.022 | 0.061 | 0.05 | 85.8
Sanrho Construction and Supplies | 24213 | L | A |  | GB1 | Land Development of Salvation Ressettlement Project | Brgy. Salvation, Tabaco, Albay | 2013-06-21 | 2nd | NHA | L | 10.488 | 150 | 2012-04-13 | 2012-09-09 | 0.17 | O | 0.3916 | 0.3 | 0.15 | 0.02 | 0.06 | 0.05 | 97.16 | -
Sanrho Construction and Supplies | 24213 | L |  |  | GE1 | Land Development of Salvacion Resettlement Project | Brgy. Salvation, Tabaco, Albay | 2012-06-22 | 1st | NHA | LF | 10.488 | 150 | 2012-04-13 | 2012-09-09 | 0.28 | O | 0.3662 | 0.3 | 0.15 | 0.03 | 0.05 | 0.05 | 94.62 | -
Santech Builders | 16797 | L | C | SB | GE2 | Impvt. of Kinabutan River Control |  | 2008-11-24 | 2nd | XIII |  | 4.765 | 90 |  |  |  | O | 0.357 | 0.2 | 0.05 | 0.015 | 0.035 | 0.2 | 85.7 | -
Santech Builders | 16797 | L | C | SB | GE2 | Impvt. of Kinabutan River Control |  | 2009-03-09 | 3rd | XIII |  | 4.765 | 331 |  |  |  | O | 0.347 | 0.3 | 0.111 | 0.03 | 0.037 | 0.033 | #VALUE! | -
Santech Builders | 16797 | L | C | SB | GE1 | Conc. of Lake Mainit Circ. Rd. Tagbuyawan-Mansayao Rd. Sect. |  | 2009-09-06 | 1st | XIII |  | 9.143 | 238 |  |  |  | O | 0.348 | 0.233 | 0.15 | 0.03 | 0.055 | 0.033 | 84.9 | -
Sarangani Rockmixer | 6549 | L | AA | MB | GE | Widening of Digos-Makar Road, South Cotabato K1631+(-068) to K1632+471, Batomelong Section | Batomelong, South Cotabato | 2014-08-16 | 1st & Final | XII | LF | 41.6825 | 180 | 2014-01-26 | 2014-06-24 | 0 | C | 0.452 | 0.189 | 0.3 |  |  |  | 94.1 | 94.10% Very Satisfactory
Sarangani Rockmixer | 6549 | L | AA | MB | GE1 | Conc./Widening of Digos-Makar Rd., Km.1624+750-Km.1626+250, Malandag Sect. | Malungon, Sarangani Province | 2013-08-22 | Final | XII | LF | 33.63 | 174 | 2013-01-31 | 2013-07-23 | 11.19 | C | 0.413 | 0.133 | 0.3 | - | - | - | 84.6 | 85.68% Satisfactory
Sarangani Rockmixer | 6549 | L | AA | SB | GE2 | Const. of Lined Canal (Buayan Sect.) along Jct. Digos-Makar-Buayan Rd., Brgy. Buayan | General Santos City | 2013-03-23 | Final | XII | LF | 7.762 | 12 | 2012-08-30 | 2012-12-27 | 1.67 | C | 0.397 | 0.157 | 0.3 | - | - | - | 85.4 | 87.74% Satisfactory
Sarangani Rockmixer | 6549 | L | AA | MB | GE1 | Conc./Widening of Digos-Makar Rd., Km.1624+750-Km.1626+250 Malandag Sect. | Malungon, Sarangani Province | 2013-03-21 | 1st | XII | LF | 33.63 | 170 | 2013-01-31 | 2013-07-19 | 10.98 | O | 0.367 | 0.229 | 0.15 | 0.03 | 0.055 | 0.033 | 86.4 | -
Sarangani Rockmixer | 6549 |  |  |  |  | Sarangani-Davao del Sur Coastal Road (Malapatan-Glan Section) |  | 2010-06-15 |  | XII |  | 14.856 | 120 |  |  |  | O | 0.318 | 0.24 | 0.15 | 0.03 | 0.047 | 0.05 | 83.5 | -
SARANGANI ROCKMIXER | 6549 | L | AA | MB | GE | Road Widening of Digos-Makar Road K1632+227-K1635+980 | General Santos City | 2015-06-12 | 1st | RRegional Office No. XII | LF | 91.135 | 215 | 2015-04-15 | 2015-12-21 | 17.83% | O | 0.325 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 84.5% | -
Sarca Estate Development Corporation / Bomel Construction Joint Venture | JV-12-470 | L | A | MA | GE1 | Widening of Lucena-Tayabas-Lucban Rd., K0143+593.50-K0145+797, K0137+345-K0137+876 | Tayabas, Quezon | 2013-08-08 | 1st | IVA | LF | 41.812 | 120 | 2013-03-14 | 2013-07-11 | -23.23 | O | 0.337 | 0.3 | 0.15 | 0.03 | 0.023 | 0.05 | 89
Sarca Estate Development Corporation/Bomel Construciton (JV) | JV-12-470 | L | A | MA | GE | Widening of Lucena-Tayabas-Lucban Road, Tayabas City, K0143+593.50 to K0145+797 (SectionI) and K0137+345 to K0137+876 (Section) | Tayabas, City | 2014-08-14 | Final | IV-A | LF | 45.029 | 240 | 2013-03-14 | 2013-11-08 | 0 | C | 0.325 | 0.2 | 0.3 |  |  |  | 82.5 | 86.40% Satisfactory
Sarex Builders | 23734 | L | B | MA | GE | Rehab./Reconst. of Damaged Paved National Roads including Drainage along Sarangani - Davao del Sur Coastal Road, K1688+850 - K1689+890, Glan, Sarangani Province | Glan, Sarangani Province | 2014-10-29 | 1st | XII | LF | 17.8889 | 135 | 2014-02-13 | 2014-06-27 | -1.57% | O | 0.241 | 0.24 | 0 | 0.023 | 0.061 | 0.033 | 59.8% | 59.8% Poor
Sarex Builders | 23734 | L | B | SB | GE2 | Rehab./Impv't. of Pangyan River Flood Control Structure along Sarangani-Davao del Sur Coastal Rd. | Glan, Sarangani Province | 2013-03-22 | Final | XII | LF | 6.613 | 165 | 2012-07-05 | 2012-12-16 | 0.61 | C | 0.475 | 0.133 | 0.3 | - | - | - | 90.8 | 89.00% Satisfactory
Sarex Builders | 23734 |  |  |  |  | Rehab./Impvt. of DPWH Sarangani DEO Building |  | 2010-06-16 |  | XII |  | 4.695 | 150 |  |  |  | O | 0.35 | 0.24 | 0.074 | 0.03 | 0.045 | 0.033 | 77.2 | -
Sarex Builders / Greco Construction & Supply (JV) | JV-12-288 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Paved) Int. Sect. along Demoloc-Little Baguio-Alabel Rd., K1669+725-K1670+520 | Alabel, Sarangani Province | 2013-08-21 | Final | XII | LF | 20.738 | 155 | 2013-01-31 | 2013-07-04 | 0 | C | 0.433 | 0.133 | 0.3 | - | - | - | 86.6 | 87.38% Satisfactory
Sarex Builders / Greco Construction and Supply (JV) | JV-12-288 | L | B | MA | GE1 | Road Upgrading (Gravel to Paved), Intermittent Sect., along Demoloc-Little Baguio-Alabel Road, K1669+725-K1670+520 | Alabel, Sarangani Province | 2013-03-21 | 1st | XII | LF | 20.738 | 131 | 2013-01-31 | 2013-06-10 | 5.04 | O | 0.361 | 0.246 | 0.15 | 0.03 | 0.042 | 0.05 | 87.9 | -
Sargasso Construction and Development Corp. | 6587 | L | AAA | B | GE2 | Raising/Strengthening of Riverwalls along Malabon River, Catmon Creek & Longos Creek, KAMANAVA, Area Flood Control & Drainage System Impv't. Proj. | Malabon City | 2013-03-16 | 1st | KAMANAVA-PMO | LF | 148.853 | 300 | 2013-02-18 | 2013-12-15 | 0.29 | O | 0.383 | 0.225 | 0.15 | 0.03 | 0.048 | 0.033 | 86.9 | -
SATRAP COCNSTRUCTION COMPANY, INC. | 2526 | L | AAA | LB | GE | Widening of National Roads, Manila North Road | KO397+320 - KO398+995; KO399+162 - KO399+295; KO399+995 - KO401+400; KO408+880 - KO409+716 | 2015-06-05 | 1st | Regional Office No. I | LF | 93.399 | 191 | 2015-02-12 | 2015-08-21 | -7.66% | O | 0.354 | 0.289 | 0.073 | 0.03 | 0.055 | 0.033 | 83.4% | -
SATRAP Construction Company, Inc. | 2526 | L | AAA | LB | GE | Const./Widening/Upgrading/Rehab. Of Access Road to Airport, Major Seaports and Declared Tourism Destinations, Widening of Manila North Road, K0406+300, - K0406+000 and K0406+500 - K0408+880, Bantay-San Idelfonso Section | Ilocos Sur | 2014-08-07 | Final | I | LF | 53.6045 | 258 | 2013-03-06 | 2013-11-18 | 3.88 | C | 0.433 | 0.049 | 0.3 |  |  |  | 78.2 | 84.20% Satisfactory
SATRAP Construction Company, Inc. | 2526 | L | AAA | LB | GE1 | Const./Widening/Upgrading/Rehab. of Access Rd. to Airport, Major Seaports & Declared Tourism Destination, Widening of Manila North Rd., K0406+300-K0406+000 & K0408+500-K0408+880, Bantay-San Ildefonso Sect. | Ilocos Sur | 2013-08-13 | 1st | I | LF | 56.762 | 210 | 2013-03-06 | 2013-10-01 | -1.42 | O | 0.336 | 0.3 | 0.136 | 0.03 | 0.047 | 0.033 | 88.2
SATRAP Construction Company, Inc. | 2526 | L | AAA | LB | GE | Constructionof Quirino-Panda Bridge along Quirino-Panda Road | Vigan City, Ilocos Sur | 2014-08-06 | 1st | I | LF | 20.7457 | 222 | 2014-03-10 | 2014-10-17 | -3.91 | O | 0.35 | 0.204 | 0.111 | 0.03 | 0.045 | 0.033 | 77.3
SATRAP Construction Company, Inc. | 2526 | L | AAA | LB | GE | Asphalt Overlay of Vigan Airport Road, K0408+000 to K0408+408+692 | Vigan City, Ilocos Sur | 2014-10-23 | 1st & Final | I | LF | 5.7553 | 22 | 2014-02-19 | 2014-03-12 | 0% | C | 0.399 | 0.2 | 0.3 | - | - | - | 89.9% | 89.9% Very Satisfactory
SATRAP Construction Company, Inc. | 2526 | L | AAA | LB | GE | Asphalt Overlay of Vigan-Caoayan Road, K0408+ (-012) to K0408+1997 | Vigan City-Caoayan, Ilocos Sur | 2014-10-23 | 1st & Final | I | LF | 19.6304 | 95 | 2014-03-06 | 2014-06-08 | 0% | C | 0.406 | 0.152 | 0.3 | - | - | - | 85.8% | 85.8% Satisfactory
SATRAP Construction Company, Inc. | 2526 | L | AAA | LB | GE1 | Replacement of Pantay Daya Bridge along Vigan-Sta.Catalina Rd. | Vigan City | 2013-03-20 | Final | I | LF | 18.395 | 296 | 2012-01-25 | 2012-11-15 | 1.07 | C | 0.478 | 0.133 | 0.3 | - | - | - | 91.1 | 87.89% Satisfactory
SBB Construction & Supply | 31238 | L | B | MA | GE | Widening of Davao-Bukidnon Road, (Lomondao Section), Km. 1659+997 - Km. 1661+091 | Davao City | 2014-10-20 | 1st & Final | XI | LF | 16.9014 | 162 | 2014-01-31 | 2014-07-11 |  | C | 0.422 | 0.139 | 0.3 | - | - | - | 86.1% | 86.1% Satisfactory
SBB Construction & Supply | 31238 | L | B | MA | GE | Construction and Maintenance of Bridges along National Roads a) Libby Bridge along Davao – Cotabato Old Road | Davao City | 2014-08-16 | 1st & Final | XI | LF | 3.9523 | 70 | 2014-02-12 | 2014-05-22 | 0 | C | 0.369 | 0.2 | 0.3 |  |  |  | 86.9 | 86.90% Satisfactory
SBB Construction & Supply | 31238 | L | C | SB | GE1 | Road Upgrading (Gravel to Paved) of Inawayan-Baracatan Road Km.1539+110-Km.1539+285 | Toril District, Davao City | 2013-08-05 | Final | XI | LF | 3.558 | 58 | 2013-01-22 | 2013-03-20 | 0 | C | 0.383 | 0.2 | 0.3 | - | - | - | 88.3 | 84.22% Satisfactory
SBB Construction & Supply | 31238 | L | C | SB | GE1 | Rd. Upgrading (Gravel to Paved) of Inawayan-Baracatan Rd., Km.1539+110-Km.1539+285 | Toril, Davao City | 2013-03-12 | 1st | XI | LF | 3.634 | 30 | 2013-01-22 | 2013-02-20 | 0 | O | 0.324 | 0.216 | 0.15 | 0.03 | 0.045 | 0.05 | 81.5 | -
SBB Construction & Supply | 31238 |  |  |  |  | Road Upgrading at Davao Regional Medical Training Center |  | 2010-06-16 |  | XI |  | 4.023 | 88 |  |  |  | O | 0.388 | 0.24 | 0.15 | 0.03 | 0.042 | 0.033 | 88.3 | -
SBB CONSTRUCTION & SUPPLY, INC. (Formerly: SBB Construction & Supply) | 31238 | L | B | MA | GE | Rehabilitation/ Reconstruction/ Upgrading of Damaged Paved along Davao-Bukidnon Road at Sitio Kibalang, Davao City | K1652+700 - K1653+090.00, 3rd Congressional District, Davao City | 2015-06-02 | Final | Davao City 2nd | LF | 6.775 | 77 | 2015-02-10 | 2015-04-27 | 0% | C | 0.403 | 0.133 | 0.3 | - | - | - | 83.6% | *83.6% Satisfactory
SBB CONSTRUCTION & SUPPLY, INC. (Formerly: SBB Construction & Supply) | 31238 | L | B | MA | GE | Off-Carriageway Improvement along J.P. Cabaguio Avenue, K1507+(-896) to K1507+770, Davao City | Davao City | 2015-11-19 | Final | Davao City 1st DEO | LF | 1.1056e-05 | 123 | 2015-04-23 | 2015-08-23 | 0 | C | 0.464 | 0.133 | 0.3 | - | - | - | 89.7% | 89.7% Very Satisfactory
SBF CONSTRUCTION & DEVELOPMENT | 11470 | L | A | MB | GE | Rehabilitation/Major Repair of Permanent Bridge, Balandra Bridge, Iloilo-East Coast-Capiz Road, Banate, Iloilo | Banate, Iloilo | 2015-11-17 | Final | Iloilo 2nd | LF | 19.3334 | 45 | 2015-10-26 | 2015-12-10 | (+) 61.48% | C | 0.5 | 0.133 | 0.3 | - | - | - | 93.3% | 93.3% Very Satisfactory
SBF Construction & Development Corporation | 11470 | L | A | MA | GB | Construction of 2-Storey 4-CL & 2-Storey 6-CL School Building in Oton National High School | Oton, Iloilo | 2014-08-05 | Final | VI | LF | 11.363 | 180 | 2013-03-27 | 2013-09-23 | 0 | C | 0.45 | 0.2 | 0.3 |  |  |  | 95 | 76.03% Unsatisfactory
SBF Construction & Development Corporation | 11470 | L | A | MA | GB1 | Const. of 2-Storey 4-CL & 2-Storey 6-CL Sch. Bldg. in Oton NHS | Oton, Iloilo | 2013-08-14 | 1st | VI | LF | 11.246 | 180 | 2013-03-27 | 2013-09-23 | -8.44 | O | 0.317 | 0.202 | 0.065 | 0.03 | 0.032 | 0.033 | 67.9
SBF CONSTRUCTION & DEVELOPMENT CORPORATION | 11470 | L | A | MB | GE | Widening of Malothot Bridge along Iloilo-Antique Road (Completion) | K0040+725, Miag-ao, Iloilo | 2015-06-03 | 1st | Iloilo First DEO | LF | 7.447 | 177 | 2015-02-16 | 2015-08-11 | 0.49% | O | 0.375 | 0.273 | 0.15 | 0.022 | 0.047 | 0.05 | 91.7% | -
SBU BUILDERS | 35570 | L | D | SB | GB | Construction of Multi-Purpose Building (Municipal Gym PH-10), Brgy. Southwestern Poblacion, Calamba, Misamis Occidental | Brgy. Southwestern Poblacion, Calamba, Misamis Occidental | 2015-11-20 | Final | Misamis Occidental 1st | LF | 1.8816 | 75 | 2015-05-18 | 2015-08-01 | (-) 2.92% | C | 0.467 | 0.2 | 0.212 | - | - | - | 87.9% | 87.9% Satisfactory
Scion Construction | 33680 | L | B | SB | GB | Construction of Multi Purpose Building, Kinalaglagan | Mataas na Kahoy, Batangas | 2014-08-09 | Final | IV-A | LF | 4.4274 | 150 | 2013-03-28 | 2013-08-24 | 0 | C | 0.414 | 0.2 | 0.3 |  |  |  | 91.4 | 84.89% Satisfactory
Scion Construction | 33680 | L | B | SB | GB1 | Const. of MPB, Kinalaglagan Mataas na Kahoy | Mataas na Kahoy, Batangas | 2013-08-01 | 1st | IVA | LF | 4.427 | 150 | 2013-03-28 | 2013-08-24 | 3.31 | O | 0.341 | 0.244 | 0.15 | 0.03 | 0.023 | 0.033 | 82.1
SCP Construction | 8797 | L | A | MB | GE2 | Sta. Josefa Pump Irrigation Project | Agusan del Sur/ Caraga Region | 2014-08-30 | Final | NIA | LF | 16.013 | 364 | 2012-09-19 | 2013-09-17 | 0 | C | 0.3758 | 0.1961 | 0.3 | - | - | - | - | 87.19% Satisfactory
SCP Construction | 8797 | L | AAA | MB | GE2 | Balingasag River Irrigation Project | Balingasag, Misamis Oriental / Region 10 | 09/26-27/11 | 1st | NIA | LF | 199.249 | 465 | 2009-11-11 | 2011-12-31 | -19.13 | O | 0.3388 | 0.2451 | 0.109 | 0.024 | 0.056 | 0.0333 | 80.62 | -
SCP Construction | 8797 | L | AAA | LB | GE1 | Rehab./Reconst. of Damaged Paved National Roads along Butuan City-Cagayan de Oro City-Iligan City Road |  | 2009-03-09 | 2nd | X |  | 18.867 | 234 |  |  |  | O | 0.327 | 0.24 | 0.055 | 0.03 | 0.045 | 0.033 | #VALUE! | -
SCP Construction | 8797 | L | AAA | LB | GE1 | Rehab./Reconst. of Damaged Paved National Roads along Butuan City-Cagayan de Oro City-Iligan City Road |  | 2008-11-24 | 1st | X |  | 18.867 | 210 |  |  |  | O | 0.365 | 0.24 | 0.1 | 0.03 | 0.035 | 0.067 | 83.7 | -
SCP Construction | 8797 | L | AAA | LB | GE1 | Conc. of Surigao-Davao Coastal Rd.(Tagsaka-Bislig Subsection) along Hinatuan-Bislig-Boston Sect. |  | 2009-09-10 | 3rd | XIII |  | 156.872 | 433 |  |  |  | O | 0.378 | 0.238 | 0.13 | 0.03 | 0.06 | 0.033 | 86.9 | -
SCP Construction | 8797 | L | AAA | LB | GE1 | Conc. of Surigao-Davao Coastal Road (Tagsaka-Bislig Subsection) along Hinatuan-Bislig-Section |  | 2009-06-06 | 2nd | XIII |  | 156.872 | 405 |  |  |  | O | 0.379 | 0.3 | 0.15 | 0.03 | 0.061 | 0.05 | 97 | -
SCP Construction | 8797 | L | AAA | LB | GE1 | Conc. of SDCR, (Tagasaka-Bislig Subsection) along Hinatuan-Bislig-Boston Section |  | 2008-11-28 | 1st | XIII |  | 158.872 | 375 |  |  |  | O | 0.278 | 0.184 | 0.1 | 0.03 | 0.03 | 0.1 | 72.2 | -
SCP Construction | 8797 | L | AA | LA | GE1 | Const. of Jct. Sayre Highway-Aglayan-Alanib-Ticalaan Road, Ticalaan-Paganan Sect. | Bukidnon | 2012-11-20 | 2nd | X | LF | 95.328 | 375 | 9//11/08 | 2009-09-20 | -398.56 | O | 0.245 | 0.208 | 0 | 0.02 | 0.012 | 0 | 48.5 | -
SCP Construction | 8797 | L | AA | LA | GE1 | Const. of Jct. Sayre Highway-Aglayan-Alanib-Ticalaan Rd., Ticalaan-Paganan Sect. | Bukidnon | 2012-08-11 | 1st | X | LF | 95.33 | 375 | 2008-09-11 | 2009-09-20 | - | O | 0.071 | 0.18 | 0 | 0.02 | 0.008 | 0.017 | 29.6 | -
SCP Construction | 8797 | L | AA | LA | GE1 | Rd. Upgrading (Gravel to Paved) of Gingoog-Claveria-Villanueva Rd. | Gingoog City, Misamis Oriental | 2012-11-21 | 2nd | X | LF | 24.513 | 531 | 2010-03-31 | 2011-09-12 | -65.63 | O | 0.191 | 0.204 | 0 | 0.02 | 0.012 | 0 | 42.7 | -
SCP Construction | 8797 | L | AA | LA | GE1 | Rd. Upgrading (Gravel to Paved) of Gingoog-Claveria-Villanueva Rd. | Gingoog City | 2012-08-07 | 1st | X | LF | 24.513 | 531 | 2010-03-31 | 2011-09-12 | - | O | 0.038 | 0.18 | 0 | 0.02 | 0 | 0.017 | 25.5 | -
SCP Construction |  | L | AAA | MB | GE2 | Balingasag River Irrigation Project | Balingasag, Misamis Oriental / Region 10 | 2012-03-27 | 2nd | NIA | LF | 199.249 | 585 | 2009-11-11 | 2011-12-31 | 0.11 | O | 0.3341 | 0.2562 | 0.15 | 0.03 | 0.056 | 0.0333 | 85.96 | -
SCP Construction | 8797 |  |  |  |  | Conc. of Surigao-davao Coastal Rd. (Tagasaka-Bislig Subsection) along Hinatuan-Bislig-Boston Section) |  | 2010-03-06 |  | XIII |  | 156.872 | 555 |  |  |  | O | 0.231 | 0.3 | 0.071 | 0.03 | 0.047 | 0.05 | 72.9 | -
SENTINA CONSTRUCTION AND SUPPLY | 20649 | L | B | SB | GE | Construction of Farm to Market Road Barangay Catungan IV, Sibalom, Antique | Barangay Catungan IV, Sibalom, Antique | 2015-11-10 | Final | Antique | LF | 1.9597 | 62 | 2015-05-22 | 2015-07-23 | 0.00% | C | 0.395 | 0.2 | 0.3 | - | - | - | 89.5% | 89.5% Very Satisfactory
Settlers Builder | 21643 | L | B | MA | GE1 | Replacement/Const. of Bongsod Bridge, Km. 105+650.50, Brgy. Bongsod | Sibalom, Antique | 2013-08-15 | 1st | VI | LF | 11.889 | 178 | 2013-02-12 | 2013-08-08 | -10.69 | O | 0.354 | 0.3 | 0.004 | 0.03 | 0.033 | 0.033 | 75.4
Settlers Builder | 21643 |  |  |  |  | Const. of 2-CL Bldg. at Apgahan Elem. School |  | 2010-02-25 |  | VI |  | 0.888 | 80 |  |  |  | O | 0.352 | 0.3 | 0.15 | 0 | 0.022 | 0.033 | 85.7 | -
Settlers Builder | 21643 | L | B | MA | GE1 | Replacement/Const. of Guinbanga-an Bridge | San Jose, Antique | 2012-11-22 | 1st | VI | LF | 16.186 | 290 | 2012-05-22 | 2013-03-06 | -2.21 | O | 0.308 | 0.275 | 0.128 | 0.03 | 0.055 | 0.033 | 82.9 | -
SETTLERS BUILDER | 21643 | L | B | MA | GE | Construction of Farm to Market Road | Brgy. Vilvar-Brgy.Baladjay-Brgy.Magdalena, San Remegio, Antique | 2015-06-04 | Final | Antique DEO | LF | 1.983 | 37 | 2015-03-04 | 2015-04-09 | 0.32% | C | 0.455 | 0.14 | 0.3 | - | - | - | 89.5% | *89.5% Very Satisfactory
SETTLERS BUILDER | 21643 | L | B | MA | GE | Construction of Farm to Market Road | Barangay Panlagangan, Sibalom, Antique | 2015-08-31 | 1st & Final | Antique | LF | 1.974 | 62 | 2015-05-22 | 2015-07-22 | 0% | C | 0.482 | 0.133 | 0.3 | - | - | - | 91.5% | *91.5% Very Satisfactory
SETTLERS BUILDER | 21643 | L | B | MA | GE | Contract I.D. No. 15GB0036 - Asset Preservation of National Roads Preventive Maintenance-Reblocking of Shattered Blocks, Hamtic-Bia-An-Egaña-Sibalom Road, K0090+(-167)-K00090+069.50 (See Attached Detailed Station Limits), K0090+069.50-K0090+626 (See Attached Detailed Station Limits), K0094+418.40-K0094+603 (See Attached Detailed Station Limits), K0095+216-K0095+997.50 (See Attached Detailed Station Limits), K0100+001.20-K0100+262.20 (See Attached Detailed Station Limits) | Hamtic and Sibalom, Antique | 2015-08-31 | 1st | Antique | LF | 20.637 | 114 | 2015-05-22 | 2015-09-12 | 0.52% | O | 0.361 | 0.239 | 0.15 | 0.03 | 0.045 | 0.05 | 87.5% | -
SETTLERS BUILDER | 21643 | L | B | MA | GE | Asset Preservation of National Roads Preventive Maintenance Reblocking of Shattered Blocks, Hamtic-Bia-an-Egana-Sibalom Road, K0090+(-167)+K0090+069.50, K0100+001.20-K0100+262.20, Hamtic and Sibalom, Antique | Hamtic and Sibalom, Antique | 2015-11-10 | Final | Antique | LF | 20.6367 | 114 | 2015-05-22 | 2015-09-13 | 0.00% | C | 0.381 | 0.2 | 0.3 | - | - | - | 88.1% | 87.74% Satisfactory
Seven Digit Construction & Supplies | 25471 | L | B | MA | GE1 | Puerto Princesa North Road (PPNR) Junction Taytay Poblacion Road (Const. of Drainage and Sidewalk) |  | 2009-06-03 | 1st | IV-B |  | 10.443 | 233 |  |  |  | O | 0.321 | 0.3 | 0.1 | 0.03 | 0.035 | 0.033 | 81.9 | -
Seven Digit Construction & Supplies | 25471 | L | B | MA | GE | Construction of Drainage/Slope Protection Works along Puerto Princesa North Road (Intermittent) Langogan-Roxas Road Section | K0082+080-K0105+604, Roxas, Palawan | 2014-11-20 | 1st & Final | IV | LF | 18.1298 | 136 | 2014-03-03 | 2014-07-16 | - | C | 0.441 | 0.133 | 0.3 | - | - | - | 87.4% | 87.4% Satisfactory
Seven Digit Construction & Supplies | 25471 | L | B | MA | GE | Construction of Drainage/Slope Protection Works along Puerto Princesa Princesa North Road (Intermittent) Roxas-Taytay Road Section | K0172+080-K0189+225, Roxas, Palawan | 2014-11-20 | 1st & Final | IV | LF | 17.875 | 181 | 2014-03-03 | 2014-08-30 | 0% | C | 0.391 | 0.133 | 0.3 | - | - | - | 82.4% | 82.4% Satisfactory
SEVEN DIGIT CONSTRUCTION & SUPPLIES | 25471 | L | B | SB | GB | Construction of Multi-Purpose Building, Barangay Mendoza | Roxas, Palawan | 2015-11-13 | 1st | Palawan 1st DEO | LF | 0.86387 | 170 | 2015-07-30 | 2016-01-15 | 0.3919 | OG | 0.39 | 0.24 | 0.15 | 0.015 | 0.029 | 0.05 | 87.4% | 87.4% Satisfactory
SEVEN DIGIT CONSTRUCTION AND SUPPLIES | 25471 | L | B | MA | GE | Construction of Access Road Leading to RORO Port Brgy. San Fernando Sta. 00+000 - Sta. 1+135 | El Nido, Palawan | 2015-06-05 | 1st | Palawan 1st DEO | LF | 22.323 | 112 | 2015-04-02 | 2015-07-22 | 0% | O | 0.357 | 0.267 | 0.15 | 0.015 | 0.058 | 0.05 | 89.7% | -
SHA SHA LUMBER & CONSTRUCTION | 15162 | L | B | SB | GB | Cluster F - Local Infrastructure Program (LIP) Construction of Multi-purpose Covered Court per Barangay: Brgy. Miaga, Brgy. Crossing, Brgy. Quezon, Brgy. San Mateo USON, Masbate & Brgy. Iligan | Municipality of USON & Esperanza, Masbate | 2015-09-04 | 1st & Final | Masbate Second DEO | LF | 1.91 | 149 | 2015-04-13 | 2015-09-08 | 1.5% | C | 0.493 | 0.133 | 0.3 | - | - | - | 92.6% | *92.6% Very Satisfactory
Shak Construction and Supply | 28289 | L | C | SB | GE1 | Repair/Rehab. of Road Poblacion | Jordan, Guimaras | 2011-04-05 | 1st | VI | LF | 4.986 | 90 | 2011-02-17 | 2011-05-17 | 37.5 | O | 0.35 | 0.237 | 0.15 | 0.03 | 0.037 | 0.033 | 83.7 | -
Shak Construction and Supply | 28289 | L |  | SB | GE2 | Construction of ITO SUR SWIP | ITO Sur, Cabanatuan, Iloilo/Region VI | 2013-08-31 | 1st | NIA | L | 5.191 | 127 | 2013-04-09 | 2013-08-13 | 0 | C | 0.3393 | 0.24 | 0.15 | 0.025 | 0.056 | 0.05 | 86.03 | -
SHANLEY CONSTRUCTION | 35633 | L | C | SB | GE | Concreting of Local Roads, Barangay Nammatan, San Agustin, Isabela 4TH LD | San Agustin, Isabela 4th | 2015-11-17 | Final | ISABELA 4TH DEO | LF | 2.1987 | 120 | 2015-06-17 | 2015-10-14 | - | C | 0.371 | 0.134 | 0.3 | - | - | - | 80.5% | 80.5% Unsatisfactory
Shear Construction and Supply | 34027 | L | B | MA | GE | Construction of Brgy. Road, Brgy. Cotmo and Brgy. Tagpocol to Pinamasagan | San Fernando, Camarines Sur | 2014-11-10 | 1st & Final | V | LF | 7.3042 | 120 | 2014-07-03 | 2014-10-30 | 6.94% | C | 0.423 | 0.133 | 0.3 | - | - | - | 85.6% | 85.6% Satisfactory
Sheen-Sheen Construction | 29015 | L | D | SB | GE1 | Rehab. of CCR, Maac-Kalipagas Section |  | 2009-03-07 | 1st | X |  | 9.536 | 197 |  |  |  | O | 0.36 | 0.24 | 0.15 | 0.03 | 0.04 | 0.033 | #VALUE! | -
Sheen-Sheen Construction | 20915 | L | D | SB | GE1 | Impvt./Const. of Road leading to St. Peter's Village (Vicente Reyes) Sitio Lamok, Benoni |  | 2009-09-05 | 1st | X |  | 1.733 | 110 |  |  |  | O | 0.383 | 0.3 | 0 | 0.03 | 0.051 | 0.017 | 78.1 | -
SHEPPERD CONSTRUCTION AND SUPPLY | 37373 | L | B | SB | GE | Concreting of Sison-Zion Road | Maitum, Sarangani Road | 2015-06-11 | Final | Sarangani DEO | LF | 4.698 | 75 | 2015-04-02 | 2015-06-15 | 6.81% | C | 0.427 | 0.133 | 0.3 | - | - | - | 86% | *86% Satisfactory
Silk & Steel Construction | 25314 |  |  |  |  | Const. of MPB at Brgy.Alang-Alang |  | 2010-09-06 |  | VIII |  | 4.785 | 244 |  |  |  | O | 0.368 | 0.24 | 0.15 | 0.03 | 0.018 | 0.033 | 83.9 | -
Silver Dragon Construction & Lumber & Glass Supply | 30835 | L | A | MA | GE2 | Repair/Rehab. of Orong Revetment Wall, Sta. 0+000-Sta. 0+072, Brgy. Orong | Kabankalan City, Negros Occidental | 2013-08-08 | Final | VI | LF | 2.982 | 102 | 2012-12-26 | 2013-04-06 | 1.39 | C | 0.414 | 0.133 | 0.3 | - | - | - | 84.7 | 86.08% Satisfactory
Silver Dragon Construction & Lumber & Glass Supply | 30835 | L | A | MA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rd. (Int. Sect.) Bacolod South Nat'l Arterial Rd. (By-Pass Rd.), K0020+029.50-K0020+685.50 | Bago City, Negros Occidental | 2013-08-11 | Final | VI | LF | 12.295 | 106 | 2013-01-24 | 2013-05-10 | 0 | C | 0.395 | 0.133 | 0.3 | - | - | - | 82.8 | 85.92% Satisfactory
Silver Dragon Construction & Lumber & Glass Supply | 30835 | L | A | MA | GE1 | Repair/Rehab./Impv't. of Iloilo-Capiz Rd. (New Route), Roxas Ave., Km.114+800-Km.115+535 w/ exception | Roxas City, Capiz | 2013-08-18 | 1st | VI | LF | 9.132 | 75 | 2013-07-08 | 2013-09-21 | 22.74 | O | 0.339 | 0.24 | 0.15 | 0.03 | 0.05 | 0.033 | 84.2
Silver Dragon Construction & Lumber & Glass Supply | 30835 | L | A | MB | GE | Widening of Arterial Road in Bacolod South Road, K0006+969 - K0008+462 with exception | Bacolod City | 2014-10-27 | 1st & Final | VI | LF | 35.4309 | 150 | 2014-04-07 | 2014-09-03 |  | C | 0.449 | 0.133 | 0.3 | - | - | - | 88.2% | 88.2% Satisfactory
Silver Dragon Construction & Lumber & Glass Supply | 30835 | L | A | MB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Road (Intermittent Section), Bacolod South Road, Section I (Valladolid Section): K0028+840 - K0031+620, Section II (San Enrique Section): K0034+503 - K0035+490 | Valladolid-San Enrique, Negros Occidental | 2014-10-27 | 1st & Final | VI | LF | 70.0952 | 275 | 2014-05-14 | 2015-02-12 | 40% | C | 0.435 | 0.133 | 0.3 | - | - | - | 86.8% | 86.8% Satisfactory
Silver Dragon Construction & Lumber & Glass Supply | 30835 | L | A | MB | GE | Assets Preservation of National Roads Generated from Pavement Management System/Highway Development and Management - 4 (HDM-4), Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Road, (Intermittent Sections), K0025+(-165) - K0026+422, Bago-Mambucal Road | Bago City, Negros Occidental | 2014-10-22 | 1st & Final | VI | LF | 23.5395 | 125 | 2014-02-24 | 2014-06-28 | 59.2% | C | 0.461 | 0.133 | 0.3 | - | - | - | 89.4% | 89.4% Very Satisfactory
Silver Dragon Construction & Lumber & Glass Supply | 30835 | L | A | MA | GE | Repair/Rehab./Impv't. of Iloilo-Capiz Road (New Route) Roxas Ave., Roxas City, Km. 14+800 - Km. 115+535 with exception | Roxas City, Capiz | 2014-08-14 | Final | VI | LF | 9.9907 | 125 | 2013-06-21 | 2013-08-21 | 2.11 | C | 0.349 | 0.2 | 0.3 |  |  |  | 84.9 | 84.48% Satisfactory
Silver Dragon Construction & Lumber & Glass Supply | 30835 | L | A | MB | GE | Road Upgrading (Gravel to Paved) Based on Gravel Road Strategies Traffic Benchmark for Upgrading to Paved Road Standard (HDM-4) Project Analysis (Intemittent Section) Bago-Mambucal National Secondary Road K0058+688 - K0059+616 | Bago City, Negros Occidental | 2014-08-07 | Final | VI | LF | 21.1977 | 250 | 2013-01-24 | 2013-05-15 | 0 | C | 0.4 | 0.2 | 0.3 |  |  |  | 90 | 86.64% Satisfactory
Silver Dragon Construction & Lumber & Glass Supply | 30835 | L | A | MA | GE1 | Road Upgrading (Gravel to Paved) (Int. Sect.) Bago-Mambucal Nat'l Sec. Rd., K0058+688.00-K0059+616 | Bago City, Negros Occidental | 2013-08-11 | 2nd | VI | LF | 21.198 | 244 | 2013-01-24 | 2013-09-24 | 1.31 | O | 0.33 | 0.237 | 0.15 | 0.03 | 0.042 | 0.05 | 83.9
Silver Dragon Construction & Lumber & Glass Supply | 30835 | L | A | MA | GE | Const. of Flood Control Structure along Bago River across Bacolod South National Arterial Road, Sta. 0+136.12 - Sta. 0+360 Bantayan Section | Bago City, Negros Occidental | 2014-08-07 | Final | VI | LF | 15.4921 | 133 | 2013-04-15 | 2013-08-25 | 1.18 | C | 0.377 | 0.2 | 0.3 |  |  |  | 87.7 | 86.56% Satisfactory
Silver Dragon Construction & Lumber & Glass Supply | 30835 | L | A | MA | GE2 | Const. of Flood Control Structure along Bago River Across Bacolod South Nat'l Arterial Rd., Sta. 0+136.12-Sta. 0+360, Bantayan Sect. | Bago City, Negros Occidental | 2013-08-11 | 1st | VI | LF | 15.492 | 133 | 2013-04-15 | 2013-08-26 | 5.79 | O | 0.3 | 0.3 | 0.15 | 0.023 | 0.035 | 0.05 | 85.8
Silver Dragon Construction & Lumber & Glass Supply | 30835 | L | A | MB | GE | Widening of Bacolod South Road, K0002+971 - K0003+787 | Bacolod City | 2015-08-28 | 1st | Bacolod City | LF | 27.732 | 190 | 2015-03-02 | 2015-09-07 | 6.13% | O | 0.356 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 88.1% | -
Silver Dragon Construction & Lumber & Glass Supply | 30835 | L | A | SB | GE2 | Repair/Rehab. of Orong Revetment Wall, Sta.0+000-Sta.0+072, Brgy. Orong | Kabankalan, Negros Occidental | 2013-03-13 | 1st | VI | LF | 2.982 | 102 | 2012-12-26 | 2013-04-06 | -6.16 | O | 0.375 | 0.3 | 0.088 | 0.024 | 0.05 | 0.033 | 87 | -
Silver Dragon Construction & Lumber & Glass Supply | 30835 | L | A | MA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l. Rd. (Int. Sect.) Bacolod South Nat'l. Arterial Rd. (By-Pass Road) K0020+029.50-K0020+685.50 | Bago City, Negros Occidental | 2013-03-14 | 1st | VI | LF | 12.295 | 75 | 2013-01-24 | 2013-04-08 | 19.19 | O | 0.322 | 0.3 | 0.15 | 0.018 | 0.04 | 0.05 | 88 | -
Silver Dragon Construction & Lumber & Glass Supply | 30835 |  |  |  |  | Rehab./Reblocking of Bacolod Circumferential Rd. from Brgy. Pahanocoy to Brgy. Banago Sect. w/ exception |  | 2010-06-07 |  | VI |  | 38.198 | 275 |  |  |  | O | 0.326 | 0.24 | 0.15 | 0.03 | 0.051 | 0.033 | 83 | -
SILVER DRAGON CONSTRUCTION & LUMBER & GLASS SUPPLY | 30835 | L | A | MB | GE | Widening of Bacolod South Road K0002+971-K0003+787 | Bacolod City | 2015-06-11 | 1st | Bacolod City | LF | 27.733 | 190 | 2015-03-02 | 2015-09-07 | 17.06% | O | 0.337 | 0.249 | 0.15 | 0.03 | 0.05 | 0.05 | 86.6% | -
SILVER DRAGON CONSTRUCTION & LUMBER & GLASS SUPPLY | 30835 | L | A | MB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Road including Drainage Based on Pavement Management System (PMS) Highway Development & Management-4 (HDM-4), Intermittent Section Secondary Road | K0108+162-K0109+138, K0109+850-K0110+424, Lanot-Loctugan-Panitan Boundary Road | 2015-06-06 | 1st | Capiz First DEO | LF | 23.984 | 135 | 2015-02-18 | 2015-07-02 | -1.18% | O | 0.324 | 0.25 | 0.138 | 0.03 | 0.04 | 0.05 | 83.2% | -
SILVER DRAGON CONSTRUCTION & LUMBER & GLASS SUPPLY | 30835 | L | A | MB | GE | Rehabilitation/ Reconstruction/ Upgrading of Damaged Paved National Road along Bacolod North Road, K0131+000 - K0132+026, K0136+882 - K0137+927, K0138+372 - K0139+303, K0140+670 - K0141+000, K0141+894 - K0142+600, K0143+250 - K0143+620, K0145+103-K0145+702 | Calatrava, San Carlos City, Negros Occidental | 2015-08-25 | 1st | Regional Office No.VI | LF | 88.298 | 280 | 2015-03-25 | 2015-12-29 | 10.19% | O | 0.369 | 0.236 | 0.15 | 0.03 | 0.055 | 0.05 | 89% | -
SILVER DRAGON CONSTRUCTION & LUMBER & GLASS SUPPLY | 30835 | L | A | MB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Road along Bacolod North Road, K0094+354-K0094+500, K0098+164-K0098+689, K0106+325-K0106+873, K0113+464-K0114+852, K0116+177-K0116+700, K0120+000-K0121+000, K0121+967-K0123+000, K0124+127-K0124+990, K0126+575-K0126+969, K0128+000-K0128+561, K0129+339-K0129+439, K0137+000-K0138+372, Bacolod, Negros Occidental | Bacolod, Negros Occidental | 2015-11-19 | 1st | Regional Office, NIR | LF | 101.4133 | 350 | 2015-03-25 | 2016-03-08 | (+)13.12% | OG | 0.374 | 0.236 | 0.15 | 0.03 | 0.06 | 0.05 | 90% | 90% Very Satisfactory
SILVER DRAGON CONSTRUCTION & LUMBER & GLASS SUPPLY | 30835 | L | A | MB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Road along Bacolod North Road, K0131+000-K0132+026, K0136+882-K0137+927, K0138+372-K0139+303, K0140+670-K0141+000, K0141+894-K0142+600, K0143+250-K0143+620, K0145+103-K0145+702, Calatrava, San Carlos City, Negros Occidental | Calatrava, San Carlos City, Negros Occidental | 2015-11-19 | 1st | Regional Office, NIR | LF | 88.2984 | 280 | 2015-03-25 | 2015-12-29 | (+)0.76% | OG | 0.343 | 0.281 | 0.15 | 0.03 | 0.055 | 0.05 | 90.9% | 90.9% Very Satisfactory
SILVER DRAGON CONSTRUCTION & LUMBER & GLASS SUPPLY | 30835 | L | A | MB | GE | Replacement of Permanent Weak Bridge, Himuang Bridge I along Bacolod South Road (S00127NR) With Contract I.D. No. 15G N0004, Valladolid, Negros Occidental | Valladolid, Negros Occidental | 2015-11-16 | Final | Negros Occidental 4th DEO | LF | 15.0041 | 195 | 2015-02-23 | 2015-09-05 | (+)15.385 | C | 0.473 | 0.133 | 0.3 | - | - | - | 90.6% | 90.6% Very Satisfactory
Silver Dragon Construction Lumber and Glass Supply | [5 empty] | Procurement of Fully Developed Lots and Completed Housing Units (559) at Escalante Heights | Brgy. Old Poblacion, Escalante City, Negros Occidental | 2016-07-23 | 1st | NHA | LF | 161.998 | 285 | 2015-03-22 | 2016-11-18 | -12.68 | O | 0.3545 | 0.2929 | 0.0135 | 0.03 | 0.056 | 0.0167 | 76.36 | -
SILVERGRACES CONSTRUCTION AND CONSTRUCTION SUPPLY | 36158 | L | C | SB | GE | Local Infrastructure Program-Concreting of Farm to Market Road | Barangay Tina, Makato, Aklan | 2015-06-05 | Final | Aklan DEO | LF | 1.939 | 67 | 2015-02-20 | 2015-04-27 | 0% | C | 0.397 | 0.183 | 0.3 | - | - | - | 88% | *88% Satisfactory
SISSI-IT CONSTRUCTION | 34967 | L | D | SB | GE | Rehabilitation of Ambabag-Lip-atan Farm to Market Road | Guinaoang, Mankayan, Benguet | 2015-06-04 | Final | Benguet 2nd DEO | LF | 0.486 | 37 | 2015-02-24 | 2015-04-01 | (+) 59.46% | C | 0.469 | 0.133 | 0.3 | - | - | - | 90.2% | *90.2% Very Satisfactory
Sixteen Enterprises - Calapan Branch | 18187 | L | A | MA | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved Road, Pinamalayan Airport Road, Gloria Section (K0077+130 - K0079+006 w/ Exception) | Gloria, Oriental Mindoro | 2014-08-12 | 1st | IV-B | LF | 18.5456 | 144 | 2014-05-12 | 2014-10-02 | 3.68 | O | 0.366 | 0.236 | 0.15 | 0.03 | 0.045 | 0.033 | 86
Sixteen Enterprises - Calapan Branch | 18187 | L | A | MA | GE | Widening (Paving of Shoulder) - Seal Widening of Calapan South Road K005+415 - K007+187 (Intermittent Section) | Calapan City, Oriental Mindoro | 2014-08-11 | 1st & Final | IV-B | LF | 16.541 | 121 | 2014-04-30 | 2014-08-28 | 11 | C | 0.415 | 0.133 | 0.3 |  |  |  | 84.8 | 84.80% Satisfactory
Sixteen Enterprises - Calapan Branch | 18187 | L | A | MA | GE | Replacement/Rehabilitation/Strengthening of Babangonan Bridge, CSR Junction Minas, K0036+370 | Victoria, Oriental Mindoro | 2014-08-11 | Final | IV-B | LF | 12.8504 | 201 | 2013-02-19 | 2013-09-07 | 0 | C | 0.439 | 0.132 | 0.3 |  |  |  | 87.1 | 85.96% Satisfactory
Sixteen Enterprises - Calapan Branch | 18187 | L | A | MA | GE1 | Replacement/Rehab./Strengthening of Babangonan Bridge, CSR Jct. Minas, K0036+370 | Victoria, Oriental Mindoro | 2013-08-01 | 1st | IVB | LF | 12.851 | 180 | 2013-02-19 | 2013-08-17 | 0.31 | O | 0.352 | 0.238 | 0.15 | 0.02 | 0.042 | 0.05 | 85.2
Sixteen Enterprises - Calapan Branch | 18187 | L | A | MA | GE2 | Const. of Bongabong Flood Control (Aplaya Sect.) | Bongabong, Oriental Mindoro | 2013-07-31 | Final | IVB | LF | 18.189 | 174 | 2013-01-28 | 2013-07-19 | 1.2 | C | 0.439 | 0.147 | 0.3 | - | - | - | 88.6 | 86.92% Satisfactory
Sixteen Enterprises - Calapan Branch | 18187 | L | A | MA | GE2 | Const. of Bongabong Seawall (Aplaya Sect.) | Bongabong, Oriental Mindoro | 2013-07-31 | Final | IVB | LF | 18.004 | 144 | 2013-01-17 | 2013-06-09 | 1.33 | C | 0.417 | 0.143 | 0.3 | - | - | - | 86 | 86.42% Satisfactory
Sixteen Enterprises - Calapan Branch | 18187 | L | A | MA | GE2 | Const. of Bansud River Control | Bansud, Oriental Mindoro | 2013-07-31 | Final | IVB | LF | 9.098 | 150 | 2013-01-28 | 2013-06-26 | 25 | C | 0.38 | 0.2 | 0.3 | - | - | - | 88 | 85.30% Satisfactory
Sixteen Enterprises - Calapan Branch | 18187 | L | A | MA | GE1 | Completion of Calapan South Road, Tuklong-San Roque Section |  | 2009-09-05 | 1st | IVB |  | 38.11 | 238 |  |  |  | O | 0.378 | 0.24 | 0.15 | 0.03 | 0.051 | 0.05 | 89.9 | -
SIXTEEN ENTERPRISES - CALAPAN BRANCH | 18187 | L | A | MB | GE | Rehab./Reconst. of Agos Bridge 1 | Pinamalayan, Oriental Mindoro | 2015-11-19 | Final | Southern Mindoro DEO | LF | 11.3639 | 207 | 2015-03-17 | 2015-10-09 | 0.01 | C | 0.489 | 0.181 | 0.3 | - | - | - | 97% | 97% Outstanding
Sixteen Enterprises / Lumel Glenn Construction (JV) | JV-12-086 | L | A | MA | GE1 | Impv't./Conc. of Calapan South Rd., Maligaya-Narra Sect. (K0075+849-K0079+233) (w/ exception) | Gloria, Oriental Mindoro | 2013-07-31 | Final | IVB | LF | 43.028 | 228 | 2012-10-05 | 2013-05-20 | 0 | C | 0.429 | 0.14 | 0.3 | - | - | - | 86.9 | 87.05% Satisfactory
Sixteen Enterprises / Lumel Glenn Construction (JV) | JV-11-086 | L | A | MA | GE1 | Impv't./Conc. of Calapan South Rd., Maligaya-Narra Sect., (K0075+849-K0079+233 w/ exception) | Gloria, Oriental Mindoro | 2013-03-20 | 2nd | IVB | LF | 41.343 | 198 | 2012-10-05 | 2013-04-20 | 9.38 | O | 0.362 | 0.24 | 0.15 | 0.03 | 0.045 | 0.033 | 86 | -
Sixteen Enterprises / Lumel Glenn Construction Joint Venture | JV-11-086 | L | A | MA | GE1 | Impvt./Conc. of Calapan South Rd., Maligaya-Narra Sect. (K0075+849-K00791+233 w/ exception) | Gloria, Oriental Mindoro | 2012-11-27 | 1st | IVB | LF | 41.343 | 183 | 2012-10-05 | 2013-04-05 | 2.9 | O | 0.367 | 0.236 | 0.15 | 0.03 | 0.05 | 0.05 | 88.3 | -
Sixteen Enterprises / Thunderheads Const. (JV) | JV-08-302 | L | A | MA | GE1 | Completion of Calapan South Road, Nasucob Section |  | 2009-09-05 | 1st | IVB |  | 19.06 | 224 |  |  |  | O | 0.359 | 0.245 | 0.15 | 0.03 | 0.051 | 0.05 | 88.5 | -
Sixteen Enterprises-Calapan Branch | 18187 | L | A | MA | GE2 | Const. of Bongabong Flood Control (Aplaya Sect.) | Bongabong, Oriental Mindoro | 2013-03-20 | 1st | IVB | LF | 18.189 | 144 | 2013-01-28 | 2013-06-20 | 16.06 | O | 0.347 | 0.243 | 0.15 | 0.03 | 0.055 | 0.033 | 85.8 | -
Sixteen Enterprises-Calapan Branch | 18187 | L | A | MA | GE2 | Const. of Bongabong Seawall (Aplaya Sect.) | Bongabong, Oriental Mindoro | 2013-03-20 | 1st | IVB | LF | 18.004 | 144 | 2013-01-17 | 2013-06-09 | 8.4 | O | 0.368 | 0.241 | 0.15 | 0.03 | 0.045 | 0.033 | 86.7 | -
Sixteen Enterprises-Calapan Branch | 18187 | L | A | MA | GE2 | Const. of Bansud River Control | Bansud, Oriental Mindoro | 2013-03-20 | 1st | IVB | LF | 9.098 | 150 | 2013-01-28 | 2013-06-26 | 29.34 | O | 0.272 | 0.3 | 0.15 | 0.03 | 0.05 | 0.033 | 83.5 | -
Sixteen Enterprises-Calapan Branch | 18187 | L | A | MA | GE2 | Const. of Sumagui River Control along Calapan South Rd., Brgy. Sumagui | Bansud, Oriental Mindoro | 2013-03-20 | Final | IVB | LF | 14.77 | 198 | 2012-08-31 | 2013-03-16 | 8.4 | C | 0.362 | 0.2 | 0.3 | - | - | - | 86.2 | 87.76% Satisfactory
Sixteen Enterprises-Calapan Branch | 18187 | L | A | MA | GE | Concreting of Calapan South Road, K0161+000-K0161+901 | Brgy. Cabalwa, Mansalay, Oriental Mindoro | 2014-11-27 | 1st & Final | IV | LF | 14.337 | 189 | 2014-05-12 | 2014-11-16 | 0.5% | C | 0.449 | 0.133 | 0.3 | - | - | - | 88.2% | 88.2% Satisfactory
Sixteen Enterprises-Calapan Branch | 18187 | L | A | MA | GE | Construction of Bubuli River Control | Baco, Oriental Mindoro | 2014-11-28 | 1st & Final | IV | LF | 9.1931 | 78 | 2014-02-24 | 2014-05-12 | 0% | C | 0.493 | 0.133 | 0.3 | - | - | - | 92.6% | 92.6% Very Satisfactory
Sixteen Enterprises-Calapan Branch | 18187 | L | A | MB | GE | Concreting & Rehabilitation of Local Road-Manganngan I | Baco, Oriental Mindoro | 2014-11-28 | 1st & Final | IV | LF | 9.2778 | 60 | 2014-04-02 | 2014-05-31 | 0% | C | 0.426 | 0.133 | 0.3 | - | - | - | 85.9% | 85.9% Satisfactory
SIXTEEN ENTERPRISES-CALAPAN BRANCH | 18187 | L | A | MA | GE | Construction of Gabions Revetment Baroc River Control | Mansalay, Oriental Mindoro | 2015-06-11 | 1st | Southern Mindoro DEO | LF | 18.57 | 163 | 2015-02-18 | 2015-07-30 | 0% | O | 0.38 | 0.244 | 0.15 | 0.03 | 0.051 | 0.05 | 90.5% | -
SIXTEEN ENTERPRISES-CALAPAN BRANCH | 18187 | L | A | MB | GE | Completion of Roma Bailey Bridge & Approaches | Mansalay, Oriental Mindoro | 2015-06-10 | Final | Southern Mindoro DEO | LF | 4.791 | 75 | 2015-02-18 | 2015-05-03 | 0% | C | 0.486 | 0.15 | 0.3 | - | - | - | 93.6% | *93.6% Very Satisfactory
Sixteen Enterprises-Calapan Branch/L.N. Salvador Construction (JV) | JV-13-410 | L | A | MA | GE | Rehab./Reconst./Upgrading of Damaged Paved National Roads at Calapan South Road Mansalay and Bulalacao | Oriental Mindoro | 2014-11-27 | 1st & Final | IV | LF | 36.615 | 240 | 2014-03-24 | 2014-11-18 | 0.08% | C | 0.468 | 0.133 | 0.3 | - | - | - | 90.1% | 90.1% Very Satisfactory
SJ Bonifacio Builders | 32226 | L | D | SB | GE1 | Prev. Maint. along Jct. Dumalinao-Margosatubig Nat'l Sec. Rd., ZDS (Asphalt Overlay, 50mm) K1719+000-K1719+794 Realigned to K1714+823-K1715+305, Lumbog, Vicencio Sagun | Zamboanga del Sur | 2013-08-16 | Final | IX | LF | 4.679 | 44 | 2013-02-11 | 2013-03-26 | 0 | C | 0.313 | 0.2 | 0.3 | - | - | - | 81.3 | 82.62% Satisfactory
SJ Bonifacio Builders | 32226 | L | D | SB | GE1 | Prev. Maint. along Jct. Dumalinao-Margosatubig Nat'l. Secondary Rd., ZDS (Asphalt Overlay, 50mm) K1714+000-K1719+794 Realigned to K1714+823-K1715+305, Lumbog-Margosatubig | Zamboanga del Sur | 2013-03-19 | 1st | IX | LF | 4.679 | 44 | 2013-02-11 | 2013-03-26 | 40 | O | 0.375 | 0.2 | 0.15 | 0.03 | 0.03 | 0.05 | 83.5 | -
SJ Bonifacio Builders | 32226 | L | D | SB | GE1 | Prev. Maint. along Pagadian City-Zamboanga City Nat'l Arterial Rd. (Reblocking w/ overlay, 0.50mm) K1677+840-K1678+081 | Dumalinao, Zamboanga del Sur | 2013-03-19 | Final | IX | LF | 2.859 | 58 | 2012-02-01 | 2012-03-29 | - | C | 0.471 | 0.2 | 0 | - | - | - | 67.1 | 64.88% Poor
SJ Bonifacio Builders | 32226 | L | D | SB | GE1 | Prev. Maint. along Pagadian City-Zamboanga City Nat'l Arterial Rd. (Reblocking w/ Overlay, 0.500mm) K1677+840-K1678+081 | Dumalinao, Zamboanga del Norte | 2012-08-16 | 1st | IX | LF | 2.859 | 58 | 2012-02-01 | 2012-03-29 | - | O | 0.336 | 0.2 | 0 | 0.03 | 0.035 | 0.033 | 63.4 | -
SJ BONIFACIO BUILDERS | 32226 | L | B | MA | GE | Replacement of Permanent Weak Bridge, Gatas Bridge 1, (B00499MN), Pagadian City-Zamboanga City Road, Pagadian City | Pagadian City | 2015-08-29 | 1st | Zamboanga del Sur 1st | LF | 24.254 | 254 | 2015-05-28 | 2016-02-05 | (+)10.70 | O | 0.3636 | 0.2576 | 0.15 | 0.03 | 0.05 | 0.05 | 90.12% | -
SJ BONIFACIO BUILDERS | 32226 | L | B | MA | GE | Replacement of Permanent Weak Bridge, Gatas Bridge 1 along Pagadian City-Zamboanga City Road, Pagadian City, Zamboanga del Sur | Pagadian City, Zamboanga del Sur | 2015-11-13 | 2nd | Zamboanga Del Sur 1st DEO | LF | 24.2535 | 224 | 2015-05-28 | 2016-01-06 | 0.17% | OG | 0.332 | 0.3 | 0.15 | 0.02 | 0.047 | 0.05 | 89.9% | 89.9% Very Satisfactory
Slver Dragon Construction & Lumber & Glass Supply | 30835 | L | A | MA | GE1 | Rd. Upgrading (Gravel to Paved) (Int. Sect.), Bago-Mambucal Nat'l. Secondary Rd., K0058+688-K0059+616 | Bago City, Negros Occidental | 2013-03-14 | 1st | VI | LF | 19.585 | 112 | 2013-01-24 | 2013-05-15 | 58.02 | O | 0.289 | 0.3 | 0.15 | 0.015 | 0.045 | 0.05 | 84.9 | -
SMT Construction | 36331 | L | D | SB | GE | Construction of Multi-Purpose Building @ Matusalem | Matusalem, Roxas, Isabela | 2014-10-25 | 1st & Final | II | LF | 2.8765 | 90 | 2014-09-01 | 2014-11-29 | 50% | C | 0.443 | 0.133 | 0.3 | - | - | - | 87.6% | 87.6% Satisfactory
SMT Construction | 36331 | L | D | SB | GB | Construction of Multi-Purpose Building at San Felipe | Ilagan City, Isabela | 2014-08-08 | 1st | II | LF | 2.97 | 79 | 2014-05-29 | 2014-08-15 | 0.03 | O | 0.293 | 0.276 | 0.15 | 0.03 | 0.047 | 0.05 | 84.6
SMT CONSTRUCTION | 36331 | L | D | SB | GB | Construction of Multi-Purpose Building, San Felipe | Iligan City, Isabela | 2015-06-04 | Final | Isabela 1st DEO | LF | 2.97 | 79 | 2014-05-29 | 2014-08-15 | 0% | C | 0.426 | 0.2 | 0.3 | - | - | - | 92.6% | *87% Satisfactory
So Construction | 17714 | L | B | MA | GE1 | Repair/Rehab./Impv't. of Nat'l Rd., Baler-Cemento Rd., K0231+500-K0238+000 w/ exceptions | Dinalupihan, Bataan | 2013-08-10 | 1st | III | LF | 10 | 152 | 2013-03-27 | 2013-08-25 | 10 | O | 0.354 | 0.24 | 0.15 | 0.03 | 0.05 | 0.033 | 85.7
Socor Construction Corporation | 8020 | L | AAA | LB | GE1 | Rehab. of A. Cortes Ave. | Mandaue City, Cebu | 2013-03-16 | Final | VII | LF | 22.001 | 180 | 2012-07-08 | 2013-01-04 | 7.2 | C | 0.465 | 0.2 | 0.3 | - | - | - | 96.5 | 90.44% V. Satisfactory
Socor Construction Corporation | 8020 | L | AAA | LB | GE | Preventive Maintenance Based on Pavement Management System/Highway Development and Management-4 (HDM-4) National Secondary Road, Governor Cuenco Ave.: a.)K0005+(-768) - K0005+000 and b.)K0005+000 - K0005+392 | Cebu City | 2014-10-20 | 1st & Final | VII | LF | 28.9927 | 140 | 2014-02-14 | 2014-07-03 | 0.71% | C | 0.44 | 0.138 | 0.3 | - | - | - | 87.8% | 87.8% Satisfactory
Socor Construction Corporation | 8020 | L | AAA | LB | GE | Preventive Maintenance of Catarman - Laoang Road KO746+535 - KO747+100, KO756+572 - KO756+1002; KO759+000 - Ko759+539; KO759+728 - KO764+520 | Catarman, Northern Samar | 2014-08-13 | Final | VIII | LF | 38.7038 | 410 | 2013-02-05 | 2014-03-21 | 0 | C | 0.424 | 0.2 | 0.3 |  |  |  | 92.4 | 82.14% Satisfactory
Socor Construction Corporation | 8020 | L | AAA | LB | GE1 | Prev. Maint. of Catarman-Laoang Rd., K0746+535-K0747+100, K0756+572- K0756+1002; K0759+000-K0759+539; K0759+728-K0764+530 | Catarman, Northern Samar | 2013-08-10 | 1st | VIII | LF | 38.704 | 200 | 2013-02-05 | 2013-08-24 | -21.41 | O | 0.33 | 0.3 | 0 | 0.03 | 0.06 | 0.033 | 75.3
Socor Construction Corporation | 8020 | L | AAA | LB | GE1 | Impv't. of Catarman Diversion Rd. K0742+(-360)-K0743+025 & K0743+025-K0743+085 | Catarman, Northern Samar | 2013-08-10 | Final | VIII | LF | 15.123 | 61 | 2013-02-05 | 2013-04-06 | 0 | C | 0.396 | 0.2 | 0.3 | - | - | - | 89.6 | 88.82% Satisfactory
Socor Construction Corpration | 8020 | L | AAA | LB | GE1 | Impv't. of Catarman Diversion Rd. 1, K0742+(-360)-K0743+025 & K0743+025-K0743+085 | Catarman, Northern Samar | 2013-03-20 | 1st | VIII | LF | 15.123 | 61 | 2013-02-05 | 2013-04-06 | 3.53 | O | 0.308 | 0.3 | 0.15 | 0.03 | 0.045 | 0.05 | 88.3 | -
Solfio P. Jacinto Construction | [5 empty] | Package X-C: Construction of lateral "N" (Sta. 6+640-Sta. 9+600) including related structures and supply, delivery and installation of steel gates | Guimba, Nueva Ecija | 2015-02-07 | 1st | NIA | L | 32.396 | 180 | 2014-07-29 | 2015-01-24 | 9.05 | O | 0.3153 | 0.2817 | 0.15 | 0.03 | 0.014 | 0.05 | 84.1 | -
Solid M Construction | 33991 |  |  | MA |  | Calbiga Irrigation Project | Calbiga, Samar Region 8 | 2014-11-22 | 1st & Final | NIA | L | 26.963 | 240 | 2013-05-01 | 2013-12-03 | 0 | C | 0.4539 | 0.2 | 0.3 | - | - | - | 95.39 | *95.39% V. Satisfactory
Solid M Construction |  | L |  |  |  | Help for Catubig Agricultural Advancement Project HCAAP-LCB-C1-2012 | Catubig, Northern Samar/Region 8 | 2014-03-15 | Final | NIA | LF | 17.747 | 300 | 2012-07-05 | 2013-05-01 | 0 | C | 0.4805 | 0.0638 | 0.3 | - | - | - | 84.43 | 84.43% Satisfactory
Solid Rock Construction | 8958 | L | A | MB | GE1 | Const. of Don Mariano Marcos Ave. Ext. Proj. under Metro Manila Urban Transport Integration Proj. (MMURTIP) | Quezon City | 2013-08-16 | Final | URPO - PMO | LF | 69.995 | 542 | 2010-05-14 | 2011-11-07 | 0 | C | 0.346 | 0.133 | 0.3 | - | - | - | 77.9 | 87.68% Satisfactory
Solid Rock Construction | 8958 | L | A | MB | GE1 | Const. of Don Mariano Marcos Ave., Ext. Project under Metro-Manila Urban Transport Integration Project (MMURTIP) | Quezon City | 2011-04-02 | 1st | URPO | LF | 65.898 | 285 | 2010-05-14 | 2011-02-22 | -0.49 | O | 0.357 | 0.3 | 0.145 | 0.03 | 0.06 | 0.05 | 94.2 | -
Solid Rock Construction | 8958 | L | A | MB | GE1 | Conc. of Congressional Ave. Ext. (Phase II) |  | 2009-09-14 | 1st | NCR |  | 28.754 | 210 |  |  |  | O | 0.341 | 0.244 | 0.15 | 0.023 | 0.05 | 0.05 | 85.8 | -
Solid Rock Corporation | 8958 | L | A | MB | GE1 | Impvt./Widening of C.P. Garcia Ave., (Sta.13+93 -Sta.14+685) | Quezon City | 2013-03-19 | Final | NCR | LF | 16.653 | 303 | 2012-03-23 | 2013-01-19 | 0 | C | 0.433 | 0.133 | 0.3 | - | - | - | 86.6 | 82.64% Satisfactory
SOPHIA CONSTRUCTION AND SUPPLY | 33484 | L | C | SB | GB | Construction of MPB (Covered Court) at Lambayong NHS | Lambayong, Sultan Kudarat | 2015-08-31 | 1st | Sultan Kudarat 1st | LF | 4.85 | 155 | 2015-06-15 | 2015-11-16 | (-) 9.60% | O | 0.382 | 0.3 | 0.054 | 0.03 | 0.052 | 0.017 | 83.5% | -
SOPHIA CONSTRUCTION AND SUPPLY | 33484 | L | B | SB | GB | Construction of Multi-Purpose Building (Covered Court) | Lambayong National High School, Lambayong, Sultan Kudarat | 2015-11-11 | 1st | Sultan Kudarat First DEO | LF | 4.8508 | 165 | 2015-06-15 | 2015-11-26 | (+) 0.68% | OG | 0.345 | 0.24 | 0.15 | 0.03 | 0.07 | 0.05 | 88.5% | 88.5% Satisfactory
SOY ENG CONSTRUCTION | 15533 | L | B | SB | GE | Asset Preservation of National Roads, Rehab./Reconst./Upgrading of Damaged Paved National Roads including Drainage Based on Pavement Management System/Highway Dev't and Management-4 (HDM-4)(Intermittent Sections) Piñan - Mutia Road, K1821+259 to K1821+971, Zamboanga del Norte | Zamboanga del Norte | 2015-06-05 | 1st | Zamboanga del Norte 3rd DEO | LF | 8.95 | 115 | 2015-02-24 | 2015-06-18 | 0.31% | O | 0.36 | 0.233 | 0.15 | 0.03 | 0.05 | 0.033 | 85.6% | -
SOY ENG CONSTRUCTION | 15533 | L | B | SB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads including Drainage Based on Project Management System/Highway Development and Management (HDM-4)(Intermittent Sections) Piñan-Mutia Road, Rehab/Recon. K1821+259-K1821+971, Zamboanga Del Norte | Piñan-Mutia Road, Rehab/Recon. K1821+259-K1821+971, Zamboanga Del Norte | 2015-08-28 | Final | Zamboanga del Norte 3rd | LF | 8.95 | 115 | 2015-02-24 | 2015-06-18 | - | C | 0.411 | 0.2 | 0.3 | - | - | - | 91.1% | *87.8% Satisfactory
Soy Eng Construction / L.C. Construction (JV) | JV-12-233 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Conc.) Int. Sect. along Piñan-Mutia Rd., K1824+(-458)-K1825+232 | Zamboanga del Norte | 2013-03-22 | 1st | IX | LF | 9.498 | 61 | 2013-01-25 | 2013-03-26 | 0.25 | O | 0.333 | 0.287 | 0.15 | 0.03 | 0.04 | 0.033 | 87.3 | -
Soy Eng Construction / L.C. Construction(JV) | JV-12-233 | L | B | MA | GE1 | Rd. Upgrading (Gravel to Conc.) Int. Sect. along Piñan-Mutia Rd., K1824+(-458)-K1825+232 | Zamboanga del Norte | 2013-08-20 | 2nd | IX | LF | 9.498 | 121 | 2013-01-25 | 2013-05-25 | -2.44 | O | 0.28 | 0.287 | 0 | 0.03 | 0.042 | 0.033 | 67.2
SPECO BUILDERS INC. (Formerly: VRF Construction) | 15301 | L | AA | MB | GE | Off-Carriageway Improvement of Sta. Rosa - Tarlac Road | KO118+(-273) - KO118+(-047); KO119+278 - KO119+663; KO119+923 - KO120+000; KO121+000 - KO122+000; KO123+221 - KO123+720; KO124+000 - KO127+296 | 2015-09-02 | 1st & Final | Nueva Ecija First DEO | LF | 42.339 | 180 | 2015-03-05 | 2015-08-31 | 7.78% | C | 0.487 | 0.133 | 0.3 | - | - | - | 92% | *92% Very Satisfactory
SPECO Builders, Inc. | 15301 | L | AAA | MB | GE | Rehabilitation/Reconstruction of Damaged Paved National Roads including Drainage of Nueva Ecija - Pangasinan Road | KO138+(-036) to KO138+876; KO146+000 to KO146+404; KO150+000 to KO151+000; KO168+695 to KO168+917 | 2014-11-27 | 1st & Final | III | LF | 16.4354 | 90 | 2014-02-24 | 2014-05-24 | 0% | C | 0.451 | 0.133 | 0.3 | - | - | - | 88.4% | 88.4% Satisfactory
SPECO Builders, Inc. | 15301 | L | AA | MA | GE | Construction of Drainage Canal along Bongabon - Rizal - Aurora Road (Rizal Section) KO 153+464 to KO 153+1372 | Rizal, Nueva Ecija | 2014-09-25 | 1st & Final | Special 3 | LF | 18.1414 | 150 | 2014-02-04 | 2014-07-03 | 0 | C | 0.415 | 0.133 | 0.3 |  |  |  | 84.8 | 84.80% Satisfactory
SPECO Builders, Inc. | 15301 | L | AA | MB | GE | Preventive Maintenance of Nueva Ecija - Pangasinan Road |  | 2014-09-24 | 1st | Special 3 | LF | 30.7555 | 90 | 2014-07-14 | 2014-10-11 | 8.89 | O | 0.387 | 0.2 | 0.15 | 0.03 | 0.035 | 0.033 | 83.5
SPECO Builders, Inc. (Formerly: VRF Construction) | 15301 | L | AA | MB | GE | Road Upgrading (Gravel to Paved) along Nueva Ecija - Aurora Road | Aurora | 2014-08-08 | 1st | III | LF | 103.3571 | 360 | 2014-01-24 | 2015-01-18 | 1.54 | O | 0.38 | 0.24 | 0.15 | 0.012 | 0.052 | 0.05 | 88.4
SPECO BUILDERS, INC. (Formerly: VRF Construction) | 15301 | L | AA | MA | GE | Improvement/Rehabilitation of the Talavera-Zaragoza Earth Dike, Nueva Ecija, Sta.104+652.50-Sta.104+831.90 | Nueva Ecija, Sta.104+652.50-Sta.104+831.90 | 2015-11-17 | Final | Nueva Ecija Second DEO | LF | 27.924 | 120 | 2015-03-10 | 2015-07-07 | 15.00% | C | 0.5 | 0.133 | 0.3 | - | - | - | 93.3% | 93.3% Very Satisfactory
SPECO BUILDERS, INC. (SBI) | 15301 | L | AA | MA | GE | Removal of Landslide and Mudflows | Carranglan, Nueva Ecija | 2015-06-10 | Final | Nueva Ecija 1st DEO | LF | 6.696 | 104 | 2014-06-23 | 2014-10-04 | 0% | C | 0.496 | 0.133 | 0.3 | - | - | - | 92.9% | *92.9% Very Satisfactory
SPJ Construction | 12584 | L |  | SB |  | Improvement of Lateral G-3, LTRIS | Talavera, Nueva Ecija/Region III | 2015-05-23 | 1st & Final | NIA | L | 6.127 | 210 | 2014-07-18 | 2015-02-12 | 0 | C | 0.3974 | 0.2 | 0.3 | - | - | - | - | *89.74% V. Satisfactory
SPJ Construction | 12584 | L |  | SB |  | Canal Structure and Steel Gates | Lupao, Nueva Ecija | 2015-05-23 | 1st | NIA | L | 1.817 | 120 | 2014-12-30 | 2015-04-28 | -33.28 | O | 0.3748 | 0.2 | 0 | 0.03 | 0.07 | 0.05 | 72.48 | -
Spring Star Construction & Supply | 20240 |  |  |  |  | Const. of Calzada Tipas Bridge |  | 2010-02-24 |  | NCR |  | 14.399 | 308 |  |  |  | O | 0.313 | 0.208 | 0.15 | 0.022 | 0.037 | 0.033 | 76.3 | -
Spring Star Construction & Supply | 20240 | L | B | MA | GE | Upgrading of Box Culvert along villanueva Creek Tributaries, UPS 5, Camella, Barangay San Isidro | Parañaque City, M.M. | 2014-11-18 | 1st & Final | NCR | LF | 6.0588 | 240 | 2014-03-14 | 2014-11-08 | 1.9% | C | 0.435 | 0.133 | 0.3 | - | - | - | 86.8% | 86.8% Satisfactory
SPRING STAR CONSTRUCTION AND SUPPLY | 20240 | L | B | MA | GE | Construction of Additional Classroom in Baclaran Elementary School Central, Parañaque City, Metro Manila | Parañaque City | 2015-06-11 | 1st | Metro Manila 2nd DEO | LF | 6.532 | 180 | 2015-03-02 | 2015-08-28 | (+) 7.05 | O | 0.339 | 0.24 | 0.15 | 0.022 | 0.054 | 0.05 | 85.5% | -
SPRING STAR CONSTRUCTION AND SUPPLY | 20240 | L | B | MA | GE | Const/Repair/Rehab/Improvement of Various Infrastructure Including Local Projects - Road and Drainage Improvement at F. Calderon Street to Tejeron Street via Suter Street and Vicinity, Sta. Ana, Manila | Sta. Ana, Manila | 2015-09-02 | 1st | SM DEO | LF | 12.492 | 150 | 2015-05-29 | 2015-10-25 | 1.13% | O | 0.346 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 87.1% | -
SPRING STAR CONSTRUCTION AND SUPPLY | 20240 | L | B | MA | GE | Indv. Proj. (Off-Carriageway Imprv't) Paving of Shoulders/Drainage Slope Protection Structures Along Nabua-Balatan Road, Sta. 491+000 to Sta. 492+000, Balatan, Camarines Sur | Balatan, Camarines Sur | 2015-08-27 | Final | Camarines Sur Fourth DEO | LF | 26.771 | 145 | 2015-03-23 | 2015-08-14 | - | C | 0.487 | 0.133 | 0.3 | - | - | - | 92% | *92% Very Satisfactory
Square Cube Const. (Formerly: Square Cube Trading Division & Const Division-Mandaue Branch) | 25120 | L | A | MA | GE1 | Jct. Osmeña-Pilar Road (Osmeña-Maasin-Mabini Section) | Siargo, Surigao del Norte | 2011-08-12 | 1st | XIII | LF | 22.824 | 270 | 2011-01-11 | 2011-10-08 | -2.03 | O | 0.361 | 0.225 | 0.13 | 0.023 | 0.043 | 0.05 | 83.2 | -
Square Cube Const. (Formerly: Square Cube Trading Division & Const. Division-Mandaue Branch) | 25120 | L | A | MA | GE2 | Ubay Flood Control | Ubay, Bohol | 2013-03-13 | 1st | VII | LF | 3.667 | 157 | 2012-12-12 | 2013-05-17 | 1.43 | O | 0.347 | 0.24 | 0.15 | 0.03 | 0.035 | 0.033 | 83.5 | -
Square Cube Construction | 25120 | L | A | MA |  | New Bohol (Panglao) Airport Development Project | Panglao, Bohol | 2014-05-22 | 1st | DOTC | LF | 49.358 | 240 | 2013-11-21 | 2014-07-18 | 1.37 | O | 0.3766 | 0.3 | 0.15 | 0.03 | 0.0323 | 0.05 | 93.89 | -
Square Cube Construction | 25120 | L | A | MA | GE1 | Const./Completion of On-going Bridges (inc. approaches) at Lower Pakigne Bridge along Natalio Bacalso Ave., Phase 8 | Minglanilla, Cebu | 2012-08-18 | 1st | VII | LF | 37.44 | 270 | 2012-01-31 | 2012-10-26 | 3.71 | O | 0.327 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 85.2 | -
Square Cube Construction | 25120 | L | A |  | GB | Construction of Two (2) Storey Six (6) Classroom School Building at Maslog National High School | Maslog, Danao City, Cebu | 2014-08-08 | Final | VII | LF | 6.4575 | 159 | 2013-06-10 | 2013-11-15 | 0 | C | 0.465 | 0.158 | 0.3 |  |  |  | 92.3 | 87.82% Satisfactory
Square Cube Construction (Formerly: Square Cube Trading Division & Construction Division-Mandaue Branch) | 25120 | L | A | MA | GE1 | Const./Completion of On-going Bridges (inc. approaches) at Lower Pakigne Bridge along Natalio Bacalso Ave. Phase 8 | Minglanilla, Cebu | 2013-08-05 | Final | VII | LF | 34.444 | 300 | 2012-01-31 | 2012-11-26 | 0.33 | C | 0.398 | 0.187 | 0.3 | - | - | - | 88.5 | 86.52% Satisfactory
Square Cube Construction (Formerly: Square Cube Trading Division & Construction Division-Mandaue Branch) | 25120 | L | A | MA | GE | Asphalt Overlay of E. Rodriguez Sr. Avenue, K0009+(-526) (J. Jimenez St.) to K0010+609 (Aurora Blvd.) | Quezon City | 2014-08-15 | 1st & Final | NCR | LF | 14.4225 | 40 | 2014-01-30 | 2014-03-10 | 0 | C | 0.452 | 0.133 | 0.3 |  |  |  | 88.5 | 88.50% Satisfactory
Square Cube Construction (Formerly: Square Cube Trading Division & Construction Division-Mandaue Branch) | 25120 | L | A | MA | GE2 | Ubay Flood Control | Ubay, Bohol | 2013-08-19 | Final | VII | LF | 3.667 | 157 | 2012-12-12 | 2013-05-18 | 0 | C | 0.428 | 0.133 | 0.3 | - | - | - | 86.1 | 84.54% Satisfactory
Square Cube Construction (Formerly: Square Cube Trading Division & Construction Division-Mandaue Branch) | 25120 | L | A | SB | GB1 | Const. of 2 Storey 6CL SB at Maslog NHS | Maslog, Danao City, Cebu | 2013-08-14 | 1st | VII | LF | 6.457 | 159 | 2013-06-10 | 2013-11-15 | 0.93 | O | 0.359 | 0.24 | 0.15 | 0.03 | 0.047 | 0.033 | 85.9
Square Cube Construction (Formerly: Square Cube Trading Division & Construction Division-Mandaue Branch) | 25120 | L | A | MA | GE | Construction of Flood Control at Barili Bridge | Barili, Cebu | 2014-08-06 | Final | VII | LF | 16.2958 | 150 | 2013-02-04 | 2013-09-24 | 0.67 | C | 0.425 | 0.133 | 0.3 |  |  |  | 85.8 | 86.94% Satisfactory
Square Cube Construction (Formerly: Square Cube Trading Division & Construction Division-Mandaue Branch) | 25120 | L | A | MA | GE2 | Const. of Flood Control at Barili Bridge | Barili, Cebu | 2013-08-07 | 1st | VII | LF | 16.296 | 203 | 2013-02-04 | 2013-08-25 | 6.33 | O | 0.373 | 0.241 | 0.15 | 0.03 | 0.05 | 0.033 | 87.7
Square Cube Construction (Formerly: Square Cube Trading Division & Construction Division-Mandaue Branch) | 25120 | L | A | MA | GE1 | Strengthening of Agas-Agas Bridge along Daang Maharlika | Sogod, Southern Leyte | 2013-08-06 | Final | VIII | LF | 17.317 | 156 | 2013-01-18 | 2013-06-22 | 0 | C | 0.469 | 0.133 | 0.3 | - | - | - | 90.2 | 87.08% Satisfactory
Square Cube Construction (Formerly: Square Cube Trading Division & Construction Division-Mandaue Branch) | 25120 | L | A | MA | GE2 | Const. of Maasin Flood Control along Tomas Opus Street (Nat'l Rd.) | Maasin City, Southern Leyte | 2013-08-07 | 2nd | VIII | LF | 39.502 | 270 | 2013-01-18 | 2013-10-14 | 12.43 | O | 0.371 | 0.24 | 0.15 | 0.006 | 0.047 | 0.05 | 86.4
Square Cube Construction (Formerly: Square Cube Trading Division & Construction Division-Mandaue Branch) | 25120 | L | A | MA | GE1 | Const. of Baybay Diversion Road, Sta. 0+000-Sta. 5+346.67, w/ exceptions | Baybay City, Leyte | 2013-08-05 | 1st | VIII | LF | 90.663 | 310 | 2013-02-08 | 2013-12-14 | 9.32 | O | 0.376 | 0.198 | 0.15 | 0.018 | 0.051 | 0.05 | 84.3
Square Cube Construction (Formerly: Square Cube Trading Division & Construction Division-Mandaue Branch) | 25120 | L | A | MA | GE2 | Repair/Rehab. Of Slope/Seawall Protection, Pob. Motiong | Motiong, Samar | 2013-08-16 | Final | VIII | LF | 15.146 | 90 | 2012-11-22 | 2013-02-19 | 4.45 | C | 0.391 | 0.2 | 0.3 | - | - | - | 89.1 | 85.26% Satisfactory
Square Cube Construction (Formerly: Square Cube Trading & Construction Division-Mandaue Branch) | 25120 | L | B | SB | GB1 | Const. of One (1) Unit 1 CL Standard/Modified Sch. Bldg. at Kagay E/S |  | 2009-09-05 | 1st | VII |  | 0.626 | 110 |  |  |  | O | 0.366 | 0.24 | 0.15 | 0.03 | 0.035 | 0.05 | 87.1 | -
Square Cube Construction (Formerly: Square Cube Trading & Construction Division-Mandaue Branch) | 25120 | L | B | SB | GB1 | Const. of One (1) Unit 2-CL Standard / Modified School Building at Kagay E/S |  | 2009-09-05 | 1st | VII |  | 0.626 | 110 |  |  |  | O | 0.348 | 0.24 | 0.15 | 0.03 | 0.035 | 0.05 | 85.3 | -
Square Cube Construction (Formerly: Square Cube Trading & Construction Division-Mandaue Branch) | 25120 | L | B | SB | GB1 | Const. of One (1) Unit-2CL Standard / Modified School Building at Nangka E/S |  | 2009-09-04 | 1st | VII |  | 1.254 | 109 |  |  |  | O | 0.303 | 0.214 | 0.15 | 0.03 | 0.023 | 0.05 | 77 | -
Square Cube Construction (Formerly: Square Cube Trading & Construction Division-Mandaue Branch) | 25120 | L | A | MA | GE | Construction of Baybay Diversion Road, Sta.0+000 - Sta.5+346.67 with exception | Baybay, Leyte | 2014-08-06 | 1st & Final | VIII | LF | 82.5333 | 370 | 2013-02-08 | 2013-10-13 | 0 | C | 0.401 | 0.133 | 0.3 |  |  |  | 83.4 | 83.40% Satisfactory
Square Cube Construction (Formerly: Square Cube Trading & Construction Division-Mandaue Branch) | 25120 |  |  |  |  | Const. of Maasin Seawall |  | 2010-06-07 |  | VIII |  | 19.102 | 300 |  |  |  | O | 0.343 | 0.3 | 0.15 | 0.03 | 0.037 | 0.05 | 91 | -
Square Cube Construction (Formerly: Square Cube Trading & Construction Division-Mandaue Branch) | 25120 |  |  |  |  | Road Upgrading, Junction Himay-angan-Silago-Abuyog Road |  | 2010-09-04 |  | VIII |  | 36.7 | 300 |  |  |  | O | 0.34 | 0.236 | 0.148 | 0.03 | 0.047 | 0.033 | 83.4 | -
Square Cube Construction (Formerly: Square Cube Trading & Construction Division-Mandaue Branch) | 25120 |  |  |  |  | Road Upgrading (Gravel to Paved) of Kananga-Tungonan Hot Spring Road |  | 2010-08-31 |  | VIII |  | 18.225 | 254 |  |  |  | O | 0.366 | 0.239 | 0.15 | 0.03 | 0.042 | 0.033 | 86 | -
Square Cube Construction (Formerly: Square Cube Trading & Construction Division-Mandaue Branch) | 25120 | L | B | MA | GE1 | Road Upgrading (Gravel to Paved) Kananga-Tungonan Hot Spring Road, Brgy. Rizal Road Section, |  | 2009-05-30 | 1st | VIII |  | 12.755 | 180 |  |  |  | O | 0.241 | 0.3 | 0.15 | 0.03 | 0.042 | 0.05 | 81.3 | -
Square Cube Construction (Formerly: Square Cube Trading & Construction Division-Mandaue Branch) | 25120 | L | B | MA | GE1 | Construction/Improvement of San Ricardo-Bil-atan Road |  | 2009-05-26 | 1st | VIII |  | 19.087 | 200 |  |  |  | O | 0.335 | 0.251 | 0.15 | 0.03 | 0.047 | 0.05 | 86.3 | -
Square Cube Construction (Formerly: Square Cube Trading & Construction Division-Mandaue Branch) | 25120 | L | B | MA | GE1 | Road Upgrading (Gravel to Paved) Ormoc-Lake Imelda Road |  | 2009-05-30 | 1st | VIII |  | 18.23 | 225 |  |  |  | O | 0.297 | 0.257 | 0.15 | 0.03 | 0.037 | 0.05 | 82.1 | -
Square Cube Construction (Formerly: Square Cube Trading & Construction Division-Mandaue Branch) | 25120 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved National Road, Ormoc-Baybay, Southern Leyte Boundary Road |  | 2009-09-06 | 1st | VIII |  | 15.501 | 249 |  |  |  | O | 0.357 | 0.3 | 0.15 | 0.015 | 0.035 | 0.05 | 90.7 | -
Square Cube Construction (Formerly: Square Cube Trading & Construction Division-Mandaue Branch) | 25120 |  |  |  |  | Road Upgrading (Gravel to Paved ) at Davao-Cotabato Old Road National Roads Davao-Cotabato at Libby Sect. |  | 2010-06-16 |  | XI |  | 19.3 | 113 |  |  |  | O | 0.363 | 0.24 | 0.15 | 0.03 | 0.047 | 0.05 | 88 | -
Square Cube Construction (Formerly: Square Cube Trading & Construction Division-Mandaue Branch) | 25120 | L | A | MA | GE | Construction/Rehabilitation of Flood Mitigation Facilities along Principal Rivers, Hijo River | Tagum City, Davao del Norte | 2014-10-24 | 1st | XI | LF | 11.2673 | 99 | 2014-08-06 | 2014-11-12 | 94% | O | 0.232 | 0.261 | 0.15 | 0.02 | 0.04 | 0.033 | 73.6% | 73.6% Poor
Square Cube Construction (Formerly: Square Cube Trading & Construction Division-Mandaue Branch) | 25120 | L | A | MA | GE | GAA - San Agustin - New Balanban Road, leading to Tagum Botanical Park and Bird Park, Tagum City, Davao del Norte (Road Upgrading (Gravel to Concrete) of San Agustin-ew Balanban Road leading to Tagum Botanical Park and Bird Park) | Tagum City, Davao del Norte | 2014-10-24 | 1st | XI | LF | 46.2815 | 209 | 2014-03-13 | 2014-10-07 | -10.44% | O | 0.208 | 0.208 | 0.046 | 0.024 | 0.03 | 0.017 | 53.3% | 53.3% Poor
Square Cube Construction (Formerly: Square Cube Trading & Construction Division-Mandaue Branch) | 25120 |  |  |  |  | Dapa-Del Carmen Road |  | 2010-02-26 |  | XIII |  | 16.57 | 266 |  |  |  | O | 0.383 | 0.24 | 0.114 | 0.03 | 0.047 | 0.033 | 84.7 | -
Square Cube Construction (Formerly: Square Cube Trading & Construction Division-Mandaue Branch) | 25120 |  |  |  |  | Jct. Cancohoy-Del Carmen Rd. |  | 2010-02-26 |  | XIII |  | 16.735 | 266 |  |  |  | O | 0.361 | 0.24 | 0.109 | 0.03 | 0.047 | 0.033 | 82 | -
Square Cube Construction (Formerly: Square Cube Trading Division & Const. Division-Mandaue Branch) | 25120 | L | A | MA | GE1 | Preventive Maint. along Bdry. So. Leyte-Maasin-Macrohon-Sogod-Daang Maharlika, Km.1139+021-Km.1139+570 & Preventive Maint. along Tomas Oppus St., Km.1135+081-Km.1135+071.9 | Southern Leyte | 2011-08-17 | 1st | VIII | LF | 6.2 | 150 | 2011-04-04 | 2011-08-31 | 12.84 | O | 0.37 | 0.3 | 0.15 | 0.03 | 0.03 | 0.033 | 91.3 | -
SQUARE CUBE CONSTRUCTION (Formerly: Square Cube Trading Division & Construction Division - Mandaue Branch) | 25120 | L | A | MA | GE | Construction of Carcar Road (Improvement of Drainage System), Phase V | Carcar City, Cebu | 2014-10-24 | 1st | VII | LF | 41.4085 | 237 | 2014-06-06 | 2015-01-28 | 4.8% | O | 0.26 | 0.3 | 0.15 | 0.022 | 0.042 | 0.05 | 82.4% | 82.4% Satisfactory
SQUARE CUBE CONSTRUCTION (Formerly: Square Cube Trading Division & Construction Division - Mandaue Branch) | 25120 | L | A | MA | GE | Rehab./Reconst./Replacement/Retrofitting of Existing Permanent Bridge at Dohinob Diut Bridge along Dipolog - Sindangan - Liloy Road, Zamboanga del Norte | Zamboanga del Norte | 2015-06-04 | Final | Zamboanga del Norte 1st DEO | LF | 14.994 | 148 | 2014-06-11 | 2014-11-05 | 0% | C | 0.48 | 0.133 | 0.3 | - | - | - | 91.3% | *91.3% Very Satisfactory
Square Cube Construction (Formerly: Square Cube Trading Division & Construction Division Mandaue Branch) | 25120 | L | A | MA | GE1 | Const./Replacement of Olivo Bridge | Tabuelan, Cebu | 2012-03-24 | 1st | VII | LF | 18.774 | 200 | 2011-11-29 | 2012-06-15 | 31.5 | O | 0.359 | 0.24 | 0.15 | 0.03 | 0.042 | 0.033 | 85.4 | -
SQUARE CUBE CONSTRUCTION (Formerly: Square Cube Trading Division & Construction Division) - Mandaue Branch | 25120 | L | A | MA | GE | Const. of Maasin Flood Control along Tomas Oppus Street (National Road) | Maasin City, Southern Leyte | 2014-08-05 | Final | VIII | LF | 39.5022 | 300 | 2013-01-02 | 2013-11-13 | 0 | C | 0.429 | 0.184 | 0.3 |  |  |  | 91.3 | 86.02% Satisfactory
SQUARE CUBE CONSTRUCTION (Formerly: Square Cube Trading Division & Construction Division-Mandaue Branch) | 25120 | L | A | MA | GE | Completion of Flood Protection Works along Daang Maharlika | Mationg, Samar | 2014-10-25 | 1st | VIII | LF | 21.4676 | 150 | 2014-06-09 | 2014-11-05 | 1.82% | O | 0.371 | 0.24 | 0.15 | 0.023 | 0.029 | 0.05 | 86.3% | 86.3% Satisfactory
Square Cube Construction (Formerly: Square Cube Trading Division & Construction Division-Mandaue Branch) | 25120 | L | A | MA | GE1 | Strengthening of Agas-Agas Bridge along Daang Maharlika | Sogod, Southern Leyte | 2013-03-16 | 1st | VIII | LF | 17.086 | 126 | 2013-01-18 | 2013-05-23 | 13.97 | O | 0.28 | 0.3 | 0.15 | 0.03 | 0.04 | 0.05 | 85 | -
Square Cube Construction (Formerly: Square Cube Trading Division & Construction Division-Mandaue Branch) | 25120 | L | A | MA | GE2 | Repair/Rehab. of Slope/Seawall Protection, Pob. Motiong | Motiong, Samar | 2013-03-18 | 1st | VIII | LF | 15.631 | 210 | 2012-11-22 | 2013-06-19 | 12.51 | O | 0.367 | 0.225 | 0.15 | 0.023 | 0.029 | 0.033 | 82.7 | -
Square Cube Construction (Formerly: Square Cube Trading Division & Construction Division-Mandaue Branch) | 25120 | L | A | MA | GE2 | Const. of Maasin Flood Control along Tomas Oppus Street (Nat'l. Rd.) | Maasin City, Southern Leyte | 2013-03-16 | 1st | VIII | LF | 37.525 | 193 | 2013-01-18 | 2013-07-29 | 8.39 | O | 0.32 | 0.225 | 0.15 | 0.03 | 0.05 | 0.05 | 82.5 | -
Square Cube Construction (Formerly: Square Cube Trading Division & Construction Division-Mandaue Branch) | 25120 | L | A | MA | GE1 | Rehab./Widening of Existing Pvmt. along Pagadian City-Zamboanga City Rd. w/ exceptions K1675+(-031) | Dumalinao, Zamboanga del Sur | 2013-08-16 | 1st | IX | LF | 37.801 | 255 | 2013-02-11 | 2013-10-23 | 3 | O | 0.325 | 0.288 | 0.15 | 0.018 | 0.033 | 0.033 | 84.7 | -
Square Cube Construction (Formerly: Squared Cube Trading Division & Construction Division-Mandaue Branch) | 25120 | L | A | MA | GE | Rehab./Widening of Existing Pavement along Pagadian City Road with exceptions K1675+(-031) - K1677+432.27 | Dumalinao, Zamboanga del Sur | 2014-08-13 | Final | IX | LF | 39.4022 | 400 | 2014-02-11 | 2014-03-16 | 0 | C | 0.288 | 0.2 | 0.3 |  |  |  | 78.8 | 85.34% Satisfactory
Square Cube Construction/QM Builders (JV) | JV-13-291 | L | A | MA | GE | Construction of Drainage Systemalong Cebu North Hagnaya Wharf Road | Catmon Section, Catmon, Cebu | 2014-08-08 | 1st | VII | LF | 17.4792 | 210 | 2014-01-31 | 2014-08-28 | 7.88 | O | 0.356 | 0.27 | 0.15 | 0.03 | 0.051 | 0.05 | 90.7
St. Bernardine Construction & Enterprises (Formerly: St. Bernardine Construction) | 18474 | L | B | MA | GE | Proposed Construction/Rehabilitation and Additional Manholes along Taft Ave. (SB) from Quirino Ave. To Remedios St. | Malate, Manila | 2014-11-20 | 1st & Final | NCR | LF | 6.0744 | 120 | 2014-07-26 | 2014-11-22 | 3.33% | C | 0.479 | 0.133 | 0.3 | - | - | - | 91.2% | 91.2% Very Satisfactory
St. Bernardine Construction & Enterprises (Formerly: St. Bernardine Construction) | 18474 | L | B | MA | GE | Construction/Improvement of Drainage System along Tigaon-Goa-San Jose-Lagonoy Road | Poblacion, Tigaon, Camarines Sur | 2014-11-13 | 1st & Final | V | LF | 7.2871 | 106 | 2014-05-06 | 2014-08-19 | 0% | C | 0.485 | 0.133 | 0.3 | - | - | - | 91.8% | 91.8% Very Satisfactory
St. Bernardine Construction & Enterprises (Formerly: St. Bernardine Construction) | 18474 | L | B | MA | GE | Construction/Rehabilitation of Canaman Flood Control, San Vicente-Del Rosario Creek | Canaman, Camarines Sur | 2014-08-08 | 1st | V | LF | 13.2645 | 174 | 2014-02-25 | 2014-08-17 | -15.4 | O | 0.366 | 0.3 | 0 | 0.02 | 0.051 | 0.033 | 77
St. Bernardine Construction & Enterprises (Formerly: St. Bernardine Construction) | 18474 | L | B | MA | GB | Const. of Two (2)-Classroom, One-Storey School Building at Sagrada Elementary School | Sipocot, Camarines Sur | 2014-08-06 | Final | V | LF | 1.1415 | 160 | 2013-05-17 | 2013-10-23 | 1.33 | C | 0.357 | 0.2 | 0.3 |  |  |  | 85.7 | 89.55% Very Satisfactory
St. Bernardine Construction & Enterprises (Formerly: St. Bernardine Construction) | 18474 | L | B | MA | GB1 | Const. of Two (2) Cl One-Storey Sch. Bldg., Sagrada Elem. Sch. | Sipocot, Camarines Sur | 2013-08-03 | 1st | V | LF | 1.141 | 150 | 2013-05-17 | 2013-10-13 | 3.67 | O | 0.344 | 0.3 | 0.15 | 0.03 | 0.055 | 0.033 | 91.2
ST. GERARD CONSTRUCTION/JANN-NORRIS CONSTRUCTION AMD SUPPLIES JOINT VENTURE | 0 | L | A | MA | GE | MFO-1 National Road Network Services: Road Upgrading (Unpaved to Paved) based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standards (HDM-4 Project Analysis) (Interminttent Sections) Bambang-Kasibu-Solano Road, K0282+472 - K028 | Nueva Vizcaya | 2015-11-19 | 1st | REGIONAL | LF | 137.5955 | 359 | 2015-02-28 | 2016-02-21 | (+) 10.33 | OG | 0.366 | 0.24 | 0.15 | 0.03 | 0.04 | 0.05 | 87.6% | 87.6% Satisfactory
St. Gerrard Construction | 31762 | L | A | MA | GE | Rehabilitation of Drainage System M.H. Del Pilar Street, Brgy. Maysilo | Malabon City | 2014-11-21 | 1st | NCR | LF | 12.5165 | 150 | 2014-06-30 | 2014-11-26 | 2.6% | O | 0.351 | 0.258 | 0.15 | 0.03 | 0.03 | 0.05 | 86.9% | 86.9% Satisfactory
ST. GERRARD CONSTRUCTION | 31762 | L | A | MB | GE | Improvement of Meycauayan River, Left Side Phase I (Sta. 2+164.6 to Sta. 2+018.20), Meycauayan, Bulacan | Meycauayan, Bulacan | 2015-06-13 | Final | Bulacan 2nd DEO | LF | 31.747 | 171 | 2014-08-28 | 2015-02-14 | 3.99% | C | 0.494 | 0.2 | 0.3 | - | - | - | 99.4% | *99.4% Outstanding
ST. GERRARD CONSTRUCTION | 31762 | L | A | MB | GE | Widening of Daang Maharlika (MN) K1502+851 - K1504+082 | Davao City | 2015-06-12 | 1st | Davao City | LF | 40.398 | 155 | 2015-03-26 | 2015-08-27 | (+)0.06% | O | 0.336 | 0.226 | 0.15 | 0.03 | 0.042 | 0.05 | 83.4% | -
ST. GERRARD CONSTRUCTION | 31762 | L | A | MB | GE | Construction/Rehabilitation of Drainage System along Deparo-Camarin Road, 1st L.D., Caloocan City | Caloocan City | 2015-06-06 | 1st | Metro Manila 3rd DEO | LF | 17.62 | 150 | 2015-03-17 | 2015-08-13 | (+) 6.06 | O | 0.35 | 0.24 | 0.15 | 0.015 | 0.037 | 0.05 | 84.2% | -
ST. GERRARD CONSTRUCTION | 31762 | L | A | MB | GE | Construction of By-Passes/Diversion Roads Including ROW, Construction/Upgrading of Baybay Diversion Road Including Bridges (Construction/Completion of Pagbanganan Bridge), Baybay City, Leyte | Baybay City, Leyte | 2015-08-29 | 1st | Regional Office No. VIII | LF | 88.84 | 266 | 2015-03-16 | 2015-12-06 | (-)4.485 | O | 0.322 | 0.3 | 0.105 | 0.01 | 0.045 | 0.033 | 81.5% | -
ST. GERRARD CONSTRUCTION | 31762 | L | A | MB | GE | Road Upgrading (Unpaved to Paved) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standards (HDM-4 Project Analysis) (Intermittent Sections) along Ubao - Taang Road, K0415+942 to K0422+122, Aguinaldo, Ifugao | Aguinaldo, Ifugao | 2015-08-28 | 1st | CAR | LF | 171.219 | 299 | 2015-04-15 | 2016-02-07 | -3.88% | O | 0.372 | 0.225 | 0.111 | 0.03 | 0.051 | 0.033 | 82.2% | -
ST. GERRARD CONSTRUCTION | 31762 | L | A | MB | GE | Upgrading/Rehabilitation/Reconstruction of National Roads with Slips, Slope Collapse and Landslide Lucena-Tayabas-Lucban-Sampaloc-Mauban Port Road | K0 139+080 - K0 139+284, K0 139+400 - K0 139+492, K0 139+596 - K0 139+720, K0 140+300 - K0 140+780, Sampaloc, Quezon | 2015-09-04 | 1st | Quezon 1st | LF | 36.41 | 231 | 2015-05-14 | 2015-12-30 | 41.95% | O | 0.375 | 0.224 | 0.15 | 0.03 | 0.029 | 0.05 | 85.8% | -
ST. GERRARD CONSTRUCTION | 31762 | L | A | MB | GE | Rehabilitation/Reconstruction of National Roads with Slips, Slope Collapse and Landslide, Lucena - Tayabas -Lucban -Sampaloc -Mauban Port Road, K0139+080 to K0139+284, K0139+400 to K0139+492, K0139+596 to K0139+720, K0140+300 to K0140+780, Quezon Province | `Quezon Province | 2015-11-20 | Final | QUEZON 1ST DEO | LF | 36.4105 | 231 | 2015-05-14 | 2015-12-30 | 0.2381 | C | 0.389 | 0.199 | 0.3 | - | - | - | 88.8% | 88.8% Satisfactory
ST. GERRARD CONSTRUCTION | 31762 | L | A | MB | GE | Rehabilitation/Major Repair of Permanent Bridges, Gakat Bridge Along Daang Maharlika (B00592LT), Libagon, Southern Leyte | Libagon, Southern Leyte | 2015-11-16 | Final | Southern Leyte DEO | LF | 12.547 | 165 | 2015-02-02 | 2015-07-16 | - | C | 0.437 | 0.187 | 0.3 | - | - | - | 92.4% | 92.4% Very Satisfactory
ST. GERRARD CONSTRUCTION / SMPE CONSTRUCTION JOINT VENTURE | 13810 | L | A | MB | GE | Improvement/Desilting of San Dionisio River Phase III, Paranaque City, Metro Manila | Paranaque City, Metro Manila | 2015-12-03 | 1st | Metro Manila 2nd DEO | LF | 34.7011 | 210 | 2015-06-15 | 2016-01-11 | (+)15.53% | OG | 0.397 | 0.24 | 0.15 | 0.03 | 0.033 | 0.05 | 90% | 90% Very Satisfactory
ST. GERRARD CONSTRUCTION / SMPE CONSTRUCTION JOINT VENTURE | JV-14-923 | L | A | MB | GE | Slope Protection/Bank Improvement of Kaybuboy Creek Tributary, Brgy. San Dionisio, Paranaque City, Metro Manila | Brgy. San Dionisio, Paranaque City, Metro Manila | 2015-12-03 | 1st | Metro Manila 2nd DEO | LF | 26.7785 | 240 | 2015-06-15 | 2016-02-09 | (+)12.23% | OG | 0.398 | 0.24 | 0.15 | 0.03 | 0.025 | 0.05 | 89.3% | 89.3% Very Satisfactory
ST. GERRARD CONSTRUCTION/ STRONGLANE CONSTRUCTION & TRADING (JOINT VENTURE) | JV-14-808 | L | A | MB | GE | Construction/Rehabilitation/Improvement of Revetment/River Control along Macabling River at Brgy. Aplaya and Brgy. Caingin | Sta. Rosa City, Laguna 1st LD | 2015-08-28 | 1st | Laguna 2nd | LF | 45.884 | 210 | 2015-03-25 | 2015-10-20 | -0.26% | O | 0.364 | 0.24 | 0.147 | 0.03 | 0.025 | 0.033 | 83.9% | -
ST. GERRARD CONSTRUCTION/BADSBRO CONSTRUCTION/BADSBRO CONSTRUCTION AND GENERAL MERCHANDISE (Joint Venture) | JV-14-580 | L | A | MB | GE | Construction/Rehabilitation of Flood Control Dike (Phase IV) at Salinding, Siay, Zamboanga Sibugay | Siay, Zamboanga Sibugay | 2015-08-25 | 1st & Final | Zamboanga Sibugay 2nd | LF | 41.25 | 205 | 2015-01-29 | 2016-08-21 | - | C | 0.468 | 0.133 | 0.3 | - | - | - | 90.1% | *90.1% Very Satisfactory
ST. GERRARD CONSTRUCTION/BLUE MOUNTAIN BUILDERS & GENERAL MERCHANDISE JOINT VENTURE | JV-15-03 | L | A | MB | GE | Construction/Rehabilitation of Flood Control Revetment along Bolo River, Brgy. San Isidro, Dumalneg, Ilocos Norte | Brgy. Isidro, Dumalneg, Ilocos Norte | 2015-11-11 | Final | ILOCOS NORTE 1ST DEO | LF | 46.3014 | 214 | 2015-07-29 | 2016-02-27 | 0.0545 | C | 0.375 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 89.5% | 89.5% Very Satisfactory
St. Gerrard Construction/CSD Engineering and Construction (JV) | 31762 | L | A | MB | GB | Construction of Eco-Tourism Park | Liwan West, Rizal, Kalinga | 2016-01-21 | 1st | TIEZA | LF | 20 | 150 | 2015-09-03 | 2016-01-30 | -17.15 | O | 0.39 | 0.3 | 0 | 0.03 | 0.058 | 0.05 | 82.93
ST. GERRARD CONSTRUCTION/PRIME PACIFIC MARINE & INDUSTRIAL SERVICES CORP. (Joint Venture) | JV-14-488 | L | A | MB | GE | Raising of River Wall along Marala River, Sta. 1+400 to Sta. 2+900, Navotas City | Navotas City | 2015-09-04 | 1st | NCR | LF | 98.682 | 282 | 2015-03-17 | 2015-12-23 | -3.18% | O | 0.391 | 0.225 | 0.118 | 0.03 | 0.055 | 0.033 | 85.2% | -
ST. GERRARD CONSTRUCTION/SMPE CONSTRUCTION (Joint Venture) | JV-14-923 | L | A | SB | GE | Slope Protection/Bank Improvement of Kaybuboy Creek Tributary, Barangay San Dionisio, Parañaque City, Metro Manila | Parañaque City, Metro Manila | 2015-09-03 | 1st | MM 3rd DEO | LF | 26.778 | 240 | 2015-06-15 | 2016-02-09 | 14.11% | O | 0.365 | 0.24 | 0.15 | 0.01 | 0.035 | 0.05 | 85% | -
St. Raymund Construction, Inc. | 19242 | L | B | MA | GE | Upgrading/Concreting (From Asphalt to Concrete) along Bacolod North Road, K0026+050 - K0026+537 | E.B. Magalona, Negros Occidental | 2014-10-21 | 1st & Final | VI | LF | 8.1187 | 116 | 2014-05-12 | 2014-09-04 |  | C | 0.441 | 0.133 | 0.3 | - | - | - | 87.4% | 87.4% Satisfactory
St. Raymund Construction, Inc. | 19242 | L | B | MA | GE1 | Conc. of Bacolod South Road, Pook Section Brgy. Pook | Hinoba-an, Negros Occidental | 2011-04-01 | 1st | VI | LF | 9.388 | 150 | 2010-12-24 | 2011-05-22 | 15.1 | O | 0.373 | 0.24 | 0.15 | 0.03 | 0.033 | 0.033 | 85.9 | -
ST. RAYMUND CONSTRUCTION, INC. | 19242 | L | B | MA | GE | Concreting of Felisa FMR, Brgy. Felisa, Bacolod City | Brgy. Felisa, Bacolod City | 2015-11-17 | Final | Bacolod City DEO | LF | 4.7257 | 130 | 2015-06-25 | 2015-11-01 | - | C | 0.438 | 0.133 | 0.3 | - | - | - | 87.1% | 87.1% Satisfactory
ST. RAYMUND CONSTRUCTION, INC. | 19242 | L | B | MA | GE | Local Infrastructure Program - Concrete Paving of Road and Road Shoulder from Jct. of National Road to Brgy. Vista Alegre to Sitio Enclaro, Brgy. Vista Alegre, Ilog, Negros Occidental | Brgy. Vista Alegre, Ilog, Negros Occidental | 2015-11-14 | Final | Negros Occidental 3rd DEO | LF | 9.309 | 190 | 2015-02-23 | 2015-08-31 | (+)0.75% | C | 0.409 | 0.135 | 0.3 | - | - | - | 84.4% | 84.4% Satisfactory
St. Raymund Construction, Inc. | 19242 |  |  |  |  | Const. of Flood Control / River Bank Protection at Canmoros-Nabuswang River Brgy. Canmoros |  | 2010-06-03 |  | VI |  | 9.335 | 190 |  |  |  | O | 0.28 | 0.3 | 0.15 | 0.03 | 0.047 | 0.033 | 84 | -
Sta Cruz Construction and General Services | 32289 | L |  | SB |  | Repair of Damaged Rock Causeway | Port of Lobo, Batangas | 2015-03-19 | 1st & Final | PPA | L | 22.373 |  | 2014-11-07 | 2015-03-06 | 0 | C | 0.4077 | 0.2 | 0.3 | - | - | - | - | *90.77% V. Satisfactory
Sta. Cruz Construction | 9301 | L | B | SB | GB | Construction/Rehabilitation/Improvement of Flood Control at San Isidro | Calabanga, Camarines Sur | 2014-08-08 | 1st & Final | V | LF | 4.495 | 125 | 2014-02-25 | 2014-06-29 | 0 | C | 0.343 | 0.2 | 0.3 |  |  |  | 84.3 | 84.30% Satisfactory
Sta. Cruz Construction and General Services | 32289 |  |  | SB |  | Construction of Diversion Works, Gabion Protection Works and Canal System for Manolo CIS | San Juan, Batangas | 2015-02-14 | 1st & Final | NIA | L | 9.347 | 150 | 2014-02-14 | 2014-07-24 | 0 | C | 0.4134 | 0.1278 | 0.3 | - | - | - | 84.12 | *84.12% Satisfactory
Sta. Cruz Construction and General Services | 32289 | L |  |  | GE5 | Repair & Maint. Of Service Road and Perimeter Lighting System at Phase II | Port of Batangas, Batangas City | 2013-02-01 | 1st | PPA | LF | 24.771 | 148 | 2012-10-24 | 2013-03-20 | 8.58 | O | 0.399 | 0.3 | 0.15 | 0.03 | 0.055 | 0.05 | 98.4 | -
Sta. Cruz Construction and General Services | 32289 | L |  |  | GE5 | Repair & Maint. Of Service Road and Perimeter Lighting System at Phase II | Port of Batangas, Batangas City | 2013-04-25 | 2nd & Final | PPA | LF | 26.735 | 175 | 2012-10-24 | 2013-04-16 | 0 | C | 0.4804 | 0.2 | 0.3 | - | - | - | 98.04 | 98.26% Outstanding
Star William Construction | 35938 | L | C | SB | GE | Desilting of Nangka River | Marikina City | 2014-08-07 | 1st & Final | NCR | LF | 3.5456 | 60 | 2014-03-19 | 2014-05-17 | 0 | C | 0.404 | 0 | 0.5 |  |  |  | 90.4 | 90.40% Very Satisfactory
STAR WILLIAM CONSTRUCTION | 35938 | L | B | MA | GE | Construction/Maintenance of Flood Control Mitigation Structures & Drainage Systems Flood Control along Angat River Rueda, Plaridel, Bulacan | Plaridel, Bulacan | 2015-08-26 | 1st | Bulacan First DEO | LF | 12.614 | 200 | 2015-03-20 | 2015-10-05 | 12.34% | O | 0.361 | 0.3 | 0.15 | 0.02 | 0.029 | 0.05 | 91% | -
STAR WILLIAM CONSTRUCTION | 35938 | L | B | MA | GE | Construction/Maintenance of Flood Control Mitigation Structures & Drainage Systems Flood Control along Angat River, Rueda, Plaridel, Bulacan | Rueda, Plaridel, Bulacan | 2015-11-20 | Final | Bulacan First DEO | LF | 12.614 | 200 | 2015-03-20 | 2015-10-05 | - | C | 0.488 | 0.133 | 0.3 | - | - | - | 92.1% | 91.44% Very Satisfactory
Stay Construction | 23323 | L | A | MA | GE | Road Upgrading (Gravel to Paved) along Acop-Kapangan-Kibungan-Bakun Road, K0326+935 - K 0328+000 (Kibungan to Sinipsip Section), K0328+(-085) - K0328+653 (To Poblacion, Bakun Section) | Benguet | 2014-11-21 | 1st | CAR | LF | 64.8989 | 240 | 2014-06-11 | 2015-02-05 | 9.25% | O | 0.348 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 87.3% | 87.3% Satisfactory
Stay Construction | 23323 | L | A | MA | GE1 | Repair & Rehab. along Kennon Road |  | 2009-05-19 | 1st | CAR |  | 6.454 | 200 |  |  |  | O | 0.304 | 0.291 | 0.15 | 0.01 | 0.032 | 0.033 | 82 | -
Stay Construction | 23323 | L | A | MA | GE1 | Concreting of Acop-Kapangan-Kibungan Road |  | 2009-05-21 | 1st | CAR |  | 19.168 | 180 |  |  |  | O | 0.297 | 0.3 | 0.065 | 0.01 | 0.025 | 0.033 | 73 | -
Stay Construction | 23323 | L | A | MA | GE1 | Concreting along Baguio-Bua-Itogon Road |  | 2009-08-26 | 1st | CAR |  | 12.72 | 200 |  |  |  | O | 0.384 | 0.24 | 0.15 | 0.03 | 0.051 | 0.033 | 88.8 | -
Stay Construction | 23323 | L | A | MA | GE1 | Conc. of Acop-Kapangan-Kibungan Road Km. 263+000- Km. 266+700 (v.s.) |  | 2009-08-26 | 2nd | CAR |  | 19.168 | 229 |  |  |  | O | 0.356 | 0.24 | 0.15 | 0.015 | 0.042 | 0.033 | 83.6 | -
Stay Construction | 23323 | L | A | MA | GE1 | Rehab. of Benguet National Road |  | 2009-08-25 | 1st | CAR |  | 4.718 | 200 |  |  |  | O | 0.379 | 0.194 | 0.067 | 0.015 | 0.042 | 0.017 | 71.4 | -
STAY CONSTRUCTION | 23323 | L | A | MA | GE | Road Upgrading (Gravel to Paved) along Acop-Kapangan-Kibungan-Bakun Road, K0326+935 - k0328+000 (Kinungan to Sinipsip Section), K0328+(-085) - K0328+653( To Poblacion, Bakun Section) | Bakun, Benguet | 2015-06-03 | Final | CAR | LF | 64.899 | 240 | 2014-06-11 | 2015-02-05 | 0% | C | 0.378 | 0.2 | 0.3 | - | - | - | 87.8% | *87.5% Satisfactory
Stay Construction/Vymeah Construction (JV) | JV-08-036 | L | A | MA | GE1 | Const. of Tabuk-Tanudan-Banaue Road, Banaue Section |  | 2009-05-25 | 1st | CAR |  | 19.126 | 284 |  |  |  | O | 0.361 | 0.145 | 0.1 | 0.015 | 0.04 | 0.033 | 69.4 | -
Steel City Fabricators Corporation | 27035 | L | B | SB | GB1 | Const./Rehab./Replacement, Completion/Repair Kalasungay E/S |  | 2009-09-02 | 1st | X |  | 6.486 | 75 |  |  |  | O | 0.318 | 0.037 | 0.15 | 0.03 | 0.047 | 0.033 | 61.5 | -
Stellar Builders | 35031 | L |  | SB | GE2 | Construction of Vista Alegre CIP | Vista Alegre, Anilao, Iloilo | 2013-08-31 | 1st | NIA | L | 2.626 | 120 | 2013-05-21 | 2013-09-21 | 0 | O | 0.381 | 0.24 | 0.15 | 0.015 | 0.0233 | 0.05 | 85.93 | -
STEVEN CONST. AND SUPPLY/JMK BUILDERS CONST. (JV) | - | L | - | - | GE | Construction/Rehabilitation of Flood Control in Manila City 4th LD-Drainage Improvement along Masbate St. (Phase II) Visayan St. to Luzon St. Sampaloc, Manila | Sampaloc, Manila | 2015-06-09 | Final | North Manila DEO | LF | 18.13 | 142 | 2015-10-03 | 2015-02-20 | (+) 1.40 | C | 0.44 | 0.133 | 0.3 | - | - | - | 87.3% | *87.3% Satisfactory
Steven Construction & Supply | 21987 | L | B | MA | GE | Construction of Flood Control System, Bolo-Pawa River | Brgy. Bolo, Matnog, Sorsogon | 2014-11-06 | 1st & Final | V | LF | 14.1003 | 140 | 2014-02-12 | 2014-07-01 | 0% | C | 0.477 | 0.123 | 0.3 | - | - | - | 90% | 90% Very Satisfactory
Steven Construction & Supply | 21987 | L | B | MA | GE | Rehabilitation/Reconstruction of Critical Sections along National Roads, Road Slip along Sta. Fe-Pastrana-Dagami Road, Km.0939+560, Brgy. San Benito | Dagami, Leyte | 2014-10-29 | 1st & Final | VIII | LF | 9.0013 | 115 | 2014-02-25 | 2014-06-19 | 0.87% | C | 0.42 | 0.133 | 0.3 | - | - | - | 85.3% | 85.3% Satisfactory
STEVEN CONSTRUCTION & SUPPLY | 21987 | L | B | MA | GE | Completion of Slope Protection and Desilting of Sapang Malaki, Brgy. Ususan, Taguig City | Brgy. Ususan, Taguig City | 2015-06-04 | Final | Metro Manila 1st DEO | LF | 17.368 | 180 | 2015-03-02 | 2015-08-28 | (+) 47.72 | C | 0.43 | 0.133 | 0.3 | - | - | - | 86.3% | *86.3% Satisfactory
STEVEN CONSTRUCTION & SUPPLY | 21987 | L | B | MA | GE | Rehabilitation of Mapulang Daga-Damacan Road, Brgy. Mapulang Daga/Damacan, Bacacay, Albay | Brgy. Mapulang Daga/Damacan, Bacacay, Albay | 2015-08-25 | 1st & Final | Albay First DEO | LF | 18.6 | 147 | 2015-03-23 | 2015-08-16 | - | C | 0.461 | 0.133 | 0.3 | - | - | - | 89.4% | *89.4% Very Satisfactory
STO. CRISTO CONSTRUCTION | 26096 | L | B | MA | GE | Network Development/Off Carriageway Improvement, Gerona/Poblacion Road, K0138+(-958.60) - K0138+1021, San Antonio-Poblacion, Gerona, Tarlac | San Antonio-Poblacion, Gerona, Tarlac | 2015-09-03 | 1st | Tarlac First DEO | LF | 42.071 | 240 | 2015-02-02 | 2015-09-29 | - | O | 0.394 | 0.24 | 0.15 | 0.03 | 0.06 | 0.05 | 92.4% | -
Sto. Cristo Construction and Trading (Formerly: Sto. Cristo Construction) | 26096 | L | B | MA | GE | Construction/Improvement of Bagac - Mariveles Road, Mariveles Section | Mariveles, Bataan | 2014-11-27 | 1st & Final | III | LF | 9.357 | 90 | 2014-05-27 | 2014-08-24 | 0% | C | 0.411 | 0.127 | 0.3 | - | - | - | 83.8% | 83.8% Satisfactory
Sto. Nino Construction | 4867 | L | A | MB | GE1 | Concreting of Jct. Tubod-Lakewood Road, Sta. 1701+818.70-Km. 1710+320 (with exceptions) |  | 2009-06-02 | 1st | IX |  | 68.948 | 508 |  |  |  | O | 0.378 | 0.24 | 0.15 | 0.03 | 0.047 | 0.05 | 89.5 | -
Sto. Nino Construction | 4867 | L | A | MB | GE1 | Concreting of Lanao-Pagadian-Zamboanga City Road, Pagadian-Dumalinao (Intermittent Section) |  | 2009-06-05 | 1st | IX |  | 27.85 | 413 |  |  |  | O | 0.359 | 0.24 | 0.15 | 0.03 | 0.047 | 0.05 | 87.6 | -
Sto. Nino Construction | 4867 | L | A | MB | GE1 | Road Upgrading (Gravel to Concrete) Dipolog-Punta-Dansullan-Sergio Osmeña |  | 2009-09-17 | 2nd | IX |  | 15.259 | 210 |  |  |  | O | 0.329 | 0.3 | 0.15 | 0.03 | 0.04 | 0.033 | 88.2 | -
Sto. Nino Construction | 4867 | L | A | MB | GE1 | Road Upgrading (Gravel to Concrete) Dipolog-Punta-Dansullan-Sergio Osmeña |  | 2009-06-10 | 1st | IX |  | 15.2589 | 210 |  |  |  | O | 0.367 | 0.24 | 0.15 | 0.03 | 0.037 | 0.05 | 87.4 | -
Sto. Nino Construction | 4867 | L | A | MA | GE2 | Construction of Flood Control Projects along Dipolo River |  | 2009-06-05 | 1st | IX |  | 9.285 | 180 |  |  |  | O | 0.356 | 0.24 | 0.15 | 0.01 | 0.042 | 0.05 | 84.8 | -
Sto. Nino Construction | 4867 | L | A | MB | GE1 | Impvt./Concrete Paving of Ilmelda-Alicia Road, Naga-naga Section, Sta. 1767+380-Sta. 1767+764 |  | 2009-05-30 | 1st | IX |  | 10.491 | 160 |  |  |  | O | 0.326 | 0.24 | 0.15 | 0.03 | 0.042 | 0.05 | 83.8 | -
Sto. Nino Construction | 4867 | L | A | MA | GE2 | Construction of River Control, Salug Diut River |  | 2009-05-05 | 3rd | IX |  | 9.31 | 420 |  |  |  | O | 0.374 | 0.24 | 0.15 | 0.01 | 0.042 | 0.05 | 86.6 | -
Sto. Nino Construction | 4867 | L | A | SB | GE2 | Const. of River Control @ Salug Diut River |  | 2009-03-12 | 2nd | IX |  | 9.31 | 340 |  |  |  | O | 0.382 | 0.24 | 0.15 | 0.03 | 0.035 | 0.05 | #VALUE! | -
Sto. Nino Construction | 4867 | L | A | SB | GE2 | Const. of River Control @ Salug River |  | 2008-08-29 | 1st | IX |  | 9.31 | 150 |  |  |  | O | 0.272 | 0.12 | 0.1 | 0.03 | 0.035 | 0.2 | 75.7 | -
Sto. Nino Construction | 4867 | L | A | MB | GE1 | Rehab. of Oroquieta City-Calamba Mt. Road |  | 2008-11-29 | 1st | X |  | 15.675 | 150 |  |  |  | O | 0.373 | 0.26 | 0 | 0.023 | 0.038 | 0.067 | 76.1 | -
Sto. Nino Construction | 4867 | L | A | MB | GE1 | Rehab./Reconst./Upgrading of Pagadian City Wharf Road |  | 2009-09-11 | 1st | IX |  | 13.938 | 203 |  |  |  | O | 0.345 | 0.3 | 0.15 | 0.023 | 0.035 | 0.033 | 88.6 | -
Sto. Nino Construction | 4867 | L | A | MB | GE1 | Conc. of Jct. Blancia-Molave-Josefina Road (Molave-Mahayag Section) |  | 2009-03-12 | 3rd | IX |  | 18.55 | 348 |  |  |  | O | 0.372 | 0.244 | 0.15 | 0.03 | 0.035 | 0.05 | #VALUE! | -
Sto. Nino Construction | 4867 | L | A | MB | GE1 | Conc. of Jct. Blancia-Molave-Josefina Road (Molave-Mahayag Section) |  | 2008-08-29 | 1st | IX |  | 18.55 | 150 |  |  |  | O | 0.237 | 0.223 | 0.1 | 0.03 | 0.042 | 0.1 | 73.2 | -
Sto. Nino Construction | 4867 | L | A | MB | GE1 | Conc. of Jct. Blancia-Molave-Josefina Road (Molave-Mahayag Section) |  | 2008-11-29 | 2nd | IX |  | 18.55 | 150 |  |  |  | O | 0.34 | 0.22 | 0.1 | 0.03 | 0.03 | 0.1 | 82 | -
Sto. Nino Construction | 4867 | L | A | MB | GE1 | Impvt./Conc. Paving of Imelda-Alicia Road, (Phase III), Guintolan Section |  | 2008-08-22 | 1st | IX |  | 33.916 | 320 |  |  |  | O | 0.295 | 0.235 | 0.1 | 0.03 | 0.042 | 0.1 | 80.2 | -
Stoneline Construction | 33707 | L |  |  |  | MALITUBOG IRRIGATION PROJECT MIP-LMC-005 Package II | Langayen-Tapudok, Pikit and aleosan, Cotabato Province | 2014-06-06 | 1st & Final | NIA | LF | 25.918 | 330 | 2013-02-18 | 2014-01-13 | 0 | C | 0.3924 | 0.2 | 0.3 | - | - | - | 89.24 | *89.24% V. Satisfactory
Stronglane Construction & Trading | 32333 | L |  | SB | GE | Repair of Cagnipa Flood Control Structure | Calbayog City | 2014-08-11 | Final | VIII | LF | 2.9962 | 75 | 2013-06-08 | 2013-08-20 | 0 | C | 0.441 | 0.133 | 0.178 |  |  |  | 75.2 | 83.36% Satisfactory
Stronglane Construction & Trading | 32333 | L | C | SB | GE2 | Repair of Cagnipa Flood Control Structure, Brgy. Canipa | Calbayog City, Samar | 2013-08-13 | 1st | VIII | LF | 2.996 | 75 | 2013-07-07 | 2013-08-20 | 0.74 | O | 0.38 | 0.235 | 0.15 | 0.03 | 0.06 | 0.033 | 88.8
Stronglane Construction & Trading | 32333 | L |  | SB | GE | Repair of Minlawaan Flood Control Structure | Calbayog City | 2014-08-13 | Final | VIII | LF | 2.9924 | 75 | 2013-06-08 | 2013-08-20 | 0 | C | 0.378 | 0.2 | 0.173 |  |  |  | 75.1 | 83.32% Satisfactory
Stronglane Construction & Trading | 32333 | L | C | SB | GE2 | Repair of Minlawaan Flood Control Structure, Brgy. San Policarpio | Calbayog City, Samar | 2013-08-13 | 1st | VIII | LF | 2.992 | 75 | 2013-06-07 | 2013-08-20 | 0.21 | O | 0.36 | 0.245 | 0.15 | 0.03 | 0.055 | 0.033 | 87.3
Stronglane Construction and Trading | 32333 | L | C | SB | GE2 | Bonotbonot Small River Impounding Project | Buenavista Bohol, Region 7 | 2013-07-13 | 1st | NIA | L | 4.526 | 120 | 2013-01-15 | 2013-08-20 | -23.31 | O | 0.34 | 0.3 | 0 | 0.02 | 0.06 | 0.03 | 75 | -
Struktura Teknika Services Co./ Three W Builders, Inc - JV | [5 empty] | Construction of Six (6) 5-Storey Residential Buildings with Land Development and Survey Works, San Juan LRB | Pinaglabanan St., Brgy. St. Joseph, San Juan City | 2015-08-11 | Final | NHA | LF | 197.73 | 360 | 2014-02-10 | 2015-05-01 | 0 | C | 0.4696 | 0.1903 | 0.3 | - | - | - | 95.99 | 85.90% Satisfactory
Struktura Teknika Services Co./Three W Builders, Inc. JV |  | L |  |  |  | Construction of Six (6) 5-Storey Residential Buildings | Pinaglabanan St., Brgy. St. Joseph, San Juan City | 2014-08-05 | 1st | NHA | L | 197.73 | 360 | 2014-02-10 | 2015-02-04 | 3.26 | O | 0.3693 | 0.2712 | 0.15 | 0.0225 | 0.0233 | 0.05 | 88.63 | -
Struktura Teknika Services Company | 16646 | L | A | SB | GE | Rehabilitation of Drainage System along Northbay Boulevard | Navotas City | 2014-11-21 | 1st | NCR | LF | 10.1678 | 155 | 2014-06-30 | 2014-12-01 | -6.01% | O | 0.36 | 0.3 | 0.09 | 0.015 | 0.035 | 0.033 | 83.3% | 83.3% Satisfactory
Struktura Teknika Services Company | 16648 | L | A | MA | GB | Construction of Three (3) Storey , Six (6) Classroom School Building at San Juan National High School | San Juan City | 2014-08-07 | Final | NCR | LF | 8.243 | 270 | 2013-05-21 | 2014-02-14 | 0 | C | 0.41 | 0.133 | 0.3 |  |  |  | 84.3 | 85.21% Satisfactory
Struktura Teknika Services Company | 16646 | L | A | MA | GB1 | Const. of Three (3) Storey, Six (6) Cl Sch. Bldg. at San Juan NHS | San Juan City | 2013-08-06 | 1st | NCR | LF | 8.243 | 270 | 2013-05-21 | 2014-02-14 | 8.89 | O | 0.362 | 0.24 | 0.15 | 0.03 | 0.041 | 0.033 | 85.6
Struktura Teknika Services Company | 16646 | L | A | MA | GE1 | Rehab. of Rds. along Union St., Brgy San Jose (Pob) | Navotas City | 2013-08-12 | Final | NCR | LF | 6.205 | 138 | 2012-12-18 | 2013-05-04 | 3.31 | C | 0.455 | 0.133 | 0.3 | - | - | - | 88.8 | 85.38% Satisfactory
Struktura Teknika Services Company | 16646 | L | A | MA | GE1 | Rehab. of Rd.s along Union St., Brgy. San Jose (Pob.) | Navotas City, Metro Manila | 2013-03-15 | 1st | NCR | LF | 6.206 | 121 | 2012-12-18 | 2013-04-17 | 12.54 | O | 0.387 | 0.209 | 0.15 | 0.022 | 0.03 | 0.033 | 83.1 | -
STRUKTURA TEKNIKA SERVICES COMPANY | 16646 | L | A | MA | GE | Rehabilitation/Improvement of Drainage System along C-4 Road to R-10 Road, Brgy. Bagumbayan South, Navotas City | Brgy. Bagumbayan South, Navotas City | 2015-06-05 | 1st | Malabon-Navotas DEO | LF | 3.631 | 120 | 2015-03-06 | 2015-07-03 | (-) 3.40 | O | 0.381 | 0.24 | 0.116 | 0.022 | 0.052 | 0.033 | 84.4% | -
STX Enterprises | 21547 | L | AAA | LB | GE | Road Upgrading (Gravel to Paved) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standard (HDM-4 Project Analysis Intermittent Section) Secondary Road, Crossing MWCR (Labangan)- Murtha- Jct. Iriron Road | San Jose, Occidental Mindoro, K0247+157.00-K0247+865.00 (with exception) K0248+978.00-K0250-803.50 | 2014-11-27 | 1st | IV | LF | 42.5053 | 299 | 2014-04-22 | 2015-02-15 | -3.81% | O | 0.371 | 0.287 | 0.112 | 0.03 | 0.032 | 0.033 | 86.5% | 86.5% Satisfactory
STX Enterprises | 21547 | L | AAA | LB | GE | Road Upgrading (Gravel to Paved) Based on Gravel Riad Strategies, Traffic benchmark for Upgrading to Paved Road Standard (HDM-4 Project Analysis Intermittent) Secondary, Crossing MWCR (Pola)- Casague Jct. Alacak Road, K0378+900-K0379+891.45, K0380+090-K0381+500 | Sta. Cruz, Occidental Mindoro | 2014-11-25 | 1st | IV | LF | 38.1908 | 299 | 2014-04-22 | 2015-02-15 | 9.11% | O | 0.349 | 0.286 | 0.15 | 0.02 | 0.038 | 0.033 | 87.6% | 87.6% Satisfactory
STX Enterprises | 21547 | L | AAA | LB | GE | Road Upgrading (Gravel to Paved) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standards (HDM-4 Project Analysis), Secondary Road, Jct. MWCR (Pola) - Casague Jct. Alacaak Road, Sta. 378+900 - 379+891.45, Sta. 0380+090 - 381+500 | Sta. Cruz, Occidental Mindoro | 2014-08-14 | 1st | IV-B | LF | 35.9392 | 209 | 2014-04-22 | 2014-11-16 | -0.98 | O | 0.368 | 0.236 | 0.14 | 0.03 | 0.035 | 0.033 | 84.2
STX Enterprises | 24547 | L | AAA | LB | GE1 | Prev. Maint. (Int. Sec.) CSR Jct. Pola, K0069+000-K0071+000, K0072+000-K0072+895 | Pola, Oriental Mindoro | 2013-08-01 | Final | IVB | LF | 18.044 | 120 | 2013-01-28 | 2013-05-27 | 38.89 | C | 0.427 | 0.133 | 0.3 | - | - | - | 86 | 83.90% Satisfactory
STX Enterprises | 21547 | L | AAA | LB | GE1 | Prev. Maint. (Int. Sect.) CSR Jct. Pola, K0069+000-K0071+000, K0072+000-K0072+895 | Pola, Oriental Mindoro | 2013-03-19 | 1st | IVB | LF | 18.044 | 120 | 2013-01-28 | 2013-05-27 | 0.07 | O | 0.355 | 0.207 | 0.15 | 0.03 | 0.05 | 0.033 | 82.5 | -
STX Enterprises / Northern Builders (JV) | JV-08-234 | L | AAA | LB | GE1 | Conc. of Calapan South Road |  | 2009-09-02 | 1st | IVB |  | 162.022 | 270 |  |  |  | O | 0.318 | 0.3 | 0.15 | 0.03 | 0.051 | 0.033 | 88.2 | -
STX Enterprises / Northern Builders (JV) | JV-08-234 |  |  |  |  | Concreting of Calapan South Road |  | 2010-02-15 |  | IVB |  | 162.92 | 270 |  |  |  | O | 0.327 | 0.3 | 0.15 | 0.03 | 0.054 | 0.033 | 89.4 | -
Subcon Corporation | 25079 |  |  |  |  | Const. of Classroom Bldg. at Sta.Rita H/S |  | 2010-05-30 |  | III |  | 2.34 | 90 |  |  |  | O | 0.367 | 0.214 | 0.15 | 0.03 | 0.021 | 0.033 | 81.5 | -
Subiccon Construction | 25079 | L | AAA | LB | GE1 | 2014 Heavy Maintenance Works Along SCTEX-Asphalt Resurfacing | Pampanga, Bataan and Zambales | 2014-08-14 | 1st | BCDA | LF | 68.47 | 120 | 2014-07-07 | 2014-11-03 | 39.18 | O | 0.349 | 0.3 | 0.15 | 0.03 | 0.048 | 0.05 | 92.7 | -
Subiccon Construction | 25079 | L | AAA | LB |  | 2014 Heavy Maintenace Works Along SCTEX - Asphalt Resurfacing | Pampanga, Bataan and Zambales | 2014-11-07 | 1st | BCDA | LF | 68.47 | 120 | 2014-07-07 | 2014-11-03 | 0 | O | 0.349 | 0.3 | 0.15 | 0.03 | 0.048 | 0.05 | 92.7 | -
Subiccon Construction | 25079 | L | AAA | LB |  | 2014 Heavy Maintenace Works Along SCTEX - Asphalt Resurfacing | Pampanga, Bataan and Zambales | 2014-11-07 | Final | BCDA | LF | 68.47 | 120 | 2014-07-07 | 2014-11-03 | 0 | C | 0.4614 | 0.2 | 0.3 | - | - | - | - | 94.08% V. Satisfactory
SUBICCON CORPORATION (Formerly Subcon Corporation) | 25079 | L | AA | SB | GE | Construction/Maintenance of Flood Mitigation Structures & Drainage System/Improvement of Deteriorated Top of West Mega Dike, Sta. Rita-Porac, Pampanga | Sta. Rita-Porac, Pampanga | 2015-09-05 | 1st | Pampanga Second DEO | LF | 31.221 | 180 | 2015-05-12 | 2015-11-07 | 16.88% | O | 0.346 | 0.197 | 0.15 | 0.03 | 0.05 | 0.05 | 82.3% | -
SUMAG BUILDERS CONSTRUCTION | 32894 | L | D | SB | GB | Completion of Multi-Purpose Building at Brgy. Supang | Sabangan, Mt. Province | 2015-06-04 | Final | Mountain Province DEO | LF | 1.139 | 81 | 2015-02-19 | 2015-05-10 | (+) 37.04% | C | 0.476 | 0.168 | 0.3 | - | - | - | 94.4% | *94.4% Very Satisfactory
Sumag Builders Corporation | 32894 | L | D | SB | GE | Replacement/Rehabilitation/Strengthening of Dawaic Bridge along Mt. Province-Ilocos Sur via Tue Road | Sabangan, Mt. Province | 2014-08-12 | Final | CAR | LF | 4.3373 | 143 | 2013-04-02 | 2013-08-30 | 0 | C | 0.427 | 0.133 | 0.153 |  |  |  | 71.3 | 79.88% Unsatisfactory
Sumag Builders Corporation | 32894 | L | D | SB | GE1 | Replacement/Rehab./Strengthening of Dawaic Bridge along Mt. Province-Ilocos Sur via Tue Rd. | Sabanga, Mt. Province | 2013-08-02 | 1st | CAR | LF | 4.337 | 143 | 2013-04-02 | 2013-08-22 | 2.35 | O | 0.356 | 0.24 | 0.15 | 0.015 | 0.045 | 0.05 | 85.6
Sumitomo Construction Co. Ltd. | FC-04-010 | F | AAA | LB | GE1 | CP V, Agas-Agas Bridge Project |  | 2009-03-07 | 3rd | PJHL |  | 995.037 | 990 |  |  |  | O | 0.367 | 0.298 | 0.15 | 0.03 | 0.07 | 0.05 | #VALUE! | -
Sumitomo Construction Co. Ltd. | FC-04-010 | F | AAA | LB | GE1 | CP V, Agas-Agas Bridge Project |  | 2008-08-30 | 2nd | PJHL |  | 869.429 | 780 |  |  |  | O | 0.386 | 0.3 | 0.1 | 0.03 | 0.07 | 0.1 | 98.6 | -
Sunstone Construction and Supply | 11122 | L | B | MA | GE2 | MALITUBOG IRRIGATION PROJECT STAGE II MIP-LMC-004 PACKAGE VI | Pikit, Cotabato | 2014-06-06 | 1st & Final | NIA | LF | 37.721 | 503 | 2013-01-15 | 2014-06-02 | 0 | C | 0.3653 | 0.1923 | 0.3 | - | - | - | 85.76 | *85.76% Satisfactory
Sunwest Construction & Development Corporation | 15906 | L | AAA | LB | GE-5 | Gaba Port Development Project | Gaba, Rapu-rapu, Albay/ Region V | 07/29/15 | 1st | DOTC | LF | 18.652 | 180 | 02/18/15 | 10/17/15 | 1.7 | O | 0.3425 | 0.3 | 0.15 | 0.02 | 0.035 | 0.05 | 89.75 | -
Sunwest Construction & Development Corporation | 15906 | l | AAA | LB |  | Bicol (New Legaspi) Int'l Airport Development Project | Daraga, Albay | 2015-08-20 | 3rd | DOTC | LF | 778.551 | 854 | 2013-11-12 | 2016-06-02 | 13.47 | O | 0.363 | 0.3 | 0.15 | 0.03 | 0.07 | 0.05 | 96.3 | -
Sunwest Construction & Development Corporation | 15906 | L | AAA |  |  | New Bicol International Airport & Development Project | Daraga, Albay/ Region V | 2014-02-04 | 2nd | DOTC | L | 708 | 540 | 2013-11-12 | 2015-08-24 | 0.83 | O | 0.3509 | 0.3 | 0.15 | 0.03 | 0.0622 | 0.05 | 94.31 | -
Sunwest Construction & Development Corporation | 15906 | L | AAA |  |  | New Bicol International Airport Development Project | Daraga, Albay/Region V | 2014-04-23 | 1st | DOTC | LF | 708 | 540 | 2013-11-12 | 2015-07-23 | 26.43 | O | 0.3546 | 0.3 | 0.15 | 0.03 | 0.042 | 0.05 | 92.66 | -
Sunwest Construction & Development Corporation | 15906 | L | AAA | LB | GE-5 | RC Wharf Extension and Construction of Back-up Area | Port of Tabaco City, Albay/Region V | 2015-09-29 | 1st | PPA | LF | 95.492 | 420 | 2014-08-21 | 2015-10-15 | 0 | O | 0.399 | 0.3 | 0.15 | 0.03 | 0.059 | 0.05 | 98.8 | -
Sunwest Construction & Development Corporation | 15906 |  | AAA | LB |  | Gaba Port Development Project | Gaba, Rapu-rapu, Albay/ Region V | 2015-11-24 | 2nd & Final | DOTC | LF | 18.652 | 180 | 2015-02-18 | 2015-10-17 | 0 | C | 0.4878 | 0.2 | 0.3 | - | - | - | 98.78 | 93.36% V. Satisfactory
Sunwest Construction & Development Corporation | 15906 |  | AAA | LB |  | Mandaon Port Development Project | Mandaon, Masbate | 2016-01-26 | 1st | DOTC | LF | 86.517 | 300 | 2015-05-19 | 2016-07-28 | 52.35 | O | 0.358 | 0.3 | 0.15 | 0.03 | 0.07 | 0.05 | 95.8 | -
Sunwest Construction & Development Corporation | 15906 |  | AAA | LB |  | Bicol (New Legaspi) Int'l Airport Development Project | Daraga, Albay | 2016-01-28 | 4th | DOTC | LF | 778.622 | 979 | 2013-11-12 | 2016-10-05 | 8.2 | O | 0.358 | 0.3 | 0.15 | 0.03 | 0.07 | 0.05 | 95.8 | -
Sunwest Construction & Development Corporation | 15906 |  | AAA | LB |  | Rehabilitation/ Upgrading of Damaged Wharf | Port of Tabaco, Tabaco City, Albay, Region V | 2016-05-27 | 1st | PPA | LF | 192.589 | 480 | 2015-07-31 | 2016-11-21 | -15.033 | O | 0.4 | 0.3 | 0 | 0.024 | 0.06 | 0.05 | 83.4 | -
Sunwest Construction & Development Corporation | 15906 | L | AAA | LB |  | Mandaon Port Development Project | Mandaon, Masbate/ Region V | 2016-04-27 | 2nd | DOTC | LF | 86.517 | 300 | 2015-05-19 | 2016-07-28 | 44.73 | O | 0.3715 | 0.3 | 0.15 | 0.02 | 0.042 | 0.05 | 93.35 | -
Sunwest Construction & Development Corporation | 15906 | L | AAA | LB |  | New Bicol Airport Development Project | Daraga, Albay/ Region V | 2016-04-28 | 5th | DOTC | LF | 778.622 | 979 | 2013-11-12 | 2016-10-05 | 0.17 | O | 0.3913 | 0.3 | 0.15 | 0.03 | 0.0467 | 0.05 | 96.8 | -
Sunwest Construction & Development Corporation | 15906 | L | AAA | LB |  | Legaspi Airport Development Project | Legaspi City/ Region V | 2016-04-29 | 1st | DOTC | LF | 17.593 | 180 | 2015-05-04 | 2016-07-09 | 11.35 | O | 0.3541 | 0.3 | 0.15 | 0.01 | 0.0311 | 0.05 | 89.52 | -
Sunwest Construction & Development Corporation | 15906 |  | AAA | LB |  | Construction of Mandaon Port | Mandaon, Masbate/ Region V | 2016-08-09 | 3rd & Final | DOTC | LF | 86.517 | 300 | 2015-05-19 | 2016-07-24 | 0 | C | 0.4926 | 0.2 | 0.3 | - | - | - | 99.26 | 96.44% Outstanding
Sunwest Construction & Development Corporation | 15906 |  | AAA | LB |  | Legazpi Airport Development Project | Legazpi City, Albay/Region V | 2016-08-10 | 2nd & Final | DOTC | LF | 17.593 | 180 | 2015-05-04 | 2016-06-19 | 0 | C | 0.4261 | 0.2 | 0.3 | - | - | - | 92.61 | 90.75% Very Satisfactory
Sunwest Construction & Development Corporation | 15906 |  | AAA | LB |  | New Bicol Airport Development Project | Daraga, Albay/ Region V | 2016-08-11 | 6th | DOTC | LF | 778.622 | 1038 | 2013-11-12 | 2016-12-03 | 0.29 | O | 0.3815 | 0.3 | 0.15 | 0.03 | 0.0467 | 0.05 | 95.82 | -
Sunwest Construction & Development Corporation | 15906 | L | AAA | LB |  | Rehabilitation/ Upgrading of Damaged Wharf | Port of Tabaco, Tabaco City, Albay, Region V | 2016-12-06 | 2nd | PPA | LF | 192.589 | 480 | 2015-07-31 | 2016-11-21 | -57.41 | O | 0.4 | 0.3 | 0 | 0.03 | 0.065 | 0.033 | 82.8 | -
Sunwest Construction & Dev't Corporation | 15906 | L | AAA | LB |  | Bicol (New Legaspi) Int'l Airport Development Project | Daraga, Albay | 2014-07-24 | 2nd & Final | DOTC | LF | 289.24 | 330 | 2009-08-05 | 2011-12-21 | 0 | C | 0.46 | 0.2 | 0.3 | - | - | - | - | 95.20% V. Satisfactory
Sunwest Construction & Dev't Corporation | 15906 | L | AAA | LB | GE1 | Bulan Airport Development Project | Bulan, Sorsogon | 2013-07-25 | Final | DOTC | L | 5.803 | 180 | 2009-07-17 | 2010-01-12 | 0 | C | 0.44 | 0.2 | 0.3 | - | - | - | 94 | 93.70% V. Satisfactory
Sunwest Construction & Dev't Corporation | 15906 | L | AAA | LB | GE5 | Dapdap Port Development Project | Brgy. Dapdap, Legaspi City/ Region V | 2013-09-03 | Final | DOTC | L | 13.971 | 135 | 2013-03-12 | 2013-07-24 | 0 | C | 0.425 | 0.2 | 0.3 | - | - | - | 92.5 | *92.50% V. Satisfactory
Sunwest Construction & Dev't Corporation | 15906 | L | AAA | LB | GE1 | Bicol (New Legaspi) Int'l Airport Development Project | Daraga, Albay | 2013-07-24 | Final | DOTC | L | 289.188 | 330 | 2009-12-10 | 2010-11-04 | 0 | C | 0.433 | 0.2 | 0.3 | - | - | - | 93.3 | 94.30% V. Satisfactory
Sunwest Construction & Dev't Corporation | 15906 | L | AAA | LB | GE5 | Construction of R. C. Wharf | Port of Legaspi, Legaspi City, Region IV | 2013-08-16 | 3rd & Final | PPA | L | 83.351 | 334 | 2012-02-23 | 2013-01-16 | 0 | C | 0.5 | 0.2 | 0 | - | - | - | 70 | 82.49% Satisfactory
Sunwest Construction and Development Corporation (Formerly: Sunwest Construction & Supply) | 15906 |  |  |  |  | Bulan Airport Development Project (Apron Expansion, Runway Extension, Continuation of Concrete Paving of Runway and Construction of Terminal Building) |  | 2010-07-15 |  | DOTC |  | 57.802 | 180 |  |  |  | O | 0.378 | 0.3 | 0.15 | 0.03 | 0.047 | 0.05 | 95.5 | -
Sunwest Construction and Development Corporation (Formerly: Sunwest Construction & Supply) | 15906 |  |  |  |  | Bicol (New Legaspi) Int'l Airport Development Project (Continuation of Construction of Airstrip) |  | 2010-07-16 |  | DOTC |  | 289.188 | 330 |  |  |  | O | 0.351 | 0.3 | 0.15 | 0.03 | 0.07 | 0.05 | 95.1 | -
Sunwest Construction and Development Corporation (Formerly: Sunwest Construction & Supply) | 15906 |  |  |  |  | Bicol (New Legaspi) Int'l Airport Development Project (Construction of Airstrip) |  | 2010-07-16 |  | DOTC |  | 289.24 | 330 |  |  |  | O | 0.347 | 0.3 | 0.15 | 0.03 | 0.07 | 0.05 | 94.7 | -
Sunwest Construction and Development Corporation (Formerly: Sunwest Construction & Supply) | 15906 |  |  |  |  | Pio Duran Port Development Project |  | 03/9-12/10 |  | PPA |  | 60.399 | 300 |  |  |  | O | 0.389 | 0.3 | 0.15 | 0.03 | 0.056 | 0.05 | 97.5 | -
Sunwest Construction and Development Corporation (Formerly: Sunwest Construction & Supply) | 15906 |  |  |  |  | Construction of Puro Rock Causeway |  | 2010-05-28 |  | V |  | 48.088 | 270 |  |  |  | O | 0.381 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 90.1 | -
Sunwest Construction and Development Corporation (Formerly: Sunwest Construction & Supply) | 15906 |  |  |  |  | Asphalt Overlay Topas-Palsong Road |  | 2010-02-27 |  | V |  | 47.767 | 190 |  |  |  | O | 0.359 | 0.24 | 0.15 | 0.03 | 0.045 | 0.05 | 87.4 | -
Sunwest Construction and Development Corporation (Formerly: Sunwest Construction & Supply) | 15906 |  |  |  |  | Asphalt Overlay of Palsong-Balaogan Road |  | 2010-02-27 |  | V |  | 47.768 | 148 |  |  |  | O | 0.337 | 0.238 | 0.15 | 0.03 | 0.045 | 0.05 | 85 | -
Sunwest Construction and Development Corporation (Formerly: Sunwest Construction & Supply) | 15906 |  |  |  |  | Asphalt Overlay of Balaogan-Casugad Road |  | 2010-02-27 |  | V |  | 4.767 | 149 |  |  |  | O | 0.354 | 0.239 | 0.15 | 0.03 | 0.045 | 0.05 | 86.8 | -
SUNWEST CONSTRUCTION AND DEVELOPMENT CORP. (Formerly: Sunwest Construction and Supply) | 15906 | L | AAA | LB | GE | Replacement of Permanent Weak Bridge, Bagacay Bridge along Jct. Gubat-Prieto Diaz Road, Bagacay, Gubat, Sorsogon | Bagacay, Gubat, Sorsogon | 2015-09-02 | 1st | Sorsogon Second | LF | 26.843 | 198 | 2015-05-09 | 2015-11-22 | -7.65% | O | 0.368 | 0.274 | 0.073 | 0.03 | 0.06 | 0.017 | 82.2% | -
Sunwest Construction and Development Corporation | 15906 | L | AAA | MB | GE | Legazpi Urban Draiange Improvement Project (Const./Impvt. Of Dike at Macabalo River) | Legazpi City, Albay | 2014-08-16 | Final | V | LF | 141.021 | 501 | 2014-01-14 | 2015-05-29 | 0 | C | 0.35 | 0.2 | 0.3 |  |  |  | 85 | 86.14% Satisfactory
Sunwest Construction and Development Corporation | 15906 | L | AAA | LB | GE1 | Reconst./Rehab. of Damaged Paved Nat'l. Rd. (Intermittent Sect.) Daang Maharlika | Baao, Camarines Sur | 2013-03-20 | Final | V | LF | 111.849 | 270 | 2012-08-06 | 2013-05-02 | 20.37 | C | 0.344 | 0.2 | 0.3 | - | - | - | 84.4 | 86.14% Satisfactory
Sunwest Construction and Development Corporation | 15906 | L | AAA | LB | GE1 | Upgrading of Balud-Milagros-Aroroy Road (San Pablo Sect.) | Masbate | 2011-08-09 | 1st | V | LF | 99.999 | 390 | 2010-11-23 | 2011-12-17 | 1.87 | O | 0.383 | 0.237 | 0.15 | 0.03 | 0.056 | 0.05 | 90.6 | -
Sunwest Construction and Development Corporation | 15906 | L | AAA | LB | GE1 | Upgrading of Balud-Tawad-Milagros-Aroroy Road (Paraiso Section) | Masbate | 2011-08-09 | 2nd | V | LF | 96.193 | 390 | 2010-11-23 | 2011-12-17 | 0.68 | O | 0.374 | 0.238 | 0.15 | 0.03 | 0.061 | 0.033 | 88.6 | -
Sunwest Construction and Development Corporation | 15906 | L | AAA | LB | GE5 | Passenger Terminal Building | Port of Legazpi, Legazpi City, Region IV | 2013-02-15 | Final | PPA | LF | 55.873 | 427 | 2011-08-25 | 2012-10-24 | - | C | 0.474 | 0.2 | - | - | - | - | 67.4 | 85.39% Satisfactory
Sunwest Construction and Development Corporation | 15906 | L |  |  | GE5 | Construction of Passenger Terminal Building | Port of Legazpi, Legazpi City, Albay | 2012-11-30 | 2nd | PPA | LF | 55.195 | 360 | 2011-08-25 | 2012-10-24 | - | O | 0.3993 | 0.2962 | 0.15 | 0.03 | 0.056 | 0.03 | 96.15 | -
Sunwest Construction and Development Corporation | 15906 | L | AAA | LB | GE5 | Proposed Passenger Terminal Building | Port of Legazpi, Legazpi City, Albay, Region IV | 2012-07-20 | 1st | PPA | LF | 55.195 | 427 | 2011-08-25 | 2012-08-18 | -7.391 | O | 0.3927 | 0.2818 | 0.0761 | 0.03 | 0.07 | 0.05 | 90.06 | -
Sunwest Construction and Development Corporation | 15906 | L | AAA | LB | GE5 | Construction of R.C. Wharf | Port of Legazpi, Legazpi City, Region IV | 2013-02-15 | 2nd | PPA | LF | 83.082 | 299 | 2012-02-23 | 2012-12-17 | - | O | 0.4 | 0.3 | 0 | 0.03 | 0.06 | 0.05 | 84 | -
Sunwest Construction and Development Corporation | 15906 | L |  |  | GE5 | Construction of R.C. Wharf | Port of Legazpi, Legazpi City, Albay | 2012-11-30 | 1st | PPA | LF | 83.083 | 240 | 2012-02-23 | 2012-10-19 | - | O | 0.394 | 0.3 | 0.15 | 0.03 | 0.0525 | 0.05 | 97.65 | -
Sunwest Construction and Development Corporation (Formerly: Sunwest Construction and Supply) | 15906 | L | AAA | LB | GE | Completion of Sula Bridge Including Approach | Bagacay, Albay | 2014-11-07 | 1st & Final | V | LF | 37.5586 | 186 | 2013-09-30 | 2014-04-03 | 1.62% | C | 0.468 | 0.133 | 0.3 | - | - | - | 90.1% | 90.1% Very Satisfactory
Sunwest Construction and Development Corporation (Formerly: Sunwest Construction and Supply) | 15906 | L | AAA | MB | GE2 | Legazpi Urban Drainage Impv't. Proj. (Const./Impv. Of Dike @ Macabalo River) | Legazpi City | 2013-08-14 | 1st | V | LF | 141.207 | 334 | 2013-01-14 | 2013-12-13 | -5.85 | O | 0.374 | 0.285 | 0.092 | 0.03 | 0.055 | 0.033 | 86.9
Sunwest Construction and Development Corporation (Formerly: Sunwest Construction and Supply) | 15906 | L | AAA | LB | GE1 | Upgrading of Balud-Tawad-Milagros-Aroroy Road (Paraiso Section), 2nd District | Masbate | 2011-04-13 | 1st | V | LF | 96.193 | 390 | 2010-11-23 | 2011-12-17 | -3.015 | O | 0.326 | 0.3 | 0.12 | 0.03 | 0.056 | 0.05 | 88.2 | -
Sunwest Construction and Development Corporation (Formerly: Sunwest Construction and Supply) | 15906 | L | AAA | LB | GE1 | Const. of San Isidro Bridge | Legazpi City | 2011-03-30 | 1st | V | LF | 48.031 | 397 | 2010-03-01 | 2011-04-02 | -4.06 | O | 0.325 | 0.3 | 0.109 | 0.03 | 0.065 | 0.033 | 86.2 | -
Sunwest Construction and Development Corporation/Hi-tone Construction and Development Corporation (JV) | JV-13-200 | L | AAA | LB | GE | Rehab./Reconst./Replacement/Retrofitting of Existing Pemanent Bridge; Bascaran Bridge along Daang Maharlika | Camalig, Albay | 2014-08-15 | 1st | V | LF | 28.3478 | 227 | 2014-02-11 | 2014-09-25 | 4.45 | O | 0.333 | 0.271 | 0.15 | 0.02 | 0.047 | 0.05 | 87.1
SUPREME ABF CONST. & CONST. SUPPLY COMPANY, INC. | 25226 | L | A | MB | GE | Rehab/Major Repair of Permanent Bridge 1) Daisug Bridge, Km. 1760+461; 2) Napisik Bridge, Km. 1774+580 and 3) Tipan Daku Bridge, Km. 1753+853, Oroquieta City-Calamba Mt. Road, Oroquieta City-Calamba Mt. Road | Oroquieta City-Calamba Mt. Road | 2015-09-01 | Final | Misamis Occidental 1st DEO | LF | 10.186 | 148 | 2015-03-02 | 2015-07-27 | 0.65% | C | 0.421 | 0.197 | 0.3 | - | - | - | 91.8% | *91.80% Very Satisfactory
SUPREME ABF CONSTRUCTION & CONSTRUCTION | JV-14-529 | L | A | MA | GE | Construction of Flood Control Structure along Himoga-an River | Sagay City, Negros Occidental | 2015-08-25 | 1st | Negros Occidental 1st | LF | 36.854 | 321 | 2015-02-13 | 2015-12-30 | 19.24% | O | 0.36 | 0.237 | 0.15 | 0.03 | 0.056 | 0.05 | 88.3% | -
Supreme ABF Construction & Construction Company, Inc./Genetian Builders (JV) | JV-13-623 | L | A | MB | GE | Construction of Bridges, Lower Landing Bridge along Mahayag-Dumingag-Siayan Road, Zamboanga del Sur | Zamboanga del Sur | 2014-10-27 | 1st | IX | LF | 23.324 | 190 | 2014-05-28 | 2014-12-03 | 6.36% | O | 0.4 | 0.24 | 0.15 | 0.03 | 0.03 | 0.017 | 86.7% | 86.7% Satisfactory
Supreme ABF Construction & Construction Supply Company | 25226 | L | A | MB | GE1 | Rd. Upgrading (Gravel to Concrete) along Dualing-New Panay-Midsayap Rd., New Leon Sect., Cotabato a)Km.1701+(421)-Km.1702+527.50; b)Km.1704+292-Km.1704+540, New Leon Sect. | Cotabato | 2013-08-12 | 1st | XII | LF | 43.485 | 170 | 2013-03-06 | 2013-08-22 | 2.67 | O | 0.324 | 0.3 | 0.15 | 0.03 | 0.06 | 0.033 | 89.7
SUPREME ABF CONSTRUCTION & CONSTRUCTION SUPPLY COMPANY , INC./SILVERGRACES CONSTRUCTION AND CONSTRUCTION SUPPLY | JV-13-274 | L | A | MA | GE | Construction of Flood Control Structure & Drainage | Victorias City, Negros Occidental | 2015-06-12 | Final | Negros First DEO | LF | 49 | 334 | 2014-02-24 | 2015-01-23 | 0% | C | 0.397 | 0.134 | 0.3 | - | - | - | 83.1% | *83.1% Satisfactory
SUPREME ABF CONSTRUCTION & CONSTRUCTION SUPPLY COMPANY INC./TSD BUILDERS CONSTRUCTION AND SUPPLY JOINT VENTURE | 0 | L | A | MA | GE | Construction of Flood Control Structure along Himoga-an River, Sagay City, Negros Occidental | Sagay City, Negros Occidental | 2015-11-19 | Final | Negros Occidental 1st DEO | LF | 36.8535 | 321 | 2015-02-13 | 2015-12-30 | (+)27.96% | C | 0.442 | 0.144 | 0.3 | - | - | - | 88.6% | 88.42% Satisfactory
Supreme ABF Construction & Construction Supply Company, Inc. | 25226 | L | A | MB | GE | Road Upgrading (Gravel to Concrete) along Dualing - New Panay - Midsayap Road, New Leon Section Cotabato A) Km.1701+(-421) - Km.1702+527.50 B) Km.1704+290 - Km.1704+540 | Aleosan, Cotabato | 2014-08-11 | Final | XII | LF | 43.485 | 170 | 2013-03-06 | 2013-08-02 | 0 | C | 0.474 | 0.133 | 0.3 |  |  |  | 90.7 | 90.10% Very Satisfactory
Supreme ABF Construction & Construction Supply Company, Inc. | 25226 | L | A | MA | GB | Construction of Standard One-Storey (3 CL) School Building at San Jose Elementary School | Kabankalan City, Negros Occidental | 2014-10-24 | 1st & Final | VI | LF | 2.7097 | 74 | 2014-07-15 | 2014-09-26 |  | C | 0.487 | 0.133 | 0.3 | - | - | - | 92% | 92% Very Satisfactory
Supreme ABF Construction & Construction Supply Company, Inc. | 25226 | L | A | MB | GE | Road Widening along Aklan West Road (Junction Nabas-Kalibo/Numancia Boundary Road Section), K0265+280 - K0268+330 | Kalibo, Aklan | 2014-10-30 | 1st | VI | LF | 30.5707 | 299 | 2014-01-27 | 2014-11-21 | 2.43% | O | 0.355 | 0.206 | 0.15 | 0.03 | 0.055 | 0.05 | 84.6% | 84.6% Satisfactory
Supreme ABF Construction & Construction Supply Company, Inc. | 25226 | L | A | MA | GE | Construction of River Control (Revetment Wall) along Aklan River Brgy. Biga-a | Malinao, Aklan | 2014-10-30 | 1st & Final | VI | LF | 43.1874 | 274 | 2014-01-27 | 2014-10-27 |  | C | 0.447 | 0.133 | 0.3 | - | - | - | 88% | 88% Satisfactory
Supreme ABF Construction & Construction Supply Company, Inc. | 25226 | L | A | MB | GE | Upgrading of Baclayon - Corella Road Leading the Philippine Tarsier and Wildlife Sanctuary, K0253+930 to K0259+100 | Bohol Province | 2014-10-26 | 1st | VII | LF | 114.7434 | 300 | 2014-05-02 | 2015-02-25 | -4.84% | O | 0.342 | 0.3 | 0.102 | 0.03 | 0.035 | 0.033 | 84.2% | 84.2% Satisfactory
Supreme ABF Construction & Construction Supply Company, Inc. | 25226 | L | A | MB | GE | Road Upgrading (Gravel to Paved) of Dolongon-Basey Road Chainage 1391-Chainage 2816 | Basey, Samar | 2014-10-25 | 1st | VIII | LF | 26.825 | 180 | 2014-03-10 | 2014-09-05 | -16.54% | O | 0.342 | 0.24 | 0 | 0.023 | 0.045 | 0.033 | 68.3% | 68.3% Poor
Supreme ABF Construction & Construction Supply Company, Inc. | 25226 | L | A | MB | GE | Completion of on going bridges (including approaches) Jaro, Iloilo City | Jaro, Iloilo City | 2014-08-04 | Final | VI | LF | 14.8646 | 210 | 2013-02-01 | 2013-06-30 | 0 | C | 0.417 | 0.2 | 0.3 |  |  |  | 91.7 | 89.42% Very Satisfactory
Supreme ABF Construction & Construction Supply Company, Inc. | 25226 | L | A | MA | GE | Road Upgrading of Isabela - Libas Negros Occidental Bdry. Road K0081+000 - K0083+000 | Isabela, Negros Occidental | 2014-08-07 | Final | VI | LF | 33.4137 | 203 | 2013-01-28 | 2013-08-18 | 0.3 | C | 0.395 | 0.2 | 0.3 |  |  |  | 89.5 | 82.12% Satisfactory
SUPREME ABF CONSTRUCTION & CONSTRUCTION SUPPLY COMPANY, INC. | 25226 | L | A | MB | GE | Concreting of Parpagoha (Marigondon)- Binoog Road, a. K0019+246- K0020+023, K0020+126-K0020+410, K0020+623-K0021+440.18 with exception | Tablas Island, Romblon | 2015-06-10 | Final | Romblon DEO | LF | 44.953 | 300 | 2014-03-28 | 2015-01-21 | 0% | C | 0.452 | 0.133 | 0.3 | - | - | - | 88.5% | *88.5% Satisfactory
SUPREME ABF CONSTRUCTION & CONSTRUCTION SUPPLY COMPANY, INC. | 25226 | L | A | MB | GE | Construction of Poblacion, Makato Revetment Wall | Makato, Aklan | 2015-06-05 | 1st | Aklan DEO | LF | 46.188 | 214 | 2015-03-06 | 2015-10-05 | 0.73% | O | 0.299 | 0.255 | 0.15 | 0.03 | 0.06 | 0.05 | 84.4% | -
SUPREME ABF CONSTRUCTION & CONSTRUCTION SUPPLY COMPANY, INC. | 25226 | L | A | MB | GE | Upgrading of Baclayon-Corella Road Leading the Philippines Tarsier and Wildlife Sanctuary, K0253+930 to K0259+100, Bohol Province | Baclayon-Corella Road, Bohol Province | 2015-06-03 | Final | Regional Office No. VII | LF | 114.743 | 354 | 2014-05-02 | 2015-04-20 | 0% | C | 0.415 | 0.144 | 0.3 | - | - | - | 85.9% | *84.88% Satisfactory
SUPREME ABF CONSTRUCTION & CONSTRUCTION SUPPLY COMPANY, INC. | 25226 | L | A | MB | GE | Rehabilitation/Major Repair of Permanent Bridge 1) Daisug Bridge 1. Km. 1760+461: 2. Napisik Bridge Km. 1774+580 & 3. Tipan Daku Bridge Km. 1753+853, Oroquieta City-Calamba Mt. Road | Oroquieta City-Calamba Mt Road | 2015-06-04 | 1st | Misamis Occidental First DEO | LF | 4.442 | 148 | 2015-03-02 | 2015-07-27 | - | O | 0.379 | 0.3 | 0.15 | 0.02 | 0.035 | 0.05 | 93.4% | -
SUPREME ABF CONSTRUCTION & CONSTRUCTION SUPPLY COMPANY, INC. | 25226 | L | A | MA | GE | Construction/Rehabilitation Of Flood Control Structure along Daang Maharlika, Poblacion Jiabong, Jiabong, Samar | Poblacion Jiabong, Jiabong, Samar | 2015-09-02 | 1st | Samar 2nd DEO | LF | 45.773 | 239 | 2015-02-11 | 2015-10-07 | (+)0.45 | O | 0.355 | 0.241 | 0.15 | 0.01 | 0.04 | 0.05 | 84.6% | -
SUPREME ABF CONSTRUCTION & CONSTRUCTION SUPPLY COMPANY, INC. | 25226 | L | A | MA | GE | Construction of Parpagoha River Control, San Andres, Romblon | San Andres, Romblon | 2015-09-04 | 1st & Final | Romblon DEO | LF | 40.757 | 250 | 2014-09-15 | 2015-05-22 | - | C | 0.443 | 0.133 | 0.3 | - | - | - | 87.6% | *87.6% Satisfactory
SUPREME ABF CONSTRUCTION & CONSTRUCTION SUPPLY COMPANY, INC./ R.A. CONSTRUCTION & GENERAL MERCHADISE JOINT VENTURE | 0 | L | A | MB | GE | Road Upgrading (Unpaved to Paved) of Dancalan-Candoni-Damutan Valley Road, K0134+000-K0138+780, K0139+000-K139+858, K0140+169-K0140+689, K0140+711-K0142+300, Candoni, Negros Occidental | Candoni, Negros Occidental | 2015-11-14 | 1st | Negros Occidental 3rd DEO | LF | 166.7292 | 380 | 2015-07-02 | 2016-07-15 | (+)1.13% | OG | 0.363 | 0.237 | 0.15 | 0.03 | 0.05 | 0.05 | 88% | 88% Satisfactory
SUPREME ABF CONSTRUCTION & CONSTRUCTION SUPPLY COMPANY, INC./EL JAKE BUILDERS JOINT VENTURE | JV-14-356 | L | C | MA | GE | Construction/Rehabilitation of Flood Control Structures at Cristanto M. Delos Reyes Avenue, Barangay Tamakan and Banay-Banay, Amadeo, Cavite (Package 03-2014, 6th Legislative District) | Amadeo, Cavite | 2015-11-12 | Final | CAVITE 2ND DEO | LF | 35.3868 | 182 | 2015-02-06 | 2015-08-06 | 0 | C | 0.49 | 0.133 | 0.3 | - | - | - | 92.3% | 92.3% Very Satisfactory
Supreme ABF Construction & Construction Supply Company, Inc./Redson Construction and Supplies Joint Venture | JV-13-273 | L | A | MA | GE | Construction of Flood Control Structure and Drainage System at Silay City | Negros Occidental | 2014-10-21 | 1st | VI | LF | 47.9314 | 304 | 2014-02-24 | 2014-12-24 |  | O | 0.368 | 0.245 | 0.15 | 0.023 | 0.047 | 0.05 | 88.3% | 88.3% Satisfactory
SUPREME ABF CONSTRUCTION & CONSTRUCTION SUPPLY, COMPANY, INC. | 25226 | L | A | MB | GE | Widening of National Road along Bacolod North Road, K0005+(-790)-K0006+157, S00025NR, Chainage 0-1255,Chainage 1320+1920, S00394NR, K0015+373 - K0015+700, K0025+500 - K0025+755, K0035+841 - K0036+135-K0036+135 - K0036+902, S00389NR, K0009+342 - K0010+000, K0011+050-K0011+981, Talisay City to Victorias City, Negros Occidental | Talisay City to Victorias City, Negros Occidental | 2015-11-18 | 1st | Regional Office, NIR | LF | 80.4644 | 255 | 2015-04-22 | 2016-01-01 | (+)7.79% | OG | 0.373 | 0.238 | 0.15 | 0.03 | 0.045 | 0.05 | 88.6% | 88.6% Satisfactory
SUPREME ABF CONSTRUCTION & CONSTRUCTION SUPPLY, COMPANY, INC. | 25226 | L | A | MB | GE | Widening of National Road Bacolod South Road (S00274NR), K0084+(-179) - K0084+497 & K0084+582 - K0085+340, Brgy. Binicuil, Kabankalan City, Negros Occidental | Brgy. Binicuil, Kabankalan City, Negros Occidental | 2015-11-14 | 1st | Negros Occidental 3rd DEO | LF | 21.7264 | 195 | 2015-07-06 | 2016-01-16 | (+)4.0% | OG | 0.35 | 0.237 | 0.15 | 0.022 | 0.04 | 0.05 | 84.9% | 84.9% Satisfactory
SUPREME ABF CONSTRUCTION & CONSTRUCTION SUPPLY, COMPANY, INC. | 25226 | L | A | MB | GE | Construction/Improvement of Flood Control and Drainage Structure along Jct. Bagonawa-La Castellana-Isabela Road (with exception), K0074+355 - K0078+500 B/S, Isabela, Negros Occidental | Isabela, Negros Occidental | 2015-11-16 | Final | Negros Occidental 2nd DEO | LF | 35.0272 | 124 | 2015-06-11 | 2015-10-12 | - | C | 0.417 | 0.133 | 0.3 | - | - | - | 85% | 85.96% Satisfactory
SUPREME ABF CONSTRUCTION AND CONST. SUPPLY COMPANY, INC. | 25226 | L | A | MA | GE | Construction of Drainage along Iznart-Ledesma-Molo Road, KO001+993-KO002+414, KO002+538-KO002+849, KO002+849-KO003+526, Iloilo City | Iloilo City | 2015-11-18 | 1st | Iloilo City | LF | 23.2683 | 188 | 2015-07-17 | 2016-01-21 | 0.40% | OG | 0.347 | 0.225 | 0.15 | 0.03 | 0.061 | 0.05 | 86.3% | 86.3% Satisfactory
Supreme ABF Construction and Construction Supply | 25226 | L | A | MB | GE1 | Completion of On-going Bridges (inc. Approaches) of Dungon Bridge along Mandurriao-Jaro Rd. | Jaro, Iloilo City | 2013-08-23 | 1st | VI | LF | 14.865 | 210 | 2013-02-01 | 2013-08-30 | 12.54 | O | 0.389 | 0.24 | 0.15 | 0.03 | 0.037 | 0.033 | 87.9
Supreme ABF Construction and Construction Supply | 25226 | L | A | MB | GE1 | Rd. Upgrading of Isabela-Libas Negros Occidental Bdry. Rd., K0081+000-K0083+000 | Isabela, Negros Occidental | 2013-08-10 | 2nd | VI | LF | 33.414 | 203 | 2013-01-28 | 2013-08-18 | -5.53 | O | 0.3 | 0.208 | 0.095 | 0.03 | 0.035 | 0.05 | 71.8
Supreme ABF Construction and Construction Supply | 25226 | L | A | MB | GE1 | Rd. Upgrading of Isabel-Libas Negros Occidental Bdry. Rd., K0081+000-K0083+000 | Isabela, Negros Occidental | 2013-03-12 | 1st | VI | LF | 33.414 | 203 | 2013-01-28 | 2013-08-18 | 37.85 | O | 0.307 | 0.249 | 0.15 | 0.015 | 0.055 | 0.05 | 82.6 | -
SUPREME ABF CONSTRUCTION AND CONSTRUCTION SUPPLY COMPANY, INC. | 25226 | L | A | MA | GE | Construction/Improvement of Flood Control and Drainage Along Jct. Bagonawa-La Castellana-Isabela Road, K0074+355 - K0078+500 B/S (with exception) Negros Occidental | Isabela, Negros Occidental | 2015-08-27 | 1st & Final | Negros Occidental 2nd | LF | 35.027 | 124 | 2015-06-11 | 2015-10-12 | 3.38% | C | 0.339 | 0.242 | 0.15 | 0.03 | 0.055 | 0.05 | 86.6% | *86.6% Satisfactory
T. M. Abad Construction | 9302 | L | B | SB |  | Pandan Port Development Project | Brgy. Pandan, Caoayan, Ilocos Sur | 2014-05-17 | 1st & Final | DOTC | LF | 4.789 | 75 | 2014-01-31 | 2014-04-15 | 0 | C | 0.446 | 0.2 | 0.3 | - | - | - | 94.6 | *94.60% V. Satisfactory
T. M. Abad Construction | 2272 | L |  |  | GB1 | Construction of Multi-Purpose Covered Court (Building) | Southville 4, Brgy. Kaingin, Sta. Rosa City, Laguna | 2011-04-01 | 1st | NHA | LF | 5.412 | 90 | 2011-02-12 | 2011-05-12 | 45.25 | O | 0.378 | 0.284 | 0 | 0.02 | 0.032 | 0 | 71.4 | -
T. Solomon Construction | 10046 | L | B | MA | GB1 | Const. of 2-Storey, 6-Cl RGR Type Sch. Bldg., Sta. Anastacia-San Rafael NHS, Brgy. San Rafael | Sto. Tomas, Batangas | 2013-08-01 | 1st | IVA | LF | 13.643 | 210 | 2013-04-10 | 2013-11-05 | 3.01 | O | 0.333 | 0.3 | 0.15 | 0.03 | 0.018 | 0.033 | 86.4
T. Solomon Construction & Development Corporation | 10046 | L | B | MA | GB | Construction of 2 Storey 6 Classroom RGR Type School Bldg, Sta. Anastacia-San Rafael NHS, Brgy. San Rafael, Sto. Romas, Batangas | Sto. Tomas, Batangas | 2014-08-09 | Final | IV-A | LF | 13.643 | 180 | 2013-04-10 | 2013-10-06 | 2.22 | C | 0.486 | 0.2 | 0.3 |  |  |  | 98.6 | 90.06% Very Satisfactory
T. Square Builders | 14268 | L | B | MA | GE | Widening of Digos Makar Road (KO1569+807 to KO1570+550), Hagonoy Section, Hagonoy | Davao del Sur | 2014-08-07 | 1st & Final | XI | LF | 18.9391 | 121 | 2014-02-05 | 2014-06-05 | 3.75 | C | 0.419 | 0.133 | 0.3 |  |  |  | 85.2 | 85.20% Satisfactory
T. Square Builders | 14268 | L | B | MA | GE1 | Rehab./Impv't. of Rd. Slip along Sarangani-Davao del Sur Coastal Rd., Nacolyael-Small Margus Sect., Km.1729+244-Km.1729+594 | Glan, Sarangani Province | 2013-08-20 | Final | XII | LF | 19.711 | 207 | 2012-12-16 | 2013-07-10 | 27.1 | C | 0.393 | 0.2 | 0.3 | - | - | - | 89.3 | 88.22% Satisfactory
T. Square Builders | 14268 | L | B | MA | GE2 | Const. of Lined Canal/Flood Control along Marbel-Makar Rd., Apopong Sect., Brgy. Apopong | General Santos City | 2013-08-23 | 1st | XII | LF | 17.323 | 213 | 2013-04-16 | 2013-11-14 | 11.57 | O | 0.338 | 0.24 | 0.15 | 0.022 | 0.047 | 0.033 | 83
T. Square Builders | 14268 | L | B | MA | GE1 | Conc. of Roads at La Fortuna Roads |  | 2009-05-29 | 1st | XI |  | 4.718 | 60 |  |  |  | O | 0.367 | 0.3 | 0.15 | 0.03 | 0.033 | 0.05 | 93 | -
T. SQUARE BUILDERS | 14268 | L | A | MA | GE | Construction of Lined Canal/Flood Control along Marbel-Makar (AH26), a)Km1655+600-Km 1656+510.4, Apopong Section | Brgy. Apopong, General Santos City | 2015-06-12 | 1st | South Cotabato 2nd DEO | LF | 17.664 | 147 | 2015-01-29 | 2015-06-24 | 0.13% | O | 0.321 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 84.1% | -
T. SQUARE BUILDERS | 14268 | L | A | MA | GE | Widening of National Roads: Coatabto-Marbel Road K1720+585-K1722+992, South Cotabato Modified to: MFO1- Widening of National Road along National Road 1 (N1) Daang Maharlika/Asian Highway 26-Cotabato-Marbel Road, K1720+585-K1722+240.40 | South Cotabato | 2015-06-02 | 1st | South Cotabato DEO | LF | 32.322 | 135 | 2015-04-01 | 2015-08-13 | 3.58% | O | 0.357 | 0.24 | 0.15 | 0.03 | 0.02 | 0.033 | 83% | -
T.E.L.O De Guzman Construction and Supply | 37151 | L | B | SB | GE | Road Concreting of Bagoladio - Itangon | Bula, Camarines Sur | 2014-08-10 | 1st & Final | V | LF | 4.6656 | 64 | 2014-03-21 | 2014-05-23 | 2.7 | C | 0.373 | 0.2 | 0.3 |  |  |  | 87.3 | 87.30% Satisfactory
T.J. Velasco Construction & Supply | 10560 | L | A | MA | GE1 | Impv't. of Major Intersections along Manila North Rd., Binalonan-Asingan-Sta. Maria Rd., K0190+(-247)-K0190+003, Binalonan Sect. | Binalonan, Pangasinan | 2013-08-09 | Final | I | LF | 6.717 | 110 | 2013-01-31 | 2013-05-20 | 0 | C | 0.488 | 0.133 | 0.3 | - | - | - | 92.1 | 91.20% V. Satisfactory
T.J. Velasco Construction & Supply | 10560 | L | A | MA | GE1 | Impv't. of Major Intersections along Manila North Rd., Binalonan-Asingan-Sta. Maria Rd., K0190+(-247)-K0190+003, Binalonan Sect. | Binalonan, Pangasinan | 2013-03-13 | 1st | I | LF | 6.717 | 80 | 2013-01-31 | 2013-04-20 | 3.5 | O | 0.355 | 0.3 | 0.15 | 0.023 | 0.045 | 0.033 | 90.6 | -
T.J. VELASCO CONSTRUCTION & SUPPLY | 10560 | L | A | MB | GE | Widening with Drainage of National Roads, Urdaneta Jct.-Dagupan-Lingayen Road, K0182+(-204)- K0185+000 with exception, Urdaneta City,Pangasinan | K0182+(-204)- K0185+000 with exception, Urdaneta City,Pangasinan | 2015-09-04 | 1st | Pangasinan 3rd DEO | LF | 44.131 | 240 | 2015-03-17 | 2015-11-12 | (+)1.21 | O | 0.382 | 0.221 | 0.15 | 0.03 | 0.037 | 0.05 | 87% | -
T.M. Abad Construction | 9302 | L | B | SB | GE-5 | Pulilan-Plaridel River Port Development Project | Brgy. Dampol, 2B, Pulilan and Brgy. Rueda, Plaridel, Bulacan | 2015-06-29 | 1st & Final | DOTC | LF | 5.124 | 90 | 2015-02-20 | 2015-05-20 | 0 | C | 0.434 | 0.2 | 0.3 | - | - | - | 93.4 | *93.40% V.Satisfactory
T.M. Abad Construction | 9302 | L | B | SB |  | Bantayan Airport Development Project | Bantayan Island, Cebu | 2016-08-22 | 1st & Final | DOTC | LF | 7.9678 | 60 | 2016-05-23 | 2016-07-21 | 0 | C | 0.383 | 0.2 | 0.3 | - | - | - | 88.3 | *88.3% Satisfactory
T.N.J Buhong Construction | 19687 | L | B | MA | GE1 | Widening/Conc. of Poblacion-Banaue-Brgy. Bangaan, Awaan-Banagan Section |  | 2009-03-06 | 2nd | CAR |  | 23.084 | 270 |  |  |  | O | 0.369 | 0.295 | 0.15 | 0.022 | 0.037 | 0.033 | #VALUE! | -
T.N.J Buhong Construction | 19687 | L | B | MA | GE1 | Widening/Conc. of Pob. Bnaue-Brgy. Bangaan, Banaue (Intermittent Sections from Awaan-Bangaan Sections) KM. 342+00-KM 354+045 (IS) |  | 2009-08-31 | 3rd | CAR |  | 23.084 | 457 |  |  |  | O | 0.335 | 0.24 | 0.15 | 0.03 | 0.056 | 0.033 | 84.4 | -
T.N.J Buhong Construction | 19687 | L | A | MA | GE1 | Widening/Conc. of Poblacion-Banaue-Brgy. Bangaan, Awaan-Banagan Section |  | 2008-11-16 | 1st | CAR |  | 23.123 | 270 |  |  |  | O | 0.268 | 0.126 | 0.07 | 0.008 | 0.03 | 0.033 | 53.5 | -
T.N.J. Buhong Construction | 19687 | L | B | MA | GE1 | Rd. Upgrading along Banaue-Hungduan-Benguet Bdry. Rd., K0364+365-K0367+980 (w/ exceptions) | Hungduan, Ifugao | 2013-08-04 | Final | CAR | LF | 40.77 | 344 | 2012-01-19 | 2012-12-27 | 0 | C | 0.454 | 0.133 | 0.3 | - | - | - | 88.7 | 88.94% Satisfactory
T.N.J. Buhong Construction | 19687 | L | B | MA | GE1 | Rd. Upgrading along Banaue-Hungduan-Benguet, K0348+380-K0353+549 | Tinoc, Ifugao | 2013-08-04 | Final | CAR | LF | 19.336 | 194 | 2012-01-31 | 2012-08-12 | 0 | C | 0.421 | 0.133 | 0.3 | - | - | - | 85.4 | 82.04% Satisfactory
T.N.J. Buhong Construction | 19687 | L | B | MA | GE1 | Rd. Upgrading along Banaue-Hungduan-Benguet Bdry. Rd., K0384+000-K0385+549 | Tinoc, Ifugao | 2012-08-05 | 1st | CAR | LF | 19.336 | 150 | 2012-01-31 | 2012-06-28 | -5 | O | 0.321 | 0.3 | 0.1 | 0.03 | 0.047 | 0 | 79.8 | -
T.Square Builders | 14268 | L | B | MA | GE2 | Rehab./Impv't. of Rd. Slip along Sarangani-Davao del Sur Coastal Rd., Nacolyaei-Small Margus Sect., Km.1729+244-Km.1729+594 | Glan, Sarangani Province | 2013-03-22 | 1st | XII | LF | 19.711 | 207 | 2012-12-16 | 2013-07-10 | 33.86 | O | 0.363 | 0.237 | 0.15 | 0.03 | 0.045 | 0.05 | 87.5 | -
T.Square Builders | 14268 | L | B | MA | GE1 | Road Upgrading (Gravel to Paved), Intermittent Sect., along Sarangani-Davao del Sur Rd., Km.1735+273-Km.1736+870 | Glan, Sarangani Province | 2013-03-22 | 1st | XII | LF | 40.192 | 182 | 2013-01-31 | 2013-07-31 | 3.19 | O | 0.355 | 0.234 | 0.15 | 0.03 | 0.05 | 0.033 | 85.2 | -
Tabada Construction & Supplies | 35997 | L | D | SB | GE | Construction of Road at Brgy. Pinana-an, Las Nieves, Agusan del Norte | Las Nieves, Agusan del Norte | 2014-10-29 | 1st & Final | XIII | LF | 3.4968 | 37 | 2014-09-19 | 2014-10-25 | 0% | C | 0.394 | 0.139 | 0.3 | - | - | - | 83.3% | 83.3% Satisfactory
TABADA CONSTRUCTION & SUPPLIES | 35997 | L | D | SB | GE | Construction/ Upgrading/ Rehabilitation of Drainage along Daang Maharlika (Surigao-Agusan Section) | K1191+300 to K1191+930, Santiago, Agusan Del Norte | 2015-06-02 | 1st | AGUSAN DEL NORTE DEO | LF | 4.749 | 87 | 2015-03-27 | 2015-06-21 | -4.99% | O | 0.32 | 0.3 | 0.1 | 0.03 | 0.045 | 0.033 | 82.8% | -
TABADA CONSTRUCTION & SUPPLIES | 35997 | L | D | SB | GE | Repair/Drainage Improvement of Butuan City-Cagayan de Oro City-Iligan City Road, Agusan-Misamis Road Section (K1262+000-K1266+000 With Exception) | Nasipit, Agusan del Norte | 2015-09-03 | 1st & Final | Agusan del Norte | LF | 11.302 | 105 | 2014-09-15 | 2014-12-28 | (+) 0.95% | C | 0.46 | 0.16 | 0.3 | - | - | - | 92% | *92% Very Satisfactory
TABADA CONSTRUCTION & SUPPLIES | 35997 | L | D | SB | GE | Construction/Upgrading/Rehabilitation of Drainage Along Butuan-Cagayan de Oro-Iligan (Agusan-Misamis Oriental Section), K1259+480 - K1260+263.80, Mantalio, Nasipit, Agusan del Norte | Mantalio, Nasipit, Agusan del Norte | 2015-11-19 | Final | Agusan del Norte DEO | LF | 1.8991 | 53 | 2015-03-27 | 2015-05-18 | - | C | 0.408 | 0.133 | 0.3 | - | - | - | 84.1% | 84.1% Satisfactory
TABADA CONSTRUCTION & SUPPLIES | 35997 | L | D | SB | GB | Completion/Rehabilitation of DPWH Building of Butuan City District Engineering Office, R. Palma Street, Butuan City | R. Palma Street, Butuan Cuty | 2015-11-18 | Final | Butuan City DEO | LF | 2.9731 | 120 | 2014-10-11 | 2015-02-07 | (+) 3.33 | C | 0.499 | 0.136 | 0.3 | 0 | - | - | 93.5% | 93.5% Very Satisfactory
Tacloban Ras Construction Corporation | 17184 | L | B | MA | GE1 | Repair/Rehab. of National Road along Jct. Taft-Arteche Road (Reblocking), Km. 891+802-Km. 921+000 w/ exception |  | 2009-06-08 | 1st | VIII |  | 7.645 | 95 |  |  |  | O | 0.224 | 0.24 | 0.15 | 0.03 | 0.045 | 0.033 | 72.2 | -
Tacloban Ras Construction Corporation | 17184 | L | B | MA | GE1 | Asphalt Overlay along Borongan-San Julian Road |  | 2009-06-09 | 1st | VIII |  | 9.553 | 138 |  |  |  | O | 0.371 | 0.24 | 0 | 0.03 | 0.035 | 0 | 67.6 | -
Tacloban Ras Construction Corporation | 17184 | L | B | MA | GE1 | Concreting of Sambulawan-Jct. Calaguise-Calubian Road |  | 2009-06-02 | 1st | VIII |  | 18.734 | 240 |  |  |  | O | 0.4 | 0.232 | 0.15 | 0.022 | 0.037 | 0.05 | 89.1 | -
Tacloban Ras Construction Corporation | 17184 | L | B | MA | GE1 | Conc. of Tabing-Kawayan-Sta. Rosa-Lawis-Tabango Road |  | 2009-09-05 | 1st | VIII |  | 18.737 | 240 |  |  |  | O | 0.367 | 0.245 | 0.15 | 0.018 | 0.04 | 0.033 | 85.3 | -
TAD CONSTRUCTION | 14098 | L | B | SB | GE | Construction of Farm to Market Road, Brgy. Isok II | Boac, Marinduque | 2015-11-16 | Final | Marinduque DEO | LF | 1.7952 | 41 | 2015-02-19 | 2015-03-31 | 0 | C | 0.44 | 0.19 | 0.3 | - | - | - | 93% | 93% Very Satisfactory
Tadian General Construction | 35339 | L | D | SB | GE | Const/Rehab of Drainage along Baguio-Bontoc Rd, Mt. Province-Ilocos Sur via Kayan Road (Tadian-Losong Section), Tadian (Drainage/Slope Protection); Const/Rehab of Drainage along Mt.Province Sur via Tue Road, Tadian | Mt. Province-Ilocos Sur Road via Kayan Tadian, Mt. Province | 2014-08-12 | 1st & Final | CAR | LF | 3.9999 | 71 | 2014-02-26 | 2014-05-07 | 0 | C | 0.475 | 0.133 | 0.3 |  |  |  | 90.8 | 90.80% Very Satisfactory
Tango Romeo General Construction | 18926 | L | B | MA | GE | Contract Package 6: Const/Imprvt of Access Road Leading to Airportsa, Seaports and Declared Tourism Destination, Road around Burnham Park, Baguio City: A) Lake Drive 1; B) Juan Luna Drive and C) Lake Drive 2 | Baguio City | 2014-08-15 | 1st & Final | CAR | LF | 14.2257 | 70 | 2014-03-10 | 2014-05-18 | 0 | C | 0.493 | 0.133 | 0.3 |  |  |  | 92.6 | 92.60% Very Satisfactory
TANGO ROMEO GENERAL CONSTRUCTION | 18926 | L | B | SB | GE | Construction/Upgrading/Rehabilitation of Drainage along National Roads: 1) Gov't Center Road (Baguio Road), Chainage 0000 to Chainage 0130, Chainage 0000 to Chainage 0216, Chainage 0000 to Chainage 0116; Gov't Center Cut-off Road, K0249+(-200) to K0249+200, Chainage 0080 to Chainage 0170; Harrison Road No. 2, Chainage 0000 to Chainage 0090; UP Drive, Chainage 0000 to Chainage 0088, Baguio City | Baguio City | 2015-09-04 | 1st & Final | Baguio City DEO | LF | 9.297 | 160 | 2015-02-05 | 2015-07-14 | 44.05% | C | 0.453 | 0.114 | 0.3 | - | - | - | 86.7% | *86.7% Satisfactory
TANTUCO CONSTRUCTION & TRADING CORPORATION | 7255 | L | A | MB | GE | Construction of Sariaya By-Pass including RROW, Sariaya, Quezon 2nd LD, Sampaloc 2 Section | Sariaya, Quezon | 2015-11-16 | 1st | North Manila DEO | LF | 46.3439 | 310 | 2014-05-05 | 2015-03-10 | 0.0018 | OG | 0.396 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 92.1% | 92.1% Very Satisfactory
Tantuco Construction & Trading Corporation (Formerly: Tantuco Lumber & Construction Supply) | 7255 | L | A | MA | GE1 | Const. of Eco-Tourism Rd. (LUC-BATCR) Phase III inc. RROW, Ilayang Talim-Isabang Sect. | Lucena City | 2013-08-03 | 1st | IVA | LF | 41.815 | 160 | 2013-06-07 | 2013-11-13 | 2.72 | O | 0.266 | 0.298 | 0.15 | 0.03 | 0.042 | 0.05 | 83.6
Tantuco Construction & Trading Corporation (Formerly: Tantuco Lumber & Construction Supply) | 7255 | L | A | MA | GE1 | Road Opening of Quezon Eco-Tourism Rd. (LUC-BATCR) inc. RROW at Salinas Sect. | Lucena City | 2013-03-16 | Final | IVA | LF | 38.635 | 281 | 2012-04-11 | 2013-01-16 | 1.51 | C | 0.42 | 0.133 | 0.3 | - | - | - | 85.3 | 85.90% Satisfactory
Tantuco Construction Trading Corporation | 7255 | L | A | MA | GE | Quezon Eco-Tourism Road (Lucena City-Batangas Coastal Road) Phase III, Concreting of Eco-Tourism Coastal Road (Section III), Talaan-Bocohan Section, K0142+343.50 to K0144+803 | Sariyaya, Quezon | 2014-08-13 | 1st | IV-A | LF | 43.1286 | 250 | 2014-05-29 | 2015-02-02 | 15.88 | O | 0.337 | 0.3 | 0.15 | 0.015 | 0.051 | 0.05 | 90.3
TAPNIO AND TAN CONSTRUCTION & DEVELOPMENT CORP. | 10798 | L | B | MA | GB | Construction of 4-Storey, 8-Classroom Bulding at Toro Hills Elementary School, Quezon City | Quezon City | 2014-06-02 | 1st | Quezon City 1st DEO | LF | 14.357 | 240 | 2015-01-12 | 2015-09-08 | (+) 2.41 | O | 0.371 | 0.251 | 0.15 | 0.015 | 0.046 | 0.05 | 88.3% | -
Tapnio and Tan Construction & Development Corporation | 10798 | L | B | MA | GB1 | Const. of Three (3) Sch. Bldgs., Nine (9) Cl at Sampaguita ES | Caloocan City | 2013-08-13 | 1st | NCR | LF | 12.545 | 210 | 2013-03-27 | 2013-10-22 | 1.87 | O | 0.282 | 0.24 | 0.15 | 0.03 | 0.058 | 0.05 | 81
Tapnio and Tan Construction & Development Corporation | 10798 | L | B | MA | GB1 | Const. of 4 storey 12 Cl. at Toro Hills, E/S | Quezon City | 2013-08-02 | 1st | NCR | LF | 22.612 | 180 | 2013-03-27 | 2013-09-22 | 14.4 | O | 0.298 | 0.24 | 0.15 | 0.03 | 0.041 | 0.033 | 79.2
Tapnio and Tan Construction & Development Corporation | 10798 | L | B | MA | GB | Construction of 4 Storey Eight (8) Classroom Building at Masambong H/S, Quezon City | Quezon City | 2014-08-14 | 1st & Final | NCR | LF | 15.4369 | 180 | 2013-09-09 | 2014-03-07 | 0 | C | 0.467 | 0.133 | 0.3 |  |  |  | 90 | 90.00% Very Satisfactory
Tarifa Construction & Supplies | 33239 | L | D | SB | GB1 | Construction of Multi-Purpose Building at Brgy. Palacpalac |  | 2009-02-27 | 1st | III |  | 2.361 | 75 |  |  |  | O | 0.205 | 0.239 | 0.15 | 0.03 | 0.035 | 0.05 | #VALUE! | -
Teckcon Construction | 33214 | L | B | SB | GE1 | Restoration of Mt. Province Bdry.-Calanan-Pinukpuk-Abbut Road K0424+900-K0483+040 | Kalinga | 2012-03-20 | 1st | CAR | LF | 10.467 | 120 | 2012-01-02 | 2012-04-30 | 2 | O | 0.358 | 0.23 | 0.15 | 0.03 | 0.035 | 0.033 | 83.6 | -
Teddie Construction and Development Corporation | 6313 |  | A |  |  | Land Development of Zamboanga City Region IX Phase I | Brgy. Tulungatong, Zamboanga City Region IX | 2016-03-04 | Final | NHA | LF | 23.711 | 240 | 2013-04-13 | 2015-08-27 | 5.13 | C | 0.4485 | 0.2 | 0.1416 | - | - | - | 79.01 | 87.91% Satisfactory
Teddie Construction Development Inc. | 6313 | L |  |  |  | Land Development of Zamboanga City Townsite | Tulungatong, Zamboanga City | 2014-01-10 | 1st | NHA | LF | 23.71 | 240 | 2013-04-13 | 2014-04-07 | -0.6 | O | 0.3808 | 0.3 | 0.144 | 0.0225 | 0.055 | 0.0333 | 93.56
Teddie Construction Development Inc. | 6313 | L | A |  |  | Land Development of Zambaonga City Townsite | Tulungatong, Zamboanga City | 2014-01-10 | 1st | NHA | LF | 23.711 | 240 | 2013-04-13 | 2014-04-07 | -0.6 | O | 0.3808 | 0.3 | 0.144 | 0.0225 | 0.055 | 0.0333 | 93.56 | -
Teddie Construction Development Inc. | 6313 | L | A | MB | GE1 | Improvement/Rehabilitation of Gov. Camins road |  | 2009-05-26 | 1st | IX |  | 26.653 | 196 |  |  |  | O | 0.381 | 0.18 | 0 | 0.01 | 0.047 | 0 | 61.8 | -
Teddie Construction Development Inc. | 6313 | L | A | MB | GE1 | Improvement/Rehabilitation of Gov. Camins Road |  | 2009-09-02 | 2nd | IX |  | 26.653 | 227 |  |  |  | O | 0.383 | 0.3 | 0 | 0.03 | 0.055 | 0.033 | 80.1 | -
Teddie Construction Development Inc. | 6313 | L | A | MB | GE1 | Const. (New Opening) of Zamboanga West Coast Road, Sirawai-Sibuco Road, Bitugan-Tapanayan-Talabiga Section |  | 2008-08-19 | 1st | IX |  | 32.446 | 340 |  |  |  | O | 0.16 | 0.043 | 0 | 0.03 | 0.042 | 0.1 | 37.5 | -
Teddie Construction Development Inc. | 6313 |  |  |  |  | Const. of Flood Control along Davao-Cotabato Road at a) Sambas Section and b) Power Section |  | 2010-02-25 |  | XI |  | 4.723 | 90 |  |  |  | O | 0.354 | 0.239 | 0.15 | 0.03 | 0.045 | 0.05 | 86.8 | -
Teddie Construction Development Inc. | 6313 | L | A | MB | GE1 | Conc. of Montevista-Compostela-Mati Road, Liboton-Saddle Section |  | 2009-06-04 | 1st | XI |  | 50.96 | 300 |  |  |  | O | 0.4 | 0.3 | 0.15 | 0.02 | 0.033 | 0.033 | 93.6 | -
Teddie Construction Development Inc. | 6313 | L | A | MB | GE1 | Conc. of Montevista-Compostela-Mati Road, Liboton-Maddle Section |  | 2009-09-09 | 2nd | XI |  | 50.96 | 300 |  |  |  | O | 0.397 | 0.286 | 0.15 | 0.024 | 0.047 | 0.05 | 95.4 | -
Teddie Construction Development Inc./Wee Eng Const., Inc. (J.V.) | JV-07-116 | L | AAA | LB | GE1 | Zamboanga Airport Development Project |  | 2009-04-30 | 1st | DOTC |  | 105.729 | 300 |  |  |  | O | 0.398 | 0.3 | 0.15 | 0.02 | 0.054 | 0.033 | 95.5 | -
Teddie Construction Development, Inc. | 6313 | L | A | MB | GE | Widening of Zamboanga City-Libuan-Limpapa Road, K1950+093 to K1957+540 (w/ exception)(as per list) modified to: K1950+080 to K1956+640 | Zamboanga City | 2014-10-21 | 1st | IX | LF | 42.2705 | 240 | 2014-04-23 | 2014-12-18 | 0.24% | O | 0.366 | 0.236 | 0.15 | 0.03 | 0.045 | 0.033 | 86% | 86% Satisfactory
Teddie Construction Development, Inc. | 6313 | L | A | MB | GE1 | Asphalt Overlay/Repair & Rehab. of Basilan Circ. Rd. (Isabela-Lamitan Section) K1+248-K2+000 w/ exception | Isabela City, Basilan Province | 2013-03-13 | Final | IX | LF | 9.714 | 58 | 2012-10-04 | 2012-11-30 | 3.45 | C | 0.429 | 0.12 | 0.3 | - | - | - | 84.9 | 83.34% Satisfactory
TEDDIE CONSTRUCTION DEVELOPMENT, INC. | 6313 | L | A | MB | GE | Rehab./Replacement Retrofitting of Existing Permanent Bridge and Construction of New Permanent Bridge (PSCG) and Approaches at Maasin, Zamboanga City | Zamboanga City | 2015-06-11 | 1st | Zamboanga City DEO | LF | 21.872 | 296 | 2014-12-11 | 2015-10-02 | -8.93% | O | 0.384 | 0.24 | 0.061 | 0.03 | 0.04 | 0.05 | 80.5% | -
TEDDIE CONSTRUCTION DEVELOPMENT, INC. | 6313 | L | A | MB | GE | Widening of Zamboanga City-Labuan-Limpapa Rd., K1950+093-K1957+540 (with exception) (as per list) modified to: K1950+080-K1956+640, Zamboanga City | Zamboanga City | 2015-09-03 | 1st | Zamboanga City | LF | 40.59 | 492 | 2015-04-23 | 2016-08-26 | (+)14.23% | O | 0.317 | 0.3 | 0.15 | 0.03 | 0.051 | 0.05 | 89.8% | -
Teddie Construction Development, Inc./Wee Eng Construction, Inc. (JV) | JV-07-116 | L | AAA | LB | GE1 | Zamboanga Airport Development Project |  | 8/6-7/09 | 2nd | DOTC |  | 0.105 | 300 |  |  |  | O | 0.387 | 0.3 | 0.15 | 0.02 | 0.044 | 0.05 | 95.1 | -
The Steadfast Builders | 8176 | L | A | MA | GE | Construction of Local Roads - Sampaguita St. Brgy. Pembo, Cadena de Amor St. Brgy. Pembo, Maya St. & its Approaches, Brgy. Rizal, District II | Makati City, Metro Manila | 2014-11-19 | 1st | NCR | LF | 5.1231 | 150 | 2014-09-10 | 2015-02-06 | 0.91% | O | 0.382 | 0.219 | 0.15 | 0.0225 | 0.045 | 0.033 | 85.15% | 85.15% Satisfactory
The Steadfast Builders | 8176 | L | A | MA | GE1 | Rehab./Reconst./Upgading of Felix Ave. (Formerly Imelda Ave.) |  | 2009-05-18 | 1st | IV-A |  | 38.426 | 180 |  |  |  | O | 0.389 | 0.24 | 0.15 | 0.03 | 0.025 | 0.05 | 88.4 | -
THE STEADFAST BUILDERS | 8176 | L | A | MA | GE | Drainage Improvement along Chino Roces Avenue, District I, Makati City | Makati City | 2015-06-11 | 1st | Metro Manila 2nd DEO | LF | 17.911 | 120 | 2015-03-10 | 2015-07-07 | (+) 0.28 | O | 0.397 | 0.24 | 0.15 | 0.022 | 0.056 | 0.05 | 91.5% | -
The Tuscan Structures & Supplies | 18257 | L | A | MA | GE1 | Concrete Paving of Biliran Circumferential Road, Look-Habuhab Section |  | 2009-06-04 | 1st | VIII |  | 19.16 | 200 |  |  |  | O | 0.356 | 0.24 | 0.15 | 0.03 | 0.037 | 0.033 | 84.6 | -
The Tuscan Structures & Supplies | 18257 | L | A | MA | GE1 | Concrete Paving of Biliran Circ. Road, (Look-Habuhab Sect.) |  | 2009-09-03 | 2nd | VIII |  | 19.16 | 200 |  |  |  | O | 0.337 | 0.24 | 0.15 | 0.03 | 0.05 | 0.033 | 84 | -
The Tuscan Structures & Supplies | 18257 | L | A | MA | GE1 | Concrete Paving of Biliran Circumferential Road, Guindapunan-Pinamihagan Section |  | 2009-06-04 | 1st | VIII |  | 19.155 | 200 |  |  |  | O | 0.311 | 0.24 | 0.15 | 0.03 | 0.037 | 0.033 | 80.1 | -
The Tuscan Structures & Supplies | 18257 | L | A | MA | GE1 | Concrete Paving of Biliran Circ. Road, (Guindapunan-Pinamihagan Sect.) |  | 2009-09-03 | 2nd | VIII |  | 19.155 | 200 |  |  |  | O | 0.344 | 0.24 | 0.15 | 0.03 | 0.05 | 0.033 | 84.7 | -
The Tuscan Structures & Supplies | 18257 | L | A | MA | GE1 | Concrete Paving of Biliran Circ. Road, (Bilwang-Mapuyo Section) |  | 2009-09-03 | 1st | VIII |  | 19.142 | 200 |  |  |  | O | 0.348 | 0.256 | 0.15 | 0.006 | 0.045 | 0.033 | 83.8 | -
The Tuscan Structures & Supplies | 18257 | L | A | MA | GE1 | Concrete Paving of Biliran Circ. Road, Tomalistis-Cabibihan Sect. | Caibiran, Biliran Province | 2012-03-22 | Final | VIII | LF | 8.959 | 257 | 2010-12-17 | 2011-08-31 | -0.01 | C | 0.404 | 0.133 | 0.299 | - | - | - | 83.6 | 84.05% Satisfactory
The Tuscan Structures & Supplies | 18257 | L | A | MA | GE | Construction of Drainage Sydtem along Naval-Caibiran CCR to Include Payment of RROW Damages, Km. 1026+800-Km.1028+000 with exceptions | Biliran Province | 2014-10-27 | 1st & Final | VIII | LF | 11.138 | 228 | 2014-02-06 | 2014-09-21 | 0% | C | 0.422 | 0.133 | 0.3 | - | - | - | 85.5% | 85.5% Satisfactory
The Tuscan Structures & Supplies | 18257 | L | A | MA | GE1 | Concrete Paving of Biliran Circ. Rd., Km.1089+100-Km.1096+640 w/ exceptions (San Agustin-Pawikan Rd. Sect.) | Biliran Province | 2013-03-12 | 1st | VIII | LF | 43.665 | 180 | 2013-02-07 | 2013-08-06 | 1.67 | O | 0.311 | 0.232 | 0.15 | 0.03 | 0.05 | 0.033 | 80.6 | -
The Tuscan Stuctures & Supplies | 18257 |  |  |  |  | Conc. Paving of Biliran Circ. Road (Masagaosao-Bulalacao Section) |  | 2010-08-26 |  | VIII |  | 24.915 | 340 |  |  |  | O | 0.356 | 0.236 | 0.15 | 0.03 | 0.047 | 0.033 | 85.2 | -
Three W Builders Inc. | 10722 | L | AAA | LB | GE1 | Const. of Pamasilan I Bridge | Magallanes, Cavite | 2011-08-18 | 1st | IVA | LF | 38.572 | 197 | 2011-02-14 | 2011-08-29 | 7 | O | 0.348 | 0.183 | 0.15 | 0.03 | 0.04 | 0.05 | 80.1 | -
Three W Builders Inc. / Sophia Construction and Supply (JV) | JV-12-258 | L | AAA | LB | GE | Road Upgrading (Gravel to Concrete) along Awang - Upi - Lebak - Kalamansig - Palimbang - Sarangani Road, Km.2036+815 to Km.2038+414 with exception | Palimbang, Sultan Kudarat | 2014-08-14 | 1st & Final | XII | LF | 34.6814 | 123 | 2014-02-19 | 2014-06-21 | 32.52 | C | 0.441 | 0.189 | 0.3 |  |  |  | 93 | 93.00% Very Satisfactory
Three W Builders Inc. / Sophia Construction and Supply (JV) | JV-12-258 | L | AAA | LB | GE | Road Upgrading (Gravel to Concrete) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standard (HDM-4 Project Analysis) along Awang-Upi-Lebak - Kalamansig - Palimbang - Sarangani Road, Km.2041+691 - Km. 2043+919 with exception | Palimbang, Sultan Kudarat | 2014-08-14 | Final | XII | LF | 46.021 | 196 | 2013-04-02 | 2013-10-15 | 8.43 | C | 0.44 | 0.2 | 0.3 |  |  |  | 94 | 90.28% Very Satisfactory
Three W Builders Inc. / Sophia Construction and Supply (JV) | JV-12-258 | L | AAA | LB | GE1 | Rd. Upgrading (Gravel to Concrete) along Awang-Upi-Lebak-Kalamansig-Palimbang-Sarangani Rd., Km.2041+691-Km.2043+919 w/ exception | Palimbang, Sultan Kudarat | 2013-08-18 | 1st | XII | LF | 46.021 | 181 | 2013-04-02 | 2013-09-29 | 13.77 | O | 0.384 | 0.236 | 0.15 | 0.024 | 0.051 | 0.033 | 87.8
Three W Builders Inc. / Sophia Construction and Supply (JV) | JV-12-258 | L | AAA | LB | GE1 | Rd. Upgrading (Gravel to Concrete) along Awang-Upi-Lebak-Kalamansig-Palimbang-Sarangani Rd., Km.2041+691-Km.2043+919 w/ exception | Palimbang, Sultan Kudarat | 2013-08-18 | 1st | XII | LF | 46.021 | 181 | 2013-04-02 | 2013-09-29 | 13.77 | O | 0.384 | 0.236 | 0.15 | 0.024 | 0.051 | 0.033 | 87.8
Three W Builders Inc./Repolman Construction (JV) | JV-13-368 | L | AAA | LB | GE | Preventive Maintenance (Asphalt Overlay of San Marcelino - Nagbayto Road) K0151+(-1012) - K0152+185 (K0151+(-1012) - K0151+853.75) | San Marcelino, Zambales | 2014-11-27 | 1st & Final | III | LF | 27.3657 | 75 | 2014-01-14 | 2014-03-29 | 0% | C | 0.448 | 0.133 | 0.3 | - | - | - | 88.1% | 88.1% Satisfactory
Three W Builders, Inc |  | L |  |  |  | Construction of Twenty (20) Two-storey Residential Buildings | Navotaas Homes 1, Brgy. Tanza, Navotas City | 2013-10-17 | 1st | NHA | LF | 222.953 | 330 | 2013-05-18 | 2014-04-12 | 2.97 | O | 0.3431 | 0.2032 | 0.15 | 0.03 | 0.0467 | 0.05 | 82.3
Three W Builders, Inc | 10722 | L | AAA | LB | GE | Rehabilitation/Upgrading (Preventive Maintenance) Regaldo Avenue South Quezon City (K0023+(-959) - K00223+(481)) with exception | Quezon City | 2014-11-26 | 1st & Final | NCR | LF | 17.3695 | 120 | 2014-05-18 | 2014-09-14 | 27.01% | C | 0.461 | 0.133 | 0.3 | - | - | - | 89.4% | 89.4% Very Satisfactory
Three W Builders, Inc | 10722 | L | AAA | LB | GE1 | Impvt. of Quirino-Andaya Highway, Quezon Side, Brgy. San Luis II-Bagong Silang I |  | 2009-05-28 | 1st | IV-A |  | 38.59 | 90 |  |  |  | O | 0.348 | 0.24 | 0.15 | 0.02 | 0.025 | 0.05 | 83.3 | -
Three W Builders, Inc | 10722 | L | AAA | LB | GE1 | Rehab./Reconst. Selective Conc. Paving & Asphalt, along Ozamis-Pagadian Road |  | 2009-06-09 | 2nd | X |  | 38.659 | 240 |  |  |  | O | 0.292 | 0.3 | 0 | 0.03 | 0.043 | 0.033 | 69.8 | -
Three W Builders, Inc | 10722 | L | AAA | LB | GE1 | Rehab./Reconst. (Selective Concrete Paving & Asphalt) along Ozamis-Pagadian Road |  | 2009-03-17 | 1st | X |  | 38.659 | 240 |  |  |  | O | 0.33 | 0.3 | 0.15 | 0.03 | 0.045 | 0.05 | #VALUE! | -
Three W Builders, Inc. |  | L | AAA |  | GB1 | Construction of (20) Two-Storey Resedential Buildings | Navotas homes 1, Brgy. Tanza, Navotas City | 2013-11-17 | 1st | NHA | LF | 222.953 | 330 | 2013-05-18 | 2014-04-12 | 2.97 | O | 0.3431 | 0.2032 | 0.15 | 0.03 | 0.0467 | 0.05 | 82.3 | -
Three W Builders, Inc. | 10722 | L | AAA | MB | GE | Construction/Maintenance of Flood Control and Drainage System / Slope Protection Works along Antipolo-Teresa Road | Barangay Dalig and San Jose, 2nd LD, Antipolo City | 2014-11-28 | 1st & Final | IV | LF | 17.9433 | 140 | 2014-02-12 | 2014-07-01 | 2.14% | C | 0.478 | 0.133 | 0.3 | - | - | - | 91.1% | 91.1% Very Satisfactory
Three W Builders, Inc. | 10722 | L | AAA | LB | GE1 | Const. of Lucban Diversion Road, Phase II | Quezon | 2011-08-09 | 1st | IVA | LF | 57.866 | 618 | 2010-03-25 | 2011-02-02 | 12 | O | 0.373 | 0.225 | 0.15 | 0.03 | 0.042 | 0.033 | 85.3 | -
Three W Builders, Inc. | 10722 | L | AAA | MB | GE | Upgrading ( Gravel to Concrete Access Road Leading to Jatico Resort, Brgy. Bayanga | Cagayan de Oro City | 2014-10-20 | 1st | X | LF | 36.384 | 280 | 2014-03-14 | 2014-12-18 | -2.89% | O | 0.329 | 0.3 | 0.121 | 0.015 | 0.037 | 0.033 | 83.5% | 83.5% Satisfactory
Three W Builders, Inc. | 35843 | L | AAA | MA | GE | Construction/Rehabilitation of Drainage Protection Works along National Roads a.) Bugo Section (Bantiles Creek) b.) Agusan River Section | Cagayan de Oro City | 2014-08-04 | 1st | X | LF | 9.8113 | 230 | 2014-01-31 | 2014-09-17 | 4.49 | O | 0.397 | 0.288 | 0.15 | 0.018 | 0.04 | 0.03 | 92.3
Three W Builders, Inc. | 10722 | L | AAA | LB | GE | Cluster A-Road Upgrading (Gravel to Paved) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standard (HDM-4 Project Analysis) (Intermittent Section) including Drainage and Road Facilities, Lumbia - Uguiaban By-Pass Road | Cagayan de Oro City | 2014-08-15 | Final | X | LF | 40.9764 | 240 | 2013-01-29 | 2013-09-25 | 0 | C | 0.434 | 0.192 | 0.3 |  |  |  | 92.6 | 86.54% Satisfactory
Three W Builders, Inc. | 10722 | L | AAA | LB | GE1 | Road Upgrading (Gravel to Paved) (Int. Sect.) inc. Drainage & Rd. Facilities Lumbia-Uquiaban By Pass Rd. a)Km.1461+861-Km.1462+093; b)Km.1462+2950-Km.1463+760 | Cagayan de Oro City | 2013-08-11 | 2nd | X | LF | 38.892 | 224 | 2013-01-29 | 2013-09-09 | -1.8 | O | 0.351 | 0.3 | 0.132 | 0.007 | 0.05 | 0.05 | 89
Three W Builders, Inc. | 10722 | L | AAA | LB | GE1 | Rd. Upgrading (Gravel to Paved) (Int. Sect.) inc. Drainage & Rd. Facilities, Lumbia-Uquiaban By Pass Rd., a)Km.1461+861-Km.1462+093; b)Km.1462+295-Km.1463+760 | Cagayan de Oro City | 2013-03-11 | 1st | X | LF | 38.892 | 179 | 2013-01-29 | 2013-07-26 | 1.38 | O | 0.3 | 0.225 | 0.15 | 0.01 | 0.042 | 0.033 | 76 | -
Three W Builders, Inc. | 10722 | L | AAA | LB | GE | Road Slip along Malalag-Malita-JAS Road, Bagsak Section Sta. 1621+920 - Sta. 1622+020 | Malita, Davao del Sur | 2014-10-22 | 1st | XI | LF | 14.4032 | 102 | 2014-08-29 | 2014-12-08 |  | O | 0.15 | 0.242 | 0.15 | 0.008 | 0.035 | 0.017 | 60.2% | 60.2% Poor
Three W Builders, Inc. | 10722 | L | AAA | LB | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rds. along Abra-Ilocos Sur, K0386+813-K0405+520 w/ exception (K0387+(-387)-K0405+407 (I.S.) as per RBIA) | San Quintin & Pidigan, Abra | 2012-11-30 | 1st | CAR | LF | 101.286 | 270 | 2012-04-02 | 2012-12-27 | -8.07 | O | 0.334 | 0.3 | 0.069 | 0.03 | 0.059 | 0.033 | 82.5 | -
Three W Builders, Inc. | 10722 | L | AAA | LB | GE1 | Road Upgrading (gravel to concrete) of Abra-Cervantes Rd., K0444+600-K0446+050 & K0446+660-K0449+360 w/ exceptions, (K0444+600-K0446+025 & K0446+710-K0449+415 as per RBIA) | Sallapadan, Abra | 2012-11-30 | 1st | CAR | LF | 55.892 | 294 | 2012-05-28 | 2013-03-17 | 3.26 | O | 0.335 | 0.24 | 0.15 | 0.03 | 0.023 | 0.033 | 81.1 | -
THREE W BUILDERS, INC. | 10722 | L | AAA | LB | GE | Desilting of Matain River, Sta. 000+000 to Sta. 002+100, Subic | Subic | 2015-06-07 | Final | Zambales 2nd DEO | LF | 14.556 | 180 | 2014-10-27 | 2015-04-24 | 0% | C | 0.451 | 0.2 | 0.3 | - | - | - | 95.1% | *95.1% Very Satisfactory
THREE W BUILDERS, INC. | 10722 | L | AAA | LB | GB | Construction of Multi Purpose Building at Brgy. Poblacion | Mabini, Batangas | 2015-06-04 | Final | Batangas 2nd DEO | LF | 4.85 | 145 | 2014-07-21 | 2014-12-12 | 0% | C | 0.476 | 0.12 | 0.3 | - | - | - | 89.6% | *89.6% Very Satisfactory
THREE W BUILDERS, INC. | 10722 | L | AAA | LB | GE | Widening of National Roads, Tanauan - Talisay - Tagaytay, K0065+037 to K0066+800 | Tanauan City, Batangas | 2015-06-06 | 1st | Batangas 3rd DEO | LF | 46.394 | 290 | 2015-02-03 | 2015-11-19 | 3.8% | O | 0.315 | 0.278 | 0.15 | 0.03 | 0.045 | 0.033 | 85.1% | -
THREE W BUILDERS, INC. | 10722 | L | AAA | MB | GE | Construction/Rehabilitation of Drainage/Protection Works along National Roads, a) Bugo Section (Bantiles Creek), b) Agusan River Section, Cagayan de Oro City | a) Bugo Section (Bantiles Creek), b) Agusan River Section, Cagayan de Oro City | 2015-06-12 | Final | Cagayan de Oro City Second DEO | LF | 9.811 | 230 | 2014-01-31 | 2014-09-17 | - | C | 0.367 | 0.2 | 0.052 | - | - | - | 61.9% | *80.14% Unsatisfactory
THREE W BUILDERS, INC. | 100722 | L | AAA | MA | GE | Local Infrastructure Program-Riprapping Projects at Anas, Brgy. Atipolo, Naval, Biliran Lone District | Brgy. Atipolo, Naval, Biliran Lone District | 2015-06-03 | Final | Biliran DEO | LF | 4.635 | 65 | 2015-03-11 | 2015-05-14 | - | C | 0.414 | 0.133 | 0.3 | - | - | - | 84.7% | *84.7% Satisfactory
THREE W BUILDERS, INC. | 10722 | L | AAA | LB | GE | Concrete Reblocking and Asphalt Overlay in Commonwealth Avenue Northbound (S05439LZ: K0015+550 - K0017+000) Quezon City | Quezon City | 2015-06-02 | Final | Quezon City 1st | LF | 33.082 | 60 | 2015-01-12 | 2015-04-11 | (+) 21.11 | C | 0.478 | 0.133 | 0.3 | - | - | - | 91.1% | *91.1% Very Satisfactory
THREE W BUILDERS, INC. | 10722 | L | AAA | LB | GB | Cementing of Circumferencial Road Leading to Seven Falls | Lake Sebu, South Cotabato | 2015-10-21 | 1st | TIEZA | LF | 20 | 250 | 2015-04-13 | 2016-01-02 | -3.62 | O | 0.384 | 0.3 | 0.12 | 0.03 | 0.058 | 0.033 | 92.5 | -
Three W Builders, Inc. | 10722 | L | AAA | LB | GB | Mindanao Tourism and Cultural Village Center | Old Airport Road, Sasa, Davao City | 2016-02-11 | 1st | TIEZA | LF | 89 | 180 | 2015-08-30 | 2016-02-25 | -10.55 | O | 0.375 | 0.287 | 0.045 | 0.03 | 0.07 | 0.05 | 85.64
Three W Builders, Inc. | 10722 | L | AAA | LB | GB | Mindanao Tourism and Cultural Village Center | Old Airport Road, Sasa, Davao City | 2016-03-28 | 2nd | TIEZA | LF | 93.5 | 180 | 2015-03-30 | 2016-02-25 | -16.44 | O | 0.384 | 0.3 | 0 | 0.03 | 0.07 | 0.033 | 81.69
Three W Builders, Inc. | 10722 | L | AAA | LB | GB | Circumferential Road Leading to Seven Falls | Lake Sebu, South Cotabato | 2016-06-01 | Final | TIEZA | LF | 20 | 355 | 2015-04-13 | 2016-04-26 |  | C | 0.493 | 0.2 | 0.3 |  |  |  | 99.3 | 95.20 Very Satisfactory
THREE W BUILDERS, INC. | 10722 | L | AAA | LB | GE | Replacement of Permanent Weak Bridge along Daang Maharlika, Nalifutan Bridge, San Pablo, Isabela | San Pablo, Isabela | 2015-11-13 | 1st | ISABELA 1ST DEO | LF | 18.6117 | 214 | 2015-06-05 | 2016-01-04 | (+) 3.26 | OG | 0.358 | 0.24 | 0.117 | 0.03 | 0.047 | 0.033 | 82.5% | 82.5% Satisfactory
THREE W BUILDERS, INC. | 10722 | L | AAA | LB | GE | Widening of National Roads, Tanauan - Talisay, Tagaytay, K0065+037 - K0066+800, Tanauan City, Batangas | Tanauan City, Batangas | 2015-11-13 | 1st | BATANGAS 3RD DEO | LF | 48.7107 | 320 | 2015-02-03 | 2015-12-19 | 0.0146 | OG | 0.378 | 0.256 | 0.15 | 0.03 | 0.07 | 0.05 | 93.4% | 93.4% Very Satisfactory
THREE W BUILDERS, INC. | 10722 | L | AAA | LB | GB | Construction of Multi-Purpose Building Kapitbahayan, Brgy NBBS, Navotas | Brgy NBBS, Navotas | 2015-12-11 | Final | Malabon-Navotas DEO | LF | 9.3503 | 165 | 2015-04-15 | 0 | 0.00% | C | 0.482 | 0.133 | 0.3 | - | - | - | 91.5% | 91.5% Very Satisfactory
THREE W BUILDERS, INC./ ME2 CONSTRUCTION JOINT VENTURE | - | L | - | - | - | Improvement of Bank Protection along Butuan City - Malaybalay Road - Phase I, (Dankias Section) | K1269+140 to K1269+330, Tungao, Butuan City | 2015-06-12 | 1st | BUTUAN CITY DEO | LF | 45.719 | 312 | 2015-02-28 | 2016-01-05 | (+) 54.61% | O | 0.384 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 90.4% | -
THREE W BUILDERS, INC./MEGA M BUILDERS JOINT VENTURE | JV-14-758 | L | AAA | LB | GE | Construction and Maintenance of Bridges along National Roads, Widening of Permanent Bridges to more than 2 lanes, Taguan Bridge along Daang Maharlika, Candelaria, Quezon | Candelaria, Quezon | 2015-11-16 | 1st | QUEZON 2ND DEO | LF | 39.1992 | 355 | 2015-03-05 | 2016-02-23 | 0.0203 | OG | 0.384 | 0.28 | 0.15 | 0.03 | 0.032 | 0.05 | 92.6% | 92.6% Very Satisfactory
THREE W BUILDERS/MGBJ RISING CONSTRUCTION & LAND DEVELOPER (JV) | - | L | B | MA | GE | Construction of Lined Canal/Drainage along Digos-Makar Road, k1649+856.89-K1650+754.95 with exception (.241Km) | General Santos City | 2015-06-12 | 1st | South Cotabato 2nd DEO | LF | 42.794 | 145 | 2015-04-26 | 2015-09-17 | 9.2% | C | 0.349 | 0.26 | 0.15 | 0.03 | 0.059 | 0.05 | 89.8% | -
Three-In-One Construction & Trading | 14695 | L | B | SB | GB1 | Proposed Repair/Maintenance of Dept. of Labor & Employment Bldg., Intramuros | Manila | 2012-11-19 | 1st | NCR | LF | 9.221 | 291 | 2012-07-10 | 2013-04-26 | -16.48 | O | 0.4 | 0 | 0 | 0.02 | 0.038 | 0.033 | 49.1 | -
Thunder Construction | 17247 | L | B | MA | GE1 | Road Upgrading , Abra-Cervantes Road, Km. 430+450 - Km. 445+450 |  | 2009-02-25 | 1st | CAR |  | 14.268 | 208 |  |  |  | O | 0.126 | 0.224 | 0.12 | 0.03 | 0.022 | 0.017 | #VALUE! | -
Thunderheads Construction Corporation | 22420 | L | D | SB | GE | Construction of Bansud River Control | Bansud, Oriental Mindoro | 2014-08-14 | 1st & Final | IV-B | LF | 9.1935 | 104 | 2014-02-12 | 2014-05-26 | 0 | C | 0.401 | 0.133 | 0.3 |  |  |  | 83.4 | 83.40% Satisfactory
THUNDERHEADS CONSTRUCTION CORPORATION | 22420 | L | D | SB | GE | Const./Rehab. of Farm to Market Rd. from Sitio Bagacay-Sitio Sinirayan, Brgy. Nasucob | Bulalacao, Oriental Mindoro | 2015-11-18 | Final | Southern Mindoro DEO | LF | 4.6048 | 45 | 2015-08-25 | 2015-10-08 | 0 | C | 0.481 | 0.133 | 0.3 | - | - | - | 91.4% | 91.4% Very Satisfactory
TIBIAO-ANTIQUE N.K. ENTERPRISE (Formerly: N.K. Enterprise) | 29292 | L | B | MA | GE | Construction of Farm to Market Road, Barangay Esperanza II, Sibalom, Antique | Barangay Esperanza II, Sibalom, Antique | 2015-11-10 | Final | Antique | LF | 1.9565 | 62 | 2015-07-10 | 2015-09-10 | 0.00% | C | 0.386 | 0.2 | 0.3 | - | - | - | 88.6% | 88.6% Satisfactory
TIBIAO-ANTIQUE N.K. ENTERPRISE, INC. (Formerly: N.K. Enterprise) | 29292 | L | B | MA | GE | Upgrading of Bugo-Gen. Fullon Road, (Unpaved to Paved), K0128+010-K0129+202.50 (Road Upgrading) & K0128+010-K0129+399 (Slope Protection and Drainage) | San Remigio, Antique | 2015-08-31 | 1st | Antique | LF | 47.109 | 138 | 2015-05-22 | 2015-10-06 | 12.6% | O | 0.367 | 0.238 | 0.15 | 0.03 | 0.051 | 0.05 | 88.6% | -
Tiger Valley Builders | 33063 |  |  |  |  | Repair/Restoration of Santiago-Tuguegarao Rd. Maddarulug Sect. |  | 2010-05-28 |  | II |  | 2.412 | 130 |  |  |  | O | 0.369 | 0.24 | 0.15 | 0.024 | 0.042 | 0.033 | 85.8 | -
TNJ Builders | 34268 | L | D | SB | GB | Construction of Buluan Multi Purpose Building | Buluan, Conner, Apayao | 2014-11-28 | 1st | CAR | LF | 3.5 | 227 | 2014-05-27 | 2015-01-08 | 1.08% | O | 0.375 | 0.24 | 0.15 | 0.03 | 0.041 | 0.033 | 86.9% | 86.9% Satisfactory
Tokwing / ZM Construction (JV) | JV-08-274 | L | AAA | LB | GE1 | Const./Replacement of Bucao Bridge and Approaches along Iba-South Road over Bucao River |  | 2009-09-03 | 2nd | III |  | 144.75 | 250 |  |  |  | O | 0.381 | 0.3 | 0.15 | 0.03 | 0.047 | 0.033 | 94.1 | -
Tokwing Const. Corp./ Fabmik Const. & Equipment Co., Inc. (JV) | 9650 |  | AAA |  |  | Talakag Irrigation Project | Talakag, Bukidnon/ Region 10 | 2015-11-26 | 1st | NIA | LF | 165.966 | 452 | 2014-12-02 | 2016-02-26 | -11.55 | O | 0.3546 | 0.3 | 0.0345 | 0.025 | 0.061 | 0.05 | 82.51 | -
Tokwing Construction |  | L |  |  |  | Construction of Eighteen (18) Three Storey Residential Buildings | Disiplina Village 2, Brgy. Ugong, Valenzuela City | 2013-07-13 | 1st | NHA | LF | 169.57 | 375 | 2012-12-01 | 2013-12-10 | 0.58 | O | 0.364 | 0.185 | 0.15 | 0.024 | 0.054 | 0.05 | 82.7
Tokwing Construction |  | L | AAA |  | GB1 | Construction of Eighteen (18) Three Storey Residential Buildings | Disiplina Village 2, Brgy. Ugong, Valenzuela City | 2013-07-13 | 1st | NHA | LF | 169.739 | 375 | 2012-12-01 | 2013-12-10 | 0.58 | O | 0.364 | 0.185 | 0.15 | 0.024 | 0.054 | 0.05 | 82.7 | -
Tokwing Construction | 9650 | L | AAA | MA | GE1 | Const. of Calaba Bridge and Approaches (Phase 2), Brgy. Calaba |  | 2009-09-07 | 2nd | PMO |  | 157.81 | 630 |  |  |  | O | 0.352 | 0.24 | 0.15 | 0.03 | 0.056 | 0.033 | 86.1 | -
Tokwing Construction | 9650 | L | AAA | LB | GE1 | Construction of Calaba Bridge and Approaches (Phase II) |  | 2009-02-24 | 1st | Sp. Bridges |  | 143.959 | 510 |  |  |  | O | 0.355 | 0.235 | 0.15 | 0.022 | 0.04 | 0.033 | #VALUE! | -
Tokwing Construction | 9650 | L | AAA | LB | GE1 | Const. of Mindanao Ave. Extension (Segment C) |  | 2008-11-28 | 1st | NCR |  | 161.879 | 360 |  |  |  | O | 0.375 | 0.18 | 0.1 | 0.03 | 0.042 | 0.067 | 79.4 | -
Tokwing Construction | 9650 |  |  |  |  | Const. (Road Opening) of Missing Link of National Road, Abra-Ilocos Norte Side, Km. 433+000 - Km. 452+620 |  | 2010-02-16 |  | CAR |  | 47.656 | 494 |  |  |  | O | 0.349 | 0.262 | 0.15 | 0.02 | 0.033 | 0.033 | 84.7 | -
Tokwing Construction | 9650 |  |  |  |  | Const. (Road Opening) of Missing Link of National Roads, Abra-Ilocos Norte, Abra Side, Km.433+000 - Km.452+620 |  | 2010-05-25 |  | CAR |  | 47.656 | 494 |  |  |  | O | 0.303 | 0 | 0.15 | 0.022 | 0.035 | 0.033 | 54.3 | -
Tokwing Construction | 9650 | L | AAA | LB | GE1 | Road Upgrading (Gravel to Paved), Baler-Casiguran Rd., Km. 276+800-Km. 285+000 | Dipaculao, Aurora | 2012-11-26 | 1st | III | LF | 144.896 | 240 | 2012-04-30 | 2012-12-25 | 1.46 | O | 0.324 | 0.28 | 0.15 | 0.03 | 0.04 | 0.033 | 85.7 | -
Tokwing Construction / Northern Builders (JV) | JV-09-017 | L | AAA | LB | GE2 | Pinatubo Hazard Urgent Mitigation Proj. (PHUMP), Phase III, CP-3B: City of San Fernando Flood Control Works, Part B-Outlet Channels & Bridges from Sta.0+000-Sta.0+840 (San Fernando River): 0+000-2+021.14 (Matulid Creek); Sta.0+000-2+161.07(PAU Creek); Sta.0+400-Sta.1+494.02 (Dalaquitan Creek); Sta.0+083.84-Sta.3+500.86 (Mapalad Creek); and Sta.0+000-Sta.1+056.79, San Felipe (Cut-Off Channel) | Pampanga | 2011-08-01 | 1st | MPE-PMO | FA | 490.933 | 540 | 2011-03-18 | 2012-09-07 | -7.1 | O | 0.387 | 0.3 | 0.079 | 0.03 | 0.058 | 0.05 | 90.4 | -
Tokwing Construction / Northern Builders (JV) | JV-09-017 | L | AAA | LB | GE2 | Pinatubo Hazard Urgent Mitigation Project (PHUMP), Phase III, CP-3B: City of San Fernando Flood Control Works, Part B- Outlet Channels and Bridges from Sta. 0+000-Sta. 0+840 (San Fernando River); Sta.0+000- Sta. 2+021.14 (Matulid Creek); Sta 0+000- Sta. 2+161.07 (PAU Creek); Sta. 0+400-Sta 1+494.02 (Dalaquitan Creek); Sta 0+083.84- Sta 3+500.86 (Mapalad Creek); & Sta 0+00- Sta 1+056.79 San Felipe (Cut-Off Channel) | Pampanga | 2012-03-12 | 2nd | MPE-PMO | FA | 490.933 | 540 | 2011-03-18 | 2012-09-07 | -4.647 | O | 0.34 | 0.289 | 0.104 | 0.03 | 0.05 | 0.033 | 84.6 | -
Tokwing Construction / Northern Builders (JV) | JV-09-017 | L | AAA | LB | GE2 | Pinatubo Hazard Urgent Mitigation Project (PHUMP), Phase III, CP-3B: City of San Fernando Flood Control Works, Part B-Outlet Channels and Bridges from Sta. 0+000-Sta. 0+840 (San Fernando River); Sta. 0+000-2+021.14 (Matulid Creek); Sta. 0+000-2+161.07 (Pau Creek); Sta.0+400-Sta. 1+494.02 (Dalaquitan Creek); Sta.0+083.84-Sta. 3+50086 (Mapalad Creek; and Sta. 0+000-Sta. 1+056.79 San Felipe (Cut-Off Channel) | Pampanga | 2012-07-30 | 3rd | PMO-MPE | FA | 490.933 | 602 | 2011-03-18 | 2012-11-08 | -1.96 | O | 0.355 | 0.259 | 0.13 | 0.03 | 0.065 | 0.05 | 88.9 | -
Tokwing Construction Corp. (Formerly: Tokwing Construction) | 9650 | L | AAA | LB | GE | Road Upgrading (Gravel to Concrete) of Kalinga-Abra Road, K0476+00 to K0473+697 with Exception, (K0476+000 to K0479+539 (with exception) as per RBIA) & K0480+300 to K0482+640 (K0480+342 to K0482+081 as per RBIA) Balenciago Norte, Pasil & Balbalan Proper Section | Kalinga | 2014-08-08 | 1st & Final | CAR | LF | 124.173 | 535 | 2012-06-25 | 2013-12-11 | 0 | C | 0.358 | 0.133 | 0.3 |  |  |  | 79.1 | 79.10% Unsatisfactory
Tokwing Construction Corp. (Formerly: Tokwing Construction) | 9650 | L | AAA | LB | GE1 | Rd. Upgrading (Gravel to Conc.) along Kalinga-Abra Rd., K0476+000-K0479+697 w/ exception, (K0476+000-K0479+539 (w/ exception) as per RBIA & K0480+300-K0482+640, (K0480+342-K0482+081 as per RBIA) Balenciagao Norte, Pasil & Balbalan Proper Sect. | Kalinga | 2013-08-08 | 3rd | CAR | LF | 124.174 | 448 | 2012-06-25 | 2013-09-15 | -7.05 | O | 0.333 | 0.3 | 0.15 | 0.03 | 0.05 | 0.033 | 89.6
Tokwing Construction Corp. (Formerly: Tokwing Construction) | 9650 | L | AAA | LB | GE1 | Rd. Upgrading (Gravel to Conc.) along Kalinga-Abra Rd., K0476+000-K0479+697 w/ exception, (K0476+000-K0479+539 (w/ exception) as per RBIA) & K0480+300-0482+640, (K0480+342-K0482+081 as per RBIA) Balenciagao Norte, Pasil & Balbalan Proper Sect. | Kalinga | 2013-03-19 | 2nd | CAR | LF | 124.174 | 388 | 2012-06-25 | 2013-07-17 | 9.5 | O | 0.365 | 0.3 | 0.15 | 0.03 | 0.045 | 0.033 | 92.3 | -
Tokwing Construction Corp. (Formerly: Tokwing Construction) | 9650 | L | AAA | LB | GE1 | Rd. Upgrading (gravel to concrete) along Kalinga-Abra Rd., K0476+000-K0479+697 w/ exception, (K0476+000-K0479+539 (with exception) as per RBIA) & K0480+300-K0482+640, (K0480+342-K0482+081 as per RBIA) Balenciagao Norte, Pasil & Balbalan Proper Sect. | Kalinga | 2012-11-28 | 1st | CAR | LF | 124.174 | 388 | 2012-06-25 | 2013-07-17 | -3.61 | O | 0.28 | 0.183 | 0.113 | 0.007 | 0.032 | 0.033 | 64.8 | -
Tokwing Construction Corporation | [5 empty] | Construction of Fourteen (14) 3-Storey LRB and Land Development, Disiplina Village Site 1 Package 1 | Brgy. Bignay, Valenzuela City | 2016-05-04 | 2nd | NHA | LF | 199.163 | 406 | 2014-11-15 | 2016-03-28 | -12.61 | O | 0.3794 | 0.2005 | 0.0239 | 0.03 | 0.0653 | 0.0332 | 73.23 | -
Tokwing Construction Corporation | [5 empty] | Construction of Fourteen (14) 3-Storey LRB and Land Development, Disiplina Village Site 1 Package 1 | Brgy. Bignay, Valenzuela City | 2015-11-11 | 1st | NHA | LF | 199.163 | 406 | 2014-11-15 | 2016-01-28 | -21.18 | O | 0.3668 | 0.1951 | 0 | 0.02 | 0.0445 | 0.033 | 65.94 | -
Tokwing Construction Corporation |  |  | AAA |  |  | Completion of Hospital Main Building (Phase 6) 5th & 6th Floor Level | Sumulong Highway, Sto. Niño, Marikina City, Phil. 1800 | 2016-07-08 | 1st | DOH | LF | 90 | 773 | 2014-06-25 | 2016-07-31 | 0.311 | O | 0.383 | 0.267 | 0.15 | 0.03 | 0.056 | 0.05 | 93.6 | -
Tokwing Construction Corporation |  |  | AAA |  |  | Completion of Hospital Main Building (Phase 7) 7th Floor Level | Sumulong Highway, Sto. Niño, Marikina City, Phil. 1800 | 2016-07-05 | 1st | DOH | LF | 50 | 180 | 2016-01-12 | 2016-08-31 | 0.311 | O | 0.39 | 0.27 | 0.15 | 0.03 | 0.06 | 0.05 | 95 | -
Tokwing Construction Corporation/ Markbilt Construction (JV) | JV-11-742 | L | AAA | LB |  | PIDPC-C-WAAISI-1 | Apayao/ CAR | 2015-10-17 | 1st | NIA | LF | 255.023 | 896 | 2013-02-06 | 2015-07-20 | -38.79 | O | 0.3902 | 0.3 | 0 | 0.03 | 0.05 | 0.05 | 82.02 | -
TOKWING CONSTRUCTION, CORP. (Formerly: Tokwing Construction) | 9650 | L | AAA | LB | GE | Restoration of Santol Creek, Slope Protection | Sitio Maligaya, Floridablanca, Pampanga | 2014-11-18 | 1st & Final | III | LF | 8.4732 | 90 | 2014-08-10 | 2014-11-07 | 0% | C | 0.439 | 0.133 | 0.3 | - | - | - | 87.2% | 87.2% Satisfactory
TOKWING CONSTRUCTION, CORP./SCION CONSTRUCTION (JV) | JV-14-284 | L | AAA | LB | GE | Construction/Opening of Lobo-Malabrigo-Laiya-San Juan Road (Lobo - Malabrigo - Laiya Section) including Construction of Bridge, K0139+469.59 to K0145+661.15 (with exception) Net Length = 5, 586.06 l.m., Bridge- 70.00 l.m. | Batangas Province | 2015-06-05 | 1st | Regional Office No. IV-A | LF | 178.926 | 570 | 2014-12-15 | 2016-07-06 | 1.87% | O | 0.372 | 0.257 | 0.15 | 0.03 | 0.045 | 0.033 | 88.7% | -
Tokwing/ZM Construction (JV) | JV-08-274 | L | AAA | LB | GE1 | Const./Replacement of Bucao Bridge and Approaches along Iba South Road over Bucao River |  | 2009-05-27 | 1st | III |  | 144.75 | 250 |  |  |  | O | 0.384 | 0.253 | 0.15 | 0.03 | 0.051 | 0.05 | 91.8 | -
Tokwing/ZM Construction (JV) | JV-08-075 | L | AAA | LB | GE1 | Const. of Tarlac-Nueva-Ecija-Aurora-Dingalan Port Road (Jct. Fort Magsaysay-Laur Section) Contract Package 2 |  | 2009-05-30 | 1st | III |  | 298.974 | 360 |  |  |  | O | 0.364 | 0.3 | 0.15 | 0.03 | 0.04 | 0.05 | 93.4 | -
Tokwing/ZM Construction (JV) | JV-08-075 | L | AAA | LB | GE1 | Const. of Tarlac-Nueva Ecija-Aurora-Dingalan Port Road (Jct. Fort Magsaysay-Laur Section) Contract Package 2 |  | 2009-09-07 | 2nd | III |  | 298.974 | 360 |  |  |  | O | 0.388 | 0.3 | 0.15 | 0.03 | 0.04 | 0.05 | 95.8 | -
Toledo Const. Corp./ Advanced Foundation Const. System Corp. (JV) | JV-02-063 | L | AAA | LB | GE1 | NAIA Expressway & its Related Road Proj. Phase I, Package 3, Skyway Ramps 2 & 3 |  | 2008-08-28 | 9th | URPO |  | 721.651 | 1543 |  |  |  | O | 0.33 | 0.3 | 0 | 0.03 | 0.047 | 0.1 | 80.7 | -
Tongka Construction | 4064 | L | B | MA | GE | Preventive Maintenance of Angeles - Porac Floridablanca - Dinalupihan Road, K0091+633 - K0092+000 | Porac, Pampanga | 2014-08-11 | 1st & Final | III | LF | 4.8256 | 25 | 2014-05-23 | 2014-06-16 | 0 | C | 0.456 | 0.133 | 0.3 |  |  |  | 88.9 | 88.90% Satisfactory
Tonka Construction | 4064 | L | B | MA | GE | Construction of Roads, San Juan Bano-Gatiawin to Aquino Byway | Arayat, Pampanga | 2014-11-17 | 1st | III | LF | 9.4879 | 133 | 2014-08-11 | 2014-12-21 | 27.63% | O | 0.38 | 0.24 | 0.15 | 0.03 | 0.047 | 0.033 | 88% | 88% Satisfactory
Top Most Development & Marketing Corporation | 13361 |  |  |  |  | Completion of Pociento Bridge, Brgy. Canipayan |  | 2010-02-25 |  | VI |  | 4.767 | 120 |  |  |  | O | 0.32 | 0.3 | 0.15 | 0.02 | 0.032 | 0.05 | 87.2 | -
Top Most Development & Marketing Corporation | 13361 | L | B | SB | GE1 | Road Upgradingof Oton-Mambog-Cabolo-An-Abilay-San Jose Road |  | 2009-06-10 | 1st | VI |  | 9.461 | 150 |  |  |  | O | 0.355 | 0.3 | 0.15 | 0.03 | 0.06 | 0.05 | 94.5 | -
Top Most Development & Marketing Corporation | 13361 | L | B | SB | GE1 | Road Upgrading of Oton-Mambog-Cabolo-An-Abilay-San Jose Road |  | 2009-09-10 | 2nd | VI |  | 9.461 | 180 |  |  |  | O | 0.358 | 0.3 | 0.15 | 0.03 | 0.05 | 0.05 | 93.8 | -
Topmost Development and Marketing Corp. | 13361 |  |  |  |  | Conc. of Lambunao-Inca Road, Km. 49+257 - Km. 59 +793.70 with exception |  | 2010-09-05 |  | VI |  | 7.091 | 150 |  |  |  | O | 0.375 | 0.24 | 0.15 | 0.03 | 0.051 | 0.033 | 87.9 | -
Toptech Trading & Construction Co., Inc. | 25522 | L | A | MA | GE | Widening of Manila-Batangas Diversion Road including Drainage System, K0061+015 to K0061+745, Sto. Tomas Section, Batangas 3rd LD | Sto. Tomas Section, Batangas | 2014-12-02 | 1st | IV | LF | 39.0184 | 390 | 2014-01-24 | 2015-02-17 | 12.48% | O | 0.345 | 0.3 | 0.15 | 0.012 | 0.035 | 0.017 | 85.9% | 85.9% Satisfactory
Toreja's Construction Supply Corporation | 15453 | L | AAA | LA | GE | Prevent Maint of Natl Scdry Rd Based on PMS/HDM-4 (Inter Sect) along Diokno Hway at 1: K0077+000 to K00077+100, 2: K0078+834 to K0078+994 and 3: K0082+689 to K0083+500 | Lemery, Batangas | 2014-08-06 | 1st & Final | IV-A | LF | 26.1767 | 179 | 2014-02-03 | 2014-07-31 | 0 | C | 0.447 | 0.2 | 0.3 |  |  |  | 94.7 | 94.70% Very Satisfactory
Toreja's Construction Supply Corporation | 15453 | L | AAA | LA | GE | Preventive Maintenance Based on Pavement Management System/Highway Development & Management-4 (HDM-4) (Intermittent Section), Sdry. Rd. along Batangas Port Diversion Rd., K0102+194 to K0102+824 | Batangas City, Batangas | 2014-08-07 | 1st & Final | IV-A | LF | 19.5539 | 75 | 2014-02-24 | 2014-05-09 | 0 | C | 0.325 | 0.2 | 0.3 |  |  |  | 82.5 | 82.50% Satisfactory
Toreja's Construction Supply Corporation | 15453 | L | AAA | LA | GE1 | Widening along Palico-Balayan-Batangas Rd., Mahayhay Jct. | Lemery, Batangas | 2013-07-30 | Final | IVA | LF | 9.667 | 141 | 2013-01-02 | 2013-05-22 | 0 | C | 0.464 | 0.133 | 0.3 | - | - | - | 89.7 | 90.06% V. Satisfactory
Toreja's Construction Supply Corporation | 15453 | L | AAA | LA | GE1 | Widening along Palico-Balayan-Batangas Rd., Mahayhay Jct. | Lemery, Batangas | 2013-03-13 | 1st | IVA | LF | 9.667 | 120 | 2013-01-02 | 2013-05-01 | 0 | O | 0.378 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 90.3 | -
Toreja's Construction Supply Corporation | 15453 | L | AAA | LA | GE | Rehabilitation/Reconstruction/Upgrading Damaged Paved National Road Including Drainage Based on Pavement Management System/Highway Development Management-4 (HDM-4) San Pablo-Rizal-Nagcarlan-Liliw | Laguna | 2014-11-27 | 1st | IV | LF | 43.3048 | 209 | 2014-05-21 | 2014-12-15 | - | O | 0.38 | 0.3 | 0.15 | 0.03 | 0.061 | 0.033 | 95.4% | 95.4% Very Satisfactory
Toreja's Construction Supply Corporation | 15453 | L | AAA | LA | GE | Rehabilitation/Reconstruction/Upgrading Damaged Paved National Road Including Drainage Based on Pavement Management System/Highway Development Management-4 (HDM-4) Calauan-Nagcarlan Road, K0088+600-K0090+153 (Intermittent Section) | Calauan-Nagcarlan Road, Laguna | 2014-11-27 | 1st | IV | LF | 26.894 | 200 | 2014-05-13 | 2014-11-28 | - | O | 0.363 | 0.3 | 0.15 | 0.03 | 0.064 | 0.033 | 94% | 94% Very Satisfactory
Toreja's Construction Supply Corporation | 15453 | L | AAA | LA | GE | A) Rehab/Reconst/Upgrading of Damaged Paved Natl Rd incl Drainage Based on Pavt Mgnt System/H-way Devt & Mgnt-4 (HDM-4) (IS), Banay-Banay-Mojon-Cuenca Rd K0092+197-K0092+369 b) Rehab/Reconst/Upgrading of Damaged Paved Natl Rd incl Drainage Based on Pavt Mgnt System/H-way Devt & Mgnt-4 (HDM-4) (IS), Banay-Banay-Mojon-Cuenca Rd K0093+964-K0094+277 | Banay-Banay-Mojon-Cuenca | 2014-12-02 | 1st & Final | IV | LF | 8.3016 | 90 | 2014-01-23 | 2014-04-22 | 1.11% | C | 0.492 | 0.133 | 0.3 | - | - | - | 92.5% | 92.5% Very Satisfactory
Toreja's Construction Supply Corporation | 15453 | L | AAA | LA | GE | Preventive Maintenance Based on Pavement Management System/Highway Dev't & Mgnt-4(HDM-4) (Intermittent Section) Arterial Road Along Palico-Batangas road, K0145+000 to K0145+800 | Bauan, Batangas | 2014-12-06 | 1st & Final | IV | LF | 12.2861 | 50 | 2014-02-06 | 2014-03-27 | 0% | C | 0.481 | 0.136 | 0.3 | - | - | - | 91.7% | 91.7% Very Satisfactory
TOREJA'S CONSTRUCTION SUPPLY CORPORATION | 15453 | L | AAA | LA | GE | Cluster I- Construction and Maintenance of Bridges along National Roads - Rehabilitation/Major Repair of Permanent Bridges, San Roque Bridge along Bauan - Mabini Road | Bauan and Lobo, Batangas | 2015-06-04 | Final | Batangas 2nd DEO | LF | 8.284 | 96 | 2015-02-05 | 2015-05-11 | 0% | C | 0.481 | 0.127 | 0.3 | - | - | - | 90.8% | *90.8% Very Satisfactory
TOREJA'S CONSTRUCTION SUPPLY CORPORATION | 15453 | L | AAA | LA | GE | Cluster I - Construction and Maintenance of Bridges along National Roads, Rehabilitation/Major Repair of Permanent Bridges: 1. Lobo Br. (Malabrigo Br.) (B03073LZ) along Lobo-Malabrigo-San Juan Road, 2. San Roque Br. (B0293LZ) along Bauan-Mabini Road, 3. Sta. Maria Br. (B02924LZ) along Bauan-Mabini Road, 4. Yama Br. (B03031LZ) along Batangas-Lobo Road | Bauan and Lobo, Batangas | 2015-09-01 | 1st & Final | Batangas 2nd | LF | 25.37 | 96 | 2015-02-05 | 2015-05-11 | 0% | C | 0.403 | 0.133 | 0.3 | - | - | - | 83.6% | *83.6% Satisfactory
TOUGHBUILT CONSTRUCTION & TRADING, INC. | 35497 | L | D | SB | GB | Construction of Multi-Purpose Building at Barangay Arkong Bato, Valenzuela City | Valenzuela City | 2015-06-06 | 1st | Metro Manila 3rd DEO | LF | 4.248 | 120 | 2015-03-18 | 2015-07-15 | (+) 1.91 | O | 0.374 | 0.24 | 0.15 | 0.022 | 0.051 | 0.05 | 88.7% | -
Toyo Construction Co. LTD / Tobishima Corporation (JV) | FC-06-034 | F | AAA | LB | GE1 | CP IV, Urgent Bridges Const. Project for Rural Devt., Quinoguitan Bridge | Carmen, Bohol | 2011-03-31 | 1st | UBCPRD | FA | 61.123 | 24 Months | 2009-03-24 | 2011-03-23 | - | O | 0.393 | 0.24 | 0 | 0.03 | 0.042 | 0.033 | 73.8 | -
Toyo Construction Co. LTD / Tobishima Corporation (JV) | FC-06-034 | F | AAA | LB | GE1 | CP IV, Urgent Bridges Const. Project for Rural Devt., Moawa Bridge | Carmen, Bohol | 2011-03-31 | 1st | UBCPRD | FA | 46.073 | 24 Months | 2009-03-24 | 2011-03-23 | - | O | 0.372 | 0.24 | 0 | 0.03 | 0.042 | 0.033 | 71.7 | -
Toyo Construction Co. Ltd. | FC-09-006 | F | AAA | LB | GE2 | Const. of Pinatubo Hazard Urgent Mitigation Project, Phase III, CP-4 Excavation & Dredging of Major Rivers from Sta. 5+850-Sta. 22+820 | Pampanga | 2012-08-15 | 4th | MPE-PMO | FA | 923.149 | 944 | 2010-02-22 | 2012-09-22 | -0.13 | O | 0.373 | 0.3 | 0.149 | 0.03 | 0.065 | 0.033 | 95 | -
Toyo Construction Co., Ltd. | FC-09-006 | F | AAA | LB | GE2 | Const. of Pinatubo Hazard Urgent Mitigation Project (PHUMP), Phase III, CP-4 (Excavation and Dredging of Major Rivers from Sta.5+850 to Sta.22+820) | Pampanga | 2011-08-01 | 2nd | MPE-PMO | FA | 868.134 | 780 | 2010-02-22 | 2012-04-11 | 12.14 | O | 0.397 | 0.297 | 0.15 | 0.03 | 0.047 | 0.05 | 97.1 | -
Toyo Construction Co., Ltd. | FC-09-006 | F | AAA | LB | GE2 | Pinatubo Hazard Urgent Mitigation Project-Phase III, CP No.4 (Dredging and Channel Excavation of Major River) | Pampanga | 2011-03-31 | 1st | MPE | FA | 922.421 | 780 | 2010-02-22 | 2012-04-11 | 19.129 | O | 0.4 | 0.3 | 0.15 | 0.03 | 0.051 | 0.025 | 95.6 | -
Toyo Construction Co., Ltd. | - | F | - | - | GE2 | The Project for Flood Disaster Mitigation in Camiguin Island | Mahinog, Camiguin | 2011-04-02 | 1st | MFCP II | FA | Y 780.000 | 550 | 2010-01-27 | 2011-07-31 | 3.93 | O | 0.361 | 0.3 | 0.15 | 0.03 | 0.07 | 0.05 | 96.1 | -
Toyo Construction Co., Ltd. | FC-09-006 | F | AAA | LB | GE2 | Const.. of Pinatubo Hazard Urgent Mitigation Project (PHUMP), Phase III, CP-4 (Excavation and Dredging of Major Rivers from Sta.5+850-Sta.22+820) | Pampanga | 2012-03-13 | 3rd | MPE-PMO | FA | 868.134 | 847 | 2010-02-22 | 2012-06-17 | 3.35 | O | 0.4 | 0.3 | 0.15 | 0.03 | 0.051 | 0.05 | 98.1 | -
Toyo-Nippon-Miyaji (JV) | SL2-SN-000843 | F | AAA | LB | GE1 | Const. of CP-1 UBCPRD (Construction of Pantal Bridge), Brgy. Kabayan Central |  | 2009-05-21 | 1st | UBCPRD |  | 26.777 | 28 mos. |  |  |  | O | 0.391 | 0.3 | 0.15 | 0.03 | 0.05 | 0.033 | 95.4 | -
Toyo-Nippon-Miyaji (JV) | SL2-SN-000843 | F | AAA | LB | GE1 | Const. of CP-1 UBCPRD (Construction of Ellet Bridge), Brgy. Eddet, Kabayan Central |  | 2009-05-21 | 1st | UBCPRD |  | 26.777 | 273 |  |  |  | O | 0.371 | 0.3 | 0.15 | 0.03 | 0.06 | 0.033 | 94.4 | -
Toyo-Tobishima (JV) | FC-06-034 |  |  |  |  | Const. of Tagbalidbid 2 Bridge Cagwait |  | 2010-03-03 |  | UBCPRD |  | 20.45 | 300 |  |  |  | O | 0.354 | 0.3 | 0.15 | 0.03 | 0.055 | 0.05 | 93.9 | -
Toyo-Tobishima (JV) | FC-06-034 | F | AAA | LB | GE1 | Const. of Package III, Urgent Bridges Const. Projects for Rural Devt. (Bacao Bridge) |  | 2008-11-28 | 2nd | UBCPRD |  | 23.103 | 10 mos. |  |  |  | O | 0.32 | 0.3 | 0.1 | 0.03 | 0.037 | 0.1 | 88.7 | -
TR Construction | 11697 | L | B | MA | GE | Construction of Flood Control System, Ariman River | Gubat, Sorsogon | 2014-11-06 | 1st & Final | V | LF | 9.3465 | 120 | 2014-02-12 | 2014-06-11 | 0% | C | 0.403 | 0.133 | 0.3 | - | - | - | 83.6% | 83.6% Satisfactory
Tracsom Builders Incorporated (Formerly: Tracsom Builders) | 5935 | L | A | MB | GB1 | Construction of 4-Storey, 16 Classroom School Building @ Sta. Lucia H/S |  | 2009-03-06 | 1st | NCR |  | 23.864 | 210 |  |  |  | O | 0.348 | 0.285 | 0 | 0.03 | 0.047 | 0.033 | #VALUE! | -
Tracsom Builders, Incorporated | 5935 | L | A | MB | GB1 | Const. of 4-Storeys, 36-Classroom Sch. Bldg. at San Andres Bonifacio Integrated Sch., Brgy. Addition Hills | Mandaluyong City | 2013-03-22 | Final | NCR | LF | 39.879 | 360 | 2011-11-23 | 2012-11-16 | 2.78 | C | 0.46 | 0.079 | 0.3 | - | - | - | 83.9 | 85.86% Satisfactory
Trans-Aurora Construction | 11388 |  |  |  |  | Road Upgrading (Gravel to Paved) Baler-Cemento via Dicaloyungan |  | 2010-06-05 |  | III |  | 20.639 | 160 |  |  |  | O | 0.378 | 0.234 | 0.15 | 0.03 | 0.055 | 0.033 | 88 | -
Tribu Design and Construction | 12756 | L | A | MA | GB1 | Const. of Conner Central NHS Talifugu Annex | Conner, Apayao | 2013-08-10 | 1st | CAR | LF | 5.379 | 120 | 2013-04-01 | 2013-07-29 | -18.48 | O | 0.368 | 0.3 | 0 | 0.015 | 0.041 | 0.017 | 74.1
Tribu Design and Construction | 12756 | L | A | MB | GE | Road Upgrading (Gravel to Paved) of Malalao National Road, (Agbannawag - Malalao - Bulu Section) | Tabuk, Ifugao | 2014-11-27 | 1st | CAR | LF | 27.5393 | 223 | 2014-03-24 | 2014-11-01 | -3% | O | 0.357 | 0.268 | 0.12 | 0.03 | 0.055 | 0.033 | 86.3% | 86.3% Satisfactory
Tribu Design and Construction | 12756 | L | A | SB | GE | Const. of Sta Fe River Flood Control along Daang Maharlika, Calitlitan Section K0226+000 | Calitlitan, Aritao, Nueva Vizcaya | 2014-08-15 | 1st & Final | II | LF | 7.5191 | 120 | 2014-01-29 | 2014-05-28 | 18.67 | C | 0.372 | 0.186 | 0.3 |  |  |  | 85.8 | 85.80% Satisfactory
Tribu Design and Construction | 12756 | L | A | MA | GE1 | Replacement of Camalugan Bridge along Balbalan-Pinukpuk Rd. | Pinukpuk, Kalinga | 2013-03-20 | 1st | CAR | LF | 12.336 | 150 | 2013-02-04 | 2013-07-03 | 0 | O | 0.331 | 0.24 | 0.15 | 0.023 | 0.04 | 0.033 | 81.7 | -
TRIBU DESIGN AND CONSTRUCTION | 12756 | L | A | MB | GE | Road Upgrading (Gravel to Paved) of Malalao National Road (Agbannawag - Malalao - Bulo Section), K0511+(074.52) - K0511+(087.52) & K0511+275 - K0512+480 | Tabuk, Kalinga | 2015-06-09 | Final | Kalinga DEO | LF | 27.539 | 223 | 2014-03-24 | 2014-11-01 | (-) 3.00% | C | 0.403 | 0.158 | 0.21 | - | - | - | 77.1% | *82.62% Satisfactory
Tribu Design and Construction / Jann Norris Construction and Supplies (Joint Venture) | JV-12-319 | L | A | MA | GE1 | Road Upgrading (Gravel to Paved) along Bambang-Kasibu-Solano Rd. 1)K0320+(-513)-K0320+(-384), 2)K0320+(-384)-K0320+726, Runruno | Quezon, Nueva Vizcaya | 2013-03-20 | 1st | II | LF | 26.53 | 148 | 2013-01-28 | 2013-06-24 | 0.63 | O | 0.35 | 0.242 | 0.15 | 0.03 | 0.042 | 0.033 | 84.7 | -
Tribu Design and Construction/Jann-Norris Construction and Supplies (JV) | JV-13-599 | L | A | MA | GE | Road Upgrading (Gravel to Paved) based on Gravel Road Strategies, Traffic Benchmark fo Upgrading to Paved Road Standard (HDM-4 Project Analysis) Intermittent Section, Bambang-Kasibu-Solano Road, K0274+155 - K0274+762, Macalong Section. K0277+519 - K0279+144, Watwat Section | Kasibu, Nueva Vizcaya | 2014-10-30 | 1st & Final | II | LF | 45.6672 | 179 | 2014-06-21 | 2014-12-16 |  | C | 0.416 | 0.133 | 0.3 | - | - | - | 84.9% | 84.9% Satisfactory
TRICHES CONSTRUCTION AND TRADING | 33876 | L | B | SB | GE | Concreting/Widening and Drainage Improvement/Rehabilitation of Scout Albano St., Quezon City | Quezon City | 2015-08-26 | 1st | QC 2nd DEO | LF | 9.206 | 206 | 2015-02-25 | 2015-09-18 | 0.16% | O | 0.368 | 0.24 | 0.15 | 0.023 | 0.05 | 0.05 | 88.1% | -
TRICHES CONSTRUCTION AND TRADING | 33876 | L | B | SB | GE | Concreting/Widening and Drainage Improvement/Rehabilitation of Scout Albano St., Quezon City | Quezon City | 2015-12-04 | Final | QC 2nd DEO | LF | 9.2055 | 206 | 2015-02-25 | 2015-09-18 | 0.00% | C | 0.42 | 0.133 | 0.3 | - | - | - | 85.3% | 86.988% Satisfactory
Tri-Dom Trading & Construction | 10843 |  |  |  |  | Concreting of Barangay Road, San Isidro Village |  | 2010-02-24 |  | V |  | 1.149 | 120 |  |  |  | O | 0.364 | 0.24 | 0.15 | 0.03 | 0.035 | 0.05 | 86.9 | -
Tri-dom Trading & Cosntruction | 10843 | L | B | MA | GE1 | Road Upgrading (Gravel to Paved) Baras-Gigmoto-Viga Road (K0031+500-K0031+900) Puraran-Benticayan Sect. | Baras, Catanduanes | 2011-08-17 | 1st | V | LF | 9.334 | 90 | 2011-06-22 | 2011-09-19 | -3.35 | O | 0.386 | 0.094 | 0.116 | 0.03 | 0.056 | 0.033 | 71.5 | -
Trilex Builders and Construction Supply |  | L | B |  |  | Rehabilitation and Development of Paco Market Wet Section | Pedro Gil cor. Angel Linao, Paco Manila | 2014-09-24 | Final | PRRC | LF | 18.889 | 75 | 2013-11-11 |  | 0 | C | 0.401 | 0.2 | 0.3 | - | - | - | - | 91.00% V. Satisfactory
Trilex Builders and Cosntruction Supply, Inc. | 26590 |  |  |  |  | Rehabilitation and Development of Estero de Binondo | Binondo, City of Manila | 2015-10-29 | 1st | PRRC | LF | 9.968 | 150 | 2015-04-28 | - | 1.64 | O | 0.321 | 0.3 | 0.134 | 0.015 | 0.026 | 0.05 | 84.6 | -
Trilex Builders and Cosntruction Supply, Inc. | 26590 |  |  |  |  | Rehabilitation and Development of Estero de Binondo | Binondo, City of Manila | 2015-12-01 | Final | PRRC | LF | 9.968 | 150 | 2015-04-28 | - | 1.64 | C | 0.396 | 0.2 | 0.2836 | - | - | - | 87.96 | 85.58% Satisfactory
Trilex Builders and Cosntruction Supply, Inc. | 26590 |  |  |  |  | Construction and Development of Linear Park along San Juan River-Ermitaño Creek | Ermitaño Creek, City of San Juan | 2016-02-04 | 1st | PRRC | LF | 11.134 | 150 | 2015-01-19 | 2016-01-09 | 7.5 | O | 0.347 | 0.3 | 0.075 | 0.018 | 0.042 | 0.05 | 83.2 | -
Trilex Builders Construction and Supply |  | L |  |  |  | Rehabilitation and Development of Paco Market Wet Section | Pedro Gil Cor. Angel Linao, Paco Manila | 2014-04-08 | 1st | PRRC | LF | 18.889 | 75 | 2013-11-11 |  | 0 | O | 0.362 | 0.3 | 0.15 | 0.02 | 0.035 | 0.05 | 91.7 | -
Trilex Builders Construction and Supply |  | L | B |  |  | Bioremediation Project in Estero de Valencia: Enclosed Wetland for Drainages (PR-BT-02) | Estero de Valencia, Manila | 2014-10-17 | 1st & Final | PRRC | LF | 4.682 | 120 | 2014-01-07 | 2014-05-07 | 0 | C | 0.361 | 0.2 | 0.3 | - | - | - | 86.1 | *86.10% Satisfactory
Trilex Builders Construction and Supply |  | L |  |  |  | Poblacion Linear Park and Makati/Mandaluyong Bridge Link-Up | Bgy. Poblacion, Makati City | 2014-03-06 | 1st & Final | PRRC |  | 0.674 | 45 |  |  |  | C | 0.485 | 0.2 | 0.3 | - | - | - | 95.8 | *95.8% Very Satisfactory
Trilex Builders Construction and Supply | 26590 | L | B | SB | GB1 | Const. of MPB at the Albert E/S (Phase I) |  | 2008-08-14 | 1st | NCR |  | 1.919 | 90 |  |  |  | O | 0.231 | 0.3 | 0.1 | 0.03 | 0.047 | 0.1 | 80.8 | -
Trinity Construction and Development | 27755 |  |  |  |  | Const. of 1 unit 2 CL S/B at Salingkubong PS |  | 2010-03-06 |  | VII |  | 0.852 | 100 |  |  |  | O | 0.392 | 0.217 | 0.15 | 0.03 | 0.045 | 0.05 | 88.4 | -
Triparco Development Corporation | 23327 | L | A | MA | GE | Rehabilitation/Reconstruction/Upgrading of Nasipit Port Road, Chainage 000-Chainage 0096 | Nasipit, Agusan del Norte | 2014-10-21 | 1st & Final | XIII | LF | 0.89779 | 37 | 2014-02-04 | 2014-03-12 | 26.78% | C | 0.423 | 0.133 | 0.3 | - | - | - | 85.6% | 85.6% Satisfactory
Triparco Development Corporation | 23327 | L | A | MA | GE | Rehab./Reconst./Improvement of Butuan City - Cagayan de Oro - Iligan (Agusan - Misamis Or.), K1247+400 - K1248+640 | Butuan City | 2014-08-15 | 1st & Final | XIII | LF | 9.3257 | 80 | 2014-05-10 | 2014-07-28 | 57.18 | C | 0.477 | 0.133 | 0.3 |  |  |  | 91 | 91.00% Very Satisfactory
TRI-PARCO DEVELOPMENT CORPORATION | 23327 | L | A | MA | GE | Construction of Telaje Flood Control, Tandag City 1st LD. | Tejale, Tandag City, Surigao del Sur | 2015-08-27 | 1st | Surigao del Sur 1st | LF | 32.568 | 119 | 2015-07-07 | 2015-11-02 | (+) 21.19% | O | 0.392 | 0.238 | 0.15 | 0.03 | 0.035 | 0.05 | 89.5% | -
TRIPARCO DEVELOPMENT CORPORATION/RAMISES CONSTRUCTION JOINT VENTURE | 0 | L | A | MA | GE | Completion of Agao River Dike Protection Barangay Agao, Butuan, Agusan del Norte, 1st Legislative District | Butuan, Agusan del Norte, 1st Legislative District | 2015-11-18 | 2nd | Butuan City DEO | LF | 45.6295 | 293 | 2015-03-10 | 2015-12-27 | (+) 10.00 | OG | 0.4 | 0.3 | 0.15 | 0.03 | 0.047 | 0.05 | 97.7% | 97.7% Outstanding
TRIPARCO DEVELOPMENT/ RAMISES CONSTRUCTION JOINT VENTURE | JV-14-553 | L | A | MA | GE | Completion of Agao River Dike Protection, Brgy. Agao, Butuan City | Brgy. Agao, Butuan City | 2015-09-01 | 1st | Butuan City | LF | 45.63 | 263 | 2015-03-10 | 2015-11-27 | (+) 22.79% | O | 0.399 | 0.226 | 0.15 | 0.03 | 0.065 | 0.05 | 92% | -
Triple 8 Construction & Supply | 10684 |  |  |  |  | Flood Control Angat River Paltao |  | 2010-06-10 |  | III |  | 4.772 | 105 |  |  |  | O | 0.389 | 0.24 | 0.15 | 0.015 | 0.053 | 0.033 | 88 | -
Triple 8 Construction & Supply | 10684 | L | B | MA | GE1 | Widening of Cavite-Batangas Rd., Km.25+306-Km.26+960 | Imus, Cavite | 2013-08-14 | Final | IVA | LF | 31.912 | 369 | 2012-02-07 | 2013-02-09 | 0 | C | 0.347 | 0.2 | 0.3 | - | - | - | 84.7 | 83.74% Satisfactory
Triple 8 Construction & Supply | 10684 | L | B | MA | GE1 | Widening of Cavite-Batangas Rd., Km.25+306-Km.26+960 | Imus, Cavite | 2012-11-23 | 1st | IVA | LF | 31.912 | 369 | 2012-02-07 | 2013-02-08 | -3.49 | O | 0.312 | 0.3 | 0.115 | 0.03 | 0.041 | 0.033 | 83.1 | -
Triple 8 Construction & Supply | 10684 | L | B | MA | GE1 | Widening of Manila-Cavite Rd. (Kawit-Noveleta Diversion Rd. / CEZ Diversion Rd.) inc. RROW Acquisition (Emergency Bays as holding areas for trucks & 40-footer vans for their maint. & repair) | Cavite Province | 2012-11-23 | 1st | IVA | LF | 31.52 | 180 | 2012-09-07 | 2013-03-05 | 0.06 | O | 0.31 | 0.26 | 0.15 | 0.03 | 0.045 | 0.033 | 82.8 | -
Triple 8 Construction & Supply | 10684 | L | B | MA | GE1 | Completion of Retaining Wall along R-10, Smokey Mountain | Tondo, Manila | 2013-03-20 | Final | NCR | LF | 4.324 | 100 | 2012-09-26 | 2013-01-03 | 6 | C | 0.485 | 0.068 | 0.3 | - | - | - | 85.3 | 83.80% Satisfactory
Triple 8 Construction & Supply | 10684 |  |  |  |  | Contract Package I, Const. of Slope Protection along Daang Maharlika, Calbiga-Tacloban Rd. Sect., Km.849+475 - Km.866+904 w/ exceptions |  | 2010-06-17 |  | VIII |  | 37.711 | 95 |  |  |  | O | 0.358 | 0.3 | 0.15 | 0.03 | 0.042 | 0.033 | 91.3 | -
TRIPLE 8 CONSTRUCTION & SUPPLY | 10684 | L | B | MA | GE | MFO 1- National Roads Network Services, Asset Preservation of National Roads, Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads including Drainage Based on Pavement Management System/Highway Development and Management-4 (HDM-4)(Intermittent Sections), Arterial Roads, Dasmariñas - Carmona Road, K0035+177 to K0035+105; MFO 1- National Road Network Services, Asset Preservation of National Roads, Network Development, Widening of National Roads, Secondary Roads, Pala - Pala Diversion Road, Chainage 493 to Chainage 509, Chainage 548 to Chainage 631 (Rehabilitation/Reconstruction) | Dasmariñas, Cavite | 2015-06-13 | Final | Cavite 1st DEO | LF | 3.348 | 45 | 2015-02-05 | 2015-03-21 | 0% | - | 0.462 | 0.133 | 0.3 | - | - | - | 89.5% | *89.5% Very Satisfactory
TRIPLE P CONSTRUCTION | 31316 | L | D | SB | GB | Construction of Barangay Inaban Multi-Purpose Building, Inaban, Dupax del Norte, Nueva Vizcaya | Inaban, Dupax del Norte, Nueva Vizcaya | 2015-09-03 | 1st & Final | NV 2nd DEO | LF | 0.953 | 60 | 2015-03-20 | 2015-05-18 | 0% | C | 0.46 | 0.133 | 0.3 | - | - | - | 89.3% | *89.3% Very Satisfactory
Triumph Builders & Steel Inc. | 2272 | L | B | MA | GB1 | Const. of MPB at Mauban South Elem. School |  | 2009-02-26 | 1st | IV-A |  | 2.701 | 60 |  |  |  | O | 0.343 | 0.3 | 0.15 | 0.03 | 0.037 | 0.05 | #VALUE! | -
Triumph Builders & Steel Inc. | 2272 |  |  |  |  | Construction of 3-Storey, 15 Classroom School Bldg. |  | 2010-04-19 |  | NHA |  | 21.886 | 150 |  |  |  | O | 0.3657 | 0.3 | 0.15 | 0.015 | 0.047 | 0.05 | 92.77 | -
Triumph Builders & Steel Inc. | 2272 | L | B | MA | GB1 | Construction of 3-Storey 15-Classroom School Building |  | 2009-06-18 | 1st | NHA |  | 18.113 | 150 |  |  |  | O | 0.3808 | 0.2522 | 0.15 | 0.024 | 0.0466 | 0.05 | 90.36 | -
Triumph Builders & Steel, Inc. |  | L |  |  | GB1 | Const. of 1 Unit 3-Storey School Building, Package 1 | Southville 9, Brgy. Pinugay, Baras, Rizal | 2012-08-24 | 1st | NHA | LF | 22.118 | 180 | 2012-03-01 | 2012-08-27 | -6.96 | O | 0.378 | 0.279 | 0.08 | 0.03 | 0.053 | 0.05 | 87 | -
Triumph Builders & Steel, Inc. |  | L |  |  | GB1 | Const. of 1 Unit 3-Storey School Building, Package 1 | Southville 9, Brgy. Pinugay, Baras, Rizal | 2012-05-10 | 1st | NHA | LF | 22.118 | 180 | 2012-03-01 | 2012-08-27 | 14.43 | O | 0.367 | 0.26 | 0.15 | 0.03 | 0.053 | 0.05 | 91 | -
TRM Construction and Development Corp. | 30731 |  |  |  |  | Construction of Livelihood, Production & Training Center |  | 2010-03-12 |  | NHA |  | 4.99 | 90 |  |  |  | O | 0.359 | 0.287 | 0.113 | 0.024 | 0.035 | 0.033 | 85.1 | -
TRM Construction and Development Corp. | 30731 | L | A | MA | GB1 | Construction of 3-Storey School Building |  | 2008-09-23 | 1st | NHA |  | 17.2 | 150 |  |  |  | O | 0.2831 | 0.3 | 0 | 0.03 | 0.032 | 0.1 | 74.51 | -
TRYST Builders Enterprises | 31164 | L | A | MA | GB | Completion of Multi-Purpose Building | Brgy. Poblacion, Bokod, Benguet | 2014-11-19 | 1st | CAR | LF | 9.0185 | 150 | 2014-09-29 | 2015-02-25 | 0.07% | O | 0.31 | 0.272 | 0.15 | 0.03 | 0.047 | 0.033 | 84.2% | 84.2% Satisfactory
TRYST Builders Enterprises | 31164 | L | A | SB | GE | Construction of Maton Flood Control, Calanasan, Apayao | Calanasan, Apayao | 2014-08-10 | 1st | CAR | LF | 3.8118 | 150 | 2014-03-21 | 2014-08-17 | 0.3 | O | 0.273 | 0.24 | 0.15 | 0.02 | 0.041 | 0.05 | 77.4
TRYST BUILDERS ENTERPRISES | 31164 | L | A | SB | GE | Construction of Maton Flood Control | Pudtol, Apayao | 2015-06-09 | Final | Apayao 2nd DEO | LF | 3.812 | 150 | 2014-03-26 | 2014-08-22 | 0% | C | 0.396 | 0.2 | 0.3 | - | - | - | 89.6% | *82.28% Satisfactory
TRYST BUILDERS ENTERPRISES | 31164 | L | A | MA | GE | Road Upgrading (Unpaved to Paved) along Apayao (Calanasan) - Ilocos Norte Road, K0608+(-726) -K0608+(-693), K0608+(-674) - K0608+(-377), K0608+1368 - K0609+356 | Bunot Section, Calansan, Apayao | 2015-06-10 | 1st | Apayao 2nd DEO | LF | 22.947 | 170 | 2015-03-03 | 2015-08-19 | (+) 7.90% | O | 0.292 | 0.186 | 0.15 | 0.024 | 0.045 | 0.05 | 74.7% | -
TRYST BUILDERS ENTERPRISES | 31164 | L | A | MA | GE | Road Upgrading (Unpaved to Paved) along Apayao (Calanasan) - Ilocos Norte Road, K0608+1368 to K0609+356, Bunot Section, Calanasan, Apayao | Calanasan, Apayao | 2015-08-26 | 1st | Apayao 2nd DEO | LF | 22.947 | 200 | 2015-03-03 | 2015-09-18 | 4.08% | O | 0.381 | 0.222 | 0.15 | 0.023 | 0.047 | 0.05 | 87.3% | -
TRYST BUILDERS ENTERPRISES | 31164 | L | A | MA | GE | Road Upgrading (Unpaved to Paved) Along Apayao-Ilocos Norte Road Tangalagan | Calanasan, Apayao | 2015-11-15 | Final | Apayao 2nd | LF | 22.947 | 200 | 2015-03-03 | 2015-09-18 | - | C | 0.387 | 0.2 | 0.3 | - | - | - | 88.7% | 88.7% Satisfactory
TSD Builders Construction and Supply | 22129 | L | A | MA | GE | Const./Widening/Upgrading/Rehab. of Access Road to declared tourism destinationalong Bacolod City Boundary Road | Bacolod City, Negros Occidental | 2014-08-11 | Final | VI | LF | 23.3498 | 269 | 2013-02-06 | 2013-08-02 | 0 | C | 0.416 | 0.2 | 0.3 |  |  |  | 91.6 | 84.82% Satisfactory
TSD Builders Construction and Supply | 22129 | L | A | MA | GE1 | Const./Widening/Upgrading/Rehab. of Access Rd. to Declared Tourism Destination along Bacolod City Bdry. Rd. | Bacolod City, Negros Occidental | 2013-08-06 | 1st | VI | LF | 23.35 | 218 | 2013-02-26 | 2013-10-01 | -8.71 | O | 0.397 | 0.24 | 0.063 | 0.023 | 0.047 | 0.033 | 80.3
TSD BUILDERS CONSTRUCTION AND SUPPLY | 22129 | L | A | MA | GE | Repair/Rehabilitation/Improvement (Concreting/Additional Pavement Width) of Bacolod North Road, S00394NR, K0079+584 - K0080+060 with exception, Sagay City, Negros Occidental | Sagay City, Negros Occidental | 2015-11-19 | 1st | Negros Occidental 1st DEO | LF | 10.5847 | 110 | 2015-08-24 | 2015-12-11 | (+)3.86 | OG | 0.337 | 0.27 | 0.15 | 0.03 | 0.055 | 0.05 | 89.2% | 89.2% Very Satisfactory
T-Square Builders | 14268 | L | B | MA | GE | Road Upgrading (Gravel to Concrete) along Paco--Roxas-Arakan Valley Junction Davao-Bukidnon Road, K1689+788 - K1691+403.80 | Arakan, Cotabato Province | 2014-08-16 | 1st & Final | XII | LF | 80.1813 | 320 | 2013-08-15 | 2014-06-10 | 21.71 | C | 0.42 | 0.186 | 0.3 |  |  |  | 90.6 | 90.60% Very Satisfactory
T-Square Builders | 14268 | L | B | MA | GE | Widening of Digos-Makar Road, South Cotabato K1640+251 to K1642+337, Katangawan Section | South Cotabato | 2014-08-16 | 1st & Final | XII | LF | 46.9533 | 180 | 2014-01-26 | 2014-06-24 | 0 | C | 0.412 | 0.191 | 0.3 |  |  |  | 90.3 | 90.30% Very Satisfactory
T-Square Builders | 14268 | L | B | MA | GE1 | Const. of Additional 2 Lanes along Davao-Cotabato Road (Poblacion Bansalan Sect.) | Bansalan, Davao del Sur | 2011-04-02 | 1st | XI | LF | 9.638 | 150 | 2011-01-04 | 2011-06-02 | 56.83 | O | 0.385 | 0.3 | 0.15 | 0.03 | 0.035 | 0.05 | 95 | -
T-Square Builders | 14268 | L | B | MA | GE1 | Impvt./Conc. of Road at Bansalan-Mt. Apo National Park Road |  | 2009-03-06 | 2nd | XI |  | 28.919 | 270 |  |  |  | O | 0.274 | 0.273 | 0.15 | 0.03 | 0.054 | 0.033 | #VALUE! | -
T-Square Builders | 14268 | L | B | MA | GE1 | Impvt./Conc. of Road at Bansalan-Mt. Apo National Park Road |  | 2008-11-19 | 1st | XI |  | 28.919 | 270 |  |  |  | O | 0.214 | 0.279 | 0.1 | 0.03 | 0.04 | 0.1 | 76.3 | -
T-Square Builders | 14268 | L | B | MA | GE1 | Conc. of Road & Reblocking, Marbel-Makar Road, Palian Section |  | 2009-03-20 | 1st | XII |  | 15.102 | 180 |  |  |  | O | 0.363 | 0.24 | 0.15 | 0.03 | 0.035 | 0.05 | #VALUE! | -
T-Square Builders | 14268 | L | B | MA | GE1 | Const. of Drainage Structure along Marbel-Makar Rd. | Koronadal City, South Cotabato | 2012-11-24 | Final | XII | LF | 12.5 | 328 | 2011-12-08 | 2012-10-30 | 0 | C | 0.482 | 0.133 | 0.3 | - | - | - | 91.5 | 86.82% Satisfactory
T-SQUARE BUILDERS | 14268 | L | A | MB | GE | Widening of National Roads: Cotabato-Marbel Road, K1720+585 - K1722+992, South Cotabato Modified to MFO1-Widening of National Roads along National Road 1 (N1) Daang Maharlika / Asian Highway 26-Cotabato-Marbel Road, K1720+585 to K1722+240.40 | South Cotabato | 2015-11-09 | Final | South Cotabato First DEO | LF | 33.3223 | 195 | 2015-04-01 | 2015-10-12 | (+) 0.5% | C | 0.453 | 0.142 | 0.3 | - | - | - | 89.5% | 89.5% Very Satisfactory
Tuchar Construction | 13644 | L | B | MA | GE | Rehabilitation of Drainage System along O. De Guzman Street & Vicinity Brgy. IVC | Marikina City | 2014-11-29 | 1st & Final | NCR | LF | 13.9494 | 180 | 2014-02-11 | 2014-08-09 | 0% | C | 0.469 | 0.133 | 0.3 | - | - | - | 90.2% | 90.2% Very Satisfactory
Turquoise Construction & Trading (Formerly: Turquoise Construction) | 21801 | L | B | MA | GE | Construction of Slope Protection along Burakan Creek | Cabalantian, Bacolor, Pampanga | 2014-11-17 | 1st | III | LF | 6.6732 | 118 | 2014-08-04 | 2014-11-29 | 0.28% | O | 0.293 | 0.24 | 0.15 | 0.03 | 0.037 | 0.033 | 78.3% | 78.3% Unsatisfactory
TURQUOISE CONSTRUCTION AND TRADING | 21801 | L | B | SB | GE | Rehabilitation of Drainage Canal along Dolores Creek, City of San Fernando, Pampanga | City of San Fernando, Pampanga | 2015-06-01 | Final | Pampanga 1st DEO | LF | 10.659 | 150 | 2014-08-08 | 2015-01-04 | 0% | C | 0.44 | 0.2 | 0.3 | - | - | - | 94% | *94% Very Satisfactory
TWIN DRAGON CONSTRUCTION | 11392 | L | B | MA | GB | Construction of Multi-Purpose Building Balatucan | Looc, Romblon | 2015-06-12 | 1st | Romblon DEO | LF | 3.919 | 120 | 2015-02-24 | 2015-06-23 | -2% | O | 0.398 | 0.242 | 0.13 | 0.02 | 0.047 | 0.033 | 87% | -
TWIN DRAGON CONSTRUCTION | 11392 | L | B | MA | GB | Constuction of Multi-Purpose Building, Mari-Sur | San Andres, Romblon | 2015-11-21 | Final | Romblon DEO | LF | 5.1179 | 120 | 2015-02-25 | 2015-06-24 | 0 | C | 0.494 | 0.133 | 0.3 | - | - | - | 92.7% | 92.7% Very Satisfactory
Twina Builders and Supply | 23897 | L | D | SB | GB | Construction of One (1) Storey, Three (3) Classroom School Building, Moria E/S, Banlag, Monkayo, Comval Province | Comval Province | 2014-08-09 | 1st & Final | XI | LF | 2.1973 | 45 | 2014-05-22 | 2014-07-05 | 0 | C | 0.49 | 0.133 | 0.3 |  |  |  | 92.3 | 92.30% Very Satisfactory
Twina Builders and Supply | 23897 |  |  |  |  | Rehabilitation/Repair of Boy's Residence Hall | Sto. Niño Tugbok District, Davao City | 2014-08-14 | 1st & Final | DOST | L | 2.226 | 90 | 2014-03-24 | 2014-06-21 | 96.11 | C | 0.487 | 0.2 | 0.1833 | - | - | - | 87.03 | *87.03% Satisfactory
Twina Builders and Supply | 23897 | L | D | SB | GB | Completion of the DPWH-Standard Two (2) Storey Building of Agusan del Sur 2nd District Engineering Office | Karaos, San Francisco, Agusan del Sur | 2014-10-23 | 1st | XIII | LF | 9.5058 | 180 | 2014-09-19 | 2015-03-17 | 34.45% | O | 0.325 | 0.284 | 0.15 | 0.02 | 0.022 | 0.05 | 85.1% | 85.1% Satisfactory
Twina Builders and Supply | 23897 | L | D | SB | GE | Local Infrastructure Program-Construction of Local Road at San Roque | Bislig , Surigao del Sur | 2014-10-24 | 1st & Final | XIII | LF | 4.98 | 133 | 2014-04-29 | 2014-09-08 | 0% | C | 0.416 | 0.145 | 0.278 | - | - | - | 83.9% | 83.9% Satisfactory
Ubas Construction | 18875 | L | B | MA | GE1 | Const./Impvt./Rehab. of La Perla-Cabulaloan-Yabyaban Road |  | 2009-03-03 | 4th | VIII |  | 14.16 | 467 |  |  |  | O | 0.251 | 0.225 | 0.07 | 0.03 | 0.037 | 0.05 | #VALUE! | -
Ubas Construction | 18875 | L | B | MA | GE1 | Const./Impvt./Rehab. of La Perla-Cabulaloan-Yabyaban Road |  | 2008-08-31 | 3rd | VIII |  | 14.16 | 270 |  |  |  | O | 0.344 | 0.225 | 0.05 | 0.03 | 0.032 | 0.067 | 74.8 | -
UBAS CONSTRUCTION | 18875 | L | AAA | MA | GE | Rehabilitation Of Binaliw Bridge (B00337SM) along Daang Maharlika (SM) (San Isidro- San Juanico Bridge), Calbayog City, Samar 1st LD | Calbayog City, Samar 1st LD | 2015-09-02 | 1st | Samar 1st DEO | LF | 5.472 | 90 | 2015-03-06 | 2015-06-03 | (-)15.38 | O | 0.346 | 0.3 | 0 | 0.01 | 0.035 | 0.033 | 72.4% | -
UKC Builders, Inc. | 10759 | L | AAA | LB | GE1 | Bayanihan sa Iligan Village, Brgy. Sta. Elena | Iligan City | 2013-03-15 | Final | X | LF | 66.5 | 240 | 2012-07-27 | 2013-03-23 | 13.75 | C | 0.429 | 0.133 | 0.3 | - | - | - | 86.2 | 89.44% V. Satisfactory
UKC Builders, Inc. | 10759 | L | AAA | LB | GE1 | Cebu North Coastal Road, Phase I |  | 2008-09-03 | 1st | VII |  | 43.189 | 228 |  |  |  | O | 0.38 | 0.225 | 0.07 | 0.03 | 0.037 | 0.1 | 84.2 | -
UKC Builders, Inc. | 10759 | L | AAA | LB |  | WHARF EXTENSION, PORT OF CAGAYAN DE ORO | CAGAYAN DE ORO CITY, MISAMIS ORIENTAL | 2015-07-24 | 1st | PPA | LF | 59.254 | 300 | 2015-02-16 | 2015-11-29 | 0.928 | O | 0.37 | 0.3 | 0.15 | 0.02 | 0.065 | 0.05 | 95.5 | -
UKC Builders, Inc./ Equi-parco Construction. Co., Inc - JV | J.V. -09-097 | L | AAA | LB | GE5 | Cagayan de Oro Improvement Project (Ports & Harbor) | Port of Cagayan de Oro, Cagayan de Oro City | 09/05-09/11 | 3rd | PPA | LF | 187.898 | 540 | 2010-04-15 | 2011-10-06 | 0.057 | O | 0.4674 | 0.2 | 0.3 | - | - | - | 96.74 | -
UKC Builders, Inc./ Equi-parco Construction. Co., Inc - JV | J. V.-09-097 | L | AAA | LB | GE5 | Const. of Cagayan de Oro Improvement Project (Ports & Harbor) | Port of Cagayan de Oro, Ca. de Oro City | 02/2-5/11 | 1st | PPA | LF | 187.898 | 540 | 2010-04-15 | 2011-10-06 | 3.51 | O | 0.3553 | 0.2983 | 0.15 | 0.03 | 0.07 | 0.05 | 95.36 | -
UKC Builders, Incorporated | 10759 | L |  | LB |  | Wharf Extension, Port of Cagayan De Oro | Cagayan de Oro City, Misamis Oriental | 2016-01-28 | Final | PPA | LF | 59.254 | 300 | 2015-02-16 | 2015-11-29 | 0 | F | 0.4974 | 0.2 | 0.3 | - | - | - | 99.74 | 97.20% Outstanding
Ulticon Builders Inc. | 17267 | L | AAA | LB | GE1 | Rehab./Reconst. of Sayre Highway (Kisolon-Lumbo Section) |  | 2009-09-04 | 1st | X |  | 189.228 | 300 |  |  |  | O | 0.286 | 0.29 | 0.15 | 0.03 | 0.051 | 0.033 | 84 | -
Ulticon Builders Inc. | 17267 |  |  |  |  | Rehabilitation/Improvement of National Road along Daang Maharlika |  | 2010-02-27 |  | XI |  | 144.738 | 270 |  |  |  | O | 0.368 | 0.3 | 0.15 | 0.03 | 0.055 | 0.05 | 95.3 | -
Ulticon Builders Inc. | 17267 |  |  |  |  | Const./Impvt. of Davao Del Sur-Sarangani Coastal Road, Meybio-Glan Bdry. Section |  | 2010-02-24 |  | XI |  | 96.289 | 280 |  |  |  | O | 0.338 | 0.3 | 0.15 | 0.03 | 0.056 | 0.05 | 92.4 | -
Ulticon Builders Inc. | 17267 |  |  |  |  | Conc. of San Ildefonso-Hulid Sect. along Cateel-Compostela Rd. |  | 2010-03-03 |  | XI |  | 62.856 | 300 |  |  |  | O | 0.309 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 83.4 | -
Ulticon Builders Inc. | 17267 |  |  |  |  | Repair/Rehab./Impvt. of Daang Maharlika Rd. |  | 2010-06-04 |  | XI |  | 88.226 | 180 |  |  |  | O | 0.374 | 0.284 | 0.102 | 0.03 | 0.051 | 0.033 | 87.4
Ulticon Builders Inc. | 17267 |  |  |  |  | Conc. of San Alfonso-Hulid Sect. along Cateel-Compostela Rd. |  | 2010-06-06 |  | XI |  | 62.856 | 330 |  |  |  | O | 0.326 | 0.234 | 0.15 | 0.03 | 0.056 | 0.05 | 84.6 | -
Ulticon Builders Inc. | 17267 | L | AAA | LB | GE1 | CP-10: Imprvt./ Conc. of Surigao-Davao Oriental Coastal Road, (Manay-Boston) Boston Section |  | 2009-09-11 | 3rd | XI |  | 286.477 | 600 |  |  |  | O | 0.373 | 0.3 | 0.15 | 0.03 | 0.054 | 0.033 | 94 | -
Ulticon Builders Inc. | 17267 | L | AAA | LB | GE1 | Impvt./Conc. of Surigao Sur-Davao Oriental Coastal Road (Manay Boston) Boston Section |  | 2009-06-09 | 2nd | XI |  | 286.479 | 600 |  |  |  | O | 0.367 | 0.3 | 0.15 | 0.03 | 0.065 | 0.05 | 96.2 | -
Ulticon Builders Inc. | 17267 | L | AAA | LB | GE1 | CP 10: Impv't./Conc. of Surogao Sur-Davao Oriental Coastal Road (Manay-Boston) Boston Section |  | 2008-11-26 | 1st | XI |  | 286.479 | 600 |  |  |  | O | 0.345 | 0.284 | 0.1 | 0.03 | 0.06 | 0.1 | 91.9 | -
Ulticon Builders Inc. | 17267 | L | AAA | LB | GE1 | Rehab./Upgrading of Digos Diversion Road |  | 2009-09-05 | 2nd | XI |  | 46.834 | 220 |  |  |  | O | 0.374 | 0.24 | 0.15 | 0.03 | 0.054 | 0.05 | 89.8 | -
Ulticon Builders Inc. | 17267 | L | AAA | LB | GE1 | Rehab./Reconst./Upgrading of Digos Diversion Road |  | 2009-05-30 | 1st | XI |  | 46.834 | 220 |  |  |  | O | 0.365 | 0.3 | 0.15 | 0.03 | 0.042 | 0.05 | 93.7 | -
Ulticon Builders Inc. | 17267 | L | AAA | LB | GE1 | Rehab./Reconst./Upgrading of Damaged Paved National Road along Daang Maharlika |  | 2009-09-07 | 1st | XI |  | 192.02 | 540 |  |  |  | O | 0.373 | 0.24 | 0.15 | 0.03 | 0.059 | 0.05 | 90.2 | -
Ulticon Builders Inc. | 17267 | L | AAA | LB | GE | Road Upgrading (Gravel to Concrete) of Bansalan Mt. Apo National Park Road | Davao del Sur | 2014-08-08 | 1st | XI | LF | 70.8334 | 231 | 2014-02-17 | 2014-09-16 | 0.58 | O | 0.381 | 0.284 | 0.15 | 0.03 | 0.047 | 0.05 | 94.2
Ulticon Builders Inc. | 17267 | L | AAA | LB | GE | Road Upgrading (Gravel to Concrete) of Bansalan Mt. Apo National Park Road | Davao del Sur | 2014-08-07 | Final | XI | LF | 56.5178 | 365 | 2013-03-19 | 2013-11-10 | 0 | C | 0.453 | 0.168 | 0.3 |  |  |  | 92.1 | 90.84% Very Satisfactory
Ulticon Builders Inc. | 17267 | L | AAA | LB | GE | Improvement/Upgrading (Gravel to Concrete) of Island Garden City of Samal (IGACOS) Circumferential Road (East Side) (Babak-Penaplata | Davao del Norte | 2014-10-29 | 1st & Final | XI | LF | 47.5283 | 190 | 2014-03-07 | 2014-09-12 |  | C | 0.394 | 0.134 | 0.3 | - | - | - | 82.8% | 82.8% Satisfactory
Ulticon Builders, Inc. | 17267 | L | AAA | LB | GE1 | Assets Preservation of Nat'l Rds. Int. Sect. Sayre Highway, a) K1555+270-K1556+000; b) K1559+000-K1560+000; c)K1560+330-K1561+000 | Maramag, Bukidnon | 2013-08-08 | Final | X | LF | 22.857 | 75 | 2013-01-24 | 2013-04-08 | 0 | C | 0.401 | 0.133 | 0.3 | - | - | - | 83.4 | 85.14% Satisfactory
Ulticon Builders, Inc. | 17267 | L | AAA | LB | GE1 | Assets Preservation of Nat'l. Rds. Gen. from Pvmt. Mgt. System Highway Dev't. & Mgt.-4 (HDM-4) (Int. Sect.) along Sayre Highway a)K1555+270-K1556+000; b)K1559+000-K1560+000; c)K1560+330-K1561+000 | Maramag, Bukidnon | 2013-03-20 | 1st | X | LF | 22.857 | 75 | 2013-01-24 | 2013-04-08 | -8.25 | O | 0.33 | 0.3 | 0.15 | 0.01 | 0.04 | 0.033 | 86.3 | -
Ulticon Builders, Inc. | 17267 | L | AAA | LB | GE1 | Widening of Sayre Highway, Lumbo-Musuan Sect., K1540+249-K1540+344 | Maramag, Bukidnon | 2013-08-20 | Final | X | LF | 21.668 | 183 | 2013-01-24 | 2013-07-25 | 8.2 | C | 0.388 | 0.133 | 0.3 | - | - | - | 82.1 | 83.12% Satisfactory
Ulticon Builders, Inc. | 17267 | L | AAA | LB | GE1 | Widening of Sayre Highway, Lumbo-Musuan Sect., K1540+249-K1540+344 | Maramag, Bukidnon | 2013-03-20 | 1st | X | LF | 20.504 | 153 | 2013-01-24 | 2013-06-25 | 49.89 | O | 0.361 | 0.249 | 0.15 | 0.01 | 0.035 | 0.033 | 83.8 | -
Ulticon Builders, Inc. | 17267 | L | AAA | LB | GE1 | Rehab./Impv't./Conc. of Surigao Sur-Davao Oriental Coastal Rd. (Manay-Boston Sect.) | Davao Oriental | 2012-08-17 | Final | XI | LF | 361.28 | 522 | 2010-03-24 | 2011-08-27 | -8.81 | C | 0.417 | 0.2 | 0.036 | - | - | - | 65.3 | 76.82% Unsatisfactory
Ulticon Builders, Inc. | 17267 | L | AAA | LB | GE1 | Rd. Upgrading (Gravel to Concrete) of Bansalan Mt. Apo Nat'l Park Rd., Bansalan | Davao del Sur | 2013-08-06 | 1st | XI | LF | 56.518 | 237 | 2013-03-19 | 2013-11-10 | 0.02 | O | 0.373 | 0.286 | 0.15 | 0.03 | 0.028 | 0.033 | 90
Ulticon Builders, Inc. | 17267 | L | AAA | LB | GE1 | Impv't./Conc. of Island Garden City of Samal (IGACOS) | Davao del Norte | 2013-03-17 | 3rd | XI | LF | 89.506 | 403 | 2012-03-28 | 2013-05-04 | 1.04 | O | 0.298 | 0.298 | 0.15 | 0.03 | 0.05 | 0.033 | 85.9 | -
Ulticon Builders, Inc. | 17267 | L | AAA | LB | GE1 | Widening of Davao-Cotabato Rd. | Davao del Sur | 2013-03-15 | 3rd | XI | LF | 121.663 | 415 | 2012-03-28 | 2013-05-16 | -5.05 | O | 0.302 | 0.3 | 0.1 | 0.03 | 0.056 | 0.05 | 83.8 | -
Ulticon Builders, Inc. | 17267 | L | AAA | LB | GE1 | Widening of Davao-Cotabato Rd. | Davao del Sur | 2012-11-23 | 2nd | XI | LF | 121.663 | 351 | 2012-03-28 | 2013-03-13 | -8.89 | O | 0.36 | 0.3 | 0.061 | 0.03 | 0.051 | 0.033 | 83.5 | -
Ulticon Builders, Inc. | 17267 | L | AAA | LB | GE1 | Widening of Davao-Cotabato Rd. | Davao del Sur | 2012-08-11 | 1st | XI | LF | 121.663 | 244 | 2012-03-28 | 2012-11-26 | -14.35 | O | 0.383 | 0.3 | 0.006 | 0.03 | 0.06 | 0.05 | 82.9 | -
Ulticon Builders, Inc. | 17267 | L | AAA | LB | GE1 | Impvt./Conc. of Island Garden City of Samal | Davao del Norte | 2012-11-28 | 2nd | XI | LF | 86.288 | 307 | 2012-03-28 | 2013-01-28 | 8.88 | O | 0.383 | 0.292 | 0.061 | 0.03 | 0.056 | 0 | 82.2 | -
Ulticon Builders, Inc. | 17267 | L | AAA | LB | GE1 | Impvt./Conc. of Island Garden City of Samal | Davao del Norte | 2012-08-22 | 1st | XI | LF | 86.288 | 214 | 2012-03-28 | 2012-10-27 | 0.03 | O | 0.359 | 0.231 | 0.15 | 0.03 | 0.051 | 0.033 | 85.4 | -
Unitec Builder Inc. | 4803 |  |  |  |  | Rehab. of Daang Maharlika Highway, Sect. 8, Allen-Malaga Rd. Sect., Km.687+366.55 - Km.690+866.55 w/ exceptions |  | 2010-06-16 |  | VIII |  | 96.441 | 200 |  |  |  | O | 0.357 | 0.3 | 0.15 | 0.03 | 0.042 | 0.033 | 91.2 | -
Unitec Builder Inc. | 4803 |  |  |  |  | Rehab. of Daang Maharlika Highway, Sect 7, Allen-Malaga Rd. Sect., Km.683+866.55 - Km.687+366.55 w/ exceptions |  | 2010-06-16 |  | VIII |  | 96.435 | 200 |  |  |  | O | 0.354 | 0.3 | 0.15 | 0.03 | 0.042 | 0.033 | 90.9 | -
Unitec Builder Inc. | 4803 |  |  |  |  | Rehab./Const./Upgrading of Damaged Paved National Rd. along Catarman-Laoang Rd. |  | 2010-06-14 |  | VIII |  | 47.963 | 150 |  |  |  | O | 0.35 | 0.24 | 0.15 | 0.03 | 0.042 | 0.05 | 86.2 | -
Unitec Builder Inc. | 4803 | L | A | MB | GE1 | Rehab./Impvt. of Balite-Seven Hills-Happy Valley Section |  | 2009-03-07 | 1st | VIII |  | 19.176 | 180 |  |  |  | O | 0.294 | 0.205 | 0.15 | 0.03 | 0.047 | 0.05 | #VALUE! | -
Unitec Builder Inc. | 4803 | L | A | MB | GE1 | Concreting of San Jose-Mandugang National Road |  | 2009-09-14 | 1st | VIII |  | 19.277 | 180 |  |  |  | O | 0.337 | 0.24 | 0.15 | 0.03 | 0.05 | 0.033 | 84 | -
Unitec Builder Inc. | 4803 | L | A | MB | GE | Widening Apitong - Paterno Road, K0908+(-868) - K0908+082 | Tacloban City | 2014-10-30 | 1st | VIII | LF | 26.5581 | 179 | 2014-09-15 | 2015-03-12 | 40% | O | 0.342 | 0.24 | 0.15 | 0.023 | 0.04 | 0.05 | 84.5% | 84.5% Satisfactory
Unitec Builder Inc. | 4803 | L | A | MB | GE1 | Widening of Sinunuc Bridge & Approaches, Phase I, along Zamboanga City-Labuan Road |  | 2008-11-18 | 2nd | IX |  | 21.668 | 436 |  |  |  | O | 0.354 | 0.289 | 0.1 | 0.03 | 0.045 | 0.1 | 91.8 | -
Unitec Builder Inc. | 4803 | L | A | MB | GE1 | Proposed Widening of Sinunuc Bridge & Approaches, Phase I, along Zamboanga City-Labuan Road |  | 2008-08-21 | 1st | IX |  | 21.672 | 436 |  |  |  | O | 0.311 | 0.24 | 0 | 0.03 | 0.042 | 0.067 | 69 | -
Unitec Builder Inc. | 4803 | L | A | MA | GE2 | Improvement/Rehabilitation of R.T. Lim Boulevard |  | 2009-05-26 | 1st | IX |  | 18.661 | 270 |  |  |  | O | 0.343 | 0.24 | 0.15 | 0.01 | 0.042 | 0.05 | 83.5 | -
Unitec Builder Inc. | 4803 | L | A | MB | GE1 | Improvement/Rehabilitation of R.T. Lim Boulevard |  | 2009-09-02 | 2nd | IX |  | 18.661 | 300 |  |  |  | O | 0.311 | 0.3 | 0.15 | 0.023 | 0.045 | 0.033 | 86.2 | -
Unitec Builder Inc. | 4803 |  |  |  |  | Proposed Widening of Sinunuc Bridge and Approaches, Phase II |  | 2010-02-22 |  | IX |  | 11.878 | 545 |  |  |  | O | 0.383 | 0.3 | 0.15 | 0.03 | 0.047 | 0.05 | 96 | -
Unitec Builder, Inc. | 4803 | L | A | MB | GE | Rehabilitation of Bridges at Ayala Bridge #2 along Zamboanga City-Labuan-Limpapa Road | Zamboanga City | 2014-08-05 | Final | IX | LF | 30.9632 | 505 | 2012-06-28 | 2013-11-13 | 0 | C | 0.453 | 0.133 | 0.3 |  |  |  | 88.6 | 85.89% Satisfactory
Unitec Builder, Inc. | 4803 | L | A | MB | GE1 | Rd. Upgrading (Gravel to Paved) Int. Sect., Zamboanga West Coast Rd., Limpapa-Sibuco Sect.) K1979+(-685)-K1980+000- K1981+980 Re: K1979+(-685)-K1981+980 w/ exceptions | Sibuco, Zamboanga del Norte | 2013-08-05 | 1st | IX | LF | 46.026 | 201 | 2013-02-21 | 2013-09-09 | 1.54 | O | 0.343 | 0.238 | 0.15 | 0.03 | 0.037 | 0.033 | 83.1
Unitec Builder, Inc. | 4803 | L | A | MB | GE1 | Rehab./Reconst./Strengthening of Bridges at Ayala Bridge #2 along Zamboanga City-Labuan-Limpapa Rd. | Zamboanga City | 2013-08-05 | 4th | IX | LF | 30.963 | 375 | 2012-06-28 | 2013-07-07 | -14.98 | O | 0.374 | 0.3 | 0 | 0.03 | 0.047 | 0.033 | 78.4
Unitec Builder, Inc. | 4803 | L | A | MB | GE1 | Impv't./Downgrading of Zamboanga City/Zamboanga del Norte Bdry. to Sibuco, Limapa-Malayal Sect., Sta.1978+640-Sta.1979+680 w/ exception | Zamboanga del Norte | 2013-08-05 | Final | IX | LF | 64.362 | 285 | 2012-05-23 | 2013-03-03 | - | C | 0.452 | 0.014 | 0 | - | - | - | 46.6 | 66.64% Poor
Unitec Builder, Inc. | 4803 | L | A | MB | GE1 | Impv't./Downgrading of Zamboanga del Norte, Brgy. to Sibuco, Limpapa-Malayal Sect., Sta.1978+640-Sta.1979+680 w/ equation | Zamboanga del Norte | 2013-03-12 | 2nd | IX | LF | 64.317 | 225 | 2012-05-23 | 2013-01-02 | - | O | 0.367 | 0.3 | 0 | 0.03 | 0.042 | 0.033 | 77.2 | -
Unitec Builder, Inc. | 4803 | L | A | MB | GE1 | Impvt./Downgrading of Zamboanga City/Zamboanga del Norte Bdry. to Sibuco, Limpapa-Malayal Sect., Sta.1978+640-Sta.1979+680 w/ equation | Zamboanga del Norte | 2012-11-19 | 1st | IX | LF | 64.317 | 225 | 2012-05-23 | 2013-01-02 | 39.41 | O | 0.332 | 0.211 | 0.15 | 0.03 | 0.055 | 0.05 | 82.8 | -
Unitec Builder, Inc. | 4803 | L | A | MB | GE1 | Rd. Upgrading (Gravel to Paved) Int. Sect., Siocon-Sirawai Rd., K2080+000-K2081+300 | Zamboanga del Norte | 2013-03-17 | 1st | IX | LF | 37.75 | 105 | 2013-02-04 | 2013-05-19 | 0.03 | O | 0.329 | 0.234 | 0.15 | 0.03 | 0.045 | 0.033 | 82.1 | -
Unitec Builder, Inc. | 4803 | L | A | MB | GE1 | Rehab./Reconst./Strengthening of Bridges at Ayala Bridge #2 along Zamboanga City-Labuan-Limpapa Rd. | Zamboanga City | 2013-03-12 | 3rd | IX | LF | 30.776 | 325 | 2012-06-28 | 2013-05-18 | -12.85 | O | 0.391 | 0.3 | 0.022 | 0.03 | 0.042 | 0.033 | 81.8 | -
Unitec Builder, Inc. | 4803 | L | A | MB | GE1 | Rehab./Upgrading of RT Lim Boulevard, (Km.1940+314-Km.1940+2034) Baliwasan Seaside Sect. | Zamboanga City | 2012-03-20 | Final | IX | LF | 17.404 | 210 | 2011-07-04 | 2012-01-29 | 2 | C | 0.404 | 0.133 | 0.3 | - | - | - | 83.7 | 83.70% Satisfactory
Unitec Builder, Inc. | 4803 | L | A | MB | GE1 | Road Upgrading (Gravel to Paved) based on Gravel Road Strategies/HDM-4 (IS), Siocon-Sirawai Road (Km.2076+193-Km.2077+913) | Zamboanga del Norte | 2012-03-22 | Final | IX | LF | 38.058 | 158 | 2011-04-04 | 2011-12-07 | 0 | C | 0.341 | 0.133 | 0.3 | - | - | - | 77.4 | 82.50% Satisfactory
Unitec Builder, Inc. | 4803 | L | A | MB | GE1 | Rehab./Reconst./ Strengthening of Bridges at Ayala Bridge #2 along Zamboanga City-Labuan-Limpapa Rd. | Zamboanga City | 2012-11-19 | 2nd | IX | LF | 30.776 | 295 | 2012-06-28 | 2013-04-18 | -10 | O | 0.36 | 0.3 | 0.05 | 0.03 | 0.053 | 0.033 | 82.6 | -
Unitec Builder, Inc. | 4803 | L | A | MB | GE1 | Rehab./Reconst./Strengthening of Bridges at Ayala Bridge #2 along Zamboanga City-Labuan-Limpapa Rd. | Zamboanga City | 2012-08-13 | 1st | IX | LF | 30.776 | 295 | 2012-06-28 | 2013-04-18 | -0.29 | O | 0.4 | 0.3 | 0.147 | 0.023 | 0.032 | 0.033 | 93.5 | -
Unitec Builder, Inc. / EZJones Const., Inc. (JV) | JV-11-363 | L | A | MB | GE1 | Const./Repair/Rehab./Impv't. of San Isidro-Lope De Vega Rd. | San Isidro, Northern Samar | 2012-08-15 | 1st | VIII | LF | 142.362 | 244 | 2012-03-22 | 2012-11-20 | 14.92 | O | 0.367 | 0.3 | 0.15 | 0.03 | 0.04 | 0.033 | 92 | -
Unitec Builder, Inc. / EZJones Const., Inc. (JV) | JV-11-121 | L | A | MB | GE1 | Rd. Upgrading of San Isidro-Lope De Vega Rd. (Sta.0+000-Sta.3+650 w/ exception) | San Isidro, Northern Samar | 2012-08-15 | 2nd | VIII | LF | 94.084 | 350 | 2011-12-26 | 2012-12-09 | 25.5 | O | 0.357 | 0.3 | 0.15 | 0.03 | 0.04 | 0.033 | 91 | -
Unitec Builder, Inc. / EZJones Const., Inc. (JV) | JV-11-363 | L | A | MB | GE1 | Concrete Paving of San Isidro-Lope De Vega Rd., Sta.1+860-Sta.8+250 with exceptions | San Isidro, Northern Samar | 2012-08-15 | 1st | VIII | LF | 137.989 | 300 | 2012-04-25 | 2013-02-18 | 7.91 | O | 0.348 | 0.237 | 0.15 | 0.03 | 0.04 | 0.033 | 83.8 | -
Unitec Builder, Inc. / EZJones Construction, Inc. (JV) | JV-11-230 | L | A | MB | GE1 | Conc. of Trujillo-E. Duran-Gemaraganan Rd. (Sta. 745+500-Sta. 749+340) w/ exceptions, Bobon & Lope de Vega | Northern Samar | 2013-03-20 | Final | VIII | LF | 96.971 | 390 | 2012-03-22 | 2013-04-15 | 5.9 | C | 0.459 | 0.133 | 0.3 | - | - | - | 89.2 | 90.58% V. Satisfactory
Unitec Builder, Inc. / EZJones Construction, Inc. (JV) | JV-11-300 | L | A | MB | GE1 | Const./Repair/Rehab./Impv't. of San Isidro-Lope de Vega Rd. | San Isidro, Northern Samar | 2013-03-20 | Final | VIII | LF | 142.362 | 364 | 2012-03-16 | 2013-03-14 | 0 | C | 0.42 | 0.2 | 0.3 | - | - | - | 92 | 90.35% V. Satisfactory
Unitec Builder, Inc. / RNMK Construction and Development (JV) | JV-12-315 | L | A | MB | GE1 | Rd. Upgrading (Gravel to Paved) of Bugko-Nenita-Mirador Cagpanitan-De Maria-San Jose Rd., Sta.6+141-Sta.11+091 w/ exceptions | Mondragon, Northern Samar | 2013-08-09 | 1st | VIII | LF | 134.287 | 300 | 2013-02-27 | 2013-12-23 | 24.42 | O | 0.356 | 0.289 | 0.15 | 0.03 | 0.06 | 0.05 | 93.5
Unitec Builder, Inc./EZJones Construction Inc. (JV) | JV-11-230 | L | A | MB | GE1 | Conc. of Trujillo-E. Duran-Gemaraganan Rd. (Sta.745+500-Sta.749+340.00) w/ exceptions, Bobon & Lope De Vega | Province of Northern Samar | 2012-11-27 | 1st | VIII | LF | 96.971 | 330 | 2012-03-22 | 2013-02-14 | 7.47 | O | 0.362 | 0.3 | 0.15 | 0.03 | 0.04 | 0.033 | 91.5 | -
Unitec Builder, Inc./EZJones Construction Inc. (JV) | JV-11-230 | L | A | MB | GE1 | Const./Repair/Rehab./Impvt. of San Isidro-Lope de Vega Rd. | San Isidro, Northern Samar | 2012-11-27 | 2nd | VIII | LF | 142.362 | 304 | 2011-03-16 | 2013-01-14 | 3.5 | O | 0.367 | 0.24 | 0.15 | 0.03 | 0.045 | 0.033 | 86.5 | -
Unitec Builder, Inc./RNMK Construction and Development Joint Venture | JV-12-315 | L | A | MB | GE | Road Upgrading (Gravel to Concrete) of Bugko - Nenita - Mirador Capinitan De Maria - San Jose Road, Sta.6+141 - Sta.11+091 with exceptions | Mondragon, Eastern Samar | 2014-08-09 | Final | VIII | LF | 142.8194 | 390 | 2013-02-27 | 2014-03-23 | 0.51 | C | 0.418 | 0.133 | 0.3 |  |  |  | 85.1 | 90.14% Very Satisfactory
UNITEC BUILDER, INC/EZJONES CONSTRUCTION INC. JOINT VENTURE | JV-14-531 | L | AAA | LA | GE | Construction of Tacloban City By-Pass Road, Including ROW, Sta. 0+000-Sta. 3+400, Brgy. Nula-Tula, Tacloban City, Leyte | Brgy. Nula-Tula, Tacloban City, Leyte | 2015-11-11 | 1st | Regional Office No. VIII | LF | 184.9437 | 360 | 2015-05-07 | 2016-04-30 | (+)5.44% | OG | 0.321 | 0.3 | 0.15 | 0.03 | 0.06 | 0.05 | 91.1% | 91.1% Very Satisfactory
Unitec Builders | 4803 | L | A |  |  | Catarman Airport Development Project | Catarman, Nothern Samar | 2014-02-12 | Final | DOTC | LF | 14.408 | 240 | 2012-06-15 | 2013-02-09 | 0 | C | 0.493 | 0.2 | 0.3 | - | - | - | 99.3 | 95.68% Very Satisfactory
Unitec Builders | 4803 | L | A |  | GE1 | Catarman Airport Development Project | Catarman, Northern Samar | 2012-11-26 | 1st | DOTC | LF | 14.408 | 240 | 2012-06-15 | 2013-02-09 | 1.44 | O | 0.391 | 0.3 | 0.15 | 0.015 | 0.035 | 0.05 | 94.1 | -
Unitec Builders, Inc./Ezjones Construction Inc. | JV-11-121 | L | A | MB | GE1 | Road Upgrading of San Isidro-Lope de Vega Road | San Isidro, Northern Samar | 2012-03-22 | 1st | VIII | LF | 94.084 | 350 | 2011-12-26 | 2012-12-09 | 17.52 | O | 0.4 | 0.225 | 0.15 | 0.03 | 0.033 | 0.033 | 87.1 | -
Universal De Leon Construction and Aggregates | 1624 | L |  |  |  | Repair and Upgrading of the Liberty Park and Cemetery of Negativism | Baguio City | 2016-01-20 | 1st | BCDA | LF | 1.578 | 57 | 2015-10-12 | 2015-12-11 | 5.79 | O | 0.3454 | 0.3 | 0.0921 | 0.03 | 0.035 | 0.025 | 82.75 | -
UY Condev Corporation | 12336 | L | AA | MA | GE | Const./Rehab. of Flood Control Project along Sayre Highway Km. 1508+500 - K1513+000 w/ exception | Malaybalay City, Bukidnon | 2014-10-24 | 2nd | X | LF | 17.1711 | 195 | 2014-02-14 | 2014-08-27 | -1.6% | C | 0.372 | 0.2 | 0.252 | - | - | - | 82.4% | 90.44% Very Satisfactory
UY Condev Corporation | 12336 | L | AA | LA | GE | Const. of Misamis Oriental - Bukidnon By-Pass Road PHIVIDEC - Alae Section | Mantibugao, Manolo Fortich, Bukidnon | 2014-08-09 | Final | X | LF | 46.3176 | 209 | 2013-01-23 | 2014-08-19 | 0 | C | 0.455 | 0.2 | 0.3 |  |  |  | 95.5 | 90.34% Very Satisfactory
UY Condev Corporation | 12336 | L | AA | MA | GE | Construction/Rehab. Of Flood Control Projects along Sayre Highway K1508+500 - K1513+300 (with exception) | Malaybalay City, Bukidnon | 2014-08-05 | 1st | X | LF | 17.1711 | 195 | 2014-02-14 | 2014-08-27 | 0.9 | O | 0.4 | 0.3 | 0.15 | 0.03 | 0.045 | 0.033 | 95.8
UY CONDEV CORPORATION | 12336 | L | AA | LA | GE | Repair/Rehabilitation of Sta. Catalina- Pamplona-Tanjay Roads, K0032+(-848) to K0032+(-088) with exceptions, Negros Oriental | 2nd District, Negros Oriental | 2015-06-02 | Final | Negros Oriental Second DEO | LF | 8.935 | 125 | 2014-12-12 | 2015-04-16 | 0% | C | 0.432 | 0.135 | 0.3 | - | - | - | 86.7% | *86.7% Satisfactory
UY Condev Corporation | 12336 | L | AA | LA |  | Dumaguete Airport Development Project | Dumaguete City, Negros Oriental Northe/ Region VII | 2016-05-18 | 1st | DOTC | LF | 87.203 | 126 | 2016-02-15 | 2016-06-20 | 19.03 | O | 0.3908 | 0.3 | 0.15 | 0.02 | 0.0377 | 0.05 | 94.85 | -
UY Condev Corporation | 12336 | L | AA | LA |  | Dumaguete Airport Development Project | Subulan, Negros Oriental/ Region VII | 2016-08-25 | 2nd & Final | DOTC | LF | 87.2029 | 126 | 2015-03-09 | 2016-06-20 | 0 | C | 0.456 | 0.2 | 0.3 | - | - | - | 95.6 | 95.10% Very Satisfactory
UY CONDEV CORPORATION (Formerly: Uy Construction and Development ) | 12336 | L | AA | LA | GE | Rehab./Reconst./ Upgrading of Damaged Paved National Road including Drainage Based on Pavement Management System / Highway Development and Management - 4 (HDM-4) (Intermittent Sections), Sta. Catalina-Pamplona--Tanjay Road, K0032+(-180)-K0032+152; K0032+152-K0032+887 and K0036+217-0037+836, 2nd District, Negros Oriental | Negros Oriental | 2015-11-13 | 1st | Negros Oriental 2nd DEO | LF | 42.7226 | 269 | 2015-03-18 | 2015-12-11 | (-)5.0% | OG | 0.378 | 0.285 | 0.1 | 0.03 | 0.055 | 0.033 | 88.1% | 88.1% Satisfactory
UY Construction | 12336 | L | AA | LA | GE | Construction/Widening/Upgrading/Rehabilitation of Access Road to RORO Port, Sta. 0+000 to Sta. 1+706, K0000+560 to K0000+593.71 (Segment 3), K0001+520 to K0001+579.49 | Siaton, Negros Oriental | 2014-10-28 | 1st | III | LF | 45.8954 | 239 | 2014-02-03 | 2014-09-29 | -4.66% | O | 0.356 | 0.3 | 0.029 | 0.03 | 0.051 | 0 | 76.6% | 76.6% Unsatisfactory
Uy Construction & Development | 12336 |  |  |  |  | Rehab./Reconst./Upgrading of Guimaras Circ. Road, Salvacion-Lucmayan Section, Km.84+000-Km.88+643 with exceptions |  | 2010-08-30 |  | VI |  | 24.179 | 360 |  |  |  | O | 0.372 | 0.238 | 0.15 | 0.03 | 0.051 | 0.033 | 87.4 | -
Uy Construction & Development | 12336 | L | A | MB | GE1 | Rehab./Recons. of Iloilo East Coast Capiz Road, Barotac Viejo Section |  | 2009-06-09 | 1st | VI |  | 38.18 | 150 |  |  |  | O | 0.351 | 0.24 | 0.15 | 0.008 | 0.035 | 0.05 | 83.4 | -
Uy Construction & Development | 12336 | L | A | MB | GE1 | Const. of Iloilo Circ. Rd. (C-1) Sect. C-Jct. Jaro-Tocas Rd. to Jct. Iloilo Sta. Barbara Rd. | Iloilo City | 2013-03-22 | Final | VI | LF | 123.507 | 353 | 2012-02-01 | 2013-01-18 | 1.7 | C | 0.47 | 0.133 | 0.3 | - | - | - | 90.3 | 86.70% Satisfactory
Uy Construction & Development | 12336 | L | A | MB | GE1 | Reconst./Replacement of Juan Colon Bridge, Brgy. Mayabon |  | 2009-09-15 | 2nd | VII |  | 26.141 | 389 |  |  |  | O | 0.39 | 0.24 | 0.15 | 0.03 | 0.042 | 0.05 | 90.2 | -
Uy Construction & Development | 12336 | L | A | MB | GE1 | Re-const./Replacement of Juan Colon Bridge Brgy. Mayabon |  | 2009-05-27 | 1st | VII |  | 26.141 | 389 |  |  |  | O | 0.345 | 0.3 | 0.15 | 0.03 | 0.051 | 0.05 | 92.6 | -
Uy Construction & Development | 12336 | L | A | MB | GE1 | Imprv't/Concrete Paving of Dumaguete South Rd. Sta.0+859-Sta.1+100 and Sta. 1+900-Sta.5+380 |  | 2009-09-15 | 1st | VII |  | 61.645 | 240 |  |  |  | O | 0.4 | 0.24 | 0.15 | 0.03 | 0.037 | 0.033 | 89 | -
Uy Construction & Development | 12336 | L | A | MB | GE1 | Imprv't. of Bayawan-Kabankalan Rd. Sta. 1+250-Sta.3+020 |  | 2009-09-16 | 1st | VII |  | 29.868 | 210 |  |  |  | O | 0.385 | 0.24 | 0.15 | 0.03 | 0.033 | 0.033 | 87.1 | -
Uy Construction & Development | 12336 |  |  |  |  | Rehab./Reconst./Upgrading of Damaged National Rd. Dumaguete South Rd. Giligaon Sect. |  | 2010-06-09 |  | VII |  | 11.214 | 160 |  |  |  | O | 0.336 | 0.293 | 0.15 | 0.03 | 0.025 | 0.033 | 86.7 | -
Uy Construction & Development | 12336 |  |  |  |  | Rehab. of Dumaguete South Road |  | 2010-09-03 |  | VII |  | 17.309 | 240 |  |  |  | O | 0.386 | 0.224 | 0.15 | 0.03 | 0.051 | 0.05 | 89.1 | -
Uy Construction & Development | 12336 | L | A | MB | GE1 | Concreting of Bais-Kabankalan Road (Intermittent Section) |  | 2009-05-27 | 1st | VII |  | 94.413 | 369 |  |  |  | O | 0.343 | 0.238 | 0.15 | 0.03 | 0.051 | 0.05 | 86.2 | -
Uy Construction & Development | 12336 | L | A | MB | GE1 | Conc. of Dumaguete South Road (DSR) |  | 2009-03-12 | 2nd | VII |  | 21.739 | 190 |  |  |  | O | 0.389 | 0.225 | 0.15 | 0.03 | 0.061 | 0.033 | #VALUE! | -
Uy Construction & Development | 12336 | L | A | MB | GE1 | Conc. of Dumaguete South Road (DSR) |  | 2008-11-26 | 1st | VII |  | 21.705 | 160 |  |  |  | O | 0.38 | 0.3 | 0.1 | 0.03 | 0.038 | 0.1 | 94.8 | -
Uy Construction & Development | 12336 | L | AA | MB | GE1 | Const. of Misamis Oriental-Bukidnon By-Pass Rd. PHIVEDEC-Alae Sect., Mantibugao | Manolo Fortich, Bukidnon | 2013-08-07 | 1st | X | LF | 46.318 | 209 | 2013-01-23 | 2013-08-19 | 3.26 | O | 0.33 | 0.281 | 0.15 | 0.03 | 0.045 | 0.033 | 86.9
Uy Construction & Development | 12336 | L | A | MB | GE1 | Const. of Misamis Oriental-Bukidnon By-Pass Rd. (PHIVEDEC-Alae) Capid Sect. | Manolo Fortich, Bukidnon | 2013-03-21 | Final | X | LF | 44.03 | 340 | 2012-01-26 | 2012-12-30 | 0.95 | C | 0.353 | 0.2 | 0.3 | - | - | - | 85.3 | 86.26% Satisfactory
Uy Construction & Development | 12336 | L | A | MB | GE1 | Road Upgrading (Gravel to Paved) of Jct. SH. Manolo Fortich-Libona-Indahag Road (Camp 9-Poblacion Sect.) | Libona, Bukidnon | 2011-03-31 | 1st | X | LF | 14.984 | 172 | 2010-12-10 | 2011-05-30 | -9.57 | O | 0.368 | 0.225 | 0.054 | 0.03 | 0.042 | 0.05 | 76.9 | -
Uy Construction & Development/ARN Builders (JV) | JV-07-001 | L | A | MB | GE1 | Conc. of Bais-Kabankalan Road @ Intermittent Section |  | 2008-08-20 | 2nd | VII |  | 95.268 | 300 |  |  |  | O | 0.295 | 0.221 | 0.07 | 0.03 | 0.065 | 0.1 | 78.1 | -
V U C Engineering | 7918 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rd. along Kalinga-Cagayan Rd. (Calanan-Enrile Sect.) K0398+366-K0499+000 & K0499+306-K0499+892 | Tabuk City, Kalinga | 2013-08-09 | 2nd | CAR | LF | 32.811 | 196 | 2013-02-04 | 2013-08-18 | 3.97 | O | 0.35 | 0.3 | 0.15 | 0.03 | 0.04 | 0.033 | 90.3
V U C Engineering | 7918 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l. Rd. along Kalinga-Cagayan Rd. (Calanan-Enrile Sect.) K0398+366-K0499+000 & K0499+306-K0499+892 | Kalinga | 2013-03-20 | 1st | CAR | LF | 32.811 | 166 | 2013-02-04 | 2013-07-20 | 1.02 | O | 0.362 | 0.208 | 0.15 | 0.023 | 0.06 | 0.05 | 85.3 | -
V U C ENGINEERING | 7198 | L | A | MB | GE | Rehabilitation/Reconstruction of Damaged Paved National Road including Drainage Based on Pavement Management System/Highway Development and Management-4 (HDM-4) of Kalinga -Cagayan Road, a.) K0498+368 to K0498+510, b.) K0499+703 to K0499+890, Tabuk City, Kalinga | Tabuk City, Kalinga | 2015-08-28 | 1st | Kalinga DEO | LF | 16.958 | 140 | 2015-05-27 | 2015-10-13 | 3.35% | O | 0.396 | 0.3 | 0.15 | 0.03 | 0.07 | 0.05 | 99.6% | -
V. R. D. J. CONSTRUCTION | 19837 | L | C | SB | GE | Rehabilitation/Improvement of Cumabao-Camasi | Tumauini, Isabela | 2015-06-04 | 1st | Isabela 1st DEO | LF | 9.264 | 105 | 2015-02-27 | 2015-06-11 | 5.45% | O | 0.231 | 0.3 | 0.15 | 0.03 | 0.035 | 0.033 | 77.9% | -
V. R. Guevarra Construction & Trading | 14-01-637 |  |  |  |  | Hot Mix Asphalt Overlay at the Bellhouse Driveway and Liberty Loop Road | John Hay Especial Economic Zone, Baguio City | 2015-01-13 | 1st & Final | BCDA | L | 5.326 | 56 | 2014-09-17 | 2014-11-12 | 0 | C | 0.43756 | 0.10587 | 0.3 | - | - | - | - | *84.34% Satisfactory
V.B. Manubay Construction | 32705 |  |  |  |  | Magat River Flood Control (Camarunggayan Sect.) |  | 2010-05-31 |  | II |  | 4.821 | 120 |  |  |  | O | 0.368 | 0.3 | 0.15 | 0.018 | 0.042 | 0.033 | 91.1 | -
V.B. Manubay Construction | 32705 |  |  |  |  | Magat River Flood Control (Kalabaza Sect.) |  | 2010-05-31 |  | II |  | 4.823 | 120 |  |  |  | O | 0.343 | 0.3 | 0.15 | 0.024 | 0.042 | 0.033 | 89.2 | -
V.B. Manubay Construction | 32705 |  |  |  |  | Magat River Flood Control (Apiat Sect.) |  | 2010-05-31 |  | II |  | 4.823 | 120 |  |  |  | O | 0.342 | 0.3 | 0.15 | 0.024 | 0.042 | 0.033 | 89.1 | -
V.B. Manubay Construction | 32705 | L | A | SB | GE | Rehabilitation/Construction of Flood Control Facilities, Gucab Flood Control | Gucab, Echague, Isabela | 2014-10-27 | 1st | II | LF | 14.3177 | 150 | 2014-09-03 | 2015-01-30 | 26.05% | O | 0.291 | 0.24 | 0.15 | 0.03 | 0.033 | 0.05 | 79.4% | 79.4% Unsatisfactory
V.B. MANUBAY CONSTRUCTION | 32705 | L | B | SB | GE | Rehabilitation/Construction of Flood Control Facilities, Gucab, Flood Control | Gucab, Echague, Isabela | 2015-06-06 | Final | Isabela 4th DEO | LF | 14.318 | 150 | 2014-09-03 | 2015-01-30 | 24.17% | C | 0.425 | 0.2 | 0.3 | - | - | - | 92.5% | *84.64% Satisfactory
V.C. VARIN CONSTRUCTION & HARDWARE SUPPLY | - | L | B | SB | GE | Local Infrastructure Program: Const. of Farm to Market Road, Brgy. San Isidro, Talisay, Camarines Norte | Brgy. San Isidro, Talisay, Camarines Norte | 2015-11-13 | Final | Camarines Norte DEO | LF | 2.3765 | 45 | 2015-03-23 | 2015-05-06 | - | C | 0.374 | 0.194 | 0.3 | - | - | - | 86.8% | 86.8% Satisfactory
V.R. GUEVARRA CONSTRUCTION & TRADING | 31565 | L | D | SB | GB | LIP - Completion of Multi-Purpose Building, Luacan National High School, Dinalupihan, Bataan | Dinalupihan, Bataan | 2015-06-05 | Final | Bataan 1st DEO | LF | 0.692 | 60 | 2014-11-03 | 2015-01-01 | 5% | C | 0.5 | 0.12 | 0.3 | - | - | - | 92% | *92% Very Satisfactory
V.R. Patron Builders & Developers | 13487 |  |  |  |  | Rehab./Reconst./Upgrading of Damaged National Roads along Bauan-Mabini Rd., Bauan Side |  | 2010-06-04 |  | IVA |  | 19.295 | 120 |  |  |  | O | 0.39 | 0.225 | 0.15 | 0.023 | 0.06 | 0.05 | 89.8 | -
V.R. Patron Builders & Developers | 13487 | L | AAA | MB | GE | Widening of Batangas-Quezon Road, Rosario Section, a) K0117+600.00 to K0118+194.20; b) K0117+600.00 to K0118+555.70 | Rosario, Batangas | 2014-12-05 | 1st & Final | IV | LF | 18.2308 | 150 | 2014-02-03 | 2014-07-02 | 0% | C | 0.492 | 0.133 | 0.3 | - | - | - | 92.5% | 92.5% Very Satisfactory
V.R. Patron Builders & Developers | 13487 | L | AAA | MB | GE | Widening of Lipa-Rosario Road, San Felipe-Poblacion Section, Padre Garcia, (A) K0087+280 to K088+604 (Right Side), K088+920 to K0089+199.5 (Left Side) | Padre Garcia, Batangas | 2014-12-05 | 1st & Final | IV | LF | 27.3558 | 232 | 2014-02-03 | 2014-09-22 | 0% | C | 0.463 | 0.133 | 0.3 | - | - | - | 89.6% | 89.6% Very Satisfactory
V.R. Patron Builders & Developers | 1487 | L | AAA | MB | GE | Widening of Lipa-Rosario Road, San Felipe-Poblacion Section K0087+280 to K0088+604 (RS), K088+920 to K0089+199.5 (LS) | San Felipe, Padre Garcia, Batangas | 2014-08-08 | 1st | IV-A | LF | 27.3558 | 210 | 2014-02-03 | 2014-08-31 | -0.68 | O | 0.368 | 0.3 | 0.143 | 0.015 | 0.063 | 0.033 | 92.2
V.R. Patron Builders & Developers | 13487 | L | AAA | MB | GE1 | Const. of Two (2) Pedestrian Overpass at Manila-Batangas Rd. Alangilan (BSU) & Kumintang Ibaba Sect. | Batangas City | 2013-07-31 | Final | IVA | LF | 27.936 | 420 | 2012-02-14 | 2013-04-08 | 3.33 | C | 0.462 | 0.133 | 0.3 | - | - | - | 89.5 | 88.03% Satisfactory
V.R. Patron Builders & Developers | 13487 | L | AAA | MB | GE1 | Const. of Two (2) Pedestrian Overpass at Manila-Batangas Rd., Alangilan (BSU) and Kumintang Ibaba Sect. | Batangas City | 2013-03-12 | 2nd | IVA | LF | 27.936 | 400 | 2012-02-14 | 2013-03-19 | 0 | O | 0.373 | 0.24 | 0.15 | 0.03 | 0.03 | 0.033 | 85.6 | -
V.R. Patron Builders & Developers | 13487 | L | AAA | MB | GE1 | Const. of Two (2) Pedestrian Overpass at Manila-Batangas Rd., Alangilan (BSU) & Kumintang Ibaba Sect. | Batangas City | 2012-11-23 | 1st | IVA | LF | 27.936 | 339 | 2012-02-14 | 2013-01-17 | 9.13 | O | 0.345 | 0.3 | 0.15 | 0.03 | 0.027 | 0.033 | 88.5 | -
V.R. Patron Builders & Developers | 13487 | L | AAA | MB | GE | Construction/ Replacement of Doña Alicia Bridge at Batangas-Lobo Road | Taysan, Batangas | 2014-08-08 | Final | IV-A | LF | 38.7998 | 405 | 2012-01-11 | 2013-02-18 | 0 | C | 0.39 | 0.2 | 0.3 |  |  |  | 89 | 86.54% Satisfactory
V.R. Patron Builders & Developers | 13487 | L | AAA | MA | GE2 | Const./Replacement of Doña Alicia Bridge at Batangas-Lobo Rd. | Taysan, Batangas | 2013-07-29 | 1st | IVA | LF | 38.8 | 405 | 2012-01-11 | 2013-02-18 | -5.04 | O | 0.347 | 0.3 | 0.1 | 0.03 | 0.047 | 0.025 | 84.9
V.R. Patron Builders & Developers | 13487 | L | AAA | MB | GE1 | Widening of Manila-Batangas Road inc. Drainage Structure, Banay-Banay-San Jose Sect. Km.85+200-Km.86+400 (One Side Only) w/ exception | Lipa City, Batangas | 2013-07-29 | Final | IVA | LF | 19.159 | 180 | 2013-01-14 | 2013-07-12 | 24.08 | C | 0.373 | 0.165 | 0.3 | - | - | - | 83.8 | 84.46% Satisfactory
V.R. Patron Builders & Developers | 13487 | L | AAA | MB | GE1 | Widening of Manila-Batangas Rd., inc. Drainage Structure, Banay-banay-San Jose Sect., Km.85+200-Km.86+400 (One Slide Only) (w/ exception) | Lipa City, Batangas | 2013-03-11 | 1st | IVA | LF | 18.362 | 150 | 2013-01-14 | 2013-06-12 | 19.33 | O | 0.358 | 0.24 | 0.15 | 0.023 | 0.045 | 0.033 | 84.9 | -
V.R. PATRON BUILDERS & DEVELOPERS CORP. (Formerly: V.R. Patron Builders & Developers) | 13487 | L | AAA | MA | GE | Restoration/Improvement of Slope Protection/Revetment of Icarbang Bridge along San Juan - Laiya Road | San Juan, Batangas | 2015-06-05 | Final | Batangas 4th DEO | LF | 4.557 | 90 | 2015-02-06 | 2015-05-06 | 0% | C | 0.359 | 0.2 | 0.3 | - | - | - | 85.9% | *85.9% Satisfactory
V.R. PATRON BUILDERS & DEVELOPERS CORP. (Formerly: V.R. Patron Builders & Developers) | 13487 | L | AAA | MB | GE | Widening of National Roads, Secondary Roads, Quezon - Batangas Road, K0104+140 to K0105+000, K0107+219 to K0107+489 | San Antonio, Quezon | 2015-06-10 | 1st | Quezon 2nd DEO | LF | 43.591 | 242 | 2015-01-28 | 2015-09-26 | 16.89% | O | 0.301 | 0.281 | 0.15 | 0.03 | 0.045 | 0.033 | 84% | -
V.R.D.J Construction | 19837 | L | D | SB | GB1 | Const. of Sto. Tomas MPB |  | 2008-11-18 | 1st | II |  | 3.818 | 120 |  |  |  | O | 0.317 | 0.24 | 0.1 | 0.03 | 0.037 | 0.067 | 79.1 | -
Valley Construction & Aggregates | 14315 | L | B | MA | GE1 | Road Upgrading (Gravel to Conc.) Acop-Kapangan-Kibungan-Bakun Rd. Km.283+800-Km.289+849 (V.S.) | Kapangan, Benguet | 2011-08-15 | 1st | CAR | LF | 21.458 | 523 | 2011-06-23 | 2012-11-27 | 2.29 | O | 0.386 | 0.225 | 0.15 | 0.03 | 0.051 | 0.05 | 89.2 | -
Valley Construction & Aggregates | 14315 | L | B | MA | GE1 | Impvt. of the Acop-Kapangan National Road |  | 2008-08-13 | 1st | CAR |  | 18.822 | 240 |  |  |  | O | 0.321 | 0.24 | 0.1 | 0.023 | 0.03 | 0.1 | 81.4 | -
VALLEY CONSTRUCTION & AGGREGATES | 14315 | L | B | SB | GE | Rehabilitation/Reconstruction of National Roads with Slips, Slope Collapse and Landslide along National Secondary Road, Abatan-Mankayan-Cervantes Road, K0337+500 | Mankayan, Benguet | 2015-06-04 | Final | Benguet 2nd DEO | LF | 1.666 | 60 | 2015-02-16 | 2015-04-16 | (+) 42.09 | C | 0.362 | 0.2 | 0.3 | - | - | - | 86.2% | *86.2% Satisfactory
VALLEY CONSTRUCTION & AGGREGATES | 14315 | L | B | MA | GE | Rehabilitation/Reconstruction of National Roads with Slips, Slope Collapse and Landslide along National Road, Baguio - Bontoc Road, K0279+900 to K0280+620, Atok, Benguet | Atok, Benguet | 2015-09-02 | 1st & Final | Benguet 2nd DEO | LF | 7.564 | 150 | 2015-02-16 | 2015-07-15 | 0.67% | C | 0.437 | 0.133 | 0.3 | - | - | - | 87% | *87% Satisfactory
Valley Construction & General Merchandise | 13777 | L | B | SB | GE2 | Repair/Maint. of Brgy. 09 Revetment | Tuguegarao, Cagayan | 2013-03-16 | Final | II | LF | 2.992 | 73 | 2012-10-19 | 2012-12-30 | 14.27 | C | 0.375 | 0.2 | 0.3 | - | - | - | 87.5 | 87.08% Satisfactory
VANMARVIL CONSTRUCTION | 19224 | L | D | SB | GE | Rehabilitation/Major Repair of Permanent Bridges, Lipit Bridge along Baler - Casiguran Road (Baler - Dinadiawan), Aurora | Baler - Casiguran, Aurora | 2015-06-11 | Final | Aurora DEO | LF | 1.369 | 76 | 2015-03-01 | 2015-05-16 | 0% | C | 0.486 | 0.2 | 0.3 | - | - | - | 98.6% | *98.6% Outstanding
Vannie General Merchandise | 27335 | L | D | SB | GE2 | Const. of 425 ln.m. Drainage Canal, Purok Riverside |  | 2009-03-03 | 2nd | VI |  | 5.793 | 564 |  |  |  | O | 0.281 | 0.3 | 0.15 | 0.03 | 0.042 | 0.05 | #VALUE! | -
Vannie General Merchandise | 27335 | L | D | SB | GE2 | Const. of Pototan Flood Control Suage River Brgy. Poblacion |  | 2009-09-09 | 1st | VI |  | 2.895 | 180 |  |  |  | O | 0.383 | 0.24 | 0.15 | 0.015 | 0.05 | 0.033 | 87.1 | -
Vannie General Merchandise | 27335 | L | D | SB | GE2 | Const. of 425 ln.m. Drainage Canal |  | 2008-11-18 | 1st | VI |  | 5.738 | 154 |  |  |  | O | 0.32 | 0.2 | 0.07 | 0.03 | 0.032 | 0.133 | 78.5 | -
Vanvi Construction | 29387 | L | C | SB | GB1 | Construction of MPB, Brgy. Poblacion |  | 2009-09-16 | 1st | XII |  | 0.286 | 75 |  |  |  | O | 0.364 | 0.3 | 0.15 | 0.03 | 0.052 | 0.05 | 94.6 | -
VC Varin Construction and Hardware Supply | 12475 | L | B | SB | GE | Rehab./Reconst./Upgrading of Damaged Paved National Roads including Drainage based on PMS/HDM-4, Intermittent Section, Arterial Road, Daang Maharlika, K0360+000 - K0361+000 | Camarines Norte | 2014-08-05 | 1st & Final | V | LF | 14.1408 | 60 | 2014-02-07 | 2014-04-07 | 0 | C | 0.431 | 0.133 | 0.3 |  |  |  | 86.4 | 86.40% Satisfactory
VCD Construction | 13949 | L | C | SB | GB1 | Construction of 2-Storey School Building @ San Nicolas E/S |  | 2009-06-04 | 1st | I |  | 1.348 | 132 |  |  |  | O | 0.325 | 0.24 | 0.15 | 0.03 | 0.05 | 0.033 | 82.8 | -
VCD Construction and Supply |  | L |  |  |  | Help for Catubig Agricultural Advancement Project HCAAP-LCB-C4-2012 | Catubig Service Area/Northern Samar, Region 8 | 2014-03-15 | 1st | NIA | LF | 14.25 | 180 | 2012-07-24 | 2014-01-20 | 13 | O | 0.3507 | 0.3 | 0 | 0.03 | 0.07 | 0.05 | 80.07 | -
VCH Construction and Trading | 32050 | L | B | SB | GE2 | Const. of Barutuan Bridge I Revetment, Km.291+797 | El Nido, Palawan | 2013-03-13 | Final | IVB | LF | 1.129 | 53 | 2012-10-15 | 2012-12-06 | 0 | C | 0.44 | 0.133 | 0.3 | - | - | - | 87.3 | 86.40% Satisfactory
VCH CONSTRUCTION AND TRADING | 32050 | L | B | SB | GE | Construction of Barok Bridge Revetment K0234+520, Taytay-El Nido Road Section | Taytay, Palawan | 2015-06-05 | Final | Palawan 1st DEO | LF | 5.632 | 110 | 2014-11-24 | 2015-03-13 | 0% | C | 0.454 | 0.133 | 0.3 | - | - | - | 88.7% | *88.7% Satisfactory
Velonta Construction & Supply | 32346 | L | D | SB | GE1 | Prev. Maint. (Int. Sect.), Arterial Rd., N. Bacalso Ave. (Cebu South), Chainage 0810-Chainage 0850 | Cebu City | 2013-08-24 | Final | VII | LF | 0.969 | 29 | 2013-02-05 | 2013-03-05 | - | C | 0.486 | 0.2 | 0 | - | - | - | 68.6 | 63.20% Poor
Velonta Construction & Supply | 32346 | L | D | SB | GE1 | Prev. Maint. (Int. Sect.) Arterial Rd., N. Bacalso Ave. (Cebu South), Chainage 0810-Chainage 0850 | Cebu City | 2013-03-21 | 1st | VII | LF | 0.969 | 5 | 2013-03-01 | 2013-03-05 | - | O | 0.4 | 0.133 | 0 | 0.02 | 0.026 | 0.017 | 59.6 | -
Ven Ray Construction | 18310 | L | AA | MB | GE1 | Conc. of Unisan-Jct.-Panaon Rd. (Poctol Sect.), K0192+262-K0194+045 | Quezon | 2013-08-08 | Final | IVA | LF | 38.151 | 180 | 2012-12-03 | 2013-05-31 | 0 | C | 0.395 | 0.144 | 0.3 | - | - | - | 83.9 | 84.52% Satisfactory
Ven Ray Construction | 18310 | L | AA | MB | GE1 | Conc. of Unisan-Jct.-Panaon Rd. (Poctol Sect.) K0192+262-K0194+045 | Quezon | 2013-03-17 | 1st | IVA | LF | 38.151 | 180 | 2012-12-03 | 2013-05-31 | 0.67 | O | 0.346 | 0.253 | 0.15 | 0.03 | 0.04 | 0.033 | 85.2 | -
Ven Ray Construction | 18310 | L | AA | MB | GE | Assets Preservation of National Roads Preventive Maintenance Based on Pavement Management System/Highway Development Management-4 (HDM-4), Intermittent Section, (K0015+000 to K0035+900), (K0036+000 to K0036+695) | Naga City, Cebu | 2014-10-28 | 1st & Final | VII | LF | 27.4075 | 209 | 2014-01-24 | 2014-08-20 | 41.15% | C | 0.361 | 0.2 | 0.3 | - | - | - | 86.1% | 86.1% Satisfactory
Ven Ray Construction | 18310 | L | AA | MB | GE | Asphalt Overlay of Brgy. Road, Brgy. Marigondon, Lapu-Lapu City, Cebu | Lapu-Lapu City, Cebu | 2014-10-21 | 1st & Final | VII | LF | 44.004 | 120 | 2014-05-09 | 2014-09-05 | 26.67% | C | 0.427 | 0.135 | 0.3 | - | - | - | 86.2% | 86.2% Satisfactory
Ven Ray Construction | 18310 | L | AA | MB | GE | Cluster III -RBH: Preventive Maintenance, (Int. Sect.) Arterial Road, N. Bacalso Avenue (Osmena Blvd. Section) A. K0001+000 to K0001+726 B. K0001+(-105) to K0001+000 | Cebu City | 2014-08-09 | 1st & Final | VII | LF | 22.2022 | 108 | 2013-05-21 | 2013-09-06 | 17.59 | C | 0.446 | 0.135 | 0.3 |  |  |  | 88.1 | 88.10% Satisfactory
Ven Ray Construction | 18310 | L | AA | MB | GE1 | Prev. Maint.(Int. Sect.), Arterial Rd., N. Bacalso Ave. (Osmeña Blvd. Sect.); a)K0001+000-K0001+726 & b)K0001+(-105)-K0001+000 | Cebu City | 2013-08-24 | 1st | VII | LF | 22.202 | 108 | 2013-05-21 | 2013-09-06 | 9.91 | O | 0.327 | 0.3 | 0.15 | 0.03 | 0.055 | 0.05 | 91.2
Ven Ray Construction | 18310 | L | AA | MB | GE1 | Const./Replacement of Cabitoonan Bridge & Approaches along Toledo-Pinamungajan-Aloguinsan-Mantalongon Rd., K0052+(-20) | Toledo City, Cebu | 2013-08-07 | 1st | VII | LF | 25.628 | 174 | 2013-04-02 | 2013-09-22 | 1.94 | O | 0.384 | 0.24 | 0.15 | 0.03 | 0.047 | 0.033 | 88.4
Ven Ray Construction | 18310 | L | AA | MB | GE1 | Rd. Upgrading (Conc.) of Tapal (Carcar)-Zaragosa-Olango-Aloguinsan Rd., K0080+065-K0081+622 | Aloguinsan, Cebu | 2013-08-07 | 1st | VII | LF | 43.174 | 219 | 2013-01-24 | 2013-08-30 | 0.12 | O | 0.337 | 0.263 | 0.15 | 0.03 | 0.055 | 0.033 | 86.8
Ven Ray Construction | 18310 | L | AA | MB | GE1 | Rehab. of Cebu North Hagnaya Wharf Rd. | Cebu | 2013-08-13 | Final | VII | LF | 124.975 | 270 | 2012-06-05 | 2013-03-01 | 7 | C | 0.377 | 0.2 | 0.3 | - | - | - | 87.7 | 84.46% Satisfactory
Ven Ray Construction | 18310 | L | AA | MB | GE1 | Asphalt Overlay (Prev.) of Toledo-Pinamungajan-Aloguinsan-Mantalongon Rd., K0055+033-K0057+000, Brgy. Bato | Toledo City, Cebu | 2013-08-07 | Final | VII | LF | 13.163 | 30 | 2013-01-24 | 2013-02-22 | 30 | C | 0.459 | 0.2 | 0.3 | - | - | - | 95.9 | 82.76% Satisfactory
Ven Ray Construction | 18310 | L | AA | MB | GE1 | Asphalt Overlay (Prev.) of Toledo-Pinamungajan-Aloguinsan-Mantalongon Rd., K0055+033-K0057+000, Brgy. Bato | Toledo City, Cebu | 2013-03-17 | 1st | VII | LF | 12.909 | 30 | 2013-01-24 | 2013-02-22 | - | O | 0.389 | 0.3 | 0 | 0.02 | 0.014 | 0.017 | 74 | -
Ven Ray Construction | 18310 | L | A | MB | GE1 | Road Upgrading (Gravel to Paved) along Argao-Ronda Road (Argao-Ronda Sect.) |  | 2009-05-29 | 1st | VII |  | 18.718 | 75 |  |  |  | O | 0.388 | 0.288 | 0.15 | 0.03 | 0.055 | 0.033 | 94.4 | -
Ven Ray Construction | 18310 | L | B | MA | GE1 | Rehab./Reconst. of Siquijor Circ., Larena-Enrique Villanueva Rd. Sect. |  | 2008-11-22 | 1st | VII |  | 46.671 | 330 |  |  |  | O | 0.331 | 0.246 | 0.1 | 0.022 | 0.027 | 0.1 | 82.6 | -
Ven Ray Construction | 18310 | L | B | MA | GE1 | Rehab./Reconst. of Siquijor Circ., Larena-Enrique Villanueva Rd. Sect. |  | 2009-03-10 | 2nd | VII |  | 46.6707 | 368 |  |  |  | O | 0.319 | 0.219 | 0.15 | 0.023 | 0.033 | 0.033 | #VALUE! | -
Ven Ray Construction | 18310 | L | B | MA | GE1 | Rehab./Reconst. of Siquijor Circ. Rd, .Km.22.860-Km.25.268, Larena -E. Villanueva-Maria Rd. Sect. |  | 2009-09-08 | 1st | VII |  | 47.68 | 515 |  |  |  | O | 0.353 | 0.244 | 0.15 | 0.03 | 0.033 | 0.033 | 84.3 | -
Ven Ray Construction | 18310 | L | B | MA | GE1 | Rehab./Reconst. of Siquijor Circumferential Road, Km. 10.475-Km.13.020, Larena, E. Villanueva Road Section |  | 2009-06-03 | 3rd | VII |  | 47.085 | 428 |  |  |  | O | 0.22 | 0.3 | 0.15 | 0.03 | 0.047 | 0.05 | 79.7 | -
Ven Ray Construction | 18310 | L | B | MA | GE1 | Rehab./Reconst. of Siquijor Circ. Rd. Km.10.475-Km.13.020, Larena-E. Villanueva Rd. Sect. |  | 2009-09-08 | 4th | VII |  | 47.085 | 459 |  |  |  | O | 0.345 | 0.247 | 0.15 | 0.03 | 0.033 | 0.033 | 83.8 | -
Ven Ray Construction | 18310 | L | B | MA | GE1 | Concrete Paving of Siquijor Circ.Rd. San Juan Rd. Sec. Km. 61.820-Km.62.883 |  | 2009-09-08 | 1st | VII |  | 18.685 | 326 |  |  |  | O | 0.344 | 0.246 | 0.15 | 0.03 | 0.033 | 0.033 | 83.6 | -
Ven Ray Construction | 18310 | L | B | MA | GE1 | Conc. of Siquijor Circ. Rd. Km.72.707-Km.74.427 San Juan Siquijor Rd. Sect. Km. 13.020-Km. 14.22-Larena E. villanueva Rd. Sect. |  | 2009-09-07 | 1st | VII |  | 52.03 | 270 |  |  |  | O | 0.325 | 0.242 | 0.15 | 0.03 | 0.033 | 0.05 | 83 | -
Ven Ray Construction | 18310 | L | A | MB | GE1 | Conc. of Toledo-Pinamungajan-Aloguinsan Barili Na'tl. Road Km. 84+450 - Km. 85+891 |  | 2009-03-12 | 1st | VII |  | 19.093 | 180 |  |  |  | O | 0.205 | 0.04 | 0 | 0.01 | 0.016 | 0.05 | #VALUE! | -
Ven Ray Construction | 18310 | L | A | MB | GE1 | Concreting of Roads Sitio Sta. Cruz |  | 2009-03-09 | 1st | VII |  | 0.245 | 90 |  |  |  | O | 0.273 | 0 | 0.15 | 0.015 | 0.03 | 0.05 | #VALUE! | -
Ven Ray Construction | 18310 | L | B | MA | GE1 | Rehab./Reconst. of Siquijor Circumferential Road, Siquijor, -Larena Road Section |  | 2009-06-02 | 3rd | VII |  | 31.724 | 351 |  |  |  | O | 0.255 | 0.3 | 0.15 | 0.03 | 0.051 | 0.05 | 83.6 | -
Ven Ray Construction | 18310 | L | B | MA | GE1 | Rehab./Reconst. of Siquijor Circ., Siquijor-Larena Rd. Sect. |  | 2009-03-10 | 2nd | VII |  | 31.7326 | 328 |  |  |  | O | 0.34 | 0.222 | 0.15 | 0.03 | 0.047 | 0.033 | #VALUE! | -
Ven Ray Construction | 18310 | L | B | MB | GE1 | Rehab./Reconst. of Siquijor Circ., Siquijor-Larena Rd. Sect. |  | 2008-11-22 | 1st | VII |  | 31.737 | 313 |  |  |  | O | 0.363 | 0.238 | 0.1 | 0.03 | 0.032 | 0.1 | 86.3 | -
Ven Ray Construction | 18310 | L | A | MB | GE1 | Conc. of Antonio de Pio Highway, (Tigabawan-Olivio-Luyang Section) |  | 2008-09-02 | 1st | VII |  | 14.154 | 90 |  |  |  | O | 0.295 | 0.3 | 0 | 0.01 | 0.022 | 0.1 | 72.7 | -
Ven Ray Construction | 18310 | L | A | MB | GE1 | Const./Widening/Upgrading/Rehab. of Access Road to RORO Port | Siquijor | 2012-03-29 | 1st | VII | LF | 7.358 | 120 | 2012-01-19 | 2012-05-18 | 2.45 | O | 0.394 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 91.4 | -
Ven Ray Construction | 18310 | L | AA | MB | GE1 | Rehab. of Cebu North Hagnaya Wharf Rd. | Cebu | 2012-11-24 | 1st | VII | LF | 115.419 | 240 | 2012-06-05 | 2013-01-30 | 43.88 | O | 0.313 | 0.24 | 0.15 | 0.03 | 0.04 | 0.05 | 82.3 | -
Ven Ray Construction | 18310 | L | AA | MB | GE | Repair/Reconst./Upgrading of Damaged Paved National Roads including Drainage Based on Pavement Management System/Highway Development and Mangement System/Highway Development and Management-4 (HDM-4), Dalaguete-Mantalongon - Badian Road (Badian Side) | Badian, Cebu | 2014-08-05 | 1st & Final | VII | LF | 24.063 | 155 | 2014-02-17 | 2014-07-21 | 20 | C | 0.369 | 0.2 | 0.3 |  |  |  | 86.9 | 86.90% Satisfactory
Ven Ray Construction | 18310 | L | AA | MB | GE | Road Upgrading of Tapal (Carcar)-Zaragosa-Olango - Alonguinsan Road | Aloguinsan, Cebu | 2014-08-06 | Final | VII | LF | 48.1734 | 168 | 2013-01-24 | 2013-07-05 | 0 | C | 0.419 | 0.159 | 0.3 |  |  |  | 87.8 | 87.20% Satisfactory
Ven Ray Construction | 18310 | L | AA | MB | GE | Const./Replacement of Cabitoonan Bridge & Approaches along Toledo - Pinamungajan - Aloguinsan - Mantalongon Road | Toledo City, Cebu | 2014-08-06 | Final | VII | LF | 25.6283 | 174 | 2013-04-02 | 2013-09-22 | 3.51 | C | 0.48 | 0.146 | 0.3 |  |  |  | 92.6 | 90.08% Very Satisfactory
Ven Ray Construction | 18310 | L | AA | MB | GE | Construction of Drainage System along Cebu North Hagnaya Wharf Road Carmen Section, Carmen, Cebu | Carmen, Cebu | 2014-08-08 | 1st | VII | LF | 17.6503 | 210 | 2014-01-31 | 2014-08-28 | 6.88 | O | 0.344 | 0.266 | 0.15 | 0.022 | 0.047 | 0.05 | 87.9
Ven Ray Construction | 18310 | L | A | MB | GE1 | Impvt. of Cagayan de Oro-Talakag-Camp Kabaritan Sto. Niño Dagumbaan-Basak Road |  | 2009-09-17 | 1st | X |  | 66.4 | 270 |  |  |  | O | 0.4 | 0.3 | 0.034 | 0.03 | 0.047 | 0.017 | 82.8 | -
Ven Ray Construction | 18310 | L | AA | MB | GE1 | Conc. of Shoulders along Suggbongcogon-Binuangan-Ampenican-Lagonglong Sect. | Misamis Oriental | 2013-08-21 | Final | X | LF | 5.116 | 75 | 2012-10-03 | 2012-12-16 | 0 | C | 0.411 | 0.2 | 0.3 | - | - | - | 91.1 | 82.04% Satisfactory
Ven Ray Construction | 18310 | L | AA | MB | GE1 | Conc. of Shoulders along Sugbongcogon-Binuangan-Ampenican-Lagonglong Sect. | Misamis Oriental | 2012-11-21 | 1st | X | LF | 5.116 | 45 | 2012-10-03 | 2012-11-16 | -68.93 | O | 0.4 | 0.3 | 0 | 0.03 | 0.03 | 0 | 76 | -
Ven Ray Construction | 18310 | L | AA | MB | GE1 | Conc. of Shoulders w/ Provisions of Turn-Outs & Lined Canal along Butuan City-Cagayan de Oro-Iligan City Rd. (BCIR), Tagbocboc-Balingoan-Esperanza Sect. | Misamis Occidental | 2013-08-21 | Final | X | LF | 5.702 | 75 | 2012-10-03 | 2012-12-16 | 0 | C | 0.414 | 0.2 | 0.3 | - | - | - | 91.4 | 82.16% Satisfactory
Ven Ray Construction | 18310 | L | AA | MB | GE1 | Conc. of Shoulders with Provisions of Turn-Outs & Lined Canal along Butuan City-Cagayan de Oro City-Iligan City Rd. (BCIR), Tagbocboc-Balingoan-Esperanza Sect. | Misamis Oriental | 2012-11-22 | 1st | X | LF | 5.701 | 45 | 2012-10-03 | 2012-11-16 | -68.71 | O | 0.4 | 0.3 | 0 | 0.03 | 0.03 | 0 | 76 | -
Ven Ray Construction | 18310 | L | AA | MB | GE | Access Road Leading to Sagpulon Falls (Upgrading Gravel to Concrete) | Jaasan, Misamis Oriental | 2014-10-27 | 2nd | X | LF | 46.0004 | 239 | 2014-03-12 | 2014-11-06 | -46.42% | O | 0.257 | 0.24 | 0 | 0.008 | 0.037 | 0.033 | 57.5% | 57.5% Poor
VEN RAY CONSTRUCTION | - | L | B | MA | GE | Rehabilitation/Reconstruction/Upgrading of Toledo-Pinamungajan-Aloguisan-Mantalongon Road, K0082+93.78- K0082+302.78; K0084+460-K0085+207, Alonguinsan, Cebu | Alonguinsan, Cebu | 2015-06-03 | 1st | Cebu Third DEO | LF | 20.149 | 141 | 2015-03-03 | 1900-01-22 | 23.87% | O | 0.347 | 0.238 | 0.15 | 0.03 | 0.047 | 0.033 | 84.5% | -
VEN RAY CONSTRUCTION | 18310 | L | A | MB | GE | Widening of National Roads- Secondary Roads along Cebu North Hagnaya Wharf Road (Old Route), K0034+(-433) to K0034+684 | Danao City, Cebu | 2015-06-05 | 1st | Cebu Fifth DEO | LF | 25.421 | 160 | 2015-03-10 | 2015-08-16 | 1.2% | O | 0.379 | 0.24 | 0.15 | 0.03 | 0.045 | 0.033 | 87.7% | -
VEN RAY CONSTRUCTION | 18310 | L | A | MA | GE | Construction of Flood Control and Drainage System along Cebu North Hagnaya Wharf Road, K0025+930 to K0027+150, Compostela, Cebu | Compostela, Cebu | 2015-06-05 | 1st | Cebu Fifth DEO | LF | 17.88 | 210 | 2015-02-09 | 2015-09-06 | 0.33% | O | 0.385 | 0.251 | 0.15 | 0.03 | 0.045 | 0.033 | 89.4% | -
VEN RAY CONSTRUCTION | 18130 | L | A | MB | GE | Road Widening with Drainage along Toledo-Pinamungajan-Aloguisan-Mantalongon Road, Sta. 50 + (-954) - Sta. 50 + (-600), Toledo City, Cebu | Toledo City, Cebu | 2015-11-12 | 1st | Cebu 3rd | LF | 13.1742 | 135 | 2015-03-03 | 2015-07-15 | -0.04 | OG | 0.397 | 0.24 | 0.11 | 0.03 | 0.05 | 0.033 | 86% | 86% Satisfactory
VEN RAY CONSTRUCTION | 18130 | L | A | MB | GE | Rehab./ Reconstruction/ Upgrading of Toledo - Pinamungajan - Aloguinsan - Mantalongon Road, K0082+93.78 - K0082+302.78; K0084+460 - K0085+207, Alonguinsan, Cebu | Alonguinsan, Cebu | 2015-11-12 | Final | Cebu 3rd | LF | 20.1485 | 141 | 2015-03-03 | 2015-07-21 | 0 | C | 0.479 | 0.133 | 0.3 | - | - | - | 91.2% | 87.18% Satisfactory
VEN RAY CONSTRUCTION | 18130 | L | A | MA | GE | Construction of Flood Control and Drainage System along Cebu North Hagnaya Wharf Road, K0025+930 - K0027+150, Compostela, Cebu | Compostela, Cebu | 2015-11-14 | Final | Cebu 5th | LF | 17.88 | 210 | 2015-02-09 | 2015-09-06 | 0 | C | 0.487 | 0.133 | 0.3 | - | - | - | 92% | 92% Very Satisfactory
VEN RAY CONSTRUCTION / JJ & J CONSTRUCTION & GENERAL SUPPLY JOINT VENTURE | 0 | L | A | MB | GE | Asset Preservation of National Roads - Rehabilitation/ Reconstruction/ Upgrading of National Roads including Drainage based on Pavement Management System/ Highway Development-4 (HDM-4) (Intermittent Sections) - National Arterial Roads, Cebu North Hagnaya Wharf Road; Section 1: K0020+492-K0020+816; Section 2: K0025+604-K0025+928; Section 3: K0025+935-K0026+000; Section 4: K0039+000-K0040+000; Section 5: K0066+433-K0067+000; Section 6: K0071+615-K0072+000; Section 7: K0073+687-K0073+771; Section 8: K0074+000-K0074+490, Cebu Province | Cebu Province | 2015-11-15 | 1st | Regional Office | LF | 74.7445 | 204 | 2015-04-07 | 2015-10-27 | 0.011 | OG | 0.473 | 0.133 | 0.3 | - | - | - | 90.6% | 90.6% Very Satisfactory
VEN RAY CONSTRUCTION CORPORATION (Formerly: Ven Ray Construction) | 18310 | L | A | MB | GE | Network Development-Widening of National Roads-Secondary Roads, Cebu North Hagnaya Wharf Road Section 1: K0031+000 - K0032+397; Section 4: K0034+(-551) - K0035+769, Cebu Province | Cebu Province | 2015-11-14 | 1st | Regional Office | LF | 141.8818 | 300 | 2015-06-10 | 2016-04-05 | -0.048 | OG | 0.4 | 0.225 | 0.102 | 0.03 | 0.04 | 0.033 | 83% | 83% Satisfactory
VEN RAY CONSTRUCTION/JEJOR'S CONSTRUCTION CORPORATION JOINT VENTURE | JV-13-436 | L | AA | MB | GE | Widenig of Sayre Highways Including RROW, Puerto-Alae Section, Cagayan de Oro City 2nd LD K1432+674.00-K1437+799.00, Net Length=51250 l.m., Puerto-Alae Section, Cagayan de Oro City | Puerto-Alae Section, Cagayan de Oro City | 2015-06-11 | Final | Regional Office X | LF | 132.384 | 360 | 2014-01-30 | 2015-01-24 | - | C | 0.427 | 0.2 | 0.3 | - | - | - | 92.7% | *88.56% Satisfactory
Ven Ray Construction/Jejor's Construction Corporation Joint Venture | JV-13-436 | L | AA | MB | GE | Widening of Sayre Highway including RROW, Puerto-Alae Section K1432+674 - K1437+799 | Cagayan de Oro City | 2014-10-20 | 1st | X | LF | 132.3845 | 300 | 2014-01-30 | 2014-11-25 | 0.08% | O | 0.311 | 0.285 | 0.15 | 0.015 | 0.047 | 0.05 | 85.8% | 85.8% Satisfactory
VENRAY CONSTRUCTION CORPORATION (Formerly: Ven Ray Construction) | 10310 | L | A | MB | GE | Road Upgrading (Unpaved to Paved) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standards (HDM-4 Project Analysis) (Intermittent Sections - National Secondary Roads, Tapal (Carcar) Zaragoza-Olango-Aloguinsan Road | K0083+000-K0085+610.84, Cebu Province | 2015-08-28 | 1st | Regional Office No. VII | LF | 51.692 | 210 | 2015-04-07 | 2015-11-02 | -6.3% | O | 0.325 | 0.3 | 0.087 | 0.03 | 0.05 | 0.033 | 82.5% | -
VERET CONSTRUCTION | 36804 | L | D | SB | GB | Construction of Level 2 Water Supply, Bancal, Sinubli, Lubao, Pampanga | Sinubli, Lubao, Pampanga | 2015-06-03 | Final | Pampanga 2nd DEO | LF | 1.891 | 75 | 2014-12-21 | 2015-03-05 | 0% | C | 0.413 | 0.2 | 0.3 | - | - | - | 91.3% | *91.3% Very Satisfactory
VERGUZ CONSTRUCTION | 26641 | L | D | SB | GB | Construction of Multi-Purpose Building, Senior Citizens Youth Building Center, Davao del Sur | Davao del Sur | 2015-08-25 | 1st & Final | Davao del Sur First DEO | LF | 4.814 | 75 | 2015-04-17 | 2015-06-30 | - | C | 0.443 | 0.133 | 0.3 | - | - | - | 87.6% | *87.81% Satisfactory
Vertical Builders | 14029 | L | A | MA | GE | Widening of Jct. Digos-Buayan Airport Road, K1650+500 - K1652+079 | Buluan, Gen. Santos City | 2014-08-16 | 1st & Final | XII | LF | 33.4351 | 156 | 2014-01-26 | 2014-06-30 | 0 | C | 0.449 | 0.133 | 0.3 |  |  |  | 88.2 | 88.20% Satisfactory
Vertical Builders | 14029 | L | A | MA | GE1 | Conc./Widening of Marbel-Makar Rd., Polonuling/Simbo Sect. | Polonuling, South Cotabato | 2013-08-23 | Final | XII | LF | 18.962 | 185 | 2013-01-14 | 2013-07-17 | 1.08 | C | 0.428 | 0.195 | 0.3 | - | - | - | 92.3 | 89.60% V. Satisfactory
Vertical Builders | 14029 | L | A | MA | GE1 | Conc. /Widening of Marbel-Makar Rd., Polonuling/Simbo Sect. | South Cotabato | 2013-03-23 | 1st | XII | LF | 18.962 | 180 | 2013-01-14 | 2013-07-12 | 7.86 | O | 0.353 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 87.8 | -
Vertical Builders | 14029 | L | A | MA | GE1 | Address Critical Bottlenecks, Traffic Decongestion, Conc./Widening of Marbel-Makar Rd., South Cotabato, Sub-DEO, Simbo Sect. | Tupi, South Cotabato | 2013-08-23 | Final | XII | LF | 18.818 | 107 | 2013-02-21 | 2013-06-07 | - | C | 0.444 | 0.2 | 0.216 | - | - | - | 86 | 86.42% Satisfactory
Vertical Builders | 14029 | L | A | MA | GE1 | Address Critical Bottlenecks Traffic Decongestion, Conc./Widening of Marbel-Makar Rd., Simbo Sect. | Tupi, South Cotabato | 2013-03-23 | 1st | XII | LF | 18.818 | 102 | 2013-02-21 | 2013-06-02 | 26.04 | O | 0.361 | 0.238 | 0.15 | 0.03 | 0.055 | 0.033 | 86.7 | -
Verzontal Builders | 31579 | L | A | SB | GE5 | Gigaquit Port Development Project | Gigaquit, Surigao del Norte | 2014-03-28 | Final | DOTC | LF | 4.943 | 90 | 2013-11-11 | 2014-02-08 | 0 | C | 0.445 | 0.2 | 0.3 | - | - | - | 94.5 | 94.50% Very Satisfactory
Verzontal Builders | JV-11-197 | L | AAA | MB |  | Pagadian Airport Development Project | Pagadian City, Zamboanga del Sur | 2015-08-28 | 2nd & Final | DOTC | LF | 35.607 | 420 | 2013-01-22 | 2015-02-27 | 0 | C | 0.479 | 0.2 | 0.3 | - | - | - | 97.9 | 93.40% V. Satisfactory
Verzontal Builders | JV-11-197 | L | AAA | MB | GE1 | Pagadian Airport Development Project | Pagadian City, Zamboanga del Sur | 2013-09-12 | 1st | DOTC | L | 35.612 | 300 | 2013-01-22 | 2013-11-17 | 17.76 | O | 0.365 | 0.3 | 0.15 | 0.02 | 0.035 | 0.033 | 90.3 | -
Verzontal Builders |  | L |  | MA | GB1 | Land Dev't of NHA-Hernandezville Housing Project | Brgy. San Isidro, Padala, Davao del Sur | 2013-06-22 | 2nd & Final | NHA | L | 17.527 | 250 | 2012-06-08 | 2013-02-13 | 7.88 | C | 0.4703 | 0.2 | 0.3 | - | - | - | 97.03 | 69.43% Poor
Verzontal Builders |  | L |  | MA | GB1 | Land Dev't of NHA-Hernandezville Housing Project | Brgy. San Isidro, Padada, Davao del Sur | 2012-10-19 | 1st | NHA | LF | 20.285 | 250 | 2012-06-08 | 2013-02-13 | -11.81 | O | 0.328 | 0.0714 | 0.0319 | 0.03 | 0.019 | 0.03 | 51.03 | -
Vesa Engineering & Construction | 32334 | L | B | SB | GE-5 | Tanjay Port Development Project | Tanjay, Negros Oriental | 2015-08-13 | 1st | DOTC | LF | 8.659 | 150 | 2015-05-03 | 2015-09-29 | 3.51 | O | 0.3816 | 0.3 | 0.15 | 0.03 | 0.0262 | 0.0333 | 92.11 | -
VESA ENGINEERING & CONSTRUCTION | 32334 | L | D | SB | GE | Construction/Rehabilitation/Completion of Multi-Purpose Buildings: a) Construction of Dauin Sports Center (Gym), Phase 1, Brgy. Poblacion, Dauin, Negros Oriental | Brgy. Poblacion, Dauin, Negros Oriental | 2015-11-13 | Final | Negros Oriental 3rd DEO | LF | 5.813 | 150 | 2015-03-10 | 2015-08-06 | - | C | 0.442 | 0.133 | 0.3 | - | - | - | 87.5% | 87.5% Satisfactory
VESA Engineering and Construction | 32344 | L | B | MA |  | Catarman Airport Development Project | Catarman, Northern Samar | 2015-03-26 | 1st & Final | DOTC | L | 7.52 | 90 | 2014-02-05 | 2015-01-31 | 0 | C | 0.428 | 0.2 | 0.3 | - | - | - | - | *92.80% V. Satisfactory
VESA Engineering and Construction | 32334 | L | B | SB | GE5 | Cantupa Port Development Project | La Libertad, Negros Oriental | 2014-01-23 | 1st & Final | DOTC | LF | 1.996 | 90 | 2013-04-07 | 2013-07-05 | 0 | C | 0.4773 | 0.2 | 0.3 | - | - | - | 97.73 | *97.73% Outstanding
VESA ENGINEERING AND CONSTRUCTION | 32334 | L | B | MA | GE | Widening of National Road Including Drainage, Dipolog-Sindangan-Liloy Road, K1847+(-228)-K1848+(-377) | K1847+(-228)-K1848+(-377) | 2015-08-27 | 1st | Zamboanga del Norte 1st | LF | 20.186 | 253 | 2015-02-28 | 2015-11-07 | (+)0.88% | O | 0.383 | 0.24 | 0.15 | 0.015 | 0.042 | 0.05 | 88% | -
VESA ENGINEERING AND CONSTRUCTION | 32334 | L | B | MA | GE | Widening of National Road Including Drainage, Dipolog-Sindangan-Liloy Road, K1847+(-228.00)-K1848+(-377.00), Taga, Katipunan, Zamboanga del Norte | K1847+(-228.00)-K1848+(-377.00), Taga, Katipunan, Zamboanga del Norte | 2015-11-16 | 2nd | Zamboanga Del Norte 1st DEO | LF | 20.1856 | 193 | 2015-02-28 | 2015-09-08 | 0.31% | OG | 0.344 | 0.273 | 0.15 | 0.022 | 0.037 | 0.05 | 87.6% | 87.6% Satisfactory
Vesa Engineering and Construction | 32334 | L | B | SB | GE5 | Tanjay Port Development Project | Tanjay, Negros Oriental | 2013-08-29 | Final | DOTC | L | 1.884 | 90 | 2013-04-07 | 2013-07-05 | 3 | C | 0.393 | 0.2 | 0.3 | - | - | - | 89.3 | *89.30% V. Satisfactory
Vesa Engineering and Construction | 32334 | L | B | SB | GE5 | Siaton Port Development Project | Siaton, Negros Oriental | 2013-08-29 | Final | DOTC | L | 1.885 | 90 | 2013-04-07 | 2013-07-15 | 4 | C | 0.434 | 0.2 | 0.3 | - | - | - | 93.4 | *93.40% V. Satisfactory
VESA ENINEERING AND CONSTRUCTION | 132334 |  | B | SB |  | Tanjay Port Development Project | Tajay, Negros Oriental | 2015-12-01 | 2nd & Final | DOTC | LF | 8.659 | 150 | 2015-05-04 | 2015-09-30 | 0 | C | 0.478 | 0.2 | 0.3 | - | - | - | 97.8 | 94.40% V. Satisfactory
VF Construction | 10048 | L | B | MA | GE | Upgrading/Improvement of Road Sta. Rosario and Sta. Cruz | Hagonoy, Bulacan | 2014-11-07 | 1st & Final | III | LF | 9.2212 | 60 | 2014-01-14 | 2014-03-14 | 0% | C | 0.435 | 0.133 | 0.3 | - | - | - | 86.8% | 86.8% Satisfactory
Vicente T. Lao Construction | 7040 |  |  |  |  | REHABILITATION/ UPGRADING OF WESTERN WHARF | MAKAR PORT, GENERAL SANTOS CITY | 2015-10-09 | 1st | PPA | LF | 102.156 | 420 | 2014-12-01 | 2016-01-24 | -4.72 | O | 0.4 | 0.3 | 0.105 | 0.03 | 0.07 | 0.05 | 95.5 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB |  | Dipolog Airport Development Project | Dipolog City, Zamboanga del Norte | 2015-08-26 | 2nd | DOTC | LF | 27.578 | 404 | 2014-02-03 | 2015-11-06 | 16.16 | O | 0.385 | 0.3 | 0.15 | 0.02 | 0.063 | 0.05 | 96.8 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB |  | Dipolog Airport Development Project | Dipolog City, Zamboanga del Norte | 2015-02-12 | 1st | DOTC | L | 27.578 | 321 | 2014-02-03 | 2015-08-15 | 15.15 | O | 0.342 | 0.3 | 0.15 | 0.01 | 0.062 | 0.05 | 91.4 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB |  | Cotabato Airport Development Project | Brgy. Awang, Datus Sinsuat, Maguindanao | 2015-09-09 | 2nd | DOTC | LF | 55.676 | 270 | 2013-11-26 | 2015-08-20 | -2.01 | O | 0.357 | 0.3 | 0.13 | 0.02 | 0.061 | 0.033 | 90.1 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB |  | Central Mindanao Airport Development Project | Brgy. Tawan-Tawan, M'lang, North Cotabato/ Region XII | 2014-06-10 | 2nd & Final | DOTC | LF | 110.216 | 360 | 2013-07-01 | 2015-04-16 | 0 | C | 0.3348 | 0.2 | 0.3 | - | - | - | 83.48 | *90.87% V.Satisfactory
Vicente T. Lao Construction | 7040 | L | AAA | LB |  | Central Mindanao Airport Development Project | M'lang North Cotabato | 2014-02-04 | 1st | DOTC | LF | 110.291 | 360 | 2013-07-01 | 2014-07-25 | 2.16 | O | 0.387 | 0.3 | 0.15 | 0.01 | 0.061 | 0.05 | 95.8 | -
Vicente T. Lao Construction | 7040 | L | AAA |  |  | Cotabato Airport Development Project | Awang, Datu Sinsuat Maguindanao/ Region XII | 2014-05-14 | 1st | DOTC | LF | 55.695 | 210 | 2013-11-26 | 2014-11-25 | 16.22 | O | 0.3196 | 0.3 | 0.15 | 0.03 | 0.0318 | 0.05 | 88.14 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE | Asset Preservation of National Roads Generated from Pavement System/Higway Dev't and Management -4 (HDM-4), Preventive Maintenance (Intermittent Sections) Bacolod South Road (Kabankalan - Hinoba-an Section) | Kabankalan City, Negros Occidental | 2014-08-08 | Final | VI | LF | 18.2907 | 180 | 2013-03-22 | 2013-07-19 | 0 | C | 0.376 | 0.2 | 0.3 |  |  |  | 87.6 | 86.22% Satisfactory
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Prev. Maint. (Int. Sect.), Bacolod South Rd. (Kabankalan-Hinoba-an Sect.) | Kabankalan City & Ilog, Negros Occidental | 2013-08-08 | 1st | VI | LF | 17.286 | 150 | 2013-03-22 | 2013-08-18 | -7.89 | O | 0.363 | 0.3 | 0.071 | 0.03 | 0.056 | 0.033 | 85.3
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Restoration/Rehab. of Jct. Pontevedra-La Castellana Rd., Sta.47+975-Sta.54+020 (w/ exceptions) | Negros Occidental | 2013-03-14 | Final | VI | LF | 78.418 | 389 | 2011-10-28 | 2012-11-21 | 0 | C | 0.363 | 0.2 | 0.3 | - | - | - | 86.3 | 84.26% Satisfactory
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE | Construction/Rehabilitation of Flood Control Structure at Olave River, Siquijor, Circumferential Road, K0025+252 | Siquijor | 2014-10-28 | 1st | VII | LF | 18.3867 | 261 | 2014-05-13 | 2015-01-28 | -13.35% | O | 0.37 | 0.3 | 0.014 | 0.03 | 0.056 | 0 | 77% | 77% Unsatisfactory
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Impvt./Conc. Paving of Sindangan-Siayan-Dumingag Road |  | 2008-09-04 | 1st | IX |  | 28.546 | 475 |  |  |  | O | 0.304 | 0.24 | 0 | 0.03 | 0.042 | 0.1 | 71.6 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Impvt./Conc. Paving of Sindangan-Siayan-Dumingag Road |  | 2008-12-04 | 2nd | IX |  | 28.948 | 345 |  |  |  | O | 0.345 | 0.24 | 0.1 | 0.03 | 0.04 | 0.1 | 85.5 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Impvt. of Access Road Leading to Dipolog Airport, Minaog |  | 2009-06-10 | 1st | IX |  | 4.762 | 100 |  |  |  | O | 0.357 | 0.24 | 0.15 | 0.03 | 0.047 | 0.033 | 85.7 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Rehab./Reconst./Upgrading of Damaged Paved National Road Junction, Polo-Dapitan Park Road |  | 2009-06-09 | 1st | IX |  | 15.268 | 126 |  |  |  | O | 0.391 | 0.24 | 0.15 | 0.02 | 0.037 | 0.033 | 87.1 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Rehab./Reconst./Upgrading of Junction Pulauan Port Road |  | 2009-06-09 | 1st | IX |  | 15.268 | 130 |  |  |  | O | 0.386 | 0.24 | 0.15 | 0.01 | 0.037 | 0.033 | 85.6 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Impvt./Concrete Paving of Gutalac-Baliguian-Siocon Road, Nonoyan-Sta. Maria Section |  | 2009-05-28 | 3rd | IX |  | 48.156 | 732 |  |  |  | O | 0.388 | 0.24 | 0.15 | 0.03 | 0.047 | 0.05 | 90.5 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Impvt./Concrete Paving of Gutalac-Baliguian-Siocon Road, Nonoyan-Sta. Maria Section |  | 2009-03-07 | 2nd | IX |  | 48.156 | 539 |  |  |  | O | 0.378 | 0.261 | 0.15 | 0.03 | 0.047 | 0.05 | #VALUE! | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Impvt./Concrete Paving of Gutalac-Baliguian-Siocon Road, Sta. Maria Section |  | 2008-08-26 | 1st | IX |  | 48.156 | 290 |  |  |  | O | 0.27 | 0.252 | 0 | 0.03 | 0.042 | 0.1 | 69.4 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Impv't/Conc. Paving of Dipolog-Punta-Dansullan-S. Osmeña Road (Dilawa Section) |  | 2009-03-16 | 1st | IX |  | 19.092 | 210 |  |  |  | O | 0.368 | 0.3 | 0.15 | 0.03 | 0.03 | 0.05 | #VALUE! | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Impv't/Conc. Paving of Dipolog-Punta-Dansullan-S. Osmeña Road, Macleodes Sect. |  | 2009-03-16 | 1st | IX |  | 19.092 | 210 |  |  |  | O | 0.376 | 0.3 | 0.15 | 0.03 | 0.03 | 0.05 | #VALUE! | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Repair/Asphalt Overlay along Titay-Ipil, Kitabog Section, Km. 2004+457-Km. 2005+457 |  | 2009-09-04 | 1st | IX |  | 19.286 | 110 |  |  |  | O | 0.367 | 0.3 | 0.15 | 0.03 | 0.05 | 0.033 | 93 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Repair/Asphalt Overlay along Titay-Ipil, Kitabog Section, Km. 2005+457-Km. 2008+197 length 1000 meters |  | 2009-09-04 | 1st | IX |  | 19.286 | 160 |  |  |  | O | 0.35 | 0.3 | 0.15 | 0.03 | 0.05 | 0.033 | 91.3 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Rehab./Reconst./Upgrading of Damaged Road of Dipolog-Polanco-Oroquieta Road |  | 2009-09-16 | 2nd | IX |  | 10.49 | 180 |  |  |  | O | 0.298 | 0.3 | 0.15 | 0.03 | 0.04 | 0.033 | 85.1 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Rehab./Reconst./Upgrading of Damaged Road of Dipolog-Polanco-Oroquieta Road |  | 2009-06-10 | 1st | IX |  | 10.49 | 180 |  |  |  | O | 0.389 | 0.24 | 0.15 | 0.03 | 0.047 | 0.05 | 90.6 | -
Vicente T. Lao Construction | 7040 |  |  |  |  | Upgrading/Improvement/Rehab. of National Road along Sindangan-Liloy- Ipil National Road Section Km. 1961+050 - Km. 1987+000 w/ exception |  | 2010-03-03 |  | IX |  | 37.15 | 95 |  |  |  | O | 0.292 | 0.3 | 0.15 | 0.022 | 0.037 | 0.05 | 85.1 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Rds. Upgrading (Gravel to Paved) of Sindangan-Siayan-Dumingag-Mahayag Rd., Sta.1942+320-Sta.1948+380 w/ exception | Zamboanga del Norte | 2012-11-28 | 1st | IX | LF | 184.569 | 348 | 2012-05-14 | 2013-04-26 | 1.81 | O | 0.309 | 0.24 | 0.15 | 0.03 | 0.059 | 0.05 | 83.8 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Rd. Upgrading (Gravel to Paved) Jct. Alicia-Imelda Rd. (Lambuyugan-Alicia Sect.) | Zamboanga Sibugay | 2012-11-23 | 2nd | IX | LF | 88.196 | 314 | 2012-05-02 | 2013-03-11 | -7.81 | O | 0.344 | 0.294 | 0.072 | 0.03 | 0.054 | 0.033 | 82.7 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Rd. Upgrading (Gravel to Paved) Jct. Alicia-Imelda Rd. (Lambuyugan-Alicia Sect.) | Zamboanga Sibugay | 2012-08-28 | 1st | IX | LF | 88.196 | 290 | 2012-05-02 | 2013-02-15 | -3.51 | O | 0.334 | 0.286 | 0.115 | 0.03 | 0.038 | 0.033 | 83.6 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE2 | Concrete Sheet Piling & Impvt. & Const. of Seawall of R.T. Lim Blvd. (Phases II & III), Sta.0+487-Sta.0+827 | Zamboanga City | 2012-11-19 | 2nd | IX | LF | 29.215 | 389 | 2012-01-09 | 2013-01-31 | -6.71 | O | 0.38 | 0.24 | 0.08 | 0.03 | 0.06 | 0.033 | 82.3 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Concrete Sheet Piling & Impvt. & Const. of Seawall of R.T. Lim Blvd. (Phase II & III), Sta.0+487-Sta.0+827 | Zamboanga City | 2012-08-13 | 1st | IX | LF | 27.69 | 359 | 2012-01-09 | 2013-01-01 | -1.48 | O | 0.385 | 0.24 | 0.135 | 0.03 | 0.032 | 0.033 | 85.5 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Concrete Sheet Piling & Impv't. & Const. of Seawall of R.T. Lim Blvd. (Phases II & III), Sta.0+487-Sta.0+827 | Zamboanga City | 2013-03-11 | 3rd | IX | LF | 30.457 | 449 | 2012-01-09 | 2013-04-01 | -1 | O | 0.358 | 0.24 | 0.14 | 0.03 | 0.047 | 0.05 | 86.5 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Prev. Maint. (Int. Sect.) Zamboanga City-Labuan-Limpapa Rd., Sta.1938+141-Sta.1945+490 | Zamboanga City | 2013-08-05 | 2nd | IX | LF | 95.845 | 300 | 2012-10-04 | 2013-07-31 | -5.12 | O | 0.346 | 0.3 | 0.099 | 0.03 | 0.037 | 0.033 | 84.5
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Prev. Maint. (Int. Sect.) Zamboanga City-Labuan-Limpapa Rd., Sta.1938+141-Sta.1945+490 | Zamboanga City | 2013-03-12 | 1st | IX | LF | 95.845 | 240 | 2012-10-04 | 2013-06-01 | -9.11 | O | 0.385 | 0.3 | 0.059 | 0.03 | 0.042 | 0.033 | 84.9 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Rd. Upgrading (Gravel to Paved) Jct. Alicia-Imelda Rd. (Lambuyugan-Alicia Sect.) | Zamboanga Sibugay | 2013-03-18 | 3rd | IX | LF | 88.196 | 402 | 2012-05-02 | 2013-06-07 | -12.7 | O | 0.378 | 0.3 | 0.023 | 0.03 | 0.061 | 0.033 | 82.5 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Prev. Maint. along Dipolog-Polanco-Piñan Jct.-Oroquieta Rd., 1)Km.1833+834-Km.1834+600; 2)Km.1834+600-Km.1834+700 | Dipolog City | 2013-08-22 | Final | IX | LF | 6.996 | 46 | 2013-02-26 | 2013-04-12 | 0 | C | 0.399 | 0.133 | 0.3 | - | - | - | 83.2 | 86.32% Satisfactory
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Prev. Maint. along Dipolog-Polanco-Piñan Jct.-Oroquieta Rd., 1) Km.1833+834-Km.1834+600; 2) Km.1834+600-Km.1834+700 | Dipolog City | 2013-03-23 | 1st | IX | LF | 6.996 | 46 | 2013-02-26 | 2013-04-12 | 4.42 | O | 0.376 | 0.24 | 0.15 | 0.03 | 0.038 | 0.05 | 88.4 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Rd. Upgrading (Gravel to Paved) of Sindangan-Siayan-Dumingag-Mahayag Rd., Sta.1942+320-Sta.1948+380 w/ exceptions | Siayan, Zamboanga del Norte | 2013-08-23 | 2nd | IX | LF | 184.569 | 484 | 2012-05-14 | 2013-09-09 | 0.579 | O | 0.274 | 0.278 | 0.15 | 0.023 | 0.059 | 0.05 | 83.4 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE | Assets Preservation of National Road Preventive Maintenance Based on Pavement Management System/Highway Development and Management-4 (HDM-4) (Intermittent Section) Dipolog-Oroquieta National Road K 1796+100 to K 1797+774 | Rizal, Zamboanga del Norte | 2014-10-28 | 1st & Final | IX | LF | 11.0434 | 30 | 2014-02-10 | 2014-03-11 | 0% | C | 0.44 | 0.199 | 0.3 | - | - | - | 93.9% | 93.9% Very Satisfactory
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE | Completion of Lower Sultan Bridge (Phase II) aong crossing Sta. Clara-Sandayong Road Km. 1792+171.551 to Km. 1792+214.371 | Zamboanga Sibugay | 2014-10-23 | 1st | IX | LF | 15.8536 | 230 | 2014-05-02 | 2014-12-17 | -12.8% | O | 0.345 | 0.286 | 0.022 | 0.03 | 0.04 | 0.017 | 74% | 74% Poor
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE | Construction/Improvement of Access Road Leading to Declared Tourism Destinations: Turno By-Pass Road Leading to Linabo Peak (3003) steps, Dipolog City | Dipolog City | 2014-10-29 | 1st & Final | IX | LF | 27.8926 | 239 | 2014-03-26 | 2014-11-19 | -10.07% | C | 0.298 | 0.3 | 0.049 | - | - | - | 73.9% | 73.9% Poor
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Road Including Drainage based on Pavement Management System/Highway Development and Management-4 (HDM-4) (Intermittent Section), Dipolog-Polanco-Piñan-Jct. Oroquieta Road K 1815+600 to K 1817 +005 | Piñan, Zamboanga del Norte | 2014-10-28 | 1st & Final | IX | LF | 20.4426 | 166 | 2014-02-17 | 2014-08-01 | 0% | C | 0.472 | 0.196 | 0.23 | - | - | - | 89.8% | 89.8% Very Satisfactory
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE | Rehabilitation/Reconstructtion/Upgrading of Damaged Paved National Road including Drainage based on Pavement Management System /Highway Devt. & Management-4 (HDM-4) (Intermittent Section), Dipolog-Polanco-Piñan-Jct. Oroqueta Road K1815+600 to K1817+005 | Piñan, Zamboanga Del Norte | 2014-08-14 | 1st & Final | IX | LF | 20.0617 | 168 | 2014-02-17 | 2014-08-03 | 0 | C | 0.407 | 0.196 | 0.3 |  |  |  | 90.3 | 90.30% Very Satisfactory
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE | Preventiive Maintenance (Intermittent Section) Zamboanga City-Lubuan-Limpapa Road, Sta. 1938+141 to Sta. 1945+520.39 | Zamboanga City | 2014-08-04 | Final | IX | LF | 98.8475 | 380 | 2012-10-04 | 2013-10-18 | 0 | C | 0.418 | 0.133 | 0.3 |  |  |  | 85.1 | 84.86% Satisfactory
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE2 | Revetment of Cagayan de Oro River (Carmen Side, Acacia Sect.) | Cagayan de Oro City | 2013-03-11 | 2nd | X | LF | 46.548 | 248 | 7/32/13 | 2013-03-27 | 0.54 | O | 0.281 | 0.3 | 0.15 | 0.01 | 0.047 | 0.05 | 83.8 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Road Upgrading (Gravel to Paved), Kibawe-Kadilingan-Kalilangan Road, K1585+152-K1586+000, Brgy. Domagook | Kibawe, Bukidnon | 2011-08-09 | 1st | X | LF | 7.671 | 87 | 2011-05-23 | 2011-08-17 | 18.3 | O | 0.338 | 0.287 | 0.15 | 0.03 | 0.04 | 0.033 | 87.8 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE2 | Revetment of Cagayan de Oro River (Carmen Side, Acacia Sect.) | Cagayan de Oro City | 2012-11-24 | 1st | X | LF | 46.548 | 195 | 2012-07-23 | 2013-02-02 | 2.4 | O | 0.3 | 0.3 | 0.15 | 0.03 | 0.05 | 0.033 | 86.3 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Road Upgrading/Asphalting of Don Carlos-Kadingilan Road |  | 2009-09-03 | 1st | X |  | 38.171 | 120 |  |  |  | O | 0.378 | 0.245 | 0.15 | 0.003 | 0.051 | 0.05 | 87.7 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Asphalting of Don Carlos - Kadilingan Road |  | 2009-09-03 | 1st | X |  | 48.25 | 210 |  |  |  | O | 0.31 | 0.3 | 0 | 0.03 | 0.056 | 0.05 | 74.6 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE | Repair/Rehab./Impvt. Along Daang Maharlika (Agusan-Davao) Road, San Roque Section | Nabunturan, Comval Province | 2014-10-26 | 1st & Final | XI | LF | 9.3092 | 84 | 2014-01-23 | 2014-04-16 |  | C | 0.415 | 0.145 | 0.3 | - | - | - | 86% | 86% Satisfactory
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Widening/Reconst. along Davao-Cotabato Rd. (Davao City-Jct. Digos) | Davao City | 2013-08-21 | 1st | XI | LF | 50.141 | 243 | 2013-03-25 | 2013-11-22 | -2.45 | O | 0.346 | 0.3 | 0.126 | 0.03 | 0.03 | 0.033 | 86.5
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Prev. Maint. (Intermittent Sect.) along Daang Maharlika Rd. | Davao City | 2013-03-17 | Final | XI | LF | 99.893 | 297 | 2012-03-28 | 2013-01-18 | 0 | C | 0.412 | 0.133 | 0.3 | - | - | - | 84.5 | 83.78% Satisfactory
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Const. of Calinan-Toril Road inc. ROW | Davao City | 2013-03-21 | 1st | XI | LF | 81.765 | 445 | 2012-04-24 | 2013-07-12 | -2.57 | O | 0.327 | 0.24 | 0.124 | 0.03 | 0.055 | 0.05 | 82.6 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Preventive Maintenance (Intermittent Sections) a.) Daang Maharlika (MN): 1)Km.1497+914-Km.1498+473.25 | Davao City | 2011-08-25 | 1st | XI | LF | 16.99 | 90 | 2011-06-03 | 2011-08-31 | 6.34 | O | 0.3 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 82.5 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE | Concreting/Widening of Dulawan-Marbel Road (New Carmen-Kalandagan Section), K1766+815 - K1769+071 w/ exceptions | Tacurong City | 2014-10-23 | 1st | XII | LF | 40.1809 | 224 | 2014-02-25 | 2014-10-06 | -6.81% | O | 0.338 | 0.215 | 0.082 | 0.02 | 0.045 | 0.033 | 73.3% | 73.3% Poor
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE | Rehabilitation/Retrofitting of Molo Bridge along Demolos-Little Baguio, Alabel Road | Alabel, Sarangani Province | 2014-10-29 | 1st & Final | XII | LF | 12.3182 | 140 | 2014-02-12 | 2014-07-01 | 0% | C | 0.446 | 0.104 | 0.3 | - | - | - | 85% | 85% Satisfactory
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE2 | Strengthening of Tunggol Bridge II Km.1660+562 (Approach "A") along Davao-Cotabato Rd. | Datu Montawal, Maguindanao | 2013-03-18 | 3rd | XII | LF | 46.452 | 340 | 2012-05-22 | 2013-04-27 | 2.97 | O | 0.317 | 0.299 | 0.15 | 0.03 | 0.065 | 0.05 | 91.1 | -
Vicente T. Lao Construction | 7040 |  |  |  |  | Const. of Allah River Bank Protection/River Control along Colongolo-Centralla Section |  | 2010-03-06 |  | XII |  | 18.152 | 140 |  |  |  | O | 0.276 | 0.3 | 0.15 | 0.03 | 0.035 | 0.033 | 82.4 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE2 | Initial Dredging of Rio Grande de Mindanao | Cotabato City | 2011-08-12 | 1st | XII | LF | 144.55 | 601 | 2010-07-27 | 2012-03-19 | -0.937 | O | 0.4 | - | 0.188 | 0.05 | 0.043 | 0.25 | 93.1 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Strengthening of Tunggol Bridge II, Km. 1660+562 (Approach "A") along Davao-Cotabato Rd. | Datu Montawal, Maguindanao | 2012-11-22 | 2nd | XII | LF | 44.887 | 295 | 2012-05-22 | 2013-03-13 | 2.54 | O | 0.352 | 0.3 | 0.15 | 0.03 | 0.055 | 0.05 | 93.7 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Strengthening of Tunggol Bridge II Km.1660+562 (Approach "A") along Davao-Cotabato Rd. | Datu Monawal, Maguindanao | 2012-08-15 | 1st | XII | LF | 44.887 | 280 | 2012-05-22 | 2013-02-26 | 4.82 | O | 0.391 | 0.24 | 0.15 | 0.03 | 0.051 | 0.05 | 91.2 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Asphalt Overlay of Fil-Am Friendship Ave., (GSC Airport Rd.) | General Santos City | 2013-03-23 | 1st | XII | LF | 10.24 | 120 | 2013-01-14 | 2013-05-13 | 7.68 | O | 0.37 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 89 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Repair/Rehab. of Cotabato-Lanao Nat'l. Rd. Simuay-Landasan-Parang Sect., Km.1865+553.40-Km.1878+442 | Sultan Mastura, Maguindanao | 2013-03-15 | Final | XII | LF | 122.303 | 375 | 2012-02-07 | 2013-02-16 | 5.81 | C | 0.408 | 0.133 | 0.3 | - | - | - | 84.1 | 88.30% Satisfactory
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Road Upgrading (Gravel to Conc.) of Jct. Lingig-Trento Rd., Km.1478+265-Km.1482+620 | Bislig, Surigao del Sur | 2013-03-22 | 1st | XIII | LF | 95.636 | 345 | 2012-04-30 | 2013-04-09 | -8.23 | O | 0.305 | 0.296 | 0.15 | 0.03 | 0.033 | 0.05 | 86.4 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Conc. of NRJ Cuevas-Bislig Road Km.1379+089.20-Km.1386+000 | Trento, Agusan del Sur | 2012-03-27 | Final | XIII | LF | 83.718 | 300 | 2011-09-26 | 2012-07-21 | -4.928 | O | 0.375 | 0.3 | 0.101 | 0.03 | 0.035 | 0.017 | 85.8 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Conc. of NRJ-Cuevas-Bislig Rd., Km. 1400+000-Km.1402+000 | Trento, Agusan del Sur | 2012-11-26 | 2nd | XIII | LF | 44.644 | 330 | 2012-01-31 | 2012-12-25 | -9.5 | O | 0.343 | 0.3 | 0.055 | 0.03 | 0.06 | 0.033 | 82.1 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Conc. of NRJ-Cuevas-Bislig Rd., Km. 1395+000-Km.1396+915.50 | Trento, Agusan del Sur | 2012-11-26 | 2nd | XIII | LF | 41.552 | 326 | 2012-01-30 | 2012-12-20 | -8.5 | O | 0.333 | 0.3 | 0.065 | 0.03 | 0.06 | 0.033 | 82.1 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE | Road Upgrading (Gravel-Paved) of Dinagat-Loreto Road (Llamera-Garcia Section), K48+700 - K52+500 with exception | Dinagat, Dinagat Province | 2014-10-27 | 1st | XIII | LF | 118.3905 | 285 | 2014-05-15 | 2015-02-23 | -8.89% | O | 0.38 | 0.3 | 0.061 | 0.023 | 0.037 | 0.033 | 83.4% | 83.4% Satisfactory
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Conc. of NRJ-Cuevas Bislig Rd., Km.1373+608-Km.1374+422; Km.1394+840-Km.1395+000 | Trento, Agusan del Sur | 2012-08-17 | 1st | XIII | LF | 20.677 | 235 | 2012-01-29 | 2012-09-20 | -8 | O | 0.374 | 0.298 | 0.07 | 0.03 | 0.05 | 0.033 | 85.5 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Conc. of NRJ-Cuevas Bislig Rd., Km.1395+000-Km.1396+915.50 | Trento, Agusan del Sur | 2012-08-17 | 1st | XIII | LF | 41.323 | 296 | 2012-01-30 | 2012-11-20 | -2.02 | O | 0.347 | 0.248 | 0.13 | 0.03 | 0.05 | 0.033 | 83.8 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB | GE1 | Conc. of NRJ-Cuevas Bislig Rd., Km.1400+000-Km.1402+000 | Trento, Agusan del Sur | 2012-08-17 | 1st | XIII | LF | 42.679 | 285 | 2012-01-31 | 2012-11-11 | -9.07 | O | 0.361 | 0.293 | 0.059 | 0.03 | 0.05 | 0.033 | 82.6 | -
Vicente T. Lao Construction | 7040 |  | AAA | LB |  | Dipolog Airport Development Project | Brgy. Minaog, Dipolog City/ Region IX | 2016-01-28 | 3rd | DOTC | LF | 27.578 | 520 | 2014-02-03 | 2015-07-07 | 2.27 | O | 0.3163 | 0.3 | 0.15 | 0.03 | 0.0509 | 0.05 | 89.72 | -
VICENTE T. LAO CONSTRUCTION | 7040 | L | AAA | LB | GE | Const./Improvement of Access Road Leading to Declared Tourism Destination, Const./Extension of Dipolog City Boulevard, Dipolog City | Dipolog City | 2015-06-04 | 1st | Zamboanga del Norte 1st DEO | LF | 46.507 | 187 | 2015-02-28 | 2015-09-02 | 1.07% | O | 0.37 | 0.271 | 0.15 | 0.03 | 0.05 | 0.05 | 92.1% | -
VICENTE T. LAO CONSTRUCTION | 7040 | L | AAA | LB | GE | Asphalt Overlay along Marbel-Makar Road, K1686+000 - K1686+392 (4-Lanes), K1687+435-K1688+150 (4-Lanes0, K1686+392-K1687+435 (6-Lanes) | Tupi, South Cotabato | 2015-06-03 | Final | Regional Office No. XII | LF | 99.438 | 194 | 2014-03-26 | 2014-10-05 | 1.9% | C | 0.466 | 0.133 | 0.3 | - | - | - | 89.9% | *89.9% Very Satisfactory
VICENTE T. LAO CONSTRUCTION | 7040 | L | AAA | LB | GE | Concreting/Widening of Dulawan-Marbel Road (New Carmen-Kalandagan Section) K1766+815-K1769+071 w/ exceptions | Tacurong City | 2015-06-03 | Final | Sultan Kudarat 1st DEO | LF | 40.181 | 253 | 2014-02-25 | 2014-11-05 | 0% | C | 0.454 | 0.2 | 0.3 | - | - | - | 95.4% | *82.14% Satisfactory
VICENTE T. LAO CONSTRUCTION | 7040 | L | AAA | LB | GE | Widening of Dipolog-Oroquieta National Road, Zamboanga del Norte, National Roads, Section 1: 1840+540 to 1841+700; Section 2:1843+604.23 to 1844+220 | Zamboanga del Norte | 2015-08-28 | 1st | Regional Office No. IX | LF | 72.074 | 261 | 2015-05-20 | 2016-02-04 | (+)12.76% | O | 0.395 | 0.24 | 0.15 | 0.022 | 0.056 | 0.05 | 91.3% | -
VICENTE T. LAO CONSTRUCTION | 7040 | L | AAA | LB | GE | Construction/Improvement of Access Roads Leading to Declared Tourism Destination: For Dipolog City Boulevard, Dipolog City | Dipolog City, Zamboanga del Norte | 2015-08-27 | 1st & Final | Zamboanga del Norte 1st | LF | 46.462 | 281 | 2015-03-27 | 1/12016 | - | C | 0.454 | 0.133 | 0.3 | - | - | - | 88.7% | *88.7% Satisfactory
Vicente T. Lao Construction | 7040 | L |  | LB |  | Rehabilitation/ Upgrading of Western Wharf | Makar Port, General Santos City | 2016-06-29 | 2nd | PPA | LF | 102.156 | 569 | 2014-12-01 | 2016-06-22 | -33.982 | O | 0.392 | 0.296 | 0 | 0.03 | 0.07 | 0.05 | 83.8 | -
Vicente T. Lao Construction | 7040 | L | AAA | LB |  | Dipolog Airport Development Project | Dipolog City, Zamboanga del Norte | 2016-04-06 | 4th & Final | DOTC | LF | 27.578 | 520 | 2014-02-03 | 2016-03-03 | 0.1 | C | 0.458 | 0.2 | 0.3 | - | - | - | 95.8 | 93.90% V. Satisfactory
Vicente T. Lao Construction | 7040 | L | AAA | LB |  | Cotabato Airport Development Project | Brgy. Awang, Datu Odin Sinsuat, Maguindanao/ Region XII | 2016-04-13 | Final | DOTC | LF | 55.676 | 270 | 2013-11-26 | 2015-04-22 | 0 | C | 0.4626 | 0.2 | 0.3 | - | - | - | 96.26 | 91.97% V. Satisfactory
VICENTE T. LAO CONSTRUCTION | 7040 | L | AAA | LB | GE | Widening of Makar-Kiamba Road, K1668+175 - K1674+100 w/ exceptions; K1669+140 - K1669+300; K1671+220 - K1671+300; K1673+200 - K1673+400 | General Santos City | 2015-11-17 | Final | Regional Office No. XII | LF | 120.9157 | 260 | 2015-04-14 | 2015-12-29 | (+) 10.09% | C | 0.352 | 0.297 | 0.15 | 0.03 | 0.05 | 0.033 | 91.2% | 91.2% Very Satisfactory
VICENTE T. LAO CONSTRUCTION | 7040 | L | AAA | LB | GE | Road Widening of Marbel-Cotabato Road, K1714+880.35 - K1715+034.35; K1715+689.69 - K1716+909.91; K1735+448.08 - K1740+230 | Suralla, South Cotabato | 2015-11-10 | 1st | Regional Office No. XII | LF | 136.1515 | 282 | 2015-04-27 | 2015-02-02 | (-) 0.80% | OG | 0.383 | 0.297 | 0.142 | 0.015 | 0.04 | 0.017 | 89.4% | 89.4% Very Satisfactory
VICENTE T. LAO CONSTRUCTION | 7040 | L | AAA | LB | GE | Road Upgrading (Unpaved to Paved) along NRJ Pulanng Lupa-Sta. Josefa Road, K1372+(-105) - K1374+120, S00472MN, Pulang Lupa, Trento, Agusan del Sur | Pulang Lupa, Trento, Agusan del Sur | 2015-11-11 | 1st | Agusan del Sur 2nd DEO | LF | 2.606 | 297 | 2015-03-25 | 2016-01-15 | (+) 8.00 | OG | 0.337 | 0.3 | 0.15 | 0.03 | 0.055 | 0.05 | 92.2% | 92.2% Very Satisfactory
Vicente T. Lao Construction | 7040 | L | AAA |  | GE5 | Port Improvement Project of Port of Glan | Glan, Sarangani Province | 2012-10-18 | Final | PPA | LF | 28.625 | 706 | 2010-07-13 | 2012-08-30 | 0.575 | O | 0.433 | 0.2 | 0.3 | - | - | - | 93.3 | 91.91% V. Satisfactory
VICENTE T. LAO CONSTRUCTION | 7040 | L | AAA | LB | GE | Road Upgrading (Unpaved to Paved) along NRJ Pulang Lupa - Sta. Josefa Road, S00472MN | K1372+(-105) to K1374+120, Pulang Lupa, Trento Agusan Del Sur | 2015-06-05 | 1st | AGUSAN DEL SUR SECOND DEO | LF | 13.802 | 117 | 2015-03-25 | 2015-07-19 | (+) 1.97% | O | 0.385 | 0.238 | 0.15 | 0.03 | 0.05 | 0.05 | 90.3% | -
Vicente T. Lao Construction | 7040 | L | AAA |  | GE5 | Construction of RC Landing and Rehabilitation of Existing Bulkhead | Port of Glan, Sarangani Province |  | 1st | PPA | LF | 28.625 | 510 | 2010-10-05 | 2012-09-03 | -3.61 | O | 38.1 | 30 | 11.85 | 2.4 | 7 | 1.67 | 91.02 | -
Vicmar Construction | 28997 | L |  |  | GE5 | Repair of Causeway | Port of Banago, Banago, Bacolod City | 2012-09-14 | 1st | PPA | LF | 35.513 | 215 | 2012-02-13 | 2012-09-14 | 0.42 | O | 0.31 | 0.3 | 0.15 | 0.03 | 0.053 | 0.05 | 89.3 | -
Vicmar Construction Inc. | 28997 |  |  |  |  | Road Upgrading (Gravel to Paved) along Batangas-Tabangao-Lobo Rd. (Talahib-Pandayan Sect.) Km.140+402 - Km.140+853 with exception |  | 2010-06-04 |  | IVA |  | 9.645 | 85 |  |  |  | O | 0.347 | 0.225 | 0.15 | 0.023 | 0.059 | 0.05 | 85.4 | -
Vicmar Construction Inc. | 28997 | L | A | MB | GE1 | Conc. of Palapag-Mapanas Gamay-Lapinig Road |  | 2009-03-03 | 1st | VIII |  | 77.044 | 298 |  |  |  | O | 0.349 | 0.237 | 0.15 | 0.03 | 0.047 | 0.05 | #VALUE! | -
Vicmar Construction Inc. | 28997 | L | AAA |  | GE5 | Construction of RC Platform Connecting Phase 1 and 2 | Port of Batangas | 2013-11-15 | Final | PPA | L | 21.173 | 210 | 2013-01-23 | 2013-09-02 | 0 | C | 0.492 | 0.2 | 0.3 | - | - | - | 99.2 | 97.70% Outstanding
Vicmar Construction Inc. | 28997 | L | AAA | MA | GB | Construction and Rehabilitation of MPB Structure (Covered Court) Brgy. Sambat | Balayan, Batangas | 2014-11-08 | 1st & Final | IV | LF | 2.79 | 90 | 2014-04-07 | 2014-07-05 | 27% | C | 0.392 | 0.133 | 0.3 | - | - | - | 82.5% | 82.5% Satisfactory
Vicmar Construction Inc. | 28997 | L | AAA | MA | GB | Widening of Nat'l. Arterial Road along Palico-Balayan-Batangas Road incl. Drainage, Batangas 1st Legislative District, K0125+260-K0125+660 & K0125+080-K0125+260, Bukal-Tubigan Section | Lemery, Batangas | 2014-11-08 | 1st & Final | IV | LF | 18.7148 | 198 | 2014-02-03 | 2014-08-19 | 0.51% | C | 0.444 | 0.133 | 0.3 | - | - | - | 87.7% | 87.7% Satisfactory
VICMAR CONSTRUCTION, INC | 28997 | L | AAA | MB | GE | Off-Cariageway Improvement, Concreting of Road Shoulder, Laoang-Calomotan Rd., 2nd Dist. Samar, K0794+700 - K0796+500, 2nd District, Northern Samar | K0794+700 - K0796+500, 2nd District, Northern Samar | 2015-09-04 | 1st & Final | Northern Samar 2nd DEO | LF | 31.274 | 165 | 2015-03-11 | 2015-08-22 | - | C | 0.386 | 0.2 | 0.3 | - | - | - | 88.6% | *88.6% Satisfactory
Vicmar Construction, Inc. | 28997 | L | AAA | SB | GE2 | Const. of Flood Control System along Palico-Balayan-Lemery Diversion Rd., K0129+560-K0131+700 (Int. Sect.) | Taal, Batangas | 2013-07-30 | Final | IVA | LF | 9.695 | 150 | 2013-02-21 | 2013-07-20 | 6 | C | 0.382 | 0.2 | 0.3 | - | - | - | 88.2 | 88.32% Satisfactory
Vicmar Construction, Inc. | 28997 | L | AAA | SB | GE2 | Const. of Flood Control System along Palico-Balayan-Lemery Diversion Rd., K0129+560-K0131+700 (Int. Sect.) | Taal, Batangas | 2013-03-13 | 1st | IVA | LF | 9.695 | 150 | 2013-02-21 | 2013-07-20 | 16.04 | O | 0.381 | 0.24 | 0.15 | 0.03 | 0.05 | 0.033 | 88.4 | -
VICMAR CONSTRUCTION, INC. | 28997 | L | AAA | MB | GE | Repair/Rehabilitation/Improvement along Tagaytay - Nasugbu Road, K0076+000 to K0077+000 with exception | Nasugbu, Batangas | 2015-06-03 | Final | Batangas 1st DEO | LF | 12.347 | 120 | 2014-12-01 | 2015-03-30 | 0% | C | 0.481 | 0.129 | 0.3 | - | - | - | 91% | *91% Very Satisfactory
VICMAR CONSTRUCTION, INC. | 28997 | L | AAA | MA | GE | Construction of Shore Protection (Flood Control), Brgy. Baclaran | Balayan, Batangas | 2015-08-31 | 1st & Final | Batangas 1st | LF | 9.389 | 90 | 2015-02-06 | 2015-05-06 | 0% | C | 0.4 | 0.133 | 0.3 | - | - | - | 83.3% | *83.3% Satisfactory
VICMAR CONSTRUCTION, INC. | 28997 | L | AAA | MB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads Inc. Drainage based on PMS/HDM-4 (Intermittent Section) Nasugbu-Lian-Calatagan Road, K0106+500 - K0107+00, K0108+000 - K0108+500, K0119+00 - K0120+073, Lemery, Batangas | Lemery, Batangas | 2015-11-15 | Final | BATANGAS 1ST DEO | LF | 33.2868 | 194 | 2015-02-09 | 2015-08-21 | 0.03 | C | 0.447 | 0.136 | 0.3 | - | - | - | 88.3% | 88.3% Satisfactory
VICMAR CONSTRUCTION, INC. | 28997 | L | AAA | SB | GE | Construction/Rehabilitation of Floodway, Barangay Maligaya, Lemery, Batangas | Lemery, Batangas | 2015-11-15 | Final | BATANGAS 1ST DEO | LF | 9.3091 | 150 | 2015-06-09 | 2015-11-05 | 0 | C | 0.465 | 0.133 | 0.3 | - | - | - | 89.8% | 89.8% Very Satisfactory
Vicmar Construction, Inc. | 28997 | L | AAA |  | GE5 | Construction of R.C. Platform Connecting Phase 1 to Phase 2 | Port of Batangas | 2013-04-25 | 1st | PPA | LF | 21.206 | 210 | 2013-01-23 | 2013-08-20 | 1.67 | O | 0.4 | 0.3 | 0.15 | 0.03 | 0.054 | 0.033 | 96.7 | -
VICMAR CONSTRUCTION, INC. / X.Y.Z. CONSTRUCTION & SUPPLIES (JOINT VENTURE) | JV-14-736 | L | AAA | MB | GE | Off Carriageway Improvement, Tagaytay-Nasugbu Road, K0 072+(-240) - K0 073+091 | Batangas | 2015-08-31 | 1st & Final | Batangas 1st | LF | 22.77 | 164 | 2015-03-09 | 2015-08-19 | 1.72% | C | 0.413 | 0.133 | 0.3 | - | - | - | 84.6% | *84.6% Satisfactory
Victoria Development & Construction Supply Corp. | 32638 | L | B |  |  | BCIDP-IC | Bislig City, Surigao del Sur | 2014-06-07 | 1st | NIA | LF | 24.559 | 150 | 2012-09-01 | 2014-06-15 | 1 | O | 0.369 | 0.262 | 0.15 | 0.03 | 0.065 | 0.05 | 92.6 | -
VICTORIA DEVELOPMENT AND CONSTRUCTION SUPPLY CORP | 32638 | L | B | MA | GE | Rehabilitation/Reconstruction/Widening, Government Center Road Network K0913+(-500)-K0913+(-250), Palo, Leyte | Palo, Leyte | 2015-11-10 | Final | Leyte First DEO | LF | 7.1258 | 118 | 2015-01-30 | 2015-05-27 | (+)5.08 | C | 0.439 | 0.133 | 0.3 | - | - | - | 87.2% | 87.2% Satisfactory
Vigan Fortune Const. & Supply | 3887 | L |  |  |  | COMPLETION OF BOY'S DORMITORY | San Ildefonso, Ilocos Sur | 2013-08-01 | Final | DOST | LF | 4.999 | 195 | 2012-12-26 | 2013-06-09 | 0 | C | 0.459 | 0.2 | 0.3 | - | - | - | - | *95.9% V. Satisfactory
Vigan Fortune Const. & Supply | 3887 | L |  |  |  | COMPLETION OF GYMNASIUM | San Ildefonso, Ilocos Sur | 2013-08-01 | Final | DOST | LF | 22.686 | 525 | 2009-12-29 | 2011-06-07 | -4.3 | C | 0.47 | 0.2 | 0.17 | - | - | - | - | 79.19% Unsatisfactory
Vigan Fortune Construction | 3887 | L | A | MA | GE | Construction/ Rehabilitation of Drainage Protection Works along National Roads, Bucong Flood Control | Candon City, Ilocos Sur | 2014-10-24 | 1st & Final | I | LF | 9.4032 | 171 | 2014-02-17 | 2014-08-06 | 37.43% | C | 0.4 | 0.133 | 0.3 | - | - | - | 83.3% | 83.3% Satisfactory
Vigan Fortune Construction | 3887 | L | A | MA | GE | Widening of Manila North Road: K0412+200 to K0415+080 | Ilocos Sur | 2014-08-07 | Final | I | LF | 8.178 | 213 | 2013-01-24 | 2013-08-24 | 7.84 | C | 0.451 | 0.133 | 0.3 |  |  |  | 88.4 | 84.53% Satisfactory
Vigan Fortune Construction | 3887 | L | A | MA | GE1 | Widening of Manila North Rd.: a) K0405+000-K0407+880; b)K0409+583-K0412+500-K0415+080 | Ilocos Sur | 2013-08-13 | 2nd | I | LF | 8.178 | 213 | 2013-01-24 | 2013-08-24 | 2.04 | O | 0.319 | 0.285 | 0.15 | 0.03 | 0.042 | 0.05 | 87.6
Vigan Fortune Construction | 3887 | L | A | MA | GE1 | Widening of MNR: a)K0405+000-K0407+880; b)K0409+583-K0412+463; c)K0412+200-K0415+080 | Ilocos Sur | 2013-03-20 | 1st | I | LF | 8.178 | 179 | 2013-01-24 | 2013-07-21 | -14.35 | O | 0.352 | 0.3 | 0.007 | 0.03 | 0.041 | 0.033 | 76.3 | -
Vigan Fortune Construction | 3887 | L | A | MA | GE | Replacement/Rehab. Strengthening of Permanent Bridge Sta. Lucia Bridge along Manila North Road | Ilocos Sur | 2014-08-10 | Final | I | LF | 11.0475 | 200 | 2013-01-28 | 2013-08-15 | 0.5 | C | 0.369 | 0.2 | 0.3 |  |  |  | 86.9 | 85.37% Satisfactory
Vigan Fortune Construction | 3887 | L | A | MA | GE1 | Replacement/Rehab./Strengthening of Permanent Bridge, Sta. Lucia Bridge along MNR | Ilocos Sur | 2013-08-13 | 2nd | I | LF | 11.047 | 201 | 2013-01-28 | 2013-08-16 | 1.22 | O | 0.371 | 0.2 | 0.15 | 0.03 | 0.042 | 0.033 | 82.6
Vigan Fortune Construction | 3887 | L | A | MA | GE1 | Replacement/Rehab./Strengthening of Permanent Bridge, Sta. Lucia Bridge along MNR | Ilocos Sur | 2013-03-19 | 1st | I | LF | 11.049 | 180 | 2013-01-28 | 2013-07-26 | -3.71 | O | 0.35 | 0.3 | 0.113 | 0.03 | 0.035 | 0.033 | 86.1 | -
Vigan Fortune Construction | 3887 | L | A | MA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved National Roads, Tagudin Section |  | 2009-09-04 | 1st | I |  | 19.09 | 222 |  |  |  | O | 0.338 | 0.3 | 0.15 | 0.022 | 0.04 | 0.033 | 88.3 | -
VIGAN FORTUNE CONSTRUCTION | 3887 | L | A | MA | GB | Construction of Tagudin MPB | Tagudin, Ilocos Sur | 2015-06-02 | 1st | Ilocos Sur 2nd DEO | LF | 9.403 | 170 | 2015-02-09 | 2015-07-28 | 9.83% | O | 0.332 | 0.24 | 0.15 | 0.03 | 0.045 | 0.033 | 83% | -
VIGAN FORTUNE CONSTRUCTION | 3887 | L | A | MB | GB | Construction of Tagudin Multi Purpose Building, Tagudin, Ilocos Sur | Tagudin, Ilocos Sur | 2015-08-28 | Final | Ilocos Sur 2nd DEO | LF | 9.402 | 198 | 2015-02-09 | 2015-08-26 | - | C | 0.457 | 0.179 | 0.3 | - | - | - | 93.6% | *86.18% Satisfactory
VIGUZ CONSTRUCTION CORP. (Formerly Viguz Construction) | 8178 | L | B | MA | GE | Construction of Flood Control Structures along Binahann River, Brgy. Tingib, Pastrana, Leyte | Brgy. Tingib, Pastrana, Leyte | 2015-11-12 | 1st | Leyte Second DEO | LF | 22.5506 | 180 | 2015-06-15 | 2015-12-11 | - | OG | 0.334 | 0.3 | 0.15 | 0.03 | 0.065 | 0.05 | 92.9% | 92.9% Very Satisfactory
Viguz Construction Corporation | - | L | - | - | GE | Rehabilitation/Reconstruction of Critical Section along Secondary Roads, Roadslip along Jaro-Dagami-Burauen-La Paz Road, K0953+308 | Brgy. Rizal, Dagami, Leyte | 2014-10-29 | 1st & Final | VIII | LF | 9.3561 | 200 | 2014-01-24 | 2014-08-11 | 0% | C | 0.456 | 0.133 | 0.3 | - | - | - | 88.9% | 88.9% Satisfactory
Viguz Construction Corporation (Formerly: Viguz Construction) | 5463 | L | B | MA | GE | Road Upgrading (Gravel to paved) Based on Gravel Road Strategies Traffic Benchmark for Upgrading to Paved Road Standard (HDM-4) Project Analysis (Intermittent Section) National Secondary Roads Jaro-Dagami - Buraen - La Paz road , km. 957+657 ……………………. | Barugo, Leyte | 2014-08-08 | 1st | VIII | LF | 44.2509 | 205 | 2014-03-07 | 2014-08-28 | 0.38 | OG | 0.364 | 0.231 | 0.15 | 0.03 | 0.045 | 0.033 | 85.3
Viguz Construction Corporation (Formerly: Viguz Construction) | 8178 | L | B | MA | GE | Const. of Busay Bridge, along Barugo - Babatngon Road | Barugo, Leyte | 2014-08-09 | 1st & Final | VIII | LF | 17.6886 | 190 | 2013-02-28 | 2013-09-05 | 1.58 | C | 0.429 | 0.133 | 0.3 |  |  |  | 86.2 | 86.20% Satisfactory
Viguz Construction Corporation (Formerly: Viguz Construction) | 8178 | L | B | MA | GE1 | Const. of Busay Bridge, along Barugo-Babatngon Rd. | Barugo, Leyte | 2013-08-17 | 1st | VIII | LF | 17.689 | 190 | 2013-02-28 | 2013-09-05 | 3.79 | O | 0.377 | 0.231 | 0.15 | 0.015 | 0.047 | 0.05 | 87
Viguz Construction Corporation (Formerly: Viguz Construction) | 8178 | L | B | MA | GE1 | Rehab./Reconst. of Damaged Paved Nat'l Rds., Dulag-Julita-Burauen Rd., K0954+000-K0955+162; K0952+794-K0953+000 | Leyte | 2013-08-17 | Final | VIII | LF | 21.985 | 160 | 2013-01-15 | 2013-06-23 | 0 | C | 0.461 | 0.133 | 0.3 | - | - | - | 89.4 | 86.88% Satisfactory
Viguz Construction Corporation (Formerly: Viguz Construction) | 8178 | L | B | MA | GE1 | Rehab./Reconst. of Damaged Paved Nat'l. Rds., Dulag-Julita-Burauen Rd., K0954+000-K0955+162; K0952+794-K0953+000 | Leyte | 2013-03-11 | 1st | VIII | LF | 21.019 | 130 | 2013-01-15 | 2013-04-24 | 0.15 | O | 0.394 | 0.18 | 0.15 | 0.023 | 0.055 | 0.05 | 85.2 | -
Viguz Construction Corporation (Formerly: Viguz Construction) | 8178 | L | B | MA | GE1 | Road Slip along Liloan-Sogod Road Section |  | 2009-05-26 | 2nd | VIII |  | 9.542 | 270 |  |  |  | O | 0.382 | 0.238 | 0.15 | 0.03 | 0.047 | 0.033 | 88 | -
Viguz Construction Corporation (Formerly: Viguz Construction) | 8178 | L | B | MA | GE1 | Road Slip along Liloan-Sogod Road Section |  | 2009-03-05 | 1st | VIII |  | 9.542 | 240 |  |  |  | O | 0.32 | 0.246 | 0.15 | 0.03 | 0.03 | 0.05 | #VALUE! | -
Viguz Construction Corporation (Formerly: Viguz Construction) | 8178 | L | B | MA | GE1 | Road Upgrading (Gravel to Paved), Libungao-Matag-ob-Palompon Road |  | 2009-05-30 | 1st | VIII |  | 18.225 | 225 |  |  |  | O | 0.367 | 0.239 | 0.15 | 0.03 | 0.042 | 0.033 | 86.1 | -
Viguz Construction Corporation (Formerly: Viguz Construction) | 8178 | L | B | MA | GE2 | Widening of Carigara Wharf |  | 2009-06-06 | 1st | VIII |  | 1.885 | 120 |  |  |  | O | 0.381 | 0.24 | 0.15 | 0.022 | 0.033 | 0.033 | 85.9 | -
Viguz Construction Corporation (Formerly: Viguz Construction) | 8178 | L | B | MA | GE1 | Const. of Bagahupi-Babatngon-Sta. Cruz-Barugo-Carigara Road, Barugo-Carigara Road Section |  | 2009-06-06 | 1st | VIII |  | 18.887 | 150 |  |  |  | O | 0.34 | 0.24 | 0.15 | 0.03 | 0.037 | 0.033 | 83 | -
Viguz Construction Corporation (Formerly: Viguz Construction) | 8178 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of Palompon-Isabel-Merida-Ormoc Road |  | 2009-05-30 | 1st | VIII |  | 12.764 | 180 |  |  |  | O | 0.341 | 0.237 | 0.105 | 0.03 | 0.033 | 0.017 | 76.3 | -
Viguz Construction Corporation (Formerly: Viguz Construction) | 8178 | L | B | MA | GE1 | Rehabilitation along Maharlika Highway (Paril Section Km 986+280) |  | 2009-03-04 | 1st | VIII |  | 7.13 | 222 |  |  |  | O | 0.343 | 0.226 | 0 | 0.03 | 0.025 | 0.05 | #VALUE! | -
Viguz Construction Corporation (Formerly: Viguz Construction) | 8178 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Secondary Rds., Jaro-Dagami-Burauen-La Paz Rd. K0952+813-K0969+460 | Dagami, Leyte | 2012-03-19 | 1st | VIII | LF | 25.9516 | 240 | 2011-12-08 | 2012-08-03 | 44.57 | O | 0.358 | 0.238 | 0.15 | 0.03 | 0.045 | 0.05 | 87.1 | -
Viking Construction & Supplies | 18129 | L | B | MA | GE2 | Rehab. of Mangitayag Flood Control along Dingris River | Piddig, Ilocos Norte | 2012-08-03 | 1st | I | LF | 13.698 | 114 | 2012-05-30 | 2012-09-20 | 9.5 | O | 0.314 | 0.235 | 0.15 | 0.02 | 0.035 | 0.033 | 78.7 | -
Viking Construction and Supplies | 18129 | L | A | MB | GE | Preventive Maintenance Based on Pavement Management System, HDM-4 Intermittent Section, Laoag-Sarrat-Piddig-Solsona Road K0498+000 to K0503-651 | Sarrat-Piddig, Ilocos Norte | 2014-10-21 | 1st & Final | I | LF | 14.0197 | 31 | 2014-02-24 | 2014-03-26 | 32.2% | C | 0.381 | 0.2 | 0.3 | - | - | - | 88.1% | 88.1% Satisfactory
Viking Construction and Supplies | 18129 | L | A | MB | GE | Replacement of Bulag Bridge 2 along Manila North Road, Bantay, Ilocos Sur, Sta.401+766.10 to Sta. 401+799.90 | Bantay, Ilocos Sur | 2014-10-23 | 1st & Final | I | LF | 5.9397 | 199 | 2014-02-19 | 2014-09-05 | 2.08% | C | 0.489 | 0.143 | 0.3 | - | - | - | 93.2% | 93.2% Very Satisfactory
Viking Construction and Supplies | 18129 | L | A | MB | GE | Replacement of Bulag Bridge 2 along Manila orth Road, Sta. 401+766.1 to Sta. 401+799.90 | Bantay, Ilocos Sur | 2014-08-06 | 1st | I | LF | 5.9397 | 199 | 2014-02-19 | 2014-09-05 | 7.71 | O | 0.33 | 0.24 | 0.15 | 0.03 | 0.045 | 0.033 | 82.8
Viking Construction and Supplies | 18129 | L | A | MB | GE1 | Prev. Maint. (Int. Sect.) Nat'l Arterial Rd., K0490+(-839)-K0490+074, Ilocos Norte-Apayao Rd. | Ilocos Norte | 2013-08-16 | Final | I | LF | 12.067 | 74 | 2013-01-24 | 2013-04-07 | 0 | C | 0.411 | 0.133 | 0.3 | - | - | - | 84.4 | 89.50% V. Satisfactory
Viking Construction and Supplies | 18129 | L | A | MB | GE1 | Prev. Maint. (Int. Sect.) Nat'l Arterial Rd., K0490+(-839)-K0490+074, Ilocos Norte-Apayao Rd. | Ilocos Norte | 2013-03-22 | 1st | I | LF | 12.067 | 74 | 2013-01-24 | 2013-04-07 | 33.03 | O | 0.363 | 0.297 | 0.15 | 0.03 | 0.039 | 0.05 | 92.9 | -
Viking Construction and Supplies | 18129 | L | A | MB | GE | Rehab./Improvement of Manila North Road, K0412+000 - K0416+000 with exception | Sto. Domingo, Ilocos Sur | 2014-08-07 | Final | I | LF | 32.3067 | 209 | 2013-02-14 | 2013-09-10 | 0.56 | C | 0.462 | 0.133 | 0.3 |  |  |  | 89.5 | 86.98% Satisfactory
Viking Construction and Supplies | 18129 | L | A | MB | GE1 | Rehab./Impv't. of MNR, K0412+000-K0416+000 w/ exceptions | Sto. Domingo, Ilocos Sur | 2013-08-13 | 2nd | I | LF | 32.307 | 209 | 2013-02-14 | 2013-09-10 | 7.81 | O | 0.326 | 0.264 | 0.15 | 0.03 | 0.047 | 0.033 | 85
Viking Construction and Supplies | 18129 | L | A | MB | GE1 | Rehab./Impv't of MNR, K0412+000-K0416+000 w/ exceptions | Sto. Domingo, Ilocos Sur | 2013-03-20 | 1st | I | LF | 32.307 | 99 | 2013-02-14 | 2013-05-23 | -3.59 | O | 0.338 | 0.3 | 0.114 | 0.03 | 0.041 | 0.033 | 85.6 | -
Viking Construction and Supplies | 18129 | L | B | MA | GE2 | Repair/Rehab. of Cabuloan Flood Control | Bangued, Abra | 2013-03-23 | Final | CAR | LF | 13.539 | 124 | 2012-09-25 | 2013-01-26 | 25 | C | 0.035 | 0.133 | 0.3 | - | - | - | 46.8 | 67.98% Poor
Viking Construction and Supplies | 18129 | L | B | MA | GE2 | Rehab. of Mangitayag Flood Control along Dingris River | Piddig, Ilocos Norte | 2013-01-24 | Final | I | LF | 16.698 | 144 | 2012-05-30 | 2012-10-20 | 11.11 | C | 0.477 | 0.133 | 0.3 | - | - | - | 91 | 83.62% Satisfactory
Viking Construction and Supplies | 18129 | L | A | MB | GE | Construction/Widening/ Upgrading/Rehabilitation of Access Road to Declared Tourism Destinations Maoini-Baduang-Saud Road a) Sta 0+000 (Equivalent to Km. 558+500) to Sta. 5+021.90 (Section 1) b) Sta. 3+282.52 to Sta. 8+000 (with exceptions) | Pagudpud, Ilocos Norte | 2014-08-10 | Final | I | LF | 88.6092 | 240 | 2013-03-12 | 2013-11-06 | 0 | C | 0.457 | 0.133 | 0.3 |  |  |  | 89 | 88.58% Satisfactory
VIKING CONSTRUCTION AND SUPPLIES | 18129 | L | AAA | MB | GE | Concreting & Improvement of Laoag International Airport-Gabu-Fort Ilocandia Road | Laoag City, Ilocos Norte | 2015-11-11 | 1st | ILOCOS NORTE 1ST DEO | LF | 34.5418 | 184 | 2015-08-19 | 2016-02-18 | 0.3942 | OG | 0.388 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 90.8% | 90.8% Very Satisfactory
Viking Construction and Supplies/JAJR Construction (JV) | JV-13-267 | L | A | MB | GE | Preventive Maintenance along San Fernando-Bagulin Road at K0270+ (-)1016 to K0270+(-773), K0270+(-647) to K0270+000, K0270+379 to K0271+000 and K0274+416 to K0274+448 | La Union | 2014-08-09 | 1st & Final | I | LF | 25.8342 | 181 | 2014-02-12 | 2014-08-11 | 0% | C | 0.417 | 0.141 | 0.3 | - | - | - | 85.8% | 85.8% Satisfactory
Viking Construction and Supply | 18129 | L | A | MB | GE1 | Const./Widening/Upgrading/Rehab.of Acess Rds. to Declared Tourism destinations Maoini Baduang-Saud Rd., a)Sta. 0+00 equivalent to Sta. 558+000-Sta. 5+021.90 (Sect. 1) b)Sta. 3+282.52-Sta. 0+000 (w/ exceptions) | Pagudpud, Ilocos Norte | 2013-08-15 | 1st | I | LF | 88.609 | 180 | 2013-03-12 | 2013-09-07 | -4.59 | O | 0.369 | 0.3 | 0.104 | 0.03 | 0.047 | 0.033 | 88.3
Villar General Construction and Supplies | 22540 | L | D | SB | GE | Impvt./Upgrading of Flood Control & Drainage Structure along MNR, Km. 239+000 - Km. 250+500 w/ exception | La Union | 2014-08-05 | 1st & Final | I | LF | 13.5383 | 180 | 2013-03-26 | 2013-09-21 | 0.56 | C | 0.356 | 0.2 | 0.3 |  |  |  | 85.6 | 85.60% Satisfactory
Villar General Construction and Supplies | 22540 | L | D | SB | GE2 | Impvt./Upgrading of Flood Control & Drainage Structures along Manila North Rd., Km. 239+000-Km.250+500 w/ exception | Agoo, La Union | 2013-08-01 | 1st | I | LF | 13.539 | 180 | 2013-03-26 | 2013-09-21 | 23.45 | O | 0.358 | 0.3 | 0.15 | 0.03 | 0.037 | 0.033 | 90.8
VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 22540 | L | D | SB | GE | Dredging and Slope Protection of Narra-Cabaroan Creek, San Fernando City, La Union | San Fernando City, La Union | 2015-08-29 | 1st | La Union 1st DEO | LF | 13.096 | 236 | 2015-02-06 | 2015-09-30 | (+)0.87 | O | 0.334 | 0.3 | 0.15 | 0.023 | 0.042 | 0.05 | 89.9% | -
VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 22540 | L | D | SB | GE | Dredging and Slope Protection of Narra-Cabaroan Creek, San Fernando City, La Union | San Fernando City, La Union | 2015-11-09 | Final | LA UNION 1ST DEO | LF | 13.0957 | 236 | 2015-02-06 | 2015-09-29 | 0.015 | C | 0.489 | 0.133 | 0.3 | - | - | - | 92.2% | 90.46% Very Satisfactory
Villaram Builders | 21632 | L | A | MA | GE5 | Widening of Causeway, Constn. Of RoRo Ramp and RC Pier | Mansalay Port, Oriental Mindoro/Region 4B | 2016-02-12 | Final | PPA | LF | 25.707 | 324 | 2015-01-27 | 2015-12-16 | 0 | C | 0.4983 | 0.2 | 0.3 | - | - | - | 99.83 | 95.35% V. Satisfactory
VILLARAM BUILDERS | 21632 | L | A | MA | GB | Construction of Multi-Purpose Building (School Building) Doña Rosario E/S Quezon City | Quezon City | 2015-06-02 | 1st | Quezon City 1st DEO | LF | 10.543 | 210 | 2015-03-09 | 2015-10-04 | (+) 1.09 | O | 0.395 | 0.24 | 0.15 | 0.012 | 0.037 | 0.05 | 88.4% | -
Villaram Builders | 21632 | L | A | MA | GE-5 | Widening of Causeway, Constn. Of RoRo Ramp and RC Pier | Mansalay Port, Oriental Mindoro/Region 4B | 2015-11-06 | 1st | PPA | LF | 25.707 | 300 | 2015-01-27 | 2015-11-22 | -3.908 | O | 0.3675 | 0.3 | 0.1109 | 0.03 | 0.0653 | 0.05 | 92.37 | -
Vinhar Construction | [5 empty] | Construction of PICC Meeting Room 1 | PICC Complex, Pasay City | 2016-01-27 | 2nd & Final | BSP | LF | 146.363 | 357 | 2014-03-20 | 2015-06-18 | 0 | C | 0.361 | 0.2 | 0.3 | - | - | - | 86.1 | 89.90% Very Satisfactory
VINHAR CONSTRUTION AND MARKETING | 13646 |  |  |  |  | BSP Lucena Branch Building: Expansion/ Additional Building Ancillary Project | Lucena City | 2015-07-23 | 1st | BSP | LF | 137.896 | 623 | 2013-11-16 | 2015-08-01 | 0.48 | O | 0.397 | 0.269 | 0.047 | 0.03 | 0.055 | 0.033 | 83.1 | -
VINHAR CONSTRUTION AND MARKETING | 13646 |  |  |  |  | BSP Lucena Branch Building: Expansion/ Additional Building Ancillary Project | Lucena City | 2015-08-19 | Final | BSP | LF | 137.896 | 623 | 2013-11-16 | 2015-08-01 | 0.48 | C | 0.359 | 0.2 | 0.3 | - | - | - | 85.9 | 83.9% Satisfactory
Virac NRC Construction | 11396 | L | B | SB | GB | Construction of Multi Purpose Building, Isaac Lopez Integrated School | Mandaluyong City, Metro Manila | 2014-08-08 | Final | NCR | LF | 9.6586 | 120 | 2013-05-31 | 2013-09-28 | 0 | C | 0.425 | 0.133 | 0.3 |  |  |  | 85.8 | 84.33% Satisfactory
Virac NRC Construction | 11369 | L | B | SB | GB1 | Const. of MPB, Isaac Lopez Integrated Sch., Brgy. Vergasa | Mandaluyong City | 2013-08-06 | 1st | NCR | LF | 9.659 | 120 | 2013-05-31 | 2013-09-27 | 21.05 | O | 0.326 | 0.24 | 0.15 | 0.03 | 0.041 | 0.05 | 83.7
Virac NRC Construction | 11396 | L | B | SB | GE1 | Rehab./Road Opening of San Antonio St., Brgy. Cabugao | Bato, Catanduanes | 2011-08-16 | 1st | V | LF | 9.594 | 225 | 2011-03-08 | 2011-10-18 | 27.26 | O | 0.375 | 0.122 | 0.15 | 0.02 | 0.028 | 0.05 | 74.5 | -
VIRAC NRC CONSTRUCTION | 11396 | L | B | MA | GB | Construction of Multi-Purpose Building at Pedro P. Cruz Elementary School, Brgy. Barangka Drive, Mandaluyong City | Brgy. Barangka Drive, Mandaluyong City | 2015-08-27 | 1st | MM 1st DEO | LF | 18.518 | 209 | 2015-03-25 | 2015-10-19 | 7.44% | O | 0.337 | 0.238 | 0.15 | 0.03 | 0.041 | 0.05 | 84.6% | -
Virlo Construction | 5765 | L | AA | MB | GE1 | Conc. of Bacolod South Road (Su-ay Section) |  | 2009-03-06 | 2nd | VI |  | 22.306 | 319 |  |  |  | O | 0.231 | 0.3 | 0.15 | 0.03 | 0.06 | 0.05 | #VALUE! | -
Virlo Construction | 5765 | L | AA | MB | GE1 | Impv't/Conc. of JCT.LIR Carmen-Sagbayan-Bacani Road |  | 2009-03-07 | 1st | VII |  | 23.6 | 252 |  |  |  | O | 0.388 | 0.2 | 0.15 | 0.03 | 0.047 | 0.033 | #VALUE! | -
Virlo Construction | 5765 | L | AA | MB | GE1 | Conc. of Bacolod South Road (Su-ay Section) |  | 2008-11-21 | 1st | VI |  | 22.306 | 319 |  |  |  | O | 0.335 | 0.225 | 0.1 | 0.01 | 0.038 | 0.067 | 77.5 | -
VIRLO CONSTRUCTION | 5765 | L | AA | MB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads Including Drainage Based on Pavement Management System / Highway Development and Management - 4 (HDM-4) (Intermittent Sections), National Secondary Roads, Martires - Pier II Rd., Chainage 0 - Chainage 103 | Cebu City | 2015-09-03 | 1st & Final | Cebu City | LF | 5.296 | 70 | 2015-02-20 | 2015-04-30 | 18.57% | C | 0.416 | 0.133 | 0.3 | - | - | - | 84.9% | *84.9% Satisfactory
Vites Construction & Development Corporation (Formerly: Vites Trading & Const.) | 9444 |  |  |  |  | Proposed Const./Repair/Rehab. of School Bldg. Manila Science H/S |  | 2010-02-16 |  | NCR |  | 4.819 | 116 |  |  |  | O | 0.364 | 0.24 | 0.15 | 0.022 | 0.041 | 0.05 | 86.7 | -
VIVID CONSTRUCTION, INC (Formerly: Vivid Construction) | 21115 | L | B | MA | GE | Rehab/Reconst/Upgrading of Damaged Paved National Roads Including Drainage Based on Pavement Management System/Highway Development and Management-4 (HDM-4) (Intermittent Section) Spine Road, Roxas Boulevard - Jalandoni St., Pasay City Lone District | Pasay City | 2015-09-02 | 1st | SM DEO | LF | 17.442 | 150 | 2015-05-29 | 2015-10-25 | 23.17% | O | 0.372 | 0.24 | 0.15 | 0.03 | 0.06 | 0.05 | 90.2% | -
Vivid Construction, Inc. (Formerly: Vivid Construction) | 21115 | L | B | SB | GE | Slope Protection/Bank Improvement of Paranaque River Diversion Channel (Phase II), Brgy. San Dionisio | Parañaque City, M.M. | 2014-11-18 | 1st & Final | NCR | LF | 8.6687 | 159 | 2014-02-07 | 2014-07-15 | 1.67% | C | 0.357 | 0.2 | 0.3 | - | - | - | 85.7% | 85.7% Satisfactory
Vivid Construction, Inc. (Formerly: Vivid Construction) | 21115 | L | B | SB | GE | Proposed Rehabilitation/Improvement of Existing Seawall and Open Canal along Roxas Boulevard | Pasay City | 2014-11-20 | 1st & Final | NCR | LF | 7.8565 | 120 | 2014-06-18 | 2014-10-15 | 13.33% | C | 0.436 | 0.133 | 0.3 | - | - | - | 86.9% | 86.9% Satisfactory
Vivid Construction, Inc. (Formerly: Vivid Construction) | 21115 | L | B | SB | GE2 | Proposed/Repair/Rehab./Impv't. of Drainage System along Taft Ave., Baclaran (Gil Puyat Ave. to EDSA) | Pasay City | 2013-03-13 | 1st | NCR | LF | 9.594 | 289 | 2012-12-12 | 2013-09-26 | 28.76 | O | 0.386 | 0.24 | 0.15 | 0.023 | 0.03 | 0.033 | 86.2 | -
Vivid Construction, Inc. (Formerly: Vivid Construction) | 21115 | L | B | MA | GB1 | Proposed Const./Rehab. of MPB (Phase I) Brgy. 190, BAC II St. | Pasay City | 2013-03-13 | Final | NCR | LF | 4.747 | 147 | 2012-07-10 | 2012-12-03 | 2.5 | C | 0.457 | 0.185 | 0.3 | - | - | - | 94.2 | 73.55% Poor
VNKC Construction | [5 empty] | Package X-I: Construction of lateral "N" (Sta. 10+100-Sta. 11+880), sub-lat. "N-7" (Sta. 0+000-Sta. 1+600) and "N-8" (Sta. 0+000-Sta. 0+905) including related structures and supply, delivery and installation of steel gates | San Rafael, Guimba, Nueva Ecija | 2015-02-07 | 1st | NIA | L | 22.118 | 180 | 2014-07-29 | 2015-03-31 | 3.64 | O | 0.3275 | 0.2812 | 0.15 | 0.03 | 0.014 | 0.05 | 85.27 | -
VNKC Construction | 12614 | L |  | MA | GE2 | Construction of Canal Lining @ Lateral F-2a Extra, Sta. 1+740-2+040 | Sta Rosa, Nueva Ecija | 2012-07-21 | 1st | NIA | LF | 3.376 | 75 | 2012-03-12 | 2012-06-06 | 26.42 | O | 0.3688 | 0.2523 | 0.15 | 0.03 | 0.0509 | 0.05 | 90.2 | -
VORTEX CONSTRUCTION | 37715 | L | C | SB | GB | Local Infrastructure Program-Construction/Repair/Rehabilitation of Multi-Purpose Building (Municipal Hall), Sto. Tomas, Pampanga, 4th LD | Sto. Tomas, Pampanga, 4th LD | 2015-11-14 | Final | Pampanga First DEO | LF | 4.74 | 120 | 2015-07-08 | 2015-11-04 | - | C | 0.493 | 0.133 | 0.3 | - | - | - | 92.6% | 92.6% Very Satisfactory
VRF Construction | 15301 |  |  |  |  | Repair/Restoration of Washed-out Overflow Bridge & Approaches (Calaocan Brgidge) Bongabon-Rizal-Aurora Rd. |  | 2010-06-08 |  | III |  | 9.366 | 110 |  |  |  | O | 0.336 | 0.24 | 0.15 | 0.023 | 0.032 | 0.05 | 83.1 | -
VRF Construction | 15301 | L | A | MA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Road Gapan-Fort Magsaysay Road | Nueva Ecija | 2012-03-21 | 1st | III | LF | 73.156 | 210 | 2011-09-22 | 2012-04-17 | 3.75 | O | 0.277 | 0.3 | 0.15 | 0.03 | 0.056 | 0.05 | 86.3 | -
VRF Construction | 15301 | L |  | MA | GE2 | Construction of Caridad Pump Irrigation Project UPRSIIS-2011-08; Package No. II | Llanera, Nueva Ecija III | 2012-08-03 | 1st | NIA | LF | 21.39 | 90 | 2012-01-06 | 2012-04-05 | 0 | O | 0.392 | 0.2701 | 0.15 | 0.03 | 0.045 | 0.05 | 93.71 | -
VRV CONSTRUCTION AND TRADING | 34776 | L | B | MA | GB | Local Infrastructure Program - Construction of 2-storey, 6 Classroom School Building, Laiya Ibabao ES, Brgy. Laiya Ibabao, San Juan Batangas | San Juan, Batangas | 2015-11-14 | 1st | BATANGAS 4TH DEO | LF | 11.7609 | 210 | 2015-06-25 | 2016-01-20 | 0.0252 | OG | 0.363 | 0.252 | 0.15 | 0.03 | 0.07 | 0.05 | 91.5% | 91.5% Very Satisfactory
VUC Engineering | 7918 | L | A | MA | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Road Along Kalinga-Cagayan Road (Calanan-Enrile Section), K0398+366-K0499+000 & K0499+306-K0499+892 | Bulanao, Tabuk City, Kalinga | 2014-08-07 | Final | CAR | LF | 33.1968 | 381 | 2013-02-04 | 2014-02-19 | 0 | C | 0.396 | 0.133 | 0.3 |  |  |  | 82.9 | 85.84% Satisfactory
VVER Construction | 14122 |  |  |  |  | Const. of Level III Water System at Poblacion Norte Maria |  | 2010-06-07 |  | VII |  | 1.446 | 155 |  |  |  | O | 0.325 | 0.3 | 0.15 | 0.03 | 0.019 | 0.05 | 87.4 | -
VVER Construction | 14122 |  |  |  |  | Const./Completion of MPB at Poblacion |  | 2010-06-07 |  | VII |  | 1.927 | 180 |  |  |  | O | 0.296 | 0.284 | 0.15 | 0.03 | 0.04 | 0.05 | 85 | -
VVER Construction | 14122 | L | B | MA | GB1 | Const. of Multi-Purpose Building at Brgy. Poblacion |  | 2009-06-02 | 1st | VII |  | 1.924 | 150 |  |  |  | O | 0.364 | 0.241 | 0.15 | 0.03 | 0.038 | 0.05 | 87.3 | -
VVER Construction | 14122 | L | B | MA | GE1 | Repair/Rehabilitation of Punta Road, Poblacion |  | 2009-03-13 | 1st | VII |  | 1.8321 | 193 |  |  |  | O | 0.4 | 0.2 | 0.15 | 0.03 | 0.033 | 0.033 | #VALUE! | -
VVH Construction Corporation | 32689 | L | A | MA | GE | Construction/Maint of Flood Mitigation Structures and Drainage System, Repair/Rehabilitation of Abaca Flood Control | Bagui, Ilocos Norte | 2014-10-21 | 1st | I | LF | 18.0416 | 212 | 2014-02-24 | 2014-09-23 | 0% | O | 0.407 | 0.16 | 0.3 |  |  |  | 86.7% | 86.7% Satisfactory
VVH Construction Corporation | 32689 | L | A |  |  | BSP Batac Branch Various Improvement Works | BSP Batac Branch, Batac City, ilocos Norte | 2014-07-08 | 1st & Final | BSP | L | 11.325 | 75 | 2013-11-28 | 2014-02-10 | 0 | C | 0.459 | 0.2 | 0.3 | - | - | - | - | *95.90% V. Satisfactory
W B X Construction | 28370 |  |  |  |  | Rehab./Rconst./Upgrading of Damaged Paved National Road at Daang Maharlika Rd. |  | 2010-06-09 |  | III |  | 19.113 | 100 |  |  |  | O | 0.377 | 0.3 | 0.15 | 0.008 | 0.027 | 0.05 | 91.2 | -
W B X Construction | 28370 | L | B | SB | GE2 | Construction of Slope Protection along Bocaue River |  | 2009-05-29 | 1st | III |  | 9.5435 | 60 |  |  |  | O | 0.376 | 0.24 | 0.15 | 0.03 | 0.038 | 0.05 | 88.4 | -
W B X Construction | 28370 | L | B | MA | GB1 | Const. of Multi-Purpose Building at Senior Citizens Federation |  | 2009-03-06 | 1st | III |  | 0.473 | 12 |  |  |  | O | 0.368 | 0.284 | 0.15 | 0.03 | 0.02 | 0.017 | #VALUE! | -
W. D. NAVARRO CONSTRUCTION CO. | 14327 | L | A | MA | GE | Network Development-Widening of National Roads - Arterial Roads Cagayan Valley Road | K0545+714 - K0549+232 - Sta. 545+714 - Sta. 545+293, Cagayan Valley Road (CVR), Gattaran, Cagayan | 2015-06-03 | 1st | Cagayan 1st DEO | LF | 46.549 | 179 | 2015-03-24 | 2015-09-18 | 2.6% | O | 0.314 | 0.3 | 0.15 | 0.03 | 0.035 | 0.033 | 86.2% | -
W.D Navarro Construction, Co. | 14327 |  |  |  |  | New Const./Completion/Continuation On-going Maxingal Bridge along Cagayan Valley Rd. |  | 2010-05-25 |  | II |  | 16.71 | 290 |  |  |  | O | 0.372 | 0.3 | 0.15 | 0.024 | 0.033 | 0.033 | 91.2 | -
W.D Navarro Construction, Co. | 14327 |  |  |  |  | New Const./Completion/Continuation of On-going Maxingal Bridge along Cagayan Valley Road |  | 2010-08-17 |  | II |  | 16.71 | 290 |  |  |  | O | 0.342 | 0.3 | 0.042 | 0.02 | 0.004 | 0 | 70.8 | -
W.D Navarro Construction, Co. | 14327 | L | A | MA | GE1 | Upgrading/Improvement of Manila North Road (JCt. Bangag-Paraddum Section) |  | 2009-05-20 | 1st | II |  | 9.445 | 251 |  |  |  | O | 0.354 | 0.24 | 0.15 | 0.03 | 0.047 | 0.05 | 87.1 | -
W.D. Navarro Construction Co. | 14327 | L | A | MA | GE | Construciton/Widening/ Rehabilitation of Access Road at Aparri Airport | Maura, Aparri, Cagayan | 2014-08-05 | Final | II | LF | 28.8249 | 194 | 2013-01-22 | 2013-08-03 | 0 | C | 0.37 | 0.2 | 0.115 |  |  |  | 68.5 | 77.02% Unsatisfactory
W.D. Navarro Construction Co. | 14327 | L | A | MA | GE | Widening/Improvement of Dugo-San Vicente Road | Sta. Teresita, Cagayan | 2014-08-04 | Final | II | LF | 13.5608 | 136 | 2013-03-01 | 2013-07-14 | 0 | C | 0.409 | 0.2 | 0.256 |  |  |  | 86.5 | 76.18% Unsatisfactory
W.D. Navarro Construction Co. | 14327 | L | A | MA | GE1 | Const./Widening//Upgrading/Rehab. of Access Rd. at Aparri Airport, Maura | Aparri, Cagayan | 2013-07-30 | 2nd | II | LF | 27.645 | 179 | 2013-01-22 | 2013-07-19 | -1.74 | O | 0.384 | 0.2 | 0.071 | 0.03 | 0.06 | 0.05 | 79.5
W.D. Navarro Construction Co. | 14327 | L | A | MA | GE1 | Widening/Impv't. of Dugo-San Vicente Rd. | Sta. Teresita, Cagayan | 2013-07-31 | 1st | II | LF | 12.98 | 121 | 2013-03-01 | 2013-06-29 | -20 | O | 0.353 | 0.238 | 0 | 0.03 | 0.055 | 0.017 | 69.3
W.D. Navarro Construction Co. | 14327 | L | A | MA | GE1 | Const./Widening/Upgrading/Rehab. of Access Rd., Aparri-Airport, Maura | Aparri, Cagayan | 2013-03-12 | 1st | II | LF | 27.645 | 179 | 2013-01-22 | 2013-07-20 | 3.45 | O | 0.353 | 0.225 | 0.15 | 0.03 | 0.051 | 0.05 | 85.9 | -
W.D. NAVARRO CONSTRUCTION CO. | 14327 | L | A | MA | GE | Widening of National Roads - Arterial Roads Cagayan Valley Road, K0545+714 to K0549+232 = Sta. 545+714 to Sta. 545+293, Cagayan Valley Road, Gattaran, Cagayan | Gattaran, Cagayan | 2015-08-26 | 2nd | Cagayan 1st DEO | LF | 46.548 | 205 | 2015-03-24 | 2015-10-14 | 1.18% | O | 0.336 | 0.295 | 0.15 | 0.03 | 0.045 | 0.05 | 90.6% | -
W.D. NAVARRO CONSTRUCTION CO. | 14327 | L | A | MA | GE | National Road Network Services: Network Development, Widening of National Roads (Dugo - Mission Section), K0574+116 to K0574+183, K0574+213 to K0574+576, K0574+603 to K0575+474.50, K0575+519.20 to K0575+807, K0575+828 to K0576+355, K0576+376 to K0576+446, Camaranuigan, Cagayan | Camaranuigan, Cagayan | 2015-08-26 | 1st | Regional Office | LF | 53.41 | 237 | 2015-02-27 | 2015-10-21 | 7.76% | O | 0.381 | 0.238 | 0.15 | 0.03 | 0.05 | 0.05 | 89.9% | -
W.J.P. Construction & Supply | 23192 | L |  | SB | GE2 | Construction of Lateral "A" at Sta. 4+256 - Sta 4+876 of Laris | Rosales, Pangasinan Region I | 02/27-03/03/12 | 1st | NIA | FA | 11.523 | 120 | 2011-11-21 | 2012-03-18 | 6.13 | O | 0.3545 | 0.2637 | 0.15 | 0.03 | 0.0509 | 0.05 | 89.91 | -
W.T.G Construction and Development Corporation | 7494 | L | AAA | LB | GE2 | Const./Rehab. of River Control including Seawall at Tabajan |  | 2009-06-05 | 1st | VII |  | 9.363 | 300 |  |  |  | O | 0.226 | 0.3 | 0.15 | 0.03 | 0.047 | 0.033 | 78.6 | -
Wakaii Construction | 34526 | L | D | SB | GE2 | Repair/Maint. of Casili Flood Control Proj. (Casili Creek), Casili | Mallig, Isabela | 2013-03-18 | Final | II | LF | 1.493 | 60 | 2012-10-08 | 2012-12-06 | 0 | C | 0.417 | 0.133 | 0.3 | - | - | - | 85 | 85.84% Satisfactory
Waldy Construction | 32473 | L | D | SB | GE | Rehab./Recons'n/ Upgrading of Damaged Paved National Roads Including Drainage Based on Pavement Management System/Highway Development & Management-4 (HDM-4), Intermittent Sections Junction Sta. Cruz-Pinpin Road, K0334+290 to K0335+000 | Ilocos Sur | 2014-10-24 | 1st | I | LF | 1.4787 | 43 | 2014-09-17 | 2014-10-29 | 2.02% | O | 0.345 | 0.258 | 0.15 | 0.03 | 0.056 | 0.05 | 88.9% | 88.9% Satisfactory
Walter Ng Lao Construction | 23739 | L | B |  | GE2 | Balingasag River Irrigation Project | Balingasag, Misamis Oriental / Region 10 | 09/26-27/11 | 1st | NIA | LF | 199.249 | 515 | 2009-11-11 | 2011-12-31 | -43.59 | O | 0.3501 | 0.24 | 0 | 0.024 | 0.056 | 0.0167 | 68.68 | -
Walter Ng Lao Construction | 23739 | L | B | SB | GE2 | Panansalan-Cartagena Communal Irrigation System |  | 10/6-10/08 | 1st | NIA |  | 5.787 | 148 |  |  |  | O | 0.3697 | 0.16 | 0.07 | 0.015 | 0.0525 | 0.2 | 86.72 | -
Walter Ng Lao Construction | 23739 | L | B | MA | GB1 | Const. of Multi-Purpose Building (Phase II) |  | 2009-06-03 | 1st | X |  | 4.82 | 120 |  |  |  | O | 0.309 | 0.24 | 0.15 | 0.03 | 0.013 | 0.05 | 79.2 | -
Walter Ng Lao Construction | 23739 | L | B | MA | GE1 | Road Upgrading (Gravel to Paved) OroquietaCity-Calamba Mt. Road Km. 1760+400-Km. 1761+274 w/ exceptions |  | 2009-09-15 | 1st | X |  | 3.211 | 120 |  |  |  | O | 0.392 | 0.297 | 0 | 0.03 | 0.061 | 0.017 | 79.7 | -
Walter ng Lao Construction |  | L |  |  | GE2 | Balingasag River Irrigation Project | Balingasag, Misamis Oriental / Region 10 | 2012-03-31 | 2nd | NIA | LF | 14.405 | 150 | 2009-07-22 | 2012-03-22 | -4.07 | O | 0.3158 | 0.2945 | 0.1093 | 0.03 | 0.042 | 0.05 | 84.16 | -
Wangjo Construction | 29924 | L | D | SB | GE1 | Asphalt Overlay/Conc. Reblocking along Nueva Vizcaya-Ifugao-Mt. Province Bdry. Road Km. 324+000-Km.334+000 |  | 2009-05-26 | 1st | CAR |  | 9.601 | 200 |  |  |  | O | 0.372 | 0.3 | 0.15 | 0.01 | 0.04 | 0.05 | 92.2 | -
Water Dragon Construction | 33046 | L |  | SB |  | MARIIS-D1-POW#3-2014, Package 2 | Doña Paulina, San Isidro, Isabela | 2015-04-24 | 1st | NIA | L | 14.055 | 90 | 2014-04-01 | 2015-05-29 | 0.87 | O | 0.431 | 0.195 | 0.15 | 0.01 | 0.027 | 0.017 | 83 | -
Waterton Construction & Realty Development Corporation | 32492 | L | D | SB | GE | Construction of Flood Control (Cluster I) Sorsogon Second District | Sorsogon Second District | 2014-11-06 | 1st & Final | V | LF | 4.132 | 90 | 2014-04-11 | 2014-07-09 | 0% | C | 0.46 | 0.133 | 0.3 | - | - | - | 89.3% | 89.3% Very Satisfactory
Waterton Construction & Realty Development Corporation | 32492 | L | D | SB | GE | Construction of Protection Works (Cluster 1) Sorsogon | Sorsogon | 2014-08-12 | 1st & Final | V | LF | 7.3614 | 90 | 2014-04-11 | 2014-07-09 | 0 | C | 0.333 | 0.2 | 0.3 |  |  |  | 83.3 | 83.30% Satisfactory
Wawot Builders | 33592 | L | D | SB | GB | Const. of School Building (1-unit - 1-Storey 3 CL & 1 unit - 1-Storey 2 CL, San Juan Tismo NHS | Babatngon, Leyte | 2014-08-10 | 1st & Final | VIII | LF | 2.9579 | 165 | 2013-03-19 | 2013-08-30 | 0 | C | 0.491 | 0.133 | 0.3 |  |  |  | 92.4 | 92.40% Very Satisfactory
Wawot Builders | 33592 | L | D | SB | GB1 | Const. of Sch. Bldg. (1 unit - 1 storey 3CL & 1 unit - 1 storey 2 CL, Juan Tismo NHS | Babatngon, Leyte | 2013-08-30 | 1st | VIII | LF | 2.963 | 165 | 2013-03-19 | 2013-08-30 | -6 | O | 0.357 | 0.3 | 0.09 | 0.012 | 0.051 | 0.033 | 84.3
WAWOT BUILDERS | 33592 | L | D | SB | GE | Farm to Market Road, Brgy. Sangputan, Babatngon, Leyte | Brgy. Sangputan, Babatngon, Leyte | 2015-11-09 | Final | Leyte First DEO | LF | 4.9018 | 150 | 2015-01-30 | 2015-06-28 | (-)1.60% | C | 0.44 | 0.133 | 0.252 | - | - | - | 82.5% | 82.5% Satisfactory
WAYCON BUILDERS & CONSTRUCTION SUPPLY | 34778 | L | B | SB | GE | Network Development - Widening of National Roads-Arterial Roads- along National Road 1 (N1)/Daang Maharlika/Asian Highway-26, Daang Maharlika (LZ) K0143+000, K0143+332, K0143+449 | Pagbilao, Quezon | 2015-06-11 | Final | Quezon 4th DEO | LF | 5.667 | 90 | 2015-02-26 | 2015-05-27 | 33.33% | C | 0.445 | 0.132 | 0.3 | - | - | - | 87.7% | *87.7% Satisfactory
WAYCON BUILDERS & CONSTRUCTION SUPPLY | 34778 | L | B | SB | GB | Construction of Water Supply Level II with Filtration | Macalelon, Quezon | 2015-06-08 | 1st | Quezon 3rd DEO | LF | 5.642 | 160 | 2015-03-18 | 2015-08-24 | 20% | O | 0.4 | 0.229 | 0.15 | 0.022 | 0.023 | 0.033 | 85.7% | -
WBX Construction | 28370 | L | A | MA | GE | Preventive Maintenance based on Pavement Management System/HDM-4 Gen. Alejo Santos Highway Km. 50+383 to Km. 51+000 | Bustos, Bulacan | 2014-11-07 | 1st & Final | III | LF | 4.3283 | 18 | 2014-02-18 | 2014-03-07 | 0% | C | 0.458 | 0.133 | 0.3 | - | - | - | 89.1% | 89.1% Very Satisfactory
WBX Construction | 28370 | L | A | MA | GE | Construction/Rehabilitation of Pecsonville Road | San Jose del Monte City, Bulacan | 2014-09-27 | 1st & Final | Special 3 | LF | 18.5708 | 149 | 2014-02-11 | 2014-07-09 | 0 | C | 0.35 | 0.19 | 0.3 |  |  |  | 84 | 84.00% Satisfactory
WBX CONSTRUCTION, INC. | 28370 | L | A | MA | GB | Construction of Sta. Maria RHU II, Sta. Maria, Bulacan | Sta. Maria, Bulacan | 2015-06-13 | Final | Bulacan 2nd DEO | LF | 1.382 | 60 | 2014-10-03 | 2014-12-01 | 5.71% | C | 0.487 | 0.2 | 0.3 | - | - | - | 98.7% | *98.7% Outstanding
WBX CONSTRUCTION, INC. (Formerly: WBX CONSTRUCTION) | 28370 | L | A | SB | GE | Construction/Rehabilitation of Drainage Canal, Binlug-Parulan, Plaridel, Bulacan | Plaridel, Bulacan | 2015-11-20 | Final | Bulacan First DEO | LF | 9.291 | 150 | 2015-02-25 | 2015-07-24 | - | C | 0.494 | 0.133 | 0.3 | - | - | - | 92.7% | 92.7% Very Satisfactory
WCS Construction Inc. (Formerly: WCS Construction) | 6516 | L | AAA | LA | GE | Preventive Maintenance based on Pavement Management System/HDM-4 (Intermittent Section) Asphalt Overlay of | Daang Maharlika Road, K0481+000-K0481+493 | 2014-11-14 | 1st & Final | V | LF | 7.1986 | 60 | 2014-02-20 | 2014-04-20 | 0% | C | 0.469 | 0.133 | 0.3 | - | - | - | 90.2% | 90.2% Very Satisfactory
WCS Construction Inc. (Formerly: WCS Construction) | 6516 | L | AAA | MB | GE | Preventive Maintenance of Daang-Maharlika (K0608+000-K0609+103) with exception | Brgy. Bacolod, Juban, Sorsogon | 2014-11-06 | 1st & Final | V | LF | 16.2913 | 75 | 2014-01-24 | 2014-04-08 | 0% | C | 0.471 | 0.133 | 0.3 | - | - | - | 90.4% | 90.4% Very Satisfactory
WCS Construction Inc. (Formerly: WCS Construction) | 6516 | L | AAA | LA | GE | Preventive Maintenance Based on Pavement Management/HDM-4 (Intermittent Section) Asphalt Overlay of Matacon-Libon- | Polanqui Jct. Road, K0491+000-K0491+990 | 2014-11-14 | 1st & Final | V | LF | 8.6745 | 35 | 2015-02-20 | 2015-03-26 | 0% | C | 0.447 | 0.133 | 0.3 | - | - | - | 88% | 88% Satisfactory
WCS Construction Inc. (Formerly: WCS Construction) | 6516 | L | AAA | MB | GE | Construction/Rehabilitation of Flood Control System Along San Vicente River, Brgy. San Vicente, Bulan, Sorsogon | Brgy. San Vicente, Bulan, Sorsogon | 2014-11-06 | 1st & Final | V | LF | 46.3478 | 169 | 2014-04-02 | 2014-09-17 | 0% | C | 0.462 | 0.133 | 0.3 | - | - | - | 89.5% | 89.5% Very Satisfactory
WCS Construction Inc. (Formerly: WCS Construction) | 6516 | L | AAA | MB | GE | Cluster 1 - Assets Preservation of National Roads from Pavement Management System HDM-4, Intermittent Secondary Roads, Sorsogon Diversion Road, Jct. Putiao-Pilar-Donsol Road, Jct. Abuyog-Gubat-Ariman Road, 1st District of Sorsogon | 1st District of Sorsogon | 2014-11-05 | 1st & Final | V | LF | 6.0811 | 75 | 2014-01-30 | 2014-04-14 | 0% | C | 0.435 | 0.133 | 0.3 | - | - | - | 86.8% | 86.8% Satisfactory
WCS Construction Inc. (Formerly: WCS Construction) | 6516 | L | AAA | LA | GE | Preventive Maintenance Based on PMS/HDM-4 (Intermittent Section), Asphalt Overlay at Matacon-Libon-Polangui Jct. Road, K0491+000 - K0491+990 | Libon & Polangui, Albay | 2014-08-11 | 1st & Final | V | LF | 8.6745 | 35 | 2014-02-20 | 2014-03-26 | 10.8 | C | 0.434 | 0.133 | 0.3 |  |  |  | 86.7 | 86.70% Satisfactory
WCS Construction Inc. (Formerly: WCS Construction) | 6515 | L | AAA | MB | GE | Construction/Improvement of Yawa River Control, Bogtong-Rawis Section | Legazpi City | 2014-08-15 | Final | V | LF | 46.0766 | 214 | 2013-01-30 | 2013-08-31 | 0.47 | C | 0.365 | 0.2 | 0.3 |  |  |  | 86.5 | 86.26% Satisfactory
WCS Construction Inc. (Formerly: WCS Construction) | 6516 | L | AAA | MB | GE2 | Const./Impv't. of Yawa River Control, Bogtong-Rawis Sect. | Legazpi City | 2013-08-10 | 1st | V | LF | 46.077 | 214 | 2013-01-30 | 2013-08-31 | 4.51 | O | 0.332 | 0.265 | 0.15 | 0.03 | 0.051 | 0.033 | 86.1
WCS Construction Inc. (Formerly: WCS Construction) | 6516 | L | AAA | MB | GE2 | Const. of Flood Control Structure in Pob. Bacon River (Reconst. of Slope Protection at Downstream (left side) | Bacon District, Sorsogon City | 2012-11-20 | 1st | V | LF | 28.444 | 210 | 2012-06-29 | 2013-01-24 | 11.12 | O | 0.302 | 0.3 | 0.15 | 0.03 | 0.052 | 0.033 | 86.7 | -
WCS Construction, Inc. | 6516 | L | AAA | MA | GE5 | Pili Port Development Project | Brgy. Pili Bacacay, Albay | 2013-07-13 | Final | DOTC | L | 8.65 | 120 | 2013-03-27 | 2013-07-24 | 4.26 | C | 0.457 | 0.2 | 0.3 | - | - | - | 95.7 | *95.70% V. Satisfactory
WCS Construction, Inc. | 6516 | L | AAA | MA | GB1 | Ligao LTO District Office Project | Sta. Cruz, Ligao City, Albay | 2013-09-04 | 1st | DOTC | L | 12.873 | 240 | 2013-03-27 | 2013-11-21 | 2.48 | O | 0.38 | 0.3 | 0.15 | 0.02 | 0.053 | 0.05 | 95.3 | -
WCS Construction, Inc. | 6516 | L | AAA | MA | GB1 | Ligao LTO District Office Project | Sta Cruz, Ligao City, Albay | 2013-12-11 | Final | DOTC | L | 12.873 | 240 | 2013-03-27 | 2013-11-21 | 0 | C | 0.418 | 0.2 | 0.3 | - | - | - | 91.8 | 94.20% V. Satisfactory
WCS Construction, Inc. (Formerly: WCS Construction) | 6516 |  |  |  |  | Completion of Padang Bridge, Sto Domingo-Legaspi City Boundary |  | 2010-05-28 |  | V |  | 11.5 | 120 |  |  |  | O | 0.344 | 0.24 | 0.15 | 0.03 | 0.045 | 0.05 | 85.9 | -
WCS Construction, Inc. (Formerly: WCS Construction) | 6516 |  |  |  |  | Const. of Basud (Labanon Section) River Control |  | 2010-05-28 |  | V |  | 8.158 | 180 |  |  |  | O | 0.336 | 0.24 | 0.15 | 0.03 | 0.04 | 0.05 | 84.6 | -
WCS Construction, Inc. (Formerly: WCS Construction) | 6516 | L | AAA | LB | GE1 | Rehab./Impvt. of Catbalogan North Road, Km. 801+000-Km. 802+000 with exception, |  | 2009-06-05 | 1st | VIII |  | 18.696 | 120 |  |  |  | O | 0.289 | 0.24 | 0.15 | 0.03 | 0.045 | 0.033 | 78.7 | -
WCS Construction, Inc. (Formerly: WCS Construction) | 6516 | L | AA | LB | GE1 | Road Conc. of San Juanico-Basey-Sohoton Road, Km. 908+890-Km. 910+140 |  | 2009-06-04 | 2nd | VIII |  | 18.697 | 202 |  |  |  | O | 0.171 | 0.24 | 0.15 | 0.03 | 0.04 | 0.033 | 66.4 | -
WCS Construction, Inc. (Formerly: WCS Construction) | 6516 | L | AAA | LB | GE1 | Conc. of San Juanico-Basey-Sohotan Road |  | 2009-03-12 | 1st | VIII |  | 18.697 | 150 |  |  |  | O | 0.357 | 0 | 0.11 | 0.03 | 0.033 | 0.05 | #VALUE! | -
WCS Construction, Inc. (Formerly: WCS Construction) | 6516 |  |  |  |  | Repair/Rehab. of National Rd. along Wright-Taft-Borongan Rd., Km.827+252 - Km.828+512 |  | 2010-06-10 |  | VIII |  | 24.375 | 240 |  |  |  | O | 0.347 | 0.3 | 0.15 | 0.03 | 0.042 | 0.033 | 90.2 | -
WCS Construction, Inc. (Formerly: WCS Construction) | 6516 | L | AAA | LB | GE1 | Land Development of Polangui Resettlement Project |  | 7/21-25/08 | 2nd | SLB |  | 23.994 | 150 |  |  |  | O | 0.3315 | 0.2431 | 0 | 0.03 | 0.065 | 0.0333 | 70.29 | -
WCS Construction, Inc. (Formerly: WCS Construction) | 6516 | L | AAA | LB | GE1 | Construction of Comon Bridge |  | 2009-09-01 | 1st | V |  | 28.813 | 180 |  |  |  | O | 0.38 | 0.24 | 0.15 | 0.03 | 0.047 | 0.05 | 89.7 | -
WCS Construction, Inc. (Formerly: WCS Construction) | 6516 | L | AAA | LB | GE1 | Const. of Bayandong Bridge |  | 2009-09-01 | 1st | V |  | 12.466 | 233 |  |  |  | O | 0.353 | 0.24 | 0.15 | 0.03 | 0.047 | 0.05 | 87 | -
WCS Construction, Inc. (Formerly: WCS Construction) | 6516 | L | AAA | MB | GE2 | Const. of Flood Control Proj. along Cogon Gully (Upstream & Downstream), Gulang-Gulang Bridge | Irosin, Sorsogon | 2012-03-12 | 1st | V | LF | 41.95 | 180 | 2011-12-09 | 2012-06-06 | 25 | O | 0.384 | 0.232 | 0.15 | 0.03 | 0.045 | 0.033 | 87.4 | -
WCS Construction, Inc. (Formerly: WCS Construction) | 6516 | L | AAA | MB | GE2 | Channel Impvt./Widening/Diking of Talisay River & Impvt./Diking of Velasco River | Libon, Albay | 2012-03-17 | 1st | V | LF | 45.726 | 210 | 2011-10-21 | 2012-05-17 | -3.3 | O | 0.3 | 0.3 | 0.117 | 0.03 | 0.059 | 0.033 | 83.9 | -
WCS Construction, Inc. (Formerly; WCS Construction) | 6516 | L | AAA | MB | GE2 | Const. of Flood Control Structure in Pob. Bacon River (Reconst. of Slope Protection at Downstream (left side) | Bacon District, Sorsogon City | 2013-03-16 | Final | V | LF | 28.444 | 210 | 2012-06-29 | 2013-01-24 | 0 | C | 0.424 | 0.133 | 0.3 | - | - | - | 85.7 | 86.30% Satisfactory
WCS Construction, Inc. (Formerly; WCS Construction) | 6516 | L | AAA | LA | GE1 | Upgrading of Asgad Spillway along Catanduanes Circ. Rd. | San Andres, Catanduanes | 2013-03-17 | Final | V | LF | 9.604 | 275 | 2012-03-12 | 2012-12-11 | 0 | C | 0.412 | 0.133 | 0.3 | - | - | - | 84.5 | 84.86% Satisfactory
WCS Construction, Inc. / DSB Construction & Supply Inc. (JV) | JV-08-206 | L | AAA | LB | GE1 | Construction of Calbayog Bridge, Phase I, Calbayog |  | 2009-05-18 | 1st | V |  | 19.178 | 180 |  |  |  | O | 0.358 | 0.24 | 0.15 | 0.023 | 0.04 | 0.05 | 86.1 | -
WCS Construction, Inc./Makapa Corporation (JV) | 6516 | L | AAA | LB | GE1 | Construction of Breakwater |  | 2009-08-24 | 1st | V |  | 23.763 | 145 |  |  |  | O | 0.333 | 0.3 | 0.15 | 0.03 | 0.051 | 0.033 | 89.7 | -
WCS Construction, Inc./WEARR Enterprises & Development Corp. (JV) | SL1-SN-0007568 | L | A | MA | GE | Const./Improvement of Cagraray Circumferential Road and Access Road, Sta. 563+400-Sta.565+400 | Cagraray Island, Bacacay, Albay | 2014-11-07 | 1st & Final | V | LF | 70.9506 | 473 | 2014-04-22 | 2015-08-07 | 0% | C | 0.46 | 0.133 | 0.3 | - | - | - | 89.3% | 89.3% Very Satisfactory
WDM Construction & Supplies | 18877 | L | B | SB | GB1 | Const. of MPB |  | 2009-03-09 | 1st | X |  | 0.94 | 105 |  |  |  | O | 0.347 | 0.24 | 0.15 | 0.03 | 0.035 | 0.05 | #VALUE! | -
WDM Construction & Supplies/ME 3 Construction Joint Venture | JV-13-737 | L | B | MA | GE | Restoration of Mambayaan Bridge I Approach "B" and Const. of 100 lm Revetment, along BCIR, Mambayaan,Balingasag, Misamis Oriental | Balingasag, Misamis Oriental | 2014-08-11 | 1st | X | LF | 29.8709 | 169 | 2014-05-30 | 2014-11-14 | 20.06 | O | 0.378 | 0.3 | 0.15 | 0.03 | 0.05 | 0.05 | 95.8
WDM CONSTRUCTION & SUPPLIES/ME 3 CONSTRUCTION JOINT VENTURE | JV-13-737 | L | B | MA | GE | Restoration of Mamabayaan Bridge I Approach "B" and Construction of 100 l.m. Revetment along BCIR, Mambayaan, Balingasag, Misamis Oriental | Balingasag, Misamis Oriental | 2015-06-10 | Final | Regional Office X | LF | 29.871 | 169 | 2014-05-30 | 2014-11-14 | - | C | 0.459 | 0.2 | 0.3 | - | - | - | 95.9% | *95.84% Very Satisfactory
Wearr Enterprises & Development Corp. | 14123 | L | A | MA | GE | Major Repair/Maintenance of Existing Permanent Bridge, Nale Bridge along Albay West Coast Road | Libon, Albay | 2014-11-14 | 1st & Final | V | LF | 2.7414 | 135 | 2014-02-20 | 2014-07-04 | 0% | C | 0.479 | 0.133 | 0.3 | - | - | - | 91.2% | 91.2% Very Satisfactory
Wearr Enterprises & Development Corp. | 14123 | L | A | MA | GE | Major Repair/Maintenance of Existinf Permanent Bridge, Nale Bridge along Albay West Coast Road | Libon, Albay | 2014-08-11 | 1st & Final | V | LF | 2.7414 | 135 | 2014-02-09 | 2014-06-23 | 5.19 | C | 0.359 | 0.2 | 0.3 |  |  |  | 85.9 | 85.90% Satisfactory
Wearr Enterprises & Development Corp. | 14123 | L | A | MA | GE2 | Const. of Carriedo River Control w/ Floodway Clearing | Carriedo, Irosin, Sorsogon | 2013-08-14 | Final | V | LF | 18.889 | 195 | 2012-10-23 | 2013-05-05 | 1.03 | C | 0.443 | 0.133 | 0.3 | - | - | - | 87.6 | 84.90% Satisfactory
Wearr Enterprises & Development Corp. | 14123 | L | A | MA | GE2 | Const. of Carriedo River Control with Floodway Clearing | Carriedo, Irosin, Sorsogon | 2013-03-15 | 1st | V | LF | 18.889 | 195 | 2012-10-23 | 2013-05-05 | 4.26 | O | 0.356 | 0.232 | 0.15 | 0.03 | 0.03 | 0.033 | 83.1 | -
Wearr Enterprises & Development Corp. | 14123 |  |  |  |  | Cullat-Bongalon-Kidaco FMR |  | 2010-05-28 |  | V |  | 2.828 | 180 |  |  |  | O | 0.351 | 0.24 | 0.15 | 0.03 | 0.035 | 0.033 | 83.9 | -
Wearr Enterprises & Development Corp. | 14123 | L | A | SB | GB1 | Const. of 17-Units, 1-CL Modified Type School Building (7.00Mx7.00M) various Locations, Catbalogan I CES |  | 2009-06-05 | 1st | VIII |  | 0.441 | 124 |  |  |  | O | 0.336 | 0.24 | 0.15 | 0.03 | 0.035 | 0.05 | 84.1 | -
Wee Builders | 16375 | L | A | MA | GE | Construction of Local Road at Cawit-Baluno, Nangkal Road | Zamboanga CIty | 2014-10-21 | 1st & Final | IX | LF | 3.7435 | 53 | 2014-04-15 | 2014-06-06 | 0% | C | 0.389 | 0.135 | 0.3 | - | - | - | 82.4% | 82.4% Satisfactory
Wee Builders | 16375 | L | B | MA | GE1 | Concreting of Zamboanga City-Labuan-Limpapa Road (Bangayan Section) |  | 2009-05-25 | 1st | IX |  | 18.887 | 185 |  |  |  | O | 0.343 | 0.24 | 0.15 | 0.03 | 0.056 | 0.05 | 86.9 | -
Wee Builders | 16375 | L | B | MA | GE1 | Conc. of Zamboanga City-Labuan-Limpapa Road (Bangayan Section) |  | 2009-09-01 | 2nd | IX |  | 18.887 | 185 |  |  |  | O | 0.192 | 0.3 | 0.15 | 0.03 | 0.05 | 0.033 | 75.5 | -
Wee Eng Construction Inc. | 16380 | L | AAA | LB | GE1 | Const. of SCDR Marihatag-Hinatuan-Bislig Road (Marihatag-San Agustin-Lianga Sect) |  | 2008-08-30 | 1st | XIII |  | 146.935 | 480 |  |  |  | O | 0.351 | 0.3 | 0.1 | 0.03 | 0.045 | 0.1 | 92.6 | -
Wee Eng Construction Inc. | 16380 | L | AAA | LB | GE1 | Const. of SDCR (Lianga-Barobo Subsection) along Marihatag-Hinatuan-Bislig Sect |  | 2008-11-27 | 1st | XIII |  | 257.508 | 480 |  |  |  | O | 0.317 | 0.3 | 0.1 | 0.03 | 0.065 | 0.1 | 91.2 | -
Wee Eng Construction Inc. | 16380 | L | AAA | LB | GE1 | Conc. of SDCR (Lianga-Barobo Subsection) along Marihatag-Hinatuan-Bislig Sect. |  | 2009-06-04 | 2nd | XIII |  | 257.508 | 480 |  |  |  | O | 0.365 | 0.3 | 0.15 | 0.03 | 0.056 | 0.033 | 93.4 | -
Wee Eng Construction Inc. | 16380 | L | AAA | LB | GE1 | Conc. of Surigao-Davao Coastal Rd.(Lianga-Borobo Subsection)along Marihatag-Hinatuan-Bislig Sect. |  | 2009-09-09 | 3rd | XIII |  | 257.508 | 480 |  |  |  | O | 0.385 | 0.285 | 0.15 | 0.03 | 0.056 | 0.05 | 95.6 | -
Wee Eng Construction Inc. | 16380 | L | AAA | LB | GE1 | Conc. of Surigao-Davao Coastal Rd.(Marihatag-San Agustin-Lianga, Salvacion-Lianga Sect) |  | 2009-09-09 | 3rd | XIII |  | 373.799 | 405 |  |  |  | O | 0.392 | 0.3 | 0.124 | 0.03 | 0.065 | 0.033 | 94.4 | -
Wee Eng Construction Inc. | 16380 | L | AAA | LB | GE1 | Concreting of SDCR (Marihatag-San Agustin-Lianga) Salvacion-Lianga Sect. |  | 2009-06-05 | 2nd | XIII |  | 373.799 | 405 |  |  |  | O | 0.358 | 0.3 | 0.15 | 0.03 | 0.056 | 0.05 | 94.4 | -
Wee Eng Construction Inc. | 16380 | L | AAA | LB | GE1 | Concreting of Surigao-Davao Coastal Road (Marihatag-San Agustin-Lianga), Salvacion-Lianga Section Section |  | 2009-03-13 | 1st | XIII |  | 373.799 | 405 |  |  |  | O | 0.33 | 0.3 | 0.15 | 0.03 | 0.047 | 0.05 | #VALUE! | -
Wee Eng Construction Inc. | 16380 | L | AAA | LB | GE | Construction of Saug Bridge and Approaches along Provincial Road | Macgum, New Corella | 2014-10-25 | 1st | XI | LF | 72.2171 | 240 | 2014-03-12 | 2014-11-06 | -12.74% | O | 0.396 | 0.3 | 0.023 | 0.03 | 0.05 | 0.033 | 83.2% | 83.2% Satisfactory
Wee Eng Construction Inc. | 16380 | L | AAA | MB | GE | Construction/ Maintenance of Flood Mitigation Structures and Drainage System 1) Construction of Lasang River Flood Control | Lasang, 2nd LD, Davao City | 2014-10-30 | 1st & Final | XI | LF | 23.9726 | 175 | 2014-02-17 | 2014-08-10 |  | C | 0.397 | 0.2 | 0.3 | - | - | - | 89.7% | 89.7% Very Satisfactory
Wee Eng Construction Inc. | 16380 | L | AAA | LB | GE | Road Upgrading (Gravel to Concrete) along Montevista-Compostela-Mati-Boundary Road (Intermittent Sections) | Compostela Valley | 2014-08-15 | 1st | XI | LF | 103.7912 | 243 | 2014-03-10 | 2014-11-07 | 3.35 | O | 0.366 | 0.225 | 0.15 | 0.03 | 0.037 | 0.05 | 85.8
Wee Eng Construction Inc. | 16380 | L | AAA | LB | GE | Completion of On-going Bridges (Including Approaches) of Lipadas Bridge II along Davao - Cotabato Road | Davao City | 2014-08-05 | Final | XI | LF | 42.3456 | 269 | 2013-02-26 | 2013-08-23 | 0 | C | 0.421 | 0.133 | 0.3 |  |  |  | 85.4 | 88.10% Satisfactory
Wee Eng Construction, Inc. | 16380 | L | AAA | LB | GE1 | Completion of on-going Bridges (inc. Approaches) of Lipadas Bridge II along Davao-Cotabato Rd. | Davao City | 2013-08-07 | 1st | XI | LF | 42.346 | 209 | 2013-02-26 | 2013-09-22 | 0.11 | O | 0.359 | 0.294 | 0.15 | 0.03 | 0.033 | 0.033 | 89.9
Wee Eng Construction, Inc. | 16380 | L | AAA | LB | GE1 | Widening of Davao-Bukidnon Rd. | Davao City | 2013-08-19 | Final | XI | LF | 27.929 | 72 | 2013-01-23 | 2013-04-04 | 0 | C | 0.348 | 0.2 | 0.3 | - | - | - | 84.8 | 85.70% Satisfactory
Wee Eng Construction, Inc. | 16380 | L | AAA | LB | GE1 | Widening of Davao-Bukidnon Rd. | Davao City | 2013-03-22 | 1st | XI | LF | 27.911 | 72 | 2013-01-23 | 2013-04-04 | 25.57 | O | 0.293 | 0.3 | 0.15 | 0.03 | 0.04 | 0.05 | 86.3 | -
Wee Eng Construction, Inc. | 16380 | L | AAA | LB | GE1 | Conc. of Jct. Gamut-San Miguel-Bayugan Rd., Km.1315+913.714-Km.1320+200 (w/ exception) | Surigao del Sur | 2013-03-20 | Final | XIII | LF | 67.735 | 435 | 2011-09-28 | 2012-12-05 | 3.57 | C | 0.33 | 0.2 | 0.3 | - | - | - | 83 | 84.56% Satisfactory
Wee Eng Construction, Inc. | 16380 | L | AAA | LB | GE2 | Const. of Lasang River Flood Control | Lasang, Davao City | 2013-08-22 | Final | XI | LF | 65.421 | 302 | 2012-09-10 | 2013-07-08 | 0 | C | 0.4 | 0.133 | 0.3 | - | - | - | 83.3 | 83.84% Satisfactory
Wee Eng Construction, Inc. | 16380 | L | AAA | MB | GE2 | Const. of Lasang River Flood Control | Lasang, Davao City | 2012-11-28 | 1st | XI | LF | 65.422 | 260 | 2012-09-10 | 2013-05-27 | 11.24 | O | 0.327 | 0.24 | 0.15 | 0.03 | 0.045 | 0.05 | 84.2 | -
WEE ENG CONSTRUCTION, INC. | 16380 | L | AAA | LB | GE | Road Upgrading (Gravel to Concrete) Along Panabo City Coastal Road from Brgy. J.P. Laurel, Panabo City to La Paz, Carmen Leading to Migratrory Bird Sanctuary, Mangrove Sanctuary, Mariculture Park, City Baywalk, Panabo City, Davao del Norte | Panabo City, Davao del Norte | 2015-08-30 | 1st | Regional Office No. XI | LF | 133.987 | 269 | 2015-05-11 | 2016-02-03 | 25.61% | O | 0.378 | 0.217 | 0.15 | 0.03 | 0.056 | 0.05 | 88.1% | -
Wee Eng Construction, Inc./P.L Sebastian Construction (JV) | JV-06-056 | L | AAA | LB | GE1 | CP-3, Const./Impv't. of Maguindanao-Sultan Kudarat-Bdry. Lebak-Kalamansig Road |  | 2009-03-11 | 1st | XII |  | 764.659 | 670 |  |  |  | O | 0.347 | 0.3 | 0.149 | 0.03 | 0.07 | 0.033 | #VALUE! | -
Welex Construction | 9323 | L | AA |  | GB1 | Land Dev't & Housing Const. of San Lorenzo Res. Project | Sitio San Lorenzo, Brgy. Bibingcahan, Sorsogon City | 2013-05-31 | 2nd & Final | NHA | L | 25.13 | 187 | 2012-04-16 | 2013-03-25 | 0 | C | 0.493 | 0.2 | 0.3 | - | - | - | 99.3 | 89.68% V. Satisfactory
Welex Construction | 9323 | L | AA |  | GE1 | Land Dev't & Housing Const. of San Lorenzo Res. Project | Sitio San Lorenzo, Brgy. Bibingcahan, Sorsogon City | 2012-06-27 | 1st | NHA | LF | 24.925 | 120 | 2012-04-16 | 2012-08-16 | 8.34 | O | 0.359 | 0.3 | 0.066 | 0.033 | 0.045 | 0.033 | 83.6 | -
Welex Construction | 9323 | L | AAA | LB | GE1 | Land Dev't. of Taysan Resettlement Project |  | 9/16-18/08 | 2nd | SLBMO-Region V |  | 49.802 | 244 |  |  |  | O | 0.382 | 0.288 | 0 | 0.03 | 0.07 | 0.067 | 83.7 | -
Welex Construction, Incorporated (Formerly: Welex Construction) | 9323 | L | AAA | LB | GE | Construction of Flood Control System, Pawa River, Bulan, Sorsogon | Bulan, Sorsogon | 2014-11-06 | 1st & Final | V | LF | 18.7642 | 140 | 2014-02-18 | 2014-07-07 | 0% | C | 0.428 | 0.153 | 0.3 | - | - | - | 88.1% | 88.1% Satisfactory
WELEX CONSTRUCTION, INCORPORATED (Formerly: Welwx Construction) | 204 | L | AAA | LB | GE | Road Upgrading (Unpaved to Paved) based on Gravel Road Strategies, for Upgrading to Paved Road Standards (HDM-4 Project Analysis), Legazpi City - Punta de Jesus Road, K0576+620 to K0576+885, K0577+707 to K0578+426, K0578+550 to K0579+190 | Manito, Albay | 2015-06-02 | 1st | Albay 2nd | LF | 38.705 | 204 | 2015-02-09 | 2015-08-31 | 2.93% | O | 0.392 | 0.287 | 0.15 | 0.022 | 0.042 | 0.033 | 92.6% | -
Werr Corp. (International) | 14133 | L | AA | LA | GE | Replacement of Chaya Bridge (Temporary to Permanent) along Banaue-Mayoyao-Alfonso Lista-Isabela Boundary Road | Mayoyao, Ifugao | 2014-11-25 | 1st & Final | CAR | LF | 13.0847 | 249 | 2014-02-17 | 2014-10-23 | 0% | C | 0.448 | 0.133 | 0.3 | - | - | - | 88.1% | 88.1% Satisfactory
Werr Corp. (International) | 14133 | L | AA | LA | GE | Construction of River Wall along Tullahan River, Phase X | Valenzuela City | 2014-11-22 | 1st | NCR | LF | 22.45 | 150 | 2014-07-31 | 2014-12-27 | 0.85% | O | 0.271 | 0.3 | 0.15 | 0.03 | 0.045 | 0.033 | 82.9% | 82.9% Satisfactory
Werr Corp. (International) | 14133 | L | AA | LA | GE | Construction/Improvement of Flood Control and Drainage Structures San Pedro Section Puerto Princesa South Road | Puerto Princesa City | 2014-08-08 | Final | IV-B | LF | 13.9855 | 270 | 2013-04-02 | 2013-12-27 | 7.94 | C | 0.434 | 0.133 | 0.3 |  |  |  | 86.7 | 85.20% Satisfactory
Werr Corp. (International) | 14133 | L | AA | LA | GE2 | Const. Impv't. of Flood Control & Drainage Structure | Puerto Princesa City | 2013-08-16 | 1st | IVB | LF | 13.788 | 270 | 2013-04-02 | 2013-12-28 | 21.3 | O | 0.387 | 0.206 | 0.15 | 0.024 | 0.042 | 0.033 | 84.2
Werr Corp. (International) | 14133 | L | AA | LA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rd. (Int.Sect.) along Baguio-Bontoc Rd., K0269+000-K0275+000 (v.s.), K0286+000-K0289+000 (v.s.), K0299+000-K0300+900 (v.s.), K0305+000-K0308+500 (v.s.), K0309+000-K0311+000 (v.s.), K0323+000-K0328+000 (v.s.) | Benguet | 2013-08-01 | Final | CAR | LF | 94.803 | 390 | 2012-05-18 | 2013-06-11 | 0 | C | 0.437 | 0.133 | 0.3 | - | - | - | 87 | 89.40% V. Satisfactory
Werr Corp. (International) | 14133 | L | AA | LA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l. Rd. (Int. Sect.) along Baguio-Bontoc Rd., K0269+000-K0275+000 (V.S.), K0286+000-K0289+000 (V.S.), K0299+000-K0300+900 (V.S.), K0305+000-K0308+500 (V.S.), K0309+000-K0311+000 (V.S.), K0323+000-K0328+000 (V.S.) | Baguio City | 2013-03-15 | 1st | CAR | LF | 11.422 | 390 | 2012-05-18 | 2013-06-11 | 1.57 | O | 0.336 | 0.3 | 0.15 | 0.03 | 0.061 | 0.033 | 91 | -
Werr Corp. (International) | 14133 | L | AA | LA | GE1 | Replacement of Pangi Bridge 1 along Dinagat-Loreto Rd. | Dinagat Islands | 2013-03-13 | Final | XIII | LF | 9.976 | 257 | 2012-03-15 | 2012-11-26 | -2.6 | C | 0.481 | 0.191 | 0.222 | - | - | - | 89.4 | 87.12% Satisfactory
Werr Corp. (International) | 14133 | L | AA | LA | GE1 | Replacement of Bayantian Bridge along Jct. Magsaysay-Cagdianao Rd. | Dinagat Islands | 2013-03-13 | 1st | XIII | LF | 6.937 | 214 | 2012-03-15 | 2012-10-15 | - | O | 0.366 | 0.3 | 0 | 0.015 | 0.005 | 0 | 68.6 | -
WERR CORP. (INTERNATIONAL) | 11153 | L | AAA | LA | GE | Replacement of Daniel Bridge Along Dinagat-Loreto Road | Tubajon, Dinagat Islands | 2015-08-31 | 1st | Dinagat Island | LF | 19.094 | 222 | 2015-01-01 | 2015-08-10 | (-) 3.28% | O | 0.362 | 0.225 | 0.117 | 0.03 | 0.055 | 0.033 | 82.2% | -
Werr Corp. (International) / Alfalfa Construction (JV) | JV-12-375 | L | AA | LA | GE1 | Const. of Guihob Bridge & Approaches, Phase II, K0345+169-K0345+240 | Banaue, Ifugao | 2013-08-04 | Final | CAR | LF | 16.343 | 165 | 2012-12-26 | 2013-06-08 | 0 | C | 0.47 | 0.133 | 0.3 | - | - | - | 90.3 | 86.82% Satisfactory
Werr Corp. (International) / Alfalfa Construction (JV) | JV-12-375 | L | AA | LA | GE1 | Const. of Guihob Bridge & Approaches (Phase II), Sta.345+169-Sta.345+240 | Banaue, Ifugao | 2013-03-18 | 1st | CAR | LF | 16.344 | 135 | 2012-12-26 | 2013-05-09 | 0.77 | O | 0.332 | 0.24 | 0.15 | 0.023 | 0.05 | 0.05 | 84.5 | -
Werr Corp. (International) / Avatar Construction Company (JV) | JV-11-201 | L | AA | LA | GE1 | Conc. of Dinagat-Loreto Road (Dinagat-San Jose Sect.) | San Jose, Dinagat Islands | 2012-08-09 | 2nd | XIII | LF | 42 | 315 | 2012-02-28 | 2013-01-07 | 9.5 | O | 0.376 | 0.24 | 0.15 | 0.03 | 0.055 | 0.033 | 88.4 | -
Werr Corp. (International) / K.D.C.M. Construction (JV) | JV-08-141 | L | A | MB | GE1 | Conc. of Bontoc-Tabuk-Tuguegarao Road (Package BLT-16), Tinglayan Boundary-Lubuagan-Tabuk Section II, Km. 483+500- Km 499+310 Balani-Tulyao Section |  | 2009-09-04 | 1st | CAR |  | 93.305 | 310 |  |  |  | O | 0.347 | 0.24 | 0.15 | 0.03 | 0.06 | 0.033 | 86 | -
WERR Corp. (International) /Bugani Construction and Enterprises, Inc. / Jovic Construction and Supply (JV) | JV-13-553 | L | AA | LA | GE | Road Upgrading (Gravel to Paved) along Banaue-Hungduan-Benguet Bdry Road KO370+123 - KO374+000 | Ifugao | 2014-11-24 | 1st | CAR | LF | 111.4223 | 315 | 2014-06-11 | 2015-04-21 | 1.76% | O | 0.355 | 0.254 | 0.15 | 0.03 | 0.055 | 0.05 | 89.4% | 89.4% Very Satisfactory
Werr Corp. (International)/Avatar Construction Company Joint Venture | JV-11-201 | L | AA | LA | GE1 | Conc. of Dinagat-Loreto Road (Dinagat-San Jose Sect.), San Jose | Province of Diangat Islands | 2012-03-21 | 1st | XIII | LF | 42.0008 | 315 | 2012-02-28 | 2013-01-07 | 2.1 | O | 0.4 | 0.3 | 0.15 | 0.022 | 0.033 | 0.033 | 93.8 | -
WERR CORP. (INTERNATIONAL)/BRE CONSTRUCTION JV | JV-12-777 | L | AA | LA | GE | Road Upgrading of Junction National Highway Cotabato-Allah-Marbel Road (Dimapatoy-Kusiong-Tapian) Provincial Road, Maguindanao | K1851+060-K1857+754, Datu Odin sinsuat, Maguindanao | 2015-11-08 | Final | Regional Office No. XII | LF | 104.115 | 360 | 2013-08-15 | 2014-08-09 | 0% | C | 0.437 | 0.133 | 0.3 | - | - | - | 87% | *87% Satisfactory
WERR Corp. (International)/Galeno Construction, Inc. Joint Venture | JV-12-499 | L | AA | LA | GE | Reconst./Replacement of Sum-ag Bridge 1 along Bacolod South Road, Brgy. Sum-ag Bacolod City | Bacolod City, Negros Occidental | 2014-08-11 | Final | VI | LF | 36.6928 | 252 | 2013-04-01 | 2013-10-10 | 0 | C | 0.299 | 0.2 | 0.3 |  |  |  | 79.9 | 83.92% Satisfactory
Werr Corp. International / Alfalfa Construction (JV) | JV-12-314 | L | AA | LA | GE1 | Rd. Upgrading (Gravel to Conc.) of Banaue-Hungduan-Benguet Bdry. Rd. K0374+000-K0376+300 | Hungduan, Ifugao | 2013-08-04 | 1st | CAR | LF | 43.787 | 296 | 2013-01-31 | 2013-11-22 | 17.67 | O | 0.328 | 0.24 | 0.15 | 0.023 | 0.055 | 0.05 | 84.6
Werr Corp.. (International) / Galeno Construction, Inc. (JV) | JV-12-499 | L | AA | LA | GE1 | Reconst./Replacement of Sum-ag Bridge 1 along Bacolod South Rd., Brgy. Sum-ag | Bacolod City, Negros Occidental | 2013-08-07 | 1st | VI | LF | 34.401 | 252 | 2013-04-01 | 2013-12-08 | 4.97 | O | 0.376 | 0.24 | 0.15 | 0.03 | 0.037 | 0.033 | 86.6
WERR Corporation International | 14133 | L | AA | LA | GE-1 | Polambato Port Development Project | Bogo City, Cebu | 2015-09-23 | 1st & Final | DOTC | LF | 27.875 | 180 | 2014-02-27 | 2014-08-25 | 0 | C | 0.4815 | 0.2 | 0 | - | - | - | 68.15 | *68.15% POOR
WERR Corporation International | 14133 | L | AA | SB |  | Dumangas Port Development Project | Dumangas, iloilo | 2015-01-28 | 2nd & Final | DOTC | L | 39.962 | 270 | 2014-03-13 | 2014-12-07 | 0 | C | 0.355 | 0.2 | 0.3 | - | - | - | - | 88.70% Satisfactory
WERR Corporation International | 14133 | L | AA | SB |  | Dumangas Port Development Project | Dumangas, Iloilo | 2014-06-05 | 1st | DOTC | LF | 39.962 | 270 | 2014-03-12 | 2014-12-06 | 3.07 | O | 0.328 | 0.3 | 0.15 | 0.03 | 0.05 | 0.05 | 90.8 | -
WERR CORPORATION INTERNATIONAL | 14133 | L |  |  |  | Construction of Baywalk and Events Center | San Fernando City, La Union | 2015-11-25 | 1st | BCDA | LF | 57.446 | 180 | 2015-07-02 | 2015-12-28 | 7.1 | O | 0.338 | 0.294 | 0.079 | 0.03 | 0.059 | 0.05 | 85 | -
WERR CORPORATION INTERNATIONAL | 14133 | L |  |  |  | Construction of Baywalk and Events Center | San Fernando City, La Union | 2016-01-26 | 2nd | BCDA | LF | 57.446 | 180 | 2015-07-02 | 2016-02-11 | 4.88 | O | 0.306 | 0.3 | 0.101 | 0.03 | 0.07 | 0.05 | 85.7 | -
WERR CORPORATION INTERNATIONAL/ HORAMABI BUILDERS (JV) | JV-13-799 | L | AA | LA | GE | Road Upgrading (Unpaved to Paved) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standard (HDM-4 Project Analysis) (Intermittent Sections), National Secondary Roads, Bagac - Mariveles Road, Bataan | Bataan | 2015-06-04 | 1st | Regional Office No. III | LF | 104.044 | 378 | 2014-07-25 | 2015-08-06 | -14.88% | O | 0.386 | 0.3 | 0.002 | 0.023 | 0.045 | 0.05 | 80.6% | -
WESTMIN ENTERPRISES AND CONSTRUCTION SERVICES | 20989 | L | A | MA | GE | Road Upgrading (Paved to Unpaved) Based on Gravel Road Strategies Traffic Benchmark for Upgrading to Paved Road Standard HDM-4 (Project Analysis) (Intermittent Section), Rizal-Dap-Dakak-Dapitan Coastal Loop Road, Concreting, K1801+(989) - K1803+048, K1852+(193) - K1852+264 | Zamboanga del Norte | 2015-08-28 | 1st | Zamboanga del Norte 3rd | LF | 26.823 | 155 | 2015-04-06 | 2015-09-07 | (+)0.69% | O | 0.359 | 0.2815 | 0.15 | 0.03 | 0.056 | 0.05 | 92.65% | -
Westmin Enterprises & Construction Services | 20989 |  |  |  |  | Completion of Multi-Purpose Building |  | 2010-03-09 |  | IX |  | 3.795 | 150 |  |  |  | O | 0.327 | 0.3 | 0.15 | 0.03 | 0.041 | 0.05 | 89.8 | -
Westmin Enterprises & Construction Services | 20989 | L | B | SB | GE2 | Construction of Drainage Canal at Brgy. Dawo |  | 2009-06-09 | 1st | IX |  | 4.77 | 180 |  |  |  | O | 0.347 | 0.24 | 0.15 | 0.03 | 0.037 | 0.05 | 85.4 | -
Westmin Enterprises and Construction Services | 20989 | L | B | SB | GE | Road Upgrading (Gravel to Concrete) Based on Gravel Road Strategies (HDM-4) Project Analysis Intermittent Sections, Dipolog-Punta-Dansullan-Sergio Osmeña, Zamboanga del Norte/Sur Boundary K1889+246 - K1889+588 | Sergio Osmeña, Zamboanga del Norte | 2014-08-14 | 1st & Final | IX | LF | 9.43 | 89 | 2014-02-03 | 2014-05-02 | 0 | C | 0.392 | 0.2 | 0.3 |  |  |  | 89.2 | 89.20% Very Satisfactory
WESTMIN ENTERPRISES AND CONSTRUCTION SERVICES | 20989 | L | A | SB | GB | Construction of Multi-Purpose Building Covered Area, Barangay Opao, Dapitan City, Zamboanga del Norte | Dapitan City, Zamboanga del Norte | 2015-06-05 | Final | Zamboanga del Norte 3rd DEO | LF | 1.911 | 58 | 2014-06-06 | 2014-08-02 | 2.5% | C | 0.487 | 0.133 | 0.3 | - | - | - | 92% | *92% Very Satisfactory
WESTMIN ENTERPRISES AND CONSTRUCTION SERVICES | 20989 | L | A | MA | GE | Road Upgrading (Unpaved to Paved) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standards (HDM-4 Project Analysis) (Intermittent Sections) Rizal-Dakak-Dapitan Coastal Loop Road, Concreting, K1852+193 - K1852+264, K1801+989 - K1803+048, Zamboanga del Norte | Zamboanga del Norte | 2015-11-14 | Final | Zamboanga Del Norte 3rd DEO | LF | 26.8234 | 125 | 2015-04-06 | 2015-08-08 | - | C | 0.451 | 0.2 | 0.3 | - | - | - | 95.1% | 93.63% Very Satisfactory
WG & J CONSTRUCTION | 26257 | L | B | SB | GE | Concreting of Local Roads, Brgy. San Isidro, City of Santiago, Isabela | Santiago City, Isabela | 2015-11-17 | Final | ISABELA 4TH DEO | LF | 1.8236 | 90 | 2015-06-17 | 2015-09-14 | - | C | 0.45 | 0.16 | 0.3 | - | - | - | 91% | 91% Very Satisfactory
Wilkinson Construction | 21422 | L | A | SB | GE | Construction/Rehabilitation of Drainage/Slope Protection along Bacolod San Carlos Road (Pagla-Um Village) | Bacolod City | 2014-10-27 | 1st & Final | VI | LF | 17.5133 | 240 | 2014-02-13 | 2014-10-10 | 16.67% | C | 0.417 | 0.133 | 0.3 | - | - | - | 85% | 85% Satisfactory
Wilkinson Construction | 21422 | L | A | MA | GE | Rehab./Reconst./Upgrading of Damaged Paved National Secondary Road along Bacolod Circumferencial Roads K003+700 - K004+851 | Bacolod City, Negros Occidental | 2014-08-11 | Final | VI | LF | 27.7719 | 255 | 2013-04-01 | 2013-12-11 | 0 | C | 0.387 | 0.2 | 0.3 |  |  |  | 88.7 | 86.60% Satisfactory
Wilkinson Construction | 21422 | L | A | MA | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Sec. Rd. along Bacolod Circ. Rd. (S), K003+700-K004+851 | Bacolod City, Negros Occidental | 2013-08-06 | 1st | VI | LF | 26.955 | 204 | 2013-04-01 | 2013-10-21 | -9.99 | O | 0.377 | 0.3 | 0.05 | 0.03 | 0.045 | 0.05 | 85.2
Wilkinson Construction | 21422 | L | A | MA | GE1 | Rehab. of Magbaboy Bridge along Bacolod North Rd. | San Carlos City, Negros Occidental | 2013-08-12 | Final | VI | LF | 14.033 | 330 | 2012-03-07 | 2013-01-30 | 0 | C | 0.482 | 0.2 | 0.3 | - | - | - | 98.2 | 88.69% Satisfactory
Wilkinson Construction | 21422 | L | A | MA | GE1 | Rehab. of Magbaboy Bridge along Bacolod North Rd. | San Carlos City, Negros Occidental | 2013-03-15 | 2nd | VI | LF | 14.033 | 255 | 2012-03-07 | 2012-11-17 | - | O | 0.321 | 0.3 | 0 | 0.023 | 0.04 | 0.033 | 71.7 | -
Wilkinson Construction | 21422 | L | A | MA | GE1 | Rehab. of Magbaboy Bridge along Bacolod North Rd. | San Carlos City, Negros Occidental | 2012-11-27 | 1st | VI | LF | 14.033 | 225 | 2012-03-07 | 2012-10-17 | 0.97 | O | 0.4 | 0.24 | 0.15 | 0.03 | 0.06 | 0.05 | 93 | -
Wilkinson Construction | 21422 | L | A | MA | GE1 | Rehab.n/Strengthening (Reconst.) of Bridges at Poncian Bridge along Bacolod-Murcia-DS Benedicto-San Carlos City Rd. | Murcia, Negros Occidental | 2013-08-12 | 3rd | VI | LF | 25.631 | 343 | 2012-03-07 | 2013-02-13 | - | O | 0.376 | 0.3 | 0 | 0.03 | 0.04 | 0.033 | 77.9
Wilkinson Construction | 21422 | L | A | MA | GE1 | Rehab./Strengthening (Reconst.) of Bridges at Poncian Bridge along Bacolod-Murcia-D.S. Benedicto-San Carlos City Rd. | Murcia, Negros Occidental | 2013-03-15 | 2nd | VI | LF | 26.631 | 340 | 2012-03-07 | 2013-02-10 | - | O | 0.27 | 0.3 | 0 | 0.022 | 0.035 | 0.033 | 66 | -
Wilkinson Construction | 21422 | L | A | MA | GE1 | Rehab./Strengthening (Reconst.) of Bridges at Poncian Bridge along Bacolod-Murcia-D.S. Benedicto-San Carlos City Rd. | Murcia, Negros Occidental | 2012-11-27 | 1st | VI | LF | 25.631 | 280 | 2012-03-07 | 2012-12-11 | 2.83 | O | 0.321 | 0.258 | 0.15 | 0.03 | 0.055 | 0.033 | 84.7 | -
WILKINSON CONSTRUCTION | 21422 | L | A | MA | GE | Widening of Bacolod Circumferential Road (N) | K0003+(-543)- K0004+657, Bacolod City | 2015-06-11 | 1st | Bacolod City | LF | 39.044 | 180 | 2105-03-02 | 2105-08-28 | 2.04% | O | 0.353 | 0.249 | 0.15 | 0.03 | 0.03 | 0.05 | 86.2% | -
WILKINSON CONSTRUCTION | 21422 | L | A | MA | GE | Construction/Improvement/Widening of Access Roads/Bridges along Bacolod-Murcia-Don Salvador Benedicto- San Carlos City Road, Murcia, Negros Occidental (Leading to Declared Tourist Destination at Mambukal Resort and Alindahawan Falls) | Murcia, Negros Occidental | 2015-06-12 | Final | Negros First DEO | LF | 45.503 | 245 | 2014-05-05 | 2015-01-04 | 0% | C | 0.427 | 0.133 | 0.3 | - | - | - | 86% | *86% Satisfactory
WILKINSON CONSTRUCTION | 21422 | L | A | MB | GE | Widening of Bacolod Circumferentail Road (North), K0003+(-543)-K0004+657, Bacolod City | Bacolod City | 2015-11-09 | 1st | Bacolod City DEO | LF | 39.0439 | 240 | 2015-03-02 | 2015-10-27 | (-)8.46% | OG | 0.356 | 0.3 | 0.065 | 0.03 | 0.047 | 0.033 | 83.1% | 83.1% Satisfactory
WILKINSON CONSTRUCTION | 21422 | L | A | MB | GE | Widening of Bacolod Circumferential Road (N, K0003+(-543) - K0004+657) | Bacolod City | 2015-08-28 | 1st | Bacolod City | LF | 39.044 | 210 | 2015-03-02 | 2015-09-27 | 0.32% | O | 0.371 | 0.24 | 0.15 | 0.03 | 0.045 | 0.05 | 88.6% | -
William Integrated Contractor | 7669 |  |  |  |  | Proposed Rehab./Impv't. of Baliwasan Seaside (Intermittent Sect.) |  | 2010-09-08 |  | IX |  | 9.104 | 162 |  |  |  | O | 0.335 | 0.228 | 0.15 | 0.023 | 0.035 | 0.05 | 82.1 | -
WILLIAM UY CONSTRUCTION | 6991 | L | B | MA | GE | Road Upgrading (Gravel to Paved) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standard (Intermittent Section), Concreting of Lub-lub - Calao - Rosario -Cansilayan Road | Dumangas, Iloilo, K0277+935 - K0279+373.30 | 2015-09-04 | 1st & Final | Iloilo 2nd | LF | 15.423 | 71 | 2015-06-04 | 2015-08-13 | -5.28% | C | 0.458 | 0.133 | 0.3 | - | - | - | 89.1% | *89.1% Very Satisfactory
Wilper Construction / Paula Mae Buhong Construction (JV) | JV-08-196 | L | AA | LA | GE1 | Widening / Conc. of Bontoc-Banaue Road View Point to Awan-Igid Section, Km. 345+828 - Km. 354+550 |  | 2009-08-30 | 1st | CAR |  | 106.072 | 405 |  |  |  | O | 0.366 | 0.24 | 0.15 | 0.03 | 0.056 | 0.033 | 87.5 | -
Wilper Construction / Paula Mae Buhong Construction (JV) | JV-08-179 | L | AAA | LA | GE1 | Conc. of Bontoc-Tuguegarao Road, Bontoc-Tinglayan Bdry. Section I Betwangan to Ampawile Sect. Km. 406+220-Km. 411+140 (with exception) |  | 2009-08-30 | 1st | CAR |  | 130.727 | 420 |  |  |  | O | 0.384 | 0.24 | 0 | 0.03 | 0.056 | 0.017 | 72.7 | -
Wilper Construction Inc. | 1632 |  |  |  |  | Const. of San Vicente-Gutan-Lubak-Anguib Road |  | 2010-02-19 |  | II |  | 96.1 | 360 |  |  |  | O | 0.336 | 0.24 | 0.15 | 0.03 | 0.053 | 0.033 | 84.2 | -
Wilper Construction Inc. | 1632 | L | AA | LA | GE1 | Conc. of San Carlos-Dumaguete Rd., Dumaguete City and Bais City |  | 2009-09-12 | 3rd | VII |  | 47.369 | 373 |  |  |  | O | 0.366 | 0.24 | 0.15 | 0.03 | 0.037 | 0.05 | 87.3 | -
Wilper Construction Inc. | 1632 |  |  |  |  | Conc. of San Carlos-Dumaguete Road Dumaguete City and Bais City |  | 2010-03-02 |  | VII |  | 47.369 | 370 |  |  |  | O | 0.204 | 0.292 | 0 | 0.03 | 0.045 | 0.05 | 62.1 | -
Wilper Construction Inc. | 1632 | L | AA | LA | GE1 | Concreting of Guiuan Airport (Access Road) |  | 2009-06-07 | 1st | VIII |  | 12.865 | 120 |  |  |  | O | 0.296 | 0.3 | 0.15 | 0.03 | 0.045 | 0.033 | 85.4 | -
Wilper Construction Inc. | 1632 | L | AA | LA | GE1 | Concreting of San Carlos-Dumaguete Road, Dumaguete City & Bais City |  | 2009-03-12 | 1st | VII |  | 44.0007 | 310 |  |  |  | O | 0.391 | 0.221 | 0.15 | 0.03 | 0.051 | 0.033 | #VALUE! | -
Wilper Construction Inc. | 1632 | L | AA | LA | GE1 | Concreting of San Carlos-Dumaguete Road, Dumaguete City and Bais City |  | 2009-05-26 | 2nd | VII |  | 44.001 | 310 |  |  |  | O | 0.38 | 0.243 | 0.148 | 0.03 | 0.056 | 0.033 | 89 | -
Wilper Construction Inc. | 1632 | L | AA | LA | GB1 | Const. of TESDA Training Center Bldg. (Phase I) |  | 2009-05-29 | 1st | X |  | 4.741 | 120 |  |  |  | O | 0.326 | 0.265 | 0.15 | 0.03 | 0.027 | 0.033 | 83.1 | -
Wilper Construction Inc. | 1632 | L | AA | LA | GE1 | Impvt. (Concreting) of Access Road leading Dawis Port |  | 2009-05-29 | 1st | XI |  | 43.322 | 220 |  |  |  | O | 0.368 | 0.3 | 0.15 | 0.03 | 0.037 | 0.033 | 91.8 | -
Wilper Construction Inc. | 1632 | L | AA | LA | GE1 | Improvement (Concreting) of Access Road Leading to Dawis Port |  | 2009-09-05 | 2nd | XI |  | 43.322 | 220 |  |  |  | O | 0.384 | 0.24 | 0.107 | 0.03 | 0.059 | 0.033 | 85.3 | -
Wilper Construction Inc. / Wangjo Construction (JV) | JV-08-195 | L | AA | LA | GE1 | Widening / Conc. of Bontoc-Banaue Road Awan-Igid to Mt.polis Section, Km.354+550 - Km.362+200 (IS) |  | 2009-08-30 | 1st | CAR |  | 106.56 | 405 |  |  |  | O | 0.367 | 0.24 | 0.139 | 0.03 | 0.056 | 0.033 | 86.5 | -
Wilper Construction Incorporated | 1632 | L |  | MA | GE2 | Talakag Irrigation Project | Talakag, Bukidnon / Region 10 | 09/26-10/01/11 | 1st | NIA | LF | 14.432 | 451 | 2009-09-03 | 2011-08-28 | -22.71 | O | 0.3273 | 0.3 | 0 | 0.03 | 0.0509 | 0.05 | 75.82 | -
Wilper Construction Incorporated | 33066 | L | D |  | GE2 | Bukidnon Irrigation Management Office / Region 10 | Talakag, Bukidnon / Region 10 | 2012-03-31 | 2nd | NIA | LF | 14.166 | 451 | 2009-09-03 | 2011-08-28 | -3.16 | O | 0.3658 | 0.2716 | 0.1185 | 0.03 | 0.045 | 0.05 | 88.09 | -
Wilpres Enterprises | 19698 | L | D | SB | GE | Rehabilitation of Lateral Drainage along Lingayen-Capitol Loop to Lingayen Cadre Road (Phase I) K0364+(-)278 to K0364+242 & Sta. 0+000 to Sta. 0+480 | Lingayen, Pangasinan | 2014-10-28 | 1st & Final | I | LF | 7.3847 | 130 | 2014-02-14 | 2014-06-23 | 0% | C | 0.453 | 0.133 | 0.3 | - | - | - | 88.6% | 88.6% Satisfactory
Winces Construction & Supply | 32341 | L |  | D | GE2 | Rehabilitation of Barotac Viejo RIS Bench Flume | Barotac Viejo, Iloilo City | 2013-08-31 | 1st & Final | NIA | L | 12.074 | 150 | 2012-04-26 | 2012-11-28 | 0 | O | 0.3472 | 0.2 | 0.3 | - | - | - | 84.72 | *84.72% Satisfactory
WINLEY TAN CONSTRUCTION | 22368 | L | B | SB | GB | Construction of Multi-Purpose Building at Brgy. Lipay, Jose Dalman, Zamboanga del Norte | Jose Dalman, Zamboanga del Norte | 2015-11-16 | Final | Zamboanga Del Norte 1st DEO | LF | 1.4943 | 165 | 2015-05-22 | 2015-11-02 | 6.06% | C | 0.459 | 0.133 | 0.3 | - | - | - | 89.2% | 87.52% Satisfactory
WINLEY TAN CONSTRUCTION | 22368 | L | B | SB | GB | Construction of Multi-Purpose Building at Jose Dalman, Zamboanga del Norte | Lumping, Balatakan, Lipay, Diwait-Tabon, Labakid and Dinasan, Zamboanga del Norte | 2015-08-27 | 1st | Zamboanga del Norte 1st | LF | 7.251 | 165 | 2015-05-22 | 2015-11-02 | (+)9.24% | O | 0.35 | 0.24 | 0.15 | 0.022 | 0.056 | 0.05 | 86.8% | -
WINPRO CONSTRUCTION | 37527 | L | D | SB | GB | Construction of Multi Purpose Building (Covered Court) at Brgy. 135, Kawit/Mirasol Sts, Tondo Manila | Kawit/Mirasol Sts, Tondo Manila | 2015-12-11 | Final | North Manila DEO | LF | 3.4642 | 118 | 2015-07-03 | 2015-10-28 | 0.00% | C | 0.483 | 0.133 | 0.3 | - | - | - | 91.6% | 91.6% Very Satisfactory
Wismon Construction | 33687 |  |  |  |  | Rehab./Reconst./Upgrading of Damaged Paved National Rd. along Daang Maharlika San Luis-Isabela Bdry. Sect. w/ exception |  | 2010-06-10 |  | II |  | 19.285 | 90 |  |  |  | O | 0.369 | 0.244 | 0.15 | 0.03 | 0.047 | 0.033 | 87.3 | -
Wizard Trading and Construction | 21921 |  |  |  |  | Upgrading of Muñoz-Lupao Road |  | 2010-06-07 |  | III |  | 4.899 | 30 |  |  |  | O | 0.338 | 0.24 | 0.15 | 0.03 | 0.054 | 0.05 | 86.2 | -
Wizard Trading and Construction | 21921 | L | A | MA | GB | Construction of School Building, Malasin E/S | San Jose City, Nueva Ecija | 2014-11-21 | 1st & Final | III | LF | 4.2617 | 188 | 2014-06-02 | 2014-12-06 | 10% | C | 0.492 | 0.133 | 0.3 | - | - | - | 92.5% | 92.5% Very Satisfactory
Wizard Trading and Construction | 21921 | L | A | MB | GE | Preventive Maintenance of San Jose City-Rizal Road via Pinili Porais Villa Joson, KO175+870 to KO176+300 | Nueva Ecija | 2014-11-21 | 1st & Final | III | LF | 5.8214 | 74 | 2014-04-28 | 2014-07-10 | 0% | C | 0.458 | 0.133 | 0.3 | - | - | - | 89.1% | 89.1% Very Satisfactory
Wizard Trading and Construction | 21921 | L | A | MB | GE | Preventive Maintenance of San Jose City-Rizal Road via Pinili-Porais-Villa Joson, KO 175+870 to KO 176+300 | Nueva Ecija | 2014-09-25 | 1st & Final | Special 3 | LF | 5.826 | 75 | 2014-04-28 | 2014-07-11 | 16 | C | 0.468 | 0.133 | 0.3 |  |  |  | 90.1 | 90.10% Very Satisfactory
Wizard Trading and Construction | 21921 | L | A | MB | GE1 | Rehab./Reconst./Upgrading of Damaged Paved Nat'l Rds, Daang Maharlika Rd. | Nueva Ecija | 2013-08-09 | Final | III | LF | 77.161 | 315 | 2012-06-01 | 2013-04-11 | 0 | C | 0.461 | 0.133 | 0.3 | - | - | - | 89.4 | 88.86% Satisfactory
WJ BUILDERS | 34436 | L | D | SB | GE | Construction and Maintenance of Bridges along National Roads, Rehabilitation/Major Repair of Permanenet Bridges Balocawe Bridge, Daang Maharlika, Leyte | Daang Maharlika, Leyte | 2015-06-09 | 1st | Leyte Second DEO | LF | 2.909 | 202 | 2015-02-20 | 2015-09-09 | - | O | 0.35 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 87% | -
WJ BUILDERS | 34436 | L | D | SB | GE | Rehabilitation/Major Repair of Permanent Bridges, Mapatong Bridges (BOO553LT) along Daang Maharlika, Maharlika (LT), Mahaplag, Leyte | Maharlika (LT), Mahaplag, Leyte | 2015-08-29 | 1st & Final | Leyte 5th DEO | LF | 5.585 | 150 | 2015-03-16 | 2015-08-12 | - | C | 0.472 | 0.133 | 0.3 | - | - | - | 90.5% | *90.5% Very Satisfactory
WMLC Trading & Construction Supply | 24535 |  |  |  |  | Rehab./Reconst./Upgrading of Damaged Roads along Rosario-San Juan Rd. |  | 2010-06-07 |  | IVA |  | 4.82 | 90 |  |  |  | O | 0.4 | 0.225 | 0.15 | 0.023 | 0.04 | 0.05 | 88.8 | -
WOODLAND CONSTRUCTION & SUPPLY, INC. (Formerly: Woodland Construction & Supply) | 33522 | L | C | SB | GB | Construction of Level III Spring Source, Brgy. Lipata | Sitio Nagpana, Barotac Viejo, Iloilo | 2015-08-29 | 1st & Final | Iloilo 3rd | LF | 4.94 | 120 | 2015-04-15 | 2015-08-12 | 4.17% | C | 0.45 | 0.133 | 0.3 | - | - | - | 88.3% | *88.3% Satisfactory
WOODLAND CONSTRUCTION & SUPPLY INC. (Formerly: Woodland Construction & Supply) | 33522 | L | C | SB | GE | Construction of Level III Spring Source | Barangay Lipata, Sitio Nagpana, Barotac Viejo, Iloilo | 2015-06-09 | 1st | Iloilo Third DEO | LF | 4.94 | 120 | 2015-04-15 | 2015-08-12 | 25.07% | O | 0.396 | 0.235 | 0.15 | 0.022 | 0.03 | 0.033 | 86.6% | -
Worldwide Builders | 31408 | L | D | SB | GE | Preventive Maintenance Based on Pavement Management System/Highway Development and Management-4 (HDM-4), Secondary Road, General Maxilom Ext., Chainage 0000 - Chainage 0340 | Cebu City | 2014-10-20 | 1st & Final | VII | LF | 12.0739 | 60 | 2014-02-14 | 2014-04-14 | 10% | C | 0.458 | 0.137 | 0.3 | - | - | - | 89.5% | 89.5% Very Satisfactory
Worldwide Builders | 31408 | L | D | SB | GB1 | Improvement of Multi-Purpose Building |  | 2009-03-03 | 1st | VII |  | 0.948 | 50 |  |  |  | O | 0.342 | 0.277 | 0.15 | 0.03 | 0.019 | 0.05 | #VALUE! | -
WORLDWIDE BUILDERS | 31408 | L | B | SB | GB | Construction of Multi-Purpose Building, Brgy Bunlan, Santander, Cebu | Brgy Bunlan, Santander, Cebu | 2015-11-11 | Final | Cebu 4th | LF | 2.9382 | 90 | 2015-02-24 | 2015-05-24 | 0 | C | 0.488 | 0.133 | 0.3 | - | - | - | 92.1% | 92.1% Very Satisfactory
WSR ENTERPRISES | 17589 | 0 | 0 | 0 | 0 | Construction/Rehabilitation/Improvement of Calabanga Flood Control, Brgy. San Antonio-Quipayo, Calabanga, Camarines Sur | Brgy. San Antonio-Quipayo, Calabanga, Camarines Sur | 2015-11-14 | Final | Camarines Sur Second DEO | LF | 4.54 | 102 | 2015-02-08 | 2015-05-21 | - | C | 0.435 | 0.122 | 0.3 | - | - | - | 85.7% | 85.7% Satisfactory
WT Construction Inc., "JV" A.M. Oreta and Company, Inc. | JV-12-229 | L | AAA | LB | GE | Improvement of Natalio Bacalso Avenue Km. 47+000 to Km. 48+297, Carcar-Sibonga, Cebu Province | Cebu | 2014-08-04 | Final | VII | LF | 17.8697 | 360 | 2013-02-13 | 2014-02-08 | 0 | C | 0.338 | 0.2 | 0.3 |  |  |  | 83.8 | 84.70% Satisfactory
WT Construction, Inc. | 5490 | L | AAA | LB | GE | Preventive Maintenance Based on Pavement Management System/Highway Development and Management-4 (HDM-4) Secondary Road, Osmeña Boulevard, Chainage 0225 - Chainage 1313 | Cebu City | 2014-10-20 | 1st & Final | VII | LF | 27.9886 | 150 | 2014-03-20 | 2014-08-16 | 0% | C | 0.433 | 0.149 | 0.3 | - | - | - | 88.2% | 88.2% Satisfactory
WT Construction, Inc. / A.M. Oreta & Company, Inc. (JV) | JV-12-230 | L | AAA | LB | GE1 | Widening of San Isidro Bridge & Approaches, Sta.27+100 inc. the Impv't. of Cross-Drainage from Sta.27+083-Sta.28+470 along Natalio Bacalso Ave. | Cebu | 2013-08-05 | 1st | VII | LF | 25.878 | 378 | 2013-02-13 | 2014-02-25 | 5.35 | O | 0.339 | 0.281 | 0.15 | 0.03 | 0.045 | 0.033 | 87.8
WT Construction, Inc. / A.M. Oreta & Company, Inc. (JV) | JV-12-229 | L | AAA | LB | GE1 | Impv't. of Natalio Bacalso Ave., Carcar-Sibonga Sect., Cebu Province, Km.47+000-K0048+297 | Cebu | 2013-08-05 | 1st | VII | LF | 16.248 | 360 | 2013-02-13 | 2014-02-07 | 44.49 | O | 0.274 | 0.3 | 0.15 | 0.03 | 0.049 | 0.05 | 85.3
WTG Construction & Development Corp | 7494 | L | AAA |  | GE5 | Rehabilitation of R.C. Pier 1 | Dumaguete City / Region VII | 2014-04-03 | 3rd & Final | PPA | LF | 74.084 | 456 | 2012-10-08 | 2014-01-06 | 0 | C | 0.451 | 0.2 | 0.3 | - | - | - | 95.1 | 96.35% Outstanding
WTG Construction & Development Corp | 7494 | L | AAA |  | GE-5 | Expansion of Back-Up Area and Construction of PTB | Port of Talibon, Bohol | 2015-08-05 | 2nd | PPA | LF | 59.89 | 429 | 2014-04-09 | 2015-10-03 | -5.989 | O | 0.3994 | 0.3 | 0.09011 | 0.03 | 0.07 | 0.05 | 93.951 | -
WTG Construction and Development Corp. (Formerly: W.T.G. Construction) | 7494 | L | AAA | LB | GE1 | Retrofitting of Ilog Bridge | Kabankalan, Negros Occidental | 2012-03-29 | 1st | VI | LF | 56.181 | 300 | 2011-11-14 | 2012-09-07 | 16.76 | O | 0.32 | 0.24 | 0.15 | 0.03 | 0.06 | 0.05 | 85 | -
WTG Construction and Development Corporation (Formerly: W.T.G Construction) | 7494 |  |  |  |  | Reconst. of Third Concrete Bridge along Marikina-Infanta Rd. (Marcos Highway) Km.35+861 Brgy. San Jose |  | 2010-06-08 |  | IVA |  | 56.621 | 180 |  |  |  | O | 0.362 | 0.3 | 0.15 | 0.03 | 0.047 | 0.05 | 93.9 | -
WTG Construction and Development Corporation (Formerly: W.T.G Construction) | 7494 | L | AAA | LB | GE1 | Rehab./Recons./Upgrading of Dumaguete North Rd. (Jct. Kabankalan, Negros Occ. Boundary) Sta.39+000-Sta.42+000;Sta.47+180-Sta47+280;Canlargo-Talongon-Bais City Rd. Sec.) |  | 2009-09-16 | 1st | VII |  | 48.07 | 270 |  |  |  | O | 0.347 | 0.24 | 0.15 | 0.03 | 0.037 | 0.033 | 83.7 | -
WTG Construction and Development Corporation (Formerly: W.T.G Construction) | 7494 | L | AAA | LB | GE1 | Rehab./Reconst. of Toledo-Tabuelan-San Remegio Road, Tuburan Section |  | 2009-05-29 | 1st | VII |  | 23.119 | 120 |  |  |  | O | 0.268 | 0.24 | 0.15 | 0.03 | 0.05 | 0.033 | 77.1 | -
WTG Construction and Development Corporation (Formerly: W.T.G Construction) | 7494 | L | AAA | LB | GE1 | Impvt./Rehab./Reconst. of Toledo-Tabuelan-San Remegio Road, Km. 48+806-Km. 55+361, Brgy. Dumhog-Sto. Niño |  | 2009-05-26 | 1st | VII |  | 8.428 | 90 |  |  |  | O | 0.217 | 0.225 | 0.15 | 0.022 | 0.05 | 0.05 | 71.4 | -
WTG Construction and Development Corporation (Formerly: W.T.G Construction) | 7494 | L | AAA | LB | GE1 | Rehab./Reconst. of Toledo-Tabuelan-San Remegio Road, Km. 47+000-Km. 103+667 |  | 2009-05-27 | 1st | VII |  | 76.969 | 365 |  |  |  | O | 0.173 | 0.222 | 0.15 | 0.03 | 0.045 | 0.033 | 65.3 | -
WTG Construction and Development Corporation (Formerly: W.T.G Construction) | 7494 | L | AAA | LB | GE1 | Conc. of Jct.TER, Jagna-Sierra Bullones Rd. Km.62.5220-Km.63.365;Km.72.812-Km.75.031;Km.75.250-Km.76.526, Canijulao-Boctol-Mayana-Jagna |  | 2009-09-04 | 1st | VII |  | 87.044 | 270 |  |  |  | O | 0.368 | 0.24 | 0.15 | 0.03 | 0.037 | 0.033 | 85.8 | -
WTG Construction and Development Corporation (Formerly: W.T.G Construction) | 7494 |  |  |  |  | Conc. of Jct. TER, Jagna-Sierra Bullones Road Km. 62.522-Km. 63.365; Km.72+812-Km. 75.031 & Km. 72.25-Km. 76.526, Canjulao-Boctol-Mayana Section |  | 2010-02-23 |  | VII |  | 87.044 | 270 |  |  |  | O | 0.333 | 0.238 | 0.15 | 0.03 | 0.045 | 0.033 | 82.9 | -
WTG Construction and Development Corporation (Formerly: W.T.G Construction) | 7494 |  |  |  |  | Rehab./Reconst. of Damaged Paved National Rd. at LIPATA Surigao Del Norte Davao City Highway through Daang Maharlika Rd. (Agusan to Davao Rd.) Panacan Sect. |  | 2010-06-16 |  | XI |  | 19.289 | 115 |  |  |  | O | 0.393 | 0.24 | 0.15 | 0.03 | 0.042 | 0.05 | 90.5 | -
WTG Construction and Development Corporation (Formerly: W.T.G Construction) | 7494 | L | AAA | LB | GE1 | Const. of Gov. Cuenco Flyover, Gov. Cuenco Ave. , Jct. A.S. Fortuna St. |  | 2009-03-02 | 2nd | VII |  | 95.036 | 559 |  |  |  | O | 0.301 | 0.3 | 0.15 | 0.03 | 0.054 | 0.05 | #VALUE! | -
WTG Construction and Development Corporation (Formerly: W.T.G Construction) | 7494 | L | AAA | LB | GE1 | Rehab./Reconst. of Damaged Paved National Roads Tagbilaran East Road (TER) (Loay-Guildulman) Intermittent Secton |  | 2009-06-05 | 1st | VII |  | 9.363 | 200 |  |  |  | O | 0.299 | 0.3 | 0.15 | 0.03 | 0.051 | 0.033 | 86.3 | -
WTG Construction and Development Corporation (Formerly: W.T.G Construction) | 7494 |  |  |  |  | Rehab./Reconst./Upgrading (Concreting) of Toledo-Tabuelan-San Remegio Road, Km. 68+720-Km. 96+340 w/ exceptions |  | 2010-08-26 |  | VII |  | 40.903 | 210 |  |  |  | O | 0.311 | 0.287 | 0.15 | 0.03 | 0.04 | 0.05 | 86.8 | -
WTG Construction and Development Corporation (Formerly: W.T.G Construction) | 7494 |  |  |  |  | Rehab./Reconst./Upgrading (Conc.) of Toledo-Tabuelan-San Remegio Rd., Km.68+720 - Km.96+340 w/ exception |  | 2010-06-12 |  | VII |  | 40.903 | 210 |  |  |  | O | 0.289 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 80.9 | -
WTG Construction and Development Corporation (Formerly: W.T.G Construction) | 7494 | L | AA | LA | GE1 | Const. of Pedestrian Overpass along Davao Diversion Road (Laverna Hills Section) |  | 2009-06-11 | 1st | XI |  | 4.71 | 120 |  |  |  | O | 0.35 | 0.3 | 0.15 | 0.03 | 0.056 | 0.05 | 93.6 | -
WTG Construction and Development Corporation (Formerly: W.T.G Construction) | 7494 | L | AA | LA | GE1 | Const. of Gov. Cuenco Flyover, Gov. Cuenco Ave. , Jct. A.S. Fortuna St. |  | 2008-09-03 | 1st | VII |  | 86.914 | 300 |  |  |  | O | 0.281 | 0.22 | 0.1 | 0.03 | 0.047 | 0.1 | 77.8 | -
WTG Construction and Development Corporation (Formerly: W.T.G Construction) | 7494 | L | AAA | LB | GE1 | Dapa-Cancohoy Rd., Cancohoy-Del Carmen |  | 2009-09-03 | 1st | XIII |  | 19.249 | 240 |  |  |  | O | 0.349 | 0.289 | 0.15 | 0.03 | 0.065 | 0.05 | 93.3 | -
WTG Construction and Development Corporation (Formerly: W.T.G Construction) | 7494 | L | AAA | LB | GE1 | Jct. Canchohoy-Pilar Rd., San Isidro Rd. Sect. |  | 2009-09-03 | 1st | XIII |  | 19.269 | 240 |  |  |  | O | 0.358 | 0.291 | 0.095 | 0.03 | 0.065 | 0.033 | 87.2 | -
WTG Construction and Development Corporation (Formerly: W.T.G Construction) | 7494 | L | AAA | LB | GE | Construction/Concreting of Brgy. Road Leading to Malabago - Kalangkang - Sulsogon Kawasan Falls | Badian, Cebu | 2014-10-24 | 1st | VII | LF | 45.6777 | 196 | 2014-04-14 | 2014-10-26 | 0.68% | O | 0.309 | 0.3 | 0.15 | 0.022 | 0.065 | 0.05 | 89.6% | 89.6% Very Satisfactory
WTG Construction and Development Corporation (Formerly: W.T.G Construction) | 7494 | L | AAA | LB | GE | Construction of Drainage System along Cebu North Hagnay Wharf RoadBorbon Section | Borbon, Cebu | 2014-08-08 | 1st | VII | LF | 17.567 | 210 | 2014-01-31 | 2014-08-28 | 5.84 | O | 0.351 | 0.272 | 0.15 | 0.022 | 0.051 | 0.05 | 89.6
WTG Construction and Development Corporation (Formerly: W.T.G Construction) | 7494 | L | AAA | LB | GE | Rehabilitation/Improvement of M.L. Quezon Street, Mandaue City, K0008+(-865) to K0008+535, Mandaue City, Cebu | Mandaue City, Cebu | 2014-10-21 | 1st | VII | LF | 43.7089 | 360 | 2014-02-05 | 2015-01-30 | 2.21% | O | 0.375 | 0.24 | 0.15 | 0.024 | 0.047 | 0.033 | 86.9% | 86.9% Satisfactory
WTG Construction and Development Corporation (Formerly: W.T.G Construction) | 7494 | L | AAA | LB | GE | Rehab./Imprv't. of M.L.Quezon St., Mandaue City K0008+(-865) to K0008+535, Mandaue City | Mandaue City, Cebu | 2014-08-08 | 1st | VII | LF | 43.7089 | 360 | 2014-02-05 | 2015-01-30 | 0.83 | O | 0.357 | 0.243 | 0.15 | 0.024 | 0.061 | 0.033 | 86.8
WTG Construction and Development Corporation (Formerly: W.T.G Construction) | 7494 | L | AAA | LA | GE | Construction of Flood Control at Sapang Daku River | Toledo City, Cebu | 2014-08-06 | Final | VII | LF | 28.4851 | 165 | 2013-01-28 | 2013-09-24 | 0 | C | 0.386 | 0.2 | 0.3 |  |  |  | 88.6 | 89.74% Very Satisfactory
WTG Construction and Development Corporation (Formerly: W.T.G. Construction) | 7494 | L | AAA | LA | GE2 | Const. of Flood Control at Sapangdaku River | Toledo City, Cebu | 2013-08-06 | 2nd | VII | LF | 28.485 | 210 | 2013-01-28 | 2013-08-25 | 0.01 | O | 0.32 | 0.3 | 0.15 | 0.03 | 0.055 | 0.05 | 90.5
WTG Construction and Development Corporation (Formerly: W.T.G. Construction) | 7494 | L | AAA | LA | GE2 | Const. of Flood Control at Sapangdaku River | Toledo City, Cebu | 2013-03-17 | 1st | VII | LF | 28.485 | 180 | 2013-01-28 | 2013-07-26 | 13.89 | O | 0.251 | 0.3 | 0.15 | 0.03 | 0.047 | 0.05 | 82.8 | -
WTG Construction and Development Corporation (Formerly: W.T.G. Construction) | 7494 | L | AAA | LB | GE1 | Rehab./Reconst./Upgrading of Corrales Extension St. Port Rd., Km.1438+000-Km.1439+557 | Cagayan de Oro City | 2012-08-06 | 2nd | X | LF | 26.118 | 210 | 2012-01-31 | 2012-08-27 | -22 | O | 0.289 | 0.3 | 0 | 0.03 | 0.035 | 0.033 | 68.7 | -
WTG CONSTRUCTION AND DEVELOPMENT CORPORATION (Formerly: W.T.G. Construction) | 7494 | L | AAA | LB | GE | Construction/Concreting of Brgy. Road Leading to Malabago-Kalangkang-Sulogon Kawasan Falls | Badlan, Cebu | 2015-06-01 | Final | Cebu Fourth DEO | LF | 45.682 | 226 | 2015-04-14 | 2015-11-25 | 0% | C | 0.429 | 0.155 | 0.3 | - | - | - | 88.4% | *89.12% Very Satisfactory
WTG CONSTRUCTION AND DEVELOPMENT CORPORATION (Formerly: W.T.G. Construction) | JV-14-854 | L | AAA | LA | GE | Construction/Ugrading/Rehabilitation of Drainage along National | K0008+(-062) to K0009+118, Mandaue City | 2015-06-01 | 1st | Cebu Sixth DEO | LF | 44.098 | 416 | 2015-03-30 | 2016-05-18 | 9.62% | O | 0.348 | 0.237 | 0.15 | 0.03 | 0.035 | 0.033 | 83.3% | -
WTG CONSTRUCTION AND DEVELOPMENT CORPORATION (Formerly: W.T.G. Construction) | 7494 | L | AAA | LB | GE | Rehabilitation/Improvement of M.L. Quezon St., Mandaue City | K0008+(-865) to K0008+535, Mandaue City | 2015-06-01 | Final | Cebu Sixth DEO | LF | 43.709 | 360 | 2014-02-05 | 2015-01-30 | 0% | C | 0.484 | 0.141 | 0.3 | - | - | - | 92.5% | *92.5% Very Satisfactory
WTG CONSTRUCTION AND DEVELOPMENT CORPORATION (Formerly: W.T.G. Construction) | 7494 | L | AAA | LB | GE | Replacement of Permanent Weak Bridges at Tapon Bridge (B00579CB) along Cebu North Hagnaya Wharf Road | Danao City, Cebu | 2015-09-02 | 1st | Cebu 5th | LF | 44.556 | 330 | 2015-05-08 | 2016-04-01 | 0.06% | O | 0.32 | 0.255 | 0.15 | 0.03 | 0.045 | 0.05 | 85% | -
WTG CONSTRUCTION AND DEVELOPMENT CORPORATION (Formerly: W.T.G. Construction) | 7494 | L | AAA | LB | GE | Improvement/ Rehabilitation of Naga - Uling Road, K0037+(-161) - K0042+254, Naga City & Toledo City, Cabu Province | Naga City & Toledo City, Cabu Province | 2015-11-12 | 1st | Cebu 3rd | LF | 35.2468 | 240 | 2015-03-26 | 2015-11-20 | -0.0183 | OG | 0.394 | 0.24 | 0.132 | 0.03 | 0.048 | 0.033 | 87.7% | 87.7% Satisfactory
WTG CONSTRUCTION AND DEVELOPMENT CORPORATION (Formerly: W.T.G. Construction) | 7494 | L | AAA | LB | GE | Replacement of Permanent Weak Bridges at Tapon Bridge (B00579CB) along Cebu North Hagnaya Wharf Road | Danao City, Cebu | 2015-11-14 | 1st | Cebu 5th | LF | 45.5557 | 330 | 2015-05-08 | 2016-04-01 | 0.0044 | OG | 0.394 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 91.4% | 91.4% Very Satisfactory
Wynn Construction | 19358 | L | B | SB | GE-5 | Siquijor Airport Development Project | Pasihagon, Siquijor/Region VII | 2015-09-09 | 1st & Final | DOTC | LF | 10.522 | 90 | 2015-03-11 | 2015-06-08 | 0 | C | 0.4471 | 0.2 | 0.3 | - | - | - | 94.71 | *94.71% V.Satisfactory
Wynn Construction | 19358 | L | B | LA | GE-5 | Dimiao Port Development Project | Dimiao, Bohol | 2014-09-11 | 1st & Final | DOTC | LF | 4.933 | 105 | 2014-03-16 | 2014-07-27 | 0 | C | 0.411 | 0.2 | 0.3 | - | - | - | 91.11 | *91.11% V. Satisfactory
Wynn Construction | 19358 | L | B | SB | GE5 | Bien Unido Port Development Project | Bien Unido, Bohol | 2014-01-22 | 1st & Final | DOTC | LF | 4.975 | 75 | 2013-03-13 | 2013-10-20 | 0 | C | 0.4464 | 0.2 | 0.3 | - | - | - | 94.64 | *94.64% Very Satisfactory
WYNN CONSTRUCTION | 19358 |  | B | SB |  | Duero Port Development Project | Duero, Bohol | 2015-12-02 | 1st & Final | DOTC | LF | 9.045 | 75 | 2014-12-09 | 2015-11-02 | 0 | C | 0.453 | 0.2 | 0.3 | - | - | - | 95.3 | *95.30% V. Satisfactory
WYNN CONSTRUCTION | 19358 | L | B | MA | GE | Concreting of Baang-Bagtic-Mahayag Norte Fram to Market Road, Catigbian, Bohol | Catigbian, Bohol | 2015-06-09 | Final | Bohol First DEO | LF | 3.77 | 50 | 2014-12-18 | 2015-02-05 | 0% | C | 0.462 | 0.136 | 0.3 | - | - | - | 89.8% | *89.8% Very Satisfactory
Wynn Construction | 19358 | L | B | MA | GE | Road Upgrading (Gravel to Paved), Balilihan - Hanopol - Butuan Road, K0037+498 to K0037+893 | Balilihan, Bohol | 2014-10-26 | 1st & Final | VII | LF | 13.5812 | 195 | 2014-02-21 | 2014-09-03 | 0% | C | 0.359 | 0.162 | 0.285 | - | - | - | 80.6% | 80.6% Unsatisfactory
Wynn Construction | [5 empty] | Emergency Repair and Rehabilitation of Alegria-Bang-Hagbuaya-Hanopol Norte Provincial Road | Catigbian & Balilihan, Bohol | 2015-01-20 | 1st | Bohol | L | 13.897 | 184 |  | 2015-02-27 | -0.35 | O | 0.384 | 0.286 | 0.147 | 0.03 | 0.06 | 0.05 | 95.7 | -
Wynn Construction | 19358 | L | D | SB | GE2 | Cayacay Small River Impounding Project | Mabini, Bohol Region VII | 2013-07-13 | 1st | NIA | L | 4.916 | 120 | 2012-09-27 | 2013-06-25 | -28.24 | O | 0.4 | 0.3 | 0 | 0.02 | 0.07 | 0.03 | 82 | -
Wynn Construction | 19358 | L |  |  | GE5 | Repair of RoRo Ramp 1 & 2, Pavement And Scoured Bulkhead | Port of Catagbacan, Loon, Bohol | 05/23-27/11 | 1st | PPA | LF | 7.883 | 221 | 2011-01-07 | 2011-08-15 | -0.63 | O | 0.4 | 0.225 | 0.1437 | 0.03 | 0.0646 | 0.05 | 91.33 | -
WYNN CONSTRUCTION / YU CONSTRUCTION JOINT VENTURE | JV-14-711 | L | B | MA | GE | Road Upgrading (Unpaved to Paved) Balilihan-Hanopol-Batuan Road, K0037+940 - K0039+120, Balilihan, Bohol | Balilihan, Bohol | 2015-11-16 | 1st | Bohol 1st | LF | 41.6199 | 235 | 2015-05-04 | 2015-12-25 | 0.0001 | OG | 0.345 | 0.24 | 0.15 | 0.03 | 0.04 | 0.05 | 85.5% | 85.5% Satisfactory
Y S Construction | 11928 | L | A | MA | GE1 | Conc./Impvt. of Sagbayan-Danao Rd. | Sagbayan and Danao, Bohol | 2013-03-13 | Final | VII | LF | 46.485 | 315 | 2012-01-20 | 2012-11-30 | 0 | C | 0.459 | 0.163 | 0.3 | - | - | - | 92.2 | 88.42% Satisfactory
Y S Construction | 11928 | L | A | MA | GB1 | Const. of MPB (Senior Citizen Hall Bldg.), Poblacion II | Tagbilaran City, Bohol | 2011-08-18 | 1st | VII | LF | 2.7 | 120 | 2011-05-30 | 2011-09-26 | 14.46 | O | 0.376 | 0.3 | 0.15 | 0.03 | 0.032 | 0.033 | 92.1 | -
Yakal Construction | 9685 | L | AAA | LB | GE | Rehabilitation/Reconstruction of Critical Sections along National Roads, Road Slip along Bato-Bontoc Road, K1113+500 - K1114+500 | Bato, Leyte | 2014-10-28 | 1st & Final | VIII | LF | 8.6479 | 130 | 2014-02-03 | 2014-06-12 | 0% | C | 0.471 | 0.133 | 0.3 | - | - | - | 90.4% | 90.4% Very Satisfactory
Yakal Construction | 9685 | L | AAA | MA | GE | Construction of River Control Structure, Pob. Cuardero, Capiz | Pob. Cuardero, Capiz | 2014-08-15 | Final | VI | LF | 29.0004 | 312 | 2012-11-18 | 2013-06-19 | 0 | C | 0.405 | 0.2 | 0.3 |  |  |  | 90.5 | 85.64% Satisfactory
Yakal Construction | 9685 | L | AAA | LB | GE | Completion for Repair/Rehab. Of Layog Bridge along Taft - Borongan - San Julian, Eastern Samar | Eastern Samar | 2014-08-14 | Final | VIII | LF | 15.3165 | 714 | 2011-10-17 | 2013-09-30 | 0.14 | C | 0.454 | 0.133 | 0.3 |  |  |  | 88.7 | 89.42% Very Satisfactory
Yakal Construction | 28289 | L | AAA | MA | GE2 | Const. of River Control | Poblacion Cuartero, Capiz | 2013-08-19 | 1st | VI | LF | 27.593 | 312 | 2012-11-18 | 2013-09-25 | -4.91 | O | 0.392 | 0.231 | 0.101 | 0.03 | 0.037 | 0.033 | 82.4
Yakal Construction | 9685 | L | AAA | MA | GE2 | Restoration & Const. of Flood Control Structure, Sitio Purisima, Brgy. Guindapunan | Palo, Leyte | 2013-08-20 | Final | VIII | LF | 45.859 | 395 | 2012-04-01 | 2013-04-30 | 0 | C | 0.451 | 0.133 | 0.3 | - | - | - | 88.4 | 85.28% Satisfactory
Yakal Construction | 9685 | L | AAA | LB | GE1 | Rehab. of Wright-Taft-Borongan Road, including Layug Bridge, Km. 860+570-Km. 938+500 |  | 2009-06-07 | 1st | VIII |  | 161.048 | 403 |  |  |  | O | 0.324 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 84.4 | -
Yakal Construction | 9685 | L | AAA | LB | GE1 | Upgrading/Concreting of Borongan-MacArthur Road with exceptions |  | 2009-06-07 | 1st | VIII |  | 161.533 | 355 |  |  |  | O | 0.321 | 0.24 | 0.15 | 0.03 | 0.05 | 0.033 | 82.4 | -
Yakal Construction | 9685 | L | AAA | LB | GE1 | Rehabilitation of Tagbilaran North Road, Clarin-Talibon Section, Km. 58.000-112.500 (w/ exception) |  | 2009-03-05 | 1st | VII |  | 14.0773 | 240 |  |  |  | O | 0.36 | 0.229 | 0.15 | 0.03 | 0.033 | 0.05 | 85.2 | -
Yakal Construction | 9685 | L | AAA | LB | GE1 | Upgrading/Conc. of Taft-Borongan Road with exception |  | 2009-09-17 | 2nd | VIII |  | 166.281 | 365 |  |  |  | O | 0.371 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 89.6 | -
Yakal Construction | 9685 | L | AAA | LB | GE1 | Road Upgrading of Bagahupi-Babatngon-Sta. Cruz-Barugo-Carigara Road, Km. 923+038-Km.927+610 w/ exceptions | Babatngon, Leyte | 2012-03-30 | 1st | VIII | LF | 37.792 | 325 | 2011-08-16 | 2012-07-05 | 1.34 | O | 0.313 | 0.245 | 0.15 | 0.03 | 0.035 | 0.05 | 82.3 | -
Yakal Construction | 9685 | L | AAA | MA | GE2 | Restoration & Const. of Flood Control Structure, Sitio Purisima, Brgy. Guindapunan | Palo, Leyte | 2012-08-23 | 1st | VIII | LF | 44.721 | 365 | 2012-04-07 | 2013-04-05 | 7 | O | 0.322 | 0.24 | 0.15 | 0.03 | 0.04 | 0.05 | 83.2 | -
Yap Mabuhay Enterprises, Incorporated | 15540 | L | B | SB | GB | Construction of Multi-Purpose Building-Maasim West Central Elementary School, Brgy. Poblacion | Brgy. Poblacion, Maasim, Sarangani | 2014-10-28 | 1st & Final | XII | LF | 2.991 | 60 | 2014-07-03 | 2014-08-31 | 0% | C | 0.492 | 0.133 | 0.3 | - | - | - | 92.5% | 92.5% Very Satisfactory
Yap Mabuhay Enterprises, Incorporated | 15540 | L | B | SB | GB | Construction of Multi-Purpose Building Poblacion Tantangan | Tantangan, South Cotabato | 2014-10-21 | 1st | XII | LF | 4.4085 | 150 | 2014-07-21 | 2014-12-17 | 18.43% | O | 0.398 | 0.224 | 0.15 | 0.02 | 0.043 | 0.033 | 86.8% | 86.8% Satisfactory
Yap Mabuhay Enterprises, Incorporated | 15540 | L | B | SB | GB1 | Const. of Multi-Purpose Building @ Poblacion |  | 2009-09-12 | 1st | XII |  | 0.95 | 84 |  |  |  | O | 0.363 | 0.3 | 0.15 | 0.03 | 0.023 | 0.033 | 89.9 | -
Yap Mabuhay Enterprises, Incorporated | 15540 | L | B | SB | GB1 | Construction of Multi-Purpose Building @ Poblacion |  | 2009-09-12 | 1st | XII |  | 0.952 | 126 |  |  |  | O | 0.364 | 0.262 | 0.15 | 0.03 | 0.035 | 0.033 | 87.4 | -
Yap Mabuhay Enterprises, Incorporated | 15540 | L | B | SB | GB1 | Construction of 2-CL School Building @ San Vicente NHS |  | 2009-09-11 | 1st | XII |  | 1.297 | 105 |  |  |  | O | 0.329 | 0.28 | 0.15 | 0.03 | 0.041 | 0.033 | 86.3 | -
YAP MABUHAY ENTERPRISES, INCORPORATED | 15540 | L | B | SB | GB | Local Infrastructure Program: Construction of Multi-Purpose Building, Poblacion | Tantangan, South Cotabato | 2015-06-02 | Final | South Cotabato DEO | LF | 4.408 | 150 | 2014-07-21 | 2014-12-17 | 0% | C | 0.485 | 0.133 | 0.3 | - | - | - | 91.8% | *91.8% Very Satisfactory
YAP MABUHAY ENTERPRISES, INCORPORATED | 15840 | L | B | SB | GB | Construction of Multi-Purpose Building (MPB) at Sunken Arena, Brgy. Poblacion | Malungon, Sarangani Province | 2015-09-03 | 1st & Final | Saranggani | LF | 4.895 | 116 | 2015-04-02 | 2015-07-26 | 0% | C | 0.496 | 0.133 | 0.3 | - | - | - | 92.9% | *92.9% Very Satisfactory
YL Trading General Merchandising | 22543 |  |  |  |  | Conc. of San Remegio-Bugo Road |  | 2010-06-10 |  | VI |  | 9.479 | 100 |  |  |  | O | 0.339 | 0.3 | 0.15 | 0.015 | 0.033 | 0.033 | 87 | -
YL Trading General Merchandising | 22543 | L | A | MA | GE1 | Concreting of Road, Funda Dalipe-San Pedro (San Jose) |  | 2009-06-04 | 1st | VI |  | 9.502 | 180 |  |  |  | O | 0.371 | 0.24 | 0.15 | 0.03 | 0.04 | 0.033 | 86.4 | -
YL Trading General Merchandising | 22543 | L | A | MA | GE1 | Conc. of Hamtic-Bia-an-Egana-Sibalom Road, Catungan Section |  | 2009-03-13 | 1st | VI |  | 19.259 | 300 |  |  |  | O | 0.28 | 0.294 | 0.15 | 0.024 | 0.05 | 0.033 | #VALUE! | -
Young Builders Corporation | 15807 |  |  |  |  | Rehab. of Bulwang Curve Section-Lumbangan Section, Bais Mabinay Road |  | 2010-09-01 |  | VII |  | 57.809 | 240 |  |  |  | O | 0.36 | 0.3 | 0.15 | 0.03 | 0.047 | 0.033 | 92 | -
Yoyen Enterprises | 15541 |  |  |  |  | Road Upgrading of Libungao-Matag-ob-Palompon Rd. |  | 2010-06-04 |  | VIII |  | 18.227 | 225 |  |  |  | O | 0.372 | 0.24 | 0.15 | 0.03 | 0.042 | 0.05 | 88.4 | -
Yoyen Enterprises | 15541 | L | A | MA | GE1 | Conc. of Culaba-Caibiran National Circ. Road, Culaba-Looc Section |  | 2008-11-18 | 1st | VIII |  | 3.742 | 160 |  |  |  | O | 0.32 | 0.281 | 0.1 | 0.015 | 0.037 | 0.1 | 85.3 | -
Yoyen Enterprises | 15541 | L | A | MA | GE1 | Conc. of Dayhagan-Salvacion-Coob-Libertad Road |  | 2008-08-26 | 1st | VIII |  | 12.537 | 150 |  |  |  | O | 0.317 | 0.22 | 0.1 | 0.02 | 0.038 | 0.1 | 79.5 | -
Yoyen Enterprises/Uy Construction & Dev't. (JV) | JV-08-263 | L | A | MA | GE1 | Upgrading/Conc. of MacArthur-Guiuan Road exception |  | 2009-09-17 | 1st | VIII |  | 90.226 | 300 |  |  |  | O | 0.367 | 0.24 | 0.15 | 0.03 | 0.05 | 0.05 | 88.7 | -
YS Construction | 11928 | L | A | MA | GE | Construction of Drainage System along National Road | Ubay, Bohol | 2014-08-11 | 1st | VII | LF | 9.2611 | 193 | 2014-02-04 | 2014-08-15 | 0.69 | O | 0.349 | 0.298 | 0.15 | 0.022 | 0.047 | 0.05 | 91.6
YS Construction | 11928 | L |  |  |  | BERRRP-Inabanga-Danao via Lapacan-Magtangtang rd. | Inabanga, Buenavista, and Danao, Bohol | 2015-01-20 | 1st | Bohol | L | 21.908 | 365 | 2014-06-12 | 2015-06-04 | -8.4159 | O | 0.368 | 0.3 | 0.066 | 0.03 | 0.051 | 0.05 | 86.5 | -
YS Construction | 11928 | L | B | MA | GE1 | Const./Imprvt. Of Vallehermoso-Canlaon City-La Castellana Rd. (VLCR) |  | 2009-09-14 | 1st | VII |  | 20.753 | 260 |  |  |  | O | 0.386 | 0.24 | 0.15 | 0.03 | 0.037 | 0.05 | 89.3 | -
YS Construction | 11928 | L | B | MA | GE1 | Widening/Concrete Paving of Tubigon Port Access Road |  | 2009-06-09 | 1st | VII |  | 4.639 | 91 |  |  |  | O | 0.375 | 0.296 | 0.15 | 0.03 | 0.047 | 0.05 | 94.8 | -
YS CONSTRUCTION | 11928 | L | A | MA | GE | Upgrading of Buenavista, Carmen-Concepcion, Danao-Getafe Road (I.S.), Bohol Province Section 1: K0092+143-K0093+900.048; Section 2: K0094+039.032-K0094+647.960; Section 3: K0095+573-K0097+106.34; Section 4: K0097+303.820-K0097+640 | Bohol Province | 2015-06-09 | Final | Regional Office No. VII | LF | 85.022 | 285 | 2014-05-02 | 2015-02-10 | 0% | C | 0.441 | 0.14 | 0.3 | - | - | - | 88.1% | *88.1% Satisfactory
YSL Builder | 19516 | L | A | MA | GB-1 | Construction of Tangub City LTO District Office | Tangub City, Misamis Oriental | 2014-08-26 | 1st & Final | DOTC | LF | 4.989 | 150 | 2013-12-26 | 2014-07-19 | 6.32 | C | 0.4853 | 0.2 | 0.3 | - | - | - | 98.53 | *98.53% Outstanding
YSL Builder | 19516 | L | A | MA | GE1 | Concreting of Dipolog-Punta-Dansullan-Segio Osmeña Road, Cogon Section |  | 2009-06-10 | 1st | IX |  | 12.322 | 210 |  |  |  | O | 0.375 | 0.24 | 0.15 | 0.03 | 0.042 | 0.05 | 88.7 | -
YSL Builder | 19516 | L | A | MA | GE1 | Road Upgrading (Gravel to Concrete) Sindangan-Siayan-Dumingag-Mahayag Road, Buyos Secion |  | 2009-06-11 | 1st | IX |  | 16.151 | 270 |  |  |  | O | 0.353 | 0.24 | 0.15 | 0.03 | 0.042 | 0.05 | 86.5 | -
YSL Builder | 19516 | L | A | MA | GE1 | Road Conc. along Dipolog-Punta-Dansullan-Sergio Osmeña Road, Sangkol Section |  | 2009-06-10 | 1st | IX |  | 12.319 | 210 |  |  |  | O | 0.352 | 0.24 | 0.15 | 0.03 | 0.037 | 0.05 | 85.9 | -
YSL Builder | 19516 | L | A | MA | GE1 | Conc. of Dipolog-Dansullan-Sergio Osmeña Road, Cogon Section |  | 2009-09-17 | 2nd | IX |  | 12.322 | 210 |  |  |  | O | 0.336 | 0.3 | 0.15 | 0.03 | 0.045 | 0.033 | 89.4 | -
YSL Builder | 19516 | L | A | MA | GE1 | Road Conc. along Dipolog-Dansullan-Sergio Osmeña Road, Sangkol Sect. |  | 2009-09-17 | 2nd | IX |  | 12.319 | 210 |  |  |  | O | 0.334 | 0.3 | 0.15 | 0.03 | 0.045 | 0.033 | 89.2 | -
YSL BUILDER | 32898 | L | A | MA | GE | Network Development -Widening of National Roads along Dipolog-Oroquieta National Road, Widening with Drainage, K1825+300-K1826+269, Dapitan City, Zamboanga Del Norte | Dapitan City, Zamboanga Del Norte | 2015-11-14 | Final | Zamboanga Del Norte 3rd DEO | LF | 22.7162 | 145 | 2015-02-25 | 2015-07-19 | - | C | 0.435 | 0.133 | 0.3 | - | - | - | 86.8% | 86.8% Satisfactory
YSL BUILDERS | 19516 | L | A | MA | GE | Network Development - Widening of National Roads along Dipolog - Oroquieta National Road, Widening with Drainage, K1825+300 to K1826+269, Zamboanga del Norte | Zamboanga del Norte | 2015-06-05 | 1st | Zamboanga del Norte 3rd DEO | LF | 22.715 | 145 | 2015-02-25 | 2015-07-19 | 76% | O | 0.356 | 0.225 | 0.15 | 0.03 | 0.045 | 0.033 | 83.9% | -
YSL BUILDERS | 19516 | L | 0 | MA | GE | Construction of Turnouts Along Sayre Highway (Alae-Kisolon Road), K1445+495-K1445+585, K1447+320-K1447+410, K1445+255-K1455+345, K1455+485-K1455+575, K1474+675-K1474+765 & K1474+840-K1474+930, Manolo Fortich & Sumilao, Bukidnon | Sumilao, Bukidnon | 2015-11-13 | Final | Bukidnon 3rd | LF | 8.326 | 80 | 2015-02-10 | 2015-05-01 | 0.00% | C | 0.486 | 0.133 | 0.3 | - | - | - | 91.9% | 91.9% Very Satisfactory
Yu Construction | 10470 | L | A |  |  | Emergency Repair and Rehabilitation of Abatan-Agahay-Busao-Toril-Aghao Road | Maribojoc,Bohol | 2015-05-14 | 1st & Final | Bohol | LF | 22.058 | 272 | 2014-06-05 | 2015-03-03 | 0 | C | 0.5 | 0.2 | 0.3 | - | - | - | 100 | *100.00% Outstanding
Yu Construction | 10470 | L | A | MA | GE | Construction/Improvement of Dauis - Panglao Road, Section 1) K0009+570 to K0010+569.15; Section 2) K0010+748 to K0017+278.56 | Bohol Province | 2014-10-27 | 1st | VII | LF | 89.2325 | 240 | 2014-05-15 | 2015-01-09 | 2.5% | O | 0.297 | 0.3 | 0.15 | 0.03 | 0.06 | 0.033 | 87% | 87% Satisfactory
Yu Construction | 10470 | L | A | MA | GE | Road Upgrading (Gravel to Paved) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standard (HDM-4 Project Analysis (Intermittent Section) Balilihan-Hanopol-Batuan Road, Batuan Section | Batuan, Bohol | 2014-08-12 | 1st | VII | LF | 44.4 | 179 | 2014-04-25 | 2014-10-20 | 4.82 | O | 0.36 | 0.252 | 0.15 | 0.022 | 0.047 | 0.05 | 88.1
Yu Construction | 10470 | L | A |  |  | Emergency Repair and Rehabilitation of Antequera-Balilihan via Dorol Road | Antequera & Balilihan, Bohol | 2015-01-19 | 1st | Bohol | L | 20.744 | 284 | 2014-06-05 | 2015-03-15 | -3.14 | O | 0.393 | 0.3 | 0.119 | 0.03 | 0.054 | 0.05 | 94.6 | -
Yu Construction | 10470 | L | A | MA | GE1 | Upgrading (Gravel to Concrete) of Balilihan-Hanopol-Batuan Rd. | Batuan, Bohol | 2013-08-20 | 1st | VII | LF | 40.386 | 209 | 2013-03-04 | 2013-09-28 | 1.01 | O | 0.349 | 0.257 | 0.15 | 0.03 | 0.065 | 0.05 | 90.1
Yu Construction | 10470 | L | A | MA | GE1 | Impv't. of Balilihan-Hanopol-Batuan Rd., Batuan Sect., K0046+702-K0048+594.23 (w/ exception) | Batuan, Bohol | 2013-03-14 | Final | VII | LF | 40.545 | 257 | 2011-12-27 | 2012-09-09 | 0 | C | 0.482 | 0.2 | 0.3 | - | - | - | 98.2 | 92.68% V. Satisfactory
Yu Construction | 10470 | L | A | MA | GE1 | Impv't. of Rd., Jct. (TNR) Manbojoc-Antiquera-Catagbacan (Loon) Rd., Km.29+000-Km.31+125 (w/ exceptions) | Loon, Bohol | 2013-03-12 | Final | VII | LF | 48.28 | 285 | 2012-01-24 | 2012-10-03 | 6.32 | C | 0.417 | 0.152 | 0.3 | - | - | - | 86.9 | 87.50% Satisfactory
Yu Construction | 10470 | L | A | MA | GE1 | Impv't./Widening of Jct. Catagbacan, Loon Rd. leading to Int'l. Cruise Ship Port (inc. Causeway) Km.35+540-Km.36+048.20, Catagbacan | Loon, Bohol | 2013-03-12 | Final | VII | LF | 19.025 | 240 | 2012-01-17 | 2012-09-12 | 0 | C | 0.423 | 0.162 | 0.3 | - | - | - | 88.5 | 87.30% Satisfactory
Yu Construction | 10470 | L | A | MA | GE1 | Const./Impvt. of Concepcion, Danao-Buenavista, Carmen Rd. Sect. 1: K0068+170- K0069+429.03 Sect. 2: K0069+630.64-K0069+740 | Carmen, Bohol | 2013-03-14 | Final | VII | LF | 28.069 | 241 | 2012-01-24 | 2012-09-20 | 3.74 | C | 0.282 | 0.2 | 0.3 | - | - | - | 78.2 | 83.12% Satisfactory
Yu Construction | 10470 | L | A | MA | GB1 | Const. of MPB (Municipal Building), Poblacion | Trinidad, Bohol | 2011-03-31 | 1st | VII | LF | 16.398 | 300 | 2010-12-10 | 2011-10-06 | 23.46 | O | 0.389 | 0.24 | 0.15 | 0.03 | 0.06 | 0.05 | 91.9 | -
Yu Construction | 10470 | L | A | MB | GE2 | Talibon Small Reservoir Irrigation Project |  | 9/29/08 10/308 | 1st | SRIP |  | 14.63 | 373 |  |  |  | O | 0.322 | 0.177 | 0.1 | 0.03 | 0.047 | 0.2 | 87.6 | -
YU CONSTRUCTION | 10470 | L | A | MB | GE | Construction/Improvement of Dauis-Panglao Road, Section 1: K0009+570-K00010+569.15, Section 2:K0010+748-K0017+278.56, Bohol Province | Dauis-Panglao Bohol Province | 2015-06-09 | Final | Regional Office No. VII | LF | 89.233 | 240 | 2014-05-15 | 2015-01-09 | 0% | C | 0.432 | 0.189 | 0.3 | - | - | - | 92.1% | *89.04% Very Satisfactory
YU CONSTRUCTION | 10470 | L | A | MB | GE | Rehabilitation/ Reconstruction/ Upgrading of Damaged Paved Road along Tagbilaran North Road (Tagbilaran-Jetafe Section), K0034+631 - K0036+300 (Raising of Grades), Catagbacan, Loon, Bohol | Catagbacan, Loon, Bohol | 2015-11-16 | 1st | Bohol 1st | LF | 45.5188 | 210 | 2015-05-04 | 2015-11-29 | 0.0052 | OG | 0.398 | 0.24 | 0.15 | 0.03 | 0.025 | 0.05 | 89.3% | 89.3% Very Satisfactory
Yu Construction / SCP Construction (JV) | JV-12-152 | L | AA | LA | GE1 | Upgrading of Jct., Dat-an, Carmen-Sierra Bullones-Pilar, Alicia Rd., K0084+272.04-K0088+724.4 | Bohol Province | 2013-08-15 | 1st | VII | LF | 60.752 | 316 | 2013-03-22 | 2014-01-31 | 0.11 | O | 0.374 | 0.251 | 0.15 | 0.03 | 0.055 | 0.033 | 89.3
YURICH BUILDERS AND CONSTRUCTION SUPPLY | 37064 | L | D | SB | GB | Construction of New Multi-Purpose Building, Brgy. Magara | Roxas, Palawan | 2015-06-05 | 1st | Palawan 1st DEO | LF | 0.995 | 84 | 2015-04-27 | 2015-07-19 | 0% | O | 0.353 | 0.24 | 0.15 | 0.03 | 0.047 | 0.05 | 87% | -
YURICH BUILDERS AND CONSTRUCTION SUPPLY | 37064 | L | D | SB | GE | Construction of Barangay Road (New Road with PCCP Surfacing), Brgy. Bucana, Sta. 00+000- Sta. 0+172.00 | El Nido, Palawan | 2015-06-05 | Final | Palawan 1st DEO | LF | 1.866 | 70 | 2015-02-16 | 2015-04-26 | 0% | C | 0.462 | 0.133 | 0.3 | - | - | - | 89.5% | *89.5% Very Satisfactory
Z & L Construction & Supplies | 25322 |  |  |  |  | Talakag IP |  | 04/13-18/09 | 1st | NIA |  | 4.748 | 240 |  |  |  | O | 0.3225 | 0.2508 | 0.15 | 0.023 | 0.063 | 0.05 | 89.4 | -
Z & L Construction & Supplies | 25322 | L | B | SB | GB1 | Const. of Multi-Purpose Bldg. @ Agusan Del Sur State College of Agriculture and Technology |  | 2009-06-08 | 1st | XIII |  | 2.799 | 135 |  |  |  | O | 0.349 | 0.3 | 0.15 | 0.03 | 0.032 | 0.033 | 89.4 | -
Z F Construction | 17676 | L | A | MA | GE1 | Road Upgrading (Gravel to Paved) Baler-Casiguran Rd., Km.284+627.38-Km.286+042.45 | Dipaculao, Aurora | 2012-03-23 | Final | III | LF | 11.51 | 120 | 2011-05-03 | 2011-08-30 | 0 | O | 0.455 | 0.133 | 0.3 | - | - | - | 88.8 | 87.30% Satisfactory
Zabu Engineering | 31104 | L | C | SB | GE1 | Replacement of Limood Bridge along Kalinga-Abra Rd., Limood, Balenciagao Sur, Pasil | Kalinga | 2013-03-19 | Final | CAR | LF | 10.959 | 285 | 2012-01-16 | 2012-10-27 | - | C | 0.446 | 0.133 | 0 | - | - | - | 57.9 | 69.54% Poor
ZAMBOANGA ERECTORS & CONTRACTORS, INC. (Formerly: Zamboanga Engineers and Contractors) | 6239 | L | B | SB | GE | Construction/Repair/Improvement of Flood Control at Ayala River, Zamboanga City | Zamboanga City | 2015-09-03 | 1st | Zamboanga City | LF | 8.529 | 303 | 2015-03-23 | 2016-01-19 | (+)1.38% | O | 0.314 | 0.3 | 0.15 | 0.03 | 0.051 | 0.05 | 89.5% | -
ZAMBOANGA ERECTORS & CONTRACTORS, INC. (Formerly: Zamboanga Engineers and Contractors) | 6239 | L | B | SB | GE | Construction/Repair/Improvement of Flood Control at Ayala River, Zamboanga City | Zamboanga City | 2015-11-19 | 2nd | Zamboanga City DEO | LF | 8.5289 | 243 | 2015-03-23 | 2015-11-20 | 11.96% | OG | 0.32 | 0.24 | 0.15 | 0.02 | 0.047 | 0.05 | 82.7% | 82.7% Satisfactory
ZAMBOANGA ERECTORS AND CONTRACTORS, INC. (Formerly: Zamboanga Engineers and Contractors) | 6239 | L | B | SB | GE | Construction of Flood Control Revetment at Limpapa Bridge along Zamboanga City - Labuan - Limpapa Road, Zamboanga City | Zamboanga City | 2015-06-11 | Final | Zamboanga City DEO | LF | 6.893 | 189 | 2014-09-29 | 2015-04-05 | 0.53% | C | 0.466 | 0.133 | 0.3 | - | - | - | 89.9% | *89.9% Very Satisfactory
Zedik Builders | 33330 | L | B | MA | GE | Construction/Concreting of Road-Pilipinas Road @ Brgy. Centro-1 | Claveria, Cagayan | 2014-10-22 | 1st & Final | II | LF | 4.8782 | 78 | 2014-06-18 | 2014-09-03 | 0.43% | C | 0.365 | 0.2 | 0.3 | - | - | - | 86.5% | 86.5% Satisfactory
Zephyr Construct Philippines, Inc. | [5 empty] | Villa Regeneracion Housing Project-Site1, | Brgy. Gogo, Estancia, Iloilo | 2016-03-11 | 1st | NHA | LF | 98.5884 | 352 | 2015-04-16 | 2016-04-03 | -18.12 | O | 0.2987 | 0.2748 | 0 | 0.03 | 0.0583 | 0.033 | 69.48 | -
Zephyr Construction Philippines, Inc. | [5 empty] | Villa Regenaracion Housing Project-Site2, | Brgy. Gogo, Estancia, Iloilo | 2016-03-11 | 1st | NHA | LF | 98.5976 | 352 | 2015-04-16 | 2016-04-01 | -28.64 | O | 0.3273 | 0.2861 | 0 | 0.03 | 0.0583 | 0.033 | 73.47 | -
ZET CONSTRUCTION | 12615 |  | A | MA |  | Completion of Pangangan Port Development Project | Pangangan, Calape, Bohol | 2015-12-03 | 2nd & Final | DOTC | LF | 23.481 | 180 | 2015-05-04 | 2015-10-30 | 0 | C | 0.391 | 0.2 | 0.3 | - | - | - | 89.1 | 87.10% Satisfactory
ZET Construction | 12615 | L | B | MA | GE | Lasang Landscape and Seascape Development Project Phase II | Initao-Libertad, Misamis Oriental | 2016-02-11 | 2nd | TIEZA | LF | 12 | 240 | 2015-08-11 | 2016-04-11 |  | O | 0.371 | 0.3 | 0.15 | 0.03 | 0.054 | 0.05 | 95.54
Zet Construction | 12615 | L | B | MA | GE-5 | Completion of Pangangan Causeway | Pangangan, Calape, Bohol/Region VII | 2015-09-22 | 1st | DOTC | LF | 23.481 | 180 | 2015-05-03 | 2015-10-29 | -1.04 | O | 0.3366 | 0.3 | 0.1396 | 0.02 | 0.0292 | 0.0333 | 85.87 | -
Zet Construction | 12615 | L | A | MA | GE5 | Lupon Port Development Project | Lupon, Davao Oriental | 2014-02-05 | Final | DOTC | LF | 30.848 | 150 | 2013-03-10 | 2013-09-20 | 0 | C | 0.458 | 0.2 | 0.3 | - | - | - | 95.8 | 92.60% Very Satistactory
Zet Construction | 12615 | L | A | MA | GE5 | Lupon Port Development Project | Lupon, Davao Oriental | 2013-09-18 | 1st | DOTC | L | 29.727 | 150 | 2013-03-10 | 2013-08-06 | -4.58 | O | 0.389 | 0.3 | 0.104 | 0.02 | 0.061 | 0.033 | 90.7 | -
Zet Construction | 12615 | L |  |  | GE5 | Replacement & Installation of Rubber Dock Fenders Phase I & II | Port of Cagayan de Oro, Cagayan de Oro City | 2013-05-31 | Final | PPA | L | 28.122 | 120 | 2012-11-06 | 2013-03-05 | 0.833 | C | 0.49 | 0.2 | 0.3 | - | - | - | 99 | 98.31% Outstanding
ZET Construction | 12615 | L | A |  | GE5 | Repair/Renovation of Passenger Terminal Building (PTB-1) | Port of Zamboanga, Zamboanga City | 2012-09-28 | 1st | PPA | LF | 15.463 | 272 | 2012-03-14 | 2012-12-10 | 2.724 | O | 0.399 | 0.27 | 0.15 | 0.03 | 0.064 | 0.05 | 96.3 | -
ZET Construction | 12615 | L |  | MA | GE5 | Replacement and Installation of Rubber Dock Fenders, Phase I & II | Port of Cagayan de Oro, Cagayan de Oro City | 2013-02-15 | 1st | PPA | LF | 28.122 | 120 | 2012-11-06 | 2013-03-05 | 4.75 | O | 0.4 | 0.3 | 0.15 | 0.03 | 0.0485 | 0.05 | 97.85 | -
ZF Construction | 17676 | L | A | MA | GE1 | Road Upgrading (Gravel to Paved) Baler-Casiguran Rd., Km.284+627.38 to Km.286+042.45 | Dipaculao, Aurora | 2011-08-16 | 1st | III | LF | 11.51 | 120 | 2011-05-03 | 2011-08-30 | 2.84 | O | 0.355 | 0.24 | 0.15 | 0.03 | 0.055 | 0.033 | 86.3 | -
ZION CONSTRUCTION | 14881 | L | B | MB | GE | Rehabilitaion/Reconstruction/Upgrading of Damaged Paved National Road including Drainage along Toledo-Tabuelan Road (Intermittent Sections): K0104+808 - K0104+985; K0105+418 - K0105+500; and K0107+000 - K0107+880, Tabuelan, Cebu | Tabuelan, Cebu | 2015-11-13 | Final | Cebu 1st | LF | 19.2428 | 179 | 2015-03-03 | 2015-08-28 | 0 | C | 0.41 | 0.133 | 0.3 | - | - | - | 84.3% | 84.3% Satisfactory
ZION CONSTRUCTION | 14881 | L | B | MB | GE | Rehabilitation/Reconstruction/Upgrading of Damaged Paved National Roads including Drainage Based on Pavement Management System / Highway Development and Management-4 (HDM-4) (International sections), Secondary Road, Imus Road, Chainage 0205-Chainage 1076 (S00056CB) (3-Lanes), Chainage 865-Chainage 1070 (S00348CB) (3-Lanes), Cebu Cuty | Cebu City | 2015-11-20 | Final | Cebu City | LF | 28.5413 | 173 | 2015-02-25 | 2015-08-18 | 0.0138 | C | 0.497 | 0.133 | 0.3 | - | - | - | 93% | 93% Very Satisfactory
Zion Construction (Formerly Masterpiece Construction and Supply) | 14881 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of Sibonga-Dumanjug Road, Tubod-Dugoan Section |  | 2009-05-29 | 1st | VII |  | 14.175 | 75 |  |  |  | O | 0.383 | 0.24 | 0.15 | 0.03 | 0.055 | 0.05 | 90.8 | -
Zion Construction (Formerly Masterpiece Construction and Supply) | 14881 | L | B | MA | GE1 | Widening of H. Abellana Road |  | 2009-06-05 | 2nd | VII |  | 4.656 | 320 |  |  |  | O | 0.343 | 0.24 | 0.15 | 0.03 | 0.047 | 0.05 | 86 | -
Zion Construction (Formerly Masterpiece Construction and Supply) | 14881 | L | B | MA | GE1 | Conc. of Jct.(LIR) Dat-an,Carmen-S. Bullones-Pilar-Alicia Rd. Sta.90+290-Sta.92+240(Alicia Sec.) with exception |  | 2009-09-04 | 2nd | VII |  | 18.637 | 232 |  |  |  | O | 0.337 | 0.237 | 0.15 | 0.03 | 0.037 | 0.033 | 82.4 | -
Zion Construction (Formerly Masterpiece Construction and Supply) | 14881 | L | B | MA | GE1 | Impv't./Conc. of Jct. (LIR) Dat-an, Carmen-Sierra Bullones-Pilar-Alicia Rd.(Pilar Sec.)Km. 81+980-Km.82+890 with exemption |  | 2009-09-04 | 1st | VII |  | 18.386 | 224 |  |  |  | O | 0.34 | 0.237 | 0.144 | 0.03 | 0.037 | 0.033 | 82.1 | -
Zion Construction (Formerly Masterpiece Construction and Supply) | 14881 |  |  |  |  | Completion of MPB, Agape |  | 2010-08-25 |  | VII |  | 1.416 | 107 |  |  |  | O | 0.347 | 0.3 | 0.15 | 0.03 | 0.032 | 0.033 | 89.2 | -
Zion Construction (Formerly Masterpiece Construction and Supply) | 14881 | L | B | MA | GE2 | Widening of H. Abellena Road |  | 2009-03-05 | 1st | VII |  | 4.656 | 261 |  |  |  | O | 0.343 | 0.3 | 0.15 | 0.03 | 0.027 | 0.05 | #VALUE! | -
Zion Construction (Formerly Masterpiece Construction and Supply) | 14881 | L | B | MA | GE1 | Conc. of Jct. (LIR) Dat-an, Carmen-Sierra Bullones-Pilar-Alicia Road (Sta. 90+290-Sta. 92+240 with exception), Alicia Section |  | 2009-06-05 | 1st | VII |  | 18.637 | 206 |  |  |  | O | 0.363 | 0.3 | 0.15 | 0.03 | 0.047 | 0.033 | 92.3 | -
Zion Construction (Formerly: Masterpiece Const. & Supply) | 14881 | L | B | MA | GE1 | Rehab./Reconst./Upgrading of Damaged Pavement along Loay Interior Rd. (LIR), Loboc Sect. 1: K0197+576-K0198+980 & Sect. 2: K0200+073-K0200+772.52 | Loboc, Bohol | 2012-08-09 | 1st | VII | LF | 33.372 | 281 | 2012-01-30 | 2012-11-05 | 21.23 | O | 0.355 | 0.24 | 0.15 | 0.03 | 0.05 | 0.033 | 85.8 | -
Zion Construction (Formerly: Masterpiece Construction and Supply) | 14881 | L | B | MA | GE | Road Upgrading (Gravel to Concrete) Based on Gravel Road Strategies, Traffic Benchmarks (HDM-4 Project Analysis), Argao - Ronda Road, K0085+090 to K0086+917 | Ronda, Cebu | 2014-10-22 | 1st & Final | VII | LF | 12.5501 | 158 | 2014-02-26 | 2014-08-02 | 1.27% | C | 0.42 | 0.138 | 0.3 | - | - | - | 85.8% | 85.8% Satisfactory
Zion Construction (Formerly: Masterpiece Construction and Supply) | 14881 | L | B | MA | GE | Preventive Maintenance Based on Pavement Management System/Highway Development and Management-4 (HDM-4), Natalio Bacalso Avenue, K0069+086 to K0071+625 | Argao, Cebu | 2014-10-24 | 1st & Final | VII | LF | 32.811 | 125 | 2014-02-17 | 2014-06-21 | 20.8% | C | 0.424 | 0.196 | 0.3 | - | - | - | 92% | 92% Very Satisfactory
Zion Construction (Formerly: Masterpiece Construction and Supply) | 14881 | L | B | MA | GE | Repair/Restoration of Damaged Slope Protection and Slope Lined Canal along Natalio Bacalso Avenue, K0059+500 to K0140+200 (Intermittent Section) | Argao, Cebu | 2014-08-05 | Final | VII | LF | 1.8065 | 195 | 2013-05-17 | 2013-11-27 | 6.19 | C | 0.427 | 0.171 | 0.3 |  |  |  | 89.8 | 90.40% Very Satisfactory
Zion Construction (Formerly: Masterpiece Construction and Supply) | 14881 | L | B | MA | GB | Construction of Two (2) Storey, Four (4) Classroom School Building at Argao National High School, Argao, Cebu | Argao, Cebu | 2014-08-05 | Final | VII | LF | 7.006 | 150 | 2014-04-03 | 2013-08-30 | 0 | C | 0.432 | 0.184 | 0.3 |  |  |  | 91.6 | 91.04% Very Satisfactory
Zion Construction (Formerly: Masterpiece Construction and Supply) | 14881 | L | B | MA | GE | Construction of Flood Control/Slope Protection along Lambusan Bridge (Upstream and Down Stream) | San Remegio, Cebu | 2014-08-07 | 1st & Final | VII | LF | 18.1359 | 140 | 2014-01-21 | 2014-06-09 | 0 | C | 0.391 | 0.2 | 0.3 |  |  |  | 89.1 | 89.10% Very Satisfactory
Zion Construction (Formerly: Masterpiece Construction and Supply) | 14881 | L | B | MA | GB1 | Const. of 2-Storey 4-CL Sch. Bldg. at Argao NHS | Argao, Cebu | 2013-08-08 | 1st | VII | LF | 4.73 | 150 | 2013-04-03 | 2013-08-30 | 0.26 | O | 0.355 | 0.27 | 0.15 | 0.03 | 0.053 | 0.05 | 90.8 | -
Zion Construction (Formerly: Masterpiece Construction and Supply) | 14881 | L | B | MA | GE2 | Repair/Restoration of Damaged Slope Protection & Slope Line Canal along Natalio Bacalso Ave., K0059+500-K0140+200 (Int. Sect.) | Argao to Santander, Cebu | 2013-08-09 | 1st | VII | LF | 18.085 | 195 | 2013-05-17 | 2013-11-27 | 37.44 | O | 0.356 | 0.3 | 0.15 | 0.03 | 0.05 | 0.05 | 93.6
ZION CONSTRUCTION (Formerly: Masterpiece Construction and Supply) | 14881 | L | B | MA | GE | Construction/Upgrading/Rehabilitation of Drainage along National Roads, Cebu Circumferential Rd. (F. Llamas St.), Chainage 000 - Chainage 1380 | Cebu City | 2015-09-03 | 1st | Cebu City | LF | 45.533 | 360 | 2015-02-25 | 2016-02-19 | 2.04% | O | 0.296 | 0.3 | 0.15 | 0.024 | 0.055 | 0.05 | 87.5% | -
Zircon Builder | 16158 | L | D | SB | GE | Road Upgrading (Gravel to Paved) Based on Gravel Road Strategies, Traffic Benchmark for Upgrading to Paved Road Standards (HDM-4 Project Analysis), National Arterial Road, Nueva Ecija - Aurora Road, K0175+984 to K0176+140 | Aurora | 2014-08-08 | 1st | III | LF | 11.5687 | 121 | 2014-03-21 | 2014-07-19 | 0.26 | O | 0.352 | 0.24 | 0.15 | 0.012 | 0.042 | 0.033 | 82.9
ZM / DMJ Construction (JV) | JV-08-056 | L | A | MB | GE1 | Replacement of Bravo Bridge |  | 2009-03-03 | 1st | III |  | 42.82 | 180 |  |  |  | O | 0.382 | 0.3 | 0.15 | 0.03 | 0.033 | 0.05 | #VALUE! | -
ZM / VRF Construction (JV) | JV-08-014 | L | A | MB | GE1 | Construction of Bridge and Approaches (Contact Package II) |  | 2009-03-03 | 1st | III |  | 38.937 | 210 |  |  |  | O | 0.357 | 0.244 | 0.15 | 0.02 | 0.028 | 0.05 | #VALUE! | -
ZM Construction / R.Z. Roncal Construction and Trading (JV) | JV-11-036 | L | AA | MB | GE1 | Road Upgrading (Gravel to Paved) of Nueva Ecija-Aurora Rd. | Nueva Ecija | 2012-08-02 | 1st | III | LF | 98.573 | 360 | 2011-11-17 | 2012-11-09 | 1.5 | O | 0.398 | 0.3 | 0.15 | 0.03 | 0.042 | 0.033 | 95.3 | -
ZM Construction /DMJ Construction (JV) | JV-07-084 | L | A | MB | GE1 | Impvt./Widening of McArthur Highway (Manila North Road) Phase V Meycauayan Bulacan) to Mabalacat Pampanga Sect., (Angeles-Mabalacat Section) CP1 |  | 2009-08-28 | 1st | III |  | 85.883 | 240 |  |  |  | O | 0.392 | 0.24 | 0.15 | 0.03 | 0.05 | 0.033 | 89.5 | -
ZM Construction/R.Z. Roncal Construction and Trading (JV) | JV-11-036 | L | AA | MB | GE1 | Rd. Upgrading (Gravel to Paved) of Nueva Ecija-Aurora Rd. | Nueva Ecija | 2013-08-10 | Final | III | LF | 98.572 | 540 | 2011-11-17 | 2013-05-08 | 0 | C | 0.438 | 0.133 | 0.3 | - | - | - | 87.1 | 92.02% V. Satisfactory
ZMS Const. & Dev. Corp. (Formerly: ZMS Construction) | 10471 | L | B | MA | GB | Construction of Two (2) Storey Four (4) Classroom School Building, Sominot NHS, (Don Mariano Marcos) | Sominot, Zamboanga del Sur | 2014-10-27 | 1st & Final | IX | LF | 4.5654 | 150 | 2014-01-09 | 2014-06-07 | 0% | C | 0.498 | 0.145 | 0.3 | - | - | - | 94.3% | 94.3% Very Satisfactory
ZMS Const. & Dev. Corp. (Formerly: ZMS Construction) | 10471 | L | B | MB | GE | Widening of Pagadian City-Zamboanga City Road K 1662+950 -K 1664+950 | Pagadian City | 2014-10-27 | 1st & Final | IX | LF | 48.3887 | 229 | 2014-02-24 | 2014-10-10 | 0% | C | 0.454 | 0.133 | 0.3 | - | - | - | 88.7% | 88.7% Satisfactory
ZMS Const. & Dev. Corp. (Formerly: ZMS Construction) | 10471 | L | B | MB | GE | Widening of Pagadian City, Zamboanga del Sur | Pagadian City, Zamboanga del Sur | 2014-08-13 | 1st | IX | LF | 45.5821 | 174 | 2014-02-24 | 2014-08-16 | 0 | O | 0.293 | 0.3 | 0.15 | 0.03 | 0.055 | 0.05 | 87.8
Zota Trading & Construction | 32641 | L | D | SB | GE2 | Upgrading of Lateral Drainage along Urdaneta Jct.-Dagupan-Lingayen Rd. (via Zambales) Tapuac Sect. | Dagupan City | 2013-03-16 | 1st | I | LF | 3.68 | 155 | 2012-11-09 | 2013-04-12 | -42.58 | O | 0.378 | 0.3 | 0 | 0.03 | 0.023 | 0 | 73.1 | -
Formulas:
COMP = [DATE]+[DUR (C.D.)]-1
Note on A3323: PC1: No 1st and 2nd visit
Note on G5592: PC1: name